## Sheet2
Max of plannedStartDate | Column Labels
Row Labels | Electrical 1st Fixes | Façade Works | FPS 1st Fix - MEP & Finishes | RCC Works - Slab | RCC Works - Vertical
B1 | 2027-02-23 |  | 2027-02-23 | 2026-07-28 | 2026-07-07
B2 | 2027-03-03 |  | 2027-03-03 | 2026-05-27 | 2026-04-29
B3 | 2027-03-11 |  | 2027-03-11 | 2026-03-21 | 2026-02-25
GF | 2027-02-15 | 2028-03-25 | 2027-02-15 | 2026-09-18 | 2026-08-18
L10 | 2027-01-19 |  | 2027-01-19 | 2026-01-29 | 2026-01-21
L11 | 2027-02-01 |  | 2027-02-01 | 2026-02-13 | 2026-02-06
L12 | 2027-02-12 |  | 2027-02-12 | 2026-02-28 | 2026-02-21
L13 | 2027-02-24 | 2026-10-19 | 2027-02-24 | 2026-03-17 | 2026-03-10
L14 | 2027-03-08 |  | 2027-03-08 | 2026-04-01 | 2026-03-25
L15 | 2027-03-19 | 2028-02-29 | 2027-03-19 | 2026-04-16 | 2026-04-09
L16 | 2027-04-01 |  | 2027-04-01 | 2026-05-02 | 2026-04-24
L17 | 2027-04-13 |  | 2027-04-13 | 2026-05-18 | 2026-05-11
L18 | 2027-04-24 | 2026-12-11 | 2027-04-24 | 2026-06-03 | 2026-05-26
L19 | 2027-05-07 |  | 2027-05-07 | 2026-06-18 | 2026-06-11
L20 | 2027-05-20 |  | 2027-05-20 | 2026-07-03 | 2026-06-26
L21 | 2027-06-01 |  | 2027-06-01 | 2026-07-21 | 2026-07-11
L22 | 2027-06-12 |  | 2027-06-12 | 2026-08-07 | 2026-07-30
L23 | 2027-06-24 | 2027-02-04 | 2027-06-24 | 2026-08-26 | 2026-08-19
L24 | 2027-07-06 |  | 2027-07-06 | 2026-09-10 | 2026-09-03
L25 | 2027-07-17 | 2028-03-30 | 2027-07-17 | 2026-09-28 | 2026-09-21
L26 | 2027-07-29 |  | 2027-07-29 | 2026-10-14 | 2026-10-07
L27 | 2027-08-10 |  | 2027-08-10 | 2026-10-30 | 2026-10-23
L28 | 2027-08-21 | 2027-03-30 | 2027-08-21 | 2026-11-12 | 2026-11-07
L29 | 2027-09-02 |  | 2027-09-02 | 2026-11-24 | 2026-11-19
L30 | 2027-09-15 |  | 2027-09-15 | 2026-12-05 | 2026-12-01
L31 | 2027-09-28 |  | 2027-09-28 | 2026-12-17 | 2026-12-12
L32 | 2027-10-12 |  | 2027-10-12 | 2026-12-30 | 2026-12-24
L33 | 2027-10-23 | 2027-06-04 | 2027-10-23 | 2027-01-11 | 2027-01-06
L34 | 2027-11-05 |  | 2027-11-05 | 2027-01-22 | 2027-01-18
L35 | 2027-11-17 | 2028-04-28 | 2027-11-17 | 2027-02-04 | 2027-01-30
L36 | 2027-11-29 |  | 2027-11-29 | 2027-02-16 | 2027-02-11
L37 | 2027-12-10 |  | 2027-12-10 | 2027-02-27 | 2027-02-23
L38 | 2027-12-22 | 2027-08-25 | 2027-12-22 | 2027-03-11 | 2027-03-06
L39 | 2028-01-04 |  | 2028-01-04 | 2027-03-24 | 2027-03-18
L40 | 2028-01-15 |  | 2028-01-15 | 2027-04-05 | 2027-03-31
L41 | 2028-01-28 |  | 2028-01-28 | 2027-04-16 | 2027-04-12
L42 | 2028-02-09 |  | 2028-02-09 | 2027-04-28 | 2027-04-23
L43 | 2028-02-21 | 2026-01-23 | 2028-02-21 | 2027-05-11 | 2027-05-06
L44 | 2028-03-03 |  | 2028-03-03 | 2027-05-24 | 2027-05-19
L45 | 2026-05-09 | 2026-08-26 | 2026-05-09 | 2025-02-06 | 2025-02-04
L46 | 2026-05-15 |  | 2026-05-15 | 2025-02-15 | 2025-02-13
L47 | 2026-05-21 |  | 2026-05-21 | 2025-02-25 | 2025-02-22
L48 | 2026-05-28 | 2026-02-17 | 2026-05-28 | 2025-03-04 | 2025-03-01
L49 | 2026-06-03 |  | 2026-06-03 | 2025-03-21 | 2025-03-15
L50 | 2026-06-09 |  | 2026-06-09 | 2025-04-03 | 2025-04-01
L51 | 2026-06-15 |  | 2026-06-15 | 2025-04-30 | 2025-04-28
L52 | 2026-06-20 |  | 2026-06-20 | 2025-05-09 | 2025-05-07
L53 | 2026-06-26 | 2026-03-07 | 2026-06-26 | 2025-05-17 | 2025-05-15
L54 | 2026-07-02 |  | 2026-07-02 | 2025-05-26 | 2025-05-23
L55 | 2026-07-08 | 2026-09-03 | 2026-07-08 | 2025-06-03 | 2025-05-31
L56 | 2026-07-15 |  | 2026-07-15 | 2025-06-12 | 2025-06-10
L57 | 2026-07-22 |  | 2026-07-22 | 2025-06-20 | 2025-06-18
L58 | 2026-07-29 | 2026-03-25 | 2026-07-29 | 2025-06-28 | 2025-06-26
L59 | 2026-08-05 |  | 2026-08-05 | 2025-07-05 | 2025-07-04
L60 | 2026-08-12 |  | 2026-08-12 | 2025-07-18 | 2025-07-11
L61 | 2026-08-20 |  | 2026-08-20 | 2025-08-02 | 2025-07-31
L62 | 2026-08-26 |  | 2026-08-26 | 2025-08-21 | 2025-08-12
L63 | 2026-09-01 | 2026-04-11 | 2026-09-01 | 2025-09-12 | 2025-09-02
L64 | 2026-09-07 |  | 2026-09-07 | 2025-09-20 | 2025-09-19
L65 | 2026-09-14 | 2026-09-12 | 2026-09-14 | 2025-10-04 | 2025-09-26
L66 | 2026-09-23 |  | 2026-09-23 | 2025-10-22 | 2025-10-15
L67 | 2026-09-30 |  | 2026-09-30 | 2025-11-06 | 2025-11-03
L68 | 2026-10-07 | 2026-04-29 | 2026-10-07 | 2025-11-18 | 2025-11-14
L69 | 2026-10-13 |  | 2026-10-13 | 2025-11-27 | 2025-11-26
L7 | 2026-12-14 | 2028-01-31 | 2026-12-14 | 2025-12-12 | 2025-12-05
L70 | 2026-10-19 |  | 2026-10-19 | 2025-12-04 | 2025-12-03
L71 | 2026-10-26 |  | 2026-10-26 | 2025-12-11 | 2025-12-10
L72 | 2026-10-31 |  | 2026-10-31 | 2025-12-18 | 2025-12-17
L73 | 2026-11-06 | 2026-05-18 | 2026-11-06 | 2025-12-29 | 2025-12-24
L74 | 2026-11-12 |  | 2026-11-12 | 2026-01-09 | 2026-01-06
L75 | 2026-11-18 |  | 2026-11-18 | 2026-01-21 | 2026-01-17
L76 | 2026-11-24 |  | 2026-11-24 | 2026-02-03 | 2026-01-30
L77 | 2026-11-30 |  | 2026-11-30 | 2026-02-17 | 2026-02-11
L8 | 2026-12-26 |  | 2026-12-26 | 2025-12-29 | 2025-12-20
L9 | 2027-01-07 |  | 2027-01-07 | 2026-01-13 | 2026-01-06
(blank) | 2027-02-06 | 2028-01-19 | 2027-02-06 | 2027-09-03 | 2027-08-23

## Sheet1
taskId | location | status | trade | baselineStartDate | baselineEndDate | taskName | totalQuantity | actualQuantity | quantityUnits | plannedStartDate | actualStartDate | plannedEndDate | actualEndDate | Tower | Structrue | Floor | Category | Sub-Category
39116 |  | Started |  | 2021-04-01 | 2028-09-28 | Birla, Century Mills Worli_Auto-schedule (11.09.2025)[VL] | 100 | 38 |  | 2021-04-01 | 2021-04-01 | 2028-09-28 | [6 empty] | Sub-Category
39278 |  | Started |  | 2021-04-01 | 2026-12-30 | Tower A | 100 | 48 |  | 2021-04-01 | 2021-04-01 | 2027-06-28 | [6 empty] | Lift Pit RCC Works
44671 |  | Started |  | 2021-04-01 | 2026-05-18 | AWARD OF PACKAGES | 100 | 75 |  | 2021-04-01 | 2021-04-01 | 2026-01-28 | [6 empty] | Raft RCC Works
44683 |  | Complete |  | 2021-04-01 | 2022-07-30 | RCC | 100 | 100 |  | 2021-04-01 | 2021-04-01 | 2022-07-30 | 2022-07-30 | [5 empty] | Retaining Wall RCC Works
44683 |  | Complete |  | 2021-04-01 | 2022-07-30 | RCC | 100 | 100 |  | 2021-04-01 | 2021-04-01 | 2022-07-30 | 2022-07-30 | [5 empty] | RCC Works - Vertical
44684 | Tower A | Complete | Award of Packages | 2021-04-01 | 2021-04-19 | Vendor Pre-Qualification | 100 | 100 |  | 2021-04-01 | 2021-04-01 | 2021-04-19 | 2021-04-19 | Tower A | -- |  |  |  | Core Wall RCC Works
39117 |  | Complete |  | 2021-05-31 | 2028-09-27 | MILESTONES | 100 | 100 |  | 2021-05-31 | 2021-05-31 | 2028-09-28 | 2023-06-16 | [5 empty] | RCC Works - Slab
39121 |  | Quality checked |  | 2021-05-31 | 2021-05-31 | Pre-Construction Report by Turner | 100 | 100 |  | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-05-31 | [5 empty] | Foundation RCC Works
44685 | Tower A | Complete | Award of Packages | 2021-09-24 | 2021-11-29 | Issue of Tender to Vendors | 100 | 100 |  | 2021-09-24 | 2021-09-24 | 2021-11-29 | 2021-11-29 | Tower A | -- |  |  |  | Gypsum Plastering Works
39129 |  | Complete |  | 2021-10-05 | 2024-08-31 | MOBILIZATION | 100 | 100 |  | 2021-10-05 | 2021-10-05 | 2024-08-31 | 2024-08-31 | [5 empty] | Staircase & Ramp RCC Works
39130 |  | Complete |  | 2021-10-05 | 2021-10-18 | Piling & Earthwork Contractor | 100 | 100 |  | 2021-10-05 | 2021-10-05 | 2021-10-18 | 2021-10-18 | [5 empty] | FPS 1st Fix - MEP & Finishes
47964 |  | Started |  | 2021-11-15 | 2025-04-28 | DEMOLITION OF EXISTING BASEMENT_ZONE 1A-1B-1C | 100 | 94 |  | 2021-11-15 | 2021-11-15 | 2025-11-20 | [6 empty] | Ceiling Painting/ PT Marking
48024 |  | Complete |  | 2021-11-15 | 2022-04-29 | Statutory Permissions | 100 | 100 |  | 2021-11-15 | 2021-11-15 | 2022-04-29 | 2022-04-29 | [5 empty] | Electrical 1st Fixes
48025 |  | Complete |  | 2021-11-15 | 2021-11-15 | Tree Transplantation | 100 | 100 |  | 2021-11-15 | 2021-11-15 | 2021-11-15 | 2021-11-15 | [5 empty] | Blockwork
48012 |  | Complete |  | 2021-11-16 | 2022-01-12 | Consultant Appointment | 100 | 100 |  | 2021-11-16 | 2021-11-16 | 2022-01-12 | 2022-01-12 | [5 empty] | Painting Works
48015 |  | Complete |  | 2021-11-16 | 2021-11-24 | Liasioning Consultant | 100 | 100 |  | 2021-11-16 | 2021-11-16 | 2021-11-24 | 2021-11-24 | [5 empty] | Façade Works
44686 | Tower A | Complete | Award of Packages | 2021-11-30 | 2022-01-15 | Pre-bid Meetings | 100 | 100 |  | 2021-11-30 | 2021-11-30 | 2022-01-15 | 2022-01-15 | Tower A | -- |  |  |  | Flooring & Dado
48013 |  | Complete |  | 2021-12-01 | 2021-12-01 | MEP Consultant | 100 | 100 |  | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2021-12-01 | [5 empty] | HVAC Ducting
48014 |  | Complete |  | 2021-12-01 | 2021-12-01 | Structural Consultant | 100 | 100 |  | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2021-12-01 | [5 empty] | HVAC Grill Fixing
48016 |  | Complete |  | 2021-12-01 | 2022-01-12 | Revised Car Parking Design | 100 | 100 |  | 2021-12-01 | 2021-12-01 | 2022-01-12 | 2022-01-12 | [5 empty] | False Ceiling
48030 |  | Complete |  | 2021-12-01 | 2022-03-17 | Design & Drawing | 100 | 100 |  | 2021-12-01 | 2021-12-01 | 2022-03-17 | 2022-03-17 | [5 empty] | FPS 2nd Fix - MEP & Finishes
48031 |  | Complete |  | 2021-12-01 | 2022-03-17 | MEP Design_Tender | 100 | 100 |  | 2021-12-01 | 2021-12-01 | 2022-03-17 | 2022-03-17 | [5 empty] | Electrical 2nd Fix - MEP & Finishes
48032 |  | Complete |  | 2021-12-01 | 2022-03-17 | Civil Drawing | 100 | 100 |  | 2021-12-01 | 2021-12-01 | 2022-03-17 | 2022-03-17 | [5 empty] | Door & Window Frame work
48033 |  | Complete |  | 2021-12-01 | 2022-03-17 | Statutory Drawings | 100 | 100 |  | 2021-12-01 | 2021-12-01 | 2022-03-17 | 2022-03-17 | [5 empty] | Lobby Plastering
48034 |  | Complete |  | 2021-12-01 | 2022-03-17 | Demolition Drawings | 100 | 100 |  | 2021-12-01 | 2021-12-01 | 2022-03-17 | 2022-03-17 | [5 empty] | Final Painting
39279 |  | Started |  | 2021-12-14 | 2026-12-30 | CONSTRUCTION_TOWER A_ZONE 1 | 100 | 37 |  | 2021-12-14 | 2021-12-14 | 2027-06-28 | [6 empty] | Electrical
43913 |  | Complete |  | 2021-12-14 | 2022-04-08 | Piling, Rock Anchoring & Excavation (Zone 1&2) | 100 | 100 |  | 2021-12-14 | 2021-12-14 | 2022-04-08 | 2022-04-08 | [5 empty] | Staircase Flooring
43914 |  | Complete |  | 2021-12-14 | 2022-03-07 | Piling Works | 100 | 100 |  | 2021-12-14 | 2021-12-14 | 2022-03-07 | 2022-03-07 | [5 empty] | FPS final fixes
43915 | Tower A - Excavation - Zone 2A | Complete | Piling Works | 2021-12-14 | 2021-12-30 | Zone 2A | 100 | 100 |  | 2021-12-14 | 2021-12-14 | 2021-12-30 | 2021-12-30 | Tower A | Excavation |  |  |  | Door & Window Fixing
43915 | Tower A - Excavation - Zone 2A | Complete | Piling Works | 2021-12-14 | 2021-12-30 | Zone 2A | 100 | 100 |  | 2021-12-14 | 2021-12-14 | 2021-12-30 | 2021-12-30 | Tower A | Excavation |  |  |  | Plumbing
43915 | Tower A - Excavation - Zone 2A | Complete | Piling Works | 2021-12-14 | 2021-12-30 | Zone 2A | 100 | 100 |  | 2021-12-14 | 2021-12-14 | 2021-12-30 | 2021-12-30 | Tower A | Excavation
43915 | Tower A - Excavation - Zone 2A | Complete | Piling Works | 2021-12-14 | 2021-12-30 | Zone 2A | 100 | 100 |  | 2021-12-14 | 2021-12-14 | 2021-12-30 | 2021-12-30 | Tower A | Excavation
43915 | Tower A - Excavation - Zone 2A | Complete | Piling Works | 2021-12-14 | 2021-12-30 | Zone 2A | 100 | 100 |  | 2021-12-14 | 2021-12-14 | 2021-12-30 | 2021-12-30 | Tower A | Excavation
43915 | Tower A - Excavation - Zone 2A | Complete | Piling Works | 2021-12-14 | 2021-12-30 | Zone 2A | 100 | 100 |  | 2021-12-14 | 2021-12-14 | 2021-12-30 | 2021-12-30 | Tower A | Excavation
43916 | Tower A - Excavation - Zone 2 | Complete | Piling Works | 2021-12-31 | 2022-01-11 | Zone 2 | 100 | 100 |  | 2021-12-31 | 2021-12-31 | 2022-01-11 | 2022-01-11 | Tower A | Excavation
43916 | Tower A - Excavation - Zone 2 | Complete | Piling Works | 2021-12-31 | 2022-01-11 | Zone 2 | 100 | 100 |  | 2021-12-31 | 2021-12-31 | 2022-01-11 | 2022-01-11 | Tower A | Excavation
43916 | Tower A - Excavation - Zone 2 | Complete | Piling Works | 2021-12-31 | 2022-01-11 | Zone 2 | 100 | 100 |  | 2021-12-31 | 2021-12-31 | 2022-01-11 | 2022-01-11 | Tower A | Excavation
43916 | Tower A - Excavation - Zone 2 | Complete | Piling Works | 2021-12-31 | 2022-01-11 | Zone 2 | 100 | 100 |  | 2021-12-31 | 2021-12-31 | 2022-01-11 | 2022-01-11 | Tower A | Excavation
43916 | Tower A - Excavation - Zone 2 | Complete | Piling Works | 2021-12-31 | 2022-01-11 | Zone 2 | 100 | 100 |  | 2021-12-31 | 2021-12-31 | 2022-01-11 | 2022-01-11 | Tower A | Excavation
43916 | Tower A - Excavation - Zone 2 | Complete | Piling Works | 2021-12-31 | 2022-01-11 | Zone 2 | 100 | 100 |  | 2021-12-31 | 2021-12-31 | 2022-01-11 | 2022-01-11 | Tower A | Excavation
43917 | Tower A - Excavation - Zone 1A | Complete | Piling Works | 2021-12-31 | 2022-01-19 | Zone 1A | 100 | 100 |  | 2021-12-31 | 2021-12-31 | 2022-01-19 | 2022-01-19 | Tower A | Excavation
43917 | Tower A - Excavation - Zone 1A | Complete | Piling Works | 2021-12-31 | 2022-01-19 | Zone 1A | 100 | 100 |  | 2021-12-31 | 2021-12-31 | 2022-01-19 | 2022-01-19 | Tower A | Excavation
43917 | Tower A - Excavation - Zone 1A | Complete | Piling Works | 2021-12-31 | 2022-01-19 | Zone 1A | 100 | 100 |  | 2021-12-31 | 2021-12-31 | 2022-01-19 | 2022-01-19 | Tower A | Excavation
43917 | Tower A - Excavation - Zone 1A | Complete | Piling Works | 2021-12-31 | 2022-01-19 | Zone 1A | 100 | 100 |  | 2021-12-31 | 2021-12-31 | 2022-01-19 | 2022-01-19 | Tower A | Excavation
43917 | Tower A - Excavation - Zone 1A | Complete | Piling Works | 2021-12-31 | 2022-01-19 | Zone 1A | 100 | 100 |  | 2021-12-31 | 2021-12-31 | 2022-01-19 | 2022-01-19 | Tower A | Excavation
43917 | Tower A - Excavation - Zone 1A | Complete | Piling Works | 2021-12-31 | 2022-01-19 | Zone 1A | 100 | 100 |  | 2021-12-31 | 2021-12-31 | 2022-01-19 | 2022-01-19 | Tower A | Excavation
43921 |  | Complete |  | 2021-12-31 | 2022-04-08 | Pile Capping Beam | 100 | 100 |  | 2021-12-31 | 2021-12-31 | 2022-04-08 | 2022-04-08
43922 |  | Complete |  | 2021-12-31 | 2022-01-31 | Zone 2A | 100 | 100 |  | 2021-12-31 | 2021-12-31 | 2022-01-31 | 2022-01-31
43922 |  | Complete |  | 2021-12-31 | 2022-01-31 | Zone 2A | 100 | 100 |  | 2021-12-31 | 2021-12-31 | 2022-01-31 | 2022-01-31
43922 |  | Complete |  | 2021-12-31 | 2022-01-31 | Zone 2A | 100 | 100 |  | 2021-12-31 | 2021-12-31 | 2022-01-31 | 2022-01-31
43922 |  | Complete |  | 2021-12-31 | 2022-01-31 | Zone 2A | 100 | 100 |  | 2021-12-31 | 2021-12-31 | 2022-01-31 | 2022-01-31
43922 |  | Complete |  | 2021-12-31 | 2022-01-31 | Zone 2A | 100 | 100 |  | 2021-12-31 | 2021-12-31 | 2022-01-31 | 2022-01-31
43922 |  | Complete |  | 2021-12-31 | 2022-01-31 | Zone 2A | 100 | 100 |  | 2021-12-31 | 2021-12-31 | 2022-01-31 | 2022-01-31
43923 | Tower A - Excavation - Zone 2A | Complete | Pile Caping Beam | 2021-12-31 | 2022-01-15 | Pile chipping | 100 | 100 |  | 2021-12-31 | 2021-12-31 | 2022-01-15 | 2022-01-15 | Tower A | Excavation
48029 |  | Complete |  | 2022-01-13 | 2022-02-11 | Revised Car Parking | 100 | 100 |  | 2022-01-13 | 2022-01-13 | 2022-02-11 | 2022-02-11
43918 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Piling Works | 2022-01-14 | 2022-02-04 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-01-14 | 2022-01-14 | 2022-02-04 | 2022-02-04 | Tower A | Excavation
43918 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Piling Works | 2022-01-14 | 2022-02-04 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-01-14 | 2022-01-14 | 2022-02-04 | 2022-02-04 | Tower A | Excavation
43918 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Piling Works | 2022-01-14 | 2022-02-04 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-01-14 | 2022-01-14 | 2022-02-04 | 2022-02-04 | Tower A | Excavation
43918 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Piling Works | 2022-01-14 | 2022-02-04 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-01-14 | 2022-01-14 | 2022-02-04 | 2022-02-04 | Tower A | Excavation
43918 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Piling Works | 2022-01-14 | 2022-02-04 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-01-14 | 2022-01-14 | 2022-02-04 | 2022-02-04 | Tower A | Excavation
43918 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Piling Works | 2022-01-14 | 2022-02-04 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-01-14 | 2022-01-14 | 2022-02-04 | 2022-02-04 | Tower A | Excavation
43924 | Tower A - Excavation - Zone 2A | Complete | Pile Caping Beam | 2022-01-17 | 2022-01-21 | Reinf. Fixing | 100 | 100 |  | 2022-01-17 | 2022-01-17 | 2022-01-21 | 2022-01-21 | Tower A | Excavation
43927 |  | Complete |  | 2022-01-17 | 2022-02-16 | Zone 2 | 100 | 100 |  | 2022-01-17 | 2022-01-17 | 2022-02-16 | 2022-02-16
43927 |  | Complete |  | 2022-01-17 | 2022-02-16 | Zone 2 | 100 | 100 |  | 2022-01-17 | 2022-01-17 | 2022-02-16 | 2022-02-16
43927 |  | Complete |  | 2022-01-17 | 2022-02-16 | Zone 2 | 100 | 100 |  | 2022-01-17 | 2022-01-17 | 2022-02-16 | 2022-02-16
43927 |  | Complete |  | 2022-01-17 | 2022-02-16 | Zone 2 | 100 | 100 |  | 2022-01-17 | 2022-01-17 | 2022-02-16 | 2022-02-16
43927 |  | Complete |  | 2022-01-17 | 2022-02-16 | Zone 2 | 100 | 100 |  | 2022-01-17 | 2022-01-17 | 2022-02-16 | 2022-02-16
43927 |  | Complete |  | 2022-01-17 | 2022-02-16 | Zone 2 | 100 | 100 |  | 2022-01-17 | 2022-01-17 | 2022-02-16 | 2022-02-16
43928 | Tower A - Excavation - Zone 2 | Complete | Pile Caping Beam | 2022-01-17 | 2022-02-02 | Pile chipping | 100 | 100 |  | 2022-01-17 | 2022-01-17 | 2022-02-02 | 2022-02-02 | Tower A | Excavation
44687 | Tower A | Complete | Award of Packages | 2022-01-17 | 2022-01-17 | Receipt of Tender Bids | 100 | 100 |  | 2022-01-17 | 2022-01-17 | 2022-01-17 | 2022-01-17 | Tower A | --
44688 | Tower A | Complete | Award of Packages | 2022-01-18 | 2022-02-16 | Negotiation meetings - 3 Rounds | 100 | 100 |  | 2022-01-18 | 2022-01-18 | 2022-02-16 | 2022-02-16 | Tower A | --
43932 |  | Complete |  | 2022-01-20 | 2022-03-03 | Zone 1A | 100 | 100 |  | 2022-01-20 | 2022-01-20 | 2022-03-03 | 2022-03-03
43932 |  | Complete |  | 2022-01-20 | 2022-03-03 | Zone 1A | 100 | 100 |  | 2022-01-20 | 2022-01-20 | 2022-03-03 | 2022-03-03
43932 |  | Complete |  | 2022-01-20 | 2022-03-03 | Zone 1A | 100 | 100 |  | 2022-01-20 | 2022-01-20 | 2022-03-03 | 2022-03-03
43932 |  | Complete |  | 2022-01-20 | 2022-03-03 | Zone 1A | 100 | 100 |  | 2022-01-20 | 2022-01-20 | 2022-03-03 | 2022-03-03
43932 |  | Complete |  | 2022-01-20 | 2022-03-03 | Zone 1A | 100 | 100 |  | 2022-01-20 | 2022-01-20 | 2022-03-03 | 2022-03-03
43932 |  | Complete |  | 2022-01-20 | 2022-03-03 | Zone 1A | 100 | 100 |  | 2022-01-20 | 2022-01-20 | 2022-03-03 | 2022-03-03
43933 | Tower A - Excavation - Zone 1A | Complete | Pile Caping Beam | 2022-01-20 | 2022-02-11 | Pile chipping | 100 | 100 |  | 2022-01-20 | 2022-01-20 | 2022-02-11 | 2022-02-11 | Tower A | Excavation
43925 | Tower A - Excavation - Zone 2A | Complete | Pile Caping Beam | 2022-01-22 | 2022-01-25 | Fwk Fixing | 100 | 100 |  | 2022-01-22 | 2022-01-22 | 2022-01-25 | 2022-01-25 | Tower A | Excavation
43926 | Tower A - Excavation - Zone 2A | Complete | Pile Caping Beam | 2022-01-27 | 2022-01-31 | Casting & de-shuttering | 100 | 100 |  | 2022-01-27 | 2022-01-27 | 2022-01-31 | 2022-01-31 | Tower A | Excavation
40561 |  | Complete |  | 2022-02-01 | 2022-08-25 | Excavation in TA Area (excl. Piling bay) | 100 | 100 |  | 2022-02-01 | 2022-02-01 | 2022-08-25 | 2022-08-25
40562 |  | Complete |  | 2022-02-01 | 2022-03-23 | Excavation up to -4.00 m | 100 | 100 |  | 2022-02-01 | 2022-02-01 | 2022-03-23 | 2022-03-23
40563 | Tower A - Excavation - Zone 2A | Complete | Excavation upto -4 Mtr | 2022-02-01 | 2022-02-02 | Zone 2A | 100 | 100 |  | 2022-02-01 | 2022-02-01 | 2022-02-02 | 2022-02-02 | Tower A | Excavation
40563 | Tower A - Excavation - Zone 2A | Complete | Excavation upto -4 Mtr | 2022-02-01 | 2022-02-02 | Zone 2A | 100 | 100 |  | 2022-02-01 | 2022-02-01 | 2022-02-02 | 2022-02-02 | Tower A | Excavation
40563 | Tower A - Excavation - Zone 2A | Complete | Excavation upto -4 Mtr | 2022-02-01 | 2022-02-02 | Zone 2A | 100 | 100 |  | 2022-02-01 | 2022-02-01 | 2022-02-02 | 2022-02-02 | Tower A | Excavation
40563 | Tower A - Excavation - Zone 2A | Complete | Excavation upto -4 Mtr | 2022-02-01 | 2022-02-02 | Zone 2A | 100 | 100 |  | 2022-02-01 | 2022-02-01 | 2022-02-02 | 2022-02-02 | Tower A | Excavation
40563 | Tower A - Excavation - Zone 2A | Complete | Excavation upto -4 Mtr | 2022-02-01 | 2022-02-02 | Zone 2A | 100 | 100 |  | 2022-02-01 | 2022-02-01 | 2022-02-02 | 2022-02-02 | Tower A | Excavation
40563 | Tower A - Excavation - Zone 2A | Complete | Excavation upto -4 Mtr | 2022-02-01 | 2022-02-02 | Zone 2A | 100 | 100 |  | 2022-02-01 | 2022-02-01 | 2022-02-02 | 2022-02-02 | Tower A | Excavation
40567 |  | Complete |  | 2022-02-03 | 2022-04-15 | Rock Anchoring - layer 1 | 100 | 100 |  | 2022-02-03 | 2022-02-03 | 2022-04-15 | 2022-04-15
40568 | Tower A - Excavation - Zone 2A | Complete | Rock Anchoring | 2022-02-03 | 2022-02-10 | Zone 2A | 100 | 100 |  | 2022-02-03 | 2022-02-03 | 2022-02-10 | 2022-02-10 | Tower A | Excavation
40568 | Tower A - Excavation - Zone 2A | Complete | Rock Anchoring | 2022-02-03 | 2022-02-10 | Zone 2A | 100 | 100 |  | 2022-02-03 | 2022-02-03 | 2022-02-10 | 2022-02-10 | Tower A | Excavation
40568 | Tower A - Excavation - Zone 2A | Complete | Rock Anchoring | 2022-02-03 | 2022-02-10 | Zone 2A | 100 | 100 |  | 2022-02-03 | 2022-02-03 | 2022-02-10 | 2022-02-10 | Tower A | Excavation
40568 | Tower A - Excavation - Zone 2A | Complete | Rock Anchoring | 2022-02-03 | 2022-02-10 | Zone 2A | 100 | 100 |  | 2022-02-03 | 2022-02-03 | 2022-02-10 | 2022-02-10 | Tower A | Excavation
40568 | Tower A - Excavation - Zone 2A | Complete | Rock Anchoring | 2022-02-03 | 2022-02-10 | Zone 2A | 100 | 100 |  | 2022-02-03 | 2022-02-03 | 2022-02-10 | 2022-02-10 | Tower A | Excavation
40568 | Tower A - Excavation - Zone 2A | Complete | Rock Anchoring | 2022-02-03 | 2022-02-10 | Zone 2A | 100 | 100 |  | 2022-02-03 | 2022-02-03 | 2022-02-10 | 2022-02-10 | Tower A | Excavation
43929 | Tower A - Excavation - Zone 2 | Complete | Pile Caping Beam | 2022-02-03 | 2022-02-08 | Reinf. Fixing | 100 | 100 |  | 2022-02-03 | 2022-02-03 | 2022-02-08 | 2022-02-08 | Tower A | Excavation
43919 | Tower A - Excavation - Zone 1 South (upto NTA Zone 2) | Complete | Piling Works | 2022-02-05 | 2022-02-16 | Zone 1 South (outside Tower A area) | 100 | 100 |  | 2022-02-05 | 2022-02-05 | 2022-02-16 | 2022-02-16 | Tower A | Excavation
43919 | Tower A - Excavation - Zone 1 South (upto NTA Zone 2) | Complete | Piling Works | 2022-02-05 | 2022-02-16 | Zone 1 South (outside Tower A area) | 100 | 100 |  | 2022-02-05 | 2022-02-05 | 2022-02-16 | 2022-02-16 | Tower A | Excavation
43937 |  | Complete |  | 2022-02-05 | 2022-03-21 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-02-05 | 2022-02-05 | 2022-03-21 | 2022-03-21
43937 |  | Complete |  | 2022-02-05 | 2022-03-21 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-02-05 | 2022-02-05 | 2022-03-21 | 2022-03-21
43937 |  | Complete |  | 2022-02-05 | 2022-03-21 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-02-05 | 2022-02-05 | 2022-03-21 | 2022-03-21
43937 |  | Complete |  | 2022-02-05 | 2022-03-21 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-02-05 | 2022-02-05 | 2022-03-21 | 2022-03-21
43937 |  | Complete |  | 2022-02-05 | 2022-03-21 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-02-05 | 2022-02-05 | 2022-03-21 | 2022-03-21
43937 |  | Complete |  | 2022-02-05 | 2022-03-21 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-02-05 | 2022-02-05 | 2022-03-21 | 2022-03-21
43938 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Pile Caping Beam | 2022-02-05 | 2022-03-05 | Pile chipping | 100 | 100 |  | 2022-02-05 | 2022-02-05 | 2022-03-05 | 2022-03-05 | Tower A | Excavation
43930 | Tower A - Excavation - Zone 2 | Complete | Pile Caping Beam | 2022-02-09 | 2022-02-11 | Fwk Fixing | 100 | 100 |  | 2022-02-09 | 2022-02-09 | 2022-02-11 | 2022-02-11 | Tower A | Excavation
40569 | Tower A - Excavation - Zone 2A | Complete | Rock Anchoring | 2022-02-11 | 2022-02-16 | waiting for grout strength & Stressing | 100 | 100 |  | 2022-02-11 | 2022-02-11 | 2022-02-16 | 2022-02-16 | Tower A | Excavation
43931 | Tower A - Excavation - Zone 2 | Complete | Pile Caping Beam | 2022-02-12 | 2022-02-16 | Casting & de-shuttering | 100 | 100 |  | 2022-02-12 | 2022-02-12 | 2022-02-16 | 2022-02-16 | Tower A | Excavation
43934 | Tower A - Excavation - Zone 1A | Complete | Pile Caping Beam | 2022-02-12 | 2022-02-19 | Reinf. Fixing | 100 | 100 |  | 2022-02-12 | 2022-02-12 | 2022-02-19 | 2022-02-19 | Tower A | Excavation
40564 | Tower A - Excavation - Zone 2 | Complete | Excavation upto -4 Mtr | 2022-02-17 | 2022-02-18 | Zone 2 | 100 | 100 |  | 2022-02-17 | 2022-02-17 | 2022-02-18 | 2022-02-18 | Tower A | Excavation
40564 | Tower A - Excavation - Zone 2 | Complete | Excavation upto -4 Mtr | 2022-02-17 | 2022-02-18 | Zone 2 | 100 | 100 |  | 2022-02-17 | 2022-02-17 | 2022-02-18 | 2022-02-18 | Tower A | Excavation
40564 | Tower A - Excavation - Zone 2 | Complete | Excavation upto -4 Mtr | 2022-02-17 | 2022-02-18 | Zone 2 | 100 | 100 |  | 2022-02-17 | 2022-02-17 | 2022-02-18 | 2022-02-18 | Tower A | Excavation
40564 | Tower A - Excavation - Zone 2 | Complete | Excavation upto -4 Mtr | 2022-02-17 | 2022-02-18 | Zone 2 | 100 | 100 |  | 2022-02-17 | 2022-02-17 | 2022-02-18 | 2022-02-18 | Tower A | Excavation
40564 | Tower A - Excavation - Zone 2 | Complete | Excavation upto -4 Mtr | 2022-02-17 | 2022-02-18 | Zone 2 | 100 | 100 |  | 2022-02-17 | 2022-02-17 | 2022-02-18 | 2022-02-18 | Tower A | Excavation
40564 | Tower A - Excavation - Zone 2 | Complete | Excavation upto -4 Mtr | 2022-02-17 | 2022-02-18 | Zone 2 | 100 | 100 |  | 2022-02-17 | 2022-02-17 | 2022-02-18 | 2022-02-18 | Tower A | Excavation
40576 |  | Complete |  | 2022-02-17 | 2022-04-18 | Excavation up to -8.00 m | 100 | 100 |  | 2022-02-17 | 2022-02-17 | 2022-04-18 | 2022-04-18
40577 | Tower A - Excavation - Zone 2A | Complete | Excavation upto -8 Mtr | 2022-02-17 | 2022-02-18 | Zone 2A | 100 | 100 |  | 2022-02-17 | 2022-02-17 | 2022-02-18 | 2022-02-18 | Tower A | Excavation
40577 | Tower A - Excavation - Zone 2A | Complete | Excavation upto -8 Mtr | 2022-02-17 | 2022-02-18 | Zone 2A | 100 | 100 |  | 2022-02-17 | 2022-02-17 | 2022-02-18 | 2022-02-18 | Tower A | Excavation
40577 | Tower A - Excavation - Zone 2A | Complete | Excavation upto -8 Mtr | 2022-02-17 | 2022-02-18 | Zone 2A | 100 | 100 |  | 2022-02-17 | 2022-02-17 | 2022-02-18 | 2022-02-18 | Tower A | Excavation
40577 | Tower A - Excavation - Zone 2A | Complete | Excavation upto -8 Mtr | 2022-02-17 | 2022-02-18 | Zone 2A | 100 | 100 |  | 2022-02-17 | 2022-02-17 | 2022-02-18 | 2022-02-18 | Tower A | Excavation
40577 | Tower A - Excavation - Zone 2A | Complete | Excavation upto -8 Mtr | 2022-02-17 | 2022-02-18 | Zone 2A | 100 | 100 |  | 2022-02-17 | 2022-02-17 | 2022-02-18 | 2022-02-18 | Tower A | Excavation
40577 | Tower A - Excavation - Zone 2A | Complete | Excavation upto -8 Mtr | 2022-02-17 | 2022-02-18 | Zone 2A | 100 | 100 |  | 2022-02-17 | 2022-02-17 | 2022-02-18 | 2022-02-18 | Tower A | Excavation
43920 | Tower A - Excavation - Zone 1 North (outside NTA Zone 2) | Complete | Piling Works | 2022-02-17 | 2022-03-07 | Zone 1 North (outside NTA Zone 2) up to hold area | 100 | 100 |  | 2022-02-17 | 2022-02-17 | 2022-03-07 | 2022-03-07 | Tower A | Excavation
43942 |  | Complete |  | 2022-02-17 | 2022-03-21 | Zone 1 South (outside Tower A area) | 100 | 100 |  | 2022-02-17 | 2022-02-17 | 2022-03-21 | 2022-03-21
43942 |  | Complete |  | 2022-02-17 | 2022-03-21 | Zone 1 South (outside Tower A area) | 100 | 100 |  | 2022-02-17 | 2022-02-17 | 2022-03-21 | 2022-03-21
43943 | Tower A - Excavation - Zone 1 South (upto NTA Zone 2) | Complete | Pile Caping Beam | 2022-02-17 | 2022-03-05 | Pile chipping | 100 | 100 |  | 2022-02-17 | 2022-02-17 | 2022-03-05 | 2022-03-05 | Tower A | Excavation
44689 | Tower A | Complete | Award of Packages | 2022-02-17 | 2022-02-24 | Final round of negotiation meeting with Sr. Management | 100 | 100 |  | 2022-02-17 | 2022-02-17 | 2022-02-24 | 2022-02-24 | Tower A | --
40570 | Tower A - Excavation - Zone 2 | Complete | Rock Anchoring | 2022-02-19 | 2022-03-01 | Zone 2 | 100 | 100 |  | 2022-02-19 | 2022-02-19 | 2022-03-01 | 2022-03-01 | Tower A | Excavation
40570 | Tower A - Excavation - Zone 2 | Complete | Rock Anchoring | 2022-02-19 | 2022-03-01 | Zone 2 | 100 | 100 |  | 2022-02-19 | 2022-02-19 | 2022-03-01 | 2022-03-01 | Tower A | Excavation
40570 | Tower A - Excavation - Zone 2 | Complete | Rock Anchoring | 2022-02-19 | 2022-03-01 | Zone 2 | 100 | 100 |  | 2022-02-19 | 2022-02-19 | 2022-03-01 | 2022-03-01 | Tower A | Excavation
40570 | Tower A - Excavation - Zone 2 | Complete | Rock Anchoring | 2022-02-19 | 2022-03-01 | Zone 2 | 100 | 100 |  | 2022-02-19 | 2022-02-19 | 2022-03-01 | 2022-03-01 | Tower A | Excavation
40570 | Tower A - Excavation - Zone 2 | Complete | Rock Anchoring | 2022-02-19 | 2022-03-01 | Zone 2 | 100 | 100 |  | 2022-02-19 | 2022-02-19 | 2022-03-01 | 2022-03-01 | Tower A | Excavation
40570 | Tower A - Excavation - Zone 2 | Complete | Rock Anchoring | 2022-02-19 | 2022-03-01 | Zone 2 | 100 | 100 |  | 2022-02-19 | 2022-02-19 | 2022-03-01 | 2022-03-01 | Tower A | Excavation
40581 |  | Complete |  | 2022-02-19 | 2022-03-04 | Rock Anchoring - layer 2 | 100 | 100 |  | 2022-02-19 | 2022-02-19 | 2022-03-04 | 2022-03-04
40582 | Tower A - Excavation - Zone 2A | Complete | Rock Anchoring | 2022-02-19 | 2022-02-26 | Zone 2A | 100 | 100 |  | 2022-02-19 | 2022-02-19 | 2022-02-26 | 2022-02-26 | Tower A | Excavation
40582 | Tower A - Excavation - Zone 2A | Complete | Rock Anchoring | 2022-02-19 | 2022-02-26 | Zone 2A | 100 | 100 |  | 2022-02-19 | 2022-02-19 | 2022-02-26 | 2022-02-26 | Tower A | Excavation
40582 | Tower A - Excavation - Zone 2A | Complete | Rock Anchoring | 2022-02-19 | 2022-02-26 | Zone 2A | 100 | 100 |  | 2022-02-19 | 2022-02-19 | 2022-02-26 | 2022-02-26 | Tower A | Excavation
40582 | Tower A - Excavation - Zone 2A | Complete | Rock Anchoring | 2022-02-19 | 2022-02-26 | Zone 2A | 100 | 100 |  | 2022-02-19 | 2022-02-19 | 2022-02-26 | 2022-02-26 | Tower A | Excavation
40582 | Tower A - Excavation - Zone 2A | Complete | Rock Anchoring | 2022-02-19 | 2022-02-26 | Zone 2A | 100 | 100 |  | 2022-02-19 | 2022-02-19 | 2022-02-26 | 2022-02-26 | Tower A | Excavation
40582 | Tower A - Excavation - Zone 2A | Complete | Rock Anchoring | 2022-02-19 | 2022-02-26 | Zone 2A | 100 | 100 |  | 2022-02-19 | 2022-02-19 | 2022-02-26 | 2022-02-26 | Tower A | Excavation
43935 | Tower A - Excavation - Zone 1A | Complete | Pile Caping Beam | 2022-02-21 | 2022-02-25 | Fwk Fixing | 100 | 100 |  | 2022-02-21 | 2022-02-21 | 2022-02-25 | 2022-02-25 | Tower A | Excavation
43936 | Tower A - Excavation - Zone 1A | Complete | Pile Caping Beam | 2022-02-26 | 2022-03-03 | Casting & de-shuttering | 100 | 100 |  | 2022-02-26 | 2022-02-26 | 2022-03-03 | 2022-03-03 | Tower A | Excavation
40583 | Tower A - Excavation - Zone 2A | Complete | Rock Anchoring | 2022-02-28 | 2022-03-04 | waiting for grout strength & Stressing | 100 | 100 |  | 2022-02-28 | 2022-02-28 | 2022-03-04 | 2022-03-04 | Tower A | Excavation
40571 | Tower A - Excavation - Zone 2 | Complete | Rock Anchoring | 2022-03-02 | 2022-03-07 | waiting for grout strength & Stressing | 100 | 100 |  | 2022-03-02 | 2022-03-02 | 2022-03-07 | 2022-03-07 | Tower A | Excavation
40565 | Tower A - Excavation - Zone 1A | Complete | Excavation upto -4 Mtr | 2022-03-04 | 2022-03-05 | Zone 1A | 100 | 100 |  | 2022-03-04 | 2022-03-04 | 2022-03-05 | 2022-03-05 | Tower A | Excavation
40565 | Tower A - Excavation - Zone 1A | Complete | Excavation upto -4 Mtr | 2022-03-04 | 2022-03-05 | Zone 1A | 100 | 100 |  | 2022-03-04 | 2022-03-04 | 2022-03-05 | 2022-03-05 | Tower A | Excavation
40565 | Tower A - Excavation - Zone 1A | Complete | Excavation upto -4 Mtr | 2022-03-04 | 2022-03-05 | Zone 1A | 100 | 100 |  | 2022-03-04 | 2022-03-04 | 2022-03-05 | 2022-03-05 | Tower A | Excavation
40565 | Tower A - Excavation - Zone 1A | Complete | Excavation upto -4 Mtr | 2022-03-04 | 2022-03-05 | Zone 1A | 100 | 100 |  | 2022-03-04 | 2022-03-04 | 2022-03-05 | 2022-03-05 | Tower A | Excavation
40565 | Tower A - Excavation - Zone 1A | Complete | Excavation upto -4 Mtr | 2022-03-04 | 2022-03-05 | Zone 1A | 100 | 100 |  | 2022-03-04 | 2022-03-04 | 2022-03-05 | 2022-03-05 | Tower A | Excavation
40565 | Tower A - Excavation - Zone 1A | Complete | Excavation upto -4 Mtr | 2022-03-04 | 2022-03-05 | Zone 1A | 100 | 100 |  | 2022-03-04 | 2022-03-04 | 2022-03-05 | 2022-03-05 | Tower A | Excavation
40584 |  | Complete |  | 2022-03-05 | 2022-08-25 | Excavation up to -14.00 m | 100 | 100 |  | 2022-03-05 | 2022-03-05 | 2022-08-25 | 2022-08-25
40585 | Tower A - Excavation - Zone 2A | Complete | Excavation upto -14 Mtr | 2022-03-05 | 2022-03-16 | Zone 2A | 100 | 100 |  | 2022-03-05 | 2022-03-05 | 2022-03-16 | 2022-03-16 | Tower A | Excavation
40585 | Tower A - Excavation - Zone 2A | Complete | Excavation upto -14 Mtr | 2022-03-05 | 2022-03-16 | Zone 2A | 100 | 100 |  | 2022-03-05 | 2022-03-05 | 2022-03-16 | 2022-03-16 | Tower A | Excavation
40585 | Tower A - Excavation - Zone 2A | Complete | Excavation upto -14 Mtr | 2022-03-05 | 2022-03-16 | Zone 2A | 100 | 100 |  | 2022-03-05 | 2022-03-05 | 2022-03-16 | 2022-03-16 | Tower A | Excavation
40585 | Tower A - Excavation - Zone 2A | Complete | Excavation upto -14 Mtr | 2022-03-05 | 2022-03-16 | Zone 2A | 100 | 100 |  | 2022-03-05 | 2022-03-05 | 2022-03-16 | 2022-03-16 | Tower A | Excavation
40585 | Tower A - Excavation - Zone 2A | Complete | Excavation upto -14 Mtr | 2022-03-05 | 2022-03-16 | Zone 2A | 100 | 100 |  | 2022-03-05 | 2022-03-05 | 2022-03-16 | 2022-03-16 | Tower A | Excavation
40585 | Tower A - Excavation - Zone 2A | Complete | Excavation upto -14 Mtr | 2022-03-05 | 2022-03-16 | Zone 2A | 100 | 100 |  | 2022-03-05 | 2022-03-05 | 2022-03-16 | 2022-03-16 | Tower A | Excavation
40572 | Tower A - Excavation - Zone 1A | Complete | Rock Anchoring | 2022-03-07 | 2022-03-22 | Zone 1A | 100 | 100 |  | 2022-03-07 | 2022-03-07 | 2022-03-22 | 2022-03-22 | Tower A | Excavation
40572 | Tower A - Excavation - Zone 1A | Complete | Rock Anchoring | 2022-03-07 | 2022-03-22 | Zone 1A | 100 | 100 |  | 2022-03-07 | 2022-03-07 | 2022-03-22 | 2022-03-22 | Tower A | Excavation
40572 | Tower A - Excavation - Zone 1A | Complete | Rock Anchoring | 2022-03-07 | 2022-03-22 | Zone 1A | 100 | 100 |  | 2022-03-07 | 2022-03-07 | 2022-03-22 | 2022-03-22 | Tower A | Excavation
40572 | Tower A - Excavation - Zone 1A | Complete | Rock Anchoring | 2022-03-07 | 2022-03-22 | Zone 1A | 100 | 100 |  | 2022-03-07 | 2022-03-07 | 2022-03-22 | 2022-03-22 | Tower A | Excavation
40572 | Tower A - Excavation - Zone 1A | Complete | Rock Anchoring | 2022-03-07 | 2022-03-22 | Zone 1A | 100 | 100 |  | 2022-03-07 | 2022-03-07 | 2022-03-22 | 2022-03-22 | Tower A | Excavation
40572 | Tower A - Excavation - Zone 1A | Complete | Rock Anchoring | 2022-03-07 | 2022-03-22 | Zone 1A | 100 | 100 |  | 2022-03-07 | 2022-03-07 | 2022-03-22 | 2022-03-22 | Tower A | Excavation
43939 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Pile Caping Beam | 2022-03-07 | 2022-03-11 | Reinf. Fixing | 100 | 100 |  | 2022-03-07 | 2022-03-07 | 2022-03-11 | 2022-03-11 | Tower A | Excavation
43944 | Tower A - Excavation - Zone 1 South (upto NTA Zone 2) | Complete | Pile Caping Beam | 2022-03-07 | 2022-03-11 | Reinf. Fixing | 100 | 100 |  | 2022-03-07 | 2022-03-07 | 2022-03-11 | 2022-03-11 | Tower A | Excavation
40578 | Tower A - Excavation - Zone 2 | Complete | Excavation upto -8 Mtr | 2022-03-08 | 2022-03-09 | Zone 2 | 100 | 100 |  | 2022-03-08 | 2022-03-08 | 2022-03-09 | 2022-03-09 | Tower A | Excavation
40578 | Tower A - Excavation - Zone 2 | Complete | Excavation upto -8 Mtr | 2022-03-08 | 2022-03-09 | Zone 2 | 100 | 100 |  | 2022-03-08 | 2022-03-08 | 2022-03-09 | 2022-03-09 | Tower A | Excavation
40578 | Tower A - Excavation - Zone 2 | Complete | Excavation upto -8 Mtr | 2022-03-08 | 2022-03-09 | Zone 2 | 100 | 100 |  | 2022-03-08 | 2022-03-08 | 2022-03-09 | 2022-03-09 | Tower A | Excavation
40578 | Tower A - Excavation - Zone 2 | Complete | Excavation upto -8 Mtr | 2022-03-08 | 2022-03-09 | Zone 2 | 100 | 100 |  | 2022-03-08 | 2022-03-08 | 2022-03-09 | 2022-03-09 | Tower A | Excavation
40578 | Tower A - Excavation - Zone 2 | Complete | Excavation upto -8 Mtr | 2022-03-08 | 2022-03-09 | Zone 2 | 100 | 100 |  | 2022-03-08 | 2022-03-08 | 2022-03-09 | 2022-03-09 | Tower A | Excavation
40578 | Tower A - Excavation - Zone 2 | Complete | Excavation upto -8 Mtr | 2022-03-08 | 2022-03-09 | Zone 2 | 100 | 100 |  | 2022-03-08 | 2022-03-08 | 2022-03-09 | 2022-03-09 | Tower A | Excavation
43947 |  | Complete |  | 2022-03-08 | 2022-04-08 | Zone 1 North (outside NTA Zone 2) | 100 | 100 |  | 2022-03-08 | 2022-03-08 | 2022-04-08 | 2022-04-08
43947 |  | Complete |  | 2022-03-08 | 2022-04-08 | Zone 1 North (outside NTA Zone 2) | 100 | 100 |  | 2022-03-08 | 2022-03-08 | 2022-04-08 | 2022-04-08
43947 |  | Complete |  | 2022-03-08 | 2022-04-08 | Zone 1 North (outside NTA Zone 2) | 100 | 100 |  | 2022-03-08 | 2022-03-08 | 2022-04-08 | 2022-04-08
43947 |  | Complete |  | 2022-03-08 | 2022-04-08 | Zone 1 North (outside NTA Zone 2) | 100 | 100 |  | 2022-03-08 | 2022-03-08 | 2022-04-08 | 2022-04-08
43948 | Tower A - Excavation - Zone 1 North (outside NTA Zone 2) | Complete | Pile Caping Beam | 2022-03-08 | 2022-03-25 | Pile chipping | 100 | 100 |  | 2022-03-08 | 2022-03-08 | 2022-03-25 | 2022-03-25 | Tower A | Excavation
40586 | Tower A - Excavation - Zone 2 | Complete | Excavation upto -14 Mtr | 2022-03-10 | 2022-03-22 | Zone 2 | 100 | 100 |  | 2022-03-10 | 2022-03-10 | 2022-03-22 | 2022-03-22 | Tower A | Excavation
40586 | Tower A - Excavation - Zone 2 | Complete | Excavation upto -14 Mtr | 2022-03-10 | 2022-03-22 | Zone 2 | 100 | 100 |  | 2022-03-10 | 2022-03-10 | 2022-03-22 | 2022-03-22 | Tower A | Excavation
40586 | Tower A - Excavation - Zone 2 | Complete | Excavation upto -14 Mtr | 2022-03-10 | 2022-03-22 | Zone 2 | 100 | 100 |  | 2022-03-10 | 2022-03-10 | 2022-03-22 | 2022-03-22 | Tower A | Excavation
40586 | Tower A - Excavation - Zone 2 | Complete | Excavation upto -14 Mtr | 2022-03-10 | 2022-03-22 | Zone 2 | 100 | 100 |  | 2022-03-10 | 2022-03-10 | 2022-03-22 | 2022-03-22 | Tower A | Excavation
40586 | Tower A - Excavation - Zone 2 | Complete | Excavation upto -14 Mtr | 2022-03-10 | 2022-03-22 | Zone 2 | 100 | 100 |  | 2022-03-10 | 2022-03-10 | 2022-03-22 | 2022-03-22 | Tower A | Excavation
40586 | Tower A - Excavation - Zone 2 | Complete | Excavation upto -14 Mtr | 2022-03-10 | 2022-03-22 | Zone 2 | 100 | 100 |  | 2022-03-10 | 2022-03-10 | 2022-03-22 | 2022-03-22 | Tower A | Excavation
43940 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Pile Caping Beam | 2022-03-12 | 2022-03-15 | Fwk Fixing | 100 | 100 |  | 2022-03-12 | 2022-03-12 | 2022-03-15 | 2022-03-15 | Tower A | Excavation
43945 | Tower A - Excavation - Zone 1 South (upto NTA Zone 2) | Complete | Pile Caping Beam | 2022-03-12 | 2022-03-15 | Fwk Fixing | 100 | 100 |  | 2022-03-12 | 2022-03-12 | 2022-03-15 | 2022-03-15 | Tower A | Excavation
43941 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Pile Caping Beam | 2022-03-16 | 2022-03-21 | Casting & de-shuttering | 100 | 100 |  | 2022-03-16 | 2022-03-16 | 2022-03-21 | 2022-03-21 | Tower A | Excavation
43946 | Tower A - Excavation - Zone 1 South (upto NTA Zone 2) | Complete | Pile Caping Beam | 2022-03-16 | 2022-03-21 | Casting & de-shuttering | 100 | 100 |  | 2022-03-16 | 2022-03-16 | 2022-03-21 | 2022-03-21 | Tower A | Excavation
48026 |  | Complete |  | 2022-03-19 | 2022-04-29 | Demolition | 100 | 100 |  | 2022-03-19 | 2022-03-19 | 2022-04-29 | 2022-04-29
48027 |  | Complete |  | 2022-03-19 | 2022-04-16 | CFO NOC | 100 | 100 |  | 2022-03-19 | 2022-03-19 | 2022-04-16 | 2022-04-16
48028 |  | Complete |  | 2022-03-19 | 2022-04-16 | New Barrication & Circulation | 100 | 100 |  | 2022-03-19 | 2022-03-19 | 2022-04-16 | 2022-04-16
40566 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Excavation upto -4 Mtr | 2022-03-22 | 2022-03-23 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-03-22 | 2022-03-22 | 2022-03-23 | 2022-03-23 | Tower A | Excavation
40566 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Excavation upto -4 Mtr | 2022-03-22 | 2022-03-23 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-03-22 | 2022-03-22 | 2022-03-23 | 2022-03-23 | Tower A | Excavation
40566 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Excavation upto -4 Mtr | 2022-03-22 | 2022-03-23 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-03-22 | 2022-03-22 | 2022-03-23 | 2022-03-23 | Tower A | Excavation
40566 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Excavation upto -4 Mtr | 2022-03-22 | 2022-03-23 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-03-22 | 2022-03-22 | 2022-03-23 | 2022-03-23 | Tower A | Excavation
40566 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Excavation upto -4 Mtr | 2022-03-22 | 2022-03-23 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-03-22 | 2022-03-22 | 2022-03-23 | 2022-03-23 | Tower A | Excavation
40566 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Excavation upto -4 Mtr | 2022-03-22 | 2022-03-23 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-03-22 | 2022-03-22 | 2022-03-23 | 2022-03-23 | Tower A | Excavation
40573 | Tower A - Excavation - Zone 1A | Complete | Rock Anchoring | 2022-03-23 | 2022-03-28 | waiting for grout strength & Stressing | 100 | 100 |  | 2022-03-23 | 2022-03-23 | 2022-03-28 | 2022-03-28 | Tower A | Excavation
40574 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Rock Anchoring | 2022-03-24 | 2022-04-09 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-03-24 | 2022-03-24 | 2022-04-09 | 2022-04-09 | Tower A | Excavation
40574 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Rock Anchoring | 2022-03-24 | 2022-04-09 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-03-24 | 2022-03-24 | 2022-04-09 | 2022-04-09 | Tower A | Excavation
40574 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Rock Anchoring | 2022-03-24 | 2022-04-09 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-03-24 | 2022-03-24 | 2022-04-09 | 2022-04-09 | Tower A | Excavation
40574 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Rock Anchoring | 2022-03-24 | 2022-04-09 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-03-24 | 2022-03-24 | 2022-04-09 | 2022-04-09 | Tower A | Excavation
40574 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Rock Anchoring | 2022-03-24 | 2022-04-09 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-03-24 | 2022-03-24 | 2022-04-09 | 2022-04-09 | Tower A | Excavation
40574 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Rock Anchoring | 2022-03-24 | 2022-04-09 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-03-24 | 2022-03-24 | 2022-04-09 | 2022-04-09 | Tower A | Excavation
43949 | Tower A - Excavation - Zone 1 North (outside NTA Zone 2) | Complete | Pile Caping Beam | 2022-03-26 | 2022-03-31 | Reinf. Fixing | 100 | 100 |  | 2022-03-26 | 2022-03-26 | 2022-03-31 | 2022-03-31 | Tower A | Excavation
40579 | Tower A - Excavation - Zone 1A | Complete | Excavation upto -8 Mtr | 2022-03-29 | 2022-03-30 | Zone 1A | 100 | 100 |  | 2022-03-29 | 2022-03-29 | 2022-03-30 | 2022-03-30 | Tower A | Excavation
40579 | Tower A - Excavation - Zone 1A | Complete | Excavation upto -8 Mtr | 2022-03-29 | 2022-03-30 | Zone 1A | 100 | 100 |  | 2022-03-29 | 2022-03-29 | 2022-03-30 | 2022-03-30 | Tower A | Excavation
40579 | Tower A - Excavation - Zone 1A | Complete | Excavation upto -8 Mtr | 2022-03-29 | 2022-03-30 | Zone 1A | 100 | 100 |  | 2022-03-29 | 2022-03-29 | 2022-03-30 | 2022-03-30 | Tower A | Excavation
40579 | Tower A - Excavation - Zone 1A | Complete | Excavation upto -8 Mtr | 2022-03-29 | 2022-03-30 | Zone 1A | 100 | 100 |  | 2022-03-29 | 2022-03-29 | 2022-03-30 | 2022-03-30 | Tower A | Excavation
40579 | Tower A - Excavation - Zone 1A | Complete | Excavation upto -8 Mtr | 2022-03-29 | 2022-03-30 | Zone 1A | 100 | 100 |  | 2022-03-29 | 2022-03-29 | 2022-03-30 | 2022-03-30 | Tower A | Excavation
40579 | Tower A - Excavation - Zone 1A | Complete | Excavation upto -8 Mtr | 2022-03-29 | 2022-03-30 | Zone 1A | 100 | 100 |  | 2022-03-29 | 2022-03-29 | 2022-03-30 | 2022-03-30 | Tower A | Excavation
43950 | Tower A - Excavation - Zone 1 North (outside NTA Zone 2) | Complete | Pile Caping Beam | 2022-04-01 | 2022-04-04 | Fwk Fixing | 100 | 100 |  | 2022-04-01 | 2022-04-01 | 2022-04-04 | 2022-04-04 | Tower A | Excavation
43951 | Tower A - Excavation - Zone 1 North (outside NTA Zone 2) | Complete | Pile Caping Beam | 2022-04-05 | 2022-04-08 | Casting & de-shuttering | 100 | 100 |  | 2022-04-05 | 2022-04-05 | 2022-04-08 | 2022-04-08 | Tower A | Excavation
40575 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Rock Anchoring | 2022-04-11 | 2022-04-15 | waiting for grout strength & Stressing | 100 | 100 |  | 2022-04-11 | 2022-04-11 | 2022-04-15 | 2022-04-15 | Tower A | Excavation
40580 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Excavation upto -8 Mtr | 2022-04-16 | 2022-04-18 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-04-16 | 2022-04-16 | 2022-04-18 | 2022-04-18 | Tower A | Excavation
40580 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Excavation upto -8 Mtr | 2022-04-16 | 2022-04-18 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-04-16 | 2022-04-16 | 2022-04-18 | 2022-04-18 | Tower A | Excavation
40580 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Excavation upto -8 Mtr | 2022-04-16 | 2022-04-18 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-04-16 | 2022-04-16 | 2022-04-18 | 2022-04-18 | Tower A | Excavation
40580 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Excavation upto -8 Mtr | 2022-04-16 | 2022-04-18 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-04-16 | 2022-04-16 | 2022-04-18 | 2022-04-18 | Tower A | Excavation
40580 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Excavation upto -8 Mtr | 2022-04-16 | 2022-04-18 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-04-16 | 2022-04-16 | 2022-04-18 | 2022-04-18 | Tower A | Excavation
40580 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Excavation upto -8 Mtr | 2022-04-16 | 2022-04-18 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-04-16 | 2022-04-16 | 2022-04-18 | 2022-04-18 | Tower A | Excavation
40588 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Excavation upto -14 Mtr | 2022-04-19 | 2022-05-07 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-04-19 | 2022-04-19 | 2022-05-07 | 2022-05-07 | Tower A | Excavation
40588 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Excavation upto -14 Mtr | 2022-04-19 | 2022-05-07 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-04-19 | 2022-04-19 | 2022-05-07 | 2022-05-07 | Tower A | Excavation
40588 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Excavation upto -14 Mtr | 2022-04-19 | 2022-05-07 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-04-19 | 2022-04-19 | 2022-05-07 | 2022-05-07 | Tower A | Excavation
40588 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Excavation upto -14 Mtr | 2022-04-19 | 2022-05-07 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-04-19 | 2022-04-19 | 2022-05-07 | 2022-05-07 | Tower A | Excavation
40588 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Excavation upto -14 Mtr | 2022-04-19 | 2022-05-07 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-04-19 | 2022-04-19 | 2022-05-07 | 2022-05-07 | Tower A | Excavation
40588 | Tower A - Excavation - Zone 1 North (upto NTA Zone 2) | Complete | Excavation upto -14 Mtr | 2022-04-19 | 2022-05-07 | Zone 1 North (up to NTA Zone 2) | 100 | 100 |  | 2022-04-19 | 2022-04-19 | 2022-05-07 | 2022-05-07 | Tower A | Excavation
44690 | Tower A | Complete | Award of Packages | 2022-07-13 | 2022-07-30 | Issue of LOI | 100 | 100 |  | 2022-07-13 | 2022-07-13 | 2022-07-30 | 2022-07-30 | Tower A | --
39134 |  | Complete |  | 2022-08-01 | 2022-12-23 | Shell & Core Contractor | 100 | 100 |  | 2022-08-01 | 2022-08-01 | 2022-12-23 | 2022-12-23
39135 |  | Complete |  | 2022-08-01 | 2022-08-31 | RCC works Sub-Contractors | 100 | 100 |  | 2022-08-01 | 2022-08-01 | 2022-08-31 | 2022-08-31
44236 |  | Started |  | 2022-08-01 | 2026-05-18 | HIGH SIDE PROCUREMENT | 100 | 33 |  | 2022-08-01 | 2022-08-01 | 2026-05-29
44239 | Tower A | Complete | High Side Procurement | 2022-08-01 | 2022-11-18 | Core Wall ACS Formwork | 100 | 100 |  | 2022-08-01 | 2022-08-01 | 2022-11-18 | 2022-11-18 | Tower A | --
44238 | Tower A | Complete | High Side Procurement | 2022-08-03 | 2022-09-08 | Placer Boom | 100 | 100 |  | 2022-08-03 | 2022-08-03 | 2022-09-08 | 2022-09-08 | Tower A | --
40587 | Tower A - Excavation - Zone 1A | Complete | Excavation upto -14 Mtr | 2022-08-18 | 2022-08-25 | Zone 1A | 100 | 100 |  | 2022-08-18 | 2022-08-18 | 2022-08-25 | 2022-08-25 | Tower A | Excavation
40587 | Tower A - Excavation - Zone 1A | Complete | Excavation upto -14 Mtr | 2022-08-18 | 2022-08-25 | Zone 1A | 100 | 100 |  | 2022-08-18 | 2022-08-18 | 2022-08-25 | 2022-08-25 | Tower A | Excavation
40587 | Tower A - Excavation - Zone 1A | Complete | Excavation upto -14 Mtr | 2022-08-18 | 2022-08-25 | Zone 1A | 100 | 100 |  | 2022-08-18 | 2022-08-18 | 2022-08-25 | 2022-08-25 | Tower A | Excavation
40587 | Tower A - Excavation - Zone 1A | Complete | Excavation upto -14 Mtr | 2022-08-18 | 2022-08-25 | Zone 1A | 100 | 100 |  | 2022-08-18 | 2022-08-18 | 2022-08-25 | 2022-08-25 | Tower A | Excavation
40587 | Tower A - Excavation - Zone 1A | Complete | Excavation upto -14 Mtr | 2022-08-18 | 2022-08-25 | Zone 1A | 100 | 100 |  | 2022-08-18 | 2022-08-18 | 2022-08-25 | 2022-08-25 | Tower A | Excavation
40587 | Tower A - Excavation - Zone 1A | Complete | Excavation upto -14 Mtr | 2022-08-18 | 2022-08-25 | Zone 1A | 100 | 100 |  | 2022-08-18 | 2022-08-18 | 2022-08-25 | 2022-08-25 | Tower A | Excavation
39136 |  | Complete |  | 2022-08-25 | 2022-09-13 | Waterproofing Agency | 100 | 100 |  | 2022-08-25 | 2022-08-25 | 2022-09-13 | 2022-09-13
40939 |  | Complete |  | 2022-08-26 | 2022-12-06 | Foundation_TA (Zone 1) | 100 | 100 |  | 2022-08-26 | 2022-08-26 | 2022-12-06 | 2022-12-06
41001 |  | Complete |  | 2022-08-26 | 2022-11-21 | PCC & Raft waterproofing | 100 | 100 |  | 2022-08-26 | 2022-08-26 | 2022-11-21 | 2022-11-21
41003 | Tower A - Foundation | Complete | PCC | 2022-08-26 | 2022-08-29 | PCC & Blockwork for vertical surface-Pour 1A & 2 lift pits | 100 | 100 |  | 2022-08-26 | 2022-08-26 | 2022-08-29 | 2022-08-29 | Tower A | Foundation | --
41004 | Tower A - Foundation | Complete | HDPE Waterproofing | 2022-08-31 | 2022-09-02 | HDPE waterproofing laying-Pour 1A & 2 lift pits | 100 | 100 |  | 2022-08-31 | 2022-08-31 | 2022-09-02 | 2022-09-02 | Tower A | Foundation | --
41002 | Tower A - Foundation | Milestone Started | PCC | 2022-09-01 |  | PCC below Liner wall | 100 | 100 |  | 2022-09-01 | 2022-09-09 |  |  | Tower A | Foundation | --
40940 |  | Complete |  | 2022-09-09 | 2022-10-03 | Liner Wall | 100 | 100 |  | 2022-09-09 | 2022-09-09 | 2022-10-03 | 2022-10-03
40941 | Tower A - Foundation | Complete | Liner Wall Casting | 2022-09-09 | 2022-09-12 | Liner wall-Section 1 | 100 | 100 |  | 2022-09-09 | 2022-09-09 | 2022-09-12 | 2022-09-12 | Tower A | Foundation | --
40942 | Tower A - Foundation | Complete | HDPE Waterproofing | 2022-09-13 | 2022-09-14 | Waterproofing-Section 1 | 100 | 100 |  | 2022-09-13 | 2022-09-13 | 2022-09-14 | 2022-09-14 | Tower A | Foundation | --
40943 | Tower A - Foundation | Complete | Liner Wall Casting | 2022-09-13 | 2022-09-15 | Liner wall-Section 4 | 100 | 100 |  | 2022-09-13 | 2022-09-13 | 2022-09-15 | 2022-09-15 | Tower A | Foundation | --
40944 | Tower A - Foundation | Complete | HDPE Waterproofing | 2022-09-16 | 2022-09-19 | Waterproofing-Section 4 | 100 | 100 |  | 2022-09-16 | 2022-09-16 | 2022-09-19 | 2022-09-19 | Tower A | Foundation | --
40945 | Tower A - Foundation | Complete | Liner Wall Casting | 2022-09-16 | 2022-09-20 | Liner wall-Section 3 | 100 | 100 |  | 2022-09-16 | 2022-09-16 | 2022-09-20 | 2022-09-20 | Tower A | Foundation | --
40953 |  | Complete |  | 2022-09-19 | 2022-10-15 | Pour 1A & 2 lift pits | 100 | 100 |  | 2022-09-19 | 2022-09-19 | 2022-10-15 | 2022-10-15
40954 | Tower A - Foundation - Pour 1A | Complete | Lift Pit RCC Works | 2022-09-19 | 2022-10-01 | Lift pit reinf. | 100 | 100 |  | 2022-09-19 | 2022-09-19 | 2022-10-01 | 2022-10-01 | Tower A | Foundation |  | RCC Sub Structure | Lift Pit RCC Works
40946 | Tower A - Foundation | Complete | HDPE Waterproofing | 2022-09-21 | 2022-09-22 | Waterproofing-Section 3 | 100 | 100 |  | 2022-09-21 | 2022-09-21 | 2022-09-22 | 2022-09-22 | Tower A | Foundation | --
40947 | Tower A - Foundation | Complete | Liner Wall Casting | 2022-09-21 | 2022-09-23 | Liner wall-Section 5 | 100 | 100 |  | 2022-09-21 | 2022-09-21 | 2022-09-23 | 2022-09-23 | Tower A | Foundation | --
41005 | Tower A - Foundation | Complete | PCC | 2022-09-22 | 2022-09-26 | PCC for vertical surface-1B | 100 | 100 |  | 2022-09-22 | 2022-09-22 | 2022-09-26 | 2022-09-26 | Tower A | Foundation | --
40948 | Tower A - Foundation | Complete | HDPE Waterproofing | 2022-09-24 | 2022-09-26 | Waterproofing-Section 5 | 100 | 100 |  | 2022-09-24 | 2022-09-24 | 2022-09-26 | 2022-09-26 | Tower A | Foundation | --
40949 | Tower A - Foundation | Complete | Liner Wall Casting | 2022-09-24 | 2022-09-27 | Liner wall-Section 2 | 100 | 100 |  | 2022-09-24 | 2022-09-24 | 2022-09-27 | 2022-09-27 | Tower A | Foundation | --
41006 | Tower A - Foundation | Complete | HDPE Waterproofing | 2022-09-26 | 2022-09-29 | HDPE waterproofing laying-1B | 100 | 100 |  | 2022-09-26 | 2022-09-26 | 2022-09-29 | 2022-09-29 | Tower A | Foundation | --
41009 | Tower A - Foundation | Complete | PCC | 2022-09-26 | 2022-09-29 | PCC- Pour 3 | 100 | 100 |  | 2022-09-26 | 2022-09-26 | 2022-09-29 | 2022-09-29 | Tower A | Foundation | --
41015 | Tower A - Foundation | Complete | PCC | 2022-09-26 | 2022-09-29 | PCC- Pour 8 | 100 | 100 |  | 2022-09-26 | 2022-09-26 | 2022-09-29 | 2022-09-29 | Tower A | Foundation | --
44237 | Tower A | Complete | High Side Procurement | 2022-09-26 | 2022-11-01 | Tower Crane | 100 | 100 |  | 2022-09-26 | 2022-09-26 | 2022-11-01 | 2022-11-01 | Tower A | --
40950 | Tower A - Foundation | Complete | HDPE Waterproofing | 2022-09-28 | 2022-09-29 | Waterproofing-Section 2 | 100 | 100 |  | 2022-09-28 | 2022-09-28 | 2022-09-29 | 2022-09-29 | Tower A | Foundation | --
40951 | Tower A - Foundation | Complete | Liner Wall Casting | 2022-09-28 | 2022-09-30 | Liner wall-Section 6 | 100 | 100 |  | 2022-09-28 | 2022-09-28 | 2022-09-30 | 2022-09-30 | Tower A | Foundation | --
40959 |  | Complete |  | 2022-09-29 | 2022-10-21 | Pour 1B lift pit | 100 | 100 |  | 2022-09-29 | 2022-09-29 | 2022-10-21 | 2022-10-21
40960 | Tower A - Foundation - Pour 1B | Complete | Lift Pit RCC Works | 2022-09-29 | 2022-10-12 | Lift pit reinf. | 100 | 100 |  | 2022-09-29 | 2022-09-29 | 2022-10-12 | 2022-10-12 | Tower A | Foundation |  | RCC Sub Structure | Lift Pit RCC Works
41010 | Tower A - Foundation | Complete | HDPE Waterproofing | 2022-09-29 | 2022-10-03 | HDPE waterproofing laying- Pour 3 | 100 | 100 |  | 2022-09-29 | 2022-09-29 | 2022-10-03 | 2022-10-03 | Tower A | Foundation | --
41016 | Tower A - Foundation | Complete | HDPE Waterproofing | 2022-09-29 | 2022-10-03 | HDPE waterproofing laying- Pour 8 | 100 | 100 |  | 2022-09-29 | 2022-09-29 | 2022-10-03 | 2022-10-03 | Tower A | Foundation | --
40952 | Tower A - Foundation | Complete | HDPE Waterproofing | 2022-10-01 | 2022-10-03 | Waterproofing-Section 6 | 100 | 100 |  | 2022-10-01 | 2022-10-01 | 2022-10-03 | 2022-10-03 | Tower A | Foundation | --
40955 | Tower A - Foundation - Pour 1A | Complete | Lift Pit RCC Works | 2022-10-03 | 2022-10-03 | Casting of pit bottom section | 100 | 100 |  | 2022-10-03 | 2022-10-03 | 2022-10-03 | 2022-10-03 | Tower A | Foundation |  | RCC Sub Structure | Lift Pit RCC Works
40969 |  | Complete |  | 2022-10-03 | 2022-10-17 | Pour 3 | 100 | 100 |  | 2022-10-03 | 2022-10-03 | 2022-10-17 | 2022-10-17
40970 | Tower A - Foundation - Pour 3 | Complete | Raft RCC Works | 2022-10-03 | 2022-10-13 | Raft reinf. | 100 | 100 |  | 2022-10-03 | 2022-10-03 | 2022-10-13 | 2022-10-13 | Tower A | Foundation |  | RCC Sub Structure | Raft RCC Works
40981 |  | Complete |  | 2022-10-03 | 2022-10-21 | Pour 8 | 100 | 100 |  | 2022-10-03 | 2022-10-03 | 2022-10-21 | 2022-10-21
40982 | Tower A - Foundation - Pour 8 | Complete | Raft RCC Works | 2022-10-03 | 2022-10-18 | Raft reinf. | 100 | 100 |  | 2022-10-03 | 2022-10-03 | 2022-10-18 | 2022-10-18 | Tower A | Foundation |  | RCC Sub Structure | Raft RCC Works
40956 | Tower A - Foundation - Pour 1A | Complete | Lift Pit RCC Works | 2022-10-04 | 2022-10-12 | Reinf. For pit wall section | 100 | 100 |  | 2022-10-04 | 2022-10-04 | 2022-10-12 | 2022-10-12 | Tower A | Foundation |  | RCC Sub Structure | Lift Pit RCC Works
41011 | Tower A - Foundation | Complete | PCC | 2022-10-10 | 2022-10-13 | PCC- Pour 6 | 100 | 100 |  | 2022-10-10 | 2022-10-10 | 2022-10-13 | 2022-10-13 | Tower A | Foundation | --
41017 | Tower A - Foundation | Complete | PCC | 2022-10-12 | 2022-10-15 | PCC- Pour 9A | 100 | 100 |  | 2022-10-12 | 2022-10-12 | 2022-10-15 | 2022-10-15 | Tower A | Foundation | --
40957 | Tower A - Foundation - Pour 1A | Complete | Lift Pit RCC Works | 2022-10-13 | 2022-10-14 | Fwk for pit wall | 100 | 100 |  | 2022-10-13 | 2022-10-13 | 2022-10-14 | 2022-10-14 | Tower A | Foundation |  | RCC Sub Structure | Lift Pit RCC Works
40961 | Tower A - Foundation - Pour 1B | Complete | Lift Pit RCC Works | 2022-10-13 | 2022-10-13 | Casting of pit bottom section | 100 | 100 |  | 2022-10-13 | 2022-10-13 | 2022-10-13 | 2022-10-13 | Tower A | Foundation |  | RCC Sub Structure | Lift Pit RCC Works
41012 | Tower A - Foundation | Complete | HDPE Waterproofing | 2022-10-13 | 2022-10-17 | HDPE waterproofing laying- Pour 6 | 100 | 100 |  | 2022-10-13 | 2022-10-13 | 2022-10-17 | 2022-10-17 | Tower A | Foundation | --
40962 | Tower A - Foundation - Pour 1B | Complete | Lift Pit RCC Works | 2022-10-14 | 2022-10-18 | Reinf. For pit wall section | 100 | 100 |  | 2022-10-14 | 2022-10-14 | 2022-10-18 | 2022-10-18 | Tower A | Foundation |  | RCC Sub Structure | Lift Pit RCC Works
40971 | Tower A - Foundation - Pour 3 | Complete | Raft RCC Works | 2022-10-14 | 2022-10-15 | Fwk fix | 100 | 100 |  | 2022-10-14 | 2022-10-14 | 2022-10-15 | 2022-10-15 | Tower A | Foundation |  | RCC Sub Structure | Raft RCC Works
40958 | Tower A - Foundation - Pour 1A | Complete | Lift Pit RCC Works | 2022-10-15 | 2022-10-15 | Casting of pit wall & top section | 100 | 100 |  | 2022-10-15 | 2022-10-15 | 2022-10-15 | 2022-10-15 | Tower A | Foundation |  | RCC Sub Structure | Lift Pit RCC Works
41018 | Tower A - Foundation | Complete | HDPE Waterproofing | 2022-10-15 | 2022-10-19 | HDPE waterproofing laying- Pour 9A | 100 | 100 |  | 2022-10-15 | 2022-10-15 | 2022-10-19 | 2022-10-19 | Tower A | Foundation | --
40972 | Tower A - Foundation - Pour 3 | Complete | Raft RCC Works | 2022-10-17 | 2022-10-17 | Checking & casting | 100 | 100 |  | 2022-10-17 | 2022-10-17 | 2022-10-17 | 2022-10-17 | Tower A | Foundation |  | RCC Sub Structure | Raft RCC Works
40973 |  | Complete |  | 2022-10-17 | 2022-11-14 | Pour 6 | 100 | 100 |  | 2022-10-17 | 2022-10-17 | 2022-11-14 | 2022-11-14
40974 | Tower A - Foundation - Pour 6 | Complete | Raft RCC Works | 2022-10-17 | 2022-11-11 | Raft reinf. | 100 | 100 |  | 2022-10-17 | 2022-10-17 | 2022-11-11 | 2022-11-11 | Tower A | Foundation |  | RCC Sub Structure | Raft RCC Works
43442 |  | Complete |  | 2022-10-17 | 2023-05-08 | Sub-Structure_TA & NTA (Zone 1) | 100 | 100 |  | 2022-10-17 | 2022-10-17 | 2023-05-08 | 2023-05-06
43444 |  | Complete |  | 2022-10-17 | 2023-01-17 | B3 to B2 | 100 | 100 |  | 2022-10-17 | 2022-10-17 | 2023-01-17 | 2023-01-17
43444 |  | Complete |  | 2022-10-17 | 2023-01-17 | B3 to B2 | 100 | 100 |  | 2022-10-17 | 2022-10-17 | 2023-01-17 | 2023-01-17
43444 |  | Complete |  | 2022-10-17 | 2023-01-17 | B3 to B2 | 100 | 100 |  | 2022-10-17 | 2022-10-17 | 2023-01-17 | 2023-01-17
43445 |  | Complete |  | 2022-10-17 | 2022-12-14 | Retaining Wall_B3 to B2_Zone 1A | 100 | 100 |  | 2022-10-17 | 2022-10-17 | 2022-12-14 | 2022-12-14
43446 |  | Complete |  | 2022-10-17 | 2022-11-09 | Section 1_13m | 100 | 100 |  | 2022-10-17 | 2022-10-17 | 2022-11-09 | 2022-11-09
43447 | Tower A - Sub Structure - B3 to B2 - Sec 1 (13 m) | Complete | Retaining Wall RCC Works | 2022-10-17 | 2022-10-19 | Liner Wall Fwk & Casting | 100 | 100 |  | 2022-10-17 | 2022-10-17 | 2022-10-19 | 2022-10-19 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
40963 | Tower A - Foundation - Pour 1B | Complete | Lift Pit RCC Works | 2022-10-19 | 2022-10-20 | Fwk for pit wall | 100 | 100 |  | 2022-10-19 | 2022-10-19 | 2022-10-20 | 2022-10-20 | Tower A | Foundation |  | RCC Sub Structure | Lift Pit RCC Works
40983 | Tower A - Foundation - Pour 8 | Complete | Raft RCC Works | 2022-10-19 | 2022-10-20 | Fwk fix | 100 | 100 |  | 2022-10-19 | 2022-10-19 | 2022-10-20 | 2022-10-20 | Tower A | Foundation |  | RCC Sub Structure | Raft RCC Works
40985 |  | Complete |  | 2022-10-19 | 2022-11-01 | Pour 9A | 100 | 100 |  | 2022-10-19 | 2022-10-19 | 2022-11-01 | 2022-11-01
40986 | Tower A - Foundation - Pour 9A | Complete | Raft RCC Works | 2022-10-19 | 2022-10-28 | Raft reinf. | 100 | 100 |  | 2022-10-19 | 2022-10-19 | 2022-10-28 | 2022-10-28 | Tower A | Foundation |  | RCC Sub Structure | Raft RCC Works
43448 | Tower A - Sub Structure - B3 to B2 - Sec 1 (13 m) | Complete | Retaining Wall RCC Works | 2022-10-20 | 2022-10-22 | Waterproofing along the liner wall | 100 | 100 |  | 2022-10-20 | 2022-10-20 | 2022-10-22 | 2022-10-22 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
40964 | Tower A - Foundation - Pour 1B | Complete | Lift Pit RCC Works | 2022-10-21 | 2022-10-21 | Casting of pit wall & top section | 100 | 100 |  | 2022-10-21 | 2022-10-21 | 2022-10-21 | 2022-10-21 | Tower A | Foundation |  | RCC Sub Structure | Lift Pit RCC Works
40984 | Tower A - Foundation - Pour 8 | Complete | Raft RCC Works | 2022-10-21 | 2022-10-21 | Checking & casting | 100 | 100 |  | 2022-10-21 | 2022-10-21 | 2022-10-21 | 2022-10-21 | Tower A | Foundation |  | RCC Sub Structure | Raft RCC Works
41019 | Tower A - Foundation | Complete | PCC | 2022-10-21 | 2022-10-26 | PCC- Pour 9B | 100 | 100 |  | 2022-10-21 | 2022-10-21 | 2022-10-26 | 2022-10-26 | Tower A | Foundation | --
41023 | Tower A - Foundation | Complete | PCC | 2022-10-21 | 2022-10-26 | PCC- Pour 4 | 100 | 100 |  | 2022-10-21 | 2022-10-21 | 2022-10-26 | 2022-10-26 | Tower A | Foundation | --
43449 | Tower A - Sub Structure - B3 to B2 - Sec 1 (13 m) | Complete | Retaining Wall RCC Works | 2022-10-25 | 2022-10-27 | Retaining Wall_Reinf_Lift 1 | 100 | 100 |  | 2022-10-25 | 2022-10-25 | 2022-10-27 | 2022-10-27 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43455 |  | Complete |  | 2022-10-25 | 2022-11-16 | Section 4_10m | 100 | 100 |  | 2022-10-25 | 2022-10-25 | 2022-11-16 | 2022-11-16
43456 | Tower A - Sub Structure - B3 to B2 - Sec 4 (10 m) | Complete | Retaining Wall RCC Works | 2022-10-25 | 2022-10-27 | Liner Wall Fwk & Casting | 100 | 100 |  | 2022-10-25 | 2022-10-25 | 2022-10-27 | 2022-10-27 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
41020 | Tower A - Foundation | Complete | HDPE Waterproofing | 2022-10-26 | 2022-10-29 | HDPE waterproofing laying- Pour 9B | 100 | 100 |  | 2022-10-26 | 2022-10-26 | 2022-10-29 | 2022-10-29 | Tower A | Foundation | --
41024 | Tower A - Foundation | Complete | HDPE Waterproofing | 2022-10-26 | 2022-10-29 | HDPE waterproofing laying- Pour 5 | 100 | 100 |  | 2022-10-26 | 2022-10-26 | 2022-10-29 | 2022-10-29 | Tower A | Foundation | --
43450 | Tower A - Sub Structure - B3 to B2 - Sec 1 (13 m) | Complete | Retaining Wall RCC Works | 2022-10-28 | 2022-10-31 | Fwk_Lift 1 RW | 100 | 100 |  | 2022-10-28 | 2022-10-28 | 2022-10-31 | 2022-10-31 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43457 | Tower A - Sub Structure - B3 to B2 - Sec 4 (10 m) | Complete | Retaining Wall RCC Works | 2022-10-28 | 2022-10-31 | Waterproofing along the liner wall | 100 | 100 |  | 2022-10-28 | 2022-10-28 | 2022-10-31 | 2022-10-31 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
40987 | Tower A - Foundation - Pour 9A | Complete | Raft RCC Works | 2022-10-29 | 2022-10-31 | Fwk fix | 100 | 100 |  | 2022-10-29 | 2022-10-29 | 2022-10-31 | 2022-10-31 | Tower A | Foundation |  | RCC Sub Structure | Raft RCC Works
40989 |  | Complete |  | 2022-10-29 | 2022-11-10 | Pour 9B | 100 | 100 |  | 2022-10-29 | 2022-10-29 | 2022-11-10 | 2022-11-10
40990 | Tower A - Foundation - Pour 9B | Complete | Raft RCC Works | 2022-10-29 | 2022-11-07 | Raft reinf. | 100 | 100 |  | 2022-10-29 | 2022-10-29 | 2022-11-07 | 2022-11-07 | Tower A | Foundation |  | RCC Sub Structure | Raft RCC Works
40997 |  | Complete |  | 2022-10-29 | 2022-11-14 | Pour 4 | 100 | 100 |  | 2022-10-29 | 2022-10-29 | 2022-11-14 | 2022-11-14
40998 | Tower A - Foundation - Pour 4 | Complete | Raft RCC Works | 2022-10-29 | 2022-11-11 | Raft reinf. | 100 | 100 |  | 2022-10-29 | 2022-10-29 | 2022-11-11 | 2022-11-11 | Tower A | Foundation |  | RCC Sub Structure | Raft RCC Works
40988 | Tower A - Foundation - Pour 9A | Complete | Raft RCC Works | 2022-11-01 | 2022-11-01 | Checking & casting | 100 | 100 |  | 2022-11-01 | 2022-11-01 | 2022-11-01 | 2022-11-01 | Tower A | Foundation |  | RCC Sub Structure | Raft RCC Works
41007 | Tower A - Foundation | Complete | PCC | 2022-11-01 | 2022-11-04 | PCC- Pour 2 | 100 | 100 |  | 2022-11-01 | 2022-11-01 | 2022-11-04 | 2022-11-04 | Tower A | Foundation | --
43451 | Tower A - Sub Structure - B3 to B2 - Sec 1 (13 m) | Complete | Retaining Wall RCC Works | 2022-11-01 | 2022-11-01 | Checking & Casting_Lift 1 | 100 | 100 |  | 2022-11-01 | 2022-11-01 | 2022-11-01 | 2022-11-01 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43458 | Tower A - Sub Structure - B3 to B2 - Sec 4 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-01 | 2022-11-03 | Retaining Wall_Reinf_Lift 1 | 100 | 100 |  | 2022-11-01 | 2022-11-01 | 2022-11-03 | 2022-11-03 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43464 |  | Complete |  | 2022-11-01 | 2022-11-23 | Section 3_10m | 100 | 100 |  | 2022-11-01 | 2022-11-01 | 2022-11-23 | 2022-11-23
43465 | Tower A - Sub Structure - B3 to B2 - Sec 3 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-01 | 2022-11-03 | Liner Wall Fwk & Casting | 100 | 100 |  | 2022-11-01 | 2022-11-01 | 2022-11-03 | 2022-11-03 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43511 |  | Complete |  | 2022-11-01 | 2023-01-09 | Pour 3_B3 to B2 | 100 | 100 |  | 2022-11-01 | 2022-11-01 | 2023-01-09 | 2023-01-09
43513 | Tower A - Sub Structure - B3 to B2 - Pour 3 | Complete | Core Wall RCC Works | 2022-11-01 | 2022-11-11 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2022-11-01 | 2022-11-01 | 2022-11-11 | 2022-11-11 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
43513 | Tower A - Sub Structure - B3 to B2 - Pour 3 | Complete | Core Wall RCC Works | 2022-11-01 | 2022-11-11 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2022-11-01 | 2022-11-01 | 2022-11-11 | 2022-11-11 | Tower A | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
43452 | Tower A - Sub Structure - B3 to B2 - Sec 1 (13 m) | Complete | Retaining Wall RCC Works | 2022-11-02 | 2022-11-04 | Retaining Wall_Reinf_Lift 2 | 100 | 100 |  | 2022-11-02 | 2022-11-02 | 2022-11-04 | 2022-11-04 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43514 | Tower A - Sub Structure - B3 to B2 - Pour 3 | Complete | Core Wall RCC Works | 2022-11-03 | 2022-11-14 | Col/ Wall Casting | 100 | 100 |  | 2022-11-03 | 2022-11-03 | 2022-11-14 | 2022-11-14 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
43514 | Tower A - Sub Structure - B3 to B2 - Pour 3 | Complete | Core Wall RCC Works | 2022-11-03 | 2022-11-14 | Col/ Wall Casting | 100 | 100 |  | 2022-11-03 | 2022-11-03 | 2022-11-14 | 2022-11-14 | Tower A | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
41008 | Tower A - Foundation | Complete | HDPE Waterproofing | 2022-11-04 | 2022-11-08 | HDPE waterproofing laying- Pour 2 | 100 | 100 |  | 2022-11-04 | 2022-11-04 | 2022-11-08 | 2022-11-08 | Tower A | Foundation | --
43459 | Tower A - Sub Structure - B3 to B2 - Sec 4 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-04 | 2022-11-07 | Fwk_Lift 1 RW | 100 | 100 |  | 2022-11-04 | 2022-11-04 | 2022-11-07 | 2022-11-07 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43466 | Tower A - Sub Structure - B3 to B2 - Sec 3 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-04 | 2022-11-07 | Waterproofing along the liner wall | 100 | 100 |  | 2022-11-04 | 2022-11-04 | 2022-11-07 | 2022-11-07 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43453 | Tower A - Sub Structure - B3 to B2 - Sec 1 (13 m) | Complete | Retaining Wall RCC Works | 2022-11-05 | 2022-11-08 | Fwk_Lift 2 RW | 100 | 100 |  | 2022-11-05 | 2022-11-05 | 2022-11-08 | 2022-11-08 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43512 | Tower A - Sub Structure - B3 to B2 - Pour 3 | Complete | Core Wall RCC Works | 2022-11-05 | 2022-11-08 | Col/ Wall Reinf. | 100 | 100 |  | 2022-11-05 | 2022-11-05 | 2022-11-08 | 2022-11-08 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
43512 | Tower A - Sub Structure - B3 to B2 - Pour 3 | Complete | Core Wall RCC Works | 2022-11-05 | 2022-11-08 | Col/ Wall Reinf. | 100 | 100 |  | 2022-11-05 | 2022-11-05 | 2022-11-08 | 2022-11-08 | Tower A | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
43515 | Tower A - Sub Structure - B3 to B2 - Pour 3 | Complete | RCC Works - Slab | 2022-11-05 | 2022-11-18 | Slab & Staircase Fwk. | 100 | 100 |  | 2022-11-05 | 2022-11-05 | 2022-11-18 | 2022-11-18 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
40965 |  | Complete |  | 2022-11-08 | 2022-11-23 | Pour 2 | 100 | 100 |  | 2022-11-08 | 2022-11-08 | 2022-11-23 | 2022-11-23
40966 | Tower A - Foundation - Pour 2 | Complete | Raft RCC Works | 2022-11-08 | 2022-11-21 | Raft reinf. | 100 | 100 |  | 2022-11-08 | 2022-11-08 | 2022-11-21 | 2022-11-21 | Tower A | Foundation |  | RCC Sub Structure | Raft RCC Works
40991 | Tower A - Foundation - Pour 9B | Complete | Raft RCC Works | 2022-11-08 | 2022-11-09 | Fwk fix | 100 | 100 |  | 2022-11-08 | 2022-11-08 | 2022-11-09 | 2022-11-09 | Tower A | Foundation |  | RCC Sub Structure | Raft RCC Works
41013 | Tower A - Foundation | Complete | PCC | 2022-11-08 | 2022-11-11 | PCC- Pour 7 | 100 | 100 |  | 2022-11-08 | 2022-11-08 | 2022-11-11 | 2022-11-11 | Tower A | Foundation | --
43460 | Tower A - Sub Structure - B3 to B2 - Sec 4 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-08 | 2022-11-08 | Checking & Casting_Lift 1 | 100 | 100 |  | 2022-11-08 | 2022-11-08 | 2022-11-08 | 2022-11-08 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43467 | Tower A - Sub Structure - B3 to B2 - Sec 3 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-08 | 2022-11-10 | Retaining Wall_Reinf_Lift 1 | 100 | 100 |  | 2022-11-08 | 2022-11-08 | 2022-11-10 | 2022-11-10 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43473 |  | Complete |  | 2022-11-08 | 2022-11-30 | Section 5_10m | 100 | 100 |  | 2022-11-08 | 2022-11-08 | 2022-11-30 | 2022-11-30
43474 | Tower A - Sub Structure - B3 to B2 - Sec 5 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-08 | 2022-11-10 | Liner Wall Fwk & Casting | 100 | 100 |  | 2022-11-08 | 2022-11-08 | 2022-11-10 | 2022-11-10 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43454 | Tower A - Sub Structure - B3 to B2 - Sec 1 (13 m) | Complete | Retaining Wall RCC Works | 2022-11-09 | 2022-11-09 | Checking & Casting_Lift 2 | 100 | 100 |  | 2022-11-09 | 2022-11-09 | 2022-11-09 | 2022-11-09 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43461 | Tower A - Sub Structure - B3 to B2 - Sec 4 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-09 | 2022-11-11 | Retaining Wall_Reinf_Lift 2 | 100 | 100 |  | 2022-11-09 | 2022-11-09 | 2022-11-11 | 2022-11-11 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43532 |  | Complete |  | 2022-11-09 | 2022-12-02 | Pour 8_B3 to B2 | 100 | 100 |  | 2022-11-09 | 2022-11-09 | 2022-12-02 | 2022-12-02
43534 | Tower A - Sub Structure - B3 to B2 - Pour 8 | Complete | Core Wall RCC Works | 2022-11-09 | 2022-11-19 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2022-11-09 | 2022-11-09 | 2022-11-19 | 2022-11-19 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
43534 | Tower A - Sub Structure - B3 to B2 - Pour 8 | Complete | Core Wall RCC Works | 2022-11-09 | 2022-11-19 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2022-11-09 | 2022-11-09 | 2022-11-19 | 2022-11-19 | Tower A | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
40992 | Tower A - Foundation - Pour 9B | Complete | Raft RCC Works | 2022-11-10 | 2022-11-10 | Checking & casting | 100 | 100 |  | 2022-11-10 | 2022-11-10 | 2022-11-10 | 2022-11-10 | Tower A | Foundation |  | RCC Sub Structure | Raft RCC Works
43533 | Tower A - Sub Structure - B3 to B2 - Pour 8 | Complete | Core Wall RCC Works | 2022-11-10 | 2022-11-16 | Col/ Wall Reinf. | 100 | 100 |  | 2022-11-10 | 2022-11-10 | 2022-11-16 | 2022-11-16 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
43533 | Tower A - Sub Structure - B3 to B2 - Pour 8 | Complete | Core Wall RCC Works | 2022-11-10 | 2022-11-16 | Col/ Wall Reinf. | 100 | 100 |  | 2022-11-10 | 2022-11-10 | 2022-11-16 | 2022-11-16 | Tower A | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
40975 | Tower A - Foundation - Pour 6 | Complete | Raft RCC Works | 2022-11-11 | 2022-11-14 | Fwk fix | 100 | 100 |  | 2022-11-11 | 2022-11-11 | 2022-11-14 | 2022-11-14 | Tower A | Foundation |  | RCC Sub Structure | Raft RCC Works
40999 | Tower A - Foundation - Pour 4 | Complete | Raft RCC Works | 2022-11-11 | 2022-11-14 | Fwk fix | 100 | 100 |  | 2022-11-11 | 2022-11-11 | 2022-11-14 | 2022-11-14 | Tower A | Foundation |  | RCC Sub Structure | Raft RCC Works
41014 | Tower A - Foundation | Complete | HDPE Waterproofing | 2022-11-11 | 2022-11-15 | HDPE waterproofing laying- Pour 7 | 100 | 100 |  | 2022-11-11 | 2022-11-11 | 2022-11-15 | 2022-11-15 | Tower A | Foundation | --
43468 | Tower A - Sub Structure - B3 to B2 - Sec 3 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-11 | 2022-11-14 | Fwk_Lift 1 RW | 100 | 100 |  | 2022-11-11 | 2022-11-11 | 2022-11-14 | 2022-11-14 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43475 | Tower A - Sub Structure - B3 to B2 - Sec 5 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-11 | 2022-11-14 | Waterproofing along the liner wall | 100 | 100 |  | 2022-11-11 | 2022-11-11 | 2022-11-14 | 2022-11-14 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43535 | Tower A - Sub Structure - B3 to B2 - Pour 8 | Complete | Core Wall RCC Works | 2022-11-11 | 2022-11-22 | Col/ Wall Casting | 100 | 100 |  | 2022-11-11 | 2022-11-11 | 2022-11-22 | 2022-11-22 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
43535 | Tower A - Sub Structure - B3 to B2 - Pour 8 | Complete | Core Wall RCC Works | 2022-11-11 | 2022-11-22 | Col/ Wall Casting | 100 | 100 |  | 2022-11-11 | 2022-11-11 | 2022-11-22 | 2022-11-22 | Tower A | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
43462 | Tower A - Sub Structure - B3 to B2 - Sec 4 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-12 | 2022-11-15 | Fwk_Lift 2 RW | 100 | 100 |  | 2022-11-12 | 2022-11-12 | 2022-11-15 | 2022-11-15 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
40976 | Tower A - Foundation - Pour 6 | Complete | Raft RCC Works | 2022-11-14 | 2022-11-14 | Checking & casting | 100 | 100 |  | 2022-11-14 | 2022-11-14 | 2022-11-14 | 2022-11-14 | Tower A | Foundation |  | RCC Sub Structure | Raft RCC Works
41000 | Tower A - Foundation - Pour 4 | Complete | Raft RCC Works | 2022-11-14 | 2022-11-14 | Checking & casting | 100 | 100 |  | 2022-11-14 | 2022-11-14 | 2022-11-14 | 2022-11-14 | Tower A | Foundation |  | RCC Sub Structure | Raft RCC Works
41021 | Tower A - Foundation | Complete | PCC | 2022-11-14 | 2022-11-17 | PCC- Pour 5 | 100 | 100 |  | 2022-11-14 | 2022-11-14 | 2022-11-17 | 2022-11-17 | Tower A | Foundation | --
43536 | Tower A - Sub Structure - B3 to B2 - Pour 8 | Complete | RCC Works - Slab | 2022-11-14 | 2022-11-26 | Slab & Staircase Fwk. | 100 | 100 |  | 2022-11-14 | 2022-11-14 | 2022-11-26 | 2022-11-26 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
40977 |  | Complete |  | 2022-11-15 | 2022-12-02 | Pour 7 | 100 | 100 |  | 2022-11-15 | 2022-11-15 | 2022-12-02 | 2022-12-02
40978 | Tower A - Foundation - Pour 7 | Complete | Raft RCC Works | 2022-11-15 | 2022-11-30 | Raft reinf. | 100 | 100 |  | 2022-11-15 | 2022-11-15 | 2022-11-30 | 2022-11-30 | Tower A | Foundation |  | RCC Sub Structure | Raft RCC Works
43469 | Tower A - Sub Structure - B3 to B2 - Sec 3 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-15 | 2022-11-15 | Checking & Casting_Lift 1 | 100 | 100 |  | 2022-11-15 | 2022-11-15 | 2022-11-15 | 2022-11-15 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43476 | Tower A - Sub Structure - B3 to B2 - Sec 5 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-15 | 2022-11-17 | Retaining Wall_Reinf_Lift 1 | 100 | 100 |  | 2022-11-15 | 2022-11-15 | 2022-11-17 | 2022-11-17 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43482 |  | Complete |  | 2022-11-15 | 2022-12-07 | Section 2_10m | 100 | 100 |  | 2022-11-15 | 2022-11-15 | 2022-12-07 | 2022-12-07
43483 | Tower A - Sub Structure - B3 to B2 - Sec 2 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-15 | 2022-11-17 | Liner Wall Fwk & Casting | 100 | 100 |  | 2022-11-15 | 2022-11-15 | 2022-11-17 | 2022-11-17 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43463 | Tower A - Sub Structure - B3 to B2 - Sec 4 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-16 | 2022-11-16 | Checking & Casting_Lift 2 | 100 | 100 |  | 2022-11-16 | 2022-11-16 | 2022-11-16 | 2022-11-16 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43470 | Tower A - Sub Structure - B3 to B2 - Sec 3 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-16 | 2022-11-18 | Retaining Wall_Reinf_Lift 2 | 100 | 100 |  | 2022-11-16 | 2022-11-16 | 2022-11-18 | 2022-11-18 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
41022 | Tower A - Foundation | Complete | HDPE Waterproofing | 2022-11-17 | 2022-11-21 | HDPE waterproofing laying- Pour 5 | 100 | 100 |  | 2022-11-17 | 2022-11-17 | 2022-11-21 | 2022-11-21 | Tower A | Foundation | --
43516 | Tower A - Sub Structure - B3 to B2 - Pour 3 | Complete | RCC Works - Slab | 2022-11-17 | 2022-11-22 | Slab & Staircase Reinf. | 100 | 100 |  | 2022-11-17 | 2022-11-17 | 2022-11-22 | 2022-11-22 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
43477 | Tower A - Sub Structure - B3 to B2 - Sec 5 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-18 | 2022-11-21 | Fwk_Lift 1 RW | 100 | 100 |  | 2022-11-18 | 2022-11-18 | 2022-11-21 | 2022-11-21 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43484 | Tower A - Sub Structure - B3 to B2 - Sec 2 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-18 | 2022-11-21 | Waterproofing along the liner wall | 100 | 100 |  | 2022-11-18 | 2022-11-18 | 2022-11-21 | 2022-11-21 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
39137 |  | Complete |  | 2022-11-19 | 2022-12-23 | Modular Formwork Agency | 100 | 100 |  | 2022-11-19 | 2022-11-19 | 2022-12-23 | 2022-12-23
43471 | Tower A - Sub Structure - B3 to B2 - Sec 3 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-19 | 2022-11-22 | Fwk_Lift 2 RW | 100 | 100 |  | 2022-11-19 | 2022-11-19 | 2022-11-22 | 2022-11-22 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43539 |  | Complete |  | 2022-11-19 | 2022-12-16 | Pour 9A_B3 to B2 | 100 | 100 |  | 2022-11-19 | 2022-11-19 | 2022-12-16 | 2022-12-16
43540 | Tower A - Sub Structure - B3 to B2 - Pour 9A | Complete | Core Wall RCC Works | 2022-11-19 | 2022-11-19 | Col/ Wall Reinf. | 100 | 100 |  | 2022-11-19 | 2022-11-19 | 2022-11-19 | 2022-11-19 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
43540 | Tower A - Sub Structure - B3 to B2 - Pour 9A | Complete | Core Wall RCC Works | 2022-11-19 | 2022-11-19 | Col/ Wall Reinf. | 100 | 100 |  | 2022-11-19 | 2022-11-19 | 2022-11-19 | 2022-11-19 | Tower A | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
40967 | Tower A - Foundation - Pour 2 | Complete | Raft RCC Works | 2022-11-21 | 2022-11-23 | Fwk fix | 100 | 100 |  | 2022-11-21 | 2022-11-21 | 2022-11-23 | 2022-11-23 | Tower A | Foundation |  | RCC Sub Structure | Raft RCC Works
40993 |  | Complete |  | 2022-11-21 | 2022-12-06 | Pour 5 | 100 | 100 |  | 2022-11-21 | 2022-11-21 | 2022-12-06 | 2022-12-06
40994 | Tower A - Foundation - Pour 5 | Complete | Raft RCC Works | 2022-11-21 | 2022-12-03 | Raft reinf. | 100 | 100 |  | 2022-11-21 | 2022-11-21 | 2022-12-03 | 2022-12-03 | Tower A | Foundation |  | RCC Sub Structure | Raft RCC Works
43541 | Tower A - Sub Structure - B3 to B2 - Pour 9A | Complete | Core Wall RCC Works | 2022-11-21 | 2022-11-21 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2022-11-21 | 2022-11-21 | 2022-11-21 | 2022-11-21 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
43541 | Tower A - Sub Structure - B3 to B2 - Pour 9A | Complete | Core Wall RCC Works | 2022-11-21 | 2022-11-21 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2022-11-21 | 2022-11-21 | 2022-11-21 | 2022-11-21 | Tower A | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
43478 | Tower A - Sub Structure - B3 to B2 - Sec 5 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-22 | 2022-11-22 | Checking & Casting_Lift 1 | 100 | 100 |  | 2022-11-22 | 2022-11-22 | 2022-11-22 | 2022-11-22 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43485 | Tower A - Sub Structure - B3 to B2 - Sec 2 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-22 | 2022-11-24 | Retaining Wall_Reinf_Lift 1 | 100 | 100 |  | 2022-11-22 | 2022-11-22 | 2022-11-24 | 2022-11-24 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43491 |  | Complete |  | 2022-11-22 | 2022-12-14 | Section 6_10m | 100 | 100 |  | 2022-11-22 | 2022-11-22 | 2022-12-14 | 2022-12-14
43492 | Tower A - Sub Structure - B3 to B2 - Sec 6 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-22 | 2022-11-24 | Liner Wall Fwk & Casting | 100 | 100 |  | 2022-11-22 | 2022-11-22 | 2022-11-24 | 2022-11-24 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43542 | Tower A - Sub Structure - B3 to B2 - Pour 9A | Complete | Core Wall RCC Works | 2022-11-22 | 2022-11-22 | Col/ Wall Casting | 100 | 100 |  | 2022-11-22 | 2022-11-22 | 2022-11-22 | 2022-11-22 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
43542 | Tower A - Sub Structure - B3 to B2 - Pour 9A | Complete | Core Wall RCC Works | 2022-11-22 | 2022-11-22 | Col/ Wall Casting | 100 | 100 |  | 2022-11-22 | 2022-11-22 | 2022-11-22 | 2022-11-22 | Tower A | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
40968 | Tower A - Foundation - Pour 2 | Complete | Raft RCC Works | 2022-11-23 | 2022-11-23 | Checking & casting | 100 | 100 |  | 2022-11-23 | 2022-11-23 | 2022-11-23 | 2022-11-23 | Tower A | Foundation |  | RCC Sub Structure | Raft RCC Works
43472 | Tower A - Sub Structure - B3 to B2 - Sec 3 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-23 | 2022-11-23 | Checking & Casting_Lift 2 | 100 | 100 |  | 2022-11-23 | 2022-11-23 | 2022-11-23 | 2022-11-23 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43479 | Tower A - Sub Structure - B3 to B2 - Sec 5 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-23 | 2022-11-25 | Retaining Wall_Reinf_Lift 2 | 100 | 100 |  | 2022-11-23 | 2022-11-23 | 2022-11-25 | 2022-11-25 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43543 | Tower A - Sub Structure - B3 to B2 - Pour 9A | Complete | RCC Works - Slab | 2022-11-24 | 2022-12-07 | Slab & Staircase Fwk. | 100 | 100 |  | 2022-11-24 | 2022-11-24 | 2022-12-07 | 2022-12-07 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
43486 | Tower A - Sub Structure - B3 to B2 - Sec 2 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-25 | 2022-11-28 | Fwk_Lift 1 RW | 100 | 100 |  | 2022-11-25 | 2022-11-25 | 2022-11-28 | 2022-11-28 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43493 | Tower A - Sub Structure - B3 to B2 - Sec 6 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-25 | 2022-11-28 | Waterproofing along the liner wall | 100 | 100 |  | 2022-11-25 | 2022-11-25 | 2022-11-28 | 2022-11-28 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43480 | Tower A - Sub Structure - B3 to B2 - Sec 5 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-26 | 2022-11-29 | Fwk_Lift 2 RW | 100 | 100 |  | 2022-11-26 | 2022-11-26 | 2022-11-29 | 2022-11-29 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43537 | Tower A - Sub Structure - B3 to B2 - Pour 8 | Complete | RCC Works - Slab | 2022-11-26 | 2022-11-30 | Slab & Staircase Reinf. | 100 | 100 |  | 2022-11-26 | 2022-11-26 | 2022-11-30 | 2022-11-30 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
43487 | Tower A - Sub Structure - B3 to B2 - Sec 2 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-29 | 2022-11-29 | Checking & Casting_Lift 1 | 100 | 100 |  | 2022-11-29 | 2022-11-29 | 2022-11-29 | 2022-11-29 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43494 | Tower A - Sub Structure - B3 to B2 - Sec 6 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-29 | 2022-12-01 | Retaining Wall_Reinf_Lift 1 | 100 | 100 |  | 2022-11-29 | 2022-11-29 | 2022-12-01 | 2022-12-01 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43546 |  | Complete |  | 2022-11-29 | 2022-12-21 | Pour 9B_B3 to B2 | 100 | 100 |  | 2022-11-29 | 2022-11-29 | 2022-12-21 | 2022-12-21
43547 | Tower A - Sub Structure - B3 to B2 - Pour 9B | Complete | Core Wall RCC Works | 2022-11-29 | 2022-11-29 | Col/ Wall Reinf. | 100 | 100 |  | 2022-11-29 | 2022-11-29 | 2022-11-29 | 2022-11-29 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
43547 | Tower A - Sub Structure - B3 to B2 - Pour 9B | Complete | Core Wall RCC Works | 2022-11-29 | 2022-11-29 | Col/ Wall Reinf. | 100 | 100 |  | 2022-11-29 | 2022-11-29 | 2022-11-29 | 2022-11-29 | Tower A | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
40979 | Tower A - Foundation - Pour 7 | Complete | Raft RCC Works | 2022-11-30 | 2022-12-02 | Fwk fix | 100 | 100 |  | 2022-11-30 | 2022-11-30 | 2022-12-02 | 2022-12-02 | Tower A | Foundation |  | RCC Sub Structure | Raft RCC Works
43481 | Tower A - Sub Structure - B3 to B2 - Sec 5 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-30 | 2022-11-30 | Checking & Casting_Lift 2 | 100 | 100 |  | 2022-11-30 | 2022-11-30 | 2022-11-30 | 2022-11-30 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43488 | Tower A - Sub Structure - B3 to B2 - Sec 2 (10 m) | Complete | Retaining Wall RCC Works | 2022-11-30 | 2022-12-02 | Retaining Wall_Reinf_Lift 2 | 100 | 100 |  | 2022-11-30 | 2022-11-30 | 2022-12-02 | 2022-12-02 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43518 |  | Complete |  | 2022-11-30 | 2023-01-09 | Pour 1B & 6_B3 to B2 | 100 | 100 |  | 2022-11-30 | 2022-11-30 | 2023-01-09 | 2023-01-09
43520 | Tower A - Sub Structure - B3 to B2 - Pour 1B & 6 | Complete | Core Wall RCC Works | 2022-11-30 | 2022-12-10 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2022-11-30 | 2022-11-30 | 2022-12-10 | 2022-12-10 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
43520 | Tower A - Sub Structure - B3 to B2 - Pour 1B & 6 | Complete | Core Wall RCC Works | 2022-11-30 | 2022-12-10 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2022-11-30 | 2022-11-30 | 2022-12-10 | 2022-12-10 | Tower A | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
43548 | Tower A - Sub Structure - B3 to B2 - Pour 9B | Complete | Core Wall RCC Works | 2022-11-30 | 2022-11-30 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2022-11-30 | 2022-11-30 | 2022-11-30 | 2022-11-30 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
43548 | Tower A - Sub Structure - B3 to B2 - Pour 9B | Complete | Core Wall RCC Works | 2022-11-30 | 2022-11-30 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2022-11-30 | 2022-11-30 | 2022-11-30 | 2022-11-30 | Tower A | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
43538 | Tower A - Sub Structure - B3 to B2 - Pour 8 | Complete | RCC Works - Slab | 2022-12-01 | 2022-12-02 | Slab & Staircase Casting | 100 | 100 |  | 2022-12-01 | 2022-12-01 | 2022-12-02 | 2022-12-02 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
43549 | Tower A - Sub Structure - B3 to B2 - Pour 9B | Complete | Core Wall RCC Works | 2022-12-01 | 2022-12-01 | Col/ Wall Casting | 100 | 100 |  | 2022-12-01 | 2022-12-01 | 2022-12-01 | 2022-12-01 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
43549 | Tower A - Sub Structure - B3 to B2 - Pour 9B | Complete | Core Wall RCC Works | 2022-12-01 | 2022-12-01 | Col/ Wall Casting | 100 | 100 |  | 2022-12-01 | 2022-12-01 | 2022-12-01 | 2022-12-01 | Tower A | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
40980 | Tower A - Foundation - Pour 7 | Complete | Raft RCC Works | 2022-12-02 | 2022-12-02 | Checking & casting | 100 | 100 |  | 2022-12-02 | 2022-12-02 | 2022-12-02 | 2022-12-02 | Tower A | Foundation |  | RCC Sub Structure | Raft RCC Works
43495 | Tower A - Sub Structure - B3 to B2 - Sec 6 (10 m) | Complete | Retaining Wall RCC Works | 2022-12-02 | 2022-12-05 | Fwk_Lift 1 RW | 100 | 100 |  | 2022-12-02 | 2022-12-02 | 2022-12-05 | 2022-12-05 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43519 | Tower A - Sub Structure - B3 to B2 - Pour 1B & 6 | Complete | Core Wall RCC Works | 2022-12-02 | 2022-12-07 | Col/ Wall Reinf. | 100 | 100 |  | 2022-12-02 | 2022-12-02 | 2022-12-07 | 2022-12-07 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
43519 | Tower A - Sub Structure - B3 to B2 - Pour 1B & 6 | Complete | Core Wall RCC Works | 2022-12-02 | 2022-12-07 | Col/ Wall Reinf. | 100 | 100 |  | 2022-12-02 | 2022-12-02 | 2022-12-07 | 2022-12-07 | Tower A | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
43521 | Tower A - Sub Structure - B3 to B2 - Pour 1B & 6 | Complete | Core Wall RCC Works | 2022-12-02 | 2022-12-13 | Col/ Wall Casting | 100 | 100 |  | 2022-12-02 | 2022-12-02 | 2022-12-13 | 2022-12-13 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
43521 | Tower A - Sub Structure - B3 to B2 - Pour 1B & 6 | Complete | Core Wall RCC Works | 2022-12-02 | 2022-12-13 | Col/ Wall Casting | 100 | 100 |  | 2022-12-02 | 2022-12-02 | 2022-12-13 | 2022-12-13 | Tower A | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
43560 |  | Complete |  | 2022-12-02 | 2022-12-26 | Pour 4_B3 to B2 | 100 | 100 |  | 2022-12-02 | 2022-12-02 | 2022-12-26 | 2022-12-26
43561 | Tower A - Sub Structure - B3 to B2 - Pour 4 | Complete | Core Wall RCC Works | 2022-12-02 | 2022-12-09 | Col/ Wall Reinf. | 100 | 100 |  | 2022-12-02 | 2022-12-02 | 2022-12-09 | 2022-12-09 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
43561 | Tower A - Sub Structure - B3 to B2 - Pour 4 | Complete | Core Wall RCC Works | 2022-12-02 | 2022-12-09 | Col/ Wall Reinf. | 100 | 100 |  | 2022-12-02 | 2022-12-02 | 2022-12-09 | 2022-12-09 | Tower A | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
43562 | Tower A - Sub Structure - B3 to B2 - Pour 4 | Complete | Core Wall RCC Works | 2022-12-02 | 2022-12-13 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2022-12-02 | 2022-12-02 | 2022-12-13 | 2022-12-13 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
43562 | Tower A - Sub Structure - B3 to B2 - Pour 4 | Complete | Core Wall RCC Works | 2022-12-02 | 2022-12-13 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2022-12-02 | 2022-12-02 | 2022-12-13 | 2022-12-13 | Tower A | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
43567 |  | Complete |  | 2022-12-02 | 2023-02-24 | B2 to B1 | 100 | 100 |  | 2022-12-02 | 2022-12-02 | 2023-02-24 | 2023-02-24
43567 |  | Complete |  | 2022-12-02 | 2023-02-24 | B2 to B1 | 100 | 100 |  | 2022-12-02 | 2022-12-02 | 2023-02-24 | 2023-02-24
43567 |  | Complete |  | 2022-12-02 | 2023-02-24 | B2 to B1 | 100 | 100 |  | 2022-12-02 | 2022-12-02 | 2023-02-24 | 2023-02-24
43668 |  | Complete |  | 2022-12-02 | 2022-12-26 | Pour 8_B2 to B1 | 100 | 100 |  | 2022-12-02 | 2022-12-02 | 2022-12-26 | 2022-12-26
43670 | Tower A - Sub Structure - B2 to B1 - Pour 8 | Complete | Core Wall RCC Works | 2022-12-02 | 2022-12-13 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2022-12-02 | 2022-12-02 | 2022-12-13 | 2022-12-13 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
43670 | Tower A - Sub Structure - B2 to B1 - Pour 8 | Complete | Core Wall RCC Works | 2022-12-02 | 2022-12-13 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2022-12-02 | 2022-12-02 | 2022-12-13 | 2022-12-13 | Tower A | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
40995 | Tower A - Foundation - Pour 5 | Complete | Raft RCC Works | 2022-12-03 | 2022-12-06 | Fwk fix | 100 | 100 |  | 2022-12-03 | 2022-12-03 | 2022-12-06 | 2022-12-06 | Tower A | Foundation |  | RCC Sub Structure | Raft RCC Works
43489 | Tower A - Sub Structure - B3 to B2 - Sec 2 (10 m) | Complete | Retaining Wall RCC Works | 2022-12-03 | 2022-12-06 | Fwk_Lift 2 RW | 100 | 100 |  | 2022-12-03 | 2022-12-03 | 2022-12-06 | 2022-12-06 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43550 | Tower A - Sub Structure - B3 to B2 - Pour 9B | Complete | RCC Works - Slab | 2022-12-03 | 2022-12-16 | Slab & Staircase Fwk. | 100 | 100 |  | 2022-12-03 | 2022-12-03 | 2022-12-16 | 2022-12-16 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
43669 | Tower A - Sub Structure - B2 to B1 - Pour 8 | Complete | Core Wall RCC Works | 2022-12-03 | 2022-12-09 | Col/ Wall Reinf. | 100 | 100 |  | 2022-12-03 | 2022-12-03 | 2022-12-09 | 2022-12-09 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
43669 | Tower A - Sub Structure - B2 to B1 - Pour 8 | Complete | Core Wall RCC Works | 2022-12-03 | 2022-12-09 | Col/ Wall Reinf. | 100 | 100 |  | 2022-12-03 | 2022-12-03 | 2022-12-09 | 2022-12-09 | Tower A | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
43522 | Tower A - Sub Structure - B3 to B2 - Pour 1B & 6 | Complete | RCC Works - Slab | 2022-12-05 | 2022-12-17 | Slab & Staircase Fwk. | 100 | 100 |  | 2022-12-05 | 2022-12-05 | 2022-12-17 | 2022-12-17 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
43563 | Tower A - Sub Structure - B3 to B2 - Pour 4 | Complete | Core Wall RCC Works | 2022-12-05 | 2022-12-15 | Col/ Wall Casting | 100 | 100 |  | 2022-12-05 | 2022-12-05 | 2022-12-15 | 2022-12-15 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
43563 | Tower A - Sub Structure - B3 to B2 - Pour 4 | Complete | Core Wall RCC Works | 2022-12-05 | 2022-12-15 | Col/ Wall Casting | 100 | 100 |  | 2022-12-05 | 2022-12-05 | 2022-12-15 | 2022-12-15 | Tower A | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
43671 | Tower A - Sub Structure - B2 to B1 - Pour 8 | Complete | Core Wall RCC Works | 2022-12-05 | 2022-12-15 | Col/ Wall Casting | 100 | 100 |  | 2022-12-05 | 2022-12-05 | 2022-12-15 | 2022-12-15 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
43671 | Tower A - Sub Structure - B2 to B1 - Pour 8 | Complete | Core Wall RCC Works | 2022-12-05 | 2022-12-15 | Col/ Wall Casting | 100 | 100 |  | 2022-12-05 | 2022-12-05 | 2022-12-15 | 2022-12-15 | Tower A | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
44285 |  | Started |  | 2022-12-05 | 2026-10-24 | CONSTRUCTION_NON TOWER AREA_ZONE 2 | 100 | 61 |  | 2022-12-05 | 2022-12-05 | 2027-03-26
44288 |  | Complete |  | 2022-12-05 | 2023-06-05 | Foundation (90 calendar days after Zone 1) | 100 | 100 |  | 2022-12-05 | 2022-12-05 | 2023-06-05 | 2023-06-05
44289 |  | Complete |  | 2022-12-05 | 2023-02-14 | Pour 1 | 100 | 100 |  | 2022-12-05 | 2022-12-05 | 2023-02-14 | 2023-02-14
44290 | NTA_Zone 2 - Foundation - Pour 1 | Complete | Foundation RCC Works | 2022-12-05 | 2022-12-08 | Dressing & PCC | 100 | 100 |  | 2022-12-05 | 2022-12-05 | 2022-12-08 | 2022-12-08 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44290 | NTA_Zone 2 - Foundation - Pour 1 | Complete | Foundation RCC Works | 2022-12-05 | 2022-12-08 | Dressing & PCC | 100 | 100 |  | 2022-12-05 | 2022-12-05 | 2022-12-08 | 2022-12-08 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44290 | NTA_Zone 2 - Foundation - Pour 1 | Complete | Foundation RCC Works | 2022-12-05 | 2022-12-08 | Dressing & PCC | 100 | 100 |  | 2022-12-05 | 2022-12-05 | 2022-12-08 | 2022-12-08 | NTA_Zone 2 | Foundation
40996 | Tower A - Foundation - Pour 5 | Complete | Raft RCC Works | 2022-12-06 | 2022-12-06 | Checking & casting | 100 | 100 |  | 2022-12-06 | 2022-12-06 | 2022-12-06 | 2022-12-06 | Tower A | Foundation |  | RCC Sub Structure | Raft RCC Works
43496 | Tower A - Sub Structure - B3 to B2 - Sec 6 (10 m) | Complete | Retaining Wall RCC Works | 2022-12-06 | 2022-12-06 | Checking & Casting_Lift 1 | 100 | 100 |  | 2022-12-06 | 2022-12-06 | 2022-12-06 | 2022-12-06 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43490 | Tower A - Sub Structure - B3 to B2 - Sec 2 (10 m) | Complete | Retaining Wall RCC Works | 2022-12-07 | 2022-12-07 | Checking & Casting_Lift 2 | 100 | 100 |  | 2022-12-07 | 2022-12-07 | 2022-12-07 | 2022-12-07 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43497 | Tower A - Sub Structure - B3 to B2 - Sec 6 (10 m) | Complete | Retaining Wall RCC Works | 2022-12-07 | 2022-12-09 | Retaining Wall_Reinf_Lift 2 | 100 | 100 |  | 2022-12-07 | 2022-12-07 | 2022-12-09 | 2022-12-09 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43564 | Tower A - Sub Structure - B3 to B2 - Pour 4 | Complete | RCC Works - Slab | 2022-12-07 | 2022-12-20 | Slab & Staircase Fwk. | 100 | 100 |  | 2022-12-07 | 2022-12-07 | 2022-12-20 | 2022-12-20 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
43672 | Tower A - Sub Structure - B2 to B1 - Pour 8 | Complete | RCC Works - Slab | 2022-12-07 | 2022-12-20 | Slab & Staircase Fwk. | 100 | 100 |  | 2022-12-07 | 2022-12-07 | 2022-12-20 | 2022-12-20 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
43544 | Tower A - Sub Structure - B3 to B2 - Pour 9A | Complete | RCC Works - Slab | 2022-12-08 | 2022-12-09 | Slab & Staircase Reinf. | 100 | 100 |  | 2022-12-08 | 2022-12-08 | 2022-12-09 | 2022-12-09 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
44291 | NTA_Zone 2 - Foundation - Pour 1 | Complete | Foundation RCC Works | 2022-12-09 | 2022-12-14 | Liner Wall | 100 | 100 |  | 2022-12-09 | 2022-12-09 | 2022-12-14 | 2022-12-14 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44291 | NTA_Zone 2 - Foundation - Pour 1 | Complete | Foundation RCC Works | 2022-12-09 | 2022-12-14 | Liner Wall | 100 | 100 |  | 2022-12-09 | 2022-12-09 | 2022-12-14 | 2022-12-14 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44291 | NTA_Zone 2 - Foundation - Pour 1 | Complete | Foundation RCC Works | 2022-12-09 | 2022-12-14 | Liner Wall | 100 | 100 |  | 2022-12-09 | 2022-12-09 | 2022-12-14 | 2022-12-14 | NTA_Zone 2 | Foundation
44292 | NTA_Zone 2 - Foundation - Pour 1 | Complete | Foundation RCC Works | 2022-12-09 | 2022-12-17 | Waterproofing Horizontal | 100 | 100 |  | 2022-12-09 | 2022-12-09 | 2022-12-17 | 2022-12-17 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44292 | NTA_Zone 2 - Foundation - Pour 1 | Complete | Foundation RCC Works | 2022-12-09 | 2022-12-17 | Waterproofing Horizontal | 100 | 100 |  | 2022-12-09 | 2022-12-09 | 2022-12-17 | 2022-12-17 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44292 | NTA_Zone 2 - Foundation - Pour 1 | Complete | Foundation RCC Works | 2022-12-09 | 2022-12-17 | Waterproofing Horizontal | 100 | 100 |  | 2022-12-09 | 2022-12-09 | 2022-12-17 | 2022-12-17 | NTA_Zone 2 | Foundation
44297 |  | Complete |  | 2022-12-09 | 2023-03-10 | Pour 2 | 100 | 100 |  | 2022-12-09 | 2022-12-09 | 2023-03-10 | 2023-03-10
44298 | NTA_Zone 2 - Foundation - Pour 2 | Complete | Foundation RCC Works | 2022-12-09 | 2022-12-13 | Dressing & PCC | 100 | 100 |  | 2022-12-09 | 2022-12-09 | 2022-12-13 | 2022-12-13 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44298 | NTA_Zone 2 - Foundation - Pour 2 | Complete | Foundation RCC Works | 2022-12-09 | 2022-12-13 | Dressing & PCC | 100 | 100 |  | 2022-12-09 | 2022-12-09 | 2022-12-13 | 2022-12-13 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44298 | NTA_Zone 2 - Foundation - Pour 2 | Complete | Foundation RCC Works | 2022-12-09 | 2022-12-13 | Dressing & PCC | 100 | 100 |  | 2022-12-09 | 2022-12-09 | 2022-12-13 | 2022-12-13 | NTA_Zone 2 | Foundation
44305 |  | Complete |  | 2022-12-09 | 2023-02-23 | Pour 3 | 100 | 100 |  | 2022-12-09 | 2022-12-09 | 2023-02-23 | 2023-02-23
44306 | NTA_Zone 2 - Foundation - Pour 3 | Complete | Foundation RCC Works | 2022-12-09 | 2022-12-12 | Dressing & PCC | 100 | 100 |  | 2022-12-09 | 2022-12-09 | 2022-12-12 | 2022-12-12 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44306 | NTA_Zone 2 - Foundation - Pour 3 | Complete | Foundation RCC Works | 2022-12-09 | 2022-12-12 | Dressing & PCC | 100 | 100 |  | 2022-12-09 | 2022-12-09 | 2022-12-12 | 2022-12-12 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44306 | NTA_Zone 2 - Foundation - Pour 3 | Complete | Foundation RCC Works | 2022-12-09 | 2022-12-12 | Dressing & PCC | 100 | 100 |  | 2022-12-09 | 2022-12-09 | 2022-12-12 | 2022-12-12 | NTA_Zone 2 | Foundation
43498 | Tower A - Sub Structure - B3 to B2 - Sec 6 (10 m) | Complete | Retaining Wall RCC Works | 2022-12-10 | 2022-12-13 | Fwk_Lift 2 RW | 100 | 100 |  | 2022-12-10 | 2022-12-10 | 2022-12-13 | 2022-12-13 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43500 |  | Complete |  | 2022-12-12 | 2023-01-06 | Core Wall B3-B2 | 100 | 100 |  | 2022-12-12 | 2022-12-12 | 2023-01-06 | 2023-01-06
43501 | Tower A - Sub Structure - B3 to B2 | Complete | Core Wall RCC Works | 2022-12-12 | 2022-12-28 | CW Reinf | 100 | 100 |  | 2022-12-12 | 2022-12-12 | 2022-12-28 | 2022-12-28 | Tower A | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
43504 |  | Complete |  | 2022-12-12 | 2023-01-09 | Pour 1A & 2_B3 to B2 | 100 | 100 |  | 2022-12-12 | 2022-12-12 | 2023-01-09 | 2023-01-09
43505 | Tower A - Sub Structure - B3 to B2 - Pour 1A & 2 | Complete | Core Wall RCC Works | 2022-12-12 | 2022-12-19 | Col/ Wall Reinf. | 100 | 100 |  | 2022-12-12 | 2022-12-12 | 2022-12-19 | 2022-12-19 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
43505 | Tower A - Sub Structure - B3 to B2 - Pour 1A & 2 | Complete | Core Wall RCC Works | 2022-12-12 | 2022-12-19 | Col/ Wall Reinf. | 100 | 100 |  | 2022-12-12 | 2022-12-12 | 2022-12-19 | 2022-12-19 | Tower A | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
43506 | Tower A - Sub Structure - B3 to B2 - Pour 1A & 2 | Complete | Core Wall RCC Works | 2022-12-12 | 2022-12-22 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2022-12-12 | 2022-12-12 | 2022-12-22 | 2022-12-22 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
43506 | Tower A - Sub Structure - B3 to B2 - Pour 1A & 2 | Complete | Core Wall RCC Works | 2022-12-12 | 2022-12-22 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2022-12-12 | 2022-12-12 | 2022-12-22 | 2022-12-22 | Tower A | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
44307 | NTA_Zone 2 - Foundation - Pour 3 | Complete | Foundation RCC Works | 2022-12-13 | 2022-12-17 | Waterproofing Horizontal | 100 | 100 |  | 2022-12-13 | 2022-12-13 | 2022-12-17 | 2022-12-17 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44307 | NTA_Zone 2 - Foundation - Pour 3 | Complete | Foundation RCC Works | 2022-12-13 | 2022-12-17 | Waterproofing Horizontal | 100 | 100 |  | 2022-12-13 | 2022-12-13 | 2022-12-17 | 2022-12-17 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44307 | NTA_Zone 2 - Foundation - Pour 3 | Complete | Foundation RCC Works | 2022-12-13 | 2022-12-17 | Waterproofing Horizontal | 100 | 100 |  | 2022-12-13 | 2022-12-13 | 2022-12-17 | 2022-12-17 | NTA_Zone 2 | Foundation
44318 |  | Complete |  | 2022-12-13 | 2023-06-05 | Pour 5 | 100 | 100 |  | 2022-12-13 | 2022-12-13 | 2023-06-05 | 2023-06-05
44319 | NTA_Zone 2 - Foundation - Pour 5 | Complete | Foundation RCC Works | 2022-12-13 | 2022-12-15 | Dressing & PCC | 100 | 100 |  | 2022-12-13 | 2022-12-13 | 2022-12-15 | 2022-12-15 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44319 | NTA_Zone 2 - Foundation - Pour 5 | Complete | Foundation RCC Works | 2022-12-13 | 2022-12-15 | Dressing & PCC | 100 | 100 |  | 2022-12-13 | 2022-12-13 | 2022-12-15 | 2022-12-15 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44319 | NTA_Zone 2 - Foundation - Pour 5 | Complete | Foundation RCC Works | 2022-12-13 | 2022-12-15 | Dressing & PCC | 100 | 100 |  | 2022-12-13 | 2022-12-13 | 2022-12-15 | 2022-12-15 | NTA_Zone 2 | Foundation
43499 | Tower A - Sub Structure - B3 to B2 - Sec 6 (10 m) | Complete | Retaining Wall RCC Works | 2022-12-14 | 2022-12-14 | Checking & Casting_Lift 2 | 100 | 100 |  | 2022-12-14 | 2022-12-14 | 2022-12-14 | 2022-12-14 | Tower A | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
43507 | Tower A - Sub Structure - B3 to B2 - Pour 1A & 2 | Complete | Core Wall RCC Works | 2022-12-14 | 2022-12-24 | Col/ Wall Casting | 100 | 100 |  | 2022-12-14 | 2022-12-14 | 2022-12-24 | 2022-12-24 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
43507 | Tower A - Sub Structure - B3 to B2 - Pour 1A & 2 | Complete | Core Wall RCC Works | 2022-12-14 | 2022-12-24 | Col/ Wall Casting | 100 | 100 |  | 2022-12-14 | 2022-12-14 | 2022-12-24 | 2022-12-24 | Tower A | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
43523 | Tower A - Sub Structure - B3 to B2 - Pour 1B & 6 | Complete | RCC Works - Slab | 2022-12-14 | 2022-12-21 | Slab & Staircase Reinf. | 100 | 100 |  | 2022-12-14 | 2022-12-14 | 2022-12-21 | 2022-12-21 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
44299 | NTA_Zone 2 - Foundation - Pour 2 | Complete | Foundation RCC Works | 2022-12-14 | 2022-12-14 | Liner Wall | 100 | 100 |  | 2022-12-14 | 2022-12-14 | 2022-12-14 | 2022-12-14 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44299 | NTA_Zone 2 - Foundation - Pour 2 | Complete | Foundation RCC Works | 2022-12-14 | 2022-12-14 | Liner Wall | 100 | 100 |  | 2022-12-14 | 2022-12-14 | 2022-12-14 | 2022-12-14 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44299 | NTA_Zone 2 - Foundation - Pour 2 | Complete | Foundation RCC Works | 2022-12-14 | 2022-12-14 | Liner Wall | 100 | 100 |  | 2022-12-14 | 2022-12-14 | 2022-12-14 | 2022-12-14 | NTA_Zone 2 | Foundation
44300 | NTA_Zone 2 - Foundation - Pour 2 | Complete | Foundation RCC Works | 2022-12-14 | 2022-12-22 | Waterproofing Horizontal | 100 | 100 |  | 2022-12-14 | 2022-12-14 | 2022-12-22 | 2022-12-22 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44300 | NTA_Zone 2 - Foundation - Pour 2 | Complete | Foundation RCC Works | 2022-12-14 | 2022-12-22 | Waterproofing Horizontal | 100 | 100 |  | 2022-12-14 | 2022-12-14 | 2022-12-22 | 2022-12-22 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44300 | NTA_Zone 2 - Foundation - Pour 2 | Complete | Foundation RCC Works | 2022-12-14 | 2022-12-22 | Waterproofing Horizontal | 100 | 100 |  | 2022-12-14 | 2022-12-14 | 2022-12-22 | 2022-12-22 | NTA_Zone 2 | Foundation
44310 |  | Complete |  | 2022-12-14 | 2023-03-06 | Pour 4 | 100 | 100 |  | 2022-12-14 | 2022-12-14 | 2023-03-06 | 2023-03-06
44311 | NTA_Zone 2 - Foundation - Pour 4 | Complete | Foundation RCC Works | 2022-12-14 | 2022-12-16 | Dressing & PCC | 100 | 100 |  | 2022-12-14 | 2022-12-14 | 2022-12-16 | 2022-12-16 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44311 | NTA_Zone 2 - Foundation - Pour 4 | Complete | Foundation RCC Works | 2022-12-14 | 2022-12-16 | Dressing & PCC | 100 | 100 |  | 2022-12-14 | 2022-12-14 | 2022-12-16 | 2022-12-16 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44311 | NTA_Zone 2 - Foundation - Pour 4 | Complete | Foundation RCC Works | 2022-12-14 | 2022-12-16 | Dressing & PCC | 100 | 100 |  | 2022-12-14 | 2022-12-14 | 2022-12-16 | 2022-12-16 | NTA_Zone 2 | Foundation
43545 | Tower A - Sub Structure - B3 to B2 - Pour 9A | Complete | RCC Works - Slab | 2022-12-15 | 2022-12-16 | Slab & Staircase Casting | 100 | 100 |  | 2022-12-15 | 2022-12-15 | 2022-12-16 | 2022-12-16 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
44293 | NTA_Zone 2 - Foundation - Pour 1 | Complete | Foundation RCC Works | 2022-12-15 | 2022-12-17 | Waterproofing vertical - toe ht. | 100 | 100 |  | 2022-12-15 | 2022-12-15 | 2022-12-17 | 2022-12-17 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44293 | NTA_Zone 2 - Foundation - Pour 1 | Complete | Foundation RCC Works | 2022-12-15 | 2022-12-17 | Waterproofing vertical - toe ht. | 100 | 100 |  | 2022-12-15 | 2022-12-15 | 2022-12-17 | 2022-12-17 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44293 | NTA_Zone 2 - Foundation - Pour 1 | Complete | Foundation RCC Works | 2022-12-15 | 2022-12-17 | Waterproofing vertical - toe ht. | 100 | 100 |  | 2022-12-15 | 2022-12-15 | 2022-12-17 | 2022-12-17 | NTA_Zone 2 | Foundation
44301 | NTA_Zone 2 - Foundation - Pour 2 | Complete | Foundation RCC Works | 2022-12-15 | 2022-12-20 | Waterproofing vertical - toe ht. | 100 | 100 |  | 2022-12-15 | 2022-12-15 | 2022-12-20 | 2022-12-20 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44301 | NTA_Zone 2 - Foundation - Pour 2 | Complete | Foundation RCC Works | 2022-12-15 | 2022-12-20 | Waterproofing vertical - toe ht. | 100 | 100 |  | 2022-12-15 | 2022-12-15 | 2022-12-20 | 2022-12-20 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44301 | NTA_Zone 2 - Foundation - Pour 2 | Complete | Foundation RCC Works | 2022-12-15 | 2022-12-20 | Waterproofing vertical - toe ht. | 100 | 100 |  | 2022-12-15 | 2022-12-15 | 2022-12-20 | 2022-12-20 | NTA_Zone 2 | Foundation
43508 | Tower A - Sub Structure - B3 to B2 - Pour 1A & 2 | Complete | RCC Works - Slab | 2022-12-16 | 2022-12-29 | Slab & Staircase Fwk. | 100 | 100 |  | 2022-12-16 | 2022-12-16 | 2022-12-29 | 2022-12-29 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
43525 |  | Complete |  | 2022-12-16 | 2023-01-09 | Pour 7_B3 to B2 | 100 | 100 |  | 2022-12-16 | 2022-12-16 | 2023-01-09 | 2023-01-09
43527 | Tower A - Sub Structure - B3 to B2 - Pour 7 | Complete | Core Wall RCC Works | 2022-12-16 | 2022-12-27 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2022-12-16 | 2022-12-16 | 2022-12-27 | 2022-12-27 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
43527 | Tower A - Sub Structure - B3 to B2 - Pour 7 | Complete | Core Wall RCC Works | 2022-12-16 | 2022-12-27 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2022-12-16 | 2022-12-16 | 2022-12-27 | 2022-12-27 | Tower A | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
44320 | NTA_Zone 2 - Foundation - Pour 5 | Complete | Foundation RCC Works | 2022-12-16 | 2022-12-21 | Waterproofing Horizontal | 100 | 100 |  | 2022-12-16 | 2022-12-16 | 2022-12-21 | 2022-12-21 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44320 | NTA_Zone 2 - Foundation - Pour 5 | Complete | Foundation RCC Works | 2022-12-16 | 2022-12-21 | Waterproofing Horizontal | 100 | 100 |  | 2022-12-16 | 2022-12-16 | 2022-12-21 | 2022-12-21 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44320 | NTA_Zone 2 - Foundation - Pour 5 | Complete | Foundation RCC Works | 2022-12-16 | 2022-12-21 | Waterproofing Horizontal | 100 | 100 |  | 2022-12-16 | 2022-12-16 | 2022-12-21 | 2022-12-21 | NTA_Zone 2 | Foundation
44323 |  | Complete |  | 2022-12-16 | 2023-04-10 | Pour 6 | 100 | 100 |  | 2022-12-16 | 2022-12-16 | 2023-04-10 | 2023-04-10
44324 | NTA_Zone 2 - Foundation - Pour 6 | Complete | Foundation RCC Works | 2022-12-16 | 2022-12-19 | Dressing & PCC | 100 | 100 |  | 2022-12-16 | 2022-12-16 | 2022-12-19 | 2022-12-19 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44324 | NTA_Zone 2 - Foundation - Pour 6 | Complete | Foundation RCC Works | 2022-12-16 | 2022-12-19 | Dressing & PCC | 100 | 100 |  | 2022-12-16 | 2022-12-16 | 2022-12-19 | 2022-12-19 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44324 | NTA_Zone 2 - Foundation - Pour 6 | Complete | Foundation RCC Works | 2022-12-16 | 2022-12-19 | Dressing & PCC | 100 | 100 |  | 2022-12-16 | 2022-12-16 | 2022-12-19 | 2022-12-19 | NTA_Zone 2 | Foundation
43551 | Tower A - Sub Structure - B3 to B2 - Pour 9B | Complete | RCC Works - Slab | 2022-12-17 | 2022-12-19 | Slab & Staircase Reinf. | 100 | 100 |  | 2022-12-17 | 2022-12-17 | 2022-12-19 | 2022-12-19 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
43675 |  | Complete |  | 2022-12-17 | 2023-02-06 | Pour 9A_B2 to B1 | 100 | 100 |  | 2022-12-17 | 2022-12-17 | 2023-02-06 | 2023-02-06
43676 | Tower A - Sub Structure - B2 to B1 - Pour 9A | Complete | Core Wall RCC Works | 2022-12-17 | 2022-12-17 | Col/ Wall Reinf. | 100 | 100 |  | 2022-12-17 | 2022-12-17 | 2022-12-17 | 2022-12-17 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
43676 | Tower A - Sub Structure - B2 to B1 - Pour 9A | Complete | Core Wall RCC Works | 2022-12-17 | 2022-12-17 | Col/ Wall Reinf. | 100 | 100 |  | 2022-12-17 | 2022-12-17 | 2022-12-17 | 2022-12-17 | Tower A | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
43677 | Tower A - Sub Structure - B2 to B1 - Pour 9A | Complete | Core Wall RCC Works | 2022-12-17 | 2022-12-17 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2022-12-17 | 2022-12-17 | 2022-12-17 | 2022-12-17 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
43677 | Tower A - Sub Structure - B2 to B1 - Pour 9A | Complete | Core Wall RCC Works | 2022-12-17 | 2022-12-17 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2022-12-17 | 2022-12-17 | 2022-12-17 | 2022-12-17 | Tower A | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
43678 | Tower A - Sub Structure - B2 to B1 - Pour 9A | Complete | Core Wall RCC Works | 2022-12-17 | 2022-12-17 | Col/ Wall Casting | 100 | 100 |  | 2022-12-17 | 2022-12-17 | 2022-12-17 | 2022-12-17 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
43678 | Tower A - Sub Structure - B2 to B1 - Pour 9A | Complete | Core Wall RCC Works | 2022-12-17 | 2022-12-17 | Col/ Wall Casting | 100 | 100 |  | 2022-12-17 | 2022-12-17 | 2022-12-17 | 2022-12-17 | Tower A | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
44312 | NTA_Zone 2 - Foundation - Pour 4 | Complete | Foundation RCC Works | 2022-12-17 | 2022-12-22 | Liner Wall | 100 | 100 |  | 2022-12-17 | 2022-12-17 | 2022-12-22 | 2022-12-22 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44312 | NTA_Zone 2 - Foundation - Pour 4 | Complete | Foundation RCC Works | 2022-12-17 | 2022-12-22 | Liner Wall | 100 | 100 |  | 2022-12-17 | 2022-12-17 | 2022-12-22 | 2022-12-22 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44312 | NTA_Zone 2 - Foundation - Pour 4 | Complete | Foundation RCC Works | 2022-12-17 | 2022-12-22 | Liner Wall | 100 | 100 |  | 2022-12-17 | 2022-12-17 | 2022-12-22 | 2022-12-22 | NTA_Zone 2 | Foundation
44313 | NTA_Zone 2 - Foundation - Pour 4 | Complete | Foundation RCC Works | 2022-12-17 | 2022-12-22 | Waterproofing Horizontal | 100 | 100 |  | 2022-12-17 | 2022-12-17 | 2022-12-22 | 2022-12-22 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44313 | NTA_Zone 2 - Foundation - Pour 4 | Complete | Foundation RCC Works | 2022-12-17 | 2022-12-22 | Waterproofing Horizontal | 100 | 100 |  | 2022-12-17 | 2022-12-17 | 2022-12-22 | 2022-12-22 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44313 | NTA_Zone 2 - Foundation - Pour 4 | Complete | Foundation RCC Works | 2022-12-17 | 2022-12-22 | Waterproofing Horizontal | 100 | 100 |  | 2022-12-17 | 2022-12-17 | 2022-12-22 | 2022-12-22 | NTA_Zone 2 | Foundation
43528 | Tower A - Sub Structure - B3 to B2 - Pour 7 | Complete | Core Wall RCC Works | 2022-12-19 | 2022-12-29 | Col/ Wall Casting | 100 | 100 |  | 2022-12-19 | 2022-12-19 | 2022-12-29 | 2022-12-29 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
43528 | Tower A - Sub Structure - B3 to B2 - Pour 7 | Complete | Core Wall RCC Works | 2022-12-19 | 2022-12-29 | Col/ Wall Casting | 100 | 100 |  | 2022-12-19 | 2022-12-19 | 2022-12-29 | 2022-12-29 | Tower A | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
44294 | NTA_Zone 2 - Foundation - Pour 1 | Complete | Foundation RCC Works | 2022-12-19 | 2022-12-19 | RW toe foundation | 100 | 100 |  | 2022-12-19 | 2022-12-19 | 2022-12-19 | 2022-12-19 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44294 | NTA_Zone 2 - Foundation - Pour 1 | Complete | Foundation RCC Works | 2022-12-19 | 2022-12-19 | RW toe foundation | 100 | 100 |  | 2022-12-19 | 2022-12-19 | 2022-12-19 | 2022-12-19 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44294 | NTA_Zone 2 - Foundation - Pour 1 | Complete | Foundation RCC Works | 2022-12-19 | 2022-12-19 | RW toe foundation | 100 | 100 |  | 2022-12-19 | 2022-12-19 | 2022-12-19 | 2022-12-19 | NTA_Zone 2 | Foundation
44295 | NTA_Zone 2 - Foundation - Pour 1 | Complete | Foundation RCC Works | 2022-12-19 | 2023-01-28 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2022-12-19 | 2022-12-19 | 2023-01-28 | 2023-01-28 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44295 | NTA_Zone 2 - Foundation - Pour 1 | Complete | Foundation RCC Works | 2022-12-19 | 2023-01-28 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2022-12-19 | 2022-12-19 | 2023-01-28 | 2023-01-28 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44295 | NTA_Zone 2 - Foundation - Pour 1 | Complete | Foundation RCC Works | 2022-12-19 | 2023-01-28 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2022-12-19 | 2022-12-19 | 2023-01-28 | 2023-01-28 | NTA_Zone 2 | Foundation
43552 | Tower A - Sub Structure - B3 to B2 - Pour 9B | Complete | RCC Works - Slab | 2022-12-20 | 2022-12-21 | Slab & Staircase Casting | 100 | 100 |  | 2022-12-20 | 2022-12-20 | 2022-12-21 | 2022-12-21 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
43565 | Tower A - Sub Structure - B3 to B2 - Pour 4 | Complete | RCC Works - Slab | 2022-12-20 | 2022-12-23 | Slab & Staircase Reinf. | 100 | 100 |  | 2022-12-20 | 2022-12-20 | 2022-12-23 | 2022-12-23 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
43673 | Tower A - Sub Structure - B2 to B1 - Pour 8 | Complete | RCC Works - Slab | 2022-12-20 | 2022-12-23 | Slab & Staircase Reinf. | 100 | 100 |  | 2022-12-20 | 2022-12-20 | 2022-12-23 | 2022-12-23 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
43679 | Tower A - Sub Structure - B2 to B1 - Pour 9A | Complete | RCC Works - Slab | 2022-12-20 | 2023-01-02 | Slab & Staircase Fwk. | 100 | 100 |  | 2022-12-20 | 2022-12-20 | 2023-01-02 | 2023-01-02 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
44325 | NTA_Zone 2 - Foundation - Pour 6 | Complete | Foundation RCC Works | 2022-12-20 | 2022-12-24 | Liner Wall | 100 | 100 |  | 2022-12-20 | 2022-12-20 | 2022-12-24 | 2022-12-24 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44325 | NTA_Zone 2 - Foundation - Pour 6 | Complete | Foundation RCC Works | 2022-12-20 | 2022-12-24 | Liner Wall | 100 | 100 |  | 2022-12-20 | 2022-12-20 | 2022-12-24 | 2022-12-24 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44325 | NTA_Zone 2 - Foundation - Pour 6 | Complete | Foundation RCC Works | 2022-12-20 | 2022-12-24 | Liner Wall | 100 | 100 |  | 2022-12-20 | 2022-12-20 | 2022-12-24 | 2022-12-24 | NTA_Zone 2 | Foundation
44326 | NTA_Zone 2 - Foundation - Pour 6 | Complete | Foundation RCC Works | 2022-12-20 | 2022-12-24 | Waterproofing Horizontal | 100 | 100 |  | 2022-12-20 | 2022-12-20 | 2022-12-24 | 2022-12-24 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44326 | NTA_Zone 2 - Foundation - Pour 6 | Complete | Foundation RCC Works | 2022-12-20 | 2022-12-24 | Waterproofing Horizontal | 100 | 100 |  | 2022-12-20 | 2022-12-20 | 2022-12-24 | 2022-12-24 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44326 | NTA_Zone 2 - Foundation - Pour 6 | Complete | Foundation RCC Works | 2022-12-20 | 2022-12-24 | Waterproofing Horizontal | 100 | 100 |  | 2022-12-20 | 2022-12-20 | 2022-12-24 | 2022-12-24 | NTA_Zone 2 | Foundation
44331 |  | Complete |  | 2022-12-20 | 2023-11-29 | Sub-Structure_NTA Zone 2 | 100 | 100 |  | 2022-12-20 | 2022-12-20 | 2023-11-29 | 2023-11-29
44332 |  | Complete |  | 2022-12-20 | 2023-07-27 | B3 to B2 | 100 | 100 |  | 2022-12-20 | 2022-12-20 | 2023-07-27 | 2023-07-27
44332 |  | Complete |  | 2022-12-20 | 2023-07-27 | B3 to B2 | 100 | 100 |  | 2022-12-20 | 2022-12-20 | 2023-07-27 | 2023-07-27
44332 |  | Complete |  | 2022-12-20 | 2023-07-27 | B3 to B2 | 100 | 100 |  | 2022-12-20 | 2022-12-20 | 2023-07-27 | 2023-07-27
44351 |  | Complete |  | 2022-12-20 | 2023-02-09 | Retaining Wall_lift 1 (Grid PA-04 to PB-N) | 100 | 100 |  | 2022-12-20 | 2022-12-20 | 2023-02-09 | 2023-02-09
44352 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2022-12-20 | 2022-12-27 | Section 1_lift 1 | 100 | 100 |  | 2022-12-20 | 2022-12-20 | 2022-12-27 | 2022-12-27 | NTA_Zone 2 | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
44352 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2022-12-20 | 2022-12-27 | Section 1_lift 1 | 100 | 100 |  | 2022-12-20 | 2022-12-20 | 2022-12-27 | 2022-12-27 | NTA_Zone 2 | Sub Structure | B3
43526 | Tower A - Sub Structure - B3 to B2 - Pour 7 | Complete | Core Wall RCC Works | 2022-12-21 | 2022-12-23 | Col/ Wall Reinf. | 100 | 100 |  | 2022-12-21 | 2022-12-21 | 2022-12-23 | 2022-12-23 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
43526 | Tower A - Sub Structure - B3 to B2 - Pour 7 | Complete | Core Wall RCC Works | 2022-12-21 | 2022-12-23 | Col/ Wall Reinf. | 100 | 100 |  | 2022-12-21 | 2022-12-21 | 2022-12-23 | 2022-12-23 | Tower A | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
43529 | Tower A - Sub Structure - B3 to B2 - Pour 7 | Complete | RCC Works - Slab | 2022-12-21 | 2023-01-03 | Slab & Staircase Fwk. | 100 | 100 |  | 2022-12-21 | 2022-12-21 | 2023-01-03 | 2023-01-03 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
44302 | NTA_Zone 2 - Foundation - Pour 2 | Complete | Foundation RCC Works | 2022-12-21 | 2022-12-29 | RW toe foundation | 100 | 100 |  | 2022-12-21 | 2022-12-21 | 2022-12-29 | 2022-12-29 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44302 | NTA_Zone 2 - Foundation - Pour 2 | Complete | Foundation RCC Works | 2022-12-21 | 2022-12-29 | RW toe foundation | 100 | 100 |  | 2022-12-21 | 2022-12-21 | 2022-12-29 | 2022-12-29 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44302 | NTA_Zone 2 - Foundation - Pour 2 | Complete | Foundation RCC Works | 2022-12-21 | 2022-12-29 | RW toe foundation | 100 | 100 |  | 2022-12-21 | 2022-12-21 | 2022-12-29 | 2022-12-29 | NTA_Zone 2 | Foundation
43682 |  | Complete |  | 2022-12-22 | 2023-02-09 | Pour 9B_B2 to B1 | 100 | 100 |  | 2022-12-22 | 2022-12-22 | 2023-02-09 | 2023-02-09
43683 | Tower A - Sub Structure - B2 to B1 - Pour 9B | Complete | Core Wall RCC Works | 2022-12-22 | 2022-12-22 | Col/ Wall Reinf. | 100 | 100 |  | 2022-12-22 | 2022-12-22 | 2022-12-22 | 2022-12-22 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
43683 | Tower A - Sub Structure - B2 to B1 - Pour 9B | Complete | Core Wall RCC Works | 2022-12-22 | 2022-12-22 | Col/ Wall Reinf. | 100 | 100 |  | 2022-12-22 | 2022-12-22 | 2022-12-22 | 2022-12-22 | Tower A | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
43684 | Tower A - Sub Structure - B2 to B1 - Pour 9B | Complete | Core Wall RCC Works | 2022-12-22 | 2022-12-22 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2022-12-22 | 2022-12-22 | 2022-12-22 | 2022-12-22 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
43684 | Tower A - Sub Structure - B2 to B1 - Pour 9B | Complete | Core Wall RCC Works | 2022-12-22 | 2022-12-22 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2022-12-22 | 2022-12-22 | 2022-12-22 | 2022-12-22 | Tower A | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
43685 | Tower A - Sub Structure - B2 to B1 - Pour 9B | Complete | Core Wall RCC Works | 2022-12-22 | 2022-12-22 | Col/ Wall Casting | 100 | 100 |  | 2022-12-22 | 2022-12-22 | 2022-12-22 | 2022-12-22 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
43685 | Tower A - Sub Structure - B2 to B1 - Pour 9B | Complete | Core Wall RCC Works | 2022-12-22 | 2022-12-22 | Col/ Wall Casting | 100 | 100 |  | 2022-12-22 | 2022-12-22 | 2022-12-22 | 2022-12-22 | Tower A | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
43502 | Tower A - Sub Structure - B3 to B2 | Complete | Core Wall RCC Works | 2022-12-23 | 2023-01-03 | CW Fwk (3.5m lift) | 100 | 100 |  | 2022-12-23 | 2022-12-23 | 2023-01-03 | 2023-01-03 | Tower A | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
44303 | NTA_Zone 2 - Foundation - Pour 2 | Complete | Foundation RCC Works | 2022-12-23 | 2023-02-16 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2022-12-23 | 2022-12-23 | 2023-02-16 | 2023-02-16 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44303 | NTA_Zone 2 - Foundation - Pour 2 | Complete | Foundation RCC Works | 2022-12-23 | 2023-02-16 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2022-12-23 | 2022-12-23 | 2023-02-16 | 2023-02-16 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44303 | NTA_Zone 2 - Foundation - Pour 2 | Complete | Foundation RCC Works | 2022-12-23 | 2023-02-16 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2022-12-23 | 2022-12-23 | 2023-02-16 | 2023-02-16 | NTA_Zone 2 | Foundation
44314 | NTA_Zone 2 - Foundation - Pour 4 | Complete | Foundation RCC Works | 2022-12-23 | 2022-12-24 | Waterproofing vertical - toe ht. | 100 | 100 |  | 2022-12-23 | 2022-12-23 | 2022-12-24 | 2022-12-24 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44314 | NTA_Zone 2 - Foundation - Pour 4 | Complete | Foundation RCC Works | 2022-12-23 | 2022-12-24 | Waterproofing vertical - toe ht. | 100 | 100 |  | 2022-12-23 | 2022-12-23 | 2022-12-24 | 2022-12-24 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44314 | NTA_Zone 2 - Foundation - Pour 4 | Complete | Foundation RCC Works | 2022-12-23 | 2022-12-24 | Waterproofing vertical - toe ht. | 100 | 100 |  | 2022-12-23 | 2022-12-23 | 2022-12-24 | 2022-12-24 | NTA_Zone 2 | Foundation
43553 |  | Complete |  | 2022-12-24 | 2023-01-17 | Pour 5_B3 to B2 | 100 | 100 |  | 2022-12-24 | 2022-12-24 | 2023-01-17 | 2023-01-17
43554 | Tower A - Sub Structure - B3 to B2 - Pour 5 | Complete | Core Wall RCC Works | 2022-12-24 | 2022-12-31 | Col/ Wall Reinf. | 100 | 100 |  | 2022-12-24 | 2022-12-24 | 2022-12-31 | 2022-12-31 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
43554 | Tower A - Sub Structure - B3 to B2 - Pour 5 | Complete | Core Wall RCC Works | 2022-12-24 | 2022-12-31 | Col/ Wall Reinf. | 100 | 100 |  | 2022-12-24 | 2022-12-24 | 2022-12-31 | 2022-12-31 | Tower A | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
43555 | Tower A - Sub Structure - B3 to B2 - Pour 5 | Complete | Core Wall RCC Works | 2022-12-24 | 2023-01-04 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2022-12-24 | 2022-12-24 | 2023-01-04 | 2023-01-04 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
43555 | Tower A - Sub Structure - B3 to B2 - Pour 5 | Complete | Core Wall RCC Works | 2022-12-24 | 2023-01-04 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2022-12-24 | 2022-12-24 | 2023-01-04 | 2023-01-04 | Tower A | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
43566 | Tower A - Sub Structure - B3 to B2 - Pour 4 | Complete | RCC Works - Slab | 2022-12-24 | 2022-12-26 | Slab & Staircase Casting | 100 | 100 |  | 2022-12-24 | 2022-12-24 | 2022-12-26 | 2022-12-26 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
43674 | Tower A - Sub Structure - B2 to B1 - Pour 8 | Complete | RCC Works - Slab | 2022-12-24 | 2022-12-26 | Slab & Staircase Casting | 100 | 100 |  | 2022-12-24 | 2022-12-24 | 2022-12-26 | 2022-12-26 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
43686 | Tower A - Sub Structure - B2 to B1 - Pour 9B | Complete | RCC Works - Slab | 2022-12-24 | 2023-01-06 | Slab & Staircase Fwk. | 100 | 100 |  | 2022-12-24 | 2022-12-24 | 2023-01-06 | 2023-01-06 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
43703 |  | Complete |  | 2022-12-26 | 2023-05-06 | B1 to GF | 100 | 100 |  | 2022-12-26 | 2022-12-26 | 2023-05-06 | 2023-05-06
43703 |  | Complete |  | 2022-12-26 | 2023-05-06 | B1 to GF | 100 | 100 |  | 2022-12-26 | 2022-12-26 | 2023-05-06 | 2023-05-06
43703 |  | Complete |  | 2022-12-26 | 2023-05-06 | B1 to GF | 100 | 100 |  | 2022-12-26 | 2022-12-26 | 2023-05-06 | 2023-05-06
43863 |  | Complete |  | 2022-12-26 | 2023-02-06 | Pour 8_B1 to GF | 100 | 100 |  | 2022-12-26 | 2022-12-26 | 2023-02-06 | 2023-02-06
43865 | Tower A - Sub Structure - B1 to GF - Pour 8 | Complete | Core Wall RCC Works | 2022-12-26 | 2023-01-05 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2022-12-26 | 2022-12-26 | 2023-01-05 | 2023-01-05 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43865 | Tower A - Sub Structure - B1 to GF - Pour 8 | Complete | Core Wall RCC Works | 2022-12-26 | 2023-01-05 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2022-12-26 | 2022-12-26 | 2023-01-05 | 2023-01-05 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44315 | NTA_Zone 2 - Foundation - Pour 4 | Complete | Foundation RCC Works | 2022-12-26 | 2022-12-30 | RW toe foundation | 100 | 100 |  | 2022-12-26 | 2022-12-26 | 2022-12-30 | 2022-12-30 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44315 | NTA_Zone 2 - Foundation - Pour 4 | Complete | Foundation RCC Works | 2022-12-26 | 2022-12-30 | RW toe foundation | 100 | 100 |  | 2022-12-26 | 2022-12-26 | 2022-12-30 | 2022-12-30 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44315 | NTA_Zone 2 - Foundation - Pour 4 | Complete | Foundation RCC Works | 2022-12-26 | 2022-12-30 | RW toe foundation | 100 | 100 |  | 2022-12-26 | 2022-12-26 | 2022-12-30 | 2022-12-30 | NTA_Zone 2 | Foundation
44327 | NTA_Zone 2 - Foundation - Pour 6 | Complete | Foundation RCC Works | 2022-12-26 | 2022-12-27 | Waterproofing vertical - toe ht. | 100 | 100 |  | 2022-12-26 | 2022-12-26 | 2022-12-27 | 2022-12-27 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44327 | NTA_Zone 2 - Foundation - Pour 6 | Complete | Foundation RCC Works | 2022-12-26 | 2022-12-27 | Waterproofing vertical - toe ht. | 100 | 100 |  | 2022-12-26 | 2022-12-26 | 2022-12-27 | 2022-12-27 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44327 | NTA_Zone 2 - Foundation - Pour 6 | Complete | Foundation RCC Works | 2022-12-26 | 2022-12-27 | Waterproofing vertical - toe ht. | 100 | 100 |  | 2022-12-26 | 2022-12-26 | 2022-12-27 | 2022-12-27 | NTA_Zone 2 | Foundation
43556 | Tower A - Sub Structure - B3 to B2 - Pour 5 | Complete | Core Wall RCC Works | 2022-12-27 | 2023-01-06 | Col/ Wall Casting | 100 | 100 |  | 2022-12-27 | 2022-12-27 | 2023-01-06 | 2023-01-06 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
43556 | Tower A - Sub Structure - B3 to B2 - Pour 5 | Complete | Core Wall RCC Works | 2022-12-27 | 2023-01-06 | Col/ Wall Casting | 100 | 100 |  | 2022-12-27 | 2022-12-27 | 2023-01-06 | 2023-01-06 | Tower A | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
43696 |  | Complete |  | 2022-12-27 | 2023-01-19 | Pour 4_B2 to B1 | 100 | 100 |  | 2022-12-27 | 2022-12-27 | 2023-01-19 | 2023-01-19
43697 | Tower A - Sub Structure - B2 to B1 - Pour 4 | Complete | Core Wall RCC Works | 2022-12-27 | 2023-01-03 | Col/ Wall Reinf. | 100 | 100 |  | 2022-12-27 | 2022-12-27 | 2023-01-03 | 2023-01-03 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
43697 | Tower A - Sub Structure - B2 to B1 - Pour 4 | Complete | Core Wall RCC Works | 2022-12-27 | 2023-01-03 | Col/ Wall Reinf. | 100 | 100 |  | 2022-12-27 | 2022-12-27 | 2023-01-03 | 2023-01-03 | Tower A | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
43698 | Tower A - Sub Structure - B2 to B1 - Pour 4 | Complete | Core Wall RCC Works | 2022-12-27 | 2023-01-06 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2022-12-27 | 2022-12-27 | 2023-01-06 | 2023-01-06 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
43698 | Tower A - Sub Structure - B2 to B1 - Pour 4 | Complete | Core Wall RCC Works | 2022-12-27 | 2023-01-06 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2022-12-27 | 2022-12-27 | 2023-01-06 | 2023-01-06 | Tower A | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
43864 | Tower A - Sub Structure - B1 to GF - Pour 8 | Complete | Core Wall RCC Works | 2022-12-27 | 2023-01-02 | Col/ Wall Reinf. | 100 | 100 |  | 2022-12-27 | 2022-12-27 | 2023-01-02 | 2023-01-02 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43864 | Tower A - Sub Structure - B1 to GF - Pour 8 | Complete | Core Wall RCC Works | 2022-12-27 | 2023-01-02 | Col/ Wall Reinf. | 100 | 100 |  | 2022-12-27 | 2022-12-27 | 2023-01-02 | 2023-01-02 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43866 | Tower A - Sub Structure - B1 to GF - Pour 8 | Complete | Core Wall RCC Works | 2022-12-28 | 2023-01-07 | Col/ Wall Casting | 100 | 100 |  | 2022-12-28 | 2022-12-28 | 2023-01-07 | 2023-01-07 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43866 | Tower A - Sub Structure - B1 to GF - Pour 8 | Complete | Core Wall RCC Works | 2022-12-28 | 2023-01-07 | Col/ Wall Casting | 100 | 100 |  | 2022-12-28 | 2022-12-28 | 2023-01-07 | 2023-01-07 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44328 | NTA_Zone 2 - Foundation - Pour 6 | Complete | Foundation RCC Works | 2022-12-28 | 2023-01-02 | RW toe foundation | 100 | 100 |  | 2022-12-28 | 2022-12-28 | 2023-01-02 | 2023-01-02 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44328 | NTA_Zone 2 - Foundation - Pour 6 | Complete | Foundation RCC Works | 2022-12-28 | 2023-01-02 | RW toe foundation | 100 | 100 |  | 2022-12-28 | 2022-12-28 | 2023-01-02 | 2023-01-02 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44328 | NTA_Zone 2 - Foundation - Pour 6 | Complete | Foundation RCC Works | 2022-12-28 | 2023-01-02 | RW toe foundation | 100 | 100 |  | 2022-12-28 | 2022-12-28 | 2023-01-02 | 2023-01-02 | NTA_Zone 2 | Foundation
44353 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2022-12-28 | 2023-01-04 | Section 2_lift 1 | 100 | 100 |  | 2022-12-28 | 2022-12-28 | 2023-01-04 | 2023-01-04 | NTA_Zone 2 | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
44353 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2022-12-28 | 2023-01-04 | Section 2_lift 1 | 100 | 100 |  | 2022-12-28 | 2022-12-28 | 2023-01-04 | 2023-01-04 | NTA_Zone 2 | Sub Structure | B3
44363 |  | Complete |  | 2022-12-28 | 2023-02-17 | Retaining Wall_lift 2 | 100 | 100 |  | 2022-12-28 | 2022-12-28 | 2023-02-17 | 2023-02-17
44363 |  | Complete |  | 2022-12-28 | 2023-02-17 | Retaining Wall_lift 2 | 100 | 100 |  | 2022-12-28 | 2022-12-28 | 2023-02-17 | 2023-02-17 |  |  |  | RCC Super Structure | Retaining Wall RCC Works
44364 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2022-12-28 | 2023-01-04 | Section 1_lift 2 | 100 | 100 |  | 2022-12-28 | 2022-12-28 | 2023-01-04 | 2023-01-04 | NTA_Zone 2 | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
44364 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2022-12-28 | 2023-01-04 | Section 1_lift 2 | 100 | 100 |  | 2022-12-28 | 2022-12-28 | 2023-01-04 | 2023-01-04 | NTA_Zone 2 | Sub Structure | B3
43509 | Tower A - Sub Structure - B3 to B2 - Pour 1A & 2 | Complete | RCC Works - Slab | 2022-12-29 | 2023-01-02 | Slab & Staircase Reinf. | 100 | 100 |  | 2022-12-29 | 2022-12-29 | 2023-01-02 | 2023-01-02 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
43557 | Tower A - Sub Structure - B3 to B2 - Pour 5 | Complete | RCC Works - Slab | 2022-12-29 | 2023-01-11 | Slab & Staircase Fwk. | 100 | 100 |  | 2022-12-29 | 2022-12-29 | 2023-01-11 | 2023-01-11 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
43699 | Tower A - Sub Structure - B2 to B1 - Pour 4 | Complete | Core Wall RCC Works | 2022-12-29 | 2023-01-09 | Col/ Wall Casting | 100 | 100 |  | 2022-12-29 | 2022-12-29 | 2023-01-09 | 2023-01-09 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
43699 | Tower A - Sub Structure - B2 to B1 - Pour 4 | Complete | Core Wall RCC Works | 2022-12-29 | 2023-01-09 | Col/ Wall Casting | 100 | 100 |  | 2022-12-29 | 2022-12-29 | 2023-01-09 | 2023-01-09 | Tower A | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
44354 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2022-12-30 | 2023-01-06 | Section 3_lift 1 | 100 | 100 |  | 2022-12-30 | 2022-12-30 | 2023-01-06 | 2023-01-06 | NTA_Zone 2 | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
44354 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2022-12-30 | 2023-01-06 | Section 3_lift 1 | 100 | 100 |  | 2022-12-30 | 2022-12-30 | 2023-01-06 | 2023-01-06 | NTA_Zone 2 | Sub Structure | B3
43700 | Tower A - Sub Structure - B2 to B1 - Pour 4 | Complete | RCC Works - Slab | 2022-12-31 | 2023-01-13 | Slab & Staircase Fwk. | 100 | 100 |  | 2022-12-31 | 2022-12-31 | 2023-01-13 | 2023-01-13 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
43530 | Tower A - Sub Structure - B3 to B2 - Pour 7 | Complete | RCC Works - Slab | 2023-01-03 | 2023-01-06 | Slab & Staircase Reinf. | 100 | 100 |  | 2023-01-03 | 2023-01-03 | 2023-01-06 | 2023-01-06 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
43680 | Tower A - Sub Structure - B2 to B1 - Pour 9A | Complete | RCC Works - Slab | 2023-01-03 | 2023-01-04 | Slab & Staircase Reinf. | 100 | 100 |  | 2023-01-03 | 2023-01-03 | 2023-01-04 | 2023-01-04 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
43503 | Tower A - Sub Structure - B3 to B2 | Complete | Core Wall RCC Works | 2023-01-04 | 2023-01-06 | CW Casting | 100 | 100 |  | 2023-01-04 | 2023-01-04 | 2023-01-06 | 2023-01-06 | Tower A | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
43661 |  | Complete |  | 2023-01-05 | 2023-02-01 | Pour 7_B2 to B1 | 100 | 100 |  | 2023-01-05 | 2023-01-05 | 2023-02-01 | 2023-02-01
43663 | Tower A - Sub Structure - B2 to B1 - Pour 7 | Complete | Core Wall RCC Works | 2023-01-05 | 2023-01-16 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2023-01-05 | 2023-01-05 | 2023-01-16 | 2023-01-16 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
43663 | Tower A - Sub Structure - B2 to B1 - Pour 7 | Complete | Core Wall RCC Works | 2023-01-05 | 2023-01-16 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2023-01-05 | 2023-01-05 | 2023-01-16 | 2023-01-16 | Tower A | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
44356 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-01-05 | 2023-01-12 | Section 5_lift 1 | 100 | 100 |  | 2023-01-05 | 2023-01-05 | 2023-01-12 | 2023-01-12 | NTA_Zone 2 | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
44356 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-01-05 | 2023-01-12 | Section 5_lift 1 | 100 | 100 |  | 2023-01-05 | 2023-01-05 | 2023-01-12 | 2023-01-12 | NTA_Zone 2 | Sub Structure | B3
44365 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-01-05 | 2023-01-12 | Section 2_lift 2 | 100 | 100 |  | 2023-01-05 | 2023-01-05 | 2023-01-12 | 2023-01-12 | NTA_Zone 2 | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
44365 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-01-05 | 2023-01-12 | Section 2_lift 2 | 100 | 100 |  | 2023-01-05 | 2023-01-05 | 2023-01-12 | 2023-01-12 | NTA_Zone 2 | Sub Structure | B3
43510 | Tower A - Sub Structure - B3 to B2 - Pour 1A & 2 | Complete | RCC Works - Slab | 2023-01-07 | 2023-01-09 | Slab & Staircase Casting | 100 | 100 |  | 2023-01-07 | 2023-01-07 | 2023-01-09 | 2023-01-09 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
43517 | Tower A - Sub Structure - B3 to B2 - Pour 3 | Complete | RCC Works - Slab | 2023-01-07 | 2023-01-09 | Slab & Staircase Casting | 100 | 100 |  | 2023-01-07 | 2023-01-07 | 2023-01-09 | 2023-01-09 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
43524 | Tower A - Sub Structure - B3 to B2 - Pour 1B & 6 | Complete | RCC Works - Slab | 2023-01-07 | 2023-01-09 | Slab & Staircase Casting | 100 | 100 |  | 2023-01-07 | 2023-01-07 | 2023-01-09 | 2023-01-09 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
43531 | Tower A - Sub Structure - B3 to B2 - Pour 7 | Complete | RCC Works - Slab | 2023-01-07 | 2023-01-09 | Slab & Staircase Casting | 100 | 100 |  | 2023-01-07 | 2023-01-07 | 2023-01-09 | 2023-01-09 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
43664 | Tower A - Sub Structure - B2 to B1 - Pour 7 | Complete | Core Wall RCC Works | 2023-01-07 | 2023-01-18 | Col/ Wall Casting | 100 | 100 |  | 2023-01-07 | 2023-01-07 | 2023-01-18 | 2023-01-18 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
43664 | Tower A - Sub Structure - B2 to B1 - Pour 7 | Complete | Core Wall RCC Works | 2023-01-07 | 2023-01-18 | Col/ Wall Casting | 100 | 100 |  | 2023-01-07 | 2023-01-07 | 2023-01-18 | 2023-01-18 | Tower A | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
43687 | Tower A - Sub Structure - B2 to B1 - Pour 9B | Complete | RCC Works - Slab | 2023-01-07 | 2023-01-09 | Slab & Staircase Reinf. | 100 | 100 |  | 2023-01-07 | 2023-01-07 | 2023-01-09 | 2023-01-09 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
44355 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-01-07 | 2023-01-14 | Section 4_lift 1 | 100 | 100 |  | 2023-01-07 | 2023-01-07 | 2023-01-14 | 2023-01-14 | NTA_Zone 2 | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
44355 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-01-07 | 2023-01-14 | Section 4_lift 1 | 100 | 100 |  | 2023-01-07 | 2023-01-07 | 2023-01-14 | 2023-01-14 | NTA_Zone 2 | Sub Structure | B3
44366 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-01-07 | 2023-01-14 | Section 3_lift 2 | 100 | 100 |  | 2023-01-07 | 2023-01-07 | 2023-01-14 | 2023-01-14 | NTA_Zone 2 | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
44366 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-01-07 | 2023-01-14 | Section 3_lift 2 | 100 | 100 |  | 2023-01-07 | 2023-01-07 | 2023-01-14 | 2023-01-14 | NTA_Zone 2 | Sub Structure | B3
43867 | Tower A - Sub Structure - B1 to GF - Pour 8 | Complete | Core Wall RCC Works | 2023-01-09 | 2023-01-11 | Col/ Wall Reinf. | 100 | 100 |  | 2023-01-09 | 2023-01-09 | 2023-01-11 | 2023-01-11 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43867 | Tower A - Sub Structure - B1 to GF - Pour 8 | Complete | Core Wall RCC Works | 2023-01-09 | 2023-01-11 | Col/ Wall Reinf. | 100 | 100 |  | 2023-01-09 | 2023-01-09 | 2023-01-11 | 2023-01-11 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43558 | Tower A - Sub Structure - B3 to B2 - Pour 5 | Complete | RCC Works - Slab | 2023-01-10 | 2023-01-14 | Slab & Staircase Reinf. | 100 | 100 |  | 2023-01-10 | 2023-01-10 | 2023-01-14 | 2023-01-14 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
43568 |  | Complete |  | 2023-01-10 | 2023-02-03 | Retaining Wall_B2 to B1_Zone 1A | 100 | 100 |  | 2023-01-10 | 2023-01-10 | 2023-02-03 | 2023-02-03
43569 |  | Complete |  | 2023-01-10 | 2023-01-24 | Section 1_13m | 100 | 100 |  | 2023-01-10 | 2023-01-10 | 2023-01-24 | 2023-01-24
43570 | Tower A - Sub Structure - B2 to B1 - Zone 1A - Sec 1 (13 m) | Complete | Retaining Wall RCC Works | 2023-01-10 | 2023-01-12 | Liner Wall Fwk & Casting | 100 | 100 |  | 2023-01-10 | 2023-01-10 | 2023-01-12 | 2023-01-12 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43575 |  | Complete |  | 2023-01-10 | 2023-01-24 | Section 4_10m | 100 | 100 |  | 2023-01-10 | 2023-01-10 | 2023-01-24 | 2023-01-24
43576 | Tower A - Sub Structure - B2 to B1 - Zone 1A - Sec 4 (10 m) | Complete | Retaining Wall RCC Works | 2023-01-10 | 2023-01-12 | Liner Wall Fwk & Casting | 100 | 100 |  | 2023-01-10 | 2023-01-10 | 2023-01-12 | 2023-01-12 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43581 |  | Complete |  | 2023-01-10 | 2023-01-30 | Section 3_10m | 100 | 100 |  | 2023-01-10 | 2023-01-10 | 2023-01-30 | 2023-01-30
43582 | Tower A - Sub Structure - B2 to B1 - Zone 1A - Sec 3 (10 m) | Complete | Retaining Wall RCC Works | 2023-01-10 | 2023-01-12 | Liner Wall Fwk & Casting | 100 | 100 |  | 2023-01-10 | 2023-01-10 | 2023-01-12 | 2023-01-12 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43587 |  | Complete |  | 2023-01-10 | 2023-01-30 | Section 5_10m | 100 | 100 |  | 2023-01-10 | 2023-01-10 | 2023-01-30 | 2023-01-30
43588 | Tower A - Sub Structure - B2 to B1 - Zone 1A - Sec 5 (10 m) | Complete | Retaining Wall RCC Works | 2023-01-10 | 2023-01-12 | Liner Wall Fwk & Casting | 100 | 100 |  | 2023-01-10 | 2023-01-10 | 2023-01-12 | 2023-01-12 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43593 |  | Complete |  | 2023-01-10 | 2023-02-03 | Section 2_10m | 100 | 100 |  | 2023-01-10 | 2023-01-10 | 2023-02-03 | 2023-02-03
43594 | Tower A - Sub Structure - B2 to B1 - Zone 1A - Sec 2 (10 m) | Complete | Retaining Wall RCC Works | 2023-01-10 | 2023-01-12 | Liner Wall Fwk & Casting | 100 | 100 |  | 2023-01-10 | 2023-01-10 | 2023-01-12 | 2023-01-12 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43599 |  | Complete |  | 2023-01-10 | 2023-02-03 | Section 6_10m | 100 | 100 |  | 2023-01-10 | 2023-01-10 | 2023-02-03 | 2023-02-03
43600 | Tower A - Sub Structure - B2 to B1 - Zone 1A - Sec 6 (10 m) | Complete | Retaining Wall RCC Works | 2023-01-10 | 2023-01-12 | Liner Wall Fwk & Casting | 100 | 100 |  | 2023-01-10 | 2023-01-10 | 2023-01-12 | 2023-01-12 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43636 |  | Complete |  | 2023-01-10 | 2023-01-31 | Core Wall B2-B1 | 100 | 100 |  | 2023-01-10 | 2023-01-10 | 2023-01-31 | 2023-01-31
43637 | Tower A - Sub Structure - B2 to B1 | Complete | Core Wall RCC Works | 2023-01-10 | 2023-01-23 | CW Reinf | 100 | 100 |  | 2023-01-10 | 2023-01-10 | 2023-01-23 | 2023-01-23 | Tower A | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
43662 | Tower A - Sub Structure - B2 to B1 - Pour 7 | Complete | Core Wall RCC Works | 2023-01-10 | 2023-01-12 | Col/ Wall Reinf. | 100 | 100 |  | 2023-01-10 | 2023-01-10 | 2023-01-12 | 2023-01-12 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
43662 | Tower A - Sub Structure - B2 to B1 - Pour 7 | Complete | Core Wall RCC Works | 2023-01-10 | 2023-01-12 | Col/ Wall Reinf. | 100 | 100 |  | 2023-01-10 | 2023-01-10 | 2023-01-12 | 2023-01-12 | Tower A | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
43665 | Tower A - Sub Structure - B2 to B1 - Pour 7 | Complete | RCC Works - Slab | 2023-01-10 | 2023-01-23 | Slab & Staircase Fwk. | 100 | 100 |  | 2023-01-10 | 2023-01-10 | 2023-01-23 | 2023-01-23 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
43868 | Tower A - Sub Structure - B1 to GF - Pour 8 | Complete | Core Wall RCC Works | 2023-01-12 | 2023-01-14 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2023-01-12 | 2023-01-12 | 2023-01-14 | 2023-01-14 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43868 | Tower A - Sub Structure - B1 to GF - Pour 8 | Complete | Core Wall RCC Works | 2023-01-12 | 2023-01-14 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2023-01-12 | 2023-01-12 | 2023-01-14 | 2023-01-14 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43571 | Tower A - Sub Structure - B2 to B1 - Zone 1A - Sec 1 (13 m) | Complete | Retaining Wall RCC Works | 2023-01-13 | 2023-01-16 | Waterproofing along the liner wall | 100 | 100 |  | 2023-01-13 | 2023-01-13 | 2023-01-16 | 2023-01-16 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43577 | Tower A - Sub Structure - B2 to B1 - Zone 1A - Sec 4 (10 m) | Complete | Retaining Wall RCC Works | 2023-01-13 | 2023-01-16 | Waterproofing along the liner wall | 100 | 100 |  | 2023-01-13 | 2023-01-13 | 2023-01-16 | 2023-01-16 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43583 | Tower A - Sub Structure - B2 to B1 - Zone 1A - Sec 3 (10 m) | Complete | Retaining Wall RCC Works | 2023-01-13 | 2023-01-16 | Waterproofing along the liner wall | 100 | 100 |  | 2023-01-13 | 2023-01-13 | 2023-01-16 | 2023-01-16 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43589 | Tower A - Sub Structure - B2 to B1 - Zone 1A - Sec 5 (10 m) | Complete | Retaining Wall RCC Works | 2023-01-13 | 2023-01-16 | Waterproofing along the liner wall | 100 | 100 |  | 2023-01-13 | 2023-01-13 | 2023-01-16 | 2023-01-16 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43595 | Tower A - Sub Structure - B2 to B1 - Zone 1A - Sec 2 (10 m) | Complete | Retaining Wall RCC Works | 2023-01-13 | 2023-01-16 | Waterproofing along the liner wall | 100 | 100 |  | 2023-01-13 | 2023-01-13 | 2023-01-16 | 2023-01-16 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43601 | Tower A - Sub Structure - B2 to B1 - Zone 1A - Sec 6 (10 m) | Complete | Retaining Wall RCC Works | 2023-01-13 | 2023-01-16 | Waterproofing along the liner wall | 100 | 100 |  | 2023-01-13 | 2023-01-13 | 2023-01-16 | 2023-01-16 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43701 | Tower A - Sub Structure - B2 to B1 - Pour 4 | Complete | RCC Works - Slab | 2023-01-13 | 2023-01-17 | Slab & Staircase Reinf. | 100 | 100 |  | 2023-01-13 | 2023-01-13 | 2023-01-17 | 2023-01-17 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
44357 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-01-13 | 2023-01-20 | Section 6_lift 1 | 100 | 100 |  | 2023-01-13 | 2023-01-13 | 2023-01-20 | 2023-01-20 | NTA_Zone 2 | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
44357 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-01-13 | 2023-01-20 | Section 6_lift 1 | 100 | 100 |  | 2023-01-13 | 2023-01-13 | 2023-01-20 | 2023-01-20 | NTA_Zone 2 | Sub Structure | B3
44368 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-01-13 | 2023-01-20 | Section 5_lift 2 | 100 | 100 |  | 2023-01-13 | 2023-01-13 | 2023-01-20 | 2023-01-20 | NTA_Zone 2 | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
44368 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-01-13 | 2023-01-20 | Section 5_lift 2 | 100 | 100 |  | 2023-01-13 | 2023-01-13 | 2023-01-20 | 2023-01-20 | NTA_Zone 2 | Sub Structure | B3
43869 | Tower A - Sub Structure - B1 to GF - Pour 8 | Complete | Core Wall RCC Works | 2023-01-14 | 2023-01-16 | Col/ Wall Casting | 100 | 100 |  | 2023-01-14 | 2023-01-14 | 2023-01-16 | 2023-01-16 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43869 | Tower A - Sub Structure - B1 to GF - Pour 8 | Complete | Core Wall RCC Works | 2023-01-14 | 2023-01-16 | Col/ Wall Casting | 100 | 100 |  | 2023-01-14 | 2023-01-14 | 2023-01-16 | 2023-01-16 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43559 | Tower A - Sub Structure - B3 to B2 - Pour 5 | Complete | RCC Works - Slab | 2023-01-16 | 2023-01-17 | Slab & Staircase Casting | 100 | 100 |  | 2023-01-16 | 2023-01-16 | 2023-01-17 | 2023-01-17 | Tower A | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
44358 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-01-16 | 2023-01-23 | Section 7_lift 1 | 100 | 100 |  | 2023-01-16 | 2023-01-16 | 2023-01-23 | 2023-01-23 | NTA_Zone 2 | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
44358 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-01-16 | 2023-01-23 | Section 7_lift 1 | 100 | 100 |  | 2023-01-16 | 2023-01-16 | 2023-01-23 | 2023-01-23 | NTA_Zone 2 | Sub Structure | B3
44367 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-01-16 | 2023-01-23 | Section 4_lift 2 | 100 | 100 |  | 2023-01-16 | 2023-01-16 | 2023-01-23 | 2023-01-23 | NTA_Zone 2 | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
44367 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-01-16 | 2023-01-23 | Section 4_lift 2 | 100 | 100 |  | 2023-01-16 | 2023-01-16 | 2023-01-23 | 2023-01-23 | NTA_Zone 2 | Sub Structure | B3
43572 | Tower A - Sub Structure - B2 to B1 - Zone 1A - Sec 1 (13 m) | Complete | Retaining Wall RCC Works | 2023-01-17 | 2023-01-19 | Retaining Wall_Reinf_Lift 1 | 100 | 100 |  | 2023-01-17 | 2023-01-17 | 2023-01-19 | 2023-01-19 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43578 | Tower A - Sub Structure - B2 to B1 - Zone 1A - Sec 4 (10 m) | Complete | Retaining Wall RCC Works | 2023-01-17 | 2023-01-19 | Retaining Wall_Reinf_Lift 1 | 100 | 100 |  | 2023-01-17 | 2023-01-17 | 2023-01-19 | 2023-01-19 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43584 | Tower A - Sub Structure - B2 to B1 - Zone 1A - Sec 3 (10 m) | Complete | Retaining Wall RCC Works | 2023-01-17 | 2023-01-19 | Retaining Wall_Reinf_Lift 1 | 100 | 100 |  | 2023-01-17 | 2023-01-17 | 2023-01-19 | 2023-01-19 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43590 | Tower A - Sub Structure - B2 to B1 - Zone 1A - Sec 5 (10 m) | Complete | Retaining Wall RCC Works | 2023-01-17 | 2023-01-19 | Retaining Wall_Reinf_Lift 1 | 100 | 100 |  | 2023-01-17 | 2023-01-17 | 2023-01-19 | 2023-01-19 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43596 | Tower A - Sub Structure - B2 to B1 - Zone 1A - Sec 2 (10 m) | Complete | Retaining Wall RCC Works | 2023-01-17 | 2023-01-19 | Retaining Wall_Reinf_Lift 1 | 100 | 100 |  | 2023-01-17 | 2023-01-17 | 2023-01-19 | 2023-01-19 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43602 | Tower A - Sub Structure - B2 to B1 - Zone 1A - Sec 6 (10 m) | Complete | Retaining Wall RCC Works | 2023-01-17 | 2023-01-19 | Retaining Wall_Reinf_Lift 1 | 100 | 100 |  | 2023-01-17 | 2023-01-17 | 2023-01-19 | 2023-01-19 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43870 | Tower A - Sub Structure - B1 to GF - Pour 8 | Complete | RCC Works - Slab | 2023-01-17 | 2023-01-31 | Slab & Staircase Fwk. | 100 | 100 |  | 2023-01-17 | 2023-01-17 | 2023-01-31 | 2023-01-31 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
40134 |  | Started |  | 2023-01-18 | 2026-05-22 | Civil Finishes | 100 | 56 |  | 2023-01-18 | 2023-01-18 | 2026-06-27
40135 |  | Started |  | 2023-01-18 | 2026-04-24 | Partition Walls - Blockwork | 100 | 58 |  | 2023-01-18 | 2023-01-18 | 2026-05-25
40136 |  | Complete |  | 2023-01-18 | 2024-04-11 | B3 to B2_TA & NTA | 100 | 100 |  | 2023-01-18 | 2023-01-18 | 2024-04-11 | 2024-04-11
40136 |  | Complete |  | 2023-01-18 | 2024-04-11 | B3 to B2_TA & NTA | 100 | 100 |  | 2023-01-18 | 2023-01-18 | 2024-04-11 | 2024-04-11 |  |  |  | Finishes | Gypsum Plastering Works
40137 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 | Complete | Partition Wall-Blockwork | 2023-01-18 | 2023-02-22 | De-shuttering & Area clearance | 100 | 100 |  | 2023-01-18 | 2023-01-18 | 2023-02-22 | 2023-02-22 | Tower A | Sub Structure | B3
43605 |  | Complete |  | 2023-01-18 | 2023-02-11 | Retaining Wall_B2 to B1_Zone 2A | 100 | 100 |  | 2023-01-18 | 2023-01-18 | 2023-02-11 | 2023-02-11
43606 |  | Complete |  | 2023-01-18 | 2023-02-02 | Section 1_11.5m | 100 | 100 |  | 2023-01-18 | 2023-01-18 | 2023-02-02 | 2023-02-02
43607 | Tower A - Sub Structure - B2 to B1 - Zone 2A - Sec 1 (11.5 m) | Complete | Retaining Wall RCC Works | 2023-01-18 | 2023-01-20 | Liner Wall Fwk & Casting | 100 | 100 |  | 2023-01-18 | 2023-01-18 | 2023-01-20 | 2023-01-20 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43612 |  | Complete |  | 2023-01-18 | 2023-02-07 | Section 3_10.8m | 100 | 100 |  | 2023-01-18 | 2023-01-18 | 2023-02-07 | 2023-02-07
43613 | Tower A - Sub Structure - B2 to B1 - Zone 2A - Sec 3 (10.8 m) | Complete | Retaining Wall RCC Works | 2023-01-18 | 2023-01-20 | Liner Wall Fwk & Casting | 100 | 100 |  | 2023-01-18 | 2023-01-18 | 2023-01-20 | 2023-01-20 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43618 |  | Complete |  | 2023-01-18 | 2023-02-11 | Section 2_14m | 100 | 100 |  | 2023-01-18 | 2023-01-18 | 2023-02-11 | 2023-02-11
43619 | Tower A - Sub Structure - B2 to B1 - Zone 2A - Sec 2 (14 m) | Complete | Retaining Wall RCC Works | 2023-01-18 | 2023-01-20 | Liner Wall Fwk & Casting | 100 | 100 |  | 2023-01-18 | 2023-01-18 | 2023-01-20 | 2023-01-20 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43624 |  | Complete |  | 2023-01-18 | 2023-02-01 | Section 4_8.2m | 100 | 100 |  | 2023-01-18 | 2023-01-18 | 2023-02-01 | 2023-02-01
43625 | Tower A - Sub Structure - B2 to B1 - Zone 2A - Sec 4 (8.2 m) | Complete | Retaining Wall RCC Works | 2023-01-18 | 2023-01-20 | Liner Wall Fwk & Casting | 100 | 100 |  | 2023-01-18 | 2023-01-18 | 2023-01-20 | 2023-01-20 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43630 |  | Complete |  | 2023-01-18 | 2023-02-06 | Section 5_8m | 100 | 100 |  | 2023-01-18 | 2023-01-18 | 2023-02-06 | 2023-02-06
43631 | Tower A - Sub Structure - B2 to B1 - Zone 2A - Sec 5 (8 m) | Complete | Retaining Wall RCC Works | 2023-01-18 | 2023-01-20 | Liner Wall Fwk & Casting | 100 | 100 |  | 2023-01-18 | 2023-01-18 | 2023-01-20 | 2023-01-20 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43638 | Tower A - Sub Structure - B2 to B1 | Complete | Core Wall RCC Works | 2023-01-18 | 2023-01-27 | CW Fwk (3.5m lift) | 100 | 100 |  | 2023-01-18 | 2023-01-18 | 2023-01-27 | 2023-01-27 | Tower A | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
43689 |  | Complete |  | 2023-01-18 | 2023-02-11 | Pour 5_B2 to B1 | 100 | 100 |  | 2023-01-18 | 2023-01-18 | 2023-02-11 | 2023-02-11
43690 | Tower A - Sub Structure - B2 to B1 - Pour 5 | Complete | Core Wall RCC Works | 2023-01-18 | 2023-01-25 | Col/ Wall Reinf. | 100 | 100 |  | 2023-01-18 | 2023-01-18 | 2023-01-25 | 2023-01-25 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
43690 | Tower A - Sub Structure - B2 to B1 - Pour 5 | Complete | Core Wall RCC Works | 2023-01-18 | 2023-01-25 | Col/ Wall Reinf. | 100 | 100 |  | 2023-01-18 | 2023-01-18 | 2023-01-25 | 2023-01-25 | Tower A | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
43691 | Tower A - Sub Structure - B2 to B1 - Pour 5 | Complete | Core Wall RCC Works | 2023-01-18 | 2023-01-30 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2023-01-18 | 2023-01-18 | 2023-01-30 | 2023-01-30 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
43691 | Tower A - Sub Structure - B2 to B1 - Pour 5 | Complete | Core Wall RCC Works | 2023-01-18 | 2023-01-30 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2023-01-18 | 2023-01-18 | 2023-01-30 | 2023-01-30 | Tower A | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
43702 | Tower A - Sub Structure - B2 to B1 - Pour 4 | Complete | RCC Works - Slab | 2023-01-18 | 2023-01-19 | Slab & Staircase Casting | 100 | 100 |  | 2023-01-18 | 2023-01-18 | 2023-01-19 | 2023-01-19 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
43573 | Tower A - Sub Structure - B2 to B1 - Zone 1A - Sec 1 (13 m) | Complete | Retaining Wall RCC Works | 2023-01-20 | 2023-01-23 | Fwk_Lift 1 RW | 100 | 100 |  | 2023-01-20 | 2023-01-20 | 2023-01-23 | 2023-01-23 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43579 | Tower A - Sub Structure - B2 to B1 - Zone 1A - Sec 4 (10 m) | Complete | Retaining Wall RCC Works | 2023-01-20 | 2023-01-23 | Fwk_Lift 1 RW | 100 | 100 |  | 2023-01-20 | 2023-01-20 | 2023-01-23 | 2023-01-23 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43692 | Tower A - Sub Structure - B2 to B1 - Pour 5 | Complete | Core Wall RCC Works | 2023-01-20 | 2023-02-01 | Col/ Wall Casting | 100 | 100 |  | 2023-01-20 | 2023-01-20 | 2023-02-01 | 2023-02-01 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
43692 | Tower A - Sub Structure - B2 to B1 - Pour 5 | Complete | Core Wall RCC Works | 2023-01-20 | 2023-02-01 | Col/ Wall Casting | 100 | 100 |  | 2023-01-20 | 2023-01-20 | 2023-02-01 | 2023-02-01 | Tower A | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
43903 |  | Complete |  | 2023-01-20 | 2023-03-03 | Pour 4_B1 to GF | 100 | 100 |  | 2023-01-20 | 2023-01-20 | 2023-03-03 | 2023-03-03
43904 | Tower A - Sub Structure - B1 to GF - Pour 4 | Complete | Core Wall RCC Works | 2023-01-20 | 2023-01-28 | Col/ Wall Reinf. | 100 | 100 |  | 2023-01-20 | 2023-01-20 | 2023-01-28 | 2023-01-28 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43904 | Tower A - Sub Structure - B1 to GF - Pour 4 | Complete | Core Wall RCC Works | 2023-01-20 | 2023-01-28 | Col/ Wall Reinf. | 100 | 100 |  | 2023-01-20 | 2023-01-20 | 2023-01-28 | 2023-01-28 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43905 | Tower A - Sub Structure - B1 to GF - Pour 4 | Complete | Core Wall RCC Works | 2023-01-20 | 2023-02-01 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2023-01-20 | 2023-01-20 | 2023-02-01 | 2023-02-01 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43905 | Tower A - Sub Structure - B1 to GF - Pour 4 | Complete | Core Wall RCC Works | 2023-01-20 | 2023-02-01 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2023-01-20 | 2023-01-20 | 2023-02-01 | 2023-02-01 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43608 | Tower A - Sub Structure - B2 to B1 - Zone 2A - Sec 1 (11.5 m) | Complete | Retaining Wall RCC Works | 2023-01-21 | 2023-01-24 | Waterproofing along the liner wall | 100 | 100 |  | 2023-01-21 | 2023-01-21 | 2023-01-24 | 2023-01-24 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43614 | Tower A - Sub Structure - B2 to B1 - Zone 2A - Sec 3 (10.8 m) | Complete | Retaining Wall RCC Works | 2023-01-21 | 2023-01-24 | Waterproofing along the liner wall | 100 | 100 |  | 2023-01-21 | 2023-01-21 | 2023-01-24 | 2023-01-24 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43620 | Tower A - Sub Structure - B2 to B1 - Zone 2A - Sec 2 (14 m) | Complete | Retaining Wall RCC Works | 2023-01-21 | 2023-01-24 | Waterproofing along the liner wall | 100 | 100 |  | 2023-01-21 | 2023-01-21 | 2023-01-24 | 2023-01-24 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43626 | Tower A - Sub Structure - B2 to B1 - Zone 2A - Sec 4 (8.2 m) | Complete | Retaining Wall RCC Works | 2023-01-21 | 2023-01-24 | Waterproofing along the liner wall | 100 | 100 |  | 2023-01-21 | 2023-01-21 | 2023-01-24 | 2023-01-24 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43632 | Tower A - Sub Structure - B2 to B1 - Zone 2A - Sec 5 (8 m) | Complete | Retaining Wall RCC Works | 2023-01-21 | 2023-01-24 | Waterproofing along the liner wall | 100 | 100 |  | 2023-01-21 | 2023-01-21 | 2023-01-24 | 2023-01-24 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
44360 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-01-21 | 2023-01-30 | Section 9_lift 1 | 100 | 100 |  | 2023-01-21 | 2023-01-21 | 2023-01-30 | 2023-01-30 | NTA_Zone 2 | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
44360 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-01-21 | 2023-01-30 | Section 9_lift 1 | 100 | 100 |  | 2023-01-21 | 2023-01-21 | 2023-01-30 | 2023-01-30 | NTA_Zone 2 | Sub Structure | B3
44369 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-01-21 | 2023-01-30 | Section 6_lift 2 | 100 | 100 |  | 2023-01-21 | 2023-01-21 | 2023-01-30 | 2023-01-30 | NTA_Zone 2 | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
44369 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-01-21 | 2023-01-30 | Section 6_lift 2 | 100 | 100 |  | 2023-01-21 | 2023-01-21 | 2023-01-30 | 2023-01-30 | NTA_Zone 2 | Sub Structure | B3
43666 | Tower A - Sub Structure - B2 to B1 - Pour 7 | Complete | RCC Works - Slab | 2023-01-23 | 2023-01-27 | Slab & Staircase Reinf. | 100 | 100 |  | 2023-01-23 | 2023-01-23 | 2023-01-27 | 2023-01-27 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
43693 | Tower A - Sub Structure - B2 to B1 - Pour 5 | Complete | RCC Works - Slab | 2023-01-23 | 2023-02-06 | Slab & Staircase Fwk. | 100 | 100 |  | 2023-01-23 | 2023-01-23 | 2023-02-06 | 2023-02-06 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
43906 | Tower A - Sub Structure - B1 to GF - Pour 4 | Complete | Core Wall RCC Works | 2023-01-23 | 2023-02-03 | Col/ Wall Casting | 100 | 100 |  | 2023-01-23 | 2023-01-23 | 2023-02-03 | 2023-02-03 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43906 | Tower A - Sub Structure - B1 to GF - Pour 4 | Complete | Core Wall RCC Works | 2023-01-23 | 2023-02-03 | Col/ Wall Casting | 100 | 100 |  | 2023-01-23 | 2023-01-23 | 2023-02-03 | 2023-02-03 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43574 | Tower A - Sub Structure - B2 to B1 - Zone 1A - Sec 1 (13 m) | Complete | Retaining Wall RCC Works | 2023-01-24 | 2023-01-24 | Checking & Casting_Lift 1 | 100 | 100 |  | 2023-01-24 | 2023-01-24 | 2023-01-24 | 2023-01-24 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43580 | Tower A - Sub Structure - B2 to B1 - Zone 1A - Sec 4 (10 m) | Complete | Retaining Wall RCC Works | 2023-01-24 | 2023-01-24 | Checking & Casting_Lift 1 | 100 | 100 |  | 2023-01-24 | 2023-01-24 | 2023-01-24 | 2023-01-24 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
44359 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-01-24 | 2023-02-01 | Section 8_lift 1 | 100 | 100 |  | 2023-01-24 | 2023-01-24 | 2023-02-01 | 2023-02-01 | NTA_Zone 2 | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
44359 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-01-24 | 2023-02-01 | Section 8_lift 1 | 100 | 100 |  | 2023-01-24 | 2023-01-24 | 2023-02-01 | 2023-02-01 | NTA_Zone 2 | Sub Structure | B3
44370 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-01-24 | 2023-02-01 | Section 7_lift 2 | 100 | 100 |  | 2023-01-24 | 2023-01-24 | 2023-02-01 | 2023-02-01 | NTA_Zone 2 | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
44370 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-01-24 | 2023-02-01 | Section 7_lift 2 | 100 | 100 |  | 2023-01-24 | 2023-01-24 | 2023-02-01 | 2023-02-01 | NTA_Zone 2 | Sub Structure | B3
43585 | Tower A - Sub Structure - B2 to B1 - Zone 1A - Sec 3 (10 m) | Complete | Retaining Wall RCC Works | 2023-01-25 | 2023-01-28 | Fwk_Lift 1 RW | 100 | 100 |  | 2023-01-25 | 2023-01-25 | 2023-01-28 | 2023-01-28 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43591 | Tower A - Sub Structure - B2 to B1 - Zone 1A - Sec 5 (10 m) | Complete | Retaining Wall RCC Works | 2023-01-25 | 2023-01-28 | Fwk_Lift 1 RW | 100 | 100 |  | 2023-01-25 | 2023-01-25 | 2023-01-28 | 2023-01-28 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43609 | Tower A - Sub Structure - B2 to B1 - Zone 2A - Sec 1 (11.5 m) | Complete | Retaining Wall RCC Works | 2023-01-25 | 2023-01-28 | Retaining Wall_Reinf_Lift 1 | 100 | 100 |  | 2023-01-25 | 2023-01-25 | 2023-01-28 | 2023-01-28 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43615 | Tower A - Sub Structure - B2 to B1 - Zone 2A - Sec 3 (10.8 m) | Complete | Retaining Wall RCC Works | 2023-01-25 | 2023-01-28 | Retaining Wall_Reinf_Lift 1 | 100 | 100 |  | 2023-01-25 | 2023-01-25 | 2023-01-28 | 2023-01-28 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43621 | Tower A - Sub Structure - B2 to B1 - Zone 2A - Sec 2 (14 m) | Complete | Retaining Wall RCC Works | 2023-01-25 | 2023-01-28 | Retaining Wall_Reinf_Lift 1 | 100 | 100 |  | 2023-01-25 | 2023-01-25 | 2023-01-28 | 2023-01-28 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43627 | Tower A - Sub Structure - B2 to B1 - Zone 2A - Sec 4 (8.2 m) | Complete | Retaining Wall RCC Works | 2023-01-25 | 2023-01-27 | Retaining Wall_Reinf_Lift 1 | 100 | 100 |  | 2023-01-25 | 2023-01-25 | 2023-01-27 | 2023-01-27 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43633 | Tower A - Sub Structure - B2 to B1 - Zone 2A - Sec 5 (8 m) | Complete | Retaining Wall RCC Works | 2023-01-25 | 2023-01-27 | Retaining Wall_Reinf_Lift 1 | 100 | 100 |  | 2023-01-25 | 2023-01-25 | 2023-01-27 | 2023-01-27 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43647 |  | Complete |  | 2023-01-27 | 2023-02-20 | Pour 3_B2 to B1 | 100 | 100 |  | 2023-01-27 | 2023-01-27 | 2023-02-20 | 2023-02-20
43649 | Tower A - Sub Structure - B2 to B1 - Pour 3 | Complete | Core Wall RCC Works | 2023-01-27 | 2023-02-07 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2023-01-27 | 2023-01-27 | 2023-02-07 | 2023-02-07 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
43649 | Tower A - Sub Structure - B2 to B1 - Pour 3 | Complete | Core Wall RCC Works | 2023-01-27 | 2023-02-07 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2023-01-27 | 2023-01-27 | 2023-02-07 | 2023-02-07 | Tower A | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
43628 | Tower A - Sub Structure - B2 to B1 - Zone 2A - Sec 4 (8.2 m) | Complete | Retaining Wall RCC Works | 2023-01-28 | 2023-01-31 | Fwk_Lift 1 RW | 100 | 100 |  | 2023-01-28 | 2023-01-28 | 2023-01-31 | 2023-01-31 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43639 | Tower A - Sub Structure - B2 to B1 | Complete | Core Wall RCC Works | 2023-01-28 | 2023-01-31 | CW Casting | 100 | 100 |  | 2023-01-28 | 2023-01-28 | 2023-01-31 | 2023-01-31 | Tower A | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
43853 |  | Complete |  | 2023-01-28 | 2023-04-11 | Pour 7_B1 to GF | 100 | 100 |  | 2023-01-28 | 2023-01-28 | 2023-04-11 | 2023-04-11
43855 | Tower A - Sub Structure - B1 to GF - Pour 7 | Complete | Core Wall RCC Works | 2023-01-28 | 2023-02-08 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2023-01-28 | 2023-01-28 | 2023-02-08 | 2023-02-08 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43855 | Tower A - Sub Structure - B1 to GF - Pour 7 | Complete | Core Wall RCC Works | 2023-01-28 | 2023-02-08 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2023-01-28 | 2023-01-28 | 2023-02-08 | 2023-02-08 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43586 | Tower A - Sub Structure - B2 to B1 - Zone 1A - Sec 3 (10 m) | Complete | Retaining Wall RCC Works | 2023-01-30 | 2023-01-30 | Checking & Casting_Lift 1 | 100 | 100 |  | 2023-01-30 | 2023-01-30 | 2023-01-30 | 2023-01-30 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43592 | Tower A - Sub Structure - B2 to B1 - Zone 1A - Sec 5 (10 m) | Complete | Retaining Wall RCC Works | 2023-01-30 | 2023-01-30 | Checking & Casting_Lift 1 | 100 | 100 |  | 2023-01-30 | 2023-01-30 | 2023-01-30 | 2023-01-30 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43610 | Tower A - Sub Structure - B2 to B1 - Zone 2A - Sec 1 (11.5 m) | Complete | Retaining Wall RCC Works | 2023-01-30 | 2023-02-01 | Fwk_Lift 1 RW | 100 | 100 |  | 2023-01-30 | 2023-01-30 | 2023-02-01 | 2023-02-01 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43650 | Tower A - Sub Structure - B2 to B1 - Pour 3 | Complete | Core Wall RCC Works | 2023-01-30 | 2023-02-09 | Col/ Wall Casting | 100 | 100 |  | 2023-01-30 | 2023-01-30 | 2023-02-09 | 2023-02-09 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
43650 | Tower A - Sub Structure - B2 to B1 - Pour 3 | Complete | Core Wall RCC Works | 2023-01-30 | 2023-02-09 | Col/ Wall Casting | 100 | 100 |  | 2023-01-30 | 2023-01-30 | 2023-02-09 | 2023-02-09 | Tower A | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
43654 |  | Complete |  | 2023-01-30 | 2023-02-22 | Pour 1B & 6_B2 to B1 | 100 | 100 |  | 2023-01-30 | 2023-01-30 | 2023-02-22 | 2023-02-22
43656 | Tower A - Sub Structure - B2 to B1 - Pour 1B & 6 | Complete | Core Wall RCC Works | 2023-01-30 | 2023-02-09 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2023-01-30 | 2023-01-30 | 2023-02-09 | 2023-02-09 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
43656 | Tower A - Sub Structure - B2 to B1 - Pour 1B & 6 | Complete | Core Wall RCC Works | 2023-01-30 | 2023-02-09 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2023-01-30 | 2023-01-30 | 2023-02-09 | 2023-02-09 | Tower A | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
44296 | NTA_Zone 2 - Foundation - Pour 1 | Complete | Foundation RCC Works | 2023-01-30 | 2023-02-14 | Fwk & Casting_NTA | 100 | 100 |  | 2023-01-30 | 2023-01-30 | 2023-02-14 | 2023-02-14 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44296 | NTA_Zone 2 - Foundation - Pour 1 | Complete | Foundation RCC Works | 2023-01-30 | 2023-02-14 | Fwk & Casting_NTA | 100 | 100 |  | 2023-01-30 | 2023-01-30 | 2023-02-14 | 2023-02-14 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44296 | NTA_Zone 2 - Foundation - Pour 1 | Complete | Foundation RCC Works | 2023-01-30 | 2023-02-14 | Fwk & Casting_NTA | 100 | 100 |  | 2023-01-30 | 2023-01-30 | 2023-02-14 | 2023-02-14 | NTA_Zone 2 | Foundation
44308 | NTA_Zone 2 - Foundation - Pour 3 | Complete | Foundation RCC Works | 2023-01-30 | 2023-02-15 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2023-01-30 | 2023-01-30 | 2023-02-15 | 2023-02-15 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44308 | NTA_Zone 2 - Foundation - Pour 3 | Complete | Foundation RCC Works | 2023-01-30 | 2023-02-15 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2023-01-30 | 2023-01-30 | 2023-02-15 | 2023-02-15 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44308 | NTA_Zone 2 - Foundation - Pour 3 | Complete | Foundation RCC Works | 2023-01-30 | 2023-02-15 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2023-01-30 | 2023-01-30 | 2023-02-15 | 2023-02-15 | NTA_Zone 2 | Foundation
43597 | Tower A - Sub Structure - B2 to B1 - Zone 1A - Sec 2 (10 m) | Complete | Retaining Wall RCC Works | 2023-01-31 | 2023-02-02 | Fwk_Lift 1 RW | 100 | 100 |  | 2023-01-31 | 2023-01-31 | 2023-02-02 | 2023-02-02 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43603 | Tower A - Sub Structure - B2 to B1 - Zone 1A - Sec 6 (10 m) | Complete | Retaining Wall RCC Works | 2023-01-31 | 2023-02-02 | Fwk_Lift 1 RW | 100 | 100 |  | 2023-01-31 | 2023-01-31 | 2023-02-02 | 2023-02-02 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43667 | Tower A - Sub Structure - B2 to B1 - Pour 7 | Complete | RCC Works - Slab | 2023-01-31 | 2023-02-01 | Slab & Staircase Casting | 100 | 100 |  | 2023-01-31 | 2023-01-31 | 2023-02-01 | 2023-02-01 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
43856 | Tower A - Sub Structure - B1 to GF - Pour 7 | Complete | Core Wall RCC Works | 2023-01-31 | 2023-02-10 | Col/ Wall Casting | 100 | 100 |  | 2023-01-31 | 2023-01-31 | 2023-02-10 | 2023-02-10 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43856 | Tower A - Sub Structure - B1 to GF - Pour 7 | Complete | Core Wall RCC Works | 2023-01-31 | 2023-02-10 | Col/ Wall Casting | 100 | 100 |  | 2023-01-31 | 2023-01-31 | 2023-02-10 | 2023-02-10 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43871 | Tower A - Sub Structure - B1 to GF - Pour 8 | Complete | RCC Works - Slab | 2023-01-31 | 2023-02-03 | Slab & Staircase Reinf. | 100 | 100 |  | 2023-01-31 | 2023-01-31 | 2023-02-03 | 2023-02-03 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
44361 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-01-31 | 2023-02-07 | Section 10_lift 1 | 100 | 100 |  | 2023-01-31 | 2023-01-31 | 2023-02-07 | 2023-02-07 | NTA_Zone 2 | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
44361 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-01-31 | 2023-02-07 | Section 10_lift 1 | 100 | 100 |  | 2023-01-31 | 2023-01-31 | 2023-02-07 | 2023-02-07 | NTA_Zone 2 | Sub Structure | B3
44372 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-01-31 | 2023-02-07 | Section 9_lift 2 | 100 | 100 |  | 2023-01-31 | 2023-01-31 | 2023-02-07 | 2023-02-07 | NTA_Zone 2 | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
44372 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-01-31 | 2023-02-07 | Section 9_lift 2 | 100 | 100 |  | 2023-01-31 | 2023-01-31 | 2023-02-07 | 2023-02-07 | NTA_Zone 2 | Sub Structure | B3
43629 | Tower A - Sub Structure - B2 to B1 - Zone 2A - Sec 4 (8.2 m) | Complete | Retaining Wall RCC Works | 2023-02-01 | 2023-02-01 | Checking & Casting_Lift 1 | 100 | 100 |  | 2023-02-01 | 2023-02-01 | 2023-02-01 | 2023-02-01 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43640 |  | Complete |  | 2023-02-01 | 2023-02-24 | Pour 1A & 2_B2 to B1 | 100 | 100 |  | 2023-02-01 | 2023-02-01 | 2023-02-24 | 2023-02-24
43641 | Tower A - Sub Structure - B2 to B1 - Pour 1A & 2 | Complete | Core Wall RCC Works | 2023-02-01 | 2023-02-08 | Col/ Wall Reinf. | 100 | 100 |  | 2023-02-01 | 2023-02-01 | 2023-02-08 | 2023-02-08 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
43641 | Tower A - Sub Structure - B2 to B1 - Pour 1A & 2 | Complete | Core Wall RCC Works | 2023-02-01 | 2023-02-08 | Col/ Wall Reinf. | 100 | 100 |  | 2023-02-01 | 2023-02-01 | 2023-02-08 | 2023-02-08 | Tower A | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
43642 | Tower A - Sub Structure - B2 to B1 - Pour 1A & 2 | Complete | Core Wall RCC Works | 2023-02-01 | 2023-02-11 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2023-02-01 | 2023-02-01 | 2023-02-11 | 2023-02-11 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
43642 | Tower A - Sub Structure - B2 to B1 - Pour 1A & 2 | Complete | Core Wall RCC Works | 2023-02-01 | 2023-02-11 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2023-02-01 | 2023-02-01 | 2023-02-11 | 2023-02-11 | Tower A | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
43648 | Tower A - Sub Structure - B2 to B1 - Pour 3 | Complete | Core Wall RCC Works | 2023-02-01 | 2023-02-03 | Col/ Wall Reinf. | 100 | 100 |  | 2023-02-01 | 2023-02-01 | 2023-02-03 | 2023-02-03 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
43648 | Tower A - Sub Structure - B2 to B1 - Pour 3 | Complete | Core Wall RCC Works | 2023-02-01 | 2023-02-03 | Col/ Wall Reinf. | 100 | 100 |  | 2023-02-01 | 2023-02-01 | 2023-02-03 | 2023-02-03 | Tower A | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
43651 | Tower A - Sub Structure - B2 to B1 - Pour 3 | Complete | RCC Works - Slab | 2023-02-01 | 2023-02-14 | Slab & Staircase Fwk. | 100 | 100 |  | 2023-02-01 | 2023-02-01 | 2023-02-14 | 2023-02-14 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
43655 | Tower A - Sub Structure - B2 to B1 - Pour 1B & 6 | Complete | Core Wall RCC Works | 2023-02-01 | 2023-02-06 | Col/ Wall Reinf. | 100 | 100 |  | 2023-02-01 | 2023-02-01 | 2023-02-06 | 2023-02-06 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
43655 | Tower A - Sub Structure - B2 to B1 - Pour 1B & 6 | Complete | Core Wall RCC Works | 2023-02-01 | 2023-02-06 | Col/ Wall Reinf. | 100 | 100 |  | 2023-02-01 | 2023-02-01 | 2023-02-06 | 2023-02-06 | Tower A | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
43657 | Tower A - Sub Structure - B2 to B1 - Pour 1B & 6 | Complete | Core Wall RCC Works | 2023-02-01 | 2023-02-11 | Col/ Wall Casting | 100 | 100 |  | 2023-02-01 | 2023-02-01 | 2023-02-11 | 2023-02-11 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
43657 | Tower A - Sub Structure - B2 to B1 - Pour 1B & 6 | Complete | Core Wall RCC Works | 2023-02-01 | 2023-02-11 | Col/ Wall Casting | 100 | 100 |  | 2023-02-01 | 2023-02-01 | 2023-02-11 | 2023-02-11 | Tower A | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
43611 | Tower A - Sub Structure - B2 to B1 - Zone 2A - Sec 1 (11.5 m) | Complete | Retaining Wall RCC Works | 2023-02-02 | 2023-02-02 | Checking & Casting_Lift 1 | 100 | 100 |  | 2023-02-02 | 2023-02-02 | 2023-02-02 | 2023-02-02 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43634 | Tower A - Sub Structure - B2 to B1 - Zone 2A - Sec 5 (8 m) | Complete | Retaining Wall RCC Works | 2023-02-02 | 2023-02-04 | Fwk_Lift 1 RW | 100 | 100 |  | 2023-02-02 | 2023-02-02 | 2023-02-04 | 2023-02-04 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43854 | Tower A - Sub Structure - B1 to GF - Pour 7 | Complete | Core Wall RCC Works | 2023-02-02 | 2023-02-04 | Col/ Wall Reinf. | 100 | 100 |  | 2023-02-02 | 2023-02-02 | 2023-02-04 | 2023-02-04 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43854 | Tower A - Sub Structure - B1 to GF - Pour 7 | Complete | Core Wall RCC Works | 2023-02-02 | 2023-02-04 | Col/ Wall Reinf. | 100 | 100 |  | 2023-02-02 | 2023-02-02 | 2023-02-04 | 2023-02-04 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44362 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-02-02 | 2023-02-09 | Section 11_lift 1 | 100 | 100 |  | 2023-02-02 | 2023-02-02 | 2023-02-09 | 2023-02-09 | NTA_Zone 2 | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
44362 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-02-02 | 2023-02-09 | Section 11_lift 1 | 100 | 100 |  | 2023-02-02 | 2023-02-02 | 2023-02-09 | 2023-02-09 | NTA_Zone 2 | Sub Structure | B3
44371 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-02-02 | 2023-02-09 | Section 8_lift 2 | 100 | 100 |  | 2023-02-02 | 2023-02-02 | 2023-02-09 | 2023-02-09 | NTA_Zone 2 | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
44371 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-02-02 | 2023-02-09 | Section 8_lift 2 | 100 | 100 |  | 2023-02-02 | 2023-02-02 | 2023-02-09 | 2023-02-09 | NTA_Zone 2 | Sub Structure | B3
43598 | Tower A - Sub Structure - B2 to B1 - Zone 1A - Sec 2 (10 m) | Complete | Retaining Wall RCC Works | 2023-02-03 | 2023-02-03 | Checking & Casting_Lift 1 | 100 | 100 |  | 2023-02-03 | 2023-02-03 | 2023-02-03 | 2023-02-03 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43604 | Tower A - Sub Structure - B2 to B1 - Zone 1A - Sec 6 (10 m) | Complete | Retaining Wall RCC Works | 2023-02-03 | 2023-02-03 | Checking & Casting_Lift 1 | 100 | 100 |  | 2023-02-03 | 2023-02-03 | 2023-02-03 | 2023-02-03 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43616 | Tower A - Sub Structure - B2 to B1 - Zone 2A - Sec 3 (10.8 m) | Complete | Retaining Wall RCC Works | 2023-02-03 | 2023-02-06 | Fwk_Lift 1 RW | 100 | 100 |  | 2023-02-03 | 2023-02-03 | 2023-02-06 | 2023-02-06 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43643 | Tower A - Sub Structure - B2 to B1 - Pour 1A & 2 | Complete | Core Wall RCC Works | 2023-02-03 | 2023-02-14 | Col/ Wall Casting | 100 | 100 |  | 2023-02-03 | 2023-02-03 | 2023-02-14 | 2023-02-14 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
43643 | Tower A - Sub Structure - B2 to B1 - Pour 1A & 2 | Complete | Core Wall RCC Works | 2023-02-03 | 2023-02-14 | Col/ Wall Casting | 100 | 100 |  | 2023-02-03 | 2023-02-03 | 2023-02-14 | 2023-02-14 | Tower A | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
43658 | Tower A - Sub Structure - B2 to B1 - Pour 1B & 6 | Complete | RCC Works - Slab | 2023-02-03 | 2023-02-16 | Slab & Staircase Fwk. | 100 | 100 |  | 2023-02-03 | 2023-02-03 | 2023-02-16 | 2023-02-16 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
43681 | Tower A - Sub Structure - B2 to B1 - Pour 9A | Complete | RCC Works - Slab | 2023-02-04 | 2023-02-06 | Slab & Staircase Casting | 100 | 100 |  | 2023-02-04 | 2023-02-04 | 2023-02-06 | 2023-02-06 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
43694 | Tower A - Sub Structure - B2 to B1 - Pour 5 | Complete | RCC Works - Slab | 2023-02-04 | 2023-02-09 | Slab & Staircase Reinf. | 100 | 100 |  | 2023-02-04 | 2023-02-04 | 2023-02-09 | 2023-02-09 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
43872 | Tower A - Sub Structure - B1 to GF - Pour 8 | Complete | RCC Works - Slab | 2023-02-04 | 2023-02-06 | Slab & Staircase Casting | 100 | 100 |  | 2023-02-04 | 2023-02-04 | 2023-02-06 | 2023-02-06 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
43907 | Tower A - Sub Structure - B1 to GF - Pour 4 | Complete | Core Wall RCC Works | 2023-02-04 | 2023-02-07 | Col/ Wall Reinf. | 100 | 100 |  | 2023-02-04 | 2023-02-04 | 2023-02-07 | 2023-02-07 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43907 | Tower A - Sub Structure - B1 to GF - Pour 4 | Complete | Core Wall RCC Works | 2023-02-04 | 2023-02-07 | Col/ Wall Reinf. | 100 | 100 |  | 2023-02-04 | 2023-02-04 | 2023-02-07 | 2023-02-07 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43635 | Tower A - Sub Structure - B2 to B1 - Zone 2A - Sec 5 (8 m) | Complete | Retaining Wall RCC Works | 2023-02-06 | 2023-02-06 | Checking & Casting_Lift 1 | 100 | 100 |  | 2023-02-06 | 2023-02-06 | 2023-02-06 | 2023-02-06 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43644 | Tower A - Sub Structure - B2 to B1 - Pour 1A & 2 | Complete | RCC Works - Slab | 2023-02-06 | 2023-02-18 | Slab & Staircase Fwk. | 100 | 100 |  | 2023-02-06 | 2023-02-06 | 2023-02-18 | 2023-02-18 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
43617 | Tower A - Sub Structure - B2 to B1 - Zone 2A - Sec 3 (10.8 m) | Complete | Retaining Wall RCC Works | 2023-02-07 | 2023-02-07 | Checking & Casting_Lift 1 | 100 | 100 |  | 2023-02-07 | 2023-02-07 | 2023-02-07 | 2023-02-07 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43873 |  | Complete |  | 2023-02-07 | 2023-04-27 | Pour 9A_B1 to GF | 100 | 100 |  | 2023-02-07 | 2023-02-07 | 2023-04-27 | 2023-04-27
43874 | Tower A - Sub Structure - B1 to GF - Pour 9A | Complete | Core Wall RCC Works | 2023-02-07 | 2023-02-07 | Col/ Wall Reinf. | 100 | 100 |  | 2023-02-07 | 2023-02-07 | 2023-02-07 | 2023-02-07 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43874 | Tower A - Sub Structure - B1 to GF - Pour 9A | Complete | Core Wall RCC Works | 2023-02-07 | 2023-02-07 | Col/ Wall Reinf. | 100 | 100 |  | 2023-02-07 | 2023-02-07 | 2023-02-07 | 2023-02-07 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43875 | Tower A - Sub Structure - B1 to GF - Pour 9A | Complete | Core Wall RCC Works | 2023-02-07 | 2023-02-07 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2023-02-07 | 2023-02-07 | 2023-02-07 | 2023-02-07 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43875 | Tower A - Sub Structure - B1 to GF - Pour 9A | Complete | Core Wall RCC Works | 2023-02-07 | 2023-02-07 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2023-02-07 | 2023-02-07 | 2023-02-07 | 2023-02-07 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43876 | Tower A - Sub Structure - B1 to GF - Pour 9A | Complete | Core Wall RCC Works | 2023-02-07 | 2023-02-07 | Col/ Wall Casting | 100 | 100 |  | 2023-02-07 | 2023-02-07 | 2023-02-07 | 2023-02-07 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43876 | Tower A - Sub Structure - B1 to GF - Pour 9A | Complete | Core Wall RCC Works | 2023-02-07 | 2023-02-07 | Col/ Wall Casting | 100 | 100 |  | 2023-02-07 | 2023-02-07 | 2023-02-07 | 2023-02-07 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43622 | Tower A - Sub Structure - B2 to B1 - Zone 2A - Sec 2 (14 m) | Complete | Retaining Wall RCC Works | 2023-02-08 | 2023-02-10 | Fwk_Lift 1 RW | 100 | 100 |  | 2023-02-08 | 2023-02-08 | 2023-02-10 | 2023-02-10 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43688 | Tower A - Sub Structure - B2 to B1 - Pour 9B | Complete | RCC Works - Slab | 2023-02-08 | 2023-02-09 | Slab & Staircase Casting | 100 | 100 |  | 2023-02-08 | 2023-02-08 | 2023-02-09 | 2023-02-09 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
43877 | Tower A - Sub Structure - B1 to GF - Pour 9A | Complete | Core Wall RCC Works | 2023-02-08 | 2023-02-08 | Col/ Wall Reinf. | 100 | 100 |  | 2023-02-08 | 2023-02-08 | 2023-02-08 | 2023-02-08 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43877 | Tower A - Sub Structure - B1 to GF - Pour 9A | Complete | Core Wall RCC Works | 2023-02-08 | 2023-02-08 | Col/ Wall Reinf. | 100 | 100 |  | 2023-02-08 | 2023-02-08 | 2023-02-08 | 2023-02-08 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43908 | Tower A - Sub Structure - B1 to GF - Pour 4 | Complete | Core Wall RCC Works | 2023-02-08 | 2023-02-10 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2023-02-08 | 2023-02-08 | 2023-02-10 | 2023-02-10 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43908 | Tower A - Sub Structure - B1 to GF - Pour 4 | Complete | Core Wall RCC Works | 2023-02-08 | 2023-02-10 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2023-02-08 | 2023-02-08 | 2023-02-10 | 2023-02-10 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44373 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-02-08 | 2023-02-15 | Section 10_lift 2 | 100 | 100 |  | 2023-02-08 | 2023-02-08 | 2023-02-15 | 2023-02-15 | NTA_Zone 2 | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
44373 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-02-08 | 2023-02-15 | Section 10_lift 2 | 100 | 100 |  | 2023-02-08 | 2023-02-08 | 2023-02-15 | 2023-02-15 | NTA_Zone 2 | Sub Structure | B3
43695 | Tower A - Sub Structure - B2 to B1 - Pour 5 | Complete | RCC Works - Slab | 2023-02-10 | 2023-02-11 | Slab & Staircase Casting | 100 | 100 |  | 2023-02-10 | 2023-02-10 | 2023-02-11 | 2023-02-11 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
43883 |  | Complete |  | 2023-02-10 | 2023-04-12 | Pour 9B_B1 to GF | 100 | 100 |  | 2023-02-10 | 2023-02-10 | 2023-04-12 | 2023-04-12
43884 | Tower A - Sub Structure - B1 to GF - Pour 9B | Complete | Core Wall RCC Works | 2023-02-10 | 2023-02-10 | Col/ Wall Reinf. | 100 | 100 |  | 2023-02-10 | 2023-02-10 | 2023-02-10 | 2023-02-10 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43884 | Tower A - Sub Structure - B1 to GF - Pour 9B | Complete | Core Wall RCC Works | 2023-02-10 | 2023-02-10 | Col/ Wall Reinf. | 100 | 100 |  | 2023-02-10 | 2023-02-10 | 2023-02-10 | 2023-02-10 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43885 | Tower A - Sub Structure - B1 to GF - Pour 9B | Complete | Core Wall RCC Works | 2023-02-10 | 2023-02-10 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2023-02-10 | 2023-02-10 | 2023-02-10 | 2023-02-10 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43885 | Tower A - Sub Structure - B1 to GF - Pour 9B | Complete | Core Wall RCC Works | 2023-02-10 | 2023-02-10 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2023-02-10 | 2023-02-10 | 2023-02-10 | 2023-02-10 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43886 | Tower A - Sub Structure - B1 to GF - Pour 9B | Complete | Core Wall RCC Works | 2023-02-10 | 2023-02-10 | Col/ Wall Casting | 100 | 100 |  | 2023-02-10 | 2023-02-10 | 2023-02-10 | 2023-02-10 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43886 | Tower A - Sub Structure - B1 to GF - Pour 9B | Complete | Core Wall RCC Works | 2023-02-10 | 2023-02-10 | Col/ Wall Casting | 100 | 100 |  | 2023-02-10 | 2023-02-10 | 2023-02-10 | 2023-02-10 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43909 | Tower A - Sub Structure - B1 to GF - Pour 4 | Complete | Core Wall RCC Works | 2023-02-10 | 2023-02-11 | Col/ Wall Casting | 100 | 100 |  | 2023-02-10 | 2023-02-10 | 2023-02-11 | 2023-02-11 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43909 | Tower A - Sub Structure - B1 to GF - Pour 4 | Complete | Core Wall RCC Works | 2023-02-10 | 2023-02-11 | Col/ Wall Casting | 100 | 100 |  | 2023-02-10 | 2023-02-10 | 2023-02-11 | 2023-02-11 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44240 | Tower A | Complete | High Side Procurement | 2023-02-10 | 2023-10-05 | Typical Slab Formwork | 100 | 100 |  | 2023-02-10 | 2023-02-10 | 2023-10-05 | 2023-10-05 | Tower A | --
44374 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-02-10 | 2023-02-17 | Section 11_lift 2 | 100 | 100 |  | 2023-02-10 | 2023-02-10 | 2023-02-17 | 2023-02-17 | NTA_Zone 2 | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
44374 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Retaining Wall RCC Works | 2023-02-10 | 2023-02-17 | Section 11_lift 2 | 100 | 100 |  | 2023-02-10 | 2023-02-10 | 2023-02-17 | 2023-02-17 | NTA_Zone 2 | Sub Structure | B3
43623 | Tower A - Sub Structure - B2 to B1 - Zone 2A - Sec 2 (14 m) | Complete | Retaining Wall RCC Works | 2023-02-11 | 2023-02-11 | Checking & Casting_Lift 1 | 100 | 100 |  | 2023-02-11 | 2023-02-11 | 2023-02-11 | 2023-02-11 | Tower A | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
43857 | Tower A - Sub Structure - B1 to GF - Pour 7 | Complete | Core Wall RCC Works | 2023-02-11 | 2023-02-13 | Col/ Wall Reinf. | 100 | 100 |  | 2023-02-11 | 2023-02-11 | 2023-02-13 | 2023-02-13 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43857 | Tower A - Sub Structure - B1 to GF - Pour 7 | Complete | Core Wall RCC Works | 2023-02-11 | 2023-02-13 | Col/ Wall Reinf. | 100 | 100 |  | 2023-02-11 | 2023-02-11 | 2023-02-13 | 2023-02-13 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43878 | Tower A - Sub Structure - B1 to GF - Pour 9A | Complete | Core Wall RCC Works | 2023-02-11 | 2023-02-11 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2023-02-11 | 2023-02-11 | 2023-02-11 | 2023-02-11 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43878 | Tower A - Sub Structure - B1 to GF - Pour 9A | Complete | Core Wall RCC Works | 2023-02-11 | 2023-02-11 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2023-02-11 | 2023-02-11 | 2023-02-11 | 2023-02-11 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43887 | Tower A - Sub Structure - B1 to GF - Pour 9B | Complete | Core Wall RCC Works | 2023-02-11 | 2023-02-11 | Col/ Wall Reinf. | 100 | 100 |  | 2023-02-11 | 2023-02-11 | 2023-02-11 | 2023-02-11 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43887 | Tower A - Sub Structure - B1 to GF - Pour 9B | Complete | Core Wall RCC Works | 2023-02-11 | 2023-02-11 | Col/ Wall Reinf. | 100 | 100 |  | 2023-02-11 | 2023-02-11 | 2023-02-11 | 2023-02-11 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43652 | Tower A - Sub Structure - B2 to B1 - Pour 3 | Complete | RCC Works - Slab | 2023-02-13 | 2023-02-17 | Slab & Staircase Reinf. | 100 | 100 |  | 2023-02-13 | 2023-02-13 | 2023-02-17 | 2023-02-17 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
43659 | Tower A - Sub Structure - B2 to B1 - Pour 1B & 6 | Complete | RCC Works - Slab | 2023-02-13 | 2023-02-20 | Slab & Staircase Reinf. | 100 | 100 |  | 2023-02-13 | 2023-02-13 | 2023-02-20 | 2023-02-20 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
43893 |  | Complete |  | 2023-02-13 | 2023-04-12 | Pour 5_B1 to GF | 100 | 100 |  | 2023-02-13 | 2023-02-13 | 2023-04-12 | 2023-04-12
43894 | Tower A - Sub Structure - B1 to GF - Pour 5 | Complete | Core Wall RCC Works | 2023-02-13 | 2023-02-20 | Col/ Wall Reinf. | 100 | 100 |  | 2023-02-13 | 2023-02-13 | 2023-02-20 | 2023-02-20 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43894 | Tower A - Sub Structure - B1 to GF - Pour 5 | Complete | Core Wall RCC Works | 2023-02-13 | 2023-02-20 | Col/ Wall Reinf. | 100 | 100 |  | 2023-02-13 | 2023-02-13 | 2023-02-20 | 2023-02-20 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43895 | Tower A - Sub Structure - B1 to GF - Pour 5 | Complete | Core Wall RCC Works | 2023-02-13 | 2023-02-23 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2023-02-13 | 2023-02-13 | 2023-02-23 | 2023-02-23 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43895 | Tower A - Sub Structure - B1 to GF - Pour 5 | Complete | Core Wall RCC Works | 2023-02-13 | 2023-02-23 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2023-02-13 | 2023-02-13 | 2023-02-23 | 2023-02-23 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43910 | Tower A - Sub Structure - B1 to GF - Pour 4 | Complete | RCC Works - Slab | 2023-02-13 | 2023-02-25 | Slab & Staircase Fwk. | 100 | 100 |  | 2023-02-13 | 2023-02-13 | 2023-02-25 | 2023-02-25 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
48017 |  | Complete |  | 2023-02-13 | 2023-08-31 | Contractor Finalization | 100 | 100 |  | 2023-02-13 | 2023-02-13 | 2023-08-31 | 2023-08-31
48020 |  | Complete |  | 2023-02-13 | 2023-03-20 | MEP Re-route & Termination | 100 | 100 |  | 2023-02-13 | 2023-02-13 | 2023-03-20 | 2023-03-20
43858 | Tower A - Sub Structure - B1 to GF - Pour 7 | Complete | Core Wall RCC Works | 2023-02-14 | 2023-02-16 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2023-02-14 | 2023-02-14 | 2023-02-16 | 2023-02-16 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43858 | Tower A - Sub Structure - B1 to GF - Pour 7 | Complete | Core Wall RCC Works | 2023-02-14 | 2023-02-16 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2023-02-14 | 2023-02-14 | 2023-02-16 | 2023-02-16 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43879 | Tower A - Sub Structure - B1 to GF - Pour 9A | Complete | Core Wall RCC Works | 2023-02-14 | 2023-02-14 | Col/ Wall Casting | 100 | 100 |  | 2023-02-14 | 2023-02-14 | 2023-02-14 | 2023-02-14 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43879 | Tower A - Sub Structure - B1 to GF - Pour 9A | Complete | Core Wall RCC Works | 2023-02-14 | 2023-02-14 | Col/ Wall Casting | 100 | 100 |  | 2023-02-14 | 2023-02-14 | 2023-02-14 | 2023-02-14 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43888 | Tower A - Sub Structure - B1 to GF - Pour 9B | Complete | Core Wall RCC Works | 2023-02-15 | 2023-02-15 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2023-02-15 | 2023-02-15 | 2023-02-15 | 2023-02-15 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43888 | Tower A - Sub Structure - B1 to GF - Pour 9B | Complete | Core Wall RCC Works | 2023-02-15 | 2023-02-15 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2023-02-15 | 2023-02-15 | 2023-02-15 | 2023-02-15 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43896 | Tower A - Sub Structure - B1 to GF - Pour 5 | Complete | Core Wall RCC Works | 2023-02-15 | 2023-02-25 | Col/ Wall Casting | 100 | 100 |  | 2023-02-15 | 2023-02-15 | 2023-02-25 | 2023-02-25 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43896 | Tower A - Sub Structure - B1 to GF - Pour 5 | Complete | Core Wall RCC Works | 2023-02-15 | 2023-02-25 | Col/ Wall Casting | 100 | 100 |  | 2023-02-15 | 2023-02-15 | 2023-02-25 | 2023-02-25 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44333 |  | Complete |  | 2023-02-15 | 2023-03-16 | Pour 1 | 100 | 100 |  | 2023-02-15 | 2023-02-15 | 2023-03-16 | 2023-03-16
44334 | NTA_Zone 2 - Sub Structure - B3 to B2 - Pour 1 | Complete | RCC Works - Vertical | 2023-02-15 | 2023-03-03 | Columns/ Walls_NTA | 100 | 100 |  | 2023-02-15 | 2023-02-15 | 2023-03-03 | 2023-03-03 | NTA_Zone 2 | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
44334 | NTA_Zone 2 - Sub Structure - B3 to B2 - Pour 1 | Complete | RCC Works - Vertical | 2023-02-15 | 2023-03-03 | Columns/ Walls_NTA | 100 | 100 |  | 2023-02-15 | 2023-02-15 | 2023-03-03 | 2023-03-03 | NTA_Zone 2 | Sub Structure | B3
43859 | Tower A - Sub Structure - B1 to GF - Pour 7 | Complete | Core Wall RCC Works | 2023-02-16 | 2023-02-17 | Col/ Wall Casting | 100 | 100 |  | 2023-02-16 | 2023-02-16 | 2023-02-17 | 2023-02-17 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43859 | Tower A - Sub Structure - B1 to GF - Pour 7 | Complete | Core Wall RCC Works | 2023-02-16 | 2023-02-17 | Col/ Wall Casting | 100 | 100 |  | 2023-02-16 | 2023-02-16 | 2023-02-17 | 2023-02-17 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43880 | Tower A - Sub Structure - B1 to GF - Pour 9A | Complete | RCC Works - Slab | 2023-02-16 | 2023-03-01 | Slab & Staircase Fwk. | 100 | 100 |  | 2023-02-16 | 2023-02-16 | 2023-03-01 | 2023-03-01 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
44309 | NTA_Zone 2 - Foundation - Pour 3 | Complete | Foundation RCC Works | 2023-02-16 | 2023-02-23 | Fwk & Casting_NTA | 100 | 100 |  | 2023-02-16 | 2023-02-16 | 2023-02-23 | 2023-02-23 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44309 | NTA_Zone 2 - Foundation - Pour 3 | Complete | Foundation RCC Works | 2023-02-16 | 2023-02-23 | Fwk & Casting_NTA | 100 | 100 |  | 2023-02-16 | 2023-02-16 | 2023-02-23 | 2023-02-23 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44309 | NTA_Zone 2 - Foundation - Pour 3 | Complete | Foundation RCC Works | 2023-02-16 | 2023-02-23 | Fwk & Casting_NTA | 100 | 100 |  | 2023-02-16 | 2023-02-16 | 2023-02-23 | 2023-02-23 | NTA_Zone 2 | Foundation
44321 | NTA_Zone 2 - Foundation - Pour 5 | Complete | Foundation RCC Works | 2023-02-16 | 2023-05-27 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2023-02-16 | 2023-02-16 | 2023-05-27 | 2023-05-27 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44321 | NTA_Zone 2 - Foundation - Pour 5 | Complete | Foundation RCC Works | 2023-02-16 | 2023-05-27 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2023-02-16 | 2023-02-16 | 2023-05-27 | 2023-05-27 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44321 | NTA_Zone 2 - Foundation - Pour 5 | Complete | Foundation RCC Works | 2023-02-16 | 2023-05-27 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2023-02-16 | 2023-02-16 | 2023-05-27 | 2023-05-27 | NTA_Zone 2 | Foundation
43889 | Tower A - Sub Structure - B1 to GF - Pour 9B | Complete | Core Wall RCC Works | 2023-02-17 | 2023-02-17 | Col/ Wall Casting | 100 | 100 |  | 2023-02-17 | 2023-02-17 | 2023-02-17 | 2023-02-17 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43889 | Tower A - Sub Structure - B1 to GF - Pour 9B | Complete | Core Wall RCC Works | 2023-02-17 | 2023-02-17 | Col/ Wall Casting | 100 | 100 |  | 2023-02-17 | 2023-02-17 | 2023-02-17 | 2023-02-17 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44304 | NTA_Zone 2 - Foundation - Pour 2 | Complete | Foundation RCC Works | 2023-02-17 | 2023-03-10 | Fwk & Casting_NTA | 100 | 100 |  | 2023-02-17 | 2023-02-17 | 2023-03-10 | 2023-03-10 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44304 | NTA_Zone 2 - Foundation - Pour 2 | Complete | Foundation RCC Works | 2023-02-17 | 2023-03-10 | Fwk & Casting_NTA | 100 | 100 |  | 2023-02-17 | 2023-02-17 | 2023-03-10 | 2023-03-10 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44304 | NTA_Zone 2 - Foundation - Pour 2 | Complete | Foundation RCC Works | 2023-02-17 | 2023-03-10 | Fwk & Casting_NTA | 100 | 100 |  | 2023-02-17 | 2023-02-17 | 2023-03-10 | 2023-03-10 | NTA_Zone 2 | Foundation
44316 | NTA_Zone 2 - Foundation - Pour 4 | Complete | Foundation RCC Works | 2023-02-17 | 2023-02-28 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2023-02-17 | 2023-02-17 | 2023-02-28 | 2023-02-28 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44316 | NTA_Zone 2 - Foundation - Pour 4 | Complete | Foundation RCC Works | 2023-02-17 | 2023-02-28 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2023-02-17 | 2023-02-17 | 2023-02-28 | 2023-02-28 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44316 | NTA_Zone 2 - Foundation - Pour 4 | Complete | Foundation RCC Works | 2023-02-17 | 2023-02-28 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2023-02-17 | 2023-02-17 | 2023-02-28 | 2023-02-28 | NTA_Zone 2 | Foundation
43645 | Tower A - Sub Structure - B2 to B1 - Pour 1A & 2 | Complete | RCC Works - Slab | 2023-02-18 | 2023-02-22 | Slab & Staircase Reinf. | 100 | 100 |  | 2023-02-18 | 2023-02-18 | 2023-02-22 | 2023-02-22 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
43653 | Tower A - Sub Structure - B2 to B1 - Pour 3 | Complete | RCC Works - Slab | 2023-02-18 | 2023-02-20 | Slab & Staircase Casting | 100 | 100 |  | 2023-02-18 | 2023-02-18 | 2023-02-20 | 2023-02-20 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
43860 | Tower A - Sub Structure - B1 to GF - Pour 7 | Complete | RCC Works - Slab | 2023-02-18 | 2023-03-03 | Slab & Staircase Fwk. | 100 | 100 |  | 2023-02-18 | 2023-02-18 | 2023-03-03 | 2023-03-03 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
43890 | Tower A - Sub Structure - B1 to GF - Pour 9B | Complete | RCC Works - Slab | 2023-02-20 | 2023-03-04 | Slab & Staircase Fwk. | 100 | 100 |  | 2023-02-20 | 2023-02-20 | 2023-03-04 | 2023-03-04 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
43660 | Tower A - Sub Structure - B2 to B1 - Pour 1B & 6 | Complete | RCC Works - Slab | 2023-02-21 | 2023-02-22 | Slab & Staircase Casting | 100 | 100 |  | 2023-02-21 | 2023-02-21 | 2023-02-22 | 2023-02-22 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
43646 | Tower A - Sub Structure - B2 to B1 - Pour 1A & 2 | Complete | RCC Works - Slab | 2023-02-23 | 2023-02-24 | Slab & Staircase Casting | 100 | 100 |  | 2023-02-23 | 2023-02-23 | 2023-02-24 | 2023-02-24 | Tower A | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
43704 |  | Complete |  | 2023-02-23 | 2023-04-25 | Retaining Wall_B1 to GF_Zone 1A | 100 | 100 |  | 2023-02-23 | 2023-02-23 | 2023-04-25 | 2023-04-25
43705 |  | Complete |  | 2023-02-23 | 2023-03-23 | Section 1_13m | 100 | 100 |  | 2023-02-23 | 2023-02-23 | 2023-03-23 | 2023-03-23
43706 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 1 (13 m) | Complete | Retaining Wall RCC Works | 2023-02-23 | 2023-02-25 | Liner Wall Fwk & Casting | 100 | 100 |  | 2023-02-23 | 2023-02-23 | 2023-02-25 | 2023-02-25 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43715 |  | Complete |  | 2023-02-23 | 2023-03-22 | Section 4_10m | 100 | 100 |  | 2023-02-23 | 2023-02-23 | 2023-03-22 | 2023-03-22
43716 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 4 (10 m) | Complete | Retaining Wall RCC Works | 2023-02-23 | 2023-02-25 | Liner Wall Fwk & Casting | 100 | 100 |  | 2023-02-23 | 2023-02-23 | 2023-02-25 | 2023-02-25 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43725 |  | Complete |  | 2023-02-23 | 2023-04-08 | Section 3_10m | 100 | 100 |  | 2023-02-23 | 2023-02-23 | 2023-04-08 | 2023-04-08
43726 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 3 (10 m) | Complete | Retaining Wall RCC Works | 2023-02-23 | 2023-02-25 | Liner Wall Fwk & Casting | 100 | 100 |  | 2023-02-23 | 2023-02-23 | 2023-02-25 | 2023-02-25 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43735 |  | Complete |  | 2023-02-23 | 2023-04-08 | Section 5_10m | 100 | 100 |  | 2023-02-23 | 2023-02-23 | 2023-04-08 | 2023-04-08
43736 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 5 (10 m) | Complete | Retaining Wall RCC Works | 2023-02-23 | 2023-02-25 | Liner Wall Fwk & Casting | 100 | 100 |  | 2023-02-23 | 2023-02-23 | 2023-02-25 | 2023-02-25 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43745 |  | Complete |  | 2023-02-23 | 2023-04-25 | Section 2_10m | 100 | 100 |  | 2023-02-23 | 2023-02-23 | 2023-04-25 | 2023-04-25
43746 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 2 (10 m) | Complete | Retaining Wall RCC Works | 2023-02-23 | 2023-02-25 | Liner Wall Fwk & Casting | 100 | 100 |  | 2023-02-23 | 2023-02-23 | 2023-02-25 | 2023-02-25 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43755 |  | Complete |  | 2023-02-23 | 2023-04-25 | Section 6_10m | 100 | 100 |  | 2023-02-23 | 2023-02-23 | 2023-04-25 | 2023-04-25
43756 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 6 (10 m) | Complete | Retaining Wall RCC Works | 2023-02-23 | 2023-02-25 | Liner Wall Fwk & Casting | 100 | 100 |  | 2023-02-23 | 2023-02-23 | 2023-02-25 | 2023-02-25 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43765 |  | Complete |  | 2023-02-23 | 2023-04-27 | Retaining Wall_B1 to GF_Zone 2A | 100 | 100 |  | 2023-02-23 | 2023-02-23 | 2023-04-27 | 2023-04-27
43766 |  | Complete |  | 2023-02-23 | 2023-03-23 | Section 1_11.5m | 100 | 100 |  | 2023-02-23 | 2023-02-23 | 2023-03-23 | 2023-03-23
43767 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 1 (11.5 m) | Complete | Retaining Wall RCC Works | 2023-02-23 | 2023-02-25 | Liner Wall Fwk & Casting | 100 | 100 |  | 2023-02-23 | 2023-02-23 | 2023-02-25 | 2023-02-25 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43776 |  | Complete |  | 2023-02-23 | 2023-04-10 | Section 3_10.8m | 100 | 100 |  | 2023-02-23 | 2023-02-23 | 2023-04-10 | 2023-04-10
43777 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 3 (10.8 m) | Complete | Retaining Wall RCC Works | 2023-02-23 | 2023-02-25 | Liner Wall Fwk & Casting | 100 | 100 |  | 2023-02-23 | 2023-02-23 | 2023-02-25 | 2023-02-25 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43786 |  | Complete |  | 2023-02-23 | 2023-04-27 | Section 2_14m | 100 | 100 |  | 2023-02-23 | 2023-02-23 | 2023-04-27 | 2023-04-27
43787 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 2 (14 m) | Complete | Retaining Wall RCC Works | 2023-02-23 | 2023-02-25 | Liner Wall Fwk & Casting | 100 | 100 |  | 2023-02-23 | 2023-02-23 | 2023-02-25 | 2023-02-25 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43796 |  | Complete |  | 2023-02-23 | 2023-03-21 | Section 4_8.2m | 100 | 100 |  | 2023-02-23 | 2023-02-23 | 2023-03-21 | 2023-03-21
43797 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 4 (8.2 m) | Complete | Retaining Wall RCC Works | 2023-02-23 | 2023-02-25 | Liner Wall Fwk & Casting | 100 | 100 |  | 2023-02-23 | 2023-02-23 | 2023-02-25 | 2023-02-25 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43806 |  | Complete |  | 2023-02-23 | 2023-04-06 | Section 5_8m | 100 | 100 |  | 2023-02-23 | 2023-02-23 | 2023-04-06 | 2023-04-06
43807 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 5 (8 m) | Complete | Retaining Wall RCC Works | 2023-02-23 | 2023-02-25 | Liner Wall Fwk & Casting | 100 | 100 |  | 2023-02-23 | 2023-02-23 | 2023-02-25 | 2023-02-25 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
44339 |  | Complete |  | 2023-02-24 | 2023-04-06 | Pour 3 | 100 | 100 |  | 2023-02-24 | 2023-02-24 | 2023-04-06 | 2023-04-06
44340 | NTA_Zone 2 - Sub Structure - B3 to B2 - Pour 3 | Complete | RCC Works - Vertical | 2023-02-24 | 2023-03-20 | Columns/ Walls_NTA | 100 | 100 |  | 2023-02-24 | 2023-02-24 | 2023-03-20 | 2023-03-20 | NTA_Zone 2 | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
44340 | NTA_Zone 2 - Sub Structure - B3 to B2 - Pour 3 | Complete | RCC Works - Vertical | 2023-02-24 | 2023-03-20 | Columns/ Walls_NTA | 100 | 100 |  | 2023-02-24 | 2023-02-24 | 2023-03-20 | 2023-03-20 | NTA_Zone 2 | Sub Structure | B3
40141 |  | Complete |  | 2023-02-25 | 2024-02-12 | B2 to B1_TA & NTA | 100 | 100 |  | 2023-02-25 | 2023-02-25 | 2024-02-12 | 2024-02-12
40141 |  | Complete |  | 2023-02-25 | 2024-02-12 | B2 to B1_TA & NTA | 100 | 100 |  | 2023-02-25 | 2023-02-25 | 2024-02-12 | 2024-02-12 |  |  |  | Finishes | Gypsum Plastering Works
40142 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 | Complete | Partition Wall-Blockwork | 2023-02-25 | 2023-03-21 | De-shuttering & Area clearance | 100 | 100 |  | 2023-02-25 | 2023-02-25 | 2023-03-21 | 2023-03-21 | Tower A | Sub Structure | B2
43816 |  | Complete |  | 2023-02-25 | 2023-03-28 | Core Wall B1 to GF | 100 | 100 |  | 2023-02-25 | 2023-02-25 | 2023-03-28 | 2023-03-28
43817 | Tower A - Sub Structure - B1 to GF | Complete | Core Wall RCC Works | 2023-02-25 | 2023-03-09 | CW Reinf_lift 1 | 100 | 100 |  | 2023-02-25 | 2023-02-25 | 2023-03-09 | 2023-03-09 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43911 | Tower A - Sub Structure - B1 to GF - Pour 4 | Complete | RCC Works - Slab | 2023-02-25 | 2023-03-01 | Slab & Staircase Reinf. | 100 | 100 |  | 2023-02-25 | 2023-02-25 | 2023-03-01 | 2023-03-01 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
43707 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 1 (13 m) | Complete | Retaining Wall RCC Works | 2023-02-27 | 2023-03-01 | Waterproofing along the liner wall | 100 | 100 |  | 2023-02-27 | 2023-02-27 | 2023-03-01 | 2023-03-01 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43717 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 4 (10 m) | Complete | Retaining Wall RCC Works | 2023-02-27 | 2023-03-01 | Waterproofing along the liner wall | 100 | 100 |  | 2023-02-27 | 2023-02-27 | 2023-03-01 | 2023-03-01 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43727 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 3 (10 m) | Complete | Retaining Wall RCC Works | 2023-02-27 | 2023-03-01 | Waterproofing along the liner wall | 100 | 100 |  | 2023-02-27 | 2023-02-27 | 2023-03-01 | 2023-03-01 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43737 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 5 (10 m) | Complete | Retaining Wall RCC Works | 2023-02-27 | 2023-03-01 | Waterproofing along the liner wall | 100 | 100 |  | 2023-02-27 | 2023-02-27 | 2023-03-01 | 2023-03-01 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43747 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 2 (10 m) | Complete | Retaining Wall RCC Works | 2023-02-27 | 2023-03-01 | Waterproofing along the liner wall | 100 | 100 |  | 2023-02-27 | 2023-02-27 | 2023-03-01 | 2023-03-01 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43757 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 6 (10 m) | Complete | Retaining Wall RCC Works | 2023-02-27 | 2023-03-01 | Waterproofing along the liner wall | 100 | 100 |  | 2023-02-27 | 2023-02-27 | 2023-03-01 | 2023-03-01 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43768 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 1 (11.5 m) | Complete | Retaining Wall RCC Works | 2023-02-27 | 2023-03-01 | Waterproofing along the liner wall | 100 | 100 |  | 2023-02-27 | 2023-02-27 | 2023-03-01 | 2023-03-01 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43778 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 3 (10.8 m) | Complete | Retaining Wall RCC Works | 2023-02-27 | 2023-03-01 | Waterproofing along the liner wall | 100 | 100 |  | 2023-02-27 | 2023-02-27 | 2023-03-01 | 2023-03-01 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43788 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 2 (14 m) | Complete | Retaining Wall RCC Works | 2023-02-27 | 2023-03-01 | Waterproofing along the liner wall | 100 | 100 |  | 2023-02-27 | 2023-02-27 | 2023-03-01 | 2023-03-01 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43798 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 4 (8.2 m) | Complete | Retaining Wall RCC Works | 2023-02-27 | 2023-03-01 | Waterproofing along the liner wall | 100 | 100 |  | 2023-02-27 | 2023-02-27 | 2023-03-01 | 2023-03-01 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43808 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 5 (8 m) | Complete | Retaining Wall RCC Works | 2023-02-27 | 2023-03-01 | Waterproofing along the liner wall | 100 | 100 |  | 2023-02-27 | 2023-02-27 | 2023-03-01 | 2023-03-01 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43897 | Tower A - Sub Structure - B1 to GF - Pour 5 | Complete | Core Wall RCC Works | 2023-02-27 | 2023-03-01 | Col/ Wall Reinf. | 100 | 100 |  | 2023-02-27 | 2023-02-27 | 2023-03-01 | 2023-03-01 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43897 | Tower A - Sub Structure - B1 to GF - Pour 5 | Complete | Core Wall RCC Works | 2023-02-27 | 2023-03-01 | Col/ Wall Reinf. | 100 | 100 |  | 2023-02-27 | 2023-02-27 | 2023-03-01 | 2023-03-01 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44335 | NTA_Zone 2 - Sub Structure - B3 to B2 - Pour 1 | Complete | RCC Works - Slab | 2023-02-27 | 2023-03-16 | Slab_NTA | 100 | 100 |  | 2023-02-27 | 2023-02-27 | 2023-03-16 | 2023-03-16 | NTA_Zone 2 | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
44335 | NTA_Zone 2 - Sub Structure - B3 to B2 - Pour 1 | Complete | RCC Works - Slab | 2023-02-27 | 2023-03-16 | Slab_NTA | 100 | 100 |  | 2023-02-27 | 2023-02-27 | 2023-03-16 | 2023-03-16 | NTA_Zone 2 | Sub Structure | B3
44317 | NTA_Zone 2 - Foundation - Pour 4 | Complete | Foundation RCC Works | 2023-03-01 | 2023-03-06 | Fwk & Casting_NTA | 100 | 100 |  | 2023-03-01 | 2023-03-01 | 2023-03-06 | 2023-03-06 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44317 | NTA_Zone 2 - Foundation - Pour 4 | Complete | Foundation RCC Works | 2023-03-01 | 2023-03-06 | Fwk & Casting_NTA | 100 | 100 |  | 2023-03-01 | 2023-03-01 | 2023-03-06 | 2023-03-06 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44317 | NTA_Zone 2 - Foundation - Pour 4 | Complete | Foundation RCC Works | 2023-03-01 | 2023-03-06 | Fwk & Casting_NTA | 100 | 100 |  | 2023-03-01 | 2023-03-01 | 2023-03-06 | 2023-03-06 | NTA_Zone 2 | Foundation
44329 | NTA_Zone 2 - Foundation - Pour 6 | Complete | Foundation RCC Works | 2023-03-01 | 2023-04-04 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2023-03-01 | 2023-03-01 | 2023-04-04 | 2023-04-04 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44329 | NTA_Zone 2 - Foundation - Pour 6 | Complete | Foundation RCC Works | 2023-03-01 | 2023-04-04 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2023-03-01 | 2023-03-01 | 2023-04-04 | 2023-04-04 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44329 | NTA_Zone 2 - Foundation - Pour 6 | Complete | Foundation RCC Works | 2023-03-01 | 2023-04-04 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2023-03-01 | 2023-03-01 | 2023-04-04 | 2023-04-04 | NTA_Zone 2 | Foundation
43708 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 1 (13 m) | Complete | Retaining Wall RCC Works | 2023-03-02 | 2023-03-04 | Retaining Wall_Reinf_Lift 1 | 100 | 100 |  | 2023-03-02 | 2023-03-02 | 2023-03-04 | 2023-03-04 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43718 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 4 (10 m) | Complete | Retaining Wall RCC Works | 2023-03-02 | 2023-03-04 | Retaining Wall_Reinf_Lift 1 | 100 | 100 |  | 2023-03-02 | 2023-03-02 | 2023-03-04 | 2023-03-04 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43728 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 3 (10 m) | Complete | Retaining Wall RCC Works | 2023-03-02 | 2023-03-04 | Retaining Wall_Reinf_Lift 1 | 100 | 100 |  | 2023-03-02 | 2023-03-02 | 2023-03-04 | 2023-03-04 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43738 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 5 (10 m) | Complete | Retaining Wall RCC Works | 2023-03-02 | 2023-03-04 | Retaining Wall_Reinf_Lift 1 | 100 | 100 |  | 2023-03-02 | 2023-03-02 | 2023-03-04 | 2023-03-04 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43748 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 2 (10 m) | Complete | Retaining Wall RCC Works | 2023-03-02 | 2023-03-04 | Retaining Wall_Reinf_Lift 1 | 100 | 100 |  | 2023-03-02 | 2023-03-02 | 2023-03-04 | 2023-03-04 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43758 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 6 (10 m) | Complete | Retaining Wall RCC Works | 2023-03-02 | 2023-03-04 | Retaining Wall_Reinf_Lift 1 | 100 | 100 |  | 2023-03-02 | 2023-03-02 | 2023-03-04 | 2023-03-04 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43769 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 1 (11.5 m) | Complete | Retaining Wall RCC Works | 2023-03-02 | 2023-03-04 | Retaining Wall_Reinf_Lift 1 | 100 | 100 |  | 2023-03-02 | 2023-03-02 | 2023-03-04 | 2023-03-04 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43779 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 3 (10.8 m) | Complete | Retaining Wall RCC Works | 2023-03-02 | 2023-03-04 | Retaining Wall_Reinf_Lift 1 | 100 | 100 |  | 2023-03-02 | 2023-03-02 | 2023-03-04 | 2023-03-04 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43789 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 2 (14 m) | Complete | Retaining Wall RCC Works | 2023-03-02 | 2023-03-04 | Retaining Wall_Reinf_Lift 1 | 100 | 100 |  | 2023-03-02 | 2023-03-02 | 2023-03-04 | 2023-03-04 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43799 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 4 (8.2 m) | Complete | Retaining Wall RCC Works | 2023-03-02 | 2023-03-03 | Retaining Wall_Reinf_Lift 1 | 100 | 100 |  | 2023-03-02 | 2023-03-02 | 2023-03-03 | 2023-03-03 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43809 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 5 (8 m) | Complete | Retaining Wall RCC Works | 2023-03-02 | 2023-03-03 | Retaining Wall_Reinf_Lift 1 | 100 | 100 |  | 2023-03-02 | 2023-03-02 | 2023-03-03 | 2023-03-03 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43881 | Tower A - Sub Structure - B1 to GF - Pour 9A | Complete | RCC Works - Slab | 2023-03-02 | 2023-03-03 | Slab & Staircase Reinf. | 100 | 100 |  | 2023-03-02 | 2023-03-02 | 2023-03-03 | 2023-03-03 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
43898 | Tower A - Sub Structure - B1 to GF - Pour 5 | Complete | Core Wall RCC Works | 2023-03-02 | 2023-03-04 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2023-03-02 | 2023-03-02 | 2023-03-04 | 2023-03-04 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43898 | Tower A - Sub Structure - B1 to GF - Pour 5 | Complete | Core Wall RCC Works | 2023-03-02 | 2023-03-04 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2023-03-02 | 2023-03-02 | 2023-03-04 | 2023-03-04 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43912 | Tower A - Sub Structure - B1 to GF - Pour 4 | Complete | RCC Works - Slab | 2023-03-02 | 2023-03-03 | Slab & Staircase Casting | 100 | 100 |  | 2023-03-02 | 2023-03-02 | 2023-03-03 | 2023-03-03 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
43818 | Tower A - Sub Structure - B1 to GF | Complete | Core Wall RCC Works | 2023-03-03 | 2023-03-13 | CW Fwk (3.5m lift)_lift 1 | 100 | 100 |  | 2023-03-03 | 2023-03-03 | 2023-03-13 | 2023-03-13 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43861 | Tower A - Sub Structure - B1 to GF - Pour 7 | Complete | RCC Works - Slab | 2023-03-03 | 2023-03-07 | Slab & Staircase Reinf. | 100 | 100 |  | 2023-03-03 | 2023-03-03 | 2023-03-07 | 2023-03-07 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
43800 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 4 (8.2 m) | Complete | Retaining Wall RCC Works | 2023-03-04 | 2023-03-07 | Fwk_Lift 1 RW | 100 | 100 |  | 2023-03-04 | 2023-03-04 | 2023-03-07 | 2023-03-07 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43899 | Tower A - Sub Structure - B1 to GF - Pour 5 | Complete | Core Wall RCC Works | 2023-03-04 | 2023-03-06 | Col/ Wall Casting | 100 | 100 |  | 2023-03-04 | 2023-03-04 | 2023-03-06 | 2023-03-06 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43899 | Tower A - Sub Structure - B1 to GF - Pour 5 | Complete | Core Wall RCC Works | 2023-03-04 | 2023-03-06 | Col/ Wall Casting | 100 | 100 |  | 2023-03-04 | 2023-03-04 | 2023-03-06 | 2023-03-06 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43709 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 1 (13 m) | Complete | Retaining Wall RCC Works | 2023-03-06 | 2023-03-09 | Fwk_Lift 1 RW | 100 | 100 |  | 2023-03-06 | 2023-03-06 | 2023-03-09 | 2023-03-09 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43719 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 4 (10 m) | Complete | Retaining Wall RCC Works | 2023-03-06 | 2023-03-09 | Fwk_Lift 1 RW | 100 | 100 |  | 2023-03-06 | 2023-03-06 | 2023-03-09 | 2023-03-09 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43770 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 1 (11.5 m) | Complete | Retaining Wall RCC Works | 2023-03-06 | 2023-03-09 | Fwk_Lift 1 RW | 100 | 100 |  | 2023-03-06 | 2023-03-06 | 2023-03-09 | 2023-03-09 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43891 | Tower A - Sub Structure - B1 to GF - Pour 9B | Complete | RCC Works - Slab | 2023-03-06 | 2023-03-07 | Slab & Staircase Reinf. | 100 | 100 |  | 2023-03-06 | 2023-03-06 | 2023-03-07 | 2023-03-07 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
43900 | Tower A - Sub Structure - B1 to GF - Pour 5 | Complete | RCC Works - Slab | 2023-03-07 | 2023-03-21 | Slab & Staircase Fwk. | 100 | 100 |  | 2023-03-07 | 2023-03-07 | 2023-03-21 | 2023-03-21 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
44342 |  | Complete |  | 2023-03-07 | 2023-04-05 | Pour 4 | 100 | 100 |  | 2023-03-07 | 2023-03-07 | 2023-04-05 | 2023-04-05
44343 | NTA_Zone 2 - Sub Structure - B3 to B2 - Pour 4 | Complete | RCC Works - Vertical | 2023-03-07 | 2023-03-24 | Columns/ Walls_NTA | 100 | 100 |  | 2023-03-07 | 2023-03-07 | 2023-03-24 | 2023-03-24 | NTA_Zone 2 | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
44343 | NTA_Zone 2 - Sub Structure - B3 to B2 - Pour 4 | Complete | RCC Works - Vertical | 2023-03-07 | 2023-03-24 | Columns/ Walls_NTA | 100 | 100 |  | 2023-03-07 | 2023-03-07 | 2023-03-24 | 2023-03-24 | NTA_Zone 2 | Sub Structure | B3
43801 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 4 (8.2 m) | Complete | Retaining Wall RCC Works | 2023-03-09 | 2023-03-09 | Checking & Casting_Lift 1 | 100 | 100 |  | 2023-03-09 | 2023-03-09 | 2023-03-09 | 2023-03-09 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
48018 |  | Complete |  | 2023-03-09 | 2023-08-25 | Demolition | 100 | 100 |  | 2023-03-09 | 2023-03-09 | 2023-08-25 | 2023-08-25
43710 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 1 (13 m) | Complete | Retaining Wall RCC Works | 2023-03-10 | 2023-03-10 | Checking & Casting_Lift 1 | 100 | 100 |  | 2023-03-10 | 2023-03-10 | 2023-03-10 | 2023-03-10 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43720 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 4 (10 m) | Complete | Retaining Wall RCC Works | 2023-03-10 | 2023-03-10 | Checking & Casting_Lift 1 | 100 | 100 |  | 2023-03-10 | 2023-03-10 | 2023-03-10 | 2023-03-10 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43771 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 1 (11.5 m) | Complete | Retaining Wall RCC Works | 2023-03-10 | 2023-03-10 | Checking & Casting_Lift 1 | 100 | 100 |  | 2023-03-10 | 2023-03-10 | 2023-03-10 | 2023-03-10 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43802 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 4 (8.2 m) | Complete | Retaining Wall RCC Works | 2023-03-10 | 2023-03-14 | De-stressing & Removal of Anchor | 100 | 100 |  | 2023-03-10 | 2023-03-10 | 2023-03-14 | 2023-03-14 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43711 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 1 (13 m) | Complete | Retaining Wall RCC Works | 2023-03-11 | 2023-03-15 | De-stressing & Removal of Anchor | 100 | 100 |  | 2023-03-11 | 2023-03-11 | 2023-03-15 | 2023-03-15 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43721 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 4 (10 m) | Complete | Retaining Wall RCC Works | 2023-03-11 | 2023-03-14 | De-stressing & Removal of Anchor | 100 | 100 |  | 2023-03-11 | 2023-03-11 | 2023-03-14 | 2023-03-14 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43772 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 1 (11.5 m) | Complete | Retaining Wall RCC Works | 2023-03-11 | 2023-03-15 | De-stressing & Removal of Anchor | 100 | 100 |  | 2023-03-11 | 2023-03-11 | 2023-03-15 | 2023-03-15 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
44336 |  | Complete |  | 2023-03-11 | 2023-04-08 | Pour 2 | 100 | 100 |  | 2023-03-11 | 2023-03-11 | 2023-04-08 | 2023-04-08
44337 | NTA_Zone 2 - Sub Structure - B3 to B2 - Pour 2 | Complete | RCC Works - Vertical | 2023-03-11 | 2023-03-28 | Columns/ Walls_NTA | 100 | 100 |  | 2023-03-11 | 2023-03-11 | 2023-03-28 | 2023-03-28 | NTA_Zone 2 | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
44337 | NTA_Zone 2 - Sub Structure - B3 to B2 - Pour 2 | Complete | RCC Works - Vertical | 2023-03-11 | 2023-03-28 | Columns/ Walls_NTA | 100 | 100 |  | 2023-03-11 | 2023-03-11 | 2023-03-28 | 2023-03-28 | NTA_Zone 2 | Sub Structure | B3
43819 | Tower A - Sub Structure - B1 to GF | Complete | Core Wall RCC Works | 2023-03-14 | 2023-03-16 | CW Casting_lift 1 | 100 | 100 |  | 2023-03-14 | 2023-03-14 | 2023-03-16 | 2023-03-16 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43722 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 4 (10 m) | Complete | Retaining Wall RCC Works | 2023-03-15 | 2023-03-17 | Retaining Wall_Reinf_Lift 2 | 100 | 100 |  | 2023-03-15 | 2023-03-15 | 2023-03-17 | 2023-03-17 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43803 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 4 (8.2 m) | Complete | Retaining Wall RCC Works | 2023-03-15 | 2023-03-16 | Retaining Wall_Reinf_Lift 2 | 100 | 100 |  | 2023-03-15 | 2023-03-15 | 2023-03-16 | 2023-03-16 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
44341 | NTA_Zone 2 - Sub Structure - B3 to B2 - Pour 3 | Complete | RCC Works - Slab | 2023-03-15 | 2023-04-06 | Slab_NTA | 100 | 100 |  | 2023-03-15 | 2023-03-15 | 2023-04-06 | 2023-04-06 | NTA_Zone 2 | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
44341 | NTA_Zone 2 - Sub Structure - B3 to B2 - Pour 3 | Complete | RCC Works - Slab | 2023-03-15 | 2023-04-06 | Slab_NTA | 100 | 100 |  | 2023-03-15 | 2023-03-15 | 2023-04-06 | 2023-04-06 | NTA_Zone 2 | Sub Structure | B3
43712 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 1 (13 m) | Complete | Retaining Wall RCC Works | 2023-03-16 | 2023-03-18 | Retaining Wall_Reinf_Lift 2 | 100 | 100 |  | 2023-03-16 | 2023-03-16 | 2023-03-18 | 2023-03-18 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43773 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 1 (11.5 m) | Complete | Retaining Wall RCC Works | 2023-03-16 | 2023-03-18 | Retaining Wall_Reinf_Lift 2 | 100 | 100 |  | 2023-03-16 | 2023-03-16 | 2023-03-18 | 2023-03-18 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43804 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 4 (8.2 m) | Complete | Retaining Wall RCC Works | 2023-03-17 | 2023-03-20 | Fwk_Lift 2 RW | 100 | 100 |  | 2023-03-17 | 2023-03-17 | 2023-03-20 | 2023-03-20 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43820 | Tower A - Sub Structure - B1 to GF | Complete | Core Wall RCC Works | 2023-03-17 | 2023-03-24 | CW Reinf_lift 2 | 100 | 100 |  | 2023-03-17 | 2023-03-17 | 2023-03-24 | 2023-03-24 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44375 |  | Complete |  | 2023-03-17 | 2023-09-19 | B2 to B1 | 100 | 100 |  | 2023-03-17 | 2023-03-17 | 2023-09-19 | 2023-09-19
44375 |  | Complete |  | 2023-03-17 | 2023-09-19 | B2 to B1 | 100 | 100 |  | 2023-03-17 | 2023-03-17 | 2023-09-19 | 2023-09-19
44375 |  | Complete |  | 2023-03-17 | 2023-09-19 | B2 to B1 | 100 | 100 |  | 2023-03-17 | 2023-03-17 | 2023-09-19 | 2023-09-19
44376 |  | Complete |  | 2023-03-17 | 2023-05-20 | Retaining Wall_lift 1 | 100 | 100 |  | 2023-03-17 | 2023-03-17 | 2023-05-20 | 2023-05-20
44376 |  | Complete |  | 2023-03-17 | 2023-05-20 | Retaining Wall_lift 1 | 100 | 100 |  | 2023-03-17 | 2023-03-17 | 2023-05-20 | 2023-05-20 |  |  |  | RCC Super Structure | Retaining Wall RCC Works
44377 | NTA_Zone 2 - Sub Structure - B2 to B1 | Complete | Retaining Wall RCC Works | 2023-03-17 | 2023-03-24 | Section 1_lift 1 | 100 | 100 |  | 2023-03-17 | 2023-03-17 | 2023-03-24 | 2023-03-24 | NTA_Zone 2 | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
44377 | NTA_Zone 2 - Sub Structure - B2 to B1 | Complete | Retaining Wall RCC Works | 2023-03-17 | 2023-03-24 | Section 1_lift 1 | 100 | 100 |  | 2023-03-17 | 2023-03-17 | 2023-03-24 | 2023-03-24 | NTA_Zone 2 | Sub Structure | B2
44388 |  | Complete |  | 2023-03-17 | 2023-04-19 | Pour 1 | 100 | 100 |  | 2023-03-17 | 2023-03-17 | 2023-04-19 | 2023-04-19
44389 | NTA_Zone 2 - Sub Structure - B2 to B1 - Pour 1 | Complete | RCC Works - Vertical | 2023-03-17 | 2023-04-03 | Columns/ Walls_NTA | 100 | 100 |  | 2023-03-17 | 2023-03-17 | 2023-04-03 | 2023-04-03 | NTA_Zone 2 | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
44389 | NTA_Zone 2 - Sub Structure - B2 to B1 - Pour 1 | Complete | RCC Works - Vertical | 2023-03-17 | 2023-04-03 | Columns/ Walls_NTA | 100 | 100 |  | 2023-03-17 | 2023-03-17 | 2023-04-03 | 2023-04-03 | NTA_Zone 2 | Sub Structure | B2
43723 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 4 (10 m) | Complete | Retaining Wall RCC Works | 2023-03-18 | 2023-03-21 | Fwk_Lift 2 RW | 100 | 100 |  | 2023-03-18 | 2023-03-18 | 2023-03-21 | 2023-03-21 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43713 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 1 (13 m) | Complete | Retaining Wall RCC Works | 2023-03-20 | 2023-03-22 | Fwk_Lift 2 RW | 100 | 100 |  | 2023-03-20 | 2023-03-20 | 2023-03-22 | 2023-03-22 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43774 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 1 (11.5 m) | Complete | Retaining Wall RCC Works | 2023-03-20 | 2023-03-22 | Fwk_Lift 2 RW | 100 | 100 |  | 2023-03-20 | 2023-03-20 | 2023-03-22 | 2023-03-22 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43821 | Tower A - Sub Structure - B1 to GF | Complete | Core Wall RCC Works | 2023-03-20 | 2023-03-24 | CW Fwk (1.2m lift)_lift 2 | 100 | 100 |  | 2023-03-20 | 2023-03-20 | 2023-03-24 | 2023-03-24 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44344 | NTA_Zone 2 - Sub Structure - B3 to B2 - Pour 4 | Complete | RCC Works - Slab | 2023-03-20 | 2023-04-05 | Slab_NTA | 100 | 100 |  | 2023-03-20 | 2023-03-20 | 2023-04-05 | 2023-04-05 | NTA_Zone 2 | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
44344 | NTA_Zone 2 - Sub Structure - B3 to B2 - Pour 4 | Complete | RCC Works - Slab | 2023-03-20 | 2023-04-05 | Slab_NTA | 100 | 100 |  | 2023-03-20 | 2023-03-20 | 2023-04-05 | 2023-04-05 | NTA_Zone 2 | Sub Structure | B3
43805 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 4 (8.2 m) | Complete | Retaining Wall RCC Works | 2023-03-21 | 2023-03-21 | Checking & Casting_Lift 2 | 100 | 100 |  | 2023-03-21 | 2023-03-21 | 2023-03-21 | 2023-03-21 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43901 | Tower A - Sub Structure - B1 to GF - Pour 5 | Complete | RCC Works - Slab | 2023-03-21 | 2023-03-24 | Slab & Staircase Reinf. | 100 | 100 |  | 2023-03-21 | 2023-03-21 | 2023-03-24 | 2023-03-24 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
47965 |  | Started |  | 2023-03-21 | 2025-04-28 | Execution | 100 | 90 |  | 2023-03-21 | 2023-03-21 | 2025-11-20
47966 |  | Complete |  | 2023-03-21 | 2024-02-13 | Zone A (External Ramp Area) | 100 | 100 |  | 2023-03-21 | 2023-03-21 | 2024-02-13 | 2024-02-13
47972 |  | Complete |  | 2023-03-21 | 2023-07-14 | Re-routing | 100 | 100 |  | 2023-03-21 | 2023-03-21 | 2023-07-14 | 2023-07-14
47973 |  | Complete |  | 2023-03-21 | 2023-05-12 | Municipal Water | 100 | 100 |  | 2023-03-21 | 2023-03-21 | 2023-05-12 | 2023-05-12
47979 |  | Complete |  | 2023-03-21 | 2024-06-29 | Zone B (Retail Area) | 100 | 100 |  | 2023-03-21 | 2023-03-21 | 2024-06-29 | 2024-06-29
48001 |  | Complete |  | 2023-03-21 | 2023-03-28 | Internal Re-routing | 100 | 100 |  | 2023-03-21 | 2023-03-21 | 2023-03-28 | 2023-03-28
48002 |  | Complete |  | 2023-03-21 | 2023-03-28 | Scaffolding | 100 | 100 |  | 2023-03-21 | 2023-03-21 | 2023-03-28 | 2023-03-28
48021 |  | Complete |  | 2023-03-21 | 2023-04-24 | Acoustic Barrier | 100 | 100 |  | 2023-03-21 | 2023-03-21 | 2023-04-24 | 2023-04-24
43724 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 4 (10 m) | Complete | Retaining Wall RCC Works | 2023-03-22 | 2023-03-22 | Checking & Casting_Lift 2 | 100 | 100 |  | 2023-03-22 | 2023-03-22 | 2023-03-22 | 2023-03-22 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43810 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 5 (8 m) | Complete | Retaining Wall RCC Works | 2023-03-22 | 2023-03-24 | Fwk_Lift 1 RW | 100 | 100 |  | 2023-03-22 | 2023-03-22 | 2023-03-24 | 2023-03-24 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43714 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 1 (13 m) | Complete | Retaining Wall RCC Works | 2023-03-23 | 2023-03-23 | Checking & Casting_Lift 2 | 100 | 100 |  | 2023-03-23 | 2023-03-23 | 2023-03-23 | 2023-03-23 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43775 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 1 (11.5 m) | Complete | Retaining Wall RCC Works | 2023-03-23 | 2023-03-23 | Checking & Casting_Lift 2 | 100 | 100 |  | 2023-03-23 | 2023-03-23 | 2023-03-23 | 2023-03-23 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
44338 | NTA_Zone 2 - Sub Structure - B3 to B2 - Pour 2 | Complete | RCC Works - Slab | 2023-03-23 | 2023-04-08 | Slab_NTA | 100 | 100 |  | 2023-03-23 | 2023-03-23 | 2023-04-08 | 2023-04-08 | NTA_Zone 2 | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
44338 | NTA_Zone 2 - Sub Structure - B3 to B2 - Pour 2 | Complete | RCC Works - Slab | 2023-03-23 | 2023-04-08 | Slab_NTA | 100 | 100 |  | 2023-03-23 | 2023-03-23 | 2023-04-08 | 2023-04-08 | NTA_Zone 2 | Sub Structure | B3
43729 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 3 (10 m) | Complete | Retaining Wall RCC Works | 2023-03-24 | 2023-03-27 | Fwk_Lift 1 RW | 100 | 100 |  | 2023-03-24 | 2023-03-24 | 2023-03-27 | 2023-03-27 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43739 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 5 (10 m) | Complete | Retaining Wall RCC Works | 2023-03-24 | 2023-03-27 | Fwk_Lift 1 RW | 100 | 100 |  | 2023-03-24 | 2023-03-24 | 2023-03-27 | 2023-03-27 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43780 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 3 (10.8 m) | Complete | Retaining Wall RCC Works | 2023-03-24 | 2023-03-27 | Fwk_Lift 1 RW | 100 | 100 |  | 2023-03-24 | 2023-03-24 | 2023-03-27 | 2023-03-27 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43833 |  | Complete |  | 2023-03-24 | 2023-05-05 | Pour 3_B1 to GF | 100 | 100 |  | 2023-03-24 | 2023-03-24 | 2023-05-05 | 2023-05-05
43835 | Tower A - Sub Structure - B1 to GF - Pour 3 | Complete | Core Wall RCC Works | 2023-03-24 | 2023-04-04 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2023-03-24 | 2023-03-24 | 2023-04-04 | 2023-04-04 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43835 | Tower A - Sub Structure - B1 to GF - Pour 3 | Complete | Core Wall RCC Works | 2023-03-24 | 2023-04-04 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2023-03-24 | 2023-03-24 | 2023-04-04 | 2023-04-04 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43811 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 5 (8 m) | Complete | Retaining Wall RCC Works | 2023-03-25 | 2023-03-25 | Checking & Casting_Lift 1 | 100 | 100 |  | 2023-03-25 | 2023-03-25 | 2023-03-25 | 2023-03-25 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43822 | Tower A - Sub Structure - B1 to GF | Complete | Core Wall RCC Works | 2023-03-25 | 2023-03-28 | CW Casting_lift 2 | 100 | 100 |  | 2023-03-25 | 2023-03-25 | 2023-03-28 | 2023-03-28 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44378 | NTA_Zone 2 - Sub Structure - B2 to B1 | Complete | Retaining Wall RCC Works | 2023-03-25 | 2023-04-01 | Section 2_lift 1 | 100 | 100 |  | 2023-03-25 | 2023-03-25 | 2023-04-01 | 2023-04-01 | NTA_Zone 2 | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
44378 | NTA_Zone 2 - Sub Structure - B2 to B1 | Complete | Retaining Wall RCC Works | 2023-03-25 | 2023-04-01 | Section 2_lift 1 | 100 | 100 |  | 2023-03-25 | 2023-03-25 | 2023-04-01 | 2023-04-01 | NTA_Zone 2 | Sub Structure | B2
43812 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 5 (8 m) | Complete | Retaining Wall RCC Works | 2023-03-27 | 2023-03-30 | De-stressing & Removal of Anchor | 100 | 100 |  | 2023-03-27 | 2023-03-27 | 2023-03-30 | 2023-03-30 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43836 | Tower A - Sub Structure - B1 to GF - Pour 3 | Complete | Core Wall RCC Works | 2023-03-27 | 2023-04-06 | Col/ Wall Casting | 100 | 100 |  | 2023-03-27 | 2023-03-27 | 2023-04-06 | 2023-04-06 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43836 | Tower A - Sub Structure - B1 to GF - Pour 3 | Complete | Core Wall RCC Works | 2023-03-27 | 2023-04-06 | Col/ Wall Casting | 100 | 100 |  | 2023-03-27 | 2023-03-27 | 2023-04-06 | 2023-04-06 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43843 |  | Complete |  | 2023-03-27 | 2023-05-06 | Pour 1B & 6_B1 to GF | 100 | 100 |  | 2023-03-27 | 2023-03-27 | 2023-05-06 | 2023-05-06
43845 | Tower A - Sub Structure - B1 to GF - Pour 1B & 6 | Complete | Core Wall RCC Works | 2023-03-27 | 2023-04-06 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2023-03-27 | 2023-03-27 | 2023-04-06 | 2023-04-06 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43845 | Tower A - Sub Structure - B1 to GF - Pour 1B & 6 | Complete | Core Wall RCC Works | 2023-03-27 | 2023-04-06 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2023-03-27 | 2023-03-27 | 2023-04-06 | 2023-04-06 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43730 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 3 (10 m) | Complete | Retaining Wall RCC Works | 2023-03-28 | 2023-03-28 | Checking & Casting_Lift 1 | 100 | 100 |  | 2023-03-28 | 2023-03-28 | 2023-03-28 | 2023-03-28 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43740 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 5 (10 m) | Complete | Retaining Wall RCC Works | 2023-03-28 | 2023-03-28 | Checking & Casting_Lift 1 | 100 | 100 |  | 2023-03-28 | 2023-03-28 | 2023-03-28 | 2023-03-28 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43781 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 3 (10.8 m) | Complete | Retaining Wall RCC Works | 2023-03-28 | 2023-03-28 | Checking & Casting_Lift 1 | 100 | 100 |  | 2023-03-28 | 2023-03-28 | 2023-03-28 | 2023-03-28 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43731 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 3 (10 m) | Complete | Retaining Wall RCC Works | 2023-03-29 | 2023-03-31 | De-stressing & Removal of Anchor | 100 | 100 |  | 2023-03-29 | 2023-03-29 | 2023-03-31 | 2023-03-31 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43741 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 5 (10 m) | Complete | Retaining Wall RCC Works | 2023-03-29 | 2023-03-31 | De-stressing & Removal of Anchor | 100 | 100 |  | 2023-03-29 | 2023-03-29 | 2023-03-31 | 2023-03-31 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43782 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 3 (10.8 m) | Complete | Retaining Wall RCC Works | 2023-03-29 | 2023-04-01 | De-stressing & Removal of Anchor | 100 | 100 |  | 2023-03-29 | 2023-03-29 | 2023-04-01 | 2023-04-01 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43823 |  | Complete |  | 2023-03-29 | 2023-04-28 | Pour 1A & 2_B1 to GF | 100 | 100 |  | 2023-03-29 | 2023-03-29 | 2023-04-28 | 2023-04-28
43824 | Tower A - Sub Structure - B1 to GF - Pour 1A & 2 | Complete | Core Wall RCC Works | 2023-03-29 | 2023-04-05 | Col/ Wall Reinf. | 100 | 100 |  | 2023-03-29 | 2023-03-29 | 2023-04-05 | 2023-04-05 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43824 | Tower A - Sub Structure - B1 to GF - Pour 1A & 2 | Complete | Core Wall RCC Works | 2023-03-29 | 2023-04-05 | Col/ Wall Reinf. | 100 | 100 |  | 2023-03-29 | 2023-03-29 | 2023-04-05 | 2023-04-05 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43825 | Tower A - Sub Structure - B1 to GF - Pour 1A & 2 | Complete | Core Wall RCC Works | 2023-03-29 | 2023-04-08 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2023-03-29 | 2023-03-29 | 2023-04-08 | 2023-04-08 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43825 | Tower A - Sub Structure - B1 to GF - Pour 1A & 2 | Complete | Core Wall RCC Works | 2023-03-29 | 2023-04-08 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2023-03-29 | 2023-03-29 | 2023-04-08 | 2023-04-08 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43834 | Tower A - Sub Structure - B1 to GF - Pour 3 | Complete | Core Wall RCC Works | 2023-03-29 | 2023-03-31 | Col/ Wall Reinf. | 100 | 100 |  | 2023-03-29 | 2023-03-29 | 2023-03-31 | 2023-03-31 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43834 | Tower A - Sub Structure - B1 to GF - Pour 3 | Complete | Core Wall RCC Works | 2023-03-29 | 2023-03-31 | Col/ Wall Reinf. | 100 | 100 |  | 2023-03-29 | 2023-03-29 | 2023-03-31 | 2023-03-31 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43844 | Tower A - Sub Structure - B1 to GF - Pour 1B & 6 | Complete | Core Wall RCC Works | 2023-03-29 | 2023-04-03 | Col/ Wall Reinf. | 100 | 100 |  | 2023-03-29 | 2023-03-29 | 2023-04-03 | 2023-04-03 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43844 | Tower A - Sub Structure - B1 to GF - Pour 1B & 6 | Complete | Core Wall RCC Works | 2023-03-29 | 2023-04-03 | Col/ Wall Reinf. | 100 | 100 |  | 2023-03-29 | 2023-03-29 | 2023-04-03 | 2023-04-03 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43846 | Tower A - Sub Structure - B1 to GF - Pour 1B & 6 | Complete | Core Wall RCC Works | 2023-03-29 | 2023-04-08 | Col/ Wall Casting | 100 | 100 |  | 2023-03-29 | 2023-03-29 | 2023-04-08 | 2023-04-08 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43846 | Tower A - Sub Structure - B1 to GF - Pour 1B & 6 | Complete | Core Wall RCC Works | 2023-03-29 | 2023-04-08 | Col/ Wall Casting | 100 | 100 |  | 2023-03-29 | 2023-03-29 | 2023-04-08 | 2023-04-08 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
47982 |  | Complete |  | 2023-03-29 | 2023-06-22 | Re-routing | 100 | 100 |  | 2023-03-29 | 2023-03-29 | 2023-06-22 | 2023-06-22
47983 |  | Complete |  | 2023-03-29 | 2023-05-20 | Municipal Water | 100 | 100 |  | 2023-03-29 | 2023-03-29 | 2023-05-20 | 2023-05-20
43813 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 5 (8 m) | Complete | Retaining Wall RCC Works | 2023-03-31 | 2023-04-01 | Retaining Wall_Reinf_Lift 2 | 100 | 100 |  | 2023-03-31 | 2023-03-31 | 2023-04-01 | 2023-04-01 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43826 | Tower A - Sub Structure - B1 to GF - Pour 1A & 2 | Complete | Core Wall RCC Works | 2023-03-31 | 2023-04-11 | Col/ Wall Casting | 100 | 100 |  | 2023-03-31 | 2023-03-31 | 2023-04-11 | 2023-04-11 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43826 | Tower A - Sub Structure - B1 to GF - Pour 1A & 2 | Complete | Core Wall RCC Works | 2023-03-31 | 2023-04-11 | Col/ Wall Casting | 100 | 100 |  | 2023-03-31 | 2023-03-31 | 2023-04-11 | 2023-04-11 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43732 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 3 (10 m) | Complete | Retaining Wall RCC Works | 2023-04-01 | 2023-04-04 | Retaining Wall_Reinf_Lift 2 | 100 | 100 |  | 2023-04-01 | 2023-04-01 | 2023-04-04 | 2023-04-04 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43742 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 5 (10 m) | Complete | Retaining Wall RCC Works | 2023-04-01 | 2023-04-04 | Retaining Wall_Reinf_Lift 2 | 100 | 100 |  | 2023-04-01 | 2023-04-01 | 2023-04-04 | 2023-04-04 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
47974 |  | Complete |  | 2023-04-01 | 2023-05-24 | Municipal Storm Water | 100 | 100 |  | 2023-04-01 | 2023-04-01 | 2023-05-24 | 2023-05-24
43783 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 3 (10.8 m) | Complete | Retaining Wall RCC Works | 2023-04-03 | 2023-04-05 | Retaining Wall_Reinf_Lift 2 | 100 | 100 |  | 2023-04-03 | 2023-04-03 | 2023-04-05 | 2023-04-05 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43814 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 5 (8 m) | Complete | Retaining Wall RCC Works | 2023-04-03 | 2023-04-05 | Fwk_Lift 2 RW | 100 | 100 |  | 2023-04-03 | 2023-04-03 | 2023-04-05 | 2023-04-05 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
44390 | NTA_Zone 2 - Sub Structure - B2 to B1 - Pour 1 | Complete | RCC Works - Slab | 2023-04-03 | 2023-04-19 | Slab_NTA | 100 | 100 |  | 2023-04-03 | 2023-04-03 | 2023-04-19 | 2023-04-19 | NTA_Zone 2 | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
44390 | NTA_Zone 2 - Sub Structure - B2 to B1 - Pour 1 | Complete | RCC Works - Slab | 2023-04-03 | 2023-04-19 | Slab_NTA | 100 | 100 |  | 2023-04-03 | 2023-04-03 | 2023-04-19 | 2023-04-19 | NTA_Zone 2 | Sub Structure | B2
43733 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 3 (10 m) | Complete | Retaining Wall RCC Works | 2023-04-05 | 2023-04-07 | Fwk_Lift 2 RW | 100 | 100 |  | 2023-04-05 | 2023-04-05 | 2023-04-07 | 2023-04-07 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43743 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 5 (10 m) | Complete | Retaining Wall RCC Works | 2023-04-05 | 2023-04-07 | Fwk_Lift 2 RW | 100 | 100 |  | 2023-04-05 | 2023-04-05 | 2023-04-07 | 2023-04-07 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
44330 | NTA_Zone 2 - Foundation - Pour 6 | Complete | Foundation RCC Works | 2023-04-05 | 2023-04-10 | Fwk & Casting_NTA | 100 | 100 |  | 2023-04-05 | 2023-04-05 | 2023-04-10 | 2023-04-10 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44330 | NTA_Zone 2 - Foundation - Pour 6 | Complete | Foundation RCC Works | 2023-04-05 | 2023-04-10 | Fwk & Casting_NTA | 100 | 100 |  | 2023-04-05 | 2023-04-05 | 2023-04-10 | 2023-04-10 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44330 | NTA_Zone 2 - Foundation - Pour 6 | Complete | Foundation RCC Works | 2023-04-05 | 2023-04-10 | Fwk & Casting_NTA | 100 | 100 |  | 2023-04-05 | 2023-04-05 | 2023-04-10 | 2023-04-10 | NTA_Zone 2 | Foundation
43784 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 3 (10.8 m) | Complete | Retaining Wall RCC Works | 2023-04-06 | 2023-04-08 | Fwk_Lift 2 RW | 100 | 100 |  | 2023-04-06 | 2023-04-06 | 2023-04-08 | 2023-04-08 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43815 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 5 (8 m) | Complete | Retaining Wall RCC Works | 2023-04-06 | 2023-04-06 | Checking & Casting_Lift 2 | 100 | 100 |  | 2023-04-06 | 2023-04-06 | 2023-04-06 | 2023-04-06 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
44397 |  | Complete |  | 2023-04-06 | 2023-05-30 | Pour 4 | 100 | 100 |  | 2023-04-06 | 2023-04-06 | 2023-05-30 | 2023-05-30
44398 | NTA_Zone 2 - Sub Structure - B2 to B1 - Pour 4 | Complete | RCC Works - Vertical | 2023-04-06 | 2023-04-22 | Columns/ Walls_NTA | 100 | 100 |  | 2023-04-06 | 2023-04-06 | 2023-04-22 | 2023-04-22 | NTA_Zone 2 | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
44398 | NTA_Zone 2 - Sub Structure - B2 to B1 - Pour 4 | Complete | RCC Works - Vertical | 2023-04-06 | 2023-04-22 | Columns/ Walls_NTA | 100 | 100 |  | 2023-04-06 | 2023-04-06 | 2023-04-22 | 2023-04-22 | NTA_Zone 2 | Sub Structure | B2
47984 |  | Complete |  | 2023-04-06 | 2023-05-29 | Municipal Storm Water | 100 | 100 |  | 2023-04-06 | 2023-04-06 | 2023-05-29 | 2023-05-29
43837 | Tower A - Sub Structure - B1 to GF - Pour 3 | Complete | Core Wall RCC Works | 2023-04-07 | 2023-04-10 | Col/ Wall Reinf. | 100 | 100 |  | 2023-04-07 | 2023-04-07 | 2023-04-10 | 2023-04-10 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43837 | Tower A - Sub Structure - B1 to GF - Pour 3 | Complete | Core Wall RCC Works | 2023-04-07 | 2023-04-10 | Col/ Wall Reinf. | 100 | 100 |  | 2023-04-07 | 2023-04-07 | 2023-04-10 | 2023-04-10 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44394 |  | Complete |  | 2023-04-07 | 2023-05-18 | Pour 3 | 100 | 100 |  | 2023-04-07 | 2023-04-07 | 2023-05-18 | 2023-05-18
44395 | NTA_Zone 2 - Sub Structure - B2 to B1 - Pour 3 | Complete | RCC Works - Vertical | 2023-04-07 | 2023-04-29 | Columns/ Walls_NTA | 100 | 100 |  | 2023-04-07 | 2023-04-07 | 2023-04-29 | 2023-04-29 | NTA_Zone 2 | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
44395 | NTA_Zone 2 - Sub Structure - B2 to B1 - Pour 3 | Complete | RCC Works - Vertical | 2023-04-07 | 2023-04-29 | Columns/ Walls_NTA | 100 | 100 |  | 2023-04-07 | 2023-04-07 | 2023-04-29 | 2023-04-29 | NTA_Zone 2 | Sub Structure | B2
43734 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 3 (10 m) | Complete | Retaining Wall RCC Works | 2023-04-08 | 2023-04-08 | Checking & Casting_Lift 2 | 100 | 100 |  | 2023-04-08 | 2023-04-08 | 2023-04-08 | 2023-04-08 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43744 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 5 (10 m) | Complete | Retaining Wall RCC Works | 2023-04-08 | 2023-04-08 | Checking & Casting_Lift 2 | 100 | 100 |  | 2023-04-08 | 2023-04-08 | 2023-04-08 | 2023-04-08 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43749 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 2 (10 m) | Complete | Retaining Wall RCC Works | 2023-04-10 | 2023-04-12 | Fwk_Lift 1 RW | 100 | 100 |  | 2023-04-10 | 2023-04-10 | 2023-04-12 | 2023-04-12 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43759 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 6 (10 m) | Complete | Retaining Wall RCC Works | 2023-04-10 | 2023-04-12 | Fwk_Lift 1 RW | 100 | 100 |  | 2023-04-10 | 2023-04-10 | 2023-04-12 | 2023-04-12 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43785 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 3 (10.8 m) | Complete | Retaining Wall RCC Works | 2023-04-10 | 2023-04-10 | Checking & Casting_Lift 2 | 100 | 100 |  | 2023-04-10 | 2023-04-10 | 2023-04-10 | 2023-04-10 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43830 | Tower A - Sub Structure - B1 to GF - Pour 1A & 2 | Complete | RCC Works - Slab | 2023-04-10 | 2023-04-22 | Slab & Staircase Fwk. | 100 | 100 |  | 2023-04-10 | 2023-04-10 | 2023-04-22 | 2023-04-22 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
43847 | Tower A - Sub Structure - B1 to GF - Pour 1B & 6 | Complete | Core Wall RCC Works | 2023-04-10 | 2023-04-11 | Col/ Wall Reinf. | 100 | 100 |  | 2023-04-10 | 2023-04-10 | 2023-04-11 | 2023-04-11 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43847 | Tower A - Sub Structure - B1 to GF - Pour 1B & 6 | Complete | Core Wall RCC Works | 2023-04-10 | 2023-04-11 | Col/ Wall Reinf. | 100 | 100 |  | 2023-04-10 | 2023-04-10 | 2023-04-11 | 2023-04-11 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43862 | Tower A - Sub Structure - B1 to GF - Pour 7 | Complete | RCC Works - Slab | 2023-04-10 | 2023-04-11 | Slab & Staircase Casting | 100 | 100 |  | 2023-04-10 | 2023-04-10 | 2023-04-11 | 2023-04-11 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
44379 | NTA_Zone 2 - Sub Structure - B2 to B1 | Complete | Retaining Wall RCC Works | 2023-04-10 | 2023-04-17 | Section 3_lift 1 | 100 | 100 |  | 2023-04-10 | 2023-04-10 | 2023-04-17 | 2023-04-17 | NTA_Zone 2 | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
44379 | NTA_Zone 2 - Sub Structure - B2 to B1 | Complete | Retaining Wall RCC Works | 2023-04-10 | 2023-04-17 | Section 3_lift 1 | 100 | 100 |  | 2023-04-10 | 2023-04-10 | 2023-04-17 | 2023-04-17 | NTA_Zone 2 | Sub Structure | B2
44381 | NTA_Zone 2 - Sub Structure - B2 to B1 | Complete | Retaining Wall RCC Works | 2023-04-10 | 2023-04-17 | Section 5_lift 1 | 100 | 100 |  | 2023-04-10 | 2023-04-10 | 2023-04-17 | 2023-04-17 | NTA_Zone 2 | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
44381 | NTA_Zone 2 - Sub Structure - B2 to B1 | Complete | Retaining Wall RCC Works | 2023-04-10 | 2023-04-17 | Section 5_lift 1 | 100 | 100 |  | 2023-04-10 | 2023-04-10 | 2023-04-17 | 2023-04-17 | NTA_Zone 2 | Sub Structure | B2
44391 |  | Complete |  | 2023-04-10 | 2023-05-13 | Pour 2 | 100 | 100 |  | 2023-04-10 | 2023-04-10 | 2023-05-13 | 2023-05-13
44392 | NTA_Zone 2 - Sub Structure - B2 to B1 - Pour 2 | Complete | RCC Works - Vertical | 2023-04-10 | 2023-04-26 | Columns/ Walls_NTA | 100 | 100 |  | 2023-04-10 | 2023-04-10 | 2023-04-26 | 2023-04-26 | NTA_Zone 2 | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
44392 | NTA_Zone 2 - Sub Structure - B2 to B1 - Pour 2 | Complete | RCC Works - Vertical | 2023-04-10 | 2023-04-26 | Columns/ Walls_NTA | 100 | 100 |  | 2023-04-10 | 2023-04-10 | 2023-04-26 | 2023-04-26 | NTA_Zone 2 | Sub Structure | B2
43790 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 2 (14 m) | Complete | Retaining Wall RCC Works | 2023-04-11 | 2023-04-13 | Fwk_Lift 1 RW | 100 | 100 |  | 2023-04-11 | 2023-04-11 | 2023-04-13 | 2023-04-13 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43838 | Tower A - Sub Structure - B1 to GF - Pour 3 | Complete | Core Wall RCC Works | 2023-04-11 | 2023-04-13 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2023-04-11 | 2023-04-11 | 2023-04-13 | 2023-04-13 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43838 | Tower A - Sub Structure - B1 to GF - Pour 3 | Complete | Core Wall RCC Works | 2023-04-11 | 2023-04-13 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2023-04-11 | 2023-04-11 | 2023-04-13 | 2023-04-13 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43892 | Tower A - Sub Structure - B1 to GF - Pour 9B | Complete | RCC Works - Slab | 2023-04-11 | 2023-04-12 | Slab & Staircase Casting | 100 | 100 |  | 2023-04-11 | 2023-04-11 | 2023-04-12 | 2023-04-12 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
43902 | Tower A - Sub Structure - B1 to GF - Pour 5 | Complete | RCC Works - Slab | 2023-04-11 | 2023-04-12 | Slab & Staircase Casting | 100 | 100 |  | 2023-04-11 | 2023-04-11 | 2023-04-12 | 2023-04-12 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
44348 |  | Complete |  | 2023-04-11 | 2023-05-10 | Pour 6 | 100 | 100 |  | 2023-04-11 | 2023-04-11 | 2023-05-10 | 2023-05-10
44349 | NTA_Zone 2 - Sub Structure - B3 to B2 - Pour 6 | Complete | RCC Works - Vertical | 2023-04-11 | 2023-04-27 | Columns/ Walls_NTA | 100 | 100 |  | 2023-04-11 | 2023-04-11 | 2023-04-27 | 2023-04-27 | NTA_Zone 2 | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
44349 | NTA_Zone 2 - Sub Structure - B3 to B2 - Pour 6 | Complete | RCC Works - Vertical | 2023-04-11 | 2023-04-27 | Columns/ Walls_NTA | 100 | 100 |  | 2023-04-11 | 2023-04-11 | 2023-04-27 | 2023-04-27 | NTA_Zone 2 | Sub Structure | B3
43827 | Tower A - Sub Structure - B1 to GF - Pour 1A & 2 | Complete | Core Wall RCC Works | 2023-04-12 | 2023-04-14 | Col/ Wall Reinf. | 100 | 100 |  | 2023-04-12 | 2023-04-12 | 2023-04-14 | 2023-04-14 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43827 | Tower A - Sub Structure - B1 to GF - Pour 1A & 2 | Complete | Core Wall RCC Works | 2023-04-12 | 2023-04-14 | Col/ Wall Reinf. | 100 | 100 |  | 2023-04-12 | 2023-04-12 | 2023-04-14 | 2023-04-14 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43848 | Tower A - Sub Structure - B1 to GF - Pour 1B & 6 | Complete | Core Wall RCC Works | 2023-04-12 | 2023-04-14 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2023-04-12 | 2023-04-12 | 2023-04-14 | 2023-04-14 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43848 | Tower A - Sub Structure - B1 to GF - Pour 1B & 6 | Complete | Core Wall RCC Works | 2023-04-12 | 2023-04-14 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2023-04-12 | 2023-04-12 | 2023-04-14 | 2023-04-14 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43750 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 2 (10 m) | Complete | Retaining Wall RCC Works | 2023-04-13 | 2023-04-13 | Checking & Casting_Lift 1 | 100 | 100 |  | 2023-04-13 | 2023-04-13 | 2023-04-13 | 2023-04-13 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43760 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 6 (10 m) | Complete | Retaining Wall RCC Works | 2023-04-13 | 2023-04-13 | Checking & Casting_Lift 1 | 100 | 100 |  | 2023-04-13 | 2023-04-13 | 2023-04-13 | 2023-04-13 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43839 | Tower A - Sub Structure - B1 to GF - Pour 3 | Complete | Core Wall RCC Works | 2023-04-13 | 2023-04-14 | Col/ Wall Casting | 100 | 100 |  | 2023-04-13 | 2023-04-13 | 2023-04-14 | 2023-04-14 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43839 | Tower A - Sub Structure - B1 to GF - Pour 3 | Complete | Core Wall RCC Works | 2023-04-13 | 2023-04-14 | Col/ Wall Casting | 100 | 100 |  | 2023-04-13 | 2023-04-13 | 2023-04-14 | 2023-04-14 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
47975 |  | Complete |  | 2023-04-13 | 2023-06-05 | STP Bypass to Municipal line | 100 | 100 |  | 2023-04-13 | 2023-04-13 | 2023-06-05 | 2023-06-05
43751 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 2 (10 m) | Complete | Retaining Wall RCC Works | 2023-04-14 | 2023-04-17 | De-stressing & Removal of Anchor | 100 | 100 |  | 2023-04-14 | 2023-04-14 | 2023-04-17 | 2023-04-17 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43761 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 6 (10 m) | Complete | Retaining Wall RCC Works | 2023-04-14 | 2023-04-17 | De-stressing & Removal of Anchor | 100 | 100 |  | 2023-04-14 | 2023-04-14 | 2023-04-17 | 2023-04-17 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43791 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 2 (14 m) | Complete | Retaining Wall RCC Works | 2023-04-14 | 2023-04-14 | Checking & Casting_Lift 1 | 100 | 100 |  | 2023-04-14 | 2023-04-14 | 2023-04-14 | 2023-04-14 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43849 | Tower A - Sub Structure - B1 to GF - Pour 1B & 6 | Complete | Core Wall RCC Works | 2023-04-14 | 2023-04-15 | Col/ Wall Casting | 100 | 100 |  | 2023-04-14 | 2023-04-14 | 2023-04-15 | 2023-04-15 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43849 | Tower A - Sub Structure - B1 to GF - Pour 1B & 6 | Complete | Core Wall RCC Works | 2023-04-14 | 2023-04-15 | Col/ Wall Casting | 100 | 100 |  | 2023-04-14 | 2023-04-14 | 2023-04-15 | 2023-04-15 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
47985 |  | Complete |  | 2023-04-14 | 2023-06-06 | STP Bypass to Municipal line | 100 | 100 |  | 2023-04-14 | 2023-04-14 | 2023-06-06 | 2023-06-06
43792 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 2 (14 m) | Complete | Retaining Wall RCC Works | 2023-04-15 | 2023-04-19 | De-stressing & Removal of Anchor | 100 | 100 |  | 2023-04-15 | 2023-04-15 | 2023-04-19 | 2023-04-19 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43828 | Tower A - Sub Structure - B1 to GF - Pour 1A & 2 | Complete | Core Wall RCC Works | 2023-04-15 | 2023-04-18 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2023-04-15 | 2023-04-15 | 2023-04-18 | 2023-04-18 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43828 | Tower A - Sub Structure - B1 to GF - Pour 1A & 2 | Complete | Core Wall RCC Works | 2023-04-15 | 2023-04-18 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2023-04-15 | 2023-04-15 | 2023-04-18 | 2023-04-18 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
43840 | Tower A - Sub Structure - B1 to GF - Pour 3 | Complete | RCC Works - Slab | 2023-04-15 | 2023-04-28 | Slab & Staircase Fwk. | 100 | 100 |  | 2023-04-15 | 2023-04-15 | 2023-04-28 | 2023-04-28 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
43850 | Tower A - Sub Structure - B1 to GF - Pour 1B & 6 | Complete | RCC Works - Slab | 2023-04-17 | 2023-04-29 | Slab & Staircase Fwk. | 100 | 100 |  | 2023-04-17 | 2023-04-17 | 2023-04-29 | 2023-04-29 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
43752 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 2 (10 m) | Complete | Retaining Wall RCC Works | 2023-04-18 | 2023-04-20 | Retaining Wall_Reinf_Lift 2 | 100 | 100 |  | 2023-04-18 | 2023-04-18 | 2023-04-20 | 2023-04-20 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43762 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 6 (10 m) | Complete | Retaining Wall RCC Works | 2023-04-18 | 2023-04-20 | Retaining Wall_Reinf_Lift 2 | 100 | 100 |  | 2023-04-18 | 2023-04-18 | 2023-04-20 | 2023-04-20 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43829 | Tower A - Sub Structure - B1 to GF - Pour 1A & 2 | Complete | Core Wall RCC Works | 2023-04-18 | 2023-04-19 | Col/ Wall Casting | 100 | 100 |  | 2023-04-18 | 2023-04-18 | 2023-04-19 | 2023-04-19 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
43829 | Tower A - Sub Structure - B1 to GF - Pour 1A & 2 | Complete | Core Wall RCC Works | 2023-04-18 | 2023-04-19 | Col/ Wall Casting | 100 | 100 |  | 2023-04-18 | 2023-04-18 | 2023-04-19 | 2023-04-19 | Tower A | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44380 | NTA_Zone 2 - Sub Structure - B2 to B1 | Complete | Retaining Wall RCC Works | 2023-04-18 | 2023-04-25 | Section 4_lift 1 | 100 | 100 |  | 2023-04-18 | 2023-04-18 | 2023-04-25 | 2023-04-25 | NTA_Zone 2 | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
44380 | NTA_Zone 2 - Sub Structure - B2 to B1 | Complete | Retaining Wall RCC Works | 2023-04-18 | 2023-04-25 | Section 4_lift 1 | 100 | 100 |  | 2023-04-18 | 2023-04-18 | 2023-04-25 | 2023-04-25 | NTA_Zone 2 | Sub Structure | B2
44382 | NTA_Zone 2 - Sub Structure - B2 to B1 | Complete | Retaining Wall RCC Works | 2023-04-18 | 2023-04-25 | Section 6_lift 1 | 100 | 100 |  | 2023-04-18 | 2023-04-18 | 2023-04-25 | 2023-04-25 | NTA_Zone 2 | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
44382 | NTA_Zone 2 - Sub Structure - B2 to B1 | Complete | Retaining Wall RCC Works | 2023-04-18 | 2023-04-25 | Section 6_lift 1 | 100 | 100 |  | 2023-04-18 | 2023-04-18 | 2023-04-25 | 2023-04-25 | NTA_Zone 2 | Sub Structure | B2
43793 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 2 (14 m) | Complete | Retaining Wall RCC Works | 2023-04-20 | 2023-04-22 | Retaining Wall_Reinf_Lift 2 | 100 | 100 |  | 2023-04-20 | 2023-04-20 | 2023-04-22 | 2023-04-22 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
44406 |  | Complete |  | 2023-04-20 | 2023-11-29 | B1 to GF | 100 | 100 |  | 2023-04-20 | 2023-04-20 | 2023-11-29 | 2023-11-29
44406 |  | Complete |  | 2023-04-20 | 2023-11-29 | B1 to GF | 100 | 100 |  | 2023-04-20 | 2023-04-20 | 2023-11-29 | 2023-11-29
44406 |  | Complete |  | 2023-04-20 | 2023-11-29 | B1 to GF | 100 | 100 |  | 2023-04-20 | 2023-04-20 | 2023-11-29 | 2023-11-29
44408 |  | Complete |  | 2023-04-20 | 2023-07-28 | Retaining Wall_lift 1 (Grid PA-04 to PB-N) | 100 | 100 |  | 2023-04-20 | 2023-04-20 | 2023-07-28 | 2023-07-28
44409 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-04-20 | 2023-05-03 | Section 1_lift 1 | 100 | 100 |  | 2023-04-20 | 2023-04-20 | 2023-05-03 | 2023-05-03 | NTA_Zone 2 | Sub Structure | B1
44409 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-04-20 | 2023-05-03 | Section 1_lift 1 | 100 | 100 |  | 2023-04-20 | 2023-04-20 | 2023-05-03 | 2023-05-03 | NTA_Zone 2 | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
44432 |  | Complete |  | 2023-04-20 | 2023-06-10 | Pour 1 | 100 | 100 |  | 2023-04-20 | 2023-04-20 | 2023-06-10 | 2023-06-10
44433 | NTA_Zone 2 - Sub Structure - B1 to GF - Pour 1 | Complete | RCC Works - Vertical | 2023-04-20 | 2023-05-08 | Columns/ Walls_NTA | 100 | 100 |  | 2023-04-20 | 2023-04-20 | 2023-05-08 | 2023-05-08 | NTA_Zone 2 | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44433 | NTA_Zone 2 - Sub Structure - B1 to GF - Pour 1 | Complete | RCC Works - Vertical | 2023-04-20 | 2023-05-08 | Columns/ Walls_NTA | 100 | 100 |  | 2023-04-20 | 2023-04-20 | 2023-05-08 | 2023-05-08 | NTA_Zone 2 | Sub Structure | B1
43753 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 2 (10 m) | Complete | Retaining Wall RCC Works | 2023-04-21 | 2023-04-24 | Fwk_Lift 2 RW | 100 | 100 |  | 2023-04-21 | 2023-04-21 | 2023-04-24 | 2023-04-24 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43763 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 6 (10 m) | Complete | Retaining Wall RCC Works | 2023-04-21 | 2023-04-24 | Fwk_Lift 2 RW | 100 | 100 |  | 2023-04-21 | 2023-04-21 | 2023-04-24 | 2023-04-24 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43831 | Tower A - Sub Structure - B1 to GF - Pour 1A & 2 | Complete | RCC Works - Slab | 2023-04-22 | 2023-04-26 | Slab & Staircase Reinf. | 100 | 100 |  | 2023-04-22 | 2023-04-22 | 2023-04-26 | 2023-04-26 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
44350 | NTA_Zone 2 - Sub Structure - B3 to B2 - Pour 6 | Complete | RCC Works - Slab | 2023-04-22 | 2023-05-10 | Slab_NTA | 100 | 100 |  | 2023-04-22 | 2023-04-22 | 2023-05-10 | 2023-05-10 | NTA_Zone 2 | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
44350 | NTA_Zone 2 - Sub Structure - B3 to B2 - Pour 6 | Complete | RCC Works - Slab | 2023-04-22 | 2023-05-10 | Slab_NTA | 100 | 100 |  | 2023-04-22 | 2023-04-22 | 2023-05-10 | 2023-05-10 | NTA_Zone 2 | Sub Structure | B3
47986 |  | Complete |  | 2023-04-22 | 2023-06-14 | IT, Telephone & Data | 100 | 100 |  | 2023-04-22 | 2023-04-22 | 2023-06-14 | 2023-06-14
43794 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 2 (14 m) | Complete | Retaining Wall RCC Works | 2023-04-24 | 2023-04-26 | Fwk_Lift 2 RW | 100 | 100 |  | 2023-04-24 | 2023-04-24 | 2023-04-26 | 2023-04-26 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43754 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 2 (10 m) | Complete | Retaining Wall RCC Works | 2023-04-25 | 2023-04-25 | Checking & Casting_Lift 2 | 100 | 100 |  | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-25 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43764 | Tower A - Sub Structure - B1 to GF - Zone 1A - Sec 6 (10 m) | Complete | Retaining Wall RCC Works | 2023-04-25 | 2023-04-25 | Checking & Casting_Lift 2 | 100 | 100 |  | 2023-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-25 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
44396 | NTA_Zone 2 - Sub Structure - B2 to B1 - Pour 3 | Complete | RCC Works - Slab | 2023-04-25 | 2023-05-18 | Slab_NTA | 100 | 100 |  | 2023-04-25 | 2023-04-25 | 2023-05-18 | 2023-05-18 | NTA_Zone 2 | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
44396 | NTA_Zone 2 - Sub Structure - B2 to B1 - Pour 3 | Complete | RCC Works - Slab | 2023-04-25 | 2023-05-18 | Slab_NTA | 100 | 100 |  | 2023-04-25 | 2023-04-25 | 2023-05-18 | 2023-05-18 | NTA_Zone 2 | Sub Structure | B2
47976 |  | Complete |  | 2023-04-25 | 2023-06-16 | IT, Telephone & Data | 100 | 100 |  | 2023-04-25 | 2023-04-25 | 2023-06-16 | 2023-06-16
48022 |  | Complete |  | 2023-04-25 | 2023-05-30 | Internal Barricading | 100 | 100 |  | 2023-04-25 | 2023-04-25 | 2023-05-30 | 2023-05-30
43851 | Tower A - Sub Structure - B1 to GF - Pour 1B & 6 | Complete | RCC Works - Slab | 2023-04-26 | 2023-05-04 | Slab & Staircase Reinf. | 100 | 100 |  | 2023-04-26 | 2023-04-26 | 2023-05-04 | 2023-05-04 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
43882 | Tower A - Sub Structure - B1 to GF - Pour 9A | Complete | RCC Works - Slab | 2023-04-26 | 2023-04-27 | Slab & Staircase Casting | 100 | 100 |  | 2023-04-26 | 2023-04-26 | 2023-04-27 | 2023-04-27 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
44383 | NTA_Zone 2 - Sub Structure - B2 to B1 | Complete | Retaining Wall RCC Works | 2023-04-26 | 2023-05-04 | Section 7_lift 1 | 100 | 100 |  | 2023-04-26 | 2023-04-26 | 2023-05-04 | 2023-05-04 | NTA_Zone 2 | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
44383 | NTA_Zone 2 - Sub Structure - B2 to B1 | Complete | Retaining Wall RCC Works | 2023-04-26 | 2023-05-04 | Section 7_lift 1 | 100 | 100 |  | 2023-04-26 | 2023-04-26 | 2023-05-04 | 2023-05-04 | NTA_Zone 2 | Sub Structure | B2
44385 | NTA_Zone 2 - Sub Structure - B2 to B1 | Complete | Retaining Wall RCC Works | 2023-04-26 | 2023-05-04 | Section 9_lift 1 | 100 | 100 |  | 2023-04-26 | 2023-04-26 | 2023-05-04 | 2023-05-04 | NTA_Zone 2 | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
44385 | NTA_Zone 2 - Sub Structure - B2 to B1 | Complete | Retaining Wall RCC Works | 2023-04-26 | 2023-05-04 | Section 9_lift 1 | 100 | 100 |  | 2023-04-26 | 2023-04-26 | 2023-05-04 | 2023-05-04 | NTA_Zone 2 | Sub Structure | B2
44393 | NTA_Zone 2 - Sub Structure - B2 to B1 - Pour 2 | Complete | RCC Works - Slab | 2023-04-26 | 2023-05-13 | Slab_NTA | 100 | 100 |  | 2023-04-26 | 2023-04-26 | 2023-05-13 | 2023-05-13 | NTA_Zone 2 | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
44393 | NTA_Zone 2 - Sub Structure - B2 to B1 - Pour 2 | Complete | RCC Works - Slab | 2023-04-26 | 2023-05-13 | Slab_NTA | 100 | 100 |  | 2023-04-26 | 2023-04-26 | 2023-05-13 | 2023-05-13 | NTA_Zone 2 | Sub Structure | B2
43795 | Tower A - Sub Structure - B1 to GF - Zone 2A - Sec 2 (14 m) | Complete | Retaining Wall RCC Works | 2023-04-27 | 2023-04-27 | Checking & Casting_Lift 2 | 100 | 100 |  | 2023-04-27 | 2023-04-27 | 2023-04-27 | 2023-04-27 | Tower A | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43832 | Tower A - Sub Structure - B1 to GF - Pour 1A & 2 | Complete | RCC Works - Slab | 2023-04-27 | 2023-04-28 | Slab & Staircase Casting | 100 | 100 |  | 2023-04-27 | 2023-04-27 | 2023-04-28 | 2023-04-28 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
43841 | Tower A - Sub Structure - B1 to GF - Pour 3 | Complete | RCC Works - Slab | 2023-04-28 | 2023-05-03 | Slab & Staircase Reinf. | 100 | 100 |  | 2023-04-28 | 2023-04-28 | 2023-05-03 | 2023-05-03 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
47987 |  | Complete |  | 2023-05-02 | 2023-06-22 | FF Works | 100 | 100 |  | 2023-05-02 | 2023-05-02 | 2023-06-22 | 2023-06-22
43842 | Tower A - Sub Structure - B1 to GF - Pour 3 | Complete | RCC Works - Slab | 2023-05-04 | 2023-05-05 | Slab & Staircase Casting | 100 | 100 |  | 2023-05-04 | 2023-05-04 | 2023-05-05 | 2023-05-05 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
44410 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-05-04 | 2023-05-16 | Section 2_lift 1 | 100 | 100 |  | 2023-05-04 | 2023-05-04 | 2023-05-16 | 2023-05-16 | NTA_Zone 2 | Sub Structure | B1
44410 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-05-04 | 2023-05-16 | Section 2_lift 1 | 100 | 100 |  | 2023-05-04 | 2023-05-04 | 2023-05-16 | 2023-05-16 | NTA_Zone 2 | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
44420 |  | Complete |  | 2023-05-04 | 2023-08-12 | Retaining Wall_lift 2 | 100 | 100 |  | 2023-05-04 | 2023-05-04 | 2023-08-12 | 2023-08-12
44420 |  | Complete |  | 2023-05-04 | 2023-08-12 | Retaining Wall_lift 2 | 100 | 100 |  | 2023-05-04 | 2023-05-04 | 2023-08-12 | 2023-08-12 |  |  |  | RCC Super Structure | Retaining Wall RCC Works
44421 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-05-04 | 2023-05-11 | Section 1_lift 2 | 100 | 100 |  | 2023-05-04 | 2023-05-04 | 2023-05-11 | 2023-05-11 | NTA_Zone 2 | Sub Structure | B1
44421 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-05-04 | 2023-05-11 | Section 1_lift 2 | 100 | 100 |  | 2023-05-04 | 2023-05-04 | 2023-05-11 | 2023-05-11 | NTA_Zone 2 | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
43852 | Tower A - Sub Structure - B1 to GF - Pour 1B & 6 | Complete | RCC Works - Slab | 2023-05-05 | 2023-05-06 | Slab & Staircase Casting | 100 | 100 |  | 2023-05-05 | 2023-05-05 | 2023-05-06 | 2023-05-06 | Tower A | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
44384 | NTA_Zone 2 - Sub Structure - B2 to B1 | Complete | Retaining Wall RCC Works | 2023-05-05 | 2023-05-12 | Section 8_lift 1 | 100 | 100 |  | 2023-05-05 | 2023-05-05 | 2023-05-12 | 2023-05-12 | NTA_Zone 2 | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
44384 | NTA_Zone 2 - Sub Structure - B2 to B1 | Complete | Retaining Wall RCC Works | 2023-05-05 | 2023-05-12 | Section 8_lift 1 | 100 | 100 |  | 2023-05-05 | 2023-05-05 | 2023-05-12 | 2023-05-12 | NTA_Zone 2 | Sub Structure | B2
40145 |  | Complete |  | 2023-05-08 | 2024-01-24 | B1 to GF_TA & NTA | 100 | 100 |  | 2023-05-08 | 2023-05-08 | 2024-01-24 | 2024-01-24
40145 |  | Complete |  | 2023-05-08 | 2024-01-24 | B1 to GF_TA & NTA | 100 | 100 |  | 2023-05-08 | 2023-05-08 | 2024-01-24 | 2024-01-24 |  |  |  | Finishes | Gypsum Plastering Works
40146 | Tower A - Sub Structure - Finishes & MEP - B1 to GF | Complete | Partition Wall-Blockwork | 2023-05-08 | 2023-05-30 | De-shuttering & Area clearance | 100 | 100 |  | 2023-05-08 | 2023-05-08 | 2023-05-30 | 2023-05-30 | Tower A | Sub Structure | B1
43443 | Tower A - Sub Structure | Milestone Started | Plinth Checking | 2023-05-08 |  | Plinth Checking (30 calendar days) | 100 | 100 |  | 2023-05-08 | 2023-06-16 |  |  | Tower A | Sub Structure | --
43443 | Tower A - Sub Structure | Milestone Started | Plinth Checking | 2023-05-08 |  | Plinth Checking (30 calendar days) | 100 | 100 |  | 2023-05-08 | 2023-06-16 |  |  | Tower A | Sub Structure | --
47977 |  | Complete |  | 2023-05-08 | 2023-06-29 | Relocation of fore court electrical panel and services | 100 | 100 |  | 2023-05-08 | 2023-05-08 | 2023-06-29 | 2023-06-29
44386 | NTA_Zone 2 - Sub Structure - B2 to B1 | Complete | Retaining Wall RCC Works | 2023-05-11 | 2023-05-18 | Section 10_lift 1 | 100 | 100 |  | 2023-05-11 | 2023-05-11 | 2023-05-18 | 2023-05-18 | NTA_Zone 2 | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
44386 | NTA_Zone 2 - Sub Structure - B2 to B1 | Complete | Retaining Wall RCC Works | 2023-05-11 | 2023-05-18 | Section 10_lift 1 | 100 | 100 |  | 2023-05-11 | 2023-05-11 | 2023-05-18 | 2023-05-18 | NTA_Zone 2 | Sub Structure | B2
44403 |  | Complete |  | 2023-05-11 | 2023-06-08 | Pour 6 | 100 | 100 |  | 2023-05-11 | 2023-05-11 | 2023-06-08 | 2023-06-08
44404 | NTA_Zone 2 - Sub Structure - B2 to B1 - Pour 6 | Complete | RCC Works - Vertical | 2023-05-11 | 2023-05-27 | Columns/ Walls_NTA | 100 | 100 |  | 2023-05-11 | 2023-05-11 | 2023-05-27 | 2023-05-27 | NTA_Zone 2 | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
44404 | NTA_Zone 2 - Sub Structure - B2 to B1 - Pour 6 | Complete | RCC Works - Vertical | 2023-05-11 | 2023-05-27 | Columns/ Walls_NTA | 100 | 100 |  | 2023-05-11 | 2023-05-11 | 2023-05-27 | 2023-05-27 | NTA_Zone 2 | Sub Structure | B2
44387 | NTA_Zone 2 - Sub Structure - B2 to B1 | Complete | Retaining Wall RCC Works | 2023-05-13 | 2023-05-20 | Section 11_lift 1 | 100 | 100 |  | 2023-05-13 | 2023-05-13 | 2023-05-20 | 2023-05-20 | NTA_Zone 2 | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
44387 | NTA_Zone 2 - Sub Structure - B2 to B1 | Complete | Retaining Wall RCC Works | 2023-05-13 | 2023-05-20 | Section 11_lift 1 | 100 | 100 |  | 2023-05-13 | 2023-05-13 | 2023-05-20 | 2023-05-20 | NTA_Zone 2 | Sub Structure | B2
44399 | NTA_Zone 2 - Sub Structure - B2 to B1 - Pour 4 | Complete | RCC Works - Slab | 2023-05-13 | 2023-05-30 | Slab_NTA | 100 | 100 |  | 2023-05-13 | 2023-05-13 | 2023-05-30 | 2023-05-30 | NTA_Zone 2 | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
44399 | NTA_Zone 2 - Sub Structure - B2 to B1 - Pour 4 | Complete | RCC Works - Slab | 2023-05-13 | 2023-05-30 | Slab_NTA | 100 | 100 |  | 2023-05-13 | 2023-05-13 | 2023-05-30 | 2023-05-30 | NTA_Zone 2 | Sub Structure | B2
44411 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-05-15 | 2023-05-26 | Section 3_lift 1 | 100 | 100 |  | 2023-05-15 | 2023-05-15 | 2023-05-26 | 2023-05-26 | NTA_Zone 2 | Sub Structure | B1
44411 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-05-15 | 2023-05-26 | Section 3_lift 1 | 100 | 100 |  | 2023-05-15 | 2023-05-15 | 2023-05-26 | 2023-05-26 | NTA_Zone 2 | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
44435 |  | Complete |  | 2023-05-15 | 2023-07-07 | Pour 2 | 100 | 100 |  | 2023-05-15 | 2023-05-15 | 2023-07-07 | 2023-07-07
44436 | NTA_Zone 2 - Sub Structure - B1 to GF - Pour 2 | Complete | RCC Works - Vertical | 2023-05-15 | 2023-05-31 | Columns/ Walls_NTA | 100 | 100 |  | 2023-05-15 | 2023-05-15 | 2023-05-31 | 2023-05-31 | NTA_Zone 2 | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44436 | NTA_Zone 2 - Sub Structure - B1 to GF - Pour 2 | Complete | RCC Works - Vertical | 2023-05-15 | 2023-05-31 | Columns/ Walls_NTA | 100 | 100 |  | 2023-05-15 | 2023-05-15 | 2023-05-31 | 2023-05-31 | NTA_Zone 2 | Sub Structure | B1
44413 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-05-17 | 2023-05-29 | Section 5_lift 1 | 100 | 100 |  | 2023-05-17 | 2023-05-17 | 2023-05-29 | 2023-05-29 | NTA_Zone 2 | Sub Structure | B1
44413 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-05-17 | 2023-05-29 | Section 5_lift 1 | 100 | 100 |  | 2023-05-17 | 2023-05-17 | 2023-05-29 | 2023-05-29 | NTA_Zone 2 | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
44422 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-05-17 | 2023-05-24 | Section 2_lift 2 | 100 | 100 |  | 2023-05-17 | 2023-05-17 | 2023-05-24 | 2023-05-24 | NTA_Zone 2 | Sub Structure | B1
44422 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-05-17 | 2023-05-24 | Section 2_lift 2 | 100 | 100 |  | 2023-05-17 | 2023-05-17 | 2023-05-24 | 2023-05-24 | NTA_Zone 2 | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
44691 |  | Started |  | 2021-04-01 | 2028-09-28 | Tower B | 100 | 12 |  | 2023-05-17 | 2023-05-17 | 2028-09-28
44692 |  | Started |  | 2023-05-17 | 2028-09-26 | CONSTRUCTION_TOWER B_ZONE 3 | 100 | 9 |  | 2023-05-17 | 2023-05-17 | 2028-09-28
44693 |  | Complete |  | 2023-05-17 | 2024-03-30 | Piling, Rock Anchoring & Excavation (Zone 3) | 100 | 100 |  | 2023-05-17 | 2023-05-17 | 2024-03-30 | 2024-03-30
44694 | Tower B | Complete | Excavation upto -4 Mtr | 2023-05-17 | 2023-10-17 | Excavation in TB Area (excl. Piling bay) | 100 | 100 |  | 2023-05-17 | 2023-05-17 | 2023-10-17 | 2023-10-17 | Tower B | --
44438 |  | Complete |  | 2023-05-19 | 2023-06-29 | Pour 3 | 100 | 100 |  | 2023-05-19 | 2023-05-19 | 2023-06-29 | 2023-06-29
44439 | NTA_Zone 2 - Sub Structure - B1 to GF - Pour 3 | Complete | RCC Works - Vertical | 2023-05-19 | 2023-06-10 | Columns/ Walls_NTA | 100 | 100 |  | 2023-05-19 | 2023-05-19 | 2023-06-10 | 2023-06-10 | NTA_Zone 2 | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44439 | NTA_Zone 2 - Sub Structure - B1 to GF - Pour 3 | Complete | RCC Works - Vertical | 2023-05-19 | 2023-06-10 | Columns/ Walls_NTA | 100 | 100 |  | 2023-05-19 | 2023-05-19 | 2023-06-10 | 2023-06-10 | NTA_Zone 2 | Sub Structure | B1
47978 |  | Complete |  | 2023-05-19 | 2023-07-14 | FF Works | 100 | 100 |  | 2023-05-19 | 2023-05-19 | 2023-07-14 | 2023-07-14
44405 | NTA_Zone 2 - Sub Structure - B2 to B1 - Pour 6 | Complete | RCC Works - Slab | 2023-05-23 | 2023-06-08 | Slab_NTA | 100 | 100 |  | 2023-05-23 | 2023-05-23 | 2023-06-08 | 2023-06-08 | NTA_Zone 2 | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
44405 | NTA_Zone 2 - Sub Structure - B2 to B1 - Pour 6 | Complete | RCC Works - Slab | 2023-05-23 | 2023-06-08 | Slab_NTA | 100 | 100 |  | 2023-05-23 | 2023-05-23 | 2023-06-08 | 2023-06-08 | NTA_Zone 2 | Sub Structure | B2
44434 | NTA_Zone 2 - Sub Structure - B1 to GF - Pour 1 | Complete | RCC Works - Slab | 2023-05-25 | 2023-06-10 | Slab_NTA | 100 | 100 |  | 2023-05-25 | 2023-05-25 | 2023-06-10 | 2023-06-10 | NTA_Zone 2 | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
44434 | NTA_Zone 2 - Sub Structure - B1 to GF - Pour 1 | Complete | RCC Works - Slab | 2023-05-25 | 2023-06-10 | Slab_NTA | 100 | 100 |  | 2023-05-25 | 2023-05-25 | 2023-06-10 | 2023-06-10 | NTA_Zone 2 | Sub Structure | B1
44412 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-05-27 | 2023-06-08 | Section 4_lift 1 | 100 | 100 |  | 2023-05-27 | 2023-05-27 | 2023-06-08 | 2023-06-08 | NTA_Zone 2 | Sub Structure | B1
44412 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-05-27 | 2023-06-08 | Section 4_lift 1 | 100 | 100 |  | 2023-05-27 | 2023-05-27 | 2023-06-08 | 2023-06-08 | NTA_Zone 2 | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
44423 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-05-27 | 2023-06-03 | Section 3_lift 2 | 100 | 100 |  | 2023-05-27 | 2023-05-27 | 2023-06-03 | 2023-06-03 | NTA_Zone 2 | Sub Structure | B1
44423 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-05-27 | 2023-06-03 | Section 3_lift 2 | 100 | 100 |  | 2023-05-27 | 2023-05-27 | 2023-06-03 | 2023-06-03 | NTA_Zone 2 | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
44322 | NTA_Zone 2 - Foundation - Pour 5 | Complete | Foundation RCC Works | 2023-05-29 | 2023-06-05 | Fwk & Casting_NTA | 100 | 100 |  | 2023-05-29 | 2023-05-29 | 2023-06-05 | 2023-06-05 | NTA_Zone 2 | Foundation |  | RCC Sub Structure | Raft RCC Works
44322 | NTA_Zone 2 - Foundation - Pour 5 | Complete | Foundation RCC Works | 2023-05-29 | 2023-06-05 | Fwk & Casting_NTA | 100 | 100 |  | 2023-05-29 | 2023-05-29 | 2023-06-05 | 2023-06-05 | NTA_Zone 2 | Foundation |  | RCC Super Structure | Foundation RCC Works
44322 | NTA_Zone 2 - Foundation - Pour 5 | Complete | Foundation RCC Works | 2023-05-29 | 2023-06-05 | Fwk & Casting_NTA | 100 | 100 |  | 2023-05-29 | 2023-05-29 | 2023-06-05 | 2023-06-05 | NTA_Zone 2 | Foundation
44414 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-05-30 | 2023-06-10 | Section 6_lift 1 | 100 | 100 |  | 2023-05-30 | 2023-05-30 | 2023-06-10 | 2023-06-10 | NTA_Zone 2 | Sub Structure | B1
44414 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-05-30 | 2023-06-10 | Section 6_lift 1 | 100 | 100 |  | 2023-05-30 | 2023-05-30 | 2023-06-10 | 2023-06-10 | NTA_Zone 2 | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
44425 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-05-30 | 2023-06-06 | Section 5_lift 2 | 100 | 100 |  | 2023-05-30 | 2023-05-30 | 2023-06-06 | 2023-06-06 | NTA_Zone 2 | Sub Structure | B1
44425 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-05-30 | 2023-06-06 | Section 5_lift 2 | 100 | 100 |  | 2023-05-30 | 2023-05-30 | 2023-06-06 | 2023-06-06 | NTA_Zone 2 | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
44441 |  | Complete |  | 2023-05-31 | 2023-08-18 | Pour 4 | 100 | 100 |  | 2023-05-31 | 2023-05-31 | 2023-08-18 | 2023-08-18
44442 | NTA_Zone 2 - Sub Structure - B1 to GF - Pour 4 | Complete | RCC Works - Vertical | 2023-05-31 | 2023-06-16 | Columns/ Walls_NTA | 100 | 100 |  | 2023-05-31 | 2023-05-31 | 2023-06-16 | 2023-06-16 | NTA_Zone 2 | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44442 | NTA_Zone 2 - Sub Structure - B1 to GF - Pour 4 | Complete | RCC Works - Vertical | 2023-05-31 | 2023-06-16 | Columns/ Walls_NTA | 100 | 100 |  | 2023-05-31 | 2023-05-31 | 2023-06-16 | 2023-06-16 | NTA_Zone 2 | Sub Structure | B1
48019 |  | Complete |  | 2023-05-31 | 2023-08-31 | Alternate Parking Works | 100 | 100 |  | 2023-05-31 | 2023-05-31 | 2023-08-31 | 2023-08-31
48023 |  | Complete |  | 2023-05-31 | 2023-07-05 | Dismantling & Stack Parking | 100 | 100 |  | 2023-05-31 | 2023-05-31 | 2023-07-05 | 2023-07-05
44345 |  | Complete |  | 2023-06-06 | 2023-07-27 | Pour 5 | 100 | 100 |  | 2023-06-06 | 2023-06-06 | 2023-07-27 | 2023-07-27
44346 | NTA_Zone 2 - Sub Structure - B3 to B2 - Pour 5 | Complete | RCC Works - Vertical | 2023-06-06 | 2023-06-29 | Columns/ Walls_NTA | 100 | 100 |  | 2023-06-06 | 2023-06-06 | 2023-06-29 | 2023-06-29 | NTA_Zone 2 | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
44346 | NTA_Zone 2 - Sub Structure - B3 to B2 - Pour 5 | Complete | RCC Works - Vertical | 2023-06-06 | 2023-06-29 | Columns/ Walls_NTA | 100 | 100 |  | 2023-06-06 | 2023-06-06 | 2023-06-29 | 2023-06-29 | NTA_Zone 2 | Sub Structure | B3
44440 | NTA_Zone 2 - Sub Structure - B1 to GF - Pour 3 | Complete | RCC Works - Slab | 2023-06-06 | 2023-06-29 | Slab_NTA | 100 | 100 |  | 2023-06-06 | 2023-06-06 | 2023-06-29 | 2023-06-29 | NTA_Zone 2 | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
44440 | NTA_Zone 2 - Sub Structure - B1 to GF - Pour 3 | Complete | RCC Works - Slab | 2023-06-06 | 2023-06-29 | Slab_NTA | 100 | 100 |  | 2023-06-06 | 2023-06-06 | 2023-06-29 | 2023-06-29 | NTA_Zone 2 | Sub Structure | B1
44415 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-06-09 | 2023-06-21 | Section 7_lift 1 | 100 | 100 |  | 2023-06-09 | 2023-06-09 | 2023-06-21 | 2023-06-21 | NTA_Zone 2 | Sub Structure | B1
44415 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-06-09 | 2023-06-21 | Section 7_lift 1 | 100 | 100 |  | 2023-06-09 | 2023-06-09 | 2023-06-21 | 2023-06-21 | NTA_Zone 2 | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
44424 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-06-09 | 2023-06-16 | Section 4_lift 2 | 100 | 100 |  | 2023-06-09 | 2023-06-09 | 2023-06-16 | 2023-06-16 | NTA_Zone 2 | Sub Structure | B1
44424 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-06-09 | 2023-06-16 | Section 4_lift 2 | 100 | 100 |  | 2023-06-09 | 2023-06-09 | 2023-06-16 | 2023-06-16 | NTA_Zone 2 | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
44447 |  | Complete |  | 2023-06-09 | 2023-09-04 | Pour 6 | 100 | 100 |  | 2023-06-09 | 2023-06-09 | 2023-09-04 | 2023-09-04
44448 | NTA_Zone 2 - Sub Structure - B1 to GF - Pour 6 | Complete | RCC Works - Vertical | 2023-06-09 | 2023-06-26 | Columns/ Walls_NTA | 100 | 100 |  | 2023-06-09 | 2023-06-09 | 2023-06-26 | 2023-06-26 | NTA_Zone 2 | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44448 | NTA_Zone 2 - Sub Structure - B1 to GF - Pour 6 | Complete | RCC Works - Vertical | 2023-06-09 | 2023-06-26 | Columns/ Walls_NTA | 100 | 100 |  | 2023-06-09 | 2023-06-09 | 2023-06-26 | 2023-06-26 | NTA_Zone 2 | Sub Structure | B1
44417 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-06-12 | 2023-06-23 | Section 9_lift 1 | 100 | 100 |  | 2023-06-12 | 2023-06-12 | 2023-06-23 | 2023-06-23 | NTA_Zone 2 | Sub Structure | B1
44417 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-06-12 | 2023-06-23 | Section 9_lift 1 | 100 | 100 |  | 2023-06-12 | 2023-06-12 | 2023-06-23 | 2023-06-23 | NTA_Zone 2 | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
44426 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-06-12 | 2023-06-19 | Section 6_lift 2 | 100 | 100 |  | 2023-06-12 | 2023-06-12 | 2023-06-19 | 2023-06-19 | NTA_Zone 2 | Sub Structure | B1
44426 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-06-12 | 2023-06-19 | Section 6_lift 2 | 100 | 100 |  | 2023-06-12 | 2023-06-12 | 2023-06-19 | 2023-06-19 | NTA_Zone 2 | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
47980 |  | Complete |  | 2023-06-15 | 2023-08-29 | Dismantling | 100 | 100 |  | 2023-06-15 | 2023-06-15 | 2023-08-29 | 2023-08-29
39122 |  | Complete |  | 2023-06-16 | 2023-06-16 | Completion of Zone 1 Ground Floor | 100 | 100 |  | 2023-06-16 | 2023-06-16 | 2023-06-16 | 2023-06-16
39281 |  | Started |  | 2023-06-16 | 2026-02-27 | Super-Structure_TA | 100 | 85 |  | 2023-06-16 | 2023-06-16 | 2026-03-30
39282 |  | Started |  | 2023-06-16 | 2026-01-08 | TA_Core Wall Construction | 100 | 91 |  | 2023-06-16 | 2023-06-16 | 2026-02-07
39283 |  | Complete |  | 2023-06-16 | 2023-11-01 | Core Wall Lift GF-P6 | 100 | 100 |  | 2023-06-16 | 2023-06-16 | 2023-11-01 | 2023-11-01
39284 |  | Complete |  | 2023-06-16 | 2023-07-31 | Core Wall GF-P1 (Conv Form) | 100 | 100 |  | 2023-06-16 | 2023-06-16 | 2023-07-31 | 2023-07-31
39285 | Tower A - Super Structure - Core Wall GF-P1 | Complete | Core Wall RCC Works | 2023-06-16 | 2023-06-23 | Verticals Reinforcement | 100 | 100 |  | 2023-06-16 | 2023-06-16 | 2023-06-23 | 2023-06-23 | Tower A | Super Structure | GF | RCC Super Structure | Core Wall RCC Works
39785 |  | Started |  | 2023-06-16 | 2026-02-27 | TA_Core & Outer Slab | 100 | 79 |  | 2023-06-16 | 2023-06-16 | 2026-03-30
39786 |  | Complete |  | 2023-06-16 | 2023-08-29 | GF-P1 (conv. Fwk.) | 100 | 100 |  | 2023-06-16 | 2023-06-16 | 2023-08-29 | 2023-08-29
39787 | Tower A - Super Structure - Core & Outer Slab GF-P1 | Complete | RCC Works - Vertical | 2023-06-16 | 2023-06-27 | Verticals Reinf | 100 | 100 |  | 2023-06-16 | 2023-06-16 | 2023-06-27 | 2023-06-27 | Tower A | Super Structure | GF | RCC Sub Structure | RCC Works - Vertical
44437 | NTA_Zone 2 - Sub Structure - B1 to GF - Pour 2 | Complete | RCC Works - Slab | 2023-06-20 | 2023-07-07 | Slab_NTA | 100 | 100 |  | 2023-06-20 | 2023-06-20 | 2023-07-07 | 2023-07-07 | NTA_Zone 2 | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
44437 | NTA_Zone 2 - Sub Structure - B1 to GF - Pour 2 | Complete | RCC Works - Slab | 2023-06-20 | 2023-07-07 | Slab_NTA | 100 | 100 |  | 2023-06-20 | 2023-06-20 | 2023-07-07 | 2023-07-07 | NTA_Zone 2 | Sub Structure | B1
39333 |  | Complete |  | 2023-06-21 | 2023-09-05 | Core Wall ACS Assembly | 100 | 100 |  | 2023-06-21 | 2023-06-21 | 2023-09-05 | 2023-09-05
39334 | Tower A - Super Structure - Core Wall ACS Assembly | Complete | ACS Assembly | 2023-06-21 | 2023-07-08 | ACS Assembly on ground | 100 | 100 |  | 2023-06-21 | 2023-06-21 | 2023-07-08 | 2023-07-08 | Tower A | Super Structure
44416 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-06-22 | 2023-07-05 | Section 8_lift 1 | 100 | 100 |  | 2023-06-22 | 2023-06-22 | 2023-07-05 | 2023-07-05 | NTA_Zone 2 | Sub Structure | B1
44416 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-06-22 | 2023-07-05 | Section 8_lift 1 | 100 | 100 |  | 2023-06-22 | 2023-06-22 | 2023-07-05 | 2023-07-05 | NTA_Zone 2 | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
44427 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-06-22 | 2023-06-30 | Section 7_lift 2 | 100 | 100 |  | 2023-06-22 | 2023-06-22 | 2023-06-30 | 2023-06-30 | NTA_Zone 2 | Sub Structure | B1
44427 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-06-22 | 2023-06-30 | Section 7_lift 2 | 100 | 100 |  | 2023-06-22 | 2023-06-22 | 2023-06-30 | 2023-06-30 | NTA_Zone 2 | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
39788 | Tower A - Super Structure - Core & Outer Slab GF-P1 | Complete | RCC Works - Vertical | 2023-06-23 | 2023-08-05 | Vertical Shuttering (incl Reckli gangform maing) | 100 | 100 |  | 2023-06-23 | 2023-06-23 | 2023-08-05 | 2023-08-05 | Tower A | Super Structure | GF | RCC Sub Structure | RCC Works - Vertical
44347 | NTA_Zone 2 - Sub Structure - B3 to B2 - Pour 5 | Complete | RCC Works - Slab | 2023-06-23 | 2023-07-27 | Slab_NTA | 100 | 100 |  | 2023-06-23 | 2023-06-23 | 2023-07-27 | 2023-07-27 | NTA_Zone 2 | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
44347 | NTA_Zone 2 - Sub Structure - B3 to B2 - Pour 5 | Complete | RCC Works - Slab | 2023-06-23 | 2023-07-27 | Slab_NTA | 100 | 100 |  | 2023-06-23 | 2023-06-23 | 2023-07-27 | 2023-07-27 | NTA_Zone 2 | Sub Structure | B3
39286 | Tower A - Super Structure - Core Wall GF-P1 | Complete | Core Wall RCC Works | 2023-06-24 | 2023-06-30 | Verticals Shuttering | 100 | 100 |  | 2023-06-24 | 2023-06-24 | 2023-06-30 | 2023-06-30 | Tower A | Super Structure | GF | RCC Super Structure | Core Wall RCC Works
44418 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-06-24 | 2023-07-07 | Section 10_lift 1 | 100 | 100 |  | 2023-06-24 | 2023-06-24 | 2023-07-07 | 2023-07-07 | NTA_Zone 2 | Sub Structure | B1
44418 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-06-24 | 2023-07-07 | Section 10_lift 1 | 100 | 100 |  | 2023-06-24 | 2023-06-24 | 2023-07-07 | 2023-07-07 | NTA_Zone 2 | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
44429 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-06-24 | 2023-07-03 | Section 9_lift 2 | 100 | 100 |  | 2023-06-24 | 2023-06-24 | 2023-07-03 | 2023-07-03 | NTA_Zone 2 | Sub Structure | B1
44429 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-06-24 | 2023-07-03 | Section 9_lift 2 | 100 | 100 |  | 2023-06-24 | 2023-06-24 | 2023-07-03 | 2023-07-03 | NTA_Zone 2 | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
44672 | Tower A | Complete | Award of Packages | 2023-06-27 | 2024-02-07 | Façade Package | 100 | 100 |  | 2023-06-27 | 2023-06-27 | 2024-02-07 | 2024-02-07 | Tower A | --
39287 | Tower A - Super Structure - Core Wall GF-P1 | Complete | Core Wall RCC Works | 2023-07-01 | 2023-07-01 | Vertical Casting | 100 | 100 |  | 2023-07-01 | 2023-07-01 | 2023-07-01 | 2023-07-01 | Tower A | Super Structure | GF | RCC Super Structure | Core Wall RCC Works
39288 | Tower A - Super Structure - Core Wall GF-P1 | Complete | RCC Works - Slab | 2023-07-03 | 2023-07-20 | Slab Shuttering | 100 | 100 |  | 2023-07-03 | 2023-07-03 | 2023-07-20 | 2023-07-20 | Tower A | Super Structure | GF | RCC Sub Structure | RCC Works - Slab
39288 | Tower A - Super Structure - Core Wall GF-P1 | Complete | RCC Works - Slab | 2023-07-03 | 2023-07-20 | Slab Shuttering | 100 | 100 |  | 2023-07-03 | 2023-07-03 | 2023-07-20 | 2023-07-20 | Tower A | Super Structure | GF | RCC Super Structure | Core Wall RCC Works
39291 |  | Complete |  | 2023-07-03 | 2023-08-19 | Core Wall P1-P2 (Conv Form) | 100 | 100 |  | 2023-07-03 | 2023-07-03 | 2023-08-19 | 2023-08-19
39292 | Tower A - Super Structure - Core Wall P1-P2 | Complete | Core Wall RCC Works | 2023-07-03 | 2023-07-13 | Verticals Reinforcement | 100 | 100 |  | 2023-07-03 | 2023-07-03 | 2023-07-13 | 2023-07-13 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
44419 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-07-06 | 2023-07-28 | Section 11_lift 1 | 100 | 100 |  | 2023-07-06 | 2023-07-06 | 2023-07-28 | 2023-07-28 | NTA_Zone 2 | Sub Structure | B1
44419 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-07-06 | 2023-07-28 | Section 11_lift 1 | 100 | 100 |  | 2023-07-06 | 2023-07-06 | 2023-07-28 | 2023-07-28 | NTA_Zone 2 | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
44428 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-07-06 | 2023-07-20 | Section 8_lift 2 | 100 | 100 |  | 2023-07-06 | 2023-07-06 | 2023-07-20 | 2023-07-20 | NTA_Zone 2 | Sub Structure | B1
44428 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-07-06 | 2023-07-20 | Section 8_lift 2 | 100 | 100 |  | 2023-07-06 | 2023-07-06 | 2023-07-20 | 2023-07-20 | NTA_Zone 2 | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
39293 | Tower A - Super Structure - Core Wall P1-P2 | Complete | Core Wall RCC Works | 2023-07-07 | 2023-07-15 | Verticals Shuttering | 100 | 100 |  | 2023-07-07 | 2023-07-07 | 2023-07-15 | 2023-07-15 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
44430 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-07-08 | 2023-07-22 | Section 10_lift 2 | 100 | 100 |  | 2023-07-08 | 2023-07-08 | 2023-07-22 | 2023-07-22 | NTA_Zone 2 | Sub Structure | B1
44430 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-07-08 | 2023-07-22 | Section 10_lift 2 | 100 | 100 |  | 2023-07-08 | 2023-07-08 | 2023-07-22 | 2023-07-22 | NTA_Zone 2 | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
47967 |  | Complete |  | 2023-07-15 | 2023-09-25 | Dismantling | 100 | 100 |  | 2023-07-15 | 2023-07-15 | 2023-09-25 | 2023-09-25
39294 | Tower A - Super Structure - Core Wall P1-P2 | Complete | Core Wall RCC Works | 2023-07-20 | 2023-07-20 | Vertical Casting | 100 | 100 |  | 2023-07-20 | 2023-07-20 | 2023-07-20 | 2023-07-20 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39289 | Tower A - Super Structure - Core Wall GF-P1 | Complete | RCC Works - Slab | 2023-07-21 | 2023-07-29 | Slab Reinforcement | 100 | 100 |  | 2023-07-21 | 2023-07-21 | 2023-07-29 | 2023-07-29 | Tower A | Super Structure | GF | RCC Sub Structure | RCC Works - Slab
39298 |  | Complete |  | 2023-07-21 | 2023-08-08 | Core Wall P2-P3 (Conv Form) | 100 | 100 |  | 2023-07-21 | 2023-07-21 | 2023-08-08 | 2023-08-08
39299 | Tower A - Super Structure - Core Wall P2-P3 | Complete | Core Wall RCC Works | 2023-07-21 | 2023-07-27 | Verticals Reinforcement | 100 | 100 |  | 2023-07-21 | 2023-07-21 | 2023-07-27 | 2023-07-27 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
44443 | NTA_Zone 2 - Sub Structure - B1 to GF - Pour 4 | Complete | RCC Works - Slab | 2023-07-21 | 2023-08-18 | Slab_NTA | 100 | 100 |  | 2023-07-21 | 2023-07-21 | 2023-08-18 | 2023-08-18 | NTA_Zone 2 | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
44443 | NTA_Zone 2 - Sub Structure - B1 to GF - Pour 4 | Complete | RCC Works - Slab | 2023-07-21 | 2023-08-18 | Slab_NTA | 100 | 100 |  | 2023-07-21 | 2023-07-21 | 2023-08-18 | 2023-08-18 | NTA_Zone 2 | Sub Structure | B1
39300 | Tower A - Super Structure - Core Wall P2-P3 | Complete | Core Wall RCC Works | 2023-07-28 | 2023-07-29 | Verticals Shuttering | 100 | 100 |  | 2023-07-28 | 2023-07-28 | 2023-07-29 | 2023-07-29 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39302 | Tower A - Super Structure - Core Wall P2-P3 | Complete | RCC Works - Slab | 2023-07-28 | 2023-08-05 | Slab Shuttering | 100 | 100 |  | 2023-07-28 | 2023-07-28 | 2023-08-05 | 2023-08-05 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Slab
39302 | Tower A - Super Structure - Core Wall P2-P3 | Complete | RCC Works - Slab | 2023-07-28 | 2023-08-05 | Slab Shuttering | 100 | 100 |  | 2023-07-28 | 2023-07-28 | 2023-08-05 | 2023-08-05 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
44400 |  | Complete |  | 2023-07-28 | 2023-09-19 | Pour 5 | 100 | 100 |  | 2023-07-28 | 2023-07-28 | 2023-09-19 | 2023-09-19
44401 | NTA_Zone 2 - Sub Structure - B2 to B1 - Pour 5 | Complete | RCC Works - Vertical | 2023-07-28 | 2023-08-31 | Columns/ Walls_NTA | 100 | 100 |  | 2023-07-28 | 2023-07-28 | 2023-08-31 | 2023-08-31 | NTA_Zone 2 | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
44401 | NTA_Zone 2 - Sub Structure - B2 to B1 - Pour 5 | Complete | RCC Works - Vertical | 2023-07-28 | 2023-08-31 | Columns/ Walls_NTA | 100 | 100 |  | 2023-07-28 | 2023-07-28 | 2023-08-31 | 2023-08-31 | NTA_Zone 2 | Sub Structure | B2
44431 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-07-29 | 2023-08-12 | Section 11_lift 2 | 100 | 100 |  | 2023-07-29 | 2023-07-29 | 2023-08-12 | 2023-08-12 | NTA_Zone 2 | Sub Structure | B1
44431 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Retaining Wall RCC Works | 2023-07-29 | 2023-08-12 | Section 11_lift 2 | 100 | 100 |  | 2023-07-29 | 2023-07-29 | 2023-08-12 | 2023-08-12 | NTA_Zone 2 | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
39290 | Tower A - Super Structure - Core Wall GF-P1 | Complete | RCC Works - Slab | 2023-07-31 | 2023-07-31 | Slab Casting | 100 | 100 |  | 2023-07-31 | 2023-07-31 | 2023-07-31 | 2023-07-31 | Tower A | Super Structure | GF | RCC Sub Structure | RCC Works - Slab
39290 | Tower A - Super Structure - Core Wall GF-P1 | Complete | RCC Works - Slab | 2023-07-31 | 2023-07-31 | Slab Casting | 100 | 100 |  | 2023-07-31 | 2023-07-31 | 2023-07-31 | 2023-07-31 | Tower A | Super Structure | GF | RCC Super Structure | Core Wall RCC Works
39301 | Tower A - Super Structure - Core Wall P2-P3 | Complete | Core Wall RCC Works | 2023-07-31 | 2023-07-31 | Vertical Casting | 100 | 100 |  | 2023-07-31 | 2023-07-31 | 2023-07-31 | 2023-07-31 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39790 | Tower A - Super Structure - Core & Outer Slab GF-P1 | Complete | RCC Works - Slab | 2023-07-31 | 2023-08-24 | Slab Shuttering | 100 | 100 |  | 2023-07-31 | 2023-07-31 | 2023-08-24 | 2023-08-24 | Tower A | Super Structure | GF | RCC Sub Structure | RCC Works - Slab
39790 | Tower A - Super Structure - Core & Outer Slab GF-P1 | Complete | RCC Works - Slab | 2023-07-31 | 2023-08-24 | Slab Shuttering | 100 | 100 |  | 2023-07-31 | 2023-07-31 | 2023-08-24 | 2023-08-24 | Tower A | Super Structure | GF | RCC Super Structure | Core Wall RCC Works
39295 | Tower A - Super Structure - Core Wall P1-P2 | Complete | RCC Works - Slab | 2023-08-04 | 2023-08-16 | Slab Shuttering | 100 | 100 |  | 2023-08-04 | 2023-08-04 | 2023-08-16 | 2023-08-16 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Slab
39295 | Tower A - Super Structure - Core Wall P1-P2 | Complete | RCC Works - Slab | 2023-08-04 | 2023-08-16 | Slab Shuttering | 100 | 100 |  | 2023-08-04 | 2023-08-04 | 2023-08-16 | 2023-08-16 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39303 | Tower A - Super Structure - Core Wall P2-P3 | Complete | RCC Works - Slab | 2023-08-04 | 2023-08-07 | Slab Reinforcement | 100 | 100 |  | 2023-08-04 | 2023-08-04 | 2023-08-07 | 2023-08-07 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Slab
39305 |  | Complete |  | 2023-08-05 | 2023-08-30 | Core Wall P3-P4 (Conv Form) | 100 | 100 |  | 2023-08-05 | 2023-08-05 | 2023-08-30 | 2023-08-30
39306 | Tower A - Super Structure - Core Wall P3-P4 | Complete | Core Wall RCC Works | 2023-08-05 | 2023-08-14 | Verticals Reinforcement | 100 | 100 |  | 2023-08-05 | 2023-08-05 | 2023-08-14 | 2023-08-14 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39789 | Tower A - Super Structure - Core & Outer Slab GF-P1 | Complete | RCC Works - Vertical | 2023-08-07 | 2023-08-07 | Verticals Casting | 100 | 100 |  | 2023-08-07 | 2023-08-07 | 2023-08-07 | 2023-08-07 | Tower A | Super Structure | GF | RCC Sub Structure | RCC Works - Vertical
39789 | Tower A - Super Structure - Core & Outer Slab GF-P1 | Complete | RCC Works - Vertical | 2023-08-07 | 2023-08-07 | Verticals Casting | 100 | 100 |  | 2023-08-07 | 2023-08-07 | 2023-08-07 | 2023-08-07 | Tower A | Super Structure | GF | RCC Super Structure | Core Wall RCC Works
39304 | Tower A - Super Structure - Core Wall P2-P3 | Complete | RCC Works - Slab | 2023-08-08 | 2023-08-08 | Slab Casting | 100 | 100 |  | 2023-08-08 | 2023-08-08 | 2023-08-08 | 2023-08-08 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Slab
39304 | Tower A - Super Structure - Core Wall P2-P3 | Complete | RCC Works - Slab | 2023-08-08 | 2023-08-08 | Slab Casting | 100 | 100 |  | 2023-08-08 | 2023-08-08 | 2023-08-08 | 2023-08-08 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39296 | Tower A - Super Structure - Core Wall P1-P2 | Complete | RCC Works - Slab | 2023-08-12 | 2023-08-18 | Slab Reinforcement | 100 | 100 |  | 2023-08-12 | 2023-08-12 | 2023-08-18 | 2023-08-18 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Slab
39307 | Tower A - Super Structure - Core Wall P3-P4 | Complete | Core Wall RCC Works | 2023-08-14 | 2023-08-17 | Verticals Shuttering | 100 | 100 |  | 2023-08-14 | 2023-08-14 | 2023-08-17 | 2023-08-17 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
44449 | NTA_Zone 2 - Sub Structure - B1 to GF - Pour 6 | Complete | RCC Works - Slab | 2023-08-14 | 2023-09-04 | Slab_NTA | 100 | 100 |  | 2023-08-14 | 2023-08-14 | 2023-09-04 | 2023-09-04 | NTA_Zone 2 | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
44449 | NTA_Zone 2 - Sub Structure - B1 to GF - Pour 6 | Complete | RCC Works - Slab | 2023-08-14 | 2023-09-04 | Slab_NTA | 100 | 100 |  | 2023-08-14 | 2023-08-14 | 2023-09-04 | 2023-09-04 | NTA_Zone 2 | Sub Structure | B1
39309 | Tower A - Super Structure - Core Wall P3-P4 | Complete | RCC Works - Slab | 2023-08-17 | 2023-08-25 | Slab Shuttering | 100 | 100 |  | 2023-08-17 | 2023-08-17 | 2023-08-25 | 2023-08-25 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Slab
39309 | Tower A - Super Structure - Core Wall P3-P4 | Complete | RCC Works - Slab | 2023-08-17 | 2023-08-25 | Slab Shuttering | 100 | 100 |  | 2023-08-17 | 2023-08-17 | 2023-08-25 | 2023-08-25 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39791 | Tower A - Super Structure - Core & Outer Slab GF-P1 | Complete | RCC Works - Slab | 2023-08-17 | 2023-08-28 | Slab Reinf | 100 | 100 |  | 2023-08-17 | 2023-08-17 | 2023-08-28 | 2023-08-28 | Tower A | Super Structure | GF | RCC Sub Structure | RCC Works - Slab
39791 | Tower A - Super Structure - Core & Outer Slab GF-P1 | Complete | RCC Works - Slab | 2023-08-17 | 2023-08-28 | Slab Reinf | 100 | 100 |  | 2023-08-17 | 2023-08-17 | 2023-08-28 | 2023-08-28 | Tower A | Super Structure | GF | RCC Super Structure | Core Wall RCC Works
39308 | Tower A - Super Structure - Core Wall P3-P4 | Complete | Core Wall RCC Works | 2023-08-18 | 2023-08-18 | Vertical Casting | 100 | 100 |  | 2023-08-18 | 2023-08-18 | 2023-08-18 | 2023-08-18 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39297 | Tower A - Super Structure - Core Wall P1-P2 | Complete | RCC Works - Slab | 2023-08-19 | 2023-08-19 | Slab Casting | 100 | 100 |  | 2023-08-19 | 2023-08-19 | 2023-08-19 | 2023-08-19 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Slab
39297 | Tower A - Super Structure - Core Wall P1-P2 | Complete | RCC Works - Slab | 2023-08-19 | 2023-08-19 | Slab Casting | 100 | 100 |  | 2023-08-19 | 2023-08-19 | 2023-08-19 | 2023-08-19 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
40149 |  | Started |  | 2023-08-25 | 2024-03-18 | GF to P1_TA | 100 | 27 |  | 2023-08-25 | 2023-08-25 | 2025-10-11
40150 | Tower A - Super Structure - Finishes & MEP - GF to P1 | Complete | Partition Wall-Blockwork | 2023-08-25 | 2023-09-05 | De-shuttering & Area clearance | 100 | 100 |  | 2023-08-25 | 2023-08-25 | 2023-09-05 | 2023-09-05 | Tower A | Super Structure | GF
39310 | Tower A - Super Structure - Core Wall P3-P4 | Complete | RCC Works - Slab | 2023-08-26 | 2023-08-29 | Slab Reinforcement | 100 | 100 |  | 2023-08-26 | 2023-08-26 | 2023-08-29 | 2023-08-29 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Slab
44402 | NTA_Zone 2 - Sub Structure - B2 to B1 - Pour 5 | Complete | RCC Works - Slab | 2023-08-26 | 2023-09-19 | Slab_NTA | 100 | 100 |  | 2023-08-26 | 2023-08-26 | 2023-09-19 | 2023-09-19 | NTA_Zone 2 | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
44402 | NTA_Zone 2 - Sub Structure - B2 to B1 - Pour 5 | Complete | RCC Works - Slab | 2023-08-26 | 2023-09-19 | Slab_NTA | 100 | 100 |  | 2023-08-26 | 2023-08-26 | 2023-09-19 | 2023-09-19 | NTA_Zone 2 | Sub Structure | B2
39335 | Tower A - Super Structure - Core Wall ACS Assembly | Complete | ACS Assembly | 2023-08-29 | 2023-09-05 | ACS Component lifting and Installation | 100 | 100 |  | 2023-08-29 | 2023-08-29 | 2023-09-05 | 2023-09-05 | Tower A | Super Structure
39792 | Tower A - Super Structure - Core & Outer Slab GF-P1 | Complete | RCC Works - Slab | 2023-08-29 | 2023-08-29 | Slab Casting | 100 | 100 |  | 2023-08-29 | 2023-08-29 | 2023-08-29 | 2023-08-29 | Tower A | Super Structure | GF | RCC Sub Structure | RCC Works - Slab
39792 | Tower A - Super Structure - Core & Outer Slab GF-P1 | Complete | RCC Works - Slab | 2023-08-29 | 2023-08-29 | Slab Casting | 100 | 100 |  | 2023-08-29 | 2023-08-29 | 2023-08-29 | 2023-08-29 | Tower A | Super Structure | GF | RCC Super Structure | Core Wall RCC Works
39311 | Tower A - Super Structure - Core Wall P3-P4 | Complete | RCC Works - Slab | 2023-08-30 | 2023-08-30 | Slab Casting | 100 | 100 |  | 2023-08-30 | 2023-08-30 | 2023-08-30 | 2023-08-30 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Slab
39311 | Tower A - Super Structure - Core Wall P3-P4 | Complete | RCC Works - Slab | 2023-08-30 | 2023-08-30 | Slab Casting | 100 | 100 |  | 2023-08-30 | 2023-08-30 | 2023-08-30 | 2023-08-30 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39793 |  | Complete |  | 2023-08-30 | 2023-10-14 | P1-P2 (conv. Fwk.) | 100 | 100 |  | 2023-08-30 | 2023-08-30 | 2023-10-14 | 2023-10-14
39794 | Tower A - Super Structure - Core & Outer Slab P1-P2 | Complete | RCC Works - Vertical | 2023-08-30 | 2023-09-15 | Verticals Reinf | 100 | 100 |  | 2023-08-30 | 2023-08-30 | 2023-09-15 | 2023-09-15 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
47988 |  | Complete |  | 2023-08-30 | 2024-06-29 | Demolition | 100 | 100 |  | 2023-08-30 | 2023-08-30 | 2024-06-29 | 2024-06-29
47989 |  | Complete |  | 2023-08-30 | 2023-12-15 | Strengthening | 100 | 100 |  | 2023-08-30 | 2023-08-30 | 2023-12-15 | 2023-12-15
44673 | Tower A | Complete | Award of Packages | 2023-09-01 | 2023-12-22 | PHE & FF | 100 | 100 |  | 2023-09-01 | 2023-09-01 | 2023-12-22 | 2023-12-22 | Tower A | --
47981 |  | Complete |  | 2023-09-01 | 2024-02-05 | Alternate Parking | 100 | 100 |  | 2023-09-01 | 2023-09-01 | 2024-02-05 | 2024-02-05
39312 |  | Complete |  | 2023-09-06 | 2023-09-21 | Core Wall P4-P5-P6_Lift 1 | 100 | 100 |  | 2023-09-06 | 2023-09-06 | 2023-09-21 | 2023-09-21
39313 | Tower A - Super Structure - Core Wall P4-P5-P6_Lift 1 | Complete | Core Wall RCC Works | 2023-09-06 | 2023-09-06 | Scaffolding & platform | 100 | 100 |  | 2023-09-06 | 2023-09-06 | 2023-09-06 | 2023-09-06 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39314 | Tower A - Super Structure - Core Wall P4-P5-P6_Lift 1 | Complete | Core Wall RCC Works | 2023-09-07 | 2023-09-14 | Reinf & Guide shoes fixing | 100 | 100 |  | 2023-09-07 | 2023-09-07 | 2023-09-14 | 2023-09-14 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39795 | Tower A - Super Structure - Core & Outer Slab P1-P2 | Complete | RCC Works - Vertical | 2023-09-12 | 2023-10-06 | Vertical Shuttering | 100 | 100 |  | 2023-09-12 | 2023-09-12 | 2023-10-06 | 2023-10-06 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
39315 | Tower A - Super Structure - Core Wall P4-P5-P6_Lift 1 | Complete | Core Wall RCC Works | 2023-09-13 | 2023-09-19 | ACS Form Closing & Alignment | 100 | 100 |  | 2023-09-13 | 2023-09-13 | 2023-09-19 | 2023-09-19 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39316 | Tower A - Super Structure - Core Wall P4-P5-P6_Lift 1 | Complete | Core Wall RCC Works | 2023-09-20 | 2023-09-20 | Casting | 100 | 100 |  | 2023-09-20 | 2023-09-20 | 2023-09-20 | 2023-09-20 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
44444 |  | Complete |  | 2023-09-20 | 2023-11-01 | Pour 5 | 100 | 100 |  | 2023-09-20 | 2023-09-20 | 2023-11-01 | 2023-11-01
44445 | NTA_Zone 2 - Sub Structure - B1 to GF - Pour 5 | Complete | RCC Works - Vertical | 2023-09-20 | 2023-10-13 | Columns/ Walls_NTA | 100 | 100 |  | 2023-09-20 | 2023-09-20 | 2023-10-13 | 2023-10-13 | NTA_Zone 2 | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44445 | NTA_Zone 2 - Sub Structure - B1 to GF - Pour 5 | Complete | RCC Works - Vertical | 2023-09-20 | 2023-10-13 | Columns/ Walls_NTA | 100 | 100 |  | 2023-09-20 | 2023-09-20 | 2023-10-13 | 2023-10-13 | NTA_Zone 2 | Sub Structure | B1
39317 | Tower A - Super Structure - Core Wall P4-P5-P6_Lift 1 | Complete | Core Wall RCC Works | 2023-09-21 | 2023-09-21 | ACS Form Release & jump to next level | 100 | 100 |  | 2023-09-21 | 2023-09-21 | 2023-09-21 | 2023-09-21 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39318 |  | Complete |  | 2023-09-22 | 2023-10-07 | Core Wall P4-P5-P6_Lift 2 | 100 | 100 |  | 2023-09-22 | 2023-09-22 | 2023-10-07 | 2023-10-07
39319 | Tower A - Super Structure - Core Wall P4-P5-P6_Lift 2 | Complete | Core Wall RCC Works | 2023-09-22 | 2023-09-22 | Scaffolding & platform | 100 | 100 |  | 2023-09-22 | 2023-09-22 | 2023-09-22 | 2023-09-22 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39320 | Tower A - Super Structure - Core Wall P4-P5-P6_Lift 2 | Complete | Core Wall RCC Works | 2023-09-23 | 2023-09-30 | Reinf & Guide shoes fixing | 100 | 100 |  | 2023-09-23 | 2023-09-23 | 2023-09-30 | 2023-09-30 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39140 |  | Started |  | 2023-09-26 | 2026-03-03 | ENERGY CENTRE RELOCATION | 100 | 66 |  | 2023-09-26 | 2023-09-26 | 2026-09-23
39141 |  | Complete |  | 2023-09-26 | 2024-01-11 | Design Deliverables | 100 | 100 |  | 2023-09-26 | 2023-09-26 | 2024-01-11 | 2024-01-11
39142 |  | Complete |  | 2023-09-26 | 2023-12-06 | MEP Tender Package | 100 | 100 |  | 2023-09-26 | 2023-09-26 | 2023-12-06 | 2023-12-06
39143 |  | Complete |  | 2023-09-26 | 2023-12-06 | Civil & Architecture Tender Package | 100 | 100 |  | 2023-09-26 | 2023-09-26 | 2023-12-06 | 2023-12-06
47968 |  | Complete |  | 2023-09-26 | 2024-02-13 | Demolition | 100 | 100 |  | 2023-09-26 | 2023-09-26 | 2024-02-13 | 2024-02-13
47969 |  | Complete |  | 2023-09-26 | 2023-10-10 | Barrication | 100 | 100 |  | 2023-09-26 | 2023-09-26 | 2023-10-10 | 2023-10-10
39321 | Tower A - Super Structure - Core Wall P4-P5-P6_Lift 2 | Complete | Core Wall RCC Works | 2023-09-29 | 2023-10-05 | ACS Form Closing & Alignment | 100 | 100 |  | 2023-09-29 | 2023-09-29 | 2023-10-05 | 2023-10-05 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39797 | Tower A - Super Structure - Core & Outer Slab P1-P2 | Complete | RCC Works - Slab | 2023-10-04 | 2023-10-10 | Slab Shuttering | 100 | 100 |  | 2023-10-04 | 2023-10-04 | 2023-10-10 | 2023-10-10 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Slab
39797 | Tower A - Super Structure - Core & Outer Slab P1-P2 | Complete | RCC Works - Slab | 2023-10-04 | 2023-10-10 | Slab Shuttering | 100 | 100 |  | 2023-10-04 | 2023-10-04 | 2023-10-10 | 2023-10-10 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39322 | Tower A - Super Structure - Core Wall P4-P5-P6_Lift 2 | Complete | Core Wall RCC Works | 2023-10-06 | 2023-10-06 | Casting | 100 | 100 |  | 2023-10-06 | 2023-10-06 | 2023-10-06 | 2023-10-06 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39323 | Tower A - Super Structure - Core Wall P4-P5-P6_Lift 2 | Complete | Core Wall RCC Works | 2023-10-07 | 2023-10-07 | ACS Form Release & jump to next level | 100 | 100 |  | 2023-10-07 | 2023-10-07 | 2023-10-07 | 2023-10-07 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39796 | Tower A - Super Structure - Core & Outer Slab P1-P2 | Complete | RCC Works - Vertical | 2023-10-07 | 2023-10-07 | Verticals Casting | 100 | 100 |  | 2023-10-07 | 2023-10-07 | 2023-10-07 | 2023-10-07 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
39796 | Tower A - Super Structure - Core & Outer Slab P1-P2 | Complete | RCC Works - Vertical | 2023-10-07 | 2023-10-07 | Verticals Casting | 100 | 100 |  | 2023-10-07 | 2023-10-07 | 2023-10-07 | 2023-10-07 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39324 |  | Complete |  | 2023-10-09 | 2023-11-01 | Core Wall P4-P5-P6_Lift 3 | 100 | 100 |  | 2023-10-09 | 2023-10-09 | 2023-11-01 | 2023-11-01
39325 | Tower A - Super Structure - Core Wall P4-P5-P6_Lift 3 | Complete | Core Wall RCC Works | 2023-10-09 | 2023-10-09 | Scaffolding & platform | 100 | 100 |  | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-09 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
44446 | NTA_Zone 2 - Sub Structure - B1 to GF - Pour 5 | Complete | RCC Works - Slab | 2023-10-09 | 2023-11-01 | Slab_NTA | 100 | 100 |  | 2023-10-09 | 2023-10-09 | 2023-11-01 | 2023-11-01 | NTA_Zone 2 | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
44446 | NTA_Zone 2 - Sub Structure - B1 to GF - Pour 5 | Complete | RCC Works - Slab | 2023-10-09 | 2023-11-01 | Slab_NTA | 100 | 100 |  | 2023-10-09 | 2023-10-09 | 2023-11-01 | 2023-11-01 | NTA_Zone 2 | Sub Structure | B1
39326 | Tower A - Super Structure - Core Wall P4-P5-P6_Lift 3 | Complete | Core Wall RCC Works | 2023-10-10 | 2023-10-19 | Reinf & Guide shoes fixing | 100 | 100 |  | 2023-10-10 | 2023-10-10 | 2023-10-19 | 2023-10-19 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39798 | Tower A - Super Structure - Core & Outer Slab P1-P2 | Complete | RCC Works - Slab | 2023-10-11 | 2023-10-13 | Slab Reinf | 100 | 100 |  | 2023-10-11 | 2023-10-11 | 2023-10-13 | 2023-10-13 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Slab
39798 | Tower A - Super Structure - Core & Outer Slab P1-P2 | Complete | RCC Works - Slab | 2023-10-11 | 2023-10-13 | Slab Reinf | 100 | 100 |  | 2023-10-11 | 2023-10-11 | 2023-10-13 | 2023-10-13 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
47970 |  | Complete |  | 2023-10-11 | 2023-11-15 | Strengthening | 100 | 100 |  | 2023-10-11 | 2023-10-11 | 2023-11-15 | 2023-11-15
39799 | Tower A - Super Structure - Core & Outer Slab P1-P2 | Complete | RCC Works - Slab | 2023-10-14 | 2023-10-14 | Slab Casting | 100 | 100 |  | 2023-10-14 | 2023-10-14 | 2023-10-14 | 2023-10-14 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Slab
39799 | Tower A - Super Structure - Core & Outer Slab P1-P2 | Complete | RCC Works - Slab | 2023-10-14 | 2023-10-14 | Slab Casting | 100 | 100 |  | 2023-10-14 | 2023-10-14 | 2023-10-14 | 2023-10-14 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39800 |  | Complete |  | 2023-10-16 | 2023-10-30 | P2-P3 (conv. Fwk.) | 100 | 100 |  | 2023-10-16 | 2023-10-16 | 2023-10-30 | 2023-10-30
39801 | Tower A - Super Structure - Core & Outer Slab P2-P3 | Complete | RCC Works - Vertical | 2023-10-16 | 2023-10-20 | Verticals Reinf | 100 | 100 |  | 2023-10-16 | 2023-10-16 | 2023-10-20 | 2023-10-20 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
40153 |  | Started |  | 2023-10-16 | 2024-04-05 | P1 to P2_TA | 100 | 16 |  | 2023-10-16 | 2023-10-16 | 2025-10-30
40154 | Tower A - Super Structure - Finishes & MEP - P1 to P2 | Complete | Partition Wall-Blockwork | 2023-10-16 | 2023-10-20 | De-shuttering & Area clearance | 100 | 100 |  | 2023-10-16 | 2023-10-16 | 2023-10-20 | 2023-10-20 | Tower A | Super Structure
39802 | Tower A - Super Structure - Core & Outer Slab P2-P3 | Complete | RCC Works - Vertical | 2023-10-17 | 2023-10-26 | Vertical Shuttering | 100 | 100 |  | 2023-10-17 | 2023-10-17 | 2023-10-26 | 2023-10-26 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
39327 | Tower A - Super Structure - Core Wall P4-P5-P6_Lift 3 | Complete | Core Wall RCC Works | 2023-10-18 | 2023-10-25 | ACS Form Closing & Alignment | 100 | 100 |  | 2023-10-18 | 2023-10-18 | 2023-10-25 | 2023-10-25 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39330 | Tower A - Super Structure - Core Wall P4-P5-P6_Lift 3 | Complete | Core Wall RCC Works | 2023-10-21 | 2023-10-28 | Slab Shuttering | 100 | 100 |  | 2023-10-21 | 2023-10-21 | 2023-10-28 | 2023-10-28 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Slab
39330 | Tower A - Super Structure - Core Wall P4-P5-P6_Lift 3 | Complete | Core Wall RCC Works | 2023-10-21 | 2023-10-28 | Slab Shuttering | 100 | 100 |  | 2023-10-21 | 2023-10-21 | 2023-10-28 | 2023-10-28 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39804 | Tower A - Super Structure - Core & Outer Slab P2-P3 | Complete | RCC Works - Slab | 2023-10-21 | 2023-10-27 | Slab Shuttering | 100 | 100 |  | 2023-10-21 | 2023-10-21 | 2023-10-27 | 2023-10-27 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Slab
39804 | Tower A - Super Structure - Core & Outer Slab P2-P3 | Complete | RCC Works - Slab | 2023-10-21 | 2023-10-27 | Slab Shuttering | 100 | 100 |  | 2023-10-21 | 2023-10-21 | 2023-10-27 | 2023-10-27 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39328 | Tower A - Super Structure - Core Wall P4-P5-P6_Lift 3 | Complete | Core Wall RCC Works | 2023-10-26 | 2023-10-26 | Verticals Casting | 100 | 100 |  | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-26 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
39328 | Tower A - Super Structure - Core Wall P4-P5-P6_Lift 3 | Complete | Core Wall RCC Works | 2023-10-26 | 2023-10-26 | Verticals Casting | 100 | 100 |  | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-26 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39805 | Tower A - Super Structure - Core & Outer Slab P2-P3 | Complete | RCC Works - Slab | 2023-10-26 | 2023-10-28 | Slab Reinf | 100 | 100 |  | 2023-10-26 | 2023-10-26 | 2023-10-28 | 2023-10-28 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Slab
39805 | Tower A - Super Structure - Core & Outer Slab P2-P3 | Complete | RCC Works - Slab | 2023-10-26 | 2023-10-28 | Slab Reinf | 100 | 100 |  | 2023-10-26 | 2023-10-26 | 2023-10-28 | 2023-10-28 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39329 | Tower A - Super Structure - Core Wall P4-P5-P6_Lift 3 | Complete | Core Wall RCC Works | 2023-10-27 | 2023-10-27 | ACS Form Release & jump to next level | 100 | 100 |  | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-10-27 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39331 | Tower A - Super Structure - Core Wall P4-P5-P6_Lift 3 | Complete | Core Wall RCC Works | 2023-10-27 | 2023-10-31 | Slab Reinf | 100 | 100 |  | 2023-10-27 | 2023-10-27 | 2023-10-31 | 2023-10-31 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Slab
39331 | Tower A - Super Structure - Core Wall P4-P5-P6_Lift 3 | Complete | Core Wall RCC Works | 2023-10-27 | 2023-10-31 | Slab Reinf | 100 | 100 |  | 2023-10-27 | 2023-10-27 | 2023-10-31 | 2023-10-31 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39803 | Tower A - Super Structure - Core & Outer Slab P2-P3 | Complete | RCC Works - Vertical | 2023-10-27 | 2023-10-27 | Verticals Casting | 100 | 100 |  | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-10-27 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
39803 | Tower A - Super Structure - Core & Outer Slab P2-P3 | Complete | RCC Works - Vertical | 2023-10-27 | 2023-10-27 | Verticals Casting | 100 | 100 |  | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-10-27 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39807 |  | Complete |  | 2023-10-27 | 2023-12-01 | P3-P4 (conv. Fwk.) | 100 | 100 |  | 2023-10-27 | 2023-10-27 | 2023-12-01 | 2023-12-01
39808 | Tower A - Super Structure - Core & Outer Slab P3-P4 | Complete | RCC Works - Vertical | 2023-10-27 | 2023-11-03 | Verticals Reinf | 100 | 100 |  | 2023-10-27 | 2023-10-27 | 2023-11-03 | 2023-11-03 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
39806 | Tower A - Super Structure - Core & Outer Slab P2-P3 | Complete | RCC Works - Slab | 2023-10-30 | 2023-10-30 | Slab Casting | 100 | 100 |  | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-10-30 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Slab
39806 | Tower A - Super Structure - Core & Outer Slab P2-P3 | Complete | RCC Works - Slab | 2023-10-30 | 2023-10-30 | Slab Casting | 100 | 100 |  | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-10-30 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39809 | Tower A - Super Structure - Core & Outer Slab P3-P4 | Complete | RCC Works - Vertical | 2023-10-31 | 2023-11-08 | Vertical Shuttering | 100 | 100 |  | 2023-10-31 | 2023-10-31 | 2023-11-08 | 2023-11-08 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
40157 |  | Started |  | 2023-10-31 | 2024-04-23 | P2 to P3_TA | 100 | 16 |  | 2023-10-31 | 2023-10-31 | 2025-11-17
40158 | Tower A - Super Structure - Finishes & MEP - P2 to P3 | Complete | Partition Wall-Blockwork | 2023-10-31 | 2023-11-04 | De-shuttering & Area clearance | 100 | 100 |  | 2023-10-31 | 2023-10-31 | 2023-11-04 | 2023-11-04 | Tower A | Super Structure
39332 | Tower A - Super Structure - Core Wall P4-P5-P6_Lift 3 | Complete | Core Wall RCC Works | 2023-11-01 | 2023-11-01 | Slab Casting | 100 | 100 |  | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Slab
39332 | Tower A - Super Structure - Core Wall P4-P5-P6_Lift 3 | Complete | Core Wall RCC Works | 2023-11-01 | 2023-11-01 | Slab Casting | 100 | 100 |  | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39336 |  | Complete |  | 2023-11-01 | 2025-02-24 | Core Wall_Low Rise | 100 | 100 |  | 2023-11-01 | 2023-11-01 | 2025-02-24 | 2025-02-24
39337 |  | Complete |  | 2023-11-01 | 2023-12-01 | Core Wall P6-L7 | 100 | 100 |  | 2023-11-01 | 2023-11-01 | 2023-12-01 | 2023-12-01
39338 | Tower A - Super Structure - Core Wall Low Rise P6-L7 | Complete | Core Wall RCC Works | 2023-11-01 | 2023-11-01 | Scaffolding & platform | 100 | 100 |  | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39339 | Tower A - Super Structure - Core Wall Low Rise P6-L7 | Complete | Core Wall RCC Works | 2023-11-02 | 2023-11-08 | Reinf & Guide shoes fixing | 100 | 100 |  | 2023-11-02 | 2023-11-02 | 2023-11-08 | 2023-11-08 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
44407 |  | Complete |  | 2023-11-02 | 2023-11-29 | Plinth Checking (30 calendar days) | 100 | 100 |  | 2023-11-02 | 2023-11-02 | 2023-11-29 | 2023-11-29
44407 |  | Complete |  | 2023-11-02 | 2023-11-29 | Plinth Checking (30 calendar days) | 100 | 100 |  | 2023-11-02 | 2023-11-02 | 2023-11-29 | 2023-11-29
39811 | Tower A - Super Structure - Core & Outer Slab P3-P4 | Complete | RCC Works - Slab | 2023-11-06 | 2023-11-11 | Slab Shuttering | 100 | 100 |  | 2023-11-06 | 2023-11-06 | 2023-11-11 | 2023-11-11 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Slab
39811 | Tower A - Super Structure - Core & Outer Slab P3-P4 | Complete | RCC Works - Slab | 2023-11-06 | 2023-11-11 | Slab Shuttering | 100 | 100 |  | 2023-11-06 | 2023-11-06 | 2023-11-11 | 2023-11-11 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39340 | Tower A - Super Structure - Core Wall Low Rise P6-L7 | Complete | Core Wall RCC Works | 2023-11-07 | 2023-11-11 | ACS Form Closing & Alignment | 100 | 100 |  | 2023-11-07 | 2023-11-07 | 2023-11-11 | 2023-11-11 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39138 |  | Complete |  | 2023-11-08 | 2023-11-28 | Events | 100 | 100 |  | 2023-11-08 | 2023-11-08 | 2023-11-28 | 2023-11-28
39139 |  | Complete |  | 2023-11-08 | 2023-11-28 | BMC Stop Work Notice to Batching Plant (Air Pollution) | 100 | 100 |  | 2023-11-08 | 2023-11-08 | 2023-11-28 | 2023-11-28
39810 | Tower A - Super Structure - Core & Outer Slab P3-P4 | Complete | RCC Works - Vertical | 2023-11-09 | 2023-11-09 | Verticals Casting | 100 | 100 |  | 2023-11-09 | 2023-11-09 | 2023-11-09 | 2023-11-09 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
39810 | Tower A - Super Structure - Core & Outer Slab P3-P4 | Complete | RCC Works - Vertical | 2023-11-09 | 2023-11-09 | Verticals Casting | 100 | 100 |  | 2023-11-09 | 2023-11-09 | 2023-11-09 | 2023-11-09 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39812 | Tower A - Super Structure - Core & Outer Slab P3-P4 | Complete | RCC Works - Slab | 2023-11-10 | 2023-11-14 | Slab Reinf | 100 | 100 |  | 2023-11-10 | 2023-11-10 | 2023-11-14 | 2023-11-14 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Slab
39812 | Tower A - Super Structure - Core & Outer Slab P3-P4 | Complete | RCC Works - Slab | 2023-11-10 | 2023-11-14 | Slab Reinf | 100 | 100 |  | 2023-11-10 | 2023-11-10 | 2023-11-14 | 2023-11-14 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
47971 |  | Complete |  | 2023-11-16 | 2024-02-13 | Demolition | 100 | 100 |  | 2023-11-16 | 2023-11-16 | 2024-02-13 | 2024-02-13
39341 | Tower A - Super Structure - Core Wall Low Rise P6-L7 | Complete | Core Wall RCC Works | 2023-11-30 | 2023-11-30 | Casting | 100 | 100 |  | 2023-11-30 | 2023-11-30 | 2023-11-30 | 2023-11-30 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
44450 |  | Started |  | 2023-11-30 | 2024-06-26 | Super-Structure_NTA Zone 2 | 100 | 91 |  | 2023-11-30 | 2023-11-30 | 2025-11-05
44451 |  | Complete |  | 2023-11-30 | 2024-01-10 | GF to P1 | 100 | 100 |  | 2023-11-30 | 2023-11-30 | 2024-01-10 | 2024-01-10
44451 |  | Complete |  | 2023-11-30 | 2024-01-10 | GF to P1 | 100 | 100 |  | 2023-11-30 | 2023-11-30 | 2024-01-10 | 2024-01-10
44451 |  | Complete |  | 2023-11-30 | 2024-01-10 | GF to P1 | 100 | 100 |  | 2023-11-30 | 2023-11-30 | 2024-01-10 | 2024-01-10
44452 |  | Complete |  | 2023-11-30 | 2024-01-10 | Pour 1 (Ramp) | 100 | 100 |  | 2023-11-30 | 2023-11-30 | 2024-01-10 | 2024-01-10
44453 | NTA_Zone 2 - Super Structure - GF to P1 - Pour 1 | Complete | RCC Works - Vertical | 2023-11-30 | 2023-12-16 | Columns/ Walls_NTA | 100 | 100 |  | 2023-11-30 | 2023-11-30 | 2023-12-16 | 2023-12-16 | NTA_Zone 2 | Super Structure | GF | RCC Sub Structure | RCC Works - Vertical
44453 | NTA_Zone 2 - Super Structure - GF to P1 - Pour 1 | Complete | RCC Works - Vertical | 2023-11-30 | 2023-12-16 | Columns/ Walls_NTA | 100 | 100 |  | 2023-11-30 | 2023-11-30 | 2023-12-16 | 2023-12-16 | NTA_Zone 2 | Super Structure | GF
44454 | NTA_Zone 2 - Super Structure - GF to P1 - Pour 1 | Complete | Staircase & Ramp RCC Works | 2023-11-30 | 2023-12-22 | Staircase & Ramp_NTA | 100 | 100 |  | 2023-11-30 | 2023-11-30 | 2023-12-22 | 2023-12-22 | NTA_Zone 2 | Super Structure | GF | RCC Sub Structure | Staircase & Ramp RCC Works
44456 |  | Complete |  | 2023-11-30 | 2023-12-29 | Pour 2 (btwn TA & NTA Ramp) | 100 | 100 |  | 2023-11-30 | 2023-11-30 | 2023-12-29 | 2023-12-29
44457 | NTA_Zone 2 - Super Structure - GF to P1 - Pour 2 | Complete | RCC Works - Vertical | 2023-11-30 | 2023-12-16 | Columns/ Walls_NTA | 100 | 100 |  | 2023-11-30 | 2023-11-30 | 2023-12-16 | 2023-12-16 | NTA_Zone 2 | Super Structure | GF | RCC Sub Structure | RCC Works - Vertical
44457 | NTA_Zone 2 - Super Structure - GF to P1 - Pour 2 | Complete | RCC Works - Vertical | 2023-11-30 | 2023-12-16 | Columns/ Walls_NTA | 100 | 100 |  | 2023-11-30 | 2023-11-30 | 2023-12-16 | 2023-12-16 | NTA_Zone 2 | Super Structure | GF
44459 |  | Complete |  | 2023-11-30 | 2024-01-04 | Pour 3 (Grid PA-A to PA-D) | 100 | 100 |  | 2023-11-30 | 2023-11-30 | 2024-01-04 | 2024-01-04
44460 | NTA_Zone 2 - Super Structure - GF to P1 - Pour 3 | Complete | RCC Works - Vertical | 2023-11-30 | 2023-12-16 | Columns/ Walls_NTA | 100 | 100 |  | 2023-11-30 | 2023-11-30 | 2023-12-16 | 2023-12-16 | NTA_Zone 2 | Super Structure | GF | RCC Sub Structure | RCC Works - Vertical
44460 | NTA_Zone 2 - Super Structure - GF to P1 - Pour 3 | Complete | RCC Works - Vertical | 2023-11-30 | 2023-12-16 | Columns/ Walls_NTA | 100 | 100 |  | 2023-11-30 | 2023-11-30 | 2023-12-16 | 2023-12-16 | NTA_Zone 2 | Super Structure | GF
44461 | NTA_Zone 2 - Super Structure - GF to P1 - Pour 3 | Complete | Staircase & Ramp RCC Works | 2023-11-30 | 2023-12-22 | Staircase_NTA | 100 | 100 |  | 2023-11-30 | 2023-11-30 | 2023-12-22 | 2023-12-22 | NTA_Zone 2 | Super Structure | GF | RCC Sub Structure | Staircase & Ramp RCC Works
44461 | NTA_Zone 2 - Super Structure - GF to P1 - Pour 3 | Complete | Staircase & Ramp RCC Works | 2023-11-30 | 2023-12-22 | Staircase_NTA | 100 | 100 |  | 2023-11-30 | 2023-11-30 | 2023-12-22 | 2023-12-22 | NTA_Zone 2 | Super Structure | GF
39342 | Tower A - Super Structure - Core Wall Low Rise P6-L7 | Complete | Core Wall RCC Works | 2023-12-01 | 2023-12-01 | ACS Form Release & jump to next level | 100 | 100 |  | 2023-12-01 | 2023-12-01 | 2023-12-01 | 2023-12-01 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
39813 | Tower A - Super Structure - Core & Outer Slab P3-P4 | Complete | RCC Works - Slab | 2023-12-01 | 2023-12-01 | Slab Casting | 100 | 100 |  | 2023-12-01 | 2023-12-01 | 2023-12-01 | 2023-12-01 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Slab
39813 | Tower A - Super Structure - Core & Outer Slab P3-P4 | Complete | RCC Works - Slab | 2023-12-01 | 2023-12-01 | Slab Casting | 100 | 100 |  | 2023-12-01 | 2023-12-01 | 2023-12-01 | 2023-12-01 | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
40552 |  | Started |  | 2023-12-01 | 2026-05-22 | MEP Shaft Masonry | 100 | 75 |  | 2023-12-01 | 2023-12-01 | 2026-06-27
40553 | Tower A - Super Structure - Finishes & MEP | Complete | MEP Shaft Masonry | 2023-12-01 | 2023-12-01 | B3-GF-L7 | 100 | 100 |  | 2023-12-01 | 2023-12-01 | 2023-12-01 | 2023-12-01 | Tower A | Super Structure
39343 |  | Complete |  | 2023-12-02 | 2023-12-14 | Core Wall L7-8 | 100 | 100 |  | 2023-12-02 | 2023-12-02 | 2023-12-14 | 2023-12-14
39344 | Tower A - Super Structure - Core Wall Low Rise L7-8 | Complete | Core Wall RCC Works | 2023-12-02 | 2023-12-02 | Scaffolding & platform | 100 | 100 |  | 2023-12-02 | 2023-12-02 | 2023-12-02 | 2023-12-02 | Tower A | Super Structure | L7 | RCC Super Structure | Core Wall RCC Works
39814 |  | Complete |  | 2023-12-02 | 2023-12-26 | P4-P5 (conv. Fwk.) | 100 | 100 |  | 2023-12-02 | 2023-12-02 | 2023-12-26 | 2023-12-26
39815 | Tower A - Super Structure - Core & Outer Slab P4-P5 | Complete | RCC Works - Vertical | 2023-12-02 | 2023-12-09 | Outer Columns_TA | 100 | 100 |  | 2023-12-02 | 2023-12-02 | 2023-12-09 | 2023-12-09 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
40161 |  | Complete |  | 2023-12-02 | 2024-05-11 | P3 to P4_TA | 100 | 100 |  | 2023-12-02 | 2023-12-02 | 2024-05-11 | 2024-05-11
40162 | Tower A - Super Structure - Finishes & MEP - P3 to P4 | Complete | Partition Wall-Blockwork | 2023-12-02 | 2023-12-07 | De-shuttering & Area clearance | 100 | 100 |  | 2023-12-02 | 2023-12-02 | 2023-12-07 | 2023-12-07 | Tower A | Super Structure
39345 | Tower A - Super Structure - Core Wall Low Rise L7-8 | Complete | Core Wall RCC Works | 2023-12-04 | 2023-12-09 | Reinf & Guide shoes fixing | 100 | 100 |  | 2023-12-04 | 2023-12-04 | 2023-12-09 | 2023-12-09 | Tower A | Super Structure | L7 | RCC Super Structure | Core Wall RCC Works
44458 | NTA_Zone 2 - Super Structure - GF to P1 - Pour 2 | Complete | RCC Works - Slab | 2023-12-06 | 2023-12-29 | Slab_NTA | 100 | 100 |  | 2023-12-06 | 2023-12-06 | 2023-12-29 | 2023-12-29 | NTA_Zone 2 | Super Structure | GF | RCC Sub Structure | RCC Works - Slab
44458 | NTA_Zone 2 - Super Structure - GF to P1 - Pour 2 | Complete | RCC Works - Slab | 2023-12-06 | 2023-12-29 | Slab_NTA | 100 | 100 |  | 2023-12-06 | 2023-12-06 | 2023-12-29 | 2023-12-29 | NTA_Zone 2 | Super Structure | GF
39144 |  | Complete |  | 2023-12-07 | 2024-01-11 | Electrical GFC | 100 | 100 |  | 2023-12-07 | 2023-12-07 | 2024-01-11 | 2024-01-11
39145 |  | Complete |  | 2023-12-07 | 2024-01-11 | HVAC GFC | 100 | 100 |  | 2023-12-07 | 2023-12-07 | 2024-01-11 | 2024-01-11
39146 |  | Complete |  | 2023-12-07 | 2024-01-11 | Civil GFC | 100 | 100 |  | 2023-12-07 | 2023-12-07 | 2024-01-11 | 2024-01-11
39147 |  | Complete |  | 2023-12-07 | 2024-06-10 | Vendor Finalisation | 100 | 100 |  | 2023-12-07 | 2023-12-07 | 2024-06-10 | 2024-06-10
39148 |  | Complete |  | 2023-12-07 | 2024-02-16 | Civil Works Vendor | 100 | 100 |  | 2023-12-07 | 2023-12-07 | 2024-02-16 | 2024-02-16
39149 |  | Complete |  | 2023-12-07 | 2024-05-09 | MEP Vendor for Energy Centre Relocation | 100 | 100 |  | 2023-12-07 | 2023-12-07 | 2024-05-09 | 2024-05-09
39150 |  | Complete |  | 2023-12-07 | 2024-06-10 | Vendor for Stack Parking | 100 | 100 |  | 2023-12-07 | 2023-12-07 | 2024-06-10 | 2024-06-10
39346 | Tower A - Super Structure - Core Wall Low Rise L7-8 | Complete | Core Wall RCC Works | 2023-12-08 | 2023-12-12 | ACS Form Closing & Alignment | 100 | 100 |  | 2023-12-08 | 2023-12-08 | 2023-12-12 | 2023-12-12 | Tower A | Super Structure | L7 | RCC Super Structure | Core Wall RCC Works
39347 | Tower A - Super Structure - Core Wall Low Rise L7-8 | Complete | Core Wall RCC Works | 2023-12-13 | 2023-12-13 | Casting | 100 | 100 |  | 2023-12-13 | 2023-12-13 | 2023-12-13 | 2023-12-13 | Tower A | Super Structure | L7 | RCC Super Structure | Core Wall RCC Works
39348 | Tower A - Super Structure - Core Wall Low Rise L7-8 | Complete | Core Wall RCC Works | 2023-12-14 | 2023-12-14 | ACS Form Release & jump to next level | 100 | 100 |  | 2023-12-14 | 2023-12-14 | 2023-12-14 | 2023-12-14 | Tower A | Super Structure | L7 | RCC Super Structure | Core Wall RCC Works
39816 | Tower A - Super Structure - Core & Outer Slab P4-P5 | Complete | RCC Works - Slab | 2023-12-14 | 2023-12-26 | Outer Slab_TA | 100 | 100 |  | 2023-12-14 | 2023-12-14 | 2023-12-26 | 2023-12-26 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Slab
39349 |  | Complete |  | 2023-12-15 | 2023-12-22 | Core Wall L8-9 | 100 | 100 |  | 2023-12-15 | 2023-12-15 | 2023-12-22 | 2023-12-22
39350 | Tower A - Super Structure - Core Wall Low Rise L8-9 | Complete | Core Wall RCC Works | 2023-12-15 | 2023-12-15 | Scaffolding & platform | 100 | 100 |  | 2023-12-15 | 2023-12-15 | 2023-12-15 | 2023-12-15 | Tower A | Super Structure | L8 | RCC Super Structure | Core Wall RCC Works
39351 | Tower A - Super Structure - Core Wall Low Rise L8-9 | Complete | Core Wall RCC Works | 2023-12-16 | 2023-12-19 | Reinf & Guide shoes fixing | 100 | 100 |  | 2023-12-16 | 2023-12-16 | 2023-12-19 | 2023-12-19 | Tower A | Super Structure | L8 | RCC Super Structure | Core Wall RCC Works
47990 |  | Complete |  | 2023-12-16 | 2024-02-02 | Barrication | 100 | 100 |  | 2023-12-16 | 2023-12-16 | 2024-02-02 | 2024-02-02
39352 | Tower A - Super Structure - Core Wall Low Rise L8-9 | Complete | Core Wall RCC Works | 2023-12-18 | 2023-12-20 | ACS Form Closing & Alignment | 100 | 100 |  | 2023-12-18 | 2023-12-18 | 2023-12-20 | 2023-12-20 | Tower A | Super Structure | L8 | RCC Super Structure | Core Wall RCC Works
44455 | NTA_Zone 2 - Super Structure - GF to P1 - Pour 1 | Complete | RCC Works - Slab | 2023-12-18 | 2024-01-10 | Slab_NTA | 100 | 100 |  | 2023-12-18 | 2023-12-18 | 2024-01-10 | 2024-01-10 | NTA_Zone 2 | Super Structure | GF | RCC Sub Structure | RCC Works - Slab
44455 | NTA_Zone 2 - Super Structure - GF to P1 - Pour 1 | Complete | RCC Works - Slab | 2023-12-18 | 2024-01-10 | Slab_NTA | 100 | 100 |  | 2023-12-18 | 2023-12-18 | 2024-01-10 | 2024-01-10 | NTA_Zone 2 | Super Structure | GF
44462 | NTA_Zone 2 - Super Structure - GF to P1 - Pour 3 | Complete | RCC Works - Slab | 2023-12-18 | 2024-01-04 | Slab_NTA (tie-beams) | 100 | 100 |  | 2023-12-18 | 2023-12-18 | 2024-01-04 | 2024-01-04 | NTA_Zone 2 | Super Structure | GF | RCC Sub Structure | RCC Works - Slab
44462 | NTA_Zone 2 - Super Structure - GF to P1 - Pour 3 | Complete | RCC Works - Slab | 2023-12-18 | 2024-01-04 | Slab_NTA (tie-beams) | 100 | 100 |  | 2023-12-18 | 2023-12-18 | 2024-01-04 | 2024-01-04 | NTA_Zone 2 | Super Structure | GF
44463 |  | Complete |  | 2023-12-18 | 2024-01-10 | Pour 4 (Grid PA-4 to PA-8) | 100 | 100 |  | 2023-12-18 | 2023-12-18 | 2024-01-10 | 2024-01-10
44464 | NTA_Zone 2 - Super Structure - GF to P1 - Pour 4 | Complete | RCC Works - Vertical | 2023-12-18 | 2024-01-04 | Columns/ Walls_NTA | 100 | 100 |  | 2023-12-18 | 2023-12-18 | 2024-01-04 | 2024-01-04 | NTA_Zone 2 | Super Structure | GF | RCC Sub Structure | RCC Works - Vertical
44464 | NTA_Zone 2 - Super Structure - GF to P1 - Pour 4 | Complete | RCC Works - Vertical | 2023-12-18 | 2024-01-04 | Columns/ Walls_NTA | 100 | 100 |  | 2023-12-18 | 2023-12-18 | 2024-01-04 | 2024-01-04 | NTA_Zone 2 | Super Structure | GF
44674 | Tower A | Complete | Award of Packages | 2023-12-19 | 2024-06-18 | Electrical | 100 | 100 |  | 2023-12-19 | 2023-12-19 | 2024-06-18 | 2024-06-18 | Tower A | --
39131 |  | Complete |  | 2023-12-20 | 2024-01-25 | MEP Package vendor | 100 | 100 |  | 2023-12-20 | 2023-12-20 | 2024-01-25 | 2024-01-25
44676 | Tower A | Complete | Award of Packages | 2023-12-20 | 2024-08-03 | Elevator | 100 | 100 |  | 2023-12-20 | 2023-12-20 | 2024-08-03 | 2024-08-03 | Tower A | --
44676 | Tower A | Complete | Award of Packages | 2023-12-20 | 2024-08-03 | Elevator | 100 | 100 |  | 2023-12-20 | 2023-12-20 | 2024-08-03 | 2024-08-03 | Tower A | --
39353 | Tower A - Super Structure - Core Wall Low Rise L8-9 | Complete | Core Wall RCC Works | 2023-12-21 | 2023-12-21 | Casting | 100 | 100 |  | 2023-12-21 | 2023-12-21 | 2023-12-21 | 2023-12-21 | Tower A | Super Structure | L8 | RCC Super Structure | Core Wall RCC Works
39354 | Tower A - Super Structure - Core Wall Low Rise L8-9 | Complete | Core Wall RCC Works | 2023-12-22 | 2023-12-22 | ACS Form Release & jump to next level | 100 | 100 |  | 2023-12-22 | 2023-12-22 | 2023-12-22 | 2023-12-22 | Tower A | Super Structure | L8 | RCC Super Structure | Core Wall RCC Works
44695 |  | Complete |  | 2023-12-22 | 2024-01-20 | Excavation up to -4.00 m | 100 | 100 |  | 2023-12-22 | 2023-12-22 | 2024-01-20 | 2024-01-20
44696 | Tower B | Complete | Excavation upto -4 Mtr | 2023-12-22 | 2024-01-20 | Zone 1 North (outside NTA Zone 2) | 100 | 100 |  | 2023-12-22 | 2023-12-22 | 2024-01-20 | 2024-01-20 | Tower B | --
44696 | Tower B | Complete | Excavation upto -4 Mtr | 2023-12-22 | 2024-01-20 | Zone 1 North (outside NTA Zone 2) | 100 | 100 |  | 2023-12-22 | 2023-12-22 | 2024-01-20 | 2024-01-20 | Tower B | --
44696 | Tower B | Complete | Excavation upto -4 Mtr | 2023-12-22 | 2024-01-20 | Zone 1 North (outside NTA Zone 2) | 100 | 100 |  | 2023-12-22 | 2023-12-22 | 2024-01-20 | 2024-01-20 | Tower B | --
44696 | Tower B | Complete | Excavation upto -4 Mtr | 2023-12-22 | 2024-01-20 | Zone 1 North (outside NTA Zone 2) | 100 | 100 |  | 2023-12-22 | 2023-12-22 | 2024-01-20 | 2024-01-20 | Tower B | --
39355 |  | Complete |  | 2023-12-23 | 2024-01-01 | Core Wall L9-10 | 100 | 100 |  | 2023-12-23 | 2023-12-23 | 2024-01-01 | 2024-01-01
39356 | Tower A - Super Structure - Core Wall Low Rise L9-10 | Complete | Core Wall RCC Works | 2023-12-23 | 2023-12-23 | Scaffolding & platform | 100 | 100 |  | 2023-12-23 | 2023-12-23 | 2023-12-23 | 2023-12-23 | Tower A | Super Structure | L9 | RCC Super Structure | Core Wall RCC Works
44465 | NTA_Zone 2 - Super Structure - GF to P1 - Pour 4 | Complete | RCC Works - Slab | 2023-12-23 | 2024-01-10 | Slab_NTA (tie-beams) | 100 | 100 |  | 2023-12-23 | 2023-12-23 | 2024-01-10 | 2024-01-10 | NTA_Zone 2 | Super Structure | GF | RCC Sub Structure | RCC Works - Slab
44465 | NTA_Zone 2 - Super Structure - GF to P1 - Pour 4 | Complete | RCC Works - Slab | 2023-12-23 | 2024-01-10 | Slab_NTA (tie-beams) | 100 | 100 |  | 2023-12-23 | 2023-12-23 | 2024-01-10 | 2024-01-10 | NTA_Zone 2 | Super Structure | GF
39357 | Tower A - Super Structure - Core Wall Low Rise L9-10 | Complete | Core Wall RCC Works | 2023-12-26 | 2023-12-28 | Reinf & Guide shoes fixing | 100 | 100 |  | 2023-12-26 | 2023-12-26 | 2023-12-28 | 2023-12-28 | Tower A | Super Structure | L9 | RCC Super Structure | Core Wall RCC Works
39358 | Tower A - Super Structure - Core Wall Low Rise L9-10 | Complete | Core Wall RCC Works | 2023-12-27 | 2023-12-29 | ACS Form Closing & Alignment | 100 | 100 |  | 2023-12-27 | 2023-12-27 | 2023-12-29 | 2023-12-29 | Tower A | Super Structure | L9 | RCC Super Structure | Core Wall RCC Works
39817 |  | Complete |  | 2023-12-27 | 2024-01-20 | P5-P6 (conv. Fwk.) | 100 | 100 |  | 2023-12-27 | 2023-12-27 | 2024-01-20 | 2024-01-20
39818 | Tower A - Super Structure - Core & Outer Slab P5-P6 | Complete | RCC Works - Vertical | 2023-12-27 | 2024-01-11 | Outer Columns_TA | 100 | 100 |  | 2023-12-27 | 2023-12-27 | 2024-01-11 | 2024-01-11 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
40138 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 | Complete | Partition Wall-Blockwork | 2023-12-27 | 2024-04-11 | Counter-weight Plum Concrete | 100 | 100 |  | 2023-12-27 | 2023-12-27 | 2024-04-11 | 2024-04-11 | Tower A | Sub Structure | B3
40147 | Tower A - Sub Structure - Finishes & MEP - B1 to GF | Complete | Partition Wall-Blockwork | 2023-12-27 | 2024-01-12 | Partition Walls | 100 | 100 |  | 2023-12-27 | 2023-12-27 | 2024-01-12 | 2024-01-12 | Tower A | Sub Structure | B1
40165 |  | Started |  | 2023-12-27 | 2024-05-29 | P4 to P5_TA | 100 | 49 |  | 2023-12-27 | 2023-12-27 | 2025-10-03
40166 | Tower A - Super Structure - Finishes & MEP - P4 to P5 | Complete | Partition Wall-Blockwork | 2023-12-27 | 2024-01-01 | De-shuttering & Area clearance | 100 | 100 |  | 2023-12-27 | 2023-12-27 | 2024-01-01 | 2024-01-01 | Tower A | Super Structure
39359 | Tower A - Super Structure - Core Wall Low Rise L9-10 | Complete | Core Wall RCC Works | 2023-12-30 | 2023-12-30 | Casting | 100 | 100 |  | 2023-12-30 | 2023-12-30 | 2023-12-30 | 2023-12-30 | Tower A | Super Structure | L9 | RCC Super Structure | Core Wall RCC Works
44466 |  | Complete |  | 2023-12-30 | 2024-02-21 | P1 to P2 | 100 | 100 |  | 2023-12-30 | 2023-12-30 | 2024-02-21 | 2024-02-21
44466 |  | Complete |  | 2023-12-30 | 2024-02-21 | P1 to P2 | 100 | 100 |  | 2023-12-30 | 2023-12-30 | 2024-02-21 | 2024-02-21
44466 |  | Complete |  | 2023-12-30 | 2024-02-21 | P1 to P2 | 100 | 100 |  | 2023-12-30 | 2023-12-30 | 2024-02-21 | 2024-02-21
44471 |  | Complete |  | 2023-12-30 | 2024-01-29 | Pour 2 (btwn TA & NTA Ramp) | 100 | 100 |  | 2023-12-30 | 2023-12-30 | 2024-01-29 | 2024-01-29
44472 | NTA_Zone 2 - Super Structure - P1 to P2 - Pour 2 | Complete | RCC Works - Vertical | 2023-12-30 | 2024-01-16 | Columns/ Walls_NTA | 100 | 100 |  | 2023-12-30 | 2023-12-30 | 2024-01-16 | 2024-01-16 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
44472 | NTA_Zone 2 - Super Structure - P1 to P2 - Pour 2 | Complete | RCC Works - Vertical | 2023-12-30 | 2024-01-16 | Columns/ Walls_NTA | 100 | 100 |  | 2023-12-30 | 2023-12-30 | 2024-01-16 | 2024-01-16 | NTA_Zone 2 | Super Structure
39360 | Tower A - Super Structure - Core Wall Low Rise L9-10 | Complete | Core Wall RCC Works | 2024-01-01 | 2024-01-01 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-01-01 | 2024-01-01 | 2024-01-01 | 2024-01-01 | Tower A | Super Structure | L9 | RCC Super Structure | Core Wall RCC Works
39361 |  | Complete |  | 2024-01-02 | 2024-01-15 | Core Wall L10-11 | 100 | 100 |  | 2024-01-02 | 2024-01-02 | 2024-01-15 | 2024-01-15
39362 | Tower A - Super Structure - Core Wall Low Rise L10-11 | Complete | Core Wall RCC Works | 2024-01-02 | 2024-01-02 | Scaffolding & platform | 100 | 100 |  | 2024-01-02 | 2024-01-02 | 2024-01-02 | 2024-01-02 | Tower A | Super Structure | L10 | RCC Super Structure | Core Wall RCC Works
39363 | Tower A - Super Structure - Core Wall Low Rise L10-11 | Complete | Core Wall RCC Works | 2024-01-03 | 2024-01-09 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-01-03 | 2024-01-03 | 2024-01-09 | 2024-01-09 | Tower A | Super Structure | L10 | RCC Super Structure | Core Wall RCC Works
44473 | NTA_Zone 2 - Super Structure - P1 to P2 - Pour 2 | Complete | RCC Works - Slab | 2024-01-05 | 2024-01-29 | Slab_NTA | 100 | 100 |  | 2024-01-05 | 2024-01-05 | 2024-01-29 | 2024-01-29 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Slab
44473 | NTA_Zone 2 - Super Structure - P1 to P2 - Pour 2 | Complete | RCC Works - Slab | 2024-01-05 | 2024-01-29 | Slab_NTA | 100 | 100 |  | 2024-01-05 | 2024-01-05 | 2024-01-29 | 2024-01-29 | NTA_Zone 2 | Super Structure
44474 |  | Complete |  | 2024-01-05 | 2024-02-15 | Pour 3 (Grid PA-A to PA-D) | 100 | 100 |  | 2024-01-05 | 2024-01-05 | 2024-02-15 | 2024-02-15
44475 | NTA_Zone 2 - Super Structure - P1 to P2 - Pour 3 | Complete | RCC Works - Vertical | 2024-01-05 | 2024-01-22 | Columns/ Walls_NTA | 100 | 100 |  | 2024-01-05 | 2024-01-05 | 2024-01-22 | 2024-01-22 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
44475 | NTA_Zone 2 - Super Structure - P1 to P2 - Pour 3 | Complete | RCC Works - Vertical | 2024-01-05 | 2024-01-22 | Columns/ Walls_NTA | 100 | 100 |  | 2024-01-05 | 2024-01-05 | 2024-01-22 | 2024-01-22 | NTA_Zone 2 | Super Structure
44476 | NTA_Zone 2 - Super Structure - P1 to P2 - Pour 3 | Complete | Staircase & Ramp RCC Works | 2024-01-05 | 2024-01-29 | Staircase_NTA | 100 | 100 |  | 2024-01-05 | 2024-01-05 | 2024-01-29 | 2024-01-29 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | Staircase & Ramp RCC Works
44476 | NTA_Zone 2 - Super Structure - P1 to P2 - Pour 3 | Complete | Staircase & Ramp RCC Works | 2024-01-05 | 2024-01-29 | Staircase_NTA | 100 | 100 |  | 2024-01-05 | 2024-01-05 | 2024-01-29 | 2024-01-29 | NTA_Zone 2 | Super Structure
39364 | Tower A - Super Structure - Core Wall Low Rise L10-11 | Complete | Core Wall RCC Works | 2024-01-08 | 2024-01-12 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-01-08 | 2024-01-08 | 2024-01-12 | 2024-01-12 | Tower A | Super Structure | L10 | RCC Super Structure | Core Wall RCC Works
39819 | Tower A - Super Structure - Core & Outer Slab P5-P6 | Complete | RCC Works - Slab | 2024-01-08 | 2024-01-20 | Outer Slab_TA | 100 | 100 |  | 2024-01-08 | 2024-01-08 | 2024-01-20 | 2024-01-20 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Slab
44467 |  | Complete |  | 2024-01-11 | 2024-02-21 | Pour 1 (Ramp) | 100 | 100 |  | 2024-01-11 | 2024-01-11 | 2024-02-21 | 2024-02-21
44468 | NTA_Zone 2 - Super Structure - P1 to P2 - Pour 1 | Complete | RCC Works - Vertical | 2024-01-11 | 2024-01-29 | Columns/ Walls_NTA | 100 | 100 |  | 2024-01-11 | 2024-01-11 | 2024-01-29 | 2024-01-29 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
44468 | NTA_Zone 2 - Super Structure - P1 to P2 - Pour 1 | Complete | RCC Works - Vertical | 2024-01-11 | 2024-01-29 | Columns/ Walls_NTA | 100 | 100 |  | 2024-01-11 | 2024-01-11 | 2024-01-29 | 2024-01-29 | NTA_Zone 2 | Super Structure
44469 | NTA_Zone 2 - Super Structure - P1 to P2 - Pour 1 | Complete | Staircase & Ramp RCC Works | 2024-01-11 | 2024-02-03 | Staircase & Ramp_NTA | 100 | 100 |  | 2024-01-11 | 2024-01-11 | 2024-02-03 | 2024-02-03 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | Staircase & Ramp RCC Works
44535 |  | Started |  | 2024-01-11 | 2024-11-12 | Masonry Works (incl. de-shutt, PT mark, B/W) | 100 | 38 |  | 2024-01-11 | 2024-01-11 | 2026-03-05
44536 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Partition Wall-Blockwork | 2024-01-11 | 2024-02-15 | B3 to B2 | 100 | 100 |  | 2024-01-11 | 2024-01-11 | 2024-02-15 | 2024-02-15 | NTA_Zone 2 | Sub Structure | B3
44536 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Partition Wall-Blockwork | 2024-01-11 | 2024-02-15 | B3 to B2 | 100 | 100 |  | 2024-01-11 | 2024-01-11 | 2024-02-15 | 2024-02-15 | NTA_Zone 2 | Sub Structure | B3
44536 | NTA_Zone 2 - Sub Structure - B3 to B2 | Complete | Partition Wall-Blockwork | 2024-01-11 | 2024-02-15 | B3 to B2 | 100 | 100 |  | 2024-01-11 | 2024-01-11 | 2024-02-15 | 2024-02-15 | NTA_Zone 2 | Sub Structure | B3
39365 | Tower A - Super Structure - Core Wall Low Rise L10-11 | Complete | Core Wall RCC Works | 2024-01-13 | 2024-01-13 | Casting | 100 | 100 |  | 2024-01-13 | 2024-01-13 | 2024-01-13 | 2024-01-13 | Tower A | Super Structure | L10 | RCC Super Structure | Core Wall RCC Works
40143 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 | Complete | Partition Wall-Blockwork | 2024-01-13 | 2024-01-31 | Partition Walls | 100 | 100 |  | 2024-01-13 | 2024-01-13 | 2024-01-31 | 2024-01-31 | Tower A | Sub Structure | B2
40148 | Tower A - Sub Structure - Finishes & MEP - B1 to GF | Complete | Partition Wall-Blockwork | 2024-01-13 | 2024-01-24 | Staircase Area | 100 | 100 |  | 2024-01-13 | 2024-01-13 | 2024-01-24 | 2024-01-24 | Tower A | Sub Structure | B1
48035 |  | Started |  | 2024-01-13 | 2026-12-29 | RETAIL & CLUBHOUSE | 100 | 21 |  | 2024-01-13 | 2024-01-13 | 2027-06-03
48113 |  | Complete |  | 2024-01-13 | 2024-06-30 | Excavation_Retail | 100 | 100 |  | 2024-01-13 | 2024-01-13 | 2024-06-30 | 2024-06-30
48114 | Retail - Foundation | Complete |  | 2024-01-13 | 2024-01-29 | Excavation up to -4.00 m | 100 | 100 |  | 2024-01-13 | 2024-01-13 | 2024-01-29 | 2024-01-29 | Retail | Foundation | --
39366 | Tower A - Super Structure - Core Wall Low Rise L10-11 | Complete | Core Wall RCC Works | 2024-01-15 | 2024-01-15 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-01-15 | 2024-01-15 | 2024-01-15 | 2024-01-15 | Tower A | Super Structure | L10 | RCC Super Structure | Core Wall RCC Works
39367 |  | Complete |  | 2024-01-16 | 2024-02-22 | Core Wall L11-12 | 100 | 100 |  | 2024-01-16 | 2024-01-16 | 2024-02-22 | 2024-02-22
39368 | Tower A - Super Structure - Core Wall Low Rise L11-12 | Complete | Core Wall RCC Works | 2024-01-16 | 2024-01-16 | Scaffolding & platform | 100 | 100 |  | 2024-01-16 | 2024-01-16 | 2024-01-16 | 2024-01-16 | Tower A | Super Structure | L11 | RCC Super Structure | Core Wall RCC Works
39369 | Tower A - Super Structure - Core Wall Low Rise L11-12 | Complete | Core Wall RCC Works | 2024-01-17 | 2024-01-22 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-01-17 | 2024-01-17 | 2024-01-22 | 2024-01-22 | Tower A | Super Structure | L11 | RCC Super Structure | Core Wall RCC Works
44478 |  | Complete |  | 2024-01-17 | 2024-02-21 | Pour 4 (Grid PA-4 to PA-8) | 100 | 100 |  | 2024-01-17 | 2024-01-17 | 2024-02-21 | 2024-02-21
44479 | NTA_Zone 2 - Super Structure - P1 to P2 - Pour 4 | Complete | RCC Works - Vertical | 2024-01-17 | 2024-02-03 | Columns/ Walls_NTA | 100 | 100 |  | 2024-01-17 | 2024-01-17 | 2024-02-03 | 2024-02-03 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
44479 | NTA_Zone 2 - Super Structure - P1 to P2 - Pour 4 | Complete | RCC Works - Vertical | 2024-01-17 | 2024-02-03 | Columns/ Walls_NTA | 100 | 100 |  | 2024-01-17 | 2024-01-17 | 2024-02-03 | 2024-02-03 | NTA_Zone 2 | Super Structure
39370 | Tower A - Super Structure - Core Wall Low Rise L11-12 | Complete | Core Wall RCC Works | 2024-01-20 | 2024-01-23 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-01-20 | 2024-01-20 | 2024-01-23 | 2024-01-23 | Tower A | Super Structure | L11 | RCC Super Structure | Core Wall RCC Works
39820 |  | Complete |  | 2024-01-22 | 2024-02-17 | P6-L7 (1st Set up = Al./ Deck form) | 100 | 100 |  | 2024-01-22 | 2024-01-22 | 2024-02-17 | 2024-02-17
39821 | Tower A - Super Structure - Core & Outer Slab P6-L7 | Complete | RCC Works - Vertical | 2024-01-22 | 2024-02-08 | 1st Typical Modular Formwork Set-up | 100 | 100 |  | 2024-01-22 | 2024-01-22 | 2024-02-08 | 2024-02-08 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
39821 | Tower A - Super Structure - Core & Outer Slab P6-L7 | Complete | RCC Works - Vertical | 2024-01-22 | 2024-02-08 | 1st Typical Modular Formwork Set-up | 100 | 100 |  | 2024-01-22 | 2024-01-22 | 2024-02-08 | 2024-02-08 | Tower A | Super Structure
40169 |  | Started |  | 2024-01-22 | 2024-06-15 | P5 to P6_TA | 100 | 15 |  | 2024-01-22 | 2024-01-22 | 2025-10-22
40170 | Tower A - Super Structure - Finishes & MEP - P5 to P6 | Complete | Partition Wall-Blockwork | 2024-01-22 | 2024-01-27 | De-shuttering & Area clearance | 100 | 100 |  | 2024-01-22 | 2024-01-22 | 2024-01-27 | 2024-01-27 | Tower A | Super Structure
44697 |  | Complete |  | 2024-01-22 | 2024-02-29 | Rock Anchoring - layer 1 | 100 | 100 |  | 2024-01-22 | 2024-01-22 | 2024-02-29 | 2024-02-29
44698 | Tower B | Complete | Rock Anchoring | 2024-01-22 | 2024-02-20 | Zone 1 North (outside NTA Zone 2) | 100 | 100 |  | 2024-01-22 | 2024-01-22 | 2024-02-20 | 2024-02-20 | Tower B | --
44698 | Tower B | Complete | Rock Anchoring | 2024-01-22 | 2024-02-20 | Zone 1 North (outside NTA Zone 2) | 100 | 100 |  | 2024-01-22 | 2024-01-22 | 2024-02-20 | 2024-02-20 | Tower B | --
44698 | Tower B | Complete | Rock Anchoring | 2024-01-22 | 2024-02-20 | Zone 1 North (outside NTA Zone 2) | 100 | 100 |  | 2024-01-22 | 2024-01-22 | 2024-02-20 | 2024-02-20 | Tower B | --
44698 | Tower B | Complete | Rock Anchoring | 2024-01-22 | 2024-02-20 | Zone 1 North (outside NTA Zone 2) | 100 | 100 |  | 2024-01-22 | 2024-01-22 | 2024-02-20 | 2024-02-20 | Tower B | --
44477 | NTA_Zone 2 - Super Structure - P1 to P2 - Pour 3 | Complete | RCC Works - Slab | 2024-01-23 | 2024-02-15 | Slab_NTA | 100 | 100 |  | 2024-01-23 | 2024-01-23 | 2024-02-15 | 2024-02-15 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Slab
44477 | NTA_Zone 2 - Super Structure - P1 to P2 - Pour 3 | Complete | RCC Works - Slab | 2024-01-23 | 2024-02-15 | Slab_NTA | 100 | 100 |  | 2024-01-23 | 2024-01-23 | 2024-02-15 | 2024-02-15 | NTA_Zone 2 | Super Structure
44480 | NTA_Zone 2 - Super Structure - P1 to P2 - Pour 4 | Complete | RCC Works - Slab | 2024-01-23 | 2024-02-21 | Slab_NTA (part double ht.) | 100 | 100 |  | 2024-01-23 | 2024-01-23 | 2024-02-21 | 2024-02-21 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Slab
39132 |  | Complete |  | 2024-01-25 | 2024-08-31 | Vertical Transport Agency | 100 | 100 |  | 2024-01-25 | 2024-01-25 | 2024-08-31 | 2024-08-31
48115 | Retail - Foundation | Complete |  | 2024-01-29 | 2024-02-14 | Rock Anchoring - layer 1 | 100 | 100 |  | 2024-01-29 | 2024-01-29 | 2024-02-14 | 2024-02-14 | Retail | Foundation | --
44470 | NTA_Zone 2 - Super Structure - P1 to P2 - Pour 1 | Complete | RCC Works - Slab | 2024-01-30 | 2024-02-21 | Slab_NTA | 100 | 100 |  | 2024-01-30 | 2024-01-30 | 2024-02-21 | 2024-02-21 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Slab
44470 | NTA_Zone 2 - Super Structure - P1 to P2 - Pour 1 | Complete | RCC Works - Slab | 2024-01-30 | 2024-02-21 | Slab_NTA | 100 | 100 |  | 2024-01-30 | 2024-01-30 | 2024-02-21 | 2024-02-21 | NTA_Zone 2 | Super Structure
44481 |  | Complete |  | 2024-01-30 | 2024-04-03 | P2 to P3 | 100 | 100 |  | 2024-01-30 | 2024-01-30 | 2024-04-03 | 2024-04-03
44481 |  | Complete |  | 2024-01-30 | 2024-04-03 | P2 to P3 | 100 | 100 |  | 2024-01-30 | 2024-01-30 | 2024-04-03 | 2024-04-03
44481 |  | Complete |  | 2024-01-30 | 2024-04-03 | P2 to P3 | 100 | 100 |  | 2024-01-30 | 2024-01-30 | 2024-04-03 | 2024-04-03
44486 |  | Complete |  | 2024-01-30 | 2024-02-27 | Pour 2 (btwn TA & NTA Ramp) | 100 | 100 |  | 2024-01-30 | 2024-01-30 | 2024-02-27 | 2024-02-27
44487 | NTA_Zone 2 - Super Structure - P2 to P3 - Pour 2 | Complete | RCC Works - Vertical | 2024-01-30 | 2024-02-15 | Columns/ Walls_NTA | 100 | 100 |  | 2024-01-30 | 2024-01-30 | 2024-02-15 | 2024-02-15 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
44487 | NTA_Zone 2 - Super Structure - P2 to P3 - Pour 2 | Complete | RCC Works - Vertical | 2024-01-30 | 2024-02-15 | Columns/ Walls_NTA | 100 | 100 |  | 2024-01-30 | 2024-01-30 | 2024-02-15 | 2024-02-15 | NTA_Zone 2 | Super Structure
40139 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 | Complete | Partition Wall-Blockwork | 2024-02-01 | 2024-02-17 | Partition Walls | 100 | 100 |  | 2024-02-01 | 2024-02-01 | 2024-02-17 | 2024-02-17 | Tower A | Sub Structure | B3
40144 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 | Complete | Partition Wall-Blockwork | 2024-02-01 | 2024-02-12 | Staircase Area | 100 | 100 |  | 2024-02-01 | 2024-02-01 | 2024-02-12 | 2024-02-12 | Tower A | Sub Structure | B2
44488 | NTA_Zone 2 - Super Structure - P2 to P3 - Pour 2 | Complete | RCC Works - Slab | 2024-02-05 | 2024-02-27 | Slab_NTA | 100 | 100 |  | 2024-02-05 | 2024-02-05 | 2024-02-27 | 2024-02-27 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Slab
44488 | NTA_Zone 2 - Super Structure - P2 to P3 - Pour 2 | Complete | RCC Works - Slab | 2024-02-05 | 2024-02-27 | Slab_NTA | 100 | 100 |  | 2024-02-05 | 2024-02-05 | 2024-02-27 | 2024-02-27 | NTA_Zone 2 | Super Structure
47998 |  | Complete |  | 2024-02-06 | 2024-04-04 | Zone-1 | 100 | 100 |  | 2024-02-06 | 2024-02-06 | 2024-04-04 | 2024-04-04
47999 |  | Complete |  | 2024-02-06 | 2024-02-10 | Isolation Cut for Demolition | 100 | 100 |  | 2024-02-06 | 2024-02-06 | 2024-02-10 | 2024-02-10
48003 |  | Started |  | 2024-02-06 | 2025-04-28 | Zone C (Area Impacted by Services Connections) | 100 | 81 |  | 2024-02-06 | 2024-02-06 | 2025-11-20
48004 |  | Complete |  | 2024-02-06 | 2024-04-16 | BMC Approval for Services Shifting | 100 | 100 |  | 2024-02-06 | 2024-02-06 | 2024-04-16 | 2024-04-16
39133 |  | Complete |  | 2024-02-08 | 2024-03-02 | Façade Agency | 100 | 100 |  | 2024-02-08 | 2024-02-08 | 2024-03-02 | 2024-03-02
39822 | Tower A - Super Structure - Core & Outer Slab P6-L7 | Complete | RCC Works - Vertical | 2024-02-09 | 2024-02-17 | Outer Columns_TA | 100 | 100 |  | 2024-02-09 | 2024-02-09 | 2024-02-17 | 2024-02-17 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
47991 |  | Complete |  | 2024-02-12 | 2024-02-28 | Removal of Backpropping | 100 | 100 |  | 2024-02-12 | 2024-02-12 | 2024-02-28 | 2024-02-28
47995 |  | Complete |  | 2024-02-12 | 2024-05-28 | Zone-2 | 100 | 100 |  | 2024-02-12 | 2024-02-12 | 2024-05-28 | 2024-05-28
47996 |  | Complete |  | 2024-02-12 | 2024-02-16 | Isolation Cut for Demolition | 100 | 100 |  | 2024-02-12 | 2024-02-12 | 2024-02-16 | 2024-02-16
48000 |  | Complete |  | 2024-02-12 | 2024-04-04 | Demolition + Segregation & Carting Away of Debris | 100 | 100 |  | 2024-02-12 | 2024-02-12 | 2024-04-04 | 2024-04-04
40589 |  | Started |  | 2024-02-13 | 2024-06-10 | Basement MEP & Finishes | 100 | 50 |  | 2024-02-13 | 2024-02-13 | 2025-12-10
40619 |  | Started |  | 2024-02-13 | 2024-04-23 | B2 Level | 100 | 53 |  | 2024-02-13 | 2024-02-13 | 2025-11-11
40620 |  | Started |  | 2024-02-13 | 2024-04-03 | Lobby/ Common Area | 100 | 56 |  | 2024-02-13 | 2024-02-13 | 2025-10-29
40621 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Started | FPS 1st Fix - MEP & Finishes | 2024-02-13 | 2024-02-15 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 65 |  | 2024-02-13 | 2024-02-13 | 2025-09-13 |  | Tower A | Sub Structure | B2 | MEP | FPS 1st Fix - MEP & Finishes
40634 |  | Started |  | 2024-02-13 | 2024-04-23 | Floor Area | 100 | 50 |  | 2024-02-13 | 2024-02-13 | 2025-11-11
40635 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Complete | Ceiling Painting/ PT Marking - MEP & Finishes | 2024-02-13 | 2024-02-17 | Ceiling Painting/ PT Marking | 100 | 100 |  | 2024-02-13 | 2024-02-13 | 2024-02-17 | 2024-02-17 | Tower A | Sub Structure | B2 | Finishes | Ceiling Painting/ PT Marking
39823 | Tower A - Super Structure - Core & Outer Slab P6-L7 | Complete | RCC Works - Slab | 2024-02-14 | 2024-02-17 | Outer Slab_TA | 100 | 100 |  | 2024-02-14 | 2024-02-14 | 2024-02-17 | 2024-02-17 | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Slab
48116 | Retail - Foundation | Complete |  | 2024-02-14 | 2024-06-30 | Excavation Retail (Zone 4) incl. Rock Anchoring | 100 | 100 |  | 2024-02-14 | 2024-02-14 | 2024-06-30 | 2024-06-30 | Retail | Foundation | --
44489 |  | Complete |  | 2024-02-16 | 2024-03-28 | Pour 3 (Grid PA-A to PA-D) | 100 | 100 |  | 2024-02-16 | 2024-02-16 | 2024-03-28 | 2024-03-28
44490 | NTA_Zone 2 - Super Structure - P2 to P3 - Pour 3 | Complete | RCC Works - Vertical | 2024-02-16 | 2024-03-04 | Columns/ Walls_NTA | 100 | 100 |  | 2024-02-16 | 2024-02-16 | 2024-03-04 | 2024-03-04 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
44490 | NTA_Zone 2 - Super Structure - P2 to P3 - Pour 3 | Complete | RCC Works - Vertical | 2024-02-16 | 2024-03-04 | Columns/ Walls_NTA | 100 | 100 |  | 2024-02-16 | 2024-02-16 | 2024-03-04 | 2024-03-04 | NTA_Zone 2 | Super Structure
44491 | NTA_Zone 2 - Super Structure - P2 to P3 - Pour 3 | Complete | Staircase & Ramp RCC Works | 2024-02-16 | 2024-03-09 | Staircase_NTA | 100 | 100 |  | 2024-02-16 | 2024-02-16 | 2024-03-09 | 2024-03-09 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | Staircase & Ramp RCC Works
44491 | NTA_Zone 2 - Super Structure - P2 to P3 - Pour 3 | Complete | Staircase & Ramp RCC Works | 2024-02-16 | 2024-03-09 | Staircase_NTA | 100 | 100 |  | 2024-02-16 | 2024-02-16 | 2024-03-09 | 2024-03-09 | NTA_Zone 2 | Super Structure
44526 |  | Started |  | 2024-02-16 | 2025-07-29 | MEP 1st Fixes | 100 | 76 |  | 2024-02-16 | 2024-02-16 | 2026-03-23
44527 | NTA_Zone 2 - Sub Structure - B3 to B2 | Started | MEP 1st Fix Works | 2024-02-16 | 2024-02-29 | B3 to B2 | 100 | 80 |  | 2024-02-16 | 2024-02-16 | 2025-09-25 |  | NTA_Zone 2 | Sub Structure | B3
44527 | NTA_Zone 2 - Sub Structure - B3 to B2 | Started | MEP 1st Fix Works | 2024-02-16 | 2024-02-29 | B3 to B2 | 100 | 80 |  | 2024-02-16 | 2024-02-16 | 2025-09-25 |  | NTA_Zone 2 | Sub Structure | B3
44527 | NTA_Zone 2 - Sub Structure - B3 to B2 | Started | MEP 1st Fix Works | 2024-02-16 | 2024-02-29 | B3 to B2 | 100 | 80 |  | 2024-02-16 | 2024-02-16 | 2025-09-25 |  | NTA_Zone 2 | Sub Structure | B3
44537 | NTA_Zone 2 - Sub Structure - B2 to B1 | Complete | Partition Wall-Blockwork | 2024-02-16 | 2024-03-21 | B2 to B1 | 100 | 100 |  | 2024-02-16 | 2024-02-16 | 2024-03-21 | 2024-03-21 | NTA_Zone 2 | Sub Structure | B2
44537 | NTA_Zone 2 - Sub Structure - B2 to B1 | Complete | Partition Wall-Blockwork | 2024-02-16 | 2024-03-21 | B2 to B1 | 100 | 100 |  | 2024-02-16 | 2024-02-16 | 2024-03-21 | 2024-03-21 | NTA_Zone 2 | Sub Structure | B2
44537 | NTA_Zone 2 - Sub Structure - B2 to B1 | Complete | Partition Wall-Blockwork | 2024-02-16 | 2024-03-21 | B2 to B1 | 100 | 100 |  | 2024-02-16 | 2024-02-16 | 2024-03-21 | 2024-03-21 | NTA_Zone 2 | Sub Structure | B2
44678 | Tower A | Complete | Award of Packages | 2024-02-16 | 2025-01-21 | Finishing | 100 | 100 |  | 2024-02-16 | 2024-02-16 | 2025-01-21 | 2025-01-21 | Tower A | --
47992 |  | Complete |  | 2024-02-17 | 2024-06-29 | Zone-3 | 100 | 100 |  | 2024-02-17 | 2024-02-17 | 2024-06-29 | 2024-06-29
47993 |  | Complete |  | 2024-02-17 | 2024-02-22 | Isolation Cut for Demolition | 100 | 100 |  | 2024-02-17 | 2024-02-17 | 2024-02-22 | 2024-02-22
39824 |  | Complete |  | 2024-02-19 | 2024-02-28 | L7-8 | 100 | 100 |  | 2024-02-19 | 2024-02-19 | 2024-02-28 | 2024-02-28
39824 |  | Complete |  | 2024-02-19 | 2024-02-28 | L7-8 | 100 | 100 |  | 2024-02-19 | 2024-02-19 | 2024-02-28 | 2024-02-28 |  |  |  | Finishes | Gypsum Plastering Works
39825 | Tower A - Super Structure - Core & Outer Slab L7-8 | Complete | RCC Works - Vertical | 2024-02-19 | 2024-02-26 | Outer Columns_TA | 100 | 100 |  | 2024-02-19 | 2024-02-19 | 2024-02-26 | 2024-02-26 | Tower A | Super Structure | L7 | RCC Sub Structure | RCC Works - Vertical
40140 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 | Complete | Partition Wall-Blockwork | 2024-02-19 | 2024-02-29 | Staircase Area | 100 | 100 |  | 2024-02-19 | 2024-02-19 | 2024-02-29 | 2024-02-29 | Tower A | Sub Structure | B3
40636 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Started | FPS 1st Fix - MEP & Finishes | 2024-02-19 | 2024-02-27 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 60 |  | 2024-02-19 | 2024-02-19 | 2025-09-20 |  | Tower A | Sub Structure | B2 | MEP | FPS 1st Fix - MEP & Finishes
39371 | Tower A - Super Structure - Core Wall Low Rise L11-12 | Complete | Core Wall RCC Works | 2024-02-21 | 2024-02-21 | Casting | 100 | 100 |  | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-21 | Tower A | Super Structure | L11 | RCC Super Structure | Core Wall RCC Works
44699 | Tower B | Complete | Rock Anchoring | 2024-02-21 | 2024-02-29 | waiting for grout strength & Stressing | 100 | 100 |  | 2024-02-21 | 2024-02-21 | 2024-02-29 | 2024-02-29 | Tower B | --
39372 | Tower A - Super Structure - Core Wall Low Rise L11-12 | Complete | Core Wall RCC Works | 2024-02-22 | 2024-02-22 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-02-22 | 2024-02-22 | 2024-02-22 | 2024-02-22 | Tower A | Super Structure | L11 | RCC Super Structure | Core Wall RCC Works
39826 | Tower A - Super Structure - Core & Outer Slab L7-8 | Complete | RCC Works - Slab | 2024-02-22 | 2024-02-28 | Outer Slab_TA | 100 | 100 |  | 2024-02-22 | 2024-02-22 | 2024-02-28 | 2024-02-28 | Tower A | Super Structure | L7 | RCC Sub Structure | RCC Works - Slab
44482 |  | Complete |  | 2024-02-22 | 2024-04-03 | Pour 1 (Ramp) | 100 | 100 |  | 2024-02-22 | 2024-02-22 | 2024-04-03 | 2024-04-03
44483 | NTA_Zone 2 - Super Structure - P2 to P3 - Pour 1 | Complete | RCC Works - Vertical | 2024-02-22 | 2024-03-09 | Columns/ Walls_NTA | 100 | 100 |  | 2024-02-22 | 2024-02-22 | 2024-03-09 | 2024-03-09 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
44483 | NTA_Zone 2 - Super Structure - P2 to P3 - Pour 1 | Complete | RCC Works - Vertical | 2024-02-22 | 2024-03-09 | Columns/ Walls_NTA | 100 | 100 |  | 2024-02-22 | 2024-02-22 | 2024-03-09 | 2024-03-09 | NTA_Zone 2 | Super Structure
44484 | NTA_Zone 2 - Super Structure - P2 to P3 - Pour 1 | Complete | Staircase & Ramp RCC Works | 2024-02-22 | 2024-03-15 | Staircase & Ramp_NTA | 100 | 100 |  | 2024-02-22 | 2024-02-22 | 2024-03-15 | 2024-03-15 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | Staircase & Ramp RCC Works
44493 |  | Complete |  | 2024-02-22 | 2024-03-21 | Pour 4 (Grid PA-4 to PA-8) | 100 | 100 |  | 2024-02-22 | 2024-02-22 | 2024-03-21 | 2024-03-21
44494 | NTA_Zone 2 - Super Structure - P2 to P3 - Pour 4 | Complete | RCC Works - Vertical | 2024-02-22 | 2024-03-09 | Columns/ Walls_NTA | 100 | 100 |  | 2024-02-22 | 2024-02-22 | 2024-03-09 | 2024-03-09 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
44494 | NTA_Zone 2 - Super Structure - P2 to P3 - Pour 4 | Complete | RCC Works - Vertical | 2024-02-22 | 2024-03-09 | Columns/ Walls_NTA | 100 | 100 |  | 2024-02-22 | 2024-02-22 | 2024-03-09 | 2024-03-09 | NTA_Zone 2 | Super Structure
39373 |  | Complete |  | 2024-02-23 | 2024-03-01 | Core Wall L12-13 | 100 | 100 |  | 2024-02-23 | 2024-02-23 | 2024-03-01 | 2024-03-01
39374 | Tower A - Super Structure - Core Wall Low Rise L12-13 | Complete | Core Wall RCC Works | 2024-02-23 | 2024-02-23 | Scaffolding & platform | 100 | 100 |  | 2024-02-23 | 2024-02-23 | 2024-02-23 | 2024-02-23 | Tower A | Super Structure | L12 | RCC Super Structure | Core Wall RCC Works
39375 | Tower A - Super Structure - Core Wall Low Rise L12-13 | Complete | Core Wall RCC Works | 2024-02-24 | 2024-02-29 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-02-24 | 2024-02-24 | 2024-02-29 | 2024-02-29 | Tower A | Super Structure | L12 | RCC Super Structure | Core Wall RCC Works
39376 | Tower A - Super Structure - Core Wall Low Rise L12-13 | Complete | Core Wall RCC Works | 2024-02-28 | 2024-03-01 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-02-28 | 2024-02-28 | 2024-03-01 | 2024-03-01 | Tower A | Super Structure | L12 | RCC Super Structure | Core Wall RCC Works
39377 | Tower A - Super Structure - Core Wall Low Rise L12-13 | Complete | Core Wall RCC Works | 2024-02-28 | 2024-02-28 | Casting | 100 | 100 |  | 2024-02-28 | 2024-02-28 | 2024-02-28 | 2024-02-28 | Tower A | Super Structure | L12 | RCC Super Structure | Core Wall RCC Works
44495 | NTA_Zone 2 - Super Structure - P2 to P3 - Pour 4 | Complete | RCC Works - Slab | 2024-02-28 | 2024-03-21 | Slab_NTA | 100 | 100 |  | 2024-02-28 | 2024-02-28 | 2024-03-21 | 2024-03-21 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Slab
44495 | NTA_Zone 2 - Super Structure - P2 to P3 - Pour 4 | Complete | RCC Works - Slab | 2024-02-28 | 2024-03-21 | Slab_NTA | 100 | 100 |  | 2024-02-28 | 2024-02-28 | 2024-03-21 | 2024-03-21 | NTA_Zone 2 | Super Structure
44496 |  | Started |  | 2024-02-28 | 2024-05-15 | P3 to P4 | 100 | 88 |  | 2024-02-28 | 2024-02-28 | 2025-10-06
44496 |  | Started |  | 2024-02-28 | 2024-05-15 | P3 to P4 | 100 | 88 |  | 2024-02-28 | 2024-02-28 | 2025-10-06
44496 |  | Started |  | 2024-02-28 | 2024-05-15 | P3 to P4 | 100 | 88 |  | 2024-02-28 | 2024-02-28 | 2025-10-06
44501 |  | Complete |  | 2024-02-28 | 2024-03-28 | Pour 2 (btwn TA & NTA Ramp) | 100 | 100 |  | 2024-02-28 | 2024-02-28 | 2024-03-28 | 2024-03-28
44502 | NTA_Zone 2 - Super Structure - P3 to P4 - Pour 2 | Complete | RCC Works - Vertical | 2024-02-28 | 2024-03-15 | Columns/ Walls_NTA | 100 | 100 |  | 2024-02-28 | 2024-02-28 | 2024-03-15 | 2024-03-15 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
44502 | NTA_Zone 2 - Super Structure - P3 to P4 - Pour 2 | Complete | RCC Works - Vertical | 2024-02-28 | 2024-03-15 | Columns/ Walls_NTA | 100 | 100 |  | 2024-02-28 | 2024-02-28 | 2024-03-15 | 2024-03-15 | NTA_Zone 2 | Super Structure
39378 | Tower A - Super Structure - Core Wall Low Rise L12-13 | Complete | Core Wall RCC Works | 2024-02-29 | 2024-02-29 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-02-29 | 2024-02-29 | 2024-02-29 | 2024-02-29 | Tower A | Super Structure | L12 | RCC Super Structure | Core Wall RCC Works
39827 |  | Complete |  | 2024-02-29 | 2024-03-10 | L8-9 | 100 | 100 |  | 2024-02-29 | 2024-02-29 | 2024-03-10 | 2024-03-10
39827 |  | Complete |  | 2024-02-29 | 2024-03-10 | L8-9 | 100 | 100 |  | 2024-02-29 | 2024-02-29 | 2024-03-10 | 2024-03-10 |  |  |  | Finishes | Gypsum Plastering Works
39828 | Tower A - Super Structure - Core & Outer Slab L8-9 | Complete | RCC Works - Vertical | 2024-02-29 | 2024-03-07 | Outer Columns_TA | 100 | 100 |  | 2024-02-29 | 2024-02-29 | 2024-03-07 | 2024-03-07 | Tower A | Super Structure | L8 | RCC Sub Structure | RCC Works - Vertical
39379 |  | Complete |  | 2024-03-01 | 2024-03-15 | Core Wall L13-14 | 100 | 100 |  | 2024-03-01 | 2024-03-01 | 2024-03-15 | 2024-03-15
39380 | Tower A - Super Structure - Core Wall Low Rise L13-14 | Complete | Core Wall RCC Works | 2024-03-01 | 2024-03-01 | Scaffolding & platform | 100 | 100 |  | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | Tower A | Super Structure | L13 | RCC Super Structure | Core Wall RCC Works
40590 |  | Started |  | 2024-03-01 | 2024-05-29 | B3 Level | 100 | 50 |  | 2024-03-01 | 2024-03-01 | 2025-12-10
40591 |  | Started |  | 2024-03-01 | 2024-05-29 | Floor Area | 100 | 46 |  | 2024-03-01 | 2024-03-01 | 2025-12-10
40592 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Complete | Ceiling Painting/ PT Marking - MEP & Finishes | 2024-03-01 | 2024-03-06 | Ceiling Painting/ PT Marking | 100 | 100 |  | 2024-03-01 | 2024-03-01 | 2024-03-06 | 2024-03-06 | Tower A | Sub Structure | B3 | Finishes | Ceiling Painting/ PT Marking
40605 |  | Started |  | 2024-03-01 | 2024-04-20 | Lobby/ Common Area | 100 | 55 |  | 2024-03-01 | 2024-03-01 | 2025-10-31
40606 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Started | FPS 1st Fix - MEP & Finishes | 2024-03-01 | 2024-03-04 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 65 |  | 2024-03-01 | 2024-03-01 | 2025-09-16 |  | Tower A | Sub Structure | B3 | MEP | FPS 1st Fix - MEP & Finishes
44700 |  | Complete |  | 2024-03-01 | 2024-03-30 | Excavation up to -14.00 m | 100 | 100 |  | 2024-03-01 | 2024-03-01 | 2024-03-30 | 2024-03-30
44701 | Tower B | Complete | Excavation upto -14 Mtr | 2024-03-01 | 2024-03-30 | Zone 1 North (outside NTA Zone 2) | 100 | 100 |  | 2024-03-01 | 2024-03-01 | 2024-03-30 | 2024-03-30 | Tower B | --
44701 | Tower B | Complete | Excavation upto -14 Mtr | 2024-03-01 | 2024-03-30 | Zone 1 North (outside NTA Zone 2) | 100 | 100 |  | 2024-03-01 | 2024-03-01 | 2024-03-30 | 2024-03-30 | Tower B | --
44701 | Tower B | Complete | Excavation upto -14 Mtr | 2024-03-01 | 2024-03-30 | Zone 1 North (outside NTA Zone 2) | 100 | 100 |  | 2024-03-01 | 2024-03-01 | 2024-03-30 | 2024-03-30 | Tower B | --
44701 | Tower B | Complete | Excavation upto -14 Mtr | 2024-03-01 | 2024-03-30 | Zone 1 North (outside NTA Zone 2) | 100 | 100 |  | 2024-03-01 | 2024-03-01 | 2024-03-30 | 2024-03-30 | Tower B | --
39381 | Tower A - Super Structure - Core Wall Low Rise L13-14 | Complete | Core Wall RCC Works | 2024-03-02 | 2024-03-07 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-03-02 | 2024-03-02 | 2024-03-07 | 2024-03-07 | Tower A | Super Structure | L13 | RCC Super Structure | Core Wall RCC Works
39829 | Tower A - Super Structure - Core & Outer Slab L8-9 | Complete | RCC Works - Slab | 2024-03-04 | 2024-03-10 | Outer Slab_TA | 100 | 100 |  | 2024-03-04 | 2024-03-04 | 2024-03-10 | 2024-03-10 | Tower A | Super Structure | L8 | RCC Sub Structure | RCC Works - Slab
44492 | NTA_Zone 2 - Super Structure - P2 to P3 - Pour 3 | Complete | RCC Works - Slab | 2024-03-05 | 2024-03-28 | Slab_NTA | 100 | 100 |  | 2024-03-05 | 2024-03-05 | 2024-03-28 | 2024-03-28 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Slab
44492 | NTA_Zone 2 - Super Structure - P2 to P3 - Pour 3 | Complete | RCC Works - Slab | 2024-03-05 | 2024-03-28 | Slab_NTA | 100 | 100 |  | 2024-03-05 | 2024-03-05 | 2024-03-28 | 2024-03-28 | NTA_Zone 2 | Super Structure
44503 | NTA_Zone 2 - Super Structure - P3 to P4 - Pour 2 | Complete | RCC Works - Slab | 2024-03-05 | 2024-03-28 | Slab_NTA | 100 | 100 |  | 2024-03-05 | 2024-03-05 | 2024-03-28 | 2024-03-28 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Slab
44503 | NTA_Zone 2 - Super Structure - P3 to P4 - Pour 2 | Complete | RCC Works - Slab | 2024-03-05 | 2024-03-28 | Slab_NTA | 100 | 100 |  | 2024-03-05 | 2024-03-05 | 2024-03-28 | 2024-03-28 | NTA_Zone 2 | Super Structure
39382 | Tower A - Super Structure - Core Wall Low Rise L13-14 | Complete | Core Wall RCC Works | 2024-03-06 | 2024-03-08 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-03-06 | 2024-03-06 | 2024-03-08 | 2024-03-08 | Tower A | Super Structure | L13 | RCC Super Structure | Core Wall RCC Works
40593 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Started | FPS 1st Fix - MEP & Finishes | 2024-03-07 | 2024-03-15 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 60 |  | 2024-03-07 | 2024-03-07 | 2025-09-20 |  | Tower A | Sub Structure | B3 | MEP | FPS 1st Fix - MEP & Finishes
40646 |  | Started |  | 2024-03-07 | 2024-06-10 | B1 Level | 100 | 47 |  | 2024-03-07 | 2024-03-07 | 2025-12-04
40661 |  | Started |  | 2024-03-07 | 2024-06-10 | Floor Area | 100 | 44 |  | 2024-03-07 | 2024-03-07 | 2025-12-04
40662 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Complete | Ceiling Painting/ PT Marking - MEP & Finishes | 2024-03-07 | 2024-03-12 | Ceiling Painting/ PT Marking | 100 | 100 |  | 2024-03-07 | 2024-03-07 | 2024-03-12 | 2024-03-12 | Tower A | Sub Structure | B1 | Finishes | Ceiling Painting/ PT Marking
40647 |  | Started |  | 2024-03-09 | 2024-04-29 | Lobby/ Common Area | 100 | 51 |  | 2024-03-09 | 2024-03-09 | 2025-11-04
40648 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Started | FPS 1st Fix - MEP & Finishes | 2024-03-09 | 2024-03-12 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 60 |  | 2024-03-09 | 2024-03-09 | 2025-09-20 |  | Tower A | Sub Structure | B1 | MEP | FPS 1st Fix - MEP & Finishes
39383 | Tower A - Super Structure - Core Wall Low Rise L13-14 | Complete | Core Wall RCC Works | 2024-03-11 | 2024-03-14 | Casting | 100 | 100 |  | 2024-03-11 | 2024-03-11 | 2024-03-14 | 2024-03-14 | Tower A | Super Structure | L13 | RCC Super Structure | Core Wall RCC Works
39830 |  | Complete |  | 2024-03-11 | 2024-03-20 | L9-10 | 100 | 100 |  | 2024-03-11 | 2024-03-11 | 2024-03-20 | 2024-03-20
39830 |  | Complete |  | 2024-03-11 | 2024-03-20 | L9-10 | 100 | 100 |  | 2024-03-11 | 2024-03-11 | 2024-03-20 | 2024-03-20 |  |  |  | Finishes | Gypsum Plastering Works
39831 | Tower A - Super Structure - Core & Outer Slab L9-10 | Complete | RCC Works - Vertical | 2024-03-11 | 2024-03-18 | Outer Columns_TA | 100 | 100 |  | 2024-03-11 | 2024-03-11 | 2024-03-18 | 2024-03-18 | Tower A | Super Structure | L9 | RCC Sub Structure | RCC Works - Vertical
40173 |  | Started |  | 2024-03-11 | 2024-06-19 | P6 to L7 | 100 | 82 |  | 2024-03-11 | 2024-03-11 | 2025-09-16 |  |  |  |  | Finishes | Gypsum Plastering Works
40173 |  | Started |  | 2024-03-11 | 2024-06-19 | P6 to L7 | 100 | 82 |  | 2024-03-11 | 2024-03-11 | 2025-09-16
40174 | Tower A - Super Structure - Finishes & MEP - P6 to L7 | Complete | Partition Wall-Blockwork | 2024-03-11 | 2024-03-28 | De-shuttering & Area clearance | 100 | 100 |  | 2024-03-11 | 2024-03-11 | 2024-03-28 | 2024-03-28 | Tower A | Super Structure
44485 | NTA_Zone 2 - Super Structure - P2 to P3 - Pour 1 | Complete | RCC Works - Slab | 2024-03-11 | 2024-04-03 | Slab_NTA | 100 | 100 |  | 2024-03-11 | 2024-03-11 | 2024-04-03 | 2024-04-03 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Slab
44485 | NTA_Zone 2 - Super Structure - P2 to P3 - Pour 1 | Complete | RCC Works - Slab | 2024-03-11 | 2024-04-03 | Slab_NTA | 100 | 100 |  | 2024-03-11 | 2024-03-11 | 2024-04-03 | 2024-04-03 | NTA_Zone 2 | Super Structure
40663 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Started | FPS 1st Fix - MEP & Finishes | 2024-03-13 | 2024-03-27 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 60 |  | 2024-03-13 | 2024-03-13 | 2025-09-25 |  | Tower A | Sub Structure | B1 | MEP | FPS 1st Fix - MEP & Finishes
39832 | Tower A - Super Structure - Core & Outer Slab L9-10 | Complete | RCC Works - Slab | 2024-03-14 | 2024-03-20 | Outer Slab_TA | 100 | 100 |  | 2024-03-14 | 2024-03-14 | 2024-03-20 | 2024-03-20 | Tower A | Super Structure | L9 | RCC Sub Structure | RCC Works - Slab
39384 | Tower A - Super Structure - Core Wall Low Rise L13-14 | Complete | Core Wall RCC Works | 2024-03-15 | 2024-03-15 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | Tower A | Super Structure | L13 | RCC Super Structure | Core Wall RCC Works
39385 |  | Complete |  | 2024-03-16 | 2024-03-26 | Core Wall L14-15 | 100 | 100 |  | 2024-03-16 | 2024-03-16 | 2024-03-26 | 2024-03-26
39386 | Tower A - Super Structure - Core Wall Low Rise L14-15 | Complete | Core Wall RCC Works | 2024-03-16 | 2024-03-16 | Scaffolding & platform | 100 | 100 |  | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-16 | Tower A | Super Structure | L14 | RCC Super Structure | Core Wall RCC Works
39387 | Tower A - Super Structure - Core Wall Low Rise L14-15 | Complete | Core Wall RCC Works | 2024-03-18 | 2024-03-22 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-03-18 | 2024-03-18 | 2024-03-22 | 2024-03-22 | Tower A | Super Structure | L14 | RCC Super Structure | Core Wall RCC Works
40673 |  | Started |  | 2024-03-19 | 2026-01-07 | Podium MEP & Finishes | 100 | 16 |  | 2024-03-19 | 2024-03-19 | 2027-04-29
40674 |  | Started |  | 2024-03-19 | 2026-01-07 | GF-P1 | 100 | 7 |  | 2024-03-19 | 2024-03-19 | 2027-04-29
40689 |  | Started |  | 2024-03-19 | 2026-01-07 | Floor Area (Grand Entrance) | 100 | 9 |  | 2024-03-19 | 2024-03-19 | 2027-04-29
40690 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Complete | FPS 1st Fix - MEP & Finishes | 2024-03-19 | 2024-04-11 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 100 |  | 2024-03-19 | 2024-03-19 | 2024-04-11 | 2024-04-11 | Tower A | Super Structure | GF | MEP | FPS 1st Fix - MEP & Finishes
39388 | Tower A - Super Structure - Core Wall Low Rise L14-15 | Complete | Core Wall RCC Works | 2024-03-21 | 2024-03-23 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-03-21 | 2024-03-21 | 2024-03-23 | 2024-03-23 | Tower A | Super Structure | L14 | RCC Super Structure | Core Wall RCC Works
39833 |  | Complete |  | 2024-03-21 | 2024-03-30 | L10-11 | 100 | 100 |  | 2024-03-21 | 2024-03-21 | 2024-03-30 | 2024-03-30
39833 |  | Complete |  | 2024-03-21 | 2024-03-30 | L10-11 | 100 | 100 |  | 2024-03-21 | 2024-03-21 | 2024-03-30 | 2024-03-30 |  |  |  | Finishes | Gypsum Plastering Works
39834 | Tower A - Super Structure - Core & Outer Slab L10-11 | Complete | RCC Works - Vertical | 2024-03-21 | 2024-03-29 | Outer Columns_TA | 100 | 100 |  | 2024-03-21 | 2024-03-21 | 2024-03-29 | 2024-03-29 | Tower A | Super Structure | L10 | RCC Sub Structure | RCC Works - Vertical
40177 |  | Complete |  | 2024-03-21 | 2024-06-27 | L7-8 | 100 | 100 |  | 2024-03-21 | 2024-03-21 | 2024-06-27 | 2024-06-27
40177 |  | Complete |  | 2024-03-21 | 2024-06-27 | L7-8 | 100 | 100 |  | 2024-03-21 | 2024-03-21 | 2024-06-27 | 2024-06-27 |  |  |  | Finishes | Gypsum Plastering Works
40178 | Tower A - Super Structure - Finishes & MEP - L7 to L8 | Complete | Partition Wall-Blockwork | 2024-03-21 | 2024-04-08 | De-shuttering & Area clearance | 100 | 100 |  | 2024-03-21 | 2024-03-21 | 2024-04-08 | 2024-04-08 | Tower A | Super Structure | L7
44508 |  | Started |  | 2024-03-22 | 2024-04-20 | Pour 4 (Grid PA-4 to PA-8) | 100 | 42 |  | 2024-03-22 | 2024-03-22 | 2025-10-06
44509 | NTA_Zone 2 - Super Structure - P3 to P4 - Pour 4 | Complete | RCC Works - Vertical | 2024-03-22 | 2024-04-09 | Columns/ Walls_NTA | 100 | 100 |  | 2024-03-22 | 2024-03-22 | 2024-04-09 | 2024-04-09 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
44509 | NTA_Zone 2 - Super Structure - P3 to P4 - Pour 4 | Complete | RCC Works - Vertical | 2024-03-22 | 2024-04-09 | Columns/ Walls_NTA | 100 | 100 |  | 2024-03-22 | 2024-03-22 | 2024-04-09 | 2024-04-09 | NTA_Zone 2 | Super Structure
44538 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Partition Wall-Blockwork | 2024-03-22 | 2024-04-26 | B1 to GF | 100 | 100 |  | 2024-03-22 | 2024-03-22 | 2024-04-26 | 2024-04-26 | NTA_Zone 2 | Sub Structure | B1
44538 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Partition Wall-Blockwork | 2024-03-22 | 2024-04-26 | B1 to GF | 100 | 100 |  | 2024-03-22 | 2024-03-22 | 2024-04-26 | 2024-04-26 | NTA_Zone 2 | Sub Structure | B1
44538 | NTA_Zone 2 - Sub Structure - B1 to GF | Complete | Partition Wall-Blockwork | 2024-03-22 | 2024-04-26 | B1 to GF | 100 | 100 |  | 2024-03-22 | 2024-03-22 | 2024-04-26 | 2024-04-26 | NTA_Zone 2 | Sub Structure | B1
39389 | Tower A - Super Structure - Core Wall Low Rise L14-15 | Milestone Started | Core Wall RCC Works | 2024-03-24 |  | Casting | 100 | 100 |  | 2024-03-24 | 2024-03-26 |  |  | Tower A | Super Structure | L14 | RCC Super Structure | Core Wall RCC Works
39390 | Tower A - Super Structure - Core Wall Low Rise L14-15 | Complete | Core Wall RCC Works | 2024-03-26 | 2024-03-26 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2024-03-26 | Tower A | Super Structure | L14 | RCC Super Structure | Core Wall RCC Works
39835 | Tower A - Super Structure - Core & Outer Slab L10-11 | Complete | RCC Works - Slab | 2024-03-26 | 2024-03-30 | Outer Slab_TA | 100 | 100 |  | 2024-03-26 | 2024-03-26 | 2024-03-30 | 2024-03-30 | Tower A | Super Structure | L10 | RCC Sub Structure | RCC Works - Slab
40554 | Tower A - Super Structure - Finishes & MEP | Complete | MEP Shaft Masonry | 2024-03-26 | 2024-03-26 | L7-L15 | 100 | 100 |  | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2024-03-26 | Tower A | Super Structure
40554 | Tower A - Super Structure - Finishes & MEP | Complete | MEP Shaft Masonry | 2024-03-26 | 2024-03-26 | L7-L15 | 100 | 100 |  | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2024-03-26 | Tower A | Super Structure
39391 |  | Complete |  | 2024-03-27 | 2024-04-04 | Core Wall L15-16 | 100 | 100 |  | 2024-03-27 | 2024-03-27 | 2024-04-04 | 2024-04-04
39392 | Tower A - Super Structure - Core Wall Low Rise L15-16 | Complete | Core Wall RCC Works | 2024-03-27 | 2024-03-27 | Scaffolding & platform | 100 | 100 |  | 2024-03-27 | 2024-03-27 | 2024-03-27 | 2024-03-27 | Tower A | Super Structure | L15 | RCC Super Structure | Core Wall RCC Works
39393 | Tower A - Super Structure - Core Wall Low Rise L15-16 | Complete | Core Wall RCC Works | 2024-03-28 | 2024-04-02 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-03-28 | 2024-03-28 | 2024-04-02 | 2024-04-02 | Tower A | Super Structure | L15 | RCC Super Structure | Core Wall RCC Works
44504 |  | Complete |  | 2024-03-29 | 2024-05-09 | Pour 3 (Grid PA-A to PA-D) | 100 | 100 |  | 2024-03-29 | 2024-03-29 | 2024-05-09 | 2024-05-09
44505 | NTA_Zone 2 - Super Structure - P3 to P4 - Pour 3 | Complete | RCC Works - Vertical | 2024-03-29 | 2024-04-15 | Columns/ Walls_NTA | 100 | 100 |  | 2024-03-29 | 2024-03-29 | 2024-04-15 | 2024-04-15 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
44505 | NTA_Zone 2 - Super Structure - P3 to P4 - Pour 3 | Complete | RCC Works - Vertical | 2024-03-29 | 2024-04-15 | Columns/ Walls_NTA | 100 | 100 |  | 2024-03-29 | 2024-03-29 | 2024-04-15 | 2024-04-15 | NTA_Zone 2 | Super Structure
44506 | NTA_Zone 2 - Super Structure - P3 to P4 - Pour 3 | Complete | Staircase & Ramp RCC Works | 2024-03-29 | 2024-04-20 | Staircase_NTA | 100 | 100 |  | 2024-03-29 | 2024-03-29 | 2024-04-20 | 2024-04-20 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | Staircase & Ramp RCC Works
44506 | NTA_Zone 2 - Super Structure - P3 to P4 - Pour 3 | Complete | Staircase & Ramp RCC Works | 2024-03-29 | 2024-04-20 | Staircase_NTA | 100 | 100 |  | 2024-03-29 | 2024-03-29 | 2024-04-20 | 2024-04-20 | NTA_Zone 2 | Super Structure
44511 |  | Started |  | 2024-03-29 | 2024-06-26 | P4 to P5 | 100 | 80 |  | 2024-03-29 | 2024-03-29 | 2025-11-05
44511 |  | Started |  | 2024-03-29 | 2024-06-26 | P4 to P5 | 100 | 80 |  | 2024-03-29 | 2024-03-29 | 2025-11-05
44511 |  | Started |  | 2024-03-29 | 2024-06-26 | P4 to P5 | 100 | 80 |  | 2024-03-29 | 2024-03-29 | 2025-11-05
44516 |  | Complete |  | 2024-03-29 | 2024-04-26 | Pour 2 (btwn TA & NTA Ramp) | 100 | 100 |  | 2024-03-29 | 2024-03-29 | 2024-04-26 | 2024-04-26
44517 | NTA_Zone 2 - Super Structure - P4 to P5 - Pour 2 | Complete | RCC Works - Vertical | 2024-03-29 | 2024-04-15 | Columns/ Walls_NTA | 100 | 100 |  | 2024-03-29 | 2024-03-29 | 2024-04-15 | 2024-04-15 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
44517 | NTA_Zone 2 - Super Structure - P4 to P5 - Pour 2 | Complete | RCC Works - Vertical | 2024-03-29 | 2024-04-15 | Columns/ Walls_NTA | 100 | 100 |  | 2024-03-29 | 2024-03-29 | 2024-04-15 | 2024-04-15 | NTA_Zone 2 | Super Structure
39394 | Tower A - Super Structure - Core Wall Low Rise L15-16 | Complete | Core Wall RCC Works | 2024-04-01 | 2024-04-03 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-04-01 | 2024-04-01 | 2024-04-03 | 2024-04-03 | Tower A | Super Structure | L15 | RCC Super Structure | Core Wall RCC Works
39836 |  | Complete |  | 2024-04-01 | 2024-04-09 | L11-12 | 100 | 100 |  | 2024-04-01 | 2024-04-01 | 2024-04-09 | 2024-04-09
39836 |  | Complete |  | 2024-04-01 | 2024-04-09 | L11-12 | 100 | 100 |  | 2024-04-01 | 2024-04-01 | 2024-04-09 | 2024-04-09 |  |  |  | Finishes | Gypsum Plastering Works
39837 | Tower A - Super Structure - Core & Outer Slab L11-12 | Complete | RCC Works - Vertical | 2024-04-01 | 2024-04-08 | Outer Columns_TA | 100 | 100 |  | 2024-04-01 | 2024-04-01 | 2024-04-08 | 2024-04-08 | Tower A | Super Structure | L11 | RCC Sub Structure | RCC Works - Vertical
40181 |  | Complete |  | 2024-04-01 | 2024-07-05 | L8-9 | 100 | 100 |  | 2024-04-01 | 2024-04-01 | 2024-07-05 | 2024-07-05
40181 |  | Complete |  | 2024-04-01 | 2024-07-05 | L8-9 | 100 | 100 |  | 2024-04-01 | 2024-04-01 | 2024-07-05 | 2024-07-05 |  |  |  | Finishes | Gypsum Plastering Works
40182 | Tower A - Super Structure - Finishes & MEP - L8 to L9 | Complete | Partition Wall-Blockwork | 2024-04-01 | 2024-04-17 | De-shuttering & Area clearance | 100 | 100 |  | 2024-04-01 | 2024-04-01 | 2024-04-17 | 2024-04-17 | Tower A | Super Structure | L8
44702 |  | Complete |  | 2024-04-01 | 2024-08-29 | Foundation_Tower B | 100 | 100 |  | 2024-04-01 | 2024-04-01 | 2024-08-29 | 2024-08-29
44703 |  | Complete |  | 2024-04-01 | 2024-07-20 | Pour 1A & 2 lift pits | 100 | 100 |  | 2024-04-01 | 2024-04-01 | 2024-07-20 | 2024-07-20
44704 | Tower B - Foundation - Pour 1A | Complete | PCC | 2024-04-01 | 2024-04-03 | PCC & Blockwork for vertical surface | 100 | 100 |  | 2024-04-01 | 2024-04-01 | 2024-04-03 | 2024-04-03 | Tower B | Foundation
44711 |  | Complete |  | 2024-04-01 | 2024-08-10 | Pour 1B lift pit | 100 | 100 |  | 2024-04-01 | 2024-04-01 | 2024-08-10 | 2024-08-10
44712 | Tower B - Foundation - Pour 1B | Complete | PCC | 2024-04-01 | 2024-04-03 | PCC & Blockwork for vertical surface | 100 | 100 |  | 2024-04-01 | 2024-04-01 | 2024-04-03 | 2024-04-03 | Tower B | Foundation
44725 |  | Complete |  | 2024-04-01 | 2024-04-25 | Pour 3 | 100 | 100 |  | 2024-04-01 | 2024-04-01 | 2024-04-25 | 2024-04-25
44726 | Tower B - Foundation - Pour 3 | Complete | PCC | 2024-04-01 | 2024-04-03 | PCC | 100 | 100 |  | 2024-04-01 | 2024-04-01 | 2024-04-03 | 2024-04-03 | Tower B | Foundation
44743 |  | Complete |  | 2024-04-01 | 2024-08-10 | Pour 8 | 100 | 100 |  | 2024-04-01 | 2024-04-01 | 2024-08-10 | 2024-08-10
44744 | Tower B - Foundation - Pour 8 | Complete | PCC | 2024-04-01 | 2024-04-03 | PCC | 100 | 100 |  | 2024-04-01 | 2024-04-01 | 2024-04-03 | 2024-04-03 | Tower B | Foundation
39395 | Tower A - Super Structure - Core Wall Low Rise L15-16 | Complete | Core Wall RCC Works | 2024-04-03 | 2024-04-03 | Casting | 100 | 100 |  | 2024-04-03 | 2024-04-03 | 2024-04-03 | 2024-04-03 | Tower A | Super Structure | L15 | RCC Super Structure | Core Wall RCC Works
39396 | Tower A - Super Structure - Core Wall Low Rise L15-16 | Complete | Core Wall RCC Works | 2024-04-04 | 2024-04-04 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-04-04 | 2024-04-04 | 2024-04-04 | 2024-04-04 | Tower A | Super Structure | L15 | RCC Super Structure | Core Wall RCC Works
39838 | Tower A - Super Structure - Core & Outer Slab L11-12 | Complete | RCC Works - Slab | 2024-04-04 | 2024-04-09 | Outer Slab_TA | 100 | 100 |  | 2024-04-04 | 2024-04-04 | 2024-04-09 | 2024-04-09 | Tower A | Super Structure | L11 | RCC Sub Structure | RCC Works - Slab
44497 |  | Complete |  | 2024-04-04 | 2024-05-15 | Pour 1 (Ramp) | 100 | 100 |  | 2024-04-04 | 2024-04-04 | 2024-05-15 | 2024-05-15
44498 | NTA_Zone 2 - Super Structure - P3 to P4 - Pour 1 | Complete | RCC Works - Vertical | 2024-04-04 | 2024-04-20 | Columns/ Walls_NTA | 100 | 100 |  | 2024-04-04 | 2024-04-04 | 2024-04-20 | 2024-04-20 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
44498 | NTA_Zone 2 - Super Structure - P3 to P4 - Pour 1 | Complete | RCC Works - Vertical | 2024-04-04 | 2024-04-20 | Columns/ Walls_NTA | 100 | 100 |  | 2024-04-04 | 2024-04-04 | 2024-04-20 | 2024-04-20 | NTA_Zone 2 | Super Structure
44499 | NTA_Zone 2 - Super Structure - P3 to P4 - Pour 1 | Complete | Staircase & Ramp RCC Works | 2024-04-04 | 2024-04-26 | Staircase & Ramp_NTA | 100 | 100 |  | 2024-04-04 | 2024-04-04 | 2024-04-26 | 2024-04-26 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | Staircase & Ramp RCC Works
44518 | NTA_Zone 2 - Super Structure - P4 to P5 - Pour 2 | Complete | RCC Works - Slab | 2024-04-04 | 2024-04-26 | Slab_NTA | 100 | 100 |  | 2024-04-04 | 2024-04-04 | 2024-04-26 | 2024-04-26 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Slab
44518 | NTA_Zone 2 - Super Structure - P4 to P5 - Pour 2 | Complete | RCC Works - Slab | 2024-04-04 | 2024-04-26 | Slab_NTA | 100 | 100 |  | 2024-04-04 | 2024-04-04 | 2024-04-26 | 2024-04-26 | NTA_Zone 2 | Super Structure
44705 | Tower B - Foundation - Pour 1A | Complete | HDPE Waterproofing | 2024-04-04 | 2024-04-06 | HDPE waterproofing laying | 100 | 100 |  | 2024-04-04 | 2024-04-04 | 2024-04-06 | 2024-04-06 | Tower B | Foundation
44713 | Tower B - Foundation - Pour 1B | Complete | HDPE Waterproofing | 2024-04-04 | 2024-04-06 | HDPE waterproofing laying | 100 | 100 |  | 2024-04-04 | 2024-04-04 | 2024-04-06 | 2024-04-06 | Tower B | Foundation
44727 | Tower B - Foundation - Pour 3 | Complete | HDPE Waterproofing | 2024-04-04 | 2024-04-06 | HDPE waterproofing laying | 100 | 100 |  | 2024-04-04 | 2024-04-04 | 2024-04-06 | 2024-04-06 | Tower B | Foundation
44745 | Tower B - Foundation - Pour 8 | Complete | HDPE Waterproofing | 2024-04-04 | 2024-04-06 | HDPE waterproofing laying | 100 | 100 |  | 2024-04-04 | 2024-04-04 | 2024-04-06 | 2024-04-06 | Tower B | Foundation
39397 |  | Complete |  | 2024-04-05 | 2024-04-15 | Core Wall L16-17 | 100 | 100 |  | 2024-04-05 | 2024-04-05 | 2024-04-15 | 2024-04-15
39398 | Tower A - Super Structure - Core Wall Low Rise L16-17 | Complete | Core Wall RCC Works | 2024-04-05 | 2024-04-05 | Scaffolding & platform | 100 | 100 |  | 2024-04-05 | 2024-04-05 | 2024-04-05 | 2024-04-05 | Tower A | Super Structure | L16 | RCC Super Structure | Core Wall RCC Works
47997 |  | Complete |  | 2024-04-05 | 2024-05-28 | Demolition + Segregation & Carting Away of Debris | 100 | 100 |  | 2024-04-05 | 2024-04-05 | 2024-05-28 | 2024-05-28
39399 | Tower A - Super Structure - Core Wall Low Rise L16-17 | Complete | Core Wall RCC Works | 2024-04-06 | 2024-04-11 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-04-06 | 2024-04-06 | 2024-04-11 | 2024-04-11 | Tower A | Super Structure | L16 | RCC Super Structure | Core Wall RCC Works
44706 | Tower B - Foundation - Pour 1A | Complete | Lift Pit RCC Works | 2024-04-08 | 2024-04-18 | Lift pit reinf. | 100 | 100 |  | 2024-04-08 | 2024-04-08 | 2024-04-18 | 2024-04-18 | Tower B | Foundation |  | RCC Sub Structure | Lift Pit RCC Works
44714 | Tower B - Foundation - Pour 1B | Complete | Lift Pit RCC Works | 2024-04-08 | 2024-04-10 | Lift pit reinf. | 100 | 100 |  | 2024-04-08 | 2024-04-08 | 2024-04-10 | 2024-04-10 | Tower B | Foundation |  | RCC Sub Structure | Lift Pit RCC Works
44728 | Tower B - Foundation - Pour 3 | Complete | Raft RCC Works | 2024-04-08 | 2024-04-22 | Raft reinf. | 100 | 100 |  | 2024-04-08 | 2024-04-08 | 2024-04-22 | 2024-04-22 | Tower B | Foundation |  | RCC Sub Structure | Raft RCC Works
44746 | Tower B - Foundation - Pour 8 | Complete | Raft RCC Works | 2024-04-08 | 2024-04-22 | Raft reinf. | 100 | 100 |  | 2024-04-08 | 2024-04-08 | 2024-04-22 | 2024-04-22 | Tower B | Foundation |  | RCC Sub Structure | Raft RCC Works
39280 | Tower A - Super Structure - Finishes & MEP | Started |  | 2024-04-09 | 2024-04-18 | Sample Apartment | 100 | 98 | Units | 2024-04-09 | 2024-04-09 | 2025-09-16 |  | Tower A | Super Structure
39400 | Tower A - Super Structure - Core Wall Low Rise L16-17 | Complete | Core Wall RCC Works | 2024-04-10 | 2024-04-12 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-04-10 | 2024-04-10 | 2024-04-12 | 2024-04-12 | Tower A | Super Structure | L16 | RCC Super Structure | Core Wall RCC Works
39839 |  | Complete |  | 2024-04-10 | 2024-04-20 | L12-13 | 100 | 100 |  | 2024-04-10 | 2024-04-10 | 2024-04-20 | 2024-04-20
39839 |  | Complete |  | 2024-04-10 | 2024-04-20 | L12-13 | 100 | 100 |  | 2024-04-10 | 2024-04-10 | 2024-04-20 | 2024-04-20 |  |  |  | Finishes | Gypsum Plastering Works
39840 | Tower A - Super Structure - Core & Outer Slab L12-13 | Complete | RCC Works - Vertical | 2024-04-10 | 2024-04-17 | Outer Columns_TA | 100 | 100 |  | 2024-04-10 | 2024-04-10 | 2024-04-17 | 2024-04-17 | Tower A | Super Structure | L12 | RCC Sub Structure | RCC Works - Vertical
40185 |  | Complete |  | 2024-04-10 | 2024-07-20 | L9-10 | 100 | 100 |  | 2024-04-10 | 2024-04-10 | 2024-07-20 | 2024-07-20
40185 |  | Complete |  | 2024-04-10 | 2024-07-20 | L9-10 | 100 | 100 |  | 2024-04-10 | 2024-04-10 | 2024-07-20 | 2024-07-20 |  |  |  | Finishes | Gypsum Plastering Works
40186 | Tower A - Super Structure - Finishes & MEP - L9 to L10 | Complete | Partition Wall-Blockwork | 2024-04-10 | 2024-04-26 | De-shuttering & Area clearance | 100 | 100 |  | 2024-04-10 | 2024-04-10 | 2024-04-26 | 2024-04-26 | Tower A | Super Structure | L9
44715 | Tower B - Foundation - Pour 1B | Complete | Lift Pit RCC Works | 2024-04-11 | 2024-04-11 | Casting of pit bottom section | 100 | 100 |  | 2024-04-11 | 2024-04-11 | 2024-04-11 | 2024-04-11 | Tower B | Foundation |  | RCC Sub Structure | Lift Pit RCC Works
40163 | Tower A - Super Structure - Finishes & MEP - P3 to P4 | Complete | Partition Wall-Blockwork | 2024-04-12 | 2024-04-29 | Partition Walls | 100 | 100 |  | 2024-04-12 | 2024-04-12 | 2024-04-29 | 2024-04-29 | Tower A | Super Structure
40704 |  | Started |  | 2024-04-06 | 2024-06-22 | P1-2 Level | 100 | 3 |  | 2024-04-12 | 2024-04-12 | 2025-12-19
40719 |  | Started |  | 2024-04-12 | 2024-06-22 | Floor Area | 100 | 4 |  | 2024-04-12 | 2024-04-12 | 2025-11-11
40720 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Complete | Ceiling Painting/ PT Marking - MEP & Finishes | 2024-04-12 | 2024-04-17 | Ceiling Painting/ PT Marking | 100 | 100 |  | 2024-04-12 | 2024-04-12 | 2024-04-17 | 2024-04-17 | Tower A | Super Structure |  | Finishes | Ceiling Painting/ PT Marking
44716 | Tower B - Foundation - Pour 1B | Complete | Lift Pit RCC Works | 2024-04-12 | 2024-04-19 | Reinf. For pit wall section | 100 | 100 |  | 2024-04-12 | 2024-04-12 | 2024-04-19 | 2024-04-19 | Tower B | Foundation |  | RCC Sub Structure | Lift Pit RCC Works
39401 | Tower A - Super Structure - Core Wall Low Rise L16-17 | Complete | Core Wall RCC Works | 2024-04-13 | 2024-04-14 | Casting | 100 | 100 |  | 2024-04-13 | 2024-04-13 | 2024-04-14 | 2024-04-14 | Tower A | Super Structure | L16 | RCC Super Structure | Core Wall RCC Works
39841 | Tower A - Super Structure - Core & Outer Slab L12-13 | Complete | RCC Works - Slab | 2024-04-13 | 2024-04-20 | Outer Slab_TA | 100 | 100 |  | 2024-04-13 | 2024-04-13 | 2024-04-20 | 2024-04-20 | Tower A | Super Structure | L12 | RCC Sub Structure | RCC Works - Slab
39402 | Tower A - Super Structure - Core Wall Low Rise L16-17 | Complete | Core Wall RCC Works | 2024-04-15 | 2024-04-15 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-04-15 | 2024-04-15 | 2024-04-15 | 2024-04-15 | Tower A | Super Structure | L16 | RCC Super Structure | Core Wall RCC Works
39403 |  | Complete |  | 2024-04-16 | 2024-04-25 | Core Wall L17-18 | 100 | 100 |  | 2024-04-16 | 2024-04-16 | 2024-04-25 | 2024-04-25
39404 | Tower A - Super Structure - Core Wall Low Rise L17-18 | Complete | Core Wall RCC Works | 2024-04-16 | 2024-04-16 | Scaffolding & platform | 100 | 100 |  | 2024-04-16 | 2024-04-16 | 2024-04-16 | 2024-04-16 | Tower A | Super Structure | L17 | RCC Super Structure | Core Wall RCC Works
44507 | NTA_Zone 2 - Super Structure - P3 to P4 - Pour 3 | Complete | RCC Works - Slab | 2024-04-16 | 2024-05-09 | Slab_NTA | 100 | 100 |  | 2024-04-16 | 2024-04-16 | 2024-05-09 | 2024-05-09 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Slab
44507 | NTA_Zone 2 - Super Structure - P3 to P4 - Pour 3 | Complete | RCC Works - Slab | 2024-04-16 | 2024-05-09 | Slab_NTA | 100 | 100 |  | 2024-04-16 | 2024-04-16 | 2024-05-09 | 2024-05-09 | NTA_Zone 2 | Super Structure
39405 | Tower A - Super Structure - Core Wall Low Rise L17-18 | Complete | Core Wall RCC Works | 2024-04-17 | 2024-04-22 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-04-17 | 2024-04-17 | 2024-04-22 | 2024-04-22 | Tower A | Super Structure | L17 | RCC Super Structure | Core Wall RCC Works
44707 | Tower B - Foundation - Pour 1A | Complete | Lift Pit RCC Works | 2024-04-19 | 2024-04-19 | Casting of pit bottom section | 100 | 100 |  | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-19 | Tower B | Foundation |  | RCC Sub Structure | Lift Pit RCC Works
39406 | Tower A - Super Structure - Core Wall Low Rise L17-18 | Complete | Core Wall RCC Works | 2024-04-20 | 2024-04-23 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-04-20 | 2024-04-20 | 2024-04-23 | 2024-04-23 | Tower A | Super Structure | L17 | RCC Super Structure | Core Wall RCC Works
44708 | Tower B - Foundation - Pour 1A | Complete | Lift Pit RCC Works | 2024-04-20 | 2024-05-02 | Reinf. For pit wall section | 100 | 100 |  | 2024-04-20 | 2024-04-20 | 2024-05-02 | 2024-05-02 | Tower B | Foundation |  | RCC Sub Structure | Lift Pit RCC Works
44717 | Tower B - Foundation - Pour 1B | Complete | Lift Pit RCC Works | 2024-04-20 | 2024-06-29 | Fwk for pit wall | 100 | 100 |  | 2024-04-20 | 2024-04-20 | 2024-06-29 | 2024-06-29 | Tower B | Foundation |  | RCC Sub Structure | Lift Pit RCC Works
39842 |  | Complete |  | 2024-04-22 | 2024-04-30 | L13-14 | 100 | 100 |  | 2024-04-22 | 2024-04-22 | 2024-04-30 | 2024-04-30
39842 |  | Complete |  | 2024-04-22 | 2024-04-30 | L13-14 | 100 | 100 |  | 2024-04-22 | 2024-04-22 | 2024-04-30 | 2024-04-30 |  |  |  | Finishes | Gypsum Plastering Works
39843 | Tower A - Super Structure - Core & Outer Slab L13-14 | Complete | RCC Works - Vertical | 2024-04-22 | 2024-04-29 | Outer Columns_TA | 100 | 100 |  | 2024-04-22 | 2024-04-22 | 2024-04-29 | 2024-04-29 | Tower A | Super Structure | L13 | RCC Sub Structure | RCC Works - Vertical
40189 |  | Complete |  | 2024-04-22 | 2024-08-01 | L10-11 | 100 | 100 |  | 2024-04-22 | 2024-04-22 | 2024-08-01 | 2024-08-01
40189 |  | Complete |  | 2024-04-22 | 2024-08-01 | L10-11 | 100 | 100 |  | 2024-04-22 | 2024-04-22 | 2024-08-01 | 2024-08-01 |  |  |  | Finishes | Gypsum Plastering Works
40190 | Tower A - Super Structure - Finishes & MEP - L10 to L11 | Complete | Partition Wall-Blockwork | 2024-04-22 | 2024-05-09 | De-shuttering & Area clearance | 100 | 100 |  | 2024-04-22 | 2024-04-22 | 2024-05-09 | 2024-05-09 | Tower A | Super Structure | L10
44500 | NTA_Zone 2 - Super Structure - P3 to P4 - Pour 1 | Complete | RCC Works - Slab | 2024-04-22 | 2024-05-15 | Slab_NTA | 100 | 100 |  | 2024-04-22 | 2024-04-22 | 2024-05-15 | 2024-05-15 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Slab
44500 | NTA_Zone 2 - Super Structure - P3 to P4 - Pour 1 | Complete | RCC Works - Slab | 2024-04-22 | 2024-05-15 | Slab_NTA | 100 | 100 |  | 2024-04-22 | 2024-04-22 | 2024-05-15 | 2024-05-15 | NTA_Zone 2 | Super Structure
44729 | Tower B - Foundation - Pour 3 | Complete | Raft RCC Works | 2024-04-23 | 2024-04-24 | Fwk fix | 100 | 100 |  | 2024-04-23 | 2024-04-23 | 2024-04-24 | 2024-04-24 | Tower B | Foundation |  | RCC Sub Structure | Raft RCC Works
44747 | Tower B - Foundation - Pour 8 | Complete | Raft RCC Works | 2024-04-23 | 2024-04-24 | Fwk fix | 100 | 100 |  | 2024-04-23 | 2024-04-23 | 2024-04-24 | 2024-04-24 | Tower B | Foundation |  | RCC Sub Structure | Raft RCC Works
39407 | Tower A - Super Structure - Core Wall Low Rise L17-18 | Complete | Core Wall RCC Works | 2024-04-24 | 2024-04-24 | Casting | 100 | 100 |  | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2024-04-24 | Tower A | Super Structure | L17 | RCC Super Structure | Core Wall RCC Works
40731 |  | Started |  | 2024-04-24 | 2024-07-04 | P2-3 Level | 100 | 11 |  | 2024-04-24 | 2024-04-24 | 2026-01-07
40732 |  | Started |  | 2024-04-24 | 2024-06-13 | Lobby/ Common Area | 100 | 9 |  | 2024-04-24 | 2025-04-30 | 2026-01-07
40733 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Started | FPS 1st Fix - MEP & Finishes | 2024-04-24 | 2024-05-02 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 10 | Units | 2024-04-24 | 2025-04-30 | 2025-11-25 |  | Tower A | Super Structure |  | MEP | FPS 1st Fix - MEP & Finishes
40746 |  | Started |  | 2024-04-24 | 2024-07-04 | Floor Area | 100 | 13 |  | 2024-04-24 | 2024-04-24 | 2025-11-11
40747 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Complete | Ceiling Painting/ PT Marking - MEP & Finishes | 2024-04-24 | 2024-04-29 | Ceiling Painting/ PT Marking | 100 | 100 |  | 2024-04-24 | 2024-04-24 | 2024-04-29 | 2024-04-29 | Tower A | Super Structure |  | Finishes | Ceiling Painting/ PT Marking
39408 | Tower A - Super Structure - Core Wall Low Rise L17-18 | Complete | Core Wall RCC Works | 2024-04-25 | 2024-04-25 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-04-25 | 2024-04-25 | 2024-04-25 | 2024-04-25 | Tower A | Super Structure | L17 | RCC Super Structure | Core Wall RCC Works
39844 | Tower A - Super Structure - Core & Outer Slab L13-14 | Complete | RCC Works - Slab | 2024-04-25 | 2024-04-30 | Outer Slab_TA | 100 | 100 |  | 2024-04-25 | 2024-04-25 | 2024-04-30 | 2024-04-30 | Tower A | Super Structure | L13 | RCC Sub Structure | RCC Works - Slab
44730 | Tower B - Foundation - Pour 3 | Complete | Raft RCC Works | 2024-04-25 | 2024-04-25 | Checking & casting | 100 | 100 |  | 2024-04-25 | 2024-04-25 | 2024-04-25 | 2024-04-25 | Tower B | Foundation |  | RCC Sub Structure | Raft RCC Works
39409 |  | Complete |  | 2024-04-26 | 2024-05-06 | Core Wall L18-19 | 100 | 100 |  | 2024-04-26 | 2024-04-26 | 2024-05-06 | 2024-05-06
39410 | Tower A - Super Structure - Core Wall Low Rise L18-19 | Complete | Core Wall RCC Works | 2024-04-26 | 2024-04-26 | Scaffolding & platform | 100 | 100 |  | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-26 | Tower A | Super Structure | L18 | RCC Super Structure | Core Wall RCC Works
39411 | Tower A - Super Structure - Core Wall Low Rise L18-19 | Complete | Core Wall RCC Works | 2024-04-27 | 2024-05-02 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-04-27 | 2024-04-27 | 2024-05-02 | 2024-05-02 | Tower A | Super Structure | L18 | RCC Super Structure | Core Wall RCC Works
44528 | NTA_Zone 2 - Sub Structure - B2 to B1 | Started | MEP 1st Fix Works | 2024-04-27 | 2024-05-11 | B2 to B1 | 100 | 80 |  | 2024-04-27 | 2024-04-27 | 2025-10-10 |  | NTA_Zone 2 | Sub Structure | B2
44528 | NTA_Zone 2 - Sub Structure - B2 to B1 | Started | MEP 1st Fix Works | 2024-04-27 | 2024-05-11 | B2 to B1 | 100 | 80 |  | 2024-04-27 | 2024-04-27 | 2025-10-10 |  | NTA_Zone 2 | Sub Structure | B2
44528 | NTA_Zone 2 - Sub Structure - B2 to B1 | Started | MEP 1st Fix Works | 2024-04-27 | 2024-05-11 | B2 to B1 | 100 | 80 |  | 2024-04-27 | 2024-04-27 | 2025-10-10 |  | NTA_Zone 2 | Sub Structure | B2
39412 | Tower A - Super Structure - Core Wall Low Rise L18-19 | Complete | Core Wall RCC Works | 2024-04-30 | 2024-05-03 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-04-30 | 2024-04-30 | 2024-05-03 | 2024-05-03 | Tower A | Super Structure | L18 | RCC Super Structure | Core Wall RCC Works
40164 | Tower A - Super Structure - Finishes & MEP - P3 to P4 | Complete | Partition Wall-Blockwork | 2024-04-30 | 2024-05-11 | Staircase Area | 100 | 100 |  | 2024-04-30 | 2024-04-30 | 2024-05-11 | 2024-05-11 | Tower A | Super Structure
40167 | Tower A - Super Structure - Finishes & MEP - P4 to P5 | Started | Partition Wall-Blockwork | 2024-04-30 | 2024-05-10 | Partition Walls | 100 | 50 |  | 2024-04-30 | 2024-04-30 | 2025-09-20 |  | Tower A | Super Structure
40748 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Started | FPS 1st Fix - MEP & Finishes | 2024-04-30 | 2024-05-23 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 15 | Units | 2024-04-30 | 2025-04-30 | 2025-10-01 |  | Tower A | Super Structure |  | MEP | FPS 1st Fix - MEP & Finishes
39845 |  | Complete |  | 2024-05-02 | 2024-05-10 | L14-15 | 100 | 100 |  | 2024-05-02 | 2024-05-02 | 2024-05-10 | 2024-05-10
39845 |  | Complete |  | 2024-05-02 | 2024-05-10 | L14-15 | 100 | 100 |  | 2024-05-02 | 2024-05-02 | 2024-05-10 | 2024-05-10 |  |  |  | Finishes | Gypsum Plastering Works
39846 | Tower A - Super Structure - Core & Outer Slab L14-15 | Complete | RCC Works - Vertical | 2024-05-02 | 2024-05-09 | Outer Columns_TA | 100 | 100 |  | 2024-05-02 | 2024-05-02 | 2024-05-09 | 2024-05-09 | Tower A | Super Structure | L14 | RCC Sub Structure | RCC Works - Vertical
40193 |  | Complete |  | 2024-05-02 | 2024-08-13 | L11-12 | 100 | 100 |  | 2024-05-02 | 2024-05-02 | 2024-08-13 | 2024-08-13
40193 |  | Complete |  | 2024-05-02 | 2024-08-13 | L11-12 | 100 | 100 |  | 2024-05-02 | 2024-05-02 | 2024-08-13 | 2024-08-13 |  |  |  | Finishes | Gypsum Plastering Works
40194 | Tower A - Super Structure - Finishes & MEP - L11 to L12 | Complete | Partition Wall-Blockwork | 2024-05-02 | 2024-05-18 | De-shuttering & Area clearance | 100 | 100 |  | 2024-05-02 | 2024-05-02 | 2024-05-18 | 2024-05-18 | Tower A | Super Structure | L11
44709 | Tower B - Foundation - Pour 1A | Complete | Lift Pit RCC Works | 2024-05-03 | 2024-05-04 | Fwk for pit wall | 100 | 100 |  | 2024-05-03 | 2024-05-03 | 2024-05-04 | 2024-05-04 | Tower B | Foundation |  | RCC Sub Structure | Lift Pit RCC Works
39413 | Tower A - Super Structure - Core Wall Low Rise L18-19 | Complete | Core Wall RCC Works | 2024-05-04 | 2024-05-04 | Casting | 100 | 100 |  | 2024-05-04 | 2024-05-04 | 2024-05-04 | 2024-05-04 | Tower A | Super Structure | L18 | RCC Super Structure | Core Wall RCC Works
39414 | Tower A - Super Structure - Core Wall Low Rise L18-19 | Complete | Core Wall RCC Works | 2024-05-06 | 2024-05-06 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-05-06 | 2024-05-06 | 2024-05-06 | 2024-05-06 | Tower A | Super Structure | L18 | RCC Super Structure | Core Wall RCC Works
39847 | Tower A - Super Structure - Core & Outer Slab L14-15 | Complete | RCC Works - Slab | 2024-05-06 | 2024-05-10 | Outer Slab_TA | 100 | 100 |  | 2024-05-06 | 2024-05-06 | 2024-05-10 | 2024-05-10 | Tower A | Super Structure | L14 | RCC Sub Structure | RCC Works - Slab
39415 |  | Complete |  | 2024-05-07 | 2024-05-13 | Core Wall L19-20 | 100 | 100 |  | 2024-05-07 | 2024-05-07 | 2024-05-13 | 2024-05-13
39416 | Tower A - Super Structure - Core Wall Low Rise L19-20 | Complete | Core Wall RCC Works | 2024-05-07 | 2024-05-07 | Scaffolding & platform | 100 | 100 |  | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-05-07 | Tower A | Super Structure | L19 | RCC Super Structure | Core Wall RCC Works
39417 | Tower A - Super Structure - Core Wall Low Rise L19-20 | Complete | Core Wall RCC Works | 2024-05-08 | 2024-05-10 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-05-08 | 2024-05-08 | 2024-05-10 | 2024-05-10 | Tower A | Super Structure | L19 | RCC Super Structure | Core Wall RCC Works
39418 | Tower A - Super Structure - Core Wall Low Rise L19-20 | Complete | Core Wall RCC Works | 2024-05-09 | 2024-05-11 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-05-09 | 2024-05-09 | 2024-05-11 | 2024-05-11 | Tower A | Super Structure | L19 | RCC Super Structure | Core Wall RCC Works
39188 |  | Started |  | 2024-05-10 | 2026-03-03 | New Installations (MEP) | 100 | 53 |  | 2024-05-10 | 2024-05-10 | 2026-09-23
39189 |  | Started |  | 2024-05-10 | 2025-04-24 | Tranformer Works (TATA Power) | 100 | 74 |  | 2024-05-10 | 2024-05-10 | 2025-11-19
39190 |  | Complete |  | 2024-05-10 | 2024-05-17 | Shop Drawing Submission | 100 | 100 |  | 2024-05-10 | 2024-05-10 | 2024-05-17 | 2024-05-17
39200 |  | Started |  | 2024-05-10 | 2025-10-14 | Electrical Works | 100 | 50 |  | 2024-05-10 | 2024-05-10 | 2026-08-26
39201 |  | Complete |  | 2024-05-10 | 2024-06-26 | Electrical Due Diligence Report | 100 | 100 |  | 2024-05-10 | 2024-05-10 | 2024-06-26 | 2024-06-26
39202 |  | Complete |  | 2024-05-10 | 2024-05-25 | Electrical - Shop Drawings and Material Submissions | 100 | 100 |  | 2024-05-10 | 2024-05-10 | 2024-05-25 | 2024-05-25
39213 |  | Started |  | 2024-05-10 | 2026-03-03 | DG Works | 100 | 29 |  | 2024-05-10 | 2024-05-10 | 2026-09-23
39214 |  | Complete |  | 2024-05-10 | 2024-06-26 | DG Due Diligence Report | 100 | 100 |  | 2024-05-10 | 2024-05-10 | 2024-06-26 | 2024-06-26
39215 |  | Complete |  | 2024-05-10 | 2024-05-25 | DG - Shop Drawings and Material Submissions | 100 | 100 |  | 2024-05-10 | 2024-05-10 | 2024-05-25 | 2024-05-25
39227 |  | Started |  | 2024-05-10 | 2025-11-11 | HVAC Works | 100 | 55 |  | 2024-05-10 | 2024-05-10 | 2026-02-25
39228 |  | Complete |  | 2024-05-10 | 2024-06-26 | HVAC Due Diligence Report | 100 | 100 |  | 2024-05-10 | 2024-05-10 | 2024-06-26 | 2024-06-26
39229 |  | Complete |  | 2024-05-10 | 2024-05-25 | HVAC - Shop Drawings and Material Submissions | 100 | 100 |  | 2024-05-10 | 2024-05-10 | 2024-05-25 | 2024-05-25
44519 |  | Complete |  | 2024-05-10 | 2024-06-20 | Pour 3 (Grid PA-A to PA-D) | 100 | 100 |  | 2024-05-10 | 2024-05-10 | 2024-06-20 | 2024-06-20
44520 | NTA_Zone 2 - Super Structure - P4 to P5 - Pour 3 | Complete | RCC Works - Vertical | 2024-05-10 | 2024-05-27 | Columns/ Walls_NTA | 100 | 100 |  | 2024-05-10 | 2024-05-10 | 2024-05-27 | 2024-05-27 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
44520 | NTA_Zone 2 - Super Structure - P4 to P5 - Pour 3 | Complete | RCC Works - Vertical | 2024-05-10 | 2024-05-27 | Columns/ Walls_NTA | 100 | 100 |  | 2024-05-10 | 2024-05-10 | 2024-05-27 | 2024-05-27 | NTA_Zone 2 | Super Structure
44521 | NTA_Zone 2 - Super Structure - P4 to P5 - Pour 3 | Complete | Staircase & Ramp RCC Works | 2024-05-10 | 2024-06-01 | Staircase_NTA | 100 | 100 |  | 2024-05-10 | 2024-05-10 | 2024-06-01 | 2024-06-01 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | Staircase & Ramp RCC Works
44521 | NTA_Zone 2 - Super Structure - P4 to P5 - Pour 3 | Complete | Staircase & Ramp RCC Works | 2024-05-10 | 2024-06-01 | Staircase_NTA | 100 | 100 |  | 2024-05-10 | 2024-05-10 | 2024-06-01 | 2024-06-01 | NTA_Zone 2 | Super Structure
39848 |  | Complete |  | 2024-05-11 | 2024-05-18 | L15-16 | 100 | 100 |  | 2024-05-11 | 2024-05-11 | 2024-05-18 | 2024-05-18
39848 |  | Complete |  | 2024-05-11 | 2024-05-18 | L15-16 | 100 | 100 |  | 2024-05-11 | 2024-05-11 | 2024-05-18 | 2024-05-18 |  |  |  | Finishes | Gypsum Plastering Works
39849 | Tower A - Super Structure - Core & Outer Slab L15-16 | Complete | RCC Works - Vertical | 2024-05-11 | 2024-05-16 | Outer Columns_TA | 100 | 100 |  | 2024-05-11 | 2024-05-11 | 2024-05-16 | 2024-05-16 | Tower A | Super Structure | L15 | RCC Sub Structure | RCC Works - Vertical
40197 |  | Complete |  | 2024-05-11 | 2024-08-29 | L12-13 | 100 | 100 |  | 2024-05-11 | 2024-05-11 | 2024-08-29 | 2024-08-29
40197 |  | Complete |  | 2024-05-11 | 2024-08-29 | L12-13 | 100 | 100 |  | 2024-05-11 | 2024-05-11 | 2024-08-29 | 2024-08-29 |  |  |  | Finishes | Gypsum Plastering Works
40198 | Tower A - Super Structure - Finishes & MEP - L12 to L13 | Complete | Partition Wall-Blockwork | 2024-05-11 | 2024-05-28 | De-shuttering & Area clearance | 100 | 100 |  | 2024-05-11 | 2024-05-11 | 2024-05-28 | 2024-05-28 | Tower A | Super Structure | L12
40866 |  | Started |  | 2024-02-19 | 2026-04-28 | Shaft MEP Works | 100 | 1 |  | 2024-05-11 | 2025-05-31 | 2026-06-04
40885 |  | Started |  | 2024-05-11 | 2024-09-10 | L7-L15 | 100 | 3 |  | 2024-05-11 | 2025-05-31 | 2025-12-29
40885 |  | Started |  | 2024-05-11 | 2024-09-10 | L7-L15 | 100 | 3 |  | 2024-05-11 | 2025-05-31 | 2025-12-29
40886 | Tower A - Super Structure - Finishes & MEP - L7 to L15 | Complete |  | 2024-05-11 | 2024-06-03 | FHR Shaft Risers | 100 | 100 |  | 2024-05-11 | 2025-05-31 | 2024-06-03 | 2025-05-31 | Tower A | Super Structure | L7
40888 | Tower A - Super Structure - Finishes & MEP - L7 to L15 | Started |  | 2024-05-11 | 2024-07-03 | Domestic Water & Flushing Riser in Plumbing Shaft | 100 | 0 |  | 2024-05-11 | 2025-06-01 | 2025-11-05 |  | Tower A | Super Structure | L7
39419 | Tower A - Super Structure - Core Wall Low Rise L19-20 | Milestone Started | Core Wall RCC Works | 2024-05-12 |  | Casting | 100 | 100 |  | 2024-05-12 | 2024-05-13 |  |  | Tower A | Super Structure | L19 | RCC Super Structure | Core Wall RCC Works
39420 | Tower A - Super Structure - Core Wall Low Rise L19-20 | Complete | Core Wall RCC Works | 2024-05-13 | 2024-05-13 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-05-13 | 2024-05-13 | 2024-05-13 | 2024-05-13 | Tower A | Super Structure | L19 | RCC Super Structure | Core Wall RCC Works
39421 |  | Complete |  | 2024-05-14 | 2024-05-22 | Core Wall L20-21 | 100 | 100 |  | 2024-05-14 | 2024-05-14 | 2024-05-22 | 2024-05-22
39422 | Tower A - Super Structure - Core Wall Low Rise L20-21 | Complete | Core Wall RCC Works | 2024-05-14 | 2024-05-14 | Scaffolding & platform | 100 | 100 |  | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2024-05-14 | Tower A | Super Structure | L20 | RCC Super Structure | Core Wall RCC Works
39423 | Tower A - Super Structure - Core Wall Low Rise L20-21 | Complete | Core Wall RCC Works | 2024-05-15 | 2024-05-17 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-05-15 | 2024-05-15 | 2024-05-17 | 2024-05-17 | Tower A | Super Structure | L20 | RCC Super Structure | Core Wall RCC Works
39850 | Tower A - Super Structure - Core & Outer Slab L15-16 | Complete | RCC Works - Slab | 2024-05-15 | 2024-05-18 | Outer Slab_TA | 100 | 100 |  | 2024-05-15 | 2024-05-15 | 2024-05-18 | 2024-05-18 | Tower A | Super Structure | L15 | RCC Sub Structure | RCC Works - Slab
44761 |  | Complete |  | 2024-05-15 | 2025-02-18 | Sub-Structure_B (Zone 3) | 100 | 100 |  | 2024-05-15 | 2024-05-15 | 2025-02-18 | 2025-02-18
44763 |  | Complete |  | 2024-05-15 | 2024-10-29 | B3 to B2 | 100 | 100 |  | 2024-05-15 | 2024-05-15 | 2024-10-29 | 2024-10-29
44763 |  | Complete |  | 2024-05-15 | 2024-10-29 | B3 to B2 | 100 | 100 |  | 2024-05-15 | 2024-05-15 | 2024-10-29 | 2024-10-29
44763 |  | Complete |  | 2024-05-15 | 2024-10-29 | B3 to B2 | 100 | 100 |  | 2024-05-15 | 2024-05-15 | 2024-10-29 | 2024-10-29
44775 |  | Complete |  | 2024-05-15 | 2024-07-30 | Pour 3_B3 to B2 | 100 | 100 |  | 2024-05-15 | 2024-05-15 | 2024-07-30 | 2024-07-30
44776 | Tower B - Sub Structure - B3 to B2 - Pour 3 | Complete | RCC Works - Vertical | 2024-05-15 | 2024-05-22 | Col/ Wall Reinf. | 100 | 100 |  | 2024-05-15 | 2024-05-15 | 2024-05-22 | 2024-05-22 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
44776 | Tower B - Sub Structure - B3 to B2 - Pour 3 | Complete | RCC Works - Vertical | 2024-05-15 | 2024-05-22 | Col/ Wall Reinf. | 100 | 100 |  | 2024-05-15 | 2024-05-15 | 2024-05-22 | 2024-05-22 | Tower B | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
44777 | Tower B - Sub Structure - B3 to B2 - Pour 3 | Complete | RCC Works - Vertical | 2024-05-15 | 2024-05-25 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-05-15 | 2024-05-15 | 2024-05-25 | 2024-05-25 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
44777 | Tower B - Sub Structure - B3 to B2 - Pour 3 | Complete | RCC Works - Vertical | 2024-05-15 | 2024-05-25 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-05-15 | 2024-05-15 | 2024-05-25 | 2024-05-25 | Tower B | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
39424 | Tower A - Super Structure - Core Wall Low Rise L20-21 | Complete | Core Wall RCC Works | 2024-05-16 | 2024-05-18 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-05-16 | 2024-05-16 | 2024-05-18 | 2024-05-18 | Tower A | Super Structure | L20 | RCC Super Structure | Core Wall RCC Works
44512 |  | Complete |  | 2024-05-16 | 2024-06-26 | Pour 1 (Ramp) | 100 | 100 |  | 2024-05-16 | 2024-05-16 | 2024-06-26 | 2024-06-26
44513 | NTA_Zone 2 - Super Structure - P4 to P5 - Pour 1 | Complete | RCC Works - Vertical | 2024-05-16 | 2024-06-01 | Columns/ Walls_NTA | 100 | 100 |  | 2024-05-16 | 2024-05-16 | 2024-06-01 | 2024-06-01 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
44513 | NTA_Zone 2 - Super Structure - P4 to P5 - Pour 1 | Complete | RCC Works - Vertical | 2024-05-16 | 2024-06-01 | Columns/ Walls_NTA | 100 | 100 |  | 2024-05-16 | 2024-05-16 | 2024-06-01 | 2024-06-01 | NTA_Zone 2 | Super Structure
44514 | NTA_Zone 2 - Super Structure - P4 to P5 - Pour 1 | Complete | Staircase & Ramp RCC Works | 2024-05-16 | 2024-06-07 | Staircase & Ramp_NTA | 100 | 100 |  | 2024-05-16 | 2024-05-16 | 2024-06-07 | 2024-06-07 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | Staircase & Ramp RCC Works
44719 |  | Complete |  | 2024-05-16 | 2024-06-08 | Pour 2 | 100 | 100 |  | 2024-05-16 | 2024-05-16 | 2024-06-08 | 2024-06-08
44720 | Tower B - Foundation - Pour 2 | Complete | PCC | 2024-05-16 | 2024-05-18 | PCC | 100 | 100 |  | 2024-05-16 | 2024-05-16 | 2024-05-18 | 2024-05-18 | Tower B | Foundation
44778 | Tower B - Sub Structure - B3 to B2 - Pour 3 | Complete | RCC Works - Vertical | 2024-05-17 | 2024-05-28 | Col/ Wall Casting | 100 | 100 |  | 2024-05-17 | 2024-05-17 | 2024-05-28 | 2024-05-28 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
44778 | Tower B - Sub Structure - B3 to B2 - Pour 3 | Complete | RCC Works - Vertical | 2024-05-17 | 2024-05-28 | Col/ Wall Casting | 100 | 100 |  | 2024-05-17 | 2024-05-17 | 2024-05-28 | 2024-05-28 | Tower B | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
39191 |  | Complete |  | 2024-05-18 | 2024-06-03 | Shop Drawing Approval | 100 | 100 |  | 2024-05-18 | 2024-05-18 | 2024-06-03 | 2024-06-03
40758 |  | Started |  | 2024-05-13 | 2024-10-01 | P3-4 Level | 100 | 36 |  | 2024-05-18 | 2025-05-15 | 2026-01-15
40773 |  | Started |  | 2024-05-13 | 2024-10-01 | Floor Area | 100 | 41 |  | 2024-05-18 | 2025-05-15 | 2026-01-09
40775 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Started | FPS 1st Fix - MEP & Finishes | 2024-05-18 | 2024-06-10 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 56 | Units | 2024-05-18 | 2025-05-15 | 2025-09-27 |  | Tower A | Super Structure |  | MEP | FPS 1st Fix - MEP & Finishes
39851 |  | Complete |  | 2024-05-20 | 2024-05-26 | L16-17 | 100 | 100 |  | 2024-05-20 | 2024-05-20 | 2024-05-26 | 2024-05-26
39851 |  | Complete |  | 2024-05-20 | 2024-05-26 | L16-17 | 100 | 100 |  | 2024-05-20 | 2024-05-20 | 2024-05-26 | 2024-05-26 |  |  |  | Finishes | Gypsum Plastering Works
39852 | Tower A - Super Structure - Core & Outer Slab L16-17 | Complete | RCC Works - Vertical | 2024-05-20 | 2024-05-24 | Outer Columns_TA | 100 | 100 |  | 2024-05-20 | 2024-05-20 | 2024-05-24 | 2024-05-24 | Tower A | Super Structure | L16 | RCC Sub Structure | RCC Works - Vertical
40201 |  | Complete |  | 2024-05-20 | 2024-09-07 | L13-14 | 100 | 100 |  | 2024-05-20 | 2024-05-20 | 2024-09-07 | 2024-09-07
40201 |  | Complete |  | 2024-05-20 | 2024-09-07 | L13-14 | 100 | 100 |  | 2024-05-20 | 2024-05-20 | 2024-09-07 | 2024-09-07 |  |  |  | Finishes | Gypsum Plastering Works
40202 | Tower A - Super Structure - Finishes & MEP - L13 to L14 | Complete | Partition Wall-Blockwork | 2024-05-20 | 2024-06-05 | De-shuttering & Area clearance | 100 | 100 |  | 2024-05-20 | 2024-05-20 | 2024-06-05 | 2024-06-05 | Tower A | Super Structure | L13
44721 | Tower B - Foundation - Pour 2 | Complete | HDPE Waterproofing | 2024-05-20 | 2024-05-22 | HDPE waterproofing laying | 100 | 100 |  | 2024-05-20 | 2024-05-20 | 2024-05-22 | 2024-05-22 | Tower B | Foundation
44779 | Tower B - Sub Structure - B3 to B2 - Pour 3 | Complete | RCC Works - Slab | 2024-05-20 | 2024-06-01 | Slab & Staircase Fwk. | 100 | 100 |  | 2024-05-20 | 2024-05-20 | 2024-06-01 | 2024-06-01 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
39425 | Tower A - Super Structure - Core Wall Low Rise L20-21 | Complete | Core Wall RCC Works | 2024-05-21 | 2024-05-21 | Casting | 100 | 100 |  | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2024-05-21 | Tower A | Super Structure | L20 | RCC Super Structure | Core Wall RCC Works
39853 | Tower A - Super Structure - Core & Outer Slab L16-17 | Complete | RCC Works - Slab | 2024-05-21 | 2024-05-26 | Outer Slab_TA | 100 | 100 |  | 2024-05-21 | 2024-05-21 | 2024-05-26 | 2024-05-26 | Tower A | Super Structure | L16 | RCC Sub Structure | RCC Works - Slab
39426 | Tower A - Super Structure - Core Wall Low Rise L20-21 | Complete | Core Wall RCC Works | 2024-05-22 | 2024-05-22 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-05-22 | 2024-05-22 | 2024-05-22 | 2024-05-22 | Tower A | Super Structure | L20 | RCC Super Structure | Core Wall RCC Works
39427 |  | Complete |  | 2024-05-23 | 2024-05-31 | Core Wall L21-22 | 100 | 100 |  | 2024-05-23 | 2024-05-23 | 2024-05-31 | 2024-05-31
39428 | Tower A - Super Structure - Core Wall Low Rise L21-22 | Complete | Core Wall RCC Works | 2024-05-23 | 2024-05-23 | Scaffolding & platform | 100 | 100 |  | 2024-05-23 | 2024-05-23 | 2024-05-23 | 2024-05-23 | Tower A | Super Structure | L21 | RCC Super Structure | Core Wall RCC Works
44722 | Tower B - Foundation - Pour 2 | Complete | Raft RCC Works | 2024-05-23 | 2024-06-06 | Raft reinf. | 100 | 100 |  | 2024-05-23 | 2024-05-23 | 2024-06-06 | 2024-06-06 | Tower B | Foundation |  | RCC Sub Structure | Raft RCC Works
39429 | Tower A - Super Structure - Core Wall Low Rise L21-22 | Complete | Core Wall RCC Works | 2024-05-24 | 2024-05-27 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-05-24 | 2024-05-24 | 2024-05-27 | 2024-05-27 | Tower A | Super Structure | L21 | RCC Super Structure | Core Wall RCC Works
39430 | Tower A - Super Structure - Core Wall Low Rise L21-22 | Complete | Core Wall RCC Works | 2024-05-25 | 2024-05-28 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-05-25 | 2024-05-25 | 2024-05-28 | 2024-05-28 | Tower A | Super Structure | L21 | RCC Super Structure | Core Wall RCC Works
39203 |  | Complete |  | 2024-05-27 | 2024-07-01 | Electrical - Shop Drawings and Material Approvals | 100 | 100 |  | 2024-05-27 | 2024-05-27 | 2024-07-01 | 2024-07-01
39216 |  | Complete |  | 2024-05-27 | 2024-07-01 | DG - Shop Drawings and Material Approvals | 100 | 100 |  | 2024-05-27 | 2024-05-27 | 2024-07-01 | 2024-07-01
39230 |  | Complete |  | 2024-05-27 | 2024-07-01 | HVAC - Shop Drawings and Material Approvals | 100 | 100 |  | 2024-05-27 | 2024-05-27 | 2024-07-01 | 2024-07-01
39854 |  | Complete |  | 2024-05-27 | 2024-06-02 | L17-18 | 100 | 100 |  | 2024-05-27 | 2024-05-27 | 2024-06-02 | 2024-06-02
39854 |  | Complete |  | 2024-05-27 | 2024-06-02 | L17-18 | 100 | 100 |  | 2024-05-27 | 2024-05-27 | 2024-06-02 | 2024-06-02 |  |  |  | Finishes | Gypsum Plastering Works
39855 | Tower A - Super Structure - Core & Outer Slab L17-18 | Complete | RCC Works - Vertical | 2024-05-27 | 2024-06-01 | Outer Columns_TA | 100 | 100 |  | 2024-05-27 | 2024-05-27 | 2024-06-01 | 2024-06-01 | Tower A | Super Structure | L17 | RCC Sub Structure | RCC Works - Vertical
40205 |  | Complete |  | 2024-05-27 | 2024-09-16 | L14-15 | 100 | 100 |  | 2024-05-27 | 2024-05-27 | 2024-09-16 | 2024-09-16
40205 |  | Complete |  | 2024-05-27 | 2024-09-16 | L14-15 | 100 | 100 |  | 2024-05-27 | 2024-05-27 | 2024-09-16 | 2024-09-16 |  |  |  | Finishes | Gypsum Plastering Works
40206 | Tower A - Super Structure - Finishes & MEP - L14 to L15 | Complete | Partition Wall-Blockwork | 2024-05-27 | 2024-06-12 | De-shuttering & Area clearance | 100 | 100 |  | 2024-05-27 | 2024-05-27 | 2024-06-12 | 2024-06-12 | Tower A | Super Structure | L14
44522 | NTA_Zone 2 - Super Structure - P4 to P5 - Pour 3 | Complete | RCC Works - Slab | 2024-05-28 | 2024-06-20 | Slab_NTA | 100 | 100 |  | 2024-05-28 | 2024-05-28 | 2024-06-20 | 2024-06-20 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Slab
44522 | NTA_Zone 2 - Super Structure - P4 to P5 - Pour 3 | Complete | RCC Works - Slab | 2024-05-28 | 2024-06-20 | Slab_NTA | 100 | 100 |  | 2024-05-28 | 2024-05-28 | 2024-06-20 | 2024-06-20 | NTA_Zone 2 | Super Structure
44749 |  | Complete |  | 2024-05-28 | 2024-06-22 | Pour 5 | 100 | 100 |  | 2024-05-28 | 2024-05-28 | 2024-06-22 | 2024-06-22
44750 | Tower B - Foundation - Pour 5 | Complete | PCC | 2024-05-28 | 2024-05-30 | PCC | 100 | 100 |  | 2024-05-28 | 2024-05-28 | 2024-05-30 | 2024-05-30 | Tower B | Foundation
47994 |  | Complete |  | 2024-05-29 | 2024-06-29 | Demolition + Segregation & Carting Away of Debris | 100 | 100 |  | 2024-05-29 | 2024-05-29 | 2024-06-29 | 2024-06-29
39431 | Tower A - Super Structure - Core Wall Low Rise L21-22 | Complete | Core Wall RCC Works | 2024-05-30 | 2024-05-30 | Casting | 100 | 100 |  | 2024-05-30 | 2024-05-30 | 2024-05-30 | 2024-05-30 | Tower A | Super Structure | L21 | RCC Super Structure | Core Wall RCC Works
39856 | Tower A - Super Structure - Core & Outer Slab L17-18 | Complete | RCC Works - Slab | 2024-05-30 | 2024-06-02 | Outer Slab_TA | 100 | 100 |  | 2024-05-30 | 2024-05-30 | 2024-06-02 | 2024-06-02 | Tower A | Super Structure | L17 | RCC Sub Structure | RCC Works - Slab
39432 | Tower A - Super Structure - Core Wall Low Rise L21-22 | Complete | Core Wall RCC Works | 2024-05-31 | 2024-05-31 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-05-31 | 2024-05-31 | 2024-05-31 | 2024-05-31 | Tower A | Super Structure | L21 | RCC Super Structure | Core Wall RCC Works
44751 | Tower B - Foundation - Pour 5 | Complete | HDPE Waterproofing | 2024-05-31 | 2024-06-03 | HDPE waterproofing laying | 100 | 100 |  | 2024-05-31 | 2024-05-31 | 2024-06-03 | 2024-06-03 | Tower B | Foundation
44780 | Tower B - Sub Structure - B3 to B2 - Pour 3 | Complete | RCC Works - Slab | 2024-05-31 | 2024-06-05 | Slab & Staircase Reinf. | 100 | 100 |  | 2024-05-31 | 2024-05-31 | 2024-06-05 | 2024-06-05 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
39433 |  | Complete |  | 2024-06-01 | 2024-06-11 | Core Wall L22-23 | 100 | 100 |  | 2024-06-01 | 2024-06-01 | 2024-06-11 | 2024-06-11
39434 | Tower A - Super Structure - Core Wall Low Rise L22-23 | Complete | Core Wall RCC Works | 2024-06-01 | 2024-06-01 | Scaffolding & platform | 100 | 100 |  | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | Tower A | Super Structure | L22 | RCC Super Structure | Core Wall RCC Works
39435 | Tower A - Super Structure - Core Wall Low Rise L22-23 | Complete | Core Wall RCC Works | 2024-06-03 | 2024-06-05 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-06-03 | 2024-06-03 | 2024-06-05 | 2024-06-05 | Tower A | Super Structure | L22 | RCC Super Structure | Core Wall RCC Works
39857 |  | Complete |  | 2024-06-03 | 2024-06-11 | L18-19 | 100 | 100 |  | 2024-06-03 | 2024-06-03 | 2024-06-11 | 2024-06-11
39857 |  | Complete |  | 2024-06-03 | 2024-06-11 | L18-19 | 100 | 100 |  | 2024-06-03 | 2024-06-03 | 2024-06-11 | 2024-06-11 |  |  |  | Finishes | Gypsum Plastering Works
39858 | Tower A - Super Structure - Core & Outer Slab L18-19 | Complete | RCC Works - Vertical | 2024-06-03 | 2024-06-10 | Outer Columns_TA | 100 | 100 |  | 2024-06-03 | 2024-06-03 | 2024-06-10 | 2024-06-10 | Tower A | Super Structure | L18 | RCC Sub Structure | RCC Works - Vertical
40209 |  | Complete |  | 2024-06-03 | 2024-09-25 | L15-16 | 100 | 100 |  | 2024-06-03 | 2024-06-03 | 2024-09-25 | 2024-09-25
40209 |  | Complete |  | 2024-06-03 | 2024-09-25 | L15-16 | 100 | 100 |  | 2024-06-03 | 2024-06-03 | 2024-09-25 | 2024-09-25 |  |  |  | Finishes | Gypsum Plastering Works
40210 | Tower A - Super Structure - Finishes & MEP - L15 to L16 | Complete | Partition Wall-Blockwork | 2024-06-03 | 2024-06-20 | De-shuttering & Area clearance | 100 | 100 |  | 2024-06-03 | 2024-06-03 | 2024-06-20 | 2024-06-20 | Tower A | Super Structure | L15
44515 | NTA_Zone 2 - Super Structure - P4 to P5 - Pour 1 | Complete | RCC Works - Slab | 2024-06-03 | 2024-06-26 | Slab_NTA | 100 | 100 |  | 2024-06-03 | 2024-06-03 | 2024-06-26 | 2024-06-26 | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Slab
44515 | NTA_Zone 2 - Super Structure - P4 to P5 - Pour 1 | Complete | RCC Works - Slab | 2024-06-03 | 2024-06-26 | Slab_NTA | 100 | 100 |  | 2024-06-03 | 2024-06-03 | 2024-06-26 | 2024-06-26 | NTA_Zone 2 | Super Structure
39192 |  | Complete |  | 2024-06-04 | 2024-06-11 | Order of Low Side Material | 100 | 100 |  | 2024-06-04 | 2024-06-04 | 2024-06-11 | 2024-06-11
39193 |  | Started |  | 2024-06-04 | 2024-06-07 | Order of High Side Material | 100 | 80 |  | 2024-06-04 | 2024-06-04 | 2025-09-12
39436 | Tower A - Super Structure - Core Wall Low Rise L22-23 | Complete | Core Wall RCC Works | 2024-06-04 | 2024-06-06 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-06-04 | 2024-06-04 | 2024-06-06 | 2024-06-06 | Tower A | Super Structure | L22 | RCC Super Structure | Core Wall RCC Works
44752 | Tower B - Foundation - Pour 5 | Complete | Raft RCC Works | 2024-06-04 | 2024-06-20 | Raft reinf. | 100 | 100 |  | 2024-06-04 | 2024-06-04 | 2024-06-20 | 2024-06-20 | Tower B | Foundation |  | RCC Sub Structure | Raft RCC Works
40175 | Tower A - Super Structure - Finishes & MEP - P6 to L7 | Complete | Partition Wall-Blockwork | 2024-06-05 | 2024-06-12 | Partition Walls | 100 | 100 |  | 2024-06-05 | 2024-06-20 | 2024-06-12 | 2024-07-10 | Tower A | Super Structure
39859 | Tower A - Super Structure - Core & Outer Slab L18-19 | Complete | RCC Works - Slab | 2024-06-06 | 2024-06-11 | Outer Slab_TA | 100 | 100 |  | 2024-06-06 | 2024-06-06 | 2024-06-11 | 2024-06-11 | Tower A | Super Structure | L18 | RCC Sub Structure | RCC Works - Slab
8358 |  | Started |  | 2024-06-07 | 2027-03-18 | BIRLA SCHEDULE COMPLETE -DETAILED MSP-V1_new | 100 | 28 | Units | 2024-06-07 | 2024-06-07 | 2027-04-21
8360 |  | Complete |  | 2024-06-07 | 2024-06-07 | LOI | 100 | 100 |  | 2024-06-07 | 2024-06-07 | 2024-06-07 | 2024-06-07
39437 | Tower A - Super Structure - Core Wall Low Rise L22-23 | Complete | Core Wall RCC Works | 2024-06-07 | 2024-06-10 | Casting | 100 | 100 |  | 2024-06-07 | 2024-06-07 | 2024-06-10 | 2024-06-10 | Tower A | Super Structure | L22 | RCC Super Structure | Core Wall RCC Works
44723 | Tower B - Foundation - Pour 2 | Complete | Raft RCC Works | 2024-06-07 | 2024-06-08 | Fwk fix | 100 | 100 |  | 2024-06-07 | 2024-06-07 | 2024-06-08 | 2024-06-08 | Tower B | Foundation |  | RCC Sub Structure | Raft RCC Works
44724 | Tower B - Foundation - Pour 2 | Complete | Raft RCC Works | 2024-06-08 | 2024-06-08 | Checking & casting | 100 | 100 |  | 2024-06-08 | 2024-06-08 | 2024-06-08 | 2024-06-08 | Tower B | Foundation |  | RCC Sub Structure | Raft RCC Works
48009 |  | Complete |  | 2024-06-10 | 2024-10-19 | Relocation of fore court electrical panel and services | 100 | 100 |  | 2024-06-10 | 2024-06-10 | 2024-10-19 | 2024-10-19
39151 |  | Started |  | 2024-06-11 | 2025-06-24 | Civil Works | 100 | 91 |  | 2024-06-11 | 2024-06-11 | 2025-09-22
39184 |  | Complete |  | 2024-06-11 | 2024-10-29 | Stack Parking Works | 100 | 100 |  | 2024-06-11 | 2024-06-11 | 2024-10-29 | 2024-10-29
39185 |  | Complete |  | 2024-06-11 | 2024-06-12 | Stack Parking Delivery & Installation | 100 | 100 |  | 2024-06-11 | 2024-06-11 | 2024-06-12 | 2024-06-12
39438 | Tower A - Super Structure - Core Wall Low Rise L22-23 | Complete | Core Wall RCC Works | 2024-06-11 | 2024-06-11 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-06-11 | 2024-06-11 | 2024-06-11 | 2024-06-11 | Tower A | Super Structure | L22 | RCC Super Structure | Core Wall RCC Works
39195 |  | Started |  | 2024-06-12 | 2024-11-27 | High Side Material Delivery | 100 | 80 |  | 2024-06-12 | 2025-07-10 | 2025-10-16
39439 |  | Complete |  | 2024-06-12 | 2024-06-20 | Core Wall L23-24 | 100 | 100 |  | 2024-06-12 | 2024-06-12 | 2024-06-20 | 2024-06-20
39440 | Tower A - Super Structure - Core Wall Low Rise L23-24 | Complete | Core Wall RCC Works | 2024-06-12 | 2024-06-12 | Scaffolding & platform | 100 | 100 |  | 2024-06-12 | 2024-06-12 | 2024-06-12 | 2024-06-12 | Tower A | Super Structure | L23 | RCC Super Structure | Core Wall RCC Works
39860 |  | Complete |  | 2024-06-12 | 2024-06-20 | L19-20 | 100 | 100 |  | 2024-06-12 | 2024-06-12 | 2024-06-20 | 2024-06-20
39860 |  | Complete |  | 2024-06-12 | 2024-06-20 | L19-20 | 100 | 100 |  | 2024-06-12 | 2024-06-12 | 2024-06-20 | 2024-06-20 |  |  |  | Finishes | Gypsum Plastering Works
39861 | Tower A - Super Structure - Core & Outer Slab L19-20 | Complete | RCC Works - Vertical | 2024-06-12 | 2024-06-19 | Outer Columns_TA | 100 | 100 |  | 2024-06-12 | 2024-06-12 | 2024-06-19 | 2024-06-19 | Tower A | Super Structure | L19 | RCC Sub Structure | RCC Works - Vertical
40213 |  | Complete |  | 2024-06-12 | 2024-11-04 | L16-17 | 100 | 100 |  | 2024-06-12 | 2024-06-12 | 2024-11-04 | 2024-11-04
40213 |  | Complete |  | 2024-06-12 | 2024-11-04 | L16-17 | 100 | 100 |  | 2024-06-12 | 2024-06-12 | 2024-11-04 | 2024-11-04 |  |  |  | Finishes | Gypsum Plastering Works
40214 | Tower A - Super Structure - Finishes & MEP - L16 to L17 | Complete | Partition Wall-Blockwork | 2024-06-12 | 2024-06-29 | De-shuttering & Area clearance | 100 | 100 |  | 2024-06-12 | 2024-06-12 | 2024-06-29 | 2024-06-29 | Tower A | Super Structure | L16
44755 |  | Complete |  | 2024-06-12 | 2024-07-09 | Pour 4 | 100 | 100 |  | 2024-06-12 | 2024-06-12 | 2024-07-09 | 2024-07-06
44756 | Tower B - Foundation - Pour 4 | Complete | PCC | 2024-06-12 | 2024-06-14 | PCC | 100 | 100 |  | 2024-06-12 | 2024-06-12 | 2024-06-14 | 2024-06-14 | Tower B | Foundation
39441 | Tower A - Super Structure - Core Wall Low Rise L23-24 | Complete | Core Wall RCC Works | 2024-06-13 | 2024-06-15 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-06-13 | 2024-06-13 | 2024-06-15 | 2024-06-15 | Tower A | Super Structure | L23 | RCC Super Structure | Core Wall RCC Works
40179 | Tower A - Super Structure - Finishes & MEP - L7 to L8 | Complete | Partition Wall-Blockwork | 2024-06-13 | 2024-06-21 | Partition Walls | 100 | 100 |  | 2024-06-13 | 2024-06-13 | 2024-06-21 | 2024-06-21 | Tower A | Super Structure | L7
39442 | Tower A - Super Structure - Core Wall Low Rise L23-24 | Complete | Core Wall RCC Works | 2024-06-14 | 2024-06-18 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-06-14 | 2024-06-14 | 2024-06-18 | 2024-06-18 | Tower A | Super Structure | L23 | RCC Super Structure | Core Wall RCC Works
39862 | Tower A - Super Structure - Core & Outer Slab L19-20 | Complete | RCC Works - Slab | 2024-06-15 | 2024-06-20 | Outer Slab_TA | 100 | 100 |  | 2024-06-15 | 2024-06-15 | 2024-06-20 | 2024-06-20 | Tower A | Super Structure | L19 | RCC Sub Structure | RCC Works - Slab
44757 | Tower B - Foundation - Pour 4 | Complete | HDPE Waterproofing | 2024-06-15 | 2024-06-19 | HDPE waterproofing laying | 100 | 100 |  | 2024-06-15 | 2024-06-15 | 2024-06-19 | 2024-06-19 | Tower B | Foundation
41025 |  | Started |  | 2024-06-16 | 2026-12-30 | Typical Floor MEP & Finishes | 100 | 41 |  | 2024-06-16 | 2024-06-16 | 2027-01-06
41026 |  | Started |  | 2024-06-16 | 2026-12-30 | Typical Floor Lobby | 100 | 43 |  | 2024-06-16 | 2024-06-16 | 2027-01-06
41059 |  | Started |  | 2024-06-16 | 2025-12-02 | L7-8 | 100 | 68 |  | 2024-06-16 | 2024-06-16 | 2025-12-23 |  |  |  |  | Finishes | Gypsum Plastering Works
41059 |  | Started |  | 2024-06-16 | 2025-12-02 | L7-8 | 100 | 68 |  | 2024-06-16 | 2024-06-16 | 2025-12-23
41060 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2024-06-16 | 2024-06-18 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 80 |  | 2024-06-16 | 2024-06-16 | 2025-11-12 |  | Tower A | Super Structure | L7 | MEP | FPS 1st Fix - MEP & Finishes
39443 | Tower A - Super Structure - Core Wall Low Rise L23-24 | Complete | Core Wall RCC Works | 2024-06-19 | 2024-06-19 | Casting | 100 | 100 |  | 2024-06-19 | 2024-06-19 | 2024-06-19 | 2024-06-19 | Tower A | Super Structure | L23 | RCC Super Structure | Core Wall RCC Works
39444 | Tower A - Super Structure - Core Wall Low Rise L23-24 | Complete | Core Wall RCC Works | 2024-06-20 | 2024-06-20 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | Tower A | Super Structure | L23 | RCC Super Structure | Core Wall RCC Works
44758 | Tower B - Foundation - Pour 4 | Complete | Raft RCC Works | 2024-06-20 | 2024-07-04 | Raft reinf. | 100 | 100 |  | 2024-06-20 | 2024-06-20 | 2024-07-04 | 2024-07-04 | Tower B | Foundation |  | RCC Sub Structure | Raft RCC Works
39445 |  | Complete |  | 2024-06-21 | 2024-07-01 | Core Wall L24-25 (MEP Transfer Floor) | 100 | 100 |  | 2024-06-21 | 2024-06-21 | 2024-07-01 | 2024-07-01
39446 | Tower A - Super Structure - Core Wall Low Rise L24-25 | Complete | Core Wall RCC Works | 2024-06-21 | 2024-06-21 | Scaffolding & platform | 100 | 100 |  | 2024-06-21 | 2024-06-21 | 2024-06-21 | 2024-06-21 | Tower A | Super Structure | L24 | RCC Super Structure | Core Wall RCC Works
39863 |  | Complete |  | 2024-06-21 | 2024-06-30 | L20-21 | 100 | 100 |  | 2024-06-21 | 2024-06-21 | 2024-06-30 | 2024-06-30
39863 |  | Complete |  | 2024-06-21 | 2024-06-30 | L20-21 | 100 | 100 |  | 2024-06-21 | 2024-06-21 | 2024-06-30 | 2024-06-30 |  |  |  | Finishes | Gypsum Plastering Works
39864 | Tower A - Super Structure - Core & Outer Slab L20-21 | Complete | RCC Works - Vertical | 2024-06-21 | 2024-06-29 | Outer Columns_TA | 100 | 100 |  | 2024-06-21 | 2024-06-21 | 2024-06-29 | 2024-06-29 | Tower A | Super Structure | L20 | RCC Sub Structure | RCC Works - Vertical
40217 |  | Complete |  | 2024-06-21 | 2024-10-14 | L17-18 | 100 | 100 |  | 2024-06-21 | 2024-06-21 | 2024-10-14 | 2024-10-14
40217 |  | Complete |  | 2024-06-21 | 2024-10-14 | L17-18 | 100 | 100 |  | 2024-06-21 | 2024-06-21 | 2024-10-14 | 2024-10-14 |  |  |  | Finishes | Gypsum Plastering Works
40218 | Tower A - Super Structure - Finishes & MEP - L17 to L18 | Complete | Partition Wall-Blockwork | 2024-06-21 | 2024-07-11 | De-shuttering & Area clearance | 100 | 100 |  | 2024-06-21 | 2024-06-21 | 2024-07-11 | 2024-07-11 | Tower A | Super Structure | L17
44753 | Tower B - Foundation - Pour 5 | Complete | Raft RCC Works | 2024-06-21 | 2024-06-22 | Fwk fix | 100 | 100 |  | 2024-06-21 | 2024-06-21 | 2024-06-22 | 2024-06-22 | Tower B | Foundation |  | RCC Sub Structure | Raft RCC Works
39447 | Tower A - Super Structure - Core Wall Low Rise L24-25 | Complete | Core Wall RCC Works | 2024-06-22 | 2024-06-25 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-06-22 | 2024-06-22 | 2024-06-25 | 2024-06-25 | Tower A | Super Structure | L24 | RCC Super Structure | Core Wall RCC Works
40180 | Tower A - Super Structure - Finishes & MEP - L7 to L8 | Complete | Partition Wall-Blockwork | 2024-06-22 | 2024-06-27 | Staircase Area | 100 | 100 |  | 2024-06-22 | 2024-06-22 | 2024-06-27 | 2024-06-27 | Tower A | Super Structure | L7
40183 | Tower A - Super Structure - Finishes & MEP - L8 to L9 | Complete | Partition Wall-Blockwork | 2024-06-22 | 2024-06-29 | Partition Walls | 100 | 100 |  | 2024-06-22 | 2024-06-22 | 2024-06-29 | 2024-06-29 | Tower A | Super Structure | L8
44754 | Tower B - Foundation - Pour 5 | Complete | Raft RCC Works | 2024-06-22 | 2024-06-22 | Checking & casting | 100 | 100 |  | 2024-06-22 | 2024-06-22 | 2024-06-22 | 2024-06-22 | Tower B | Foundation |  | RCC Sub Structure | Raft RCC Works
39448 | Tower A - Super Structure - Core Wall Low Rise L24-25 | Complete | Core Wall RCC Works | 2024-06-24 | 2024-06-26 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-06-24 | 2024-06-24 | 2024-06-26 | 2024-06-26 | Tower A | Super Structure | L24 | RCC Super Structure | Core Wall RCC Works
40839 |  | Started |  | 2024-06-24 | 2024-09-07 | P6-7 Level (Refuge) | 100 | 47 |  | 2024-06-24 | 2024-06-24 | 2026-02-10
40854 |  | Started |  | 2024-06-24 | 2024-09-07 | Floor Area | 100 | 56 |  | 2024-06-24 | 2024-06-24 | 2025-10-25
40855 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Complete | Ceiling Painting/ PT Marking - MEP & Finishes | 2024-06-24 | 2024-06-28 | Ceiling Painting/ PT Marking | 100 | 100 |  | 2024-06-24 | 2024-06-24 | 2024-06-28 | 2024-06-28 | Tower A | Super Structure |  | Finishes | Ceiling Painting/ PT Marking
39865 | Tower A - Super Structure - Core & Outer Slab L20-21 | Complete | RCC Works - Slab | 2024-06-25 | 2024-06-30 | Outer Slab_TA | 100 | 100 |  | 2024-06-25 | 2024-06-25 | 2024-06-30 | 2024-06-30 | Tower A | Super Structure | L20 | RCC Sub Structure | RCC Works - Slab
44680 | Tower A | Complete | Award of Packages | 2024-06-26 | 2024-12-13 | BMU | 100 | 100 |  | 2024-06-26 | 2024-06-26 | 2024-12-13 | 2024-12-13 | Tower A | --
39449 | Tower A - Super Structure - Core Wall Low Rise L24-25 | Complete | Core Wall RCC Works | 2024-06-27 | 2024-06-30 | Casting | 100 | 100 |  | 2024-06-27 | 2024-06-27 | 2024-06-30 | 2024-06-30 | Tower A | Super Structure | L24 | RCC Super Structure | Core Wall RCC Works
44241 | Tower A | Complete | High Side Procurement | 2024-06-27 | 2025-01-14 | Elevators | 100 | 100 |  | 2024-06-27 | 2024-06-27 | 2025-01-14 | 2025-01-14 | Tower A | --
8359 |  | Started |  | 2024-06-07 | 2027-03-18 | BIRLA TRIMAYA | 100 | 28 |  | 2024-06-28 | 2024-06-28 | 2027-04-21
8361 |  | Complete |  | 2024-06-28 | 2024-06-29 | Kick of Meeting | 100 | 100 |  | 2024-06-28 | 2024-06-28 | 2024-06-29 | 2024-06-29
42163 |  | Started |  | 2024-06-28 | 2026-10-31 | Typical Apartment Area | 100 | 40 |  | 2024-06-28 | 2024-06-28 | 2026-10-14
42200 |  | Started |  | 2024-06-28 | 2026-05-23 | L7-8 | 100 | 83 |  | 2024-06-28 | 2024-06-28 | 2026-05-21 |  |  |  |  | Finishes | Gypsum Plastering Works
42200 |  | Started |  | 2024-06-28 | 2026-05-23 | L7-8 | 100 | 83 |  | 2024-06-28 | 2024-06-28 | 2026-05-21
42201 |  | Started |  | 2024-06-28 | 2024-07-26 | MEP 1st Fixes & Waterproofing | 100 | 86 |  | 2024-06-28 | 2024-06-28 | 2025-09-13
42202 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Apartment Area | Started | FPS 1st Fix - MEP & Finishes | 2024-06-28 | 2024-06-29 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 80 |  | 2024-06-28 | 2024-06-28 | 2025-09-12 |  | Tower A | Super Structure | L7 | MEP | FPS 1st Fix - MEP & Finishes
42203 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Apartment Area | Started | Electrical 1st Fix - MEP & Finishes | 2024-06-28 | 2024-06-28 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 90 |  | 2024-06-28 | 2024-06-28 | 2025-09-11 |  | Tower A | Super Structure | L7 | MEP | Electrical 1st Fixes
42204 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Apartment Area | Started | PHE 1st Fix - MEP & Finishes | 2024-06-28 | 2024-06-29 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 80 |  | 2024-06-28 | 2024-06-28 | 2025-09-12 |  | Tower A | Super Structure | L7
42205 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Apartment Area | Started | Wet Area Waterproofing - MEP & Finishes | 2024-06-28 | 2024-06-29 | Wet Area Waterproofing | 100 | 90 |  | 2024-06-28 | 2024-06-28 | 2025-09-12 |  | Tower A | Super Structure | L7
48008 |  | Started |  | 2024-06-28 | 2024-07-03 | IT, Telephone & Data | 100 | 95 |  | 2024-06-28 | 2024-06-28 | 2025-09-16
40857 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Started | PHE 1st Fix - MEP & Finishes | 2024-06-29 | 2024-07-06 | PHE 1st Fixes (Pipe Installations & Testing) | 100 | 69 |  | 2024-06-29 | 2024-06-29 | 2025-09-19 |  | Tower A | Super Structure
8362 |  | Complete |  | 2024-06-30 | 2024-09-04 | MOBILIZATION | 100 | 100 |  | 2024-06-30 | 2024-06-30 | 2024-09-04 | 2024-09-04
41075 |  | Started |  | 2024-06-30 | 2025-12-08 | L8-9 | 100 | 68 |  | 2024-06-30 | 2024-06-30 | 2025-12-30 |  |  |  |  | Finishes | Gypsum Plastering Works
41075 |  | Started |  | 2024-06-30 | 2025-12-08 | L8-9 | 100 | 68 |  | 2024-06-30 | 2024-06-30 | 2025-12-30
41076 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2024-06-30 | 2024-07-01 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 80 |  | 2024-06-30 | 2024-06-30 | 2025-11-18 |  | Tower A | Super Structure | L8 | MEP | FPS 1st Fix - MEP & Finishes
39243 |  | Started |  | 2024-07-01 | 2026-06-10 | RETAIL ZONE C | 100 | 3 |  | 2024-07-01 | 2024-07-01 | 2026-12-14
39245 |  | Started |  | 2024-07-01 | 2025-08-23 | Foundation_Retail | 100 | 5 |  | 2024-07-01 | 2024-07-01 | 2026-02-09
39246 | Retail - Foundation | Started | Raft RCC Works | 2024-07-01 | 2024-07-03 | Dressing & PCC | 100 | 5 |  | 2024-07-01 | 2024-07-01 | 2026-01-03 |  | Retail | Foundation | -- | RCC Sub Structure | Raft RCC Works
39246 | Retail - Foundation | Started | Raft RCC Works | 2024-07-01 | 2024-07-03 | Dressing & PCC | 100 | 5 |  | 2024-07-01 | 2024-07-01 | 2026-01-03 |  | Retail | Foundation | -- | RCC Super Structure | Foundation RCC Works
39246 | Retail - Foundation | Started | Raft RCC Works | 2024-07-01 | 2024-07-03 | Dressing & PCC | 100 | 5 |  | 2024-07-01 | 2024-07-01 | 2026-01-03 |  | Retail | Foundation | --
39450 | Tower A - Super Structure - Core Wall Low Rise L24-25 | Complete | Core Wall RCC Works | 2024-07-01 | 2024-07-01 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | Tower A | Super Structure | L24 | RCC Super Structure | Core Wall RCC Works
39866 |  | Complete |  | 2024-07-01 | 2024-07-11 | L21-22 | 100 | 100 |  | 2024-07-01 | 2024-07-01 | 2024-07-11 | 2024-07-11
39866 |  | Complete |  | 2024-07-01 | 2024-07-11 | L21-22 | 100 | 100 |  | 2024-07-01 | 2024-07-01 | 2024-07-11 | 2024-07-11 |  |  |  | Finishes | Gypsum Plastering Works
39867 | Tower A - Super Structure - Core & Outer Slab L21-22 | Complete | RCC Works - Vertical | 2024-07-01 | 2024-07-11 | Outer Columns_TA | 100 | 100 |  | 2024-07-01 | 2024-07-01 | 2024-07-11 | 2024-07-11 | Tower A | Super Structure | L21 | RCC Sub Structure | RCC Works - Vertical
40184 | Tower A - Super Structure - Finishes & MEP - L8 to L9 | Complete | Partition Wall-Blockwork | 2024-07-01 | 2024-07-05 | Staircase Area | 100 | 100 |  | 2024-07-01 | 2024-07-01 | 2024-07-05 | 2024-07-05 | Tower A | Super Structure | L8
40187 | Tower A - Super Structure - Finishes & MEP - L9 to L10 | Complete | Partition Wall-Blockwork | 2024-07-01 | 2024-07-11 | Partition Walls | 100 | 100 |  | 2024-07-01 | 2024-07-01 | 2024-07-11 | 2024-07-11 | Tower A | Super Structure | L9
40221 |  | Complete |  | 2024-07-01 | 2024-10-22 | L18-19 | 100 | 100 |  | 2024-07-01 | 2024-07-01 | 2024-10-22 | 2024-10-22
40221 |  | Complete |  | 2024-07-01 | 2024-10-22 | L18-19 | 100 | 100 |  | 2024-07-01 | 2024-07-01 | 2024-10-22 | 2024-10-22 |  |  |  | Finishes | Gypsum Plastering Works
40222 | Tower A - Super Structure - Finishes & MEP - L18 to L19 | Complete | Partition Wall-Blockwork | 2024-07-01 | 2024-07-27 | De-shuttering & Area clearance | 100 | 100 |  | 2024-07-01 | 2024-07-01 | 2024-07-27 | 2024-07-27 | Tower A | Super Structure | L18
40555 | Tower A - Super Structure - Finishes & MEP | Complete | MEP Shaft Masonry | 2024-07-01 | 2024-07-01 | L15-L25 | 100 | 100 |  | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | Tower A | Super Structure
48036 |  | Complete |  | 2024-07-01 | 2024-09-07 | Plum Concrete | 100 | 100 |  | 2024-07-01 | 2024-07-01 | 2024-09-07 | 2024-09-07
39204 |  | Complete |  | 2024-07-02 | 2024-10-04 | Delivery of Low side Materials | 100 | 100 |  | 2024-07-02 | 2024-07-02 | 2024-10-04 | 2024-10-04
39217 |  | Complete |  | 2024-07-02 | 2024-08-23 | Delivery of Low side Materials | 100 | 100 |  | 2024-07-02 | 2024-07-02 | 2024-08-23 | 2024-08-23
39231 |  | Complete |  | 2024-07-02 | 2024-08-23 | Delivery of Low side Materials | 100 | 100 |  | 2024-07-02 | 2024-07-02 | 2024-08-23 | 2024-08-23
39235 |  | Complete |  | 2024-07-02 | 2024-08-23 | Delivery of High side Materials | 100 | 100 |  | 2024-07-02 | 2024-07-02 | 2024-08-23 | 2024-08-23
39451 |  | Complete |  | 2024-07-02 | 2024-07-11 | Core Wall L25-26 | 100 | 100 |  | 2024-07-02 | 2024-07-02 | 2024-07-11 | 2024-07-11
39452 | Tower A - Super Structure - Core Wall Low Rise L25-26 | Complete | Core Wall RCC Works | 2024-07-02 | 2024-07-02 | Scaffolding & platform | 100 | 100 |  | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2024-07-02 | Tower A | Super Structure | L25 | RCC Super Structure | Core Wall RCC Works
39453 | Tower A - Super Structure - Core Wall Low Rise L25-26 | Complete | Core Wall RCC Works | 2024-07-03 | 2024-07-05 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-07-03 | 2024-07-03 | 2024-07-05 | 2024-07-05 | Tower A | Super Structure | L25 | RCC Super Structure | Core Wall RCC Works
39454 | Tower A - Super Structure - Core Wall Low Rise L25-26 | Complete | Core Wall RCC Works | 2024-07-04 | 2024-07-06 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-07-04 | 2024-07-04 | 2024-07-06 | 2024-07-06 | Tower A | Super Structure | L25 | RCC Super Structure | Core Wall RCC Works
39868 | Tower A - Super Structure - Core & Outer Slab L21-22 | Complete | RCC Works - Slab | 2024-07-04 | 2024-07-11 | Outer Slab_TA | 100 | 100 |  | 2024-07-04 | 2024-07-04 | 2024-07-11 | 2024-07-11 | Tower A | Super Structure | L21 | RCC Sub Structure | RCC Works - Slab
44731 |  | Complete |  | 2024-07-05 | 2024-08-29 | Pour 6 | 100 | 100 |  | 2024-07-05 | 2024-07-05 | 2024-08-29 | 2024-08-29
44732 | Tower B - Foundation - Pour 6 | Complete | PCC | 2024-07-05 | 2024-07-11 | PCC | 100 | 100 |  | 2024-07-05 | 2024-07-05 | 2024-07-11 | 2024-07-11 | Tower B | Foundation
44759 | Tower B - Foundation - Pour 4 | Complete | Raft RCC Works | 2024-07-05 | 2024-07-06 | Fwk fix | 100 | 100 |  | 2024-07-05 | 2024-07-05 | 2024-07-06 | 2024-07-06 | Tower B | Foundation |  | RCC Sub Structure | Raft RCC Works
40469 |  | Started |  | 2024-02-03 | 2026-05-07 | Gypsum Plastering Works (Non-MEP Walls) | 100 | 30 |  | 2024-07-06 | 2024-07-06 | 2026-06-06
40480 |  | Started |  | 2024-07-06 | 2026-05-07 | Typical Floors | 100 | 35 |  | 2024-07-06 | 2024-07-06 | 2026-06-06
40481 | Tower A - Super Structure - Finishes & MEP - L7 to L8 | Complete | Gypsum Plastering Works | 2024-07-06 | 2025-04-30 | L7-8 | 100 | 100 |  | 2024-07-06 | 2024-07-06 | 2025-04-30 | 2025-04-30 | Tower A | Super Structure | L7 | Finishes | Gypsum Plastering Works
40481 | Tower A - Super Structure - Finishes & MEP - L7 to L8 | Complete | Gypsum Plastering Works | 2024-07-06 | 2025-04-30 | L7-8 | 100 | 100 |  | 2024-07-06 | 2024-07-06 | 2025-04-30 | 2025-04-30 | Tower A | Super Structure | L7
42218 |  | Started |  | 2024-07-06 | 2026-05-23 | L8-9 | 100 | 84 |  | 2024-07-06 | 2024-07-06 | 2026-05-21 |  |  |  |  | Finishes | Gypsum Plastering Works
42218 |  | Started |  | 2024-07-06 | 2026-05-23 | L8-9 | 100 | 84 |  | 2024-07-06 | 2024-07-06 | 2026-05-21
42219 |  | Started |  | 2024-07-06 | 2024-08-03 | MEP 1st Fixes & Waterproofing | 100 | 87 |  | 2024-07-06 | 2024-07-06 | 2025-09-13
42220 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Apartment Area | Started | FPS 1st Fix - MEP & Finishes | 2024-07-06 | 2024-07-09 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 85 |  | 2024-07-06 | 2024-07-06 | 2025-09-12 |  | Tower A | Super Structure | L8 | MEP | FPS 1st Fix - MEP & Finishes
42221 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Apartment Area | Started | Electrical 1st Fix - MEP & Finishes | 2024-07-06 | 2024-07-06 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 90 |  | 2024-07-06 | 2024-07-06 | 2025-09-11 |  | Tower A | Super Structure | L8 | MEP | Electrical 1st Fixes
42222 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Apartment Area | Started | PHE 1st Fix - MEP & Finishes | 2024-07-06 | 2024-07-09 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 80 |  | 2024-07-06 | 2024-07-06 | 2025-09-12 |  | Tower A | Super Structure | L8
42223 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Apartment Area | Started | Wet Area Waterproofing - MEP & Finishes | 2024-07-06 | 2024-07-09 | Wet Area Waterproofing | 100 | 90 |  | 2024-07-06 | 2024-07-06 | 2025-09-12 |  | Tower A | Super Structure | L8
44760 | Tower B - Foundation - Pour 4 | Milestone Started | Raft RCC Works | 2024-07-09 |  | Checking & casting | 100 | 100 |  | 2024-07-09 | 2024-07-05 |  |  | Tower B | Foundation |  | RCC Sub Structure | Raft RCC Works
39455 | Tower A - Super Structure - Core Wall Low Rise L25-26 | Milestone Started | Core Wall RCC Works | 2024-07-10 |  | Casting | 100 | 100 |  | 2024-07-10 | 2024-07-11 |  |  | Tower A | Super Structure | L25 | RCC Super Structure | Core Wall RCC Works
39456 | Tower A - Super Structure - Core Wall Low Rise L25-26 | Complete | Core Wall RCC Works | 2024-07-11 | 2024-07-11 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-07-11 | 2024-07-11 | 2024-07-11 | 2024-07-11 | Tower A | Super Structure | L25 | RCC Super Structure | Core Wall RCC Works
39457 |  | Complete |  | 2024-07-12 | 2024-07-19 | Core Wall L26-27 | 100 | 100 |  | 2024-07-12 | 2024-07-12 | 2024-07-19 | 2024-07-19
39458 | Tower A - Super Structure - Core Wall Low Rise L26-27 | Complete | Core Wall RCC Works | 2024-07-12 | 2024-07-12 | Scaffolding & platform | 100 | 100 |  | 2024-07-12 | 2024-07-12 | 2024-07-12 | 2024-07-12 | Tower A | Super Structure | L26 | RCC Super Structure | Core Wall RCC Works
39869 |  | Complete |  | 2024-07-12 | 2024-07-19 | L22-23 | 100 | 100 |  | 2024-07-12 | 2024-07-12 | 2024-07-19 | 2024-07-19
39869 |  | Complete |  | 2024-07-12 | 2024-07-19 | L22-23 | 100 | 100 |  | 2024-07-12 | 2024-07-12 | 2024-07-19 | 2024-07-19 |  |  |  | Finishes | Gypsum Plastering Works
39870 | Tower A - Super Structure - Core & Outer Slab L22-23 | Complete | RCC Works - Vertical | 2024-07-12 | 2024-07-19 | Outer Columns_TA | 100 | 100 |  | 2024-07-12 | 2024-07-12 | 2024-07-19 | 2024-07-19 | Tower A | Super Structure | L22 | RCC Sub Structure | RCC Works - Vertical
40188 | Tower A - Super Structure - Finishes & MEP - L9 to L10 | Complete | Partition Wall-Blockwork | 2024-07-12 | 2024-07-20 | Staircase Area | 100 | 100 |  | 2024-07-12 | 2024-07-12 | 2024-07-20 | 2024-07-20 | Tower A | Super Structure | L9
40191 | Tower A - Super Structure - Finishes & MEP - L10 to L11 | Complete | Partition Wall-Blockwork | 2024-07-12 | 2024-07-26 | Partition Walls | 100 | 100 |  | 2024-07-12 | 2024-07-12 | 2024-07-26 | 2024-07-26 | Tower A | Super Structure | L10
44529 | NTA_Zone 2 - Sub Structure - B1 to GF | Started | MEP 1st Fix Works | 2024-07-12 | 2024-07-31 | B1 to GF | 100 | 80 |  | 2024-07-12 | 2024-07-12 | 2025-10-29 |  | NTA_Zone 2 | Sub Structure | B1
44529 | NTA_Zone 2 - Sub Structure - B1 to GF | Started | MEP 1st Fix Works | 2024-07-12 | 2024-07-31 | B1 to GF | 100 | 80 |  | 2024-07-12 | 2024-07-12 | 2025-10-29 |  | NTA_Zone 2 | Sub Structure | B1
44529 | NTA_Zone 2 - Sub Structure - B1 to GF | Started | MEP 1st Fix Works | 2024-07-12 | 2024-07-31 | B1 to GF | 100 | 80 |  | 2024-07-12 | 2024-07-12 | 2025-10-29 |  | NTA_Zone 2 | Sub Structure | B1
44733 | Tower B - Foundation - Pour 6 | Complete | HDPE Waterproofing | 2024-07-12 | 2024-07-18 | HDPE waterproofing laying | 100 | 100 |  | 2024-07-12 | 2024-07-12 | 2024-07-18 | 2024-07-18 | Tower B | Foundation
48117 |  | Started |  | 2024-07-12 | 2025-02-11 | Foundation_Retail | 100 | 95 |  | 2024-07-12 | 2024-07-12 | 2025-09-29
48118 |  | Complete |  | 2024-07-12 | 2024-08-22 | Pour RT-1 | 100 | 100 |  | 2024-07-12 | 2024-07-12 | 2024-08-22 | 2024-08-22
48119 | Retail - Foundation P1 | Complete |  | 2024-07-12 | 2024-07-18 | Dressing & PCC | 100 | 100 |  | 2024-07-12 | 2024-07-12 | 2024-07-18 | 2024-07-18 | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48119 | Retail - Foundation P1 | Complete |  | 2024-07-12 | 2024-07-18 | Dressing & PCC | 100 | 100 |  | 2024-07-12 | 2024-07-12 | 2024-07-18 | 2024-07-18 | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48119 | Retail - Foundation P1 | Complete |  | 2024-07-12 | 2024-07-18 | Dressing & PCC | 100 | 100 |  | 2024-07-12 | 2024-07-12 | 2024-07-18 | 2024-07-18 | Retail | Foundation
39459 | Tower A - Super Structure - Core Wall Low Rise L26-27 | Complete | Core Wall RCC Works | 2024-07-13 | 2024-07-14 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-07-13 | 2024-07-13 | 2024-07-14 | 2024-07-14 | Tower A | Super Structure | L26 | RCC Super Structure | Core Wall RCC Works
40225 |  | Complete |  | 2024-07-13 | 2024-12-15 | L19-20 | 100 | 100 |  | 2024-07-13 | 2024-07-13 | 2024-12-15 | 2024-12-15
40225 |  | Complete |  | 2024-07-13 | 2024-12-15 | L19-20 | 100 | 100 |  | 2024-07-13 | 2024-07-13 | 2024-12-15 | 2024-12-15 |  |  |  | Finishes | Gypsum Plastering Works
40226 | Tower A - Super Structure - Finishes & MEP - L19 to L20 | Complete | Partition Wall-Blockwork | 2024-07-13 | 2024-08-09 | De-shuttering & Area clearance | 100 | 100 |  | 2024-07-13 | 2024-07-13 | 2024-08-09 | 2024-08-09 | Tower A | Super Structure | L19
44675 | Tower A | Started | Award of Packages | 2024-07-13 | 2024-08-23 | HVAC (Lift & Stairwell Pressurisation) | 100 | 70 |  | 2024-07-13 | 2024-07-13 | 2025-10-22 |  | Tower A | --
44737 |  | Complete |  | 2024-07-13 | 2024-08-18 | Pour 7 | 100 | 100 |  | 2024-07-13 | 2024-07-13 | 2024-08-18 | 2024-08-17
44738 | Tower B - Foundation - Pour 7 | Complete | PCC | 2024-07-13 | 2024-07-19 | PCC | 100 | 100 |  | 2024-07-13 | 2024-07-13 | 2024-07-19 | 2024-07-19 | Tower B | Foundation
39460 | Tower A - Super Structure - Core Wall Low Rise L26-27 | Milestone Started | Core Wall RCC Works | 2024-07-16 |  | ACS Form Closing & Alignment | 100 | 100 |  | 2024-07-16 | 2024-07-18 |  |  | Tower A | Super Structure | L26 | RCC Super Structure | Core Wall RCC Works
39461 | Tower A - Super Structure - Core Wall Low Rise L26-27 | Complete | Core Wall RCC Works | 2024-07-18 | 2024-07-18 | Casting | 100 | 100 |  | 2024-07-18 | 2024-07-18 | 2024-07-18 | 2024-07-18 | Tower A | Super Structure | L26 | RCC Super Structure | Core Wall RCC Works
44803 |  | Complete |  | 2024-07-18 | 2024-09-28 | Pour 5_B3 to B2 | 100 | 100 |  | 2024-07-18 | 2024-07-18 | 2024-09-28 | 2024-09-28
44804 | Tower B - Sub Structure - B3 to B2 - Pour 5 | Complete | RCC Works - Vertical | 2024-07-18 | 2024-07-29 | Col/ Wall Reinf. | 100 | 100 |  | 2024-07-18 | 2024-07-18 | 2024-07-29 | 2024-07-29 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
44804 | Tower B - Sub Structure - B3 to B2 - Pour 5 | Complete | RCC Works - Vertical | 2024-07-18 | 2024-07-29 | Col/ Wall Reinf. | 100 | 100 |  | 2024-07-18 | 2024-07-18 | 2024-07-29 | 2024-07-29 | Tower B | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
44805 | Tower B - Sub Structure - B3 to B2 - Pour 5 | Complete | RCC Works - Vertical | 2024-07-18 | 2024-08-01 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-07-18 | 2024-07-18 | 2024-08-01 | 2024-08-01 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
44805 | Tower B - Sub Structure - B3 to B2 - Pour 5 | Complete | RCC Works - Vertical | 2024-07-18 | 2024-08-01 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-07-18 | 2024-07-18 | 2024-08-01 | 2024-08-01 | Tower B | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
39462 | Tower A - Super Structure - Core Wall Low Rise L26-27 | Complete | Core Wall RCC Works | 2024-07-19 | 2024-07-19 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-07-19 | 2024-07-19 | 2024-07-19 | 2024-07-19 | Tower A | Super Structure | L26 | RCC Super Structure | Core Wall RCC Works
39871 | Tower A - Super Structure - Core & Outer Slab L22-23 | Complete | RCC Works - Slab | 2024-07-19 | 2024-07-19 | Outer Slab_TA | 100 | 100 |  | 2024-07-19 | 2024-07-19 | 2024-07-19 | 2024-07-19 | Tower A | Super Structure | L22 | RCC Sub Structure | RCC Works - Slab
44734 | Tower B - Foundation - Pour 6 | Complete | Raft RCC Works | 2024-07-19 | 2024-08-23 | Raft reinf. | 100 | 100 |  | 2024-07-19 | 2024-07-19 | 2024-08-23 | 2024-08-23 | Tower B | Foundation |  | RCC Sub Structure | Raft RCC Works
48120 | Retail - Foundation P1 | Complete |  | 2024-07-19 | 2024-07-25 | Liner Wall | 100 | 100 |  | 2024-07-19 | 2024-07-19 | 2024-07-25 | 2024-07-25 | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48120 | Retail - Foundation P1 | Complete |  | 2024-07-19 | 2024-07-25 | Liner Wall | 100 | 100 |  | 2024-07-19 | 2024-07-19 | 2024-07-25 | 2024-07-25 | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48120 | Retail - Foundation P1 | Complete |  | 2024-07-19 | 2024-07-25 | Liner Wall | 100 | 100 |  | 2024-07-19 | 2024-07-19 | 2024-07-25 | 2024-07-25 | Retail | Foundation
48121 | Retail - Foundation P1 | Complete |  | 2024-07-19 | 2024-07-27 | Waterproofing Horizontal | 100 | 100 |  | 2024-07-19 | 2024-07-19 | 2024-07-27 | 2024-07-27 | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48121 | Retail - Foundation P1 | Complete |  | 2024-07-19 | 2024-07-27 | Waterproofing Horizontal | 100 | 100 |  | 2024-07-19 | 2024-07-19 | 2024-07-27 | 2024-07-27 | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48121 | Retail - Foundation P1 | Complete |  | 2024-07-19 | 2024-07-27 | Waterproofing Horizontal | 100 | 100 |  | 2024-07-19 | 2024-07-19 | 2024-07-27 | 2024-07-27 | Retail | Foundation
39463 |  | Complete |  | 2024-07-20 | 2024-07-30 | Core Wall L27-28 | 100 | 100 |  | 2024-07-20 | 2024-07-20 | 2024-07-30 | 2024-07-30
39464 | Tower A - Super Structure - Core Wall Low Rise L27-28 | Complete | Core Wall RCC Works | 2024-07-20 | 2024-07-20 | Scaffolding & platform | 100 | 100 |  | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-07-20 | Tower A | Super Structure | L27 | RCC Super Structure | Core Wall RCC Works
39872 |  | Complete |  | 2024-07-20 | 2024-07-30 | L23-24 | 100 | 100 |  | 2024-07-20 | 2024-07-20 | 2024-07-30 | 2024-07-30
39872 |  | Complete |  | 2024-07-20 | 2024-07-30 | L23-24 | 100 | 100 |  | 2024-07-20 | 2024-07-20 | 2024-07-30 | 2024-07-30 |  |  |  | Finishes | Gypsum Plastering Works
39873 | Tower A - Super Structure - Core & Outer Slab L23-24 | Complete | RCC Works - Vertical | 2024-07-20 | 2024-07-30 | Outer Columns_TA | 100 | 100 |  | 2024-07-20 | 2024-07-20 | 2024-07-30 | 2024-07-30 | Tower A | Super Structure | L23 | RCC Sub Structure | RCC Works - Vertical
40229 |  | Complete |  | 2024-07-20 | 2024-12-30 | L20-21 | 100 | 100 |  | 2024-07-20 | 2024-07-20 | 2024-12-30 | 2024-12-30
40229 |  | Complete |  | 2024-07-20 | 2024-12-30 | L20-21 | 100 | 100 |  | 2024-07-20 | 2024-07-20 | 2024-12-30 | 2024-12-30 |  |  |  | Finishes | Gypsum Plastering Works
40230 | Tower A - Super Structure - Finishes & MEP - L20 to L21 | Complete | Partition Wall-Blockwork | 2024-07-20 | 2024-08-13 | De-shuttering & Area clearance | 100 | 100 |  | 2024-07-20 | 2024-07-20 | 2024-08-13 | 2024-08-13 | Tower A | Super Structure | L20
44710 | Tower B - Foundation - Pour 1A | Complete | Lift Pit RCC Works | 2024-07-20 | 2024-07-20 | Casting of pit wall & top section | 100 | 100 |  | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-07-20 | Tower B | Foundation |  | RCC Sub Structure | Lift Pit RCC Works
44739 | Tower B - Foundation - Pour 7 | Complete | HDPE Waterproofing | 2024-07-20 | 2024-07-26 | HDPE waterproofing laying | 100 | 100 |  | 2024-07-20 | 2024-07-20 | 2024-07-26 | 2024-07-26 | Tower B | Foundation
44806 | Tower B - Sub Structure - B3 to B2 - Pour 5 | Complete | RCC Works - Vertical | 2024-07-20 | 2024-08-03 | Col/ Wall Casting | 100 | 100 |  | 2024-07-20 | 2024-07-20 | 2024-08-03 | 2024-08-03 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
44806 | Tower B - Sub Structure - B3 to B2 - Pour 5 | Complete | RCC Works - Vertical | 2024-07-20 | 2024-08-03 | Col/ Wall Casting | 100 | 100 |  | 2024-07-20 | 2024-07-20 | 2024-08-03 | 2024-08-03 | Tower B | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
41091 |  | Started |  | 2024-07-24 | 2025-12-13 | L9-10 | 100 | 67 |  | 2024-07-24 | 2024-07-24 | 2026-01-05 |  |  |  |  | Finishes | Gypsum Plastering Works
41091 |  | Started |  | 2024-07-24 | 2025-12-13 | L9-10 | 100 | 67 |  | 2024-07-24 | 2024-07-24 | 2026-01-05
41092 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2024-07-24 | 2024-07-24 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 80 |  | 2024-07-24 | 2024-07-24 | 2025-11-24 |  | Tower A | Super Structure | L9 | MEP | FPS 1st Fix - MEP & Finishes
39465 | Tower A - Super Structure - Core Wall Low Rise L27-28 | Complete | Core Wall RCC Works | 2024-07-25 | 2024-07-27 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-07-25 | 2024-07-25 | 2024-07-27 | 2024-07-27 | Tower A | Super Structure | L27 | RCC Super Structure | Core Wall RCC Works
40482 | Tower A - Super Structure - Finishes & MEP - L8 to L9 | Complete | Gypsum Plastering Works | 2024-07-25 | 2024-08-03 | L8-9 | 100 | 100 |  | 2024-07-25 | 2024-07-25 | 2024-08-03 | 2025-05-12 | Tower A | Super Structure | L8 | Finishes | Gypsum Plastering Works
40482 | Tower A - Super Structure - Finishes & MEP - L8 to L9 | Complete | Gypsum Plastering Works | 2024-07-25 | 2024-08-03 | L8-9 | 100 | 100 |  | 2024-07-25 | 2024-07-25 | 2024-08-03 | 2025-05-12 | Tower A | Super Structure | L8
42236 |  | Started |  | 2024-07-25 | 2026-05-23 | L9-10 | 100 | 71 |  | 2024-07-25 | 2024-07-25 | 2026-05-21 |  |  |  |  | Finishes | Gypsum Plastering Works
42236 |  | Started |  | 2024-07-25 | 2026-05-23 | L9-10 | 100 | 71 |  | 2024-07-25 | 2024-07-25 | 2026-05-21
42237 |  | Started |  | 2024-07-25 | 2024-08-16 | MEP 1st Fixes & Waterproofing | 100 | 86 |  | 2024-07-25 | 2024-07-25 | 2025-09-13
42238 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Apartment Area | Started | FPS 1st Fix - MEP & Finishes | 2024-07-25 | 2024-07-26 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 80 |  | 2024-07-25 | 2024-07-25 | 2025-09-12 |  | Tower A | Super Structure | L9 | MEP | FPS 1st Fix - MEP & Finishes
42239 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Apartment Area | Started | Electrical 1st Fix - MEP & Finishes | 2024-07-25 | 2024-07-25 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 90 |  | 2024-07-25 | 2024-07-25 | 2025-09-11 |  | Tower A | Super Structure | L9 | MEP | Electrical 1st Fixes
42240 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Apartment Area | Started | PHE 1st Fix - MEP & Finishes | 2024-07-25 | 2024-07-26 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 80 |  | 2024-07-25 | 2024-07-25 | 2025-09-12 |  | Tower A | Super Structure | L9
42241 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Apartment Area | Started | Wet Area Waterproofing - MEP & Finishes | 2024-07-25 | 2024-07-26 | Wet Area Waterproofing | 100 | 90 |  | 2024-07-25 | 2024-07-25 | 2025-09-12 |  | Tower A | Super Structure | L9
48126 |  | Complete |  | 2024-07-25 | 2024-11-07 | Pour RT-2 | 100 | 100 |  | 2024-07-25 | 2024-07-25 | 2024-11-07 | 2024-11-07
48127 | Retail - Foundation P2 | Complete |  | 2024-07-25 | 2024-07-29 | Dressing & PCC | 100 | 100 |  | 2024-07-25 | 2024-07-25 | 2024-07-29 | 2024-07-29 | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48127 | Retail - Foundation P2 | Complete |  | 2024-07-25 | 2024-07-29 | Dressing & PCC | 100 | 100 |  | 2024-07-25 | 2024-07-25 | 2024-07-29 | 2024-07-29 | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48127 | Retail - Foundation P2 | Complete |  | 2024-07-25 | 2024-07-29 | Dressing & PCC | 100 | 100 |  | 2024-07-25 | 2024-07-25 | 2024-07-29 | 2024-07-29 | Retail | Foundation
39466 | Tower A - Super Structure - Core Wall Low Rise L27-28 | Complete | Core Wall RCC Works | 2024-07-26 | 2024-07-28 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-07-26 | 2024-07-26 | 2024-07-28 | 2024-07-28 | Tower A | Super Structure | L27 | RCC Super Structure | Core Wall RCC Works
39874 | Tower A - Super Structure - Core & Outer Slab L23-24 | Complete | RCC Works - Slab | 2024-07-26 | 2024-07-30 | Outer Slab_TA | 100 | 100 |  | 2024-07-26 | 2024-07-26 | 2024-07-30 | 2024-07-30 | Tower A | Super Structure | L23 | RCC Sub Structure | RCC Works - Slab
42206 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Apartment Area | Started | Cement Plastering in Wet Areas - MEP & Finishes | 2024-07-26 | 2024-07-26 | Cement Plastering in wet areas | 100 | 90 |  | 2024-07-26 | 2024-07-26 | 2025-09-13 |  | Tower A | Super Structure | L7
44807 | Tower B - Sub Structure - B3 to B2 - Pour 5 | Complete | RCC Works - Slab | 2024-07-26 | 2024-08-12 | Slab & Staircase Fwk. | 100 | 100 |  | 2024-07-26 | 2024-07-26 | 2024-08-12 | 2024-08-12 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
48122 | Retail - Foundation P1 | Complete |  | 2024-07-26 | 2024-07-27 | Waterproofing vertical - toe ht. | 100 | 100 |  | 2024-07-26 | 2024-07-26 | 2024-07-27 | 2024-07-27 | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48122 | Retail - Foundation P1 | Complete |  | 2024-07-26 | 2024-07-27 | Waterproofing vertical - toe ht. | 100 | 100 |  | 2024-07-26 | 2024-07-26 | 2024-07-27 | 2024-07-27 | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48122 | Retail - Foundation P1 | Complete |  | 2024-07-26 | 2024-07-27 | Waterproofing vertical - toe ht. | 100 | 100 |  | 2024-07-26 | 2024-07-26 | 2024-07-27 | 2024-07-27 | Retail | Foundation
40192 | Tower A - Super Structure - Finishes & MEP - L10 to L11 | Complete | Partition Wall-Blockwork | 2024-07-27 | 2024-08-01 | Staircase Area | 100 | 100 |  | 2024-07-27 | 2024-07-27 | 2024-08-01 | 2024-08-01 | Tower A | Super Structure | L10
40195 | Tower A - Super Structure - Finishes & MEP - L11 to L12 | Complete | Partition Wall-Blockwork | 2024-07-27 | 2024-08-03 | Partition Walls | 100 | 100 |  | 2024-07-27 | 2024-07-27 | 2024-08-03 | 2024-08-03 | Tower A | Super Structure | L11
44740 | Tower B - Foundation - Pour 7 | Complete | Raft RCC Works | 2024-07-27 | 2024-08-14 | Raft reinf. | 100 | 100 |  | 2024-07-27 | 2024-07-27 | 2024-08-14 | 2024-08-14 | Tower B | Foundation |  | RCC Sub Structure | Raft RCC Works
39467 | Tower A - Super Structure - Core Wall Low Rise L27-28 | Complete | Core Wall RCC Works | 2024-07-29 | 2024-07-29 | Casting | 100 | 100 |  | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | Tower A | Super Structure | L27 | RCC Super Structure | Core Wall RCC Works
48123 | Retail - Foundation P1 | Complete |  | 2024-07-29 | 2024-08-02 | RW toe foundation | 100 | 100 |  | 2024-07-29 | 2024-07-29 | 2024-08-02 | 2024-08-02 | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48123 | Retail - Foundation P1 | Complete |  | 2024-07-29 | 2024-08-02 | RW toe foundation | 100 | 100 |  | 2024-07-29 | 2024-07-29 | 2024-08-02 | 2024-08-02 | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48123 | Retail - Foundation P1 | Complete |  | 2024-07-29 | 2024-08-02 | RW toe foundation | 100 | 100 |  | 2024-07-29 | 2024-07-29 | 2024-08-02 | 2024-08-02 | Retail | Foundation
48124 | Retail - Foundation P1 | Complete |  | 2024-07-29 | 2024-08-12 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2024-07-29 | 2024-07-29 | 2024-08-12 | 2024-08-12 | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48124 | Retail - Foundation P1 | Complete |  | 2024-07-29 | 2024-08-12 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2024-07-29 | 2024-07-29 | 2024-08-12 | 2024-08-12 | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48124 | Retail - Foundation P1 | Complete |  | 2024-07-29 | 2024-08-12 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2024-07-29 | 2024-07-29 | 2024-08-12 | 2024-08-12 | Retail | Foundation
48128 | Retail - Foundation P2 | Complete |  | 2024-07-29 | 2024-08-01 | Liner Wall | 100 | 100 |  | 2024-07-29 | 2024-07-29 | 2024-08-01 | 2024-08-01 | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48128 | Retail - Foundation P2 | Complete |  | 2024-07-29 | 2024-08-01 | Liner Wall | 100 | 100 |  | 2024-07-29 | 2024-07-29 | 2024-08-01 | 2024-08-01 | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48128 | Retail - Foundation P2 | Complete |  | 2024-07-29 | 2024-08-01 | Liner Wall | 100 | 100 |  | 2024-07-29 | 2024-07-29 | 2024-08-01 | 2024-08-01 | Retail | Foundation
39468 | Tower A - Super Structure - Core Wall Low Rise L27-28 | Complete | Core Wall RCC Works | 2024-07-30 | 2024-07-30 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | Tower A | Super Structure | L27 | RCC Super Structure | Core Wall RCC Works
44781 | Tower B - Sub Structure - B3 to B2 - Pour 3 | Complete | RCC Works - Slab | 2024-07-30 | 2024-07-30 | Slab & Staircase Casting | 100 | 100 |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
39469 |  | Complete |  | 2024-07-31 | 2024-08-09 | Core Wall L28-29 | 100 | 100 |  | 2024-07-31 | 2024-07-31 | 2024-08-09 | 2024-08-09
39470 | Tower A - Super Structure - Core Wall Low Rise L28-29 | Complete | Core Wall RCC Works | 2024-07-31 | 2024-07-31 | Scaffolding & platform | 100 | 100 |  | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2024-07-31 | Tower A | Super Structure | L28 | RCC Super Structure | Core Wall RCC Works
39875 |  | Complete |  | 2024-07-31 | 2024-08-10 | L24-25 | 100 | 100 |  | 2024-07-31 | 2024-07-31 | 2024-08-10 | 2024-08-10
39875 |  | Complete |  | 2024-07-31 | 2024-08-10 | L24-25 | 100 | 100 |  | 2024-07-31 | 2024-07-31 | 2024-08-10 | 2024-08-10 |  |  |  | Finishes | Gypsum Plastering Works
39876 | Tower A - Super Structure - Core & Outer Slab L24-25 | Complete | RCC Works - Vertical | 2024-07-31 | 2024-08-09 | Outer Columns_TA | 100 | 100 |  | 2024-07-31 | 2024-07-31 | 2024-08-09 | 2024-08-09 | Tower A | Super Structure | L24 | RCC Sub Structure | RCC Works - Vertical
40233 |  | Complete |  | 2024-07-31 | 2024-12-19 | L21-22 | 100 | 100 |  | 2024-07-31 | 2024-07-31 | 2024-12-19 | 2024-12-19
40233 |  | Complete |  | 2024-07-31 | 2024-12-19 | L21-22 | 100 | 100 |  | 2024-07-31 | 2024-07-31 | 2024-12-19 | 2024-12-19 |  |  |  | Finishes | Gypsum Plastering Works
40234 | Tower A - Super Structure - Finishes & MEP - L21 to L22 | Complete | Partition Wall-Blockwork | 2024-07-31 | 2024-08-24 | De-shuttering & Area clearance | 100 | 100 |  | 2024-07-31 | 2024-07-31 | 2024-08-24 | 2024-08-24 | Tower A | Super Structure | L21
29802 |  | Not Committed |  | 2024-08-01 | 2029-03-31 | RERA Milestones | 100 | 0 |  | 2024-08-01 |  | 2029-03-31
29803 | Tower A | Not Committed |  | 2024-08-01 | 2028-03-31 | Tower A Milestones | 100 | 0 |  | 2024-08-01 |  | 2028-03-31 |  | Tower A | --
39152 |  | Complete |  | 2024-08-01 | 2024-11-13 | Construction of Transformer Room at B1 level | 100 | 100 |  | 2024-08-01 | 2024-08-01 | 2024-11-13 | 2024-11-13
39153 |  | Complete |  | 2024-08-01 | 2024-08-16 | Dismantling of Existing Puzzle Parking | 100 | 100 |  | 2024-08-01 | 2024-08-01 | 2024-08-16 | 2024-08-16
39176 |  | Complete |  | 2024-08-01 | 2024-11-27 | Construction of Chiller Room at B2 Level | 100 | 100 |  | 2024-08-01 | 2024-08-01 | 2024-11-27 | 2024-11-27
39177 |  | Complete |  | 2024-08-01 | 2024-08-16 | Dismantling of Existing Puzzle Parking | 100 | 100 |  | 2024-08-01 | 2024-08-01 | 2024-08-16 | 2024-08-16
39471 | Tower A - Super Structure - Core Wall Low Rise L28-29 | Complete | Core Wall RCC Works | 2024-08-01 | 2024-08-03 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-08-01 | 2024-08-01 | 2024-08-03 | 2024-08-03 | Tower A | Super Structure | L28 | RCC Super Structure | Core Wall RCC Works
48130 | Retail - Foundation P2 | Complete |  | 2024-08-01 | 2024-08-03 | Waterproofing vertical - toe ht. | 100 | 100 |  | 2024-08-01 | 2024-08-01 | 2024-08-03 | 2024-08-03 | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48130 | Retail - Foundation P2 | Complete |  | 2024-08-01 | 2024-08-03 | Waterproofing vertical - toe ht. | 100 | 100 |  | 2024-08-01 | 2024-08-01 | 2024-08-03 | 2024-08-03 | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48130 | Retail - Foundation P2 | Complete |  | 2024-08-01 | 2024-08-03 | Waterproofing vertical - toe ht. | 100 | 100 |  | 2024-08-01 | 2024-08-01 | 2024-08-03 | 2024-08-03 | Retail | Foundation
39472 | Tower A - Super Structure - Core Wall Low Rise L28-29 | Complete | Core Wall RCC Works | 2024-08-02 | 2024-08-08 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-08-02 | 2024-08-02 | 2024-08-08 | 2024-08-08 | Tower A | Super Structure | L28 | RCC Super Structure | Core Wall RCC Works
39877 | Tower A - Super Structure - Core & Outer Slab L24-25 | Complete | RCC Works - Slab | 2024-08-02 | 2024-08-10 | Outer Slab_TA | 100 | 100 |  | 2024-08-02 | 2024-08-02 | 2024-08-10 | 2024-08-10 | Tower A | Super Structure | L24 | RCC Sub Structure | RCC Works - Slab
40483 | Tower A - Super Structure - Finishes & MEP - L9 to L10 | Complete | Gypsum Plastering Works | 2024-08-02 | 2024-08-22 | L9-10 | 100 | 100 |  | 2024-08-02 | 2024-08-02 | 2024-08-22 | 2025-05-22 | Tower A | Super Structure | L9 | Finishes | Gypsum Plastering Works
40483 | Tower A - Super Structure - Finishes & MEP - L9 to L10 | Complete | Gypsum Plastering Works | 2024-08-02 | 2024-08-22 | L9-10 | 100 | 100 |  | 2024-08-02 | 2024-08-02 | 2024-08-22 | 2025-05-22 | Tower A | Super Structure | L9
42254 |  | Started |  | 2024-08-02 | 2026-05-30 | L10-11 | 100 | 83 |  | 2024-08-02 | 2024-08-02 | 2026-05-28 |  |  |  |  | Finishes | Gypsum Plastering Works
42254 |  | Started |  | 2024-08-02 | 2026-05-30 | L10-11 | 100 | 83 |  | 2024-08-02 | 2024-08-02 | 2026-05-28
42255 |  | Started |  | 2024-08-02 | 2024-09-10 | MEP 1st Fixes & Waterproofing | 100 | 86 |  | 2024-08-02 | 2024-08-02 | 2025-09-15
42256 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Apartment Area | Started | FPS 1st Fix - MEP & Finishes | 2024-08-02 | 2024-08-03 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 80 |  | 2024-08-02 | 2024-08-02 | 2025-09-12 |  | Tower A | Super Structure | L10 | MEP | FPS 1st Fix - MEP & Finishes
42257 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Apartment Area | Started | Electrical 1st Fix - MEP & Finishes | 2024-08-02 | 2024-08-02 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 90 |  | 2024-08-02 | 2024-08-02 | 2025-09-11 |  | Tower A | Super Structure | L10 | MEP | Electrical 1st Fixes
42258 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Apartment Area | Started | PHE 1st Fix - MEP & Finishes | 2024-08-02 | 2024-08-03 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 80 |  | 2024-08-02 | 2024-08-02 | 2025-09-12 |  | Tower A | Super Structure | L10
8363 |  | Started |  | 2024-08-03 | 2026-12-20 | Tower 14 | 100 | 16 |  | 2024-08-03 | 2024-08-03 | 2027-01-07
8364 |  | Started |  | 2024-08-03 | 2025-06-10 | Sub Structure Up to Podium | 100 | 55 |  | 2024-08-03 | 2024-08-03 | 2025-12-09
8365 |  | Started |  | 2024-08-03 | 2025-03-26 | Footings | 100 | 84 |  | 2024-08-03 | 2024-08-03 | 2025-10-04
8366 |  | Complete |  | 2024-08-03 | 2025-03-11 | Isolated & Combined Footings | 100 | 100 |  | 2024-08-03 | 2024-08-03 | 2025-10-04 | 2024-10-03
8367 | T-14-Sub structure Footings | Quality checked | PCC | 2024-08-03 | 2025-03-09 | PCC | 100 | 100 | CUM | 2024-08-03 | 2024-08-03 | 2025-10-01 | 2024-09-29
42224 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Apartment Area | Started | Cement Plastering in Wet Areas - MEP & Finishes | 2024-08-03 | 2024-08-03 | Cement Plastering in wet areas | 100 | 90 |  | 2024-08-03 | 2024-08-03 | 2025-09-13 |  | Tower A | Super Structure | L8
48129 | Retail - Foundation P2 | Complete |  | 2024-08-03 | 2024-08-13 | Waterproofing Horizontal | 100 | 100 |  | 2024-08-03 | 2024-08-03 | 2024-08-13 | 2024-08-13 | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48129 | Retail - Foundation P2 | Complete |  | 2024-08-03 | 2024-08-13 | Waterproofing Horizontal | 100 | 100 |  | 2024-08-03 | 2024-08-03 | 2024-08-13 | 2024-08-13 | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48129 | Retail - Foundation P2 | Complete |  | 2024-08-03 | 2024-08-13 | Waterproofing Horizontal | 100 | 100 |  | 2024-08-03 | 2024-08-03 | 2024-08-13 | 2024-08-13 | Retail | Foundation
48131 | Retail - Foundation P2 | Complete |  | 2024-08-03 | 2024-08-13 | RW toe foundation | 100 | 100 |  | 2024-08-03 | 2024-08-03 | 2024-08-13 | 2024-08-13 | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48131 | Retail - Foundation P2 | Complete |  | 2024-08-03 | 2024-08-13 | RW toe foundation | 100 | 100 |  | 2024-08-03 | 2024-08-03 | 2024-08-13 | 2024-08-13 | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48131 | Retail - Foundation P2 | Complete |  | 2024-08-03 | 2024-08-13 | RW toe foundation | 100 | 100 |  | 2024-08-03 | 2024-08-03 | 2024-08-13 | 2024-08-13 | Retail | Foundation
48264 |  | Started |  | 2024-08-03 | 2025-06-17 | Sub-Structure_Retail | 100 | 53 |  | 2024-08-03 | 2024-08-03 | 2025-11-03
48322 |  | Started |  | 2024-08-03 | 2025-03-17 | B3 to B2 | 100 | 62 |  | 2024-08-03 | 2024-08-03 | 2025-11-03
48322 |  | Started |  | 2024-08-03 | 2025-03-17 | B3 to B2 | 100 | 62 |  | 2024-08-03 | 2024-08-03 | 2025-11-03
48322 |  | Started |  | 2024-08-03 | 2025-03-17 | B3 to B2 | 100 | 62 |  | 2024-08-03 | 2024-08-03 | 2025-11-03
48343 |  | Complete |  | 2024-08-03 | 2025-02-18 | Retaining Wall_lift 1 (Grid PA-A onwards) | 100 | 100 |  | 2024-08-03 | 2024-08-03 | 2025-02-18 | 2025-02-18
48344 |  | Complete |  | 2024-08-03 | 2024-09-04 | Pour RT-1 | 100 | 100 |  | 2024-08-03 | 2024-08-03 | 2024-09-04 | 2024-09-04
48345 | Retail - Sub structure - B3 to B2 - P1 | Complete |  | 2024-08-03 | 2024-08-14 | Section 1_lift 1 | 100 | 100 |  | 2024-08-03 | 2024-08-03 | 2024-08-14 | 2024-08-14 | Retail | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
48345 | Retail - Sub structure - B3 to B2 - P1 | Complete |  | 2024-08-03 | 2024-08-14 | Section 1_lift 1 | 100 | 100 |  | 2024-08-03 | 2024-08-03 | 2024-08-14 | 2024-08-14 | Retail | Sub Structure | B3
39473 | Tower A - Super Structure - Core Wall Low Rise L28-29 | Complete | Core Wall RCC Works | 2024-08-08 | 2024-08-08 | Casting | 100 | 100 |  | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-08 | Tower A | Super Structure | L28 | RCC Super Structure | Core Wall RCC Works
40196 | Tower A - Super Structure - Finishes & MEP - L11 to L12 | Complete | Partition Wall-Blockwork | 2024-08-08 | 2024-08-13 | Staircase Area | 100 | 100 |  | 2024-08-08 | 2024-08-08 | 2024-08-13 | 2024-08-13 | Tower A | Super Structure | L11
40199 | Tower A - Super Structure - Finishes & MEP - L12 to L13 | Complete | Partition Wall-Blockwork | 2024-08-08 | 2024-08-16 | Partition Walls | 100 | 100 |  | 2024-08-08 | 2024-08-08 | 2024-08-16 | 2024-08-16 | Tower A | Super Structure | L12
44810 |  | Complete |  | 2024-08-08 | 2024-09-12 | Pour 4_B3 to B2 | 100 | 100 |  | 2024-08-08 | 2024-08-08 | 2024-09-12 | 2024-09-12
44811 | Tower B - Sub Structure - B3 to B2 - Pour 4 | Complete | RCC Works - Vertical | 2024-08-08 | 2024-08-16 | Col/ Wall Reinf. | 100 | 100 |  | 2024-08-08 | 2024-08-08 | 2024-08-16 | 2024-08-16 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
44811 | Tower B - Sub Structure - B3 to B2 - Pour 4 | Complete | RCC Works - Vertical | 2024-08-08 | 2024-08-16 | Col/ Wall Reinf. | 100 | 100 |  | 2024-08-08 | 2024-08-08 | 2024-08-16 | 2024-08-16 | Tower B | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
44812 | Tower B - Sub Structure - B3 to B2 - Pour 4 | Complete | RCC Works - Vertical | 2024-08-08 | 2024-08-23 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-08-08 | 2024-08-08 | 2024-08-23 | 2024-08-23 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
44812 | Tower B - Sub Structure - B3 to B2 - Pour 4 | Complete | RCC Works - Vertical | 2024-08-08 | 2024-08-23 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-08-08 | 2024-08-08 | 2024-08-23 | 2024-08-23 | Tower B | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
39474 | Tower A - Super Structure - Core Wall Low Rise L28-29 | Complete | Core Wall RCC Works | 2024-08-09 | 2024-08-09 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-08-09 | 2024-08-09 | 2024-08-09 | 2024-08-09 | Tower A | Super Structure | L28 | RCC Super Structure | Core Wall RCC Works
44718 | Tower B - Foundation - Pour 1B | Complete | Lift Pit RCC Works | 2024-08-09 | 2024-08-10 | Casting of pit wall & top section | 100 | 100 |  | 2024-08-09 | 2024-08-09 | 2024-08-10 | 2024-08-10 | Tower B | Foundation |  | RCC Sub Structure | Lift Pit RCC Works
39475 |  | Complete |  | 2024-08-10 | 2024-08-17 | Core Wall L29-30 | 100 | 100 |  | 2024-08-10 | 2024-08-10 | 2024-08-17 | 2024-08-17
39476 | Tower A - Super Structure - Core Wall Low Rise L29-30 | Complete | Core Wall RCC Works | 2024-08-10 | 2024-08-10 | Scaffolding & platform | 100 | 100 |  | 2024-08-10 | 2024-08-10 | 2024-08-10 | 2024-08-10 | Tower A | Super Structure | L29 | RCC Super Structure | Core Wall RCC Works
44748 | Tower B - Foundation - Pour 8 | Complete | Raft RCC Works | 2024-08-10 | 2024-08-10 | Checking & casting | 100 | 100 |  | 2024-08-10 | 2024-08-10 | 2024-08-10 | 2024-08-10 | Tower B | Foundation |  | RCC Sub Structure | Raft RCC Works
44808 | Tower B - Sub Structure - B3 to B2 - Pour 5 | Complete | RCC Works - Slab | 2024-08-10 | 2024-08-16 | Slab & Staircase Reinf. | 100 | 100 |  | 2024-08-10 | 2024-08-10 | 2024-08-16 | 2024-08-16 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
44813 | Tower B - Sub Structure - B3 to B2 - Pour 4 | Complete | RCC Works - Vertical | 2024-08-10 | 2024-08-29 | Col/ Wall Casting | 100 | 100 |  | 2024-08-10 | 2024-08-10 | 2024-08-29 | 2024-08-29 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
44813 | Tower B - Sub Structure - B3 to B2 - Pour 4 | Complete | RCC Works - Vertical | 2024-08-10 | 2024-08-29 | Col/ Wall Casting | 100 | 100 |  | 2024-08-10 | 2024-08-10 | 2024-08-29 | 2024-08-29 | Tower B | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
9436 |  | Started |  | 2024-08-12 | 2027-03-13 | Tower 16 | 100 | 37 |  | 2024-08-12 | 2024-08-12 | 2027-02-11
9437 |  | Started |  | 2024-08-12 | 2026-02-22 | Sub Structure Up to Podium | 100 | 64 |  | 2024-08-12 | 2024-08-12 | 2025-07-30
9438 |  | Started |  | 2024-08-12 | 2025-04-22 | Footings | 100 | 65 |  | 2024-08-12 | 2024-08-12 | 2025-06-25
9439 |  | Complete |  | 2024-08-12 | 2025-03-30 | Isolated & Combined Footings | 100 | 100 |  | 2024-08-12 | 2024-08-12 | 2025-03-30 | 2024-11-15
9440 | T-16-Sub structure Footings | Quality checked | PCC | 2024-08-12 | 2025-03-27 | PCC | 98 | 98 | CUM | 2024-08-12 | 2024-08-12 | 2025-03-27 | 2024-11-12
9444 |  | Started |  | 2024-08-12 | 2025-04-22 | Retaining Wall | 100 | 41 |  | 2024-08-12 | 2024-08-12 | 2025-06-25
9445 | T-16-Sub structure Retaining Wall | Started | PCC | 2024-08-12 | 2025-03-19 | PCC | 100 | 50 | Units | 2024-08-12 | 2024-08-12 | 2025-05-23
39477 | Tower A - Super Structure - Core Wall Low Rise L29-30 | Complete | Core Wall RCC Works | 2024-08-12 | 2024-08-14 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-08-12 | 2024-08-12 | 2024-08-14 | 2024-08-14 | Tower A | Super Structure | L29 | RCC Super Structure | Core Wall RCC Works
39878 |  | Complete |  | 2024-08-12 | 2024-08-19 | L25-26 | 100 | 100 |  | 2024-08-12 | 2024-08-12 | 2024-08-19 | 2024-08-19
39878 |  | Complete |  | 2024-08-12 | 2024-08-19 | L25-26 | 100 | 100 |  | 2024-08-12 | 2024-08-12 | 2024-08-19 | 2024-08-19 |  |  |  | Finishes | Gypsum Plastering Works
39879 | Tower A - Super Structure - Core & Outer Slab L25-26 | Complete | RCC Works - Vertical | 2024-08-12 | 2024-08-19 | Outer Columns_TA | 100 | 100 |  | 2024-08-12 | 2024-08-12 | 2024-08-19 | 2024-08-19 | Tower A | Super Structure | L25 | RCC Sub Structure | RCC Works - Vertical
40237 |  | Complete |  | 2024-08-12 | 2025-01-01 | L22-23 | 100 | 100 |  | 2024-08-12 | 2024-08-12 | 2025-01-01 | 2025-01-01
40237 |  | Complete |  | 2024-08-12 | 2025-01-01 | L22-23 | 100 | 100 |  | 2024-08-12 | 2024-08-12 | 2025-01-01 | 2025-01-01 |  |  |  | Finishes | Gypsum Plastering Works
40238 | Tower A - Super Structure - Finishes & MEP - L22 to L23 | Complete | Partition Wall-Blockwork | 2024-08-12 | 2024-09-05 | De-shuttering & Area clearance | 100 | 100 |  | 2024-08-12 | 2024-08-12 | 2024-09-05 | 2024-09-05 | Tower A | Super Structure | L22
48346 | Retail - Sub structure - B3 to B2 - P1 | Complete |  | 2024-08-12 | 2024-08-23 | Section 2_lift 1 | 100 | 100 |  | 2024-08-12 | 2024-08-12 | 2024-08-23 | 2024-08-23 | Retail | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
48346 | Retail - Sub structure - B3 to B2 - P1 | Complete |  | 2024-08-12 | 2024-08-23 | Section 2_lift 1 | 100 | 100 |  | 2024-08-12 | 2024-08-12 | 2024-08-23 | 2024-08-23 | Retail | Sub Structure | B3
39478 | Tower A - Super Structure - Core Wall Low Rise L29-30 | Complete | Core Wall RCC Works | 2024-08-13 | 2024-08-16 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-08-13 | 2024-08-13 | 2024-08-16 | 2024-08-16 | Tower A | Super Structure | L29 | RCC Super Structure | Core Wall RCC Works
44814 | Tower B - Sub Structure - B3 to B2 - Pour 4 | Complete | RCC Works - Slab | 2024-08-13 | 2024-09-03 | Slab & Staircase Fwk. | 100 | 100 |  | 2024-08-13 | 2024-08-13 | 2024-09-03 | 2024-09-03 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
48125 | Retail - Foundation P1 | Complete |  | 2024-08-13 | 2024-08-22 | Fwk & Casting_NTA | 100 | 100 |  | 2024-08-13 | 2024-08-13 | 2024-08-22 | 2024-08-22 | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48125 | Retail - Foundation P1 | Complete |  | 2024-08-13 | 2024-08-22 | Fwk & Casting_NTA | 100 | 100 |  | 2024-08-13 | 2024-08-13 | 2024-08-22 | 2024-08-22 | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48125 | Retail - Foundation P1 | Complete |  | 2024-08-13 | 2024-08-22 | Fwk & Casting_NTA | 100 | 100 |  | 2024-08-13 | 2024-08-13 | 2024-08-22 | 2024-08-22 | Retail | Foundation
48132 | Retail - Foundation P2 | Complete |  | 2024-08-13 | 2024-08-31 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2024-08-13 | 2024-08-13 | 2024-08-31 | 2024-08-31 | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48132 | Retail - Foundation P2 | Complete |  | 2024-08-13 | 2024-08-31 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2024-08-13 | 2024-08-13 | 2024-08-31 | 2024-08-31 | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48132 | Retail - Foundation P2 | Complete |  | 2024-08-13 | 2024-08-31 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2024-08-13 | 2024-08-13 | 2024-08-31 | 2024-08-31 | Retail | Foundation
39880 | Tower A - Super Structure - Core & Outer Slab L25-26 | Complete | RCC Works - Slab | 2024-08-14 | 2024-08-19 | Outer Slab_TA | 100 | 100 |  | 2024-08-14 | 2024-08-14 | 2024-08-19 | 2024-08-19 | Tower A | Super Structure | L25 | RCC Sub Structure | RCC Works - Slab
40484 | Tower A - Super Structure - Finishes & MEP - L10 to L11 | Complete | Gypsum Plastering Works | 2024-08-14 | 2025-04-28 | L10-11 | 100 | 100 |  | 2024-08-14 | 2024-08-14 | 2025-04-28 | 2025-04-28 | Tower A | Super Structure | L10 | Finishes | Gypsum Plastering Works
40484 | Tower A - Super Structure - Finishes & MEP - L10 to L11 | Complete | Gypsum Plastering Works | 2024-08-14 | 2025-04-28 | L10-11 | 100 | 100 |  | 2024-08-14 | 2024-08-14 | 2025-04-28 | 2025-04-28 | Tower A | Super Structure | L10
42259 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Apartment Area | Started | Wet Area Waterproofing - MEP & Finishes | 2024-08-14 | 2024-08-16 | Wet Area Waterproofing | 100 | 90 |  | 2024-08-14 | 2024-08-14 | 2025-09-13 |  | Tower A | Super Structure | L10
42272 |  | Started |  | 2024-08-14 | 2026-05-30 | L11-12 | 100 | 82 |  | 2024-08-14 | 2024-08-14 | 2026-05-28 |  |  |  |  | Finishes | Gypsum Plastering Works
42272 |  | Started |  | 2024-08-14 | 2026-05-30 | L11-12 | 100 | 82 |  | 2024-08-14 | 2024-08-14 | 2026-05-28
42273 |  | Started |  | 2024-08-14 | 2024-09-10 | MEP 1st Fixes & Waterproofing | 100 | 86 |  | 2024-08-14 | 2024-08-14 | 2025-09-13
42274 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Apartment Area | Started | FPS 1st Fix - MEP & Finishes | 2024-08-14 | 2024-08-16 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 80 |  | 2024-08-14 | 2024-08-14 | 2025-09-12 |  | Tower A | Super Structure | L11 | MEP | FPS 1st Fix - MEP & Finishes
42275 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Apartment Area | Started | Electrical 1st Fix - MEP & Finishes | 2024-08-14 | 2024-08-14 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 90 |  | 2024-08-14 | 2024-08-14 | 2025-09-11 |  | Tower A | Super Structure | L11 | MEP | Electrical 1st Fixes
42276 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Apartment Area | Started | PHE 1st Fix - MEP & Finishes | 2024-08-14 | 2024-08-16 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 80 |  | 2024-08-14 | 2024-08-14 | 2025-09-12 |  | Tower A | Super Structure | L11
42277 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Apartment Area | Started | Wet Area Waterproofing - MEP & Finishes | 2024-08-14 | 2024-08-16 | Wet Area Waterproofing | 100 | 90 |  | 2024-08-14 | 2024-08-14 | 2025-09-12 |  | Tower A | Super Structure | L11
9446 | T-16-Sub structure Retaining Wall | Started | Reinforcement | 2024-08-15 | 2025-04-22 | Reinforcement | 15 | 15 | MT | 2024-08-15 | 2024-08-15 | 2025-06-25
39186 |  | Complete |  | 2024-08-16 | 2024-10-25 | Shifting of Carparks from B1 Level | 100 | 100 |  | 2024-08-16 | 2024-08-16 | 2024-10-25 | 2024-10-25
39187 |  | Complete |  | 2024-08-16 | 2024-10-29 | Shifting of Carparks from B2 Level | 100 | 100 |  | 2024-08-16 | 2024-08-16 | 2024-10-29 | 2024-10-29
39479 | Tower A - Super Structure - Core Wall Low Rise L29-30 | Complete | Core Wall RCC Works | 2024-08-16 | 2024-08-16 | Casting | 100 | 100 |  | 2024-08-16 | 2024-08-16 | 2024-08-16 | 2024-08-16 | Tower A | Super Structure | L29 | RCC Super Structure | Core Wall RCC Works
42242 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Apartment Area | Started | Cement Plastering in Wet Areas - MEP & Finishes | 2024-08-16 | 2024-08-16 | Cement Plastering in wet areas | 100 | 90 |  | 2024-08-16 | 2024-08-16 | 2025-09-13 |  | Tower A | Super Structure | L9
44741 | Tower B - Foundation - Pour 7 | Complete | Raft RCC Works | 2024-08-16 | 2024-08-17 | Fwk fix | 100 | 100 |  | 2024-08-16 | 2024-08-16 | 2024-08-17 | 2024-08-17 | Tower B | Foundation |  | RCC Sub Structure | Raft RCC Works
44768 |  | Complete |  | 2024-08-16 | 2024-09-21 | Pour 1A & 2_B3 to B2 | 100 | 100 |  | 2024-08-16 | 2024-08-16 | 2024-09-21 | 2024-09-21
44769 | Tower B - Sub Structure - B3 to B2 - Pour 1A & 2 | Complete | RCC Works - Vertical | 2024-08-16 | 2024-09-03 | Col/ Wall Reinf. | 100 | 100 |  | 2024-08-16 | 2024-08-16 | 2024-09-03 | 2024-09-03 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
44769 | Tower B - Sub Structure - B3 to B2 - Pour 1A & 2 | Complete | RCC Works - Vertical | 2024-08-16 | 2024-09-03 | Col/ Wall Reinf. | 100 | 100 |  | 2024-08-16 | 2024-08-16 | 2024-09-03 | 2024-09-03 | Tower B | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
48323 |  | Started |  | 2024-08-16 | 2025-02-26 | Retaining Wall_lift 2 (Grid PA-A onwards) | 100 | 57 |  | 2024-08-16 | 2024-08-16 | 2025-10-15
48324 |  | Complete |  | 2024-08-16 | 2024-09-13 | Pour RT-1 | 100 | 100 |  | 2024-08-16 | 2024-08-16 | 2024-09-13 | 2024-09-13
48325 | Retail - Sub structure - B3 to B2 - P1 | Complete |  | 2024-08-16 | 2024-08-30 | Section 1_lift 2 | 100 | 100 |  | 2024-08-16 | 2024-08-16 | 2024-08-30 | 2024-08-30 | Retail | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
48325 | Retail - Sub structure - B3 to B2 - P1 | Complete |  | 2024-08-16 | 2024-08-30 | Section 1_lift 2 | 100 | 100 |  | 2024-08-16 | 2024-08-16 | 2024-08-30 | 2024-08-30 | Retail | Sub Structure | B3
48347 | Retail - Sub structure - B3 to B2 - P1 | Complete |  | 2024-08-16 | 2024-08-30 | Section 3_lift 1 | 100 | 100 |  | 2024-08-16 | 2024-08-16 | 2024-08-30 | 2024-08-30 | Retail | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
48347 | Retail - Sub structure - B3 to B2 - P1 | Complete |  | 2024-08-16 | 2024-08-30 | Section 3_lift 1 | 100 | 100 |  | 2024-08-16 | 2024-08-16 | 2024-08-30 | 2024-08-30 | Retail | Sub Structure | B3
39154 |  | Complete |  | 2024-08-17 | 2024-09-30 | Lightweight Filling in the Parking Pits | 100 | 100 |  | 2024-08-17 | 2024-08-17 | 2024-09-30 | 2024-09-30
39480 | Tower A - Super Structure - Core Wall Low Rise L29-30 | Complete | Core Wall RCC Works | 2024-08-17 | 2024-08-17 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-08-17 | Tower A | Super Structure | L29 | RCC Super Structure | Core Wall RCC Works
40200 | Tower A - Super Structure - Finishes & MEP - L12 to L13 | Complete | Partition Wall-Blockwork | 2024-08-17 | 2024-08-29 | Staircase Area | 100 | 100 |  | 2024-08-17 | 2024-08-17 | 2024-08-29 | 2024-08-29 | Tower A | Super Structure | L12
40203 | Tower A - Super Structure - Finishes & MEP - L13 to L14 | Complete | Partition Wall-Blockwork | 2024-08-17 | 2024-08-31 | Partition Walls | 100 | 100 |  | 2024-08-17 | 2024-08-17 | 2024-08-31 | 2024-08-31 | Tower A | Super Structure | L13
48134 |  | Complete |  | 2024-08-17 | 2025-01-19 | Pour RT-3 | 100 | 100 |  | 2024-08-17 | 2024-08-17 | 2025-01-19 | 2025-01-19
48138 | Retail - Foundation P3 | Complete |  | 2024-08-17 | 2024-08-23 | Waterproofing vertical - toe ht. | 100 | 100 |  | 2024-08-17 | 2024-08-17 | 2024-08-23 | 2024-08-23 | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48138 | Retail - Foundation P3 | Complete |  | 2024-08-17 | 2024-08-23 | Waterproofing vertical - toe ht. | 100 | 100 |  | 2024-08-17 | 2024-08-17 | 2024-08-23 | 2024-08-23 | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48138 | Retail - Foundation P3 | Complete |  | 2024-08-17 | 2024-08-23 | Waterproofing vertical - toe ht. | 100 | 100 |  | 2024-08-17 | 2024-08-17 | 2024-08-23 | 2024-08-23 | Retail | Foundation
44742 | Tower B - Foundation - Pour 7 | Milestone Started | Raft RCC Works | 2024-08-18 |  | Checking & casting | 100 | 100 |  | 2024-08-18 | 2024-08-16 |  |  | Tower B | Foundation |  | RCC Sub Structure | Raft RCC Works
8371 |  | Started |  | 2024-08-20 | 2025-03-26 | Retaining Wall | 100 | 60 |  | 2024-08-20 | 2024-08-20 | 2025-05-30
8372 | T-14-Sub structure Retaining Wall | Started | PCC | 2024-08-20 | 2025-03-12 | PCC | 100 | 75 | Units | 2024-08-20 | 2024-08-20 | 2025-05-17
8916 |  | Started |  | 2024-08-20 | 2027-01-13 | Tower 15 | 100 | 24 |  | 2024-08-20 | 2024-08-20 | 2027-01-08
8917 |  | Started |  | 2024-08-20 | 2025-06-24 | Sub Structure Up to Podium | 100 | 40 |  | 2024-08-20 | 2024-08-20 | 2025-11-20
8918 |  | Started |  | 2024-08-20 | 2025-05-04 | Footings | 100 | 78 |  | 2024-08-20 | 2024-08-20 | 2025-11-20
8924 |  | Started |  | 2024-08-20 | 2025-05-04 | Retaining Wall | 100 | 47 |  | 2024-08-20 | 2024-08-20 | 2025-07-06
8925 | T-15-Sub structure Retaining Wall | Started | PCC | 2024-08-20 | 2025-03-22 | PCC | 100 | 50 | Units | 2024-08-20 | 2024-08-20 | 2025-05-27
8373 | T-14-Sub structure Retaining Wall | Started | Reinforcement | 2024-08-21 | 2025-03-26 | Reinforcement | 8.3 | 8 | MT | 2024-08-21 | 2024-08-21 | 2025-05-30
8374 | T-14-Sub structure Retaining Wall | Started | Shuttering | 2024-08-21 | 2025-03-19 | Shuttering | 1037.3 | 70 | Sqm | 2024-08-21 | 2024-08-21 | 2025-05-23
8926 | T-15-Sub structure Retaining Wall | Started | Reinforcement | 2024-08-21 | 2025-05-04 | Reinforcement | 15 | 15 | MT | 2024-08-21 | 2024-08-21 | 2025-07-06
8927 | T-15-Sub structure Retaining Wall | Started | Shuttering | 2024-08-21 | 2025-04-12 | Shuttering | 1001.9 | 200.38 | Sqm | 2024-08-21 | 2024-08-21 | 2025-06-15
8928 | T-15-Sub structure Retaining Wall | Started | RCC | 2024-08-22 | 2025-04-11 | RCC | 100.2 | 15 | CUM | 2024-08-22 | 2024-08-22 | 2025-06-14
8928 | T-15-Sub structure Retaining Wall | Started | RCC | 2024-08-22 | 2025-04-11 | RCC | 100.2 | 15 | CUM | 2024-08-22 | 2024-08-22 | 2025-06-14
9447 | T-16-Sub structure Retaining Wall | Started | Shuttering | 2024-08-22 | 2025-04-08 | Shuttering | 1600.8 | 15 | Sqm | 2024-08-22 | 2024-08-22 | 2025-06-11
39481 |  | Complete |  | 2024-08-22 | 2024-08-25 | Core Wall L30-31 | 100 | 100 |  | 2024-08-22 | 2024-08-22 | 2024-08-25 | 2024-08-24
39482 | Tower A - Super Structure - Core Wall Low Rise L30-31 | Complete | Core Wall RCC Works | 2024-08-22 | 2024-08-22 | Scaffolding & platform | 100 | 100 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | Tower A | Super Structure | L30 | RCC Super Structure | Core Wall RCC Works
39881 |  | Complete |  | 2024-08-22 | 2024-08-27 | L26-27 | 100 | 100 |  | 2024-08-22 | 2024-08-22 | 2024-08-27 | 2024-08-27
39881 |  | Complete |  | 2024-08-22 | 2024-08-27 | L26-27 | 100 | 100 |  | 2024-08-22 | 2024-08-22 | 2024-08-27 | 2024-08-27 |  |  |  | Finishes | Gypsum Plastering Works
39882 | Tower A - Super Structure - Core & Outer Slab L26-27 | Complete | RCC Works - Vertical | 2024-08-22 | 2024-08-27 | Outer Columns_TA | 100 | 100 |  | 2024-08-22 | 2024-08-22 | 2024-08-27 | 2024-08-27 | Tower A | Super Structure | L26 | RCC Sub Structure | RCC Works - Vertical
40241 |  | Complete |  | 2024-08-22 | 2025-01-09 | L23-24 | 100 | 100 |  | 2024-08-22 | 2024-08-22 | 2025-01-09 | 2025-01-09
40241 |  | Complete |  | 2024-08-22 | 2025-01-09 | L23-24 | 100 | 100 |  | 2024-08-22 | 2024-08-22 | 2025-01-09 | 2025-01-09 |  |  |  | Finishes | Gypsum Plastering Works
40242 | Tower A - Super Structure - Finishes & MEP - L23 to L24 | Complete | Partition Wall-Blockwork | 2024-08-22 | 2024-09-12 | De-shuttering & Area clearance | 100 | 100 |  | 2024-08-22 | 2024-08-22 | 2024-09-12 | 2024-09-12 | Tower A | Super Structure | L23
9956 |  | Started |  | 2024-08-23 | 2026-12-26 | Tower 21 | 100 | 35 |  | 2024-08-23 | 2024-08-23 | 2026-11-10
9957 |  | Started |  | 2024-08-23 | 2025-06-12 | Sub Structure Up to Podium | 100 | 54 |  | 2024-08-23 | 2024-08-23 | 2025-10-08
9958 |  | Started |  | 2024-08-23 | 2025-03-16 | Footings | 100 | 96 |  | 2024-08-23 | 2024-08-23 | 2025-10-08
9964 |  | Started |  | 2024-08-23 | 2025-03-16 | Retaining Wall | 100 | 89 |  | 2024-08-23 | 2024-08-23 | 2025-05-20
9965 | T-21-Sub structure Retaining Wall | Quality checked | PCC | 2024-08-23 | 2024-10-10 | PCC | 14 | 14 | CUM | 2024-08-23 | 2024-08-23 | 2024-10-10 | 2024-10-10
39483 | Tower A - Super Structure - Core Wall Low Rise L30-31 | Complete | Core Wall RCC Works | 2024-08-23 | 2024-08-23 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-08-23 | 2024-08-23 | 2024-08-23 | 2024-08-23 | Tower A | Super Structure | L30 | RCC Super Structure | Core Wall RCC Works
44770 | Tower B - Sub Structure - B3 to B2 - Pour 1A & 2 | Complete | RCC Works - Vertical | 2024-08-23 | 2024-09-07 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-08-23 | 2024-08-23 | 2024-09-07 | 2024-09-07 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
44770 | Tower B - Sub Structure - B3 to B2 - Pour 1A & 2 | Complete | RCC Works - Vertical | 2024-08-23 | 2024-09-07 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-08-23 | 2024-08-23 | 2024-09-07 | 2024-09-07 | Tower B | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
48139 | Retail - Foundation P3 | Complete |  | 2024-08-23 | 2024-09-02 | RW toe foundation | 100 | 100 |  | 2024-08-23 | 2024-08-23 | 2024-09-02 | 2024-09-02 | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48139 | Retail - Foundation P3 | Complete |  | 2024-08-23 | 2024-09-02 | RW toe foundation | 100 | 100 |  | 2024-08-23 | 2024-08-23 | 2024-09-02 | 2024-09-02 | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48139 | Retail - Foundation P3 | Complete |  | 2024-08-23 | 2024-09-02 | RW toe foundation | 100 | 100 |  | 2024-08-23 | 2024-08-23 | 2024-09-02 | 2024-09-02 | Retail | Foundation
48363 |  | Complete |  | 2024-08-23 | 2025-01-30 | Pour RT-1 | 100 | 100 |  | 2024-08-23 | 2024-08-23 | 2025-01-30 | 2025-01-30
48364 | Retail - Sub structure - B3 to B2 - P1 | Complete |  | 2024-08-23 | 2024-09-14 | Columns/ Walls_NTA | 100 | 100 |  | 2024-08-23 | 2024-08-23 | 2024-09-14 | 2024-09-14 | Retail | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
48364 | Retail - Sub structure - B3 to B2 - P1 | Complete |  | 2024-08-23 | 2024-09-14 | Columns/ Walls_NTA | 100 | 100 |  | 2024-08-23 | 2024-08-23 | 2024-09-14 | 2024-09-14 | Retail | Sub Structure | B3
39218 |  | Complete |  | 2024-08-24 | 2024-10-04 | Low Side Installation - Laying of Buried Cabling till Centurion B01 | 100 | 100 |  | 2024-08-24 | 2024-08-24 | 2024-10-04 | 2024-10-04
39240 |  | Started |  | 2024-08-24 | 2024-11-15 | Basement Ventilation Works with T & C (B01 and B02) | 100 | 50 |  | 2024-08-24 | 2024-08-24 | 2025-12-03
39484 | Tower A - Super Structure - Core Wall Low Rise L30-31 | Complete | Core Wall RCC Works | 2024-08-24 | 2024-08-24 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-08-24 | Tower A | Super Structure | L30 | RCC Super Structure | Core Wall RCC Works
39485 | Tower A - Super Structure - Core Wall Low Rise L30-31 | Complete | Core Wall RCC Works | 2024-08-24 | 2024-08-24 | Casting | 100 | 100 |  | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-08-24 | Tower A | Super Structure | L30 | RCC Super Structure | Core Wall RCC Works
39883 | Tower A - Super Structure - Core & Outer Slab L26-27 | Complete | RCC Works - Slab | 2024-08-24 | 2024-08-27 | Outer Slab_TA | 100 | 100 |  | 2024-08-24 | 2024-08-24 | 2024-08-27 | 2024-08-27 | Tower A | Super Structure | L26 | RCC Sub Structure | RCC Works - Slab
44735 | Tower B - Foundation - Pour 6 | Complete | Raft RCC Works | 2024-08-24 | 2024-08-29 | Fwk fix | 100 | 100 |  | 2024-08-24 | 2024-08-24 | 2024-08-29 | 2024-08-29 | Tower B | Foundation |  | RCC Sub Structure | Raft RCC Works
48326 | Retail - Sub structure - B3 to B2 - P1 | Complete |  | 2024-08-24 | 2024-09-04 | Section 2_lift 2 | 100 | 100 |  | 2024-08-24 | 2024-08-24 | 2024-09-04 | 2024-09-04 | Retail | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
48326 | Retail - Sub structure - B3 to B2 - P1 | Complete |  | 2024-08-24 | 2024-09-04 | Section 2_lift 2 | 100 | 100 |  | 2024-08-24 | 2024-08-24 | 2024-09-04 | 2024-09-04 | Retail | Sub Structure | B3
48348 | Retail - Sub structure - B3 to B2 - P1 | Complete |  | 2024-08-24 | 2024-09-04 | Section 4_lift 1 | 100 | 100 |  | 2024-08-24 | 2024-08-24 | 2024-09-04 | 2024-09-04 | Retail | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
48348 | Retail - Sub structure - B3 to B2 - P1 | Complete |  | 2024-08-24 | 2024-09-04 | Section 4_lift 1 | 100 | 100 |  | 2024-08-24 | 2024-08-24 | 2024-09-04 | 2024-09-04 | Retail | Sub Structure | B3
8375 | T-14-Sub structure Retaining Wall | Started | RCC | 2024-08-25 | 2025-03-21 | RCC | 103.73 | 65 | CUM | 2024-08-25 | 2024-08-25 | 2025-05-25
8375 | T-14-Sub structure Retaining Wall | Started | RCC | 2024-08-25 | 2025-03-21 | RCC | 103.73 | 65 | CUM | 2024-08-25 | 2024-08-25 | 2025-05-25
9448 | T-16-Sub structure Retaining Wall | Started | RCC | 2024-08-25 | 2025-04-08 | RCC | 160.1 | 15 | CUM | 2024-08-25 | 2024-08-25 | 2025-06-11
9448 | T-16-Sub structure Retaining Wall | Started | RCC | 2024-08-25 | 2025-04-08 | RCC | 160.1 | 15 | CUM | 2024-08-25 | 2024-08-25 | 2025-06-11
39486 | Tower A - Super Structure - Core Wall Low Rise L30-31 | Milestone Started | Core Wall RCC Works | 2024-08-25 |  | ACS Form Release & jump to next level | 100 | 100 |  | 2024-08-25 | 2024-08-29 |  |  | Tower A | Super Structure | L30 | RCC Super Structure | Core Wall RCC Works
39487 |  | Complete |  | 2024-08-29 | 2024-09-02 | Core Wall L31-32 | 100 | 100 |  | 2024-08-29 | 2024-08-29 | 2024-09-02 | 2024-09-02
39488 | Tower A - Super Structure - Core Wall Low Rise L31-32 | Complete | Core Wall RCC Works | 2024-08-29 | 2024-08-29 | Scaffolding & platform | 100 | 100 |  | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-08-29 | Tower A | Super Structure | L31 | RCC Super Structure | Core Wall RCC Works
39884 |  | Complete |  | 2024-08-29 | 2024-09-06 | L27-28 | 100 | 100 |  | 2024-08-29 | 2024-08-29 | 2024-09-06 | 2024-09-06
39884 |  | Complete |  | 2024-08-29 | 2024-09-06 | L27-28 | 100 | 100 |  | 2024-08-29 | 2024-08-29 | 2024-09-06 | 2024-09-06 |  |  |  | Finishes | Gypsum Plastering Works
39885 | Tower A - Super Structure - Core & Outer Slab L27-28 | Complete | RCC Works - Vertical | 2024-08-29 | 2024-09-04 | Outer Columns_TA | 100 | 100 |  | 2024-08-29 | 2024-08-29 | 2024-09-04 | 2024-09-04 | Tower A | Super Structure | L27 | RCC Sub Structure | RCC Works - Vertical
40245 |  | Complete |  | 2024-08-29 | 2025-01-17 | L24-25 | 100 | 100 |  | 2024-08-29 | 2024-08-29 | 2025-01-17 | 2025-01-17
40245 |  | Complete |  | 2024-08-29 | 2025-01-17 | L24-25 | 100 | 100 |  | 2024-08-29 | 2024-08-29 | 2025-01-17 | 2025-01-17 |  |  |  | Finishes | Gypsum Plastering Works
40246 | Tower A - Super Structure - Finishes & MEP - L24 to L25 | Complete | Partition Wall-Blockwork | 2024-08-29 | 2024-09-16 | De-shuttering & Area clearance | 100 | 100 |  | 2024-08-29 | 2024-08-29 | 2024-09-16 | 2024-09-16 | Tower A | Super Structure | L24
41107 |  | Started |  | 2024-08-29 | 2025-12-19 | L10-11 | 100 | 66 |  | 2024-08-29 | 2024-08-29 | 2026-01-10 |  |  |  |  | Finishes | Gypsum Plastering Works
41107 |  | Started |  | 2024-08-29 | 2025-12-19 | L10-11 | 100 | 66 |  | 2024-08-29 | 2024-08-29 | 2026-01-10
41108 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2024-08-29 | 2024-08-29 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 80 |  | 2024-08-29 | 2024-08-29 | 2025-11-29 |  | Tower A | Super Structure | L10 | MEP | FPS 1st Fix - MEP & Finishes
44736 | Tower B - Foundation - Pour 6 | Complete | Raft RCC Works | 2024-08-29 | 2024-08-29 | Checking & casting | 100 | 100 |  | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-08-29 | Tower B | Foundation |  | RCC Sub Structure | Raft RCC Works
44771 | Tower B - Sub Structure - B3 to B2 - Pour 1A & 2 | Complete | RCC Works - Vertical | 2024-08-29 | 2024-09-10 | Col/ Wall Casting | 100 | 100 |  | 2024-08-29 | 2024-08-29 | 2024-09-10 | 2024-09-10 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
44771 | Tower B - Sub Structure - B3 to B2 - Pour 1A & 2 | Complete | RCC Works - Vertical | 2024-08-29 | 2024-09-10 | Col/ Wall Casting | 100 | 100 |  | 2024-08-29 | 2024-08-29 | 2024-09-10 | 2024-09-10 | Tower B | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
39489 | Tower A - Super Structure - Core Wall Low Rise L31-32 | Complete | Core Wall RCC Works | 2024-08-30 | 2024-08-30 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-08-30 | 2024-08-30 | 2024-08-30 | 2024-08-30 | Tower A | Super Structure | L31 | RCC Super Structure | Core Wall RCC Works
39490 | Tower A - Super Structure - Core Wall Low Rise L31-32 | Complete | Core Wall RCC Works | 2024-08-30 | 2024-08-31 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-08-30 | 2024-08-30 | 2024-08-31 | 2024-08-31 | Tower A | Super Structure | L31 | RCC Super Structure | Core Wall RCC Works
40485 | Tower A - Super Structure - Finishes & MEP - L11 to L12 | Complete | Gypsum Plastering Works | 2024-08-30 | 2024-09-18 | L11-12 | 100 | 100 |  | 2024-08-30 | 2024-08-30 | 2024-09-18 | 2025-05-20 | Tower A | Super Structure | L11 | Finishes | Gypsum Plastering Works
40485 | Tower A - Super Structure - Finishes & MEP - L11 to L12 | Complete | Gypsum Plastering Works | 2024-08-30 | 2024-09-18 | L11-12 | 100 | 100 |  | 2024-08-30 | 2024-08-30 | 2024-09-18 | 2025-05-20 | Tower A | Super Structure | L11
42290 |  | Started |  | 2024-08-30 | 2026-05-30 | L12-13 | 100 | 82 |  | 2024-08-30 | 2024-08-30 | 2026-05-28 |  |  |  |  | Finishes | Gypsum Plastering Works
42290 |  | Started |  | 2024-08-30 | 2026-05-30 | L12-13 | 100 | 82 |  | 2024-08-30 | 2024-08-30 | 2026-05-28
42291 |  | Started |  | 2024-08-30 | 2024-09-19 | MEP 1st Fixes | 100 | 86 |  | 2024-08-30 | 2024-08-30 | 2025-09-13
42292 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Apartment Area | Started | FPS 1st Fix - MEP & Finishes | 2024-08-30 | 2024-08-31 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 80 |  | 2024-08-30 | 2024-08-30 | 2025-09-12 |  | Tower A | Super Structure | L12 | MEP | FPS 1st Fix - MEP & Finishes
42293 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Apartment Area | Started | Electrical 1st Fix - MEP & Finishes | 2024-08-30 | 2024-08-30 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 90 |  | 2024-08-30 | 2024-08-30 | 2025-09-11 |  | Tower A | Super Structure | L12 | MEP | Electrical 1st Fixes
42294 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Apartment Area | Started | PHE 1st Fix - MEP & Finishes | 2024-08-30 | 2024-08-31 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 80 |  | 2024-08-30 | 2024-08-30 | 2025-09-12 |  | Tower A | Super Structure | L12
42295 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Apartment Area | Started | Wet Area Waterproofing - MEP & Finishes | 2024-08-30 | 2024-08-31 | Wet Area Waterproofing | 100 | 90 |  | 2024-08-30 | 2024-08-30 | 2025-09-12 |  | Tower A | Super Structure | L12
39491 | Tower A - Super Structure - Core Wall Low Rise L31-32 | Complete | Core Wall RCC Works | 2024-08-31 | 2024-08-31 | Casting | 100 | 100 |  | 2024-08-31 | 2024-08-31 | 2024-08-31 | 2024-08-31 | Tower A | Super Structure | L31 | RCC Super Structure | Core Wall RCC Works
39886 | Tower A - Super Structure - Core & Outer Slab L27-28 | Complete | RCC Works - Slab | 2024-08-31 | 2024-09-06 | Outer Slab_TA | 100 | 100 |  | 2024-08-31 | 2024-08-31 | 2024-09-06 | 2024-09-06 | Tower A | Super Structure | L27 | RCC Sub Structure | RCC Works - Slab
44772 | Tower B - Sub Structure - B3 to B2 - Pour 1A & 2 | Complete | RCC Works - Slab | 2024-08-31 | 2024-09-14 | Slab & Staircase Fwk. | 100 | 100 |  | 2024-08-31 | 2024-08-31 | 2024-09-14 | 2024-09-14 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
48327 | Retail - Sub structure - B3 to B2 - P1 | Complete |  | 2024-08-31 | 2024-09-09 | Section 3_lift 2 | 100 | 100 |  | 2024-08-31 | 2024-08-31 | 2024-09-09 | 2024-09-09 | Retail | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
48327 | Retail - Sub structure - B3 to B2 - P1 | Complete |  | 2024-08-31 | 2024-09-09 | Section 3_lift 2 | 100 | 100 |  | 2024-08-31 | 2024-08-31 | 2024-09-09 | 2024-09-09 | Retail | Sub Structure | B3
48349 |  | Complete |  | 2024-08-31 | 2024-09-18 | Pour RT-2 | 100 | 100 |  | 2024-08-31 | 2024-08-31 | 2024-09-18 | 2024-09-18
48350 | Retail - Sub structure - B3 to B2 - P2 | Complete |  | 2024-08-31 | 2024-09-09 | Section 5_lift 1 | 100 | 100 |  | 2024-08-31 | 2024-08-31 | 2024-09-09 | 2024-09-09 | Retail | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
48350 | Retail - Sub structure - B3 to B2 - P2 | Complete |  | 2024-08-31 | 2024-09-09 | Section 5_lift 1 | 100 | 100 |  | 2024-08-31 | 2024-08-31 | 2024-09-09 | 2024-09-09 | Retail | Sub Structure | B3
39492 | Tower A - Super Structure - Core Wall Low Rise L31-32 | Complete | Core Wall RCC Works | 2024-09-02 | 2024-09-02 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-09-02 | Tower A | Super Structure | L31 | RCC Super Structure | Core Wall RCC Works
40204 | Tower A - Super Structure - Finishes & MEP - L13 to L14 | Complete | Partition Wall-Blockwork | 2024-09-02 | 2024-09-07 | Staircase Area | 100 | 100 |  | 2024-09-02 | 2024-09-02 | 2024-09-07 | 2024-09-07 | Tower A | Super Structure | L13
40207 | Tower A - Super Structure - Finishes & MEP - L14 to L15 | Complete | Partition Wall-Blockwork | 2024-09-02 | 2024-09-10 | Partition Walls | 100 | 100 |  | 2024-09-02 | 2024-09-02 | 2024-09-10 | 2024-09-10 | Tower A | Super Structure | L14
48133 | Retail - Foundation P2 | Complete |  | 2024-09-02 | 2024-11-07 | Fwk & Casting_NTA | 100 | 100 |  | 2024-09-02 | 2024-09-02 | 2024-11-07 | 2024-11-07 | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48133 | Retail - Foundation P2 | Complete |  | 2024-09-02 | 2024-11-07 | Fwk & Casting_NTA | 100 | 100 |  | 2024-09-02 | 2024-09-02 | 2024-11-07 | 2024-11-07 | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48133 | Retail - Foundation P2 | Complete |  | 2024-09-02 | 2024-11-07 | Fwk & Casting_NTA | 100 | 100 |  | 2024-09-02 | 2024-09-02 | 2024-11-07 | 2024-11-07 | Retail | Foundation
48140 | Retail - Foundation P3 | Complete |  | 2024-09-02 | 2025-01-13 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2024-09-02 | 2024-09-02 | 2025-01-13 | 2025-01-13 | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48140 | Retail - Foundation P3 | Complete |  | 2024-09-02 | 2025-01-13 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2024-09-02 | 2024-09-02 | 2025-01-13 | 2025-01-13 | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48140 | Retail - Foundation P3 | Complete |  | 2024-09-02 | 2025-01-13 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2024-09-02 | 2024-09-02 | 2025-01-13 | 2025-01-13 | Retail | Foundation
39493 |  | Complete |  | 2024-09-03 | 2024-09-12 | Core Wall L32-33 | 100 | 100 |  | 2024-09-03 | 2024-09-03 | 2024-09-12 | 2024-09-12
39494 | Tower A - Super Structure - Core Wall Low Rise L32-33 | Complete | Core Wall RCC Works | 2024-09-03 | 2024-09-03 | Scaffolding & platform | 100 | 100 |  | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2024-09-03 | Tower A | Super Structure | L32 | RCC Super Structure | Core Wall RCC Works
44815 | Tower B - Sub Structure - B3 to B2 - Pour 4 | Complete | RCC Works - Slab | 2024-09-03 | 2024-09-10 | Slab & Staircase Reinf. | 100 | 100 |  | 2024-09-03 | 2024-09-03 | 2024-09-10 | 2024-09-10 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
39495 | Tower A - Super Structure - Core Wall Low Rise L32-33 | Complete | Core Wall RCC Works | 2024-09-04 | 2024-09-05 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-09-04 | 2024-09-04 | 2024-09-05 | 2024-09-05 | Tower A | Super Structure | L32 | RCC Super Structure | Core Wall RCC Works
39496 | Tower A - Super Structure - Core Wall Low Rise L32-33 | Complete | Core Wall RCC Works | 2024-09-04 | 2024-09-05 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-09-04 | 2024-09-04 | 2024-09-05 | 2024-09-05 | Tower A | Super Structure | L32 | RCC Super Structure | Core Wall RCC Works
41123 |  | Started |  | 2024-09-04 | 2025-12-26 | L11-12 | 100 | 66 |  | 2024-09-04 | 2024-09-04 | 2026-01-16 |  |  |  |  | Finishes | Gypsum Plastering Works
41123 |  | Started |  | 2024-09-04 | 2025-12-26 | L11-12 | 100 | 66 |  | 2024-09-04 | 2024-09-04 | 2026-01-16
41124 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2024-09-04 | 2024-09-04 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 80 |  | 2024-09-04 | 2024-09-04 | 2025-12-05 |  | Tower A | Super Structure | L11 | MEP | FPS 1st Fix - MEP & Finishes
42243 |  | Started |  | 2024-09-04 | 2025-10-01 | Finishes after 1st Fix | 100 | 6 |  | 2024-09-04 | 2025-07-26 | 2025-10-23
42244 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Apartment Area | Started | Blockwork & Gypsym Works - MEP & Finishes | 2024-09-04 | 2024-09-28 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2024-09-04 | 2025-09-01 | 2025-10-09 |  | Tower A | Super Structure | L9 | Finishes | Blockwork
8368 | T-14-Sub structure Footings | Complete | Reinforcement | 2024-09-05 | 2025-03-11 | Reinforcement | 71 | 71 | MT | 2024-09-05 | 2024-09-05 | 2025-10-02 | 2024-09-29
48005 |  | Complete |  | 2024-09-05 | 2024-11-01 | Municipal Water | 100 | 100 |  | 2024-09-05 | 2024-09-05 | 2024-11-01 | 2024-11-01
48006 |  | Complete |  | 2024-09-05 | 2024-11-01 | Municipal Storm Water | 100 | 100 |  | 2024-09-05 | 2024-09-05 | 2024-11-01 | 2024-11-01
48007 |  | Complete |  | 2024-09-05 | 2024-11-01 | STP Bypass to Municipal line | 100 | 100 |  | 2024-09-05 | 2024-09-05 | 2024-11-01 | 2024-11-01
48010 |  | Complete |  | 2024-09-05 | 2024-10-14 | FF Works | 100 | 100 |  | 2024-09-05 | 2024-09-05 | 2024-10-14 | 2024-10-14
48328 | Retail - Sub structure - B3 to B2 - P1 | Complete |  | 2024-09-05 | 2024-09-13 | Section 4_lift 2 | 100 | 100 |  | 2024-09-05 | 2024-09-05 | 2024-09-13 | 2024-09-13 | Retail | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
48328 | Retail - Sub structure - B3 to B2 - P1 | Complete |  | 2024-09-05 | 2024-09-13 | Section 4_lift 2 | 100 | 100 |  | 2024-09-05 | 2024-09-05 | 2024-09-13 | 2024-09-13 | Retail | Sub Structure | B3
48351 | Retail - Sub structure - B3 to B2 - P2 | Complete |  | 2024-09-05 | 2024-09-13 | Section 6_lift 1 | 100 | 100 |  | 2024-09-05 | 2024-09-05 | 2024-09-13 | 2024-09-13 | Retail | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
48351 | Retail - Sub structure - B3 to B2 - P2 | Complete |  | 2024-09-05 | 2024-09-13 | Section 6_lift 1 | 100 | 100 |  | 2024-09-05 | 2024-09-05 | 2024-09-13 | 2024-09-13 | Retail | Sub Structure | B3
39887 |  | Complete |  | 2024-09-07 | 2024-09-14 | L28-29 | 100 | 100 |  | 2024-09-07 | 2024-09-07 | 2024-09-14 | 2024-09-14
39887 |  | Complete |  | 2024-09-07 | 2024-09-14 | L28-29 | 100 | 100 |  | 2024-09-07 | 2024-09-07 | 2024-09-14 | 2024-09-14 |  |  |  | Finishes | Gypsum Plastering Works
39888 | Tower A - Super Structure - Core & Outer Slab L28-29 | Complete | RCC Works - Vertical | 2024-09-07 | 2024-09-13 | Outer Columns_TA | 100 | 100 |  | 2024-09-07 | 2024-09-07 | 2024-09-13 | 2024-09-13 | Tower A | Super Structure | L28 | RCC Sub Structure | RCC Works - Vertical
40249 |  | Complete |  | 2024-09-07 | 2025-01-25 | L25-26 | 100 | 100 |  | 2024-09-07 | 2024-09-07 | 2025-01-25 | 2025-01-25
40249 |  | Complete |  | 2024-09-07 | 2025-01-25 | L25-26 | 100 | 100 |  | 2024-09-07 | 2024-09-07 | 2025-01-25 | 2025-01-25 |  |  |  | Finishes | Gypsum Plastering Works
40250 | Tower A - Super Structure - Finishes & MEP - L25 to L26 | Complete | Partition Wall-Blockwork | 2024-09-07 | 2024-09-25 | De-shuttering & Area clearance | 100 | 100 |  | 2024-09-07 | 2024-09-07 | 2024-09-25 | 2024-09-25 | Tower A | Super Structure | L25
40556 | Tower A - Super Structure - Finishes & MEP | Complete | MEP Shaft Masonry | 2024-09-07 | 2024-09-07 | L25-L35 | 100 | 100 |  | 2024-09-07 | 2024-09-07 | 2024-09-07 | 2024-09-07 | Tower A | Super Structure
44796 |  | Complete |  | 2024-09-07 | 2024-10-29 | Pour 8_B3 to B2 | 100 | 100 |  | 2024-09-07 | 2024-09-07 | 2024-10-29 | 2024-10-29
44797 | Tower B - Sub Structure - B3 to B2 - Pour 8 | Complete | RCC Works - Vertical | 2024-09-07 | 2024-09-14 | Col/ Wall Reinf. | 100 | 100 |  | 2024-09-07 | 2024-09-07 | 2024-09-14 | 2024-09-14 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
44797 | Tower B - Sub Structure - B3 to B2 - Pour 8 | Complete | RCC Works - Vertical | 2024-09-07 | 2024-09-14 | Col/ Wall Reinf. | 100 | 100 |  | 2024-09-07 | 2024-09-07 | 2024-09-14 | 2024-09-14 | Tower B | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
44798 | Tower B - Sub Structure - B3 to B2 - Pour 8 | Complete | RCC Works - Vertical | 2024-09-07 | 2024-09-19 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-09-07 | 2024-09-07 | 2024-09-19 | 2024-09-19 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
44798 | Tower B - Sub Structure - B3 to B2 - Pour 8 | Complete | RCC Works - Vertical | 2024-09-07 | 2024-09-19 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-09-07 | 2024-09-07 | 2024-09-19 | 2024-09-19 | Tower B | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
39497 | Tower A - Super Structure - Core Wall Low Rise L32-33 | Complete | Core Wall RCC Works | 2024-09-08 | 2024-09-11 | Casting | 100 | 100 |  | 2024-09-08 | 2024-09-08 | 2024-09-11 | 2024-09-11 | Tower A | Super Structure | L32 | RCC Super Structure | Core Wall RCC Works
40557 | Tower A - Super Structure - Finishes & MEP | Complete | MEP Shaft Masonry | 2024-09-08 | 2025-02-28 | L35-L45 | 100 | 100 |  | 2024-09-08 | 2024-09-08 | 2025-02-28 | 2025-02-28 | Tower A | Super Structure
8369 | T-14-Sub structure Footings | Complete | Shuttering | 2024-09-09 | 2025-03-11 | Shuttering | 673 | 673 | Sqm | 2024-09-09 | 2024-09-09 | 2025-10-04 | 2024-10-01
40486 | Tower A - Super Structure - Finishes & MEP - L12 to L13 | Complete | Gypsum Plastering Works | 2024-09-09 | 2024-09-26 | L12-13 | 100 | 100 |  | 2024-09-09 | 2024-09-09 | 2024-09-26 | 2025-05-25 | Tower A | Super Structure | L12 | Finishes | Gypsum Plastering Works
40486 | Tower A - Super Structure - Finishes & MEP - L12 to L13 | Complete | Gypsum Plastering Works | 2024-09-09 | 2024-09-26 | L12-13 | 100 | 100 |  | 2024-09-09 | 2024-09-09 | 2024-09-26 | 2025-05-25 | Tower A | Super Structure | L12
42308 |  | Started |  | 2024-09-09 | 2026-06-05 | L13-14 (Refuge) | 100 | 82 |  | 2024-09-09 | 2024-09-09 | 2026-06-03
42309 |  | Started |  | 2024-09-09 | 2024-09-27 | MEP 1st Fixes | 100 | 86 |  | 2024-09-09 | 2024-09-09 | 2025-09-13
42310 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Apartment Area | Started | FPS 1st Fix - MEP & Finishes | 2024-09-09 | 2024-09-10 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 80 |  | 2024-09-09 | 2024-09-09 | 2025-09-12 |  | Tower A | Super Structure | L13 | MEP | FPS 1st Fix - MEP & Finishes
42311 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Apartment Area | Started | Electrical 1st Fix - MEP & Finishes | 2024-09-09 | 2024-09-09 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 90 |  | 2024-09-09 | 2024-09-09 | 2025-09-11 |  | Tower A | Super Structure | L13 | MEP | Electrical 1st Fixes
42312 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Apartment Area | Started | PHE 1st Fix - MEP & Finishes | 2024-09-09 | 2024-09-10 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 80 |  | 2024-09-09 | 2024-09-09 | 2025-09-12 |  | Tower A | Super Structure | L13
42313 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Apartment Area | Started | Wet Area Waterproofing - MEP & Finishes | 2024-09-09 | 2024-09-10 | Wet Area Waterproofing | 100 | 90 |  | 2024-09-09 | 2024-09-09 | 2025-09-12 |  | Tower A | Super Structure | L13
39889 | Tower A - Super Structure - Core & Outer Slab L28-29 | Complete | RCC Works - Slab | 2024-09-10 | 2024-09-14 | Outer Slab_TA | 100 | 100 |  | 2024-09-10 | 2024-09-10 | 2024-09-14 | 2024-09-14 | Tower A | Super Structure | L28 | RCC Sub Structure | RCC Works - Slab
42260 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Apartment Area | Started | Cement Plastering in Wet Areas - MEP & Finishes | 2024-09-10 | 2024-09-10 | Cement Plastering in wet areas | 100 | 90 |  | 2024-09-10 | 2024-09-10 | 2025-09-15 |  | Tower A | Super Structure | L10
42278 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Apartment Area | Started | Cement Plastering in Wet Areas - MEP & Finishes | 2024-09-10 | 2024-09-10 | Cement Plastering in wet areas | 100 | 90 |  | 2024-09-10 | 2024-09-10 | 2025-09-13 |  | Tower A | Super Structure | L11
44799 | Tower B - Sub Structure - B3 to B2 - Pour 8 | Complete | RCC Works - Vertical | 2024-09-10 | 2024-09-21 | Col/ Wall Casting | 100 | 100 |  | 2024-09-10 | 2024-09-10 | 2024-09-21 | 2024-09-21 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
44799 | Tower B - Sub Structure - B3 to B2 - Pour 8 | Complete | RCC Works - Vertical | 2024-09-10 | 2024-09-21 | Col/ Wall Casting | 100 | 100 |  | 2024-09-10 | 2024-09-10 | 2024-09-21 | 2024-09-21 | Tower B | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
48329 |  | Complete |  | 2024-09-10 | 2024-09-26 | Pour RT-2 | 100 | 100 |  | 2024-09-10 | 2024-09-10 | 2024-09-26 | 2024-09-26
48330 | Retail - Sub structure - B3 to B2 - P2 | Complete |  | 2024-09-10 | 2024-09-18 | Section 5_lift 2 | 100 | 100 |  | 2024-09-10 | 2024-09-10 | 2024-09-18 | 2024-09-18 | Retail | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
48330 | Retail - Sub structure - B3 to B2 - P2 | Complete |  | 2024-09-10 | 2024-09-18 | Section 5_lift 2 | 100 | 100 |  | 2024-09-10 | 2024-09-10 | 2024-09-18 | 2024-09-18 | Retail | Sub Structure | B3
48352 | Retail - Sub structure - B3 to B2 - P2 | Complete |  | 2024-09-10 | 2024-09-18 | Section 7_lift 1 | 100 | 100 |  | 2024-09-10 | 2024-09-10 | 2024-09-18 | 2024-09-18 | Retail | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
48352 | Retail - Sub structure - B3 to B2 - P2 | Complete |  | 2024-09-10 | 2024-09-18 | Section 7_lift 1 | 100 | 100 |  | 2024-09-10 | 2024-09-10 | 2024-09-18 | 2024-09-18 | Retail | Sub Structure | B3
40208 | Tower A - Super Structure - Finishes & MEP - L14 to L15 | Complete | Partition Wall-Blockwork | 2024-09-11 | 2024-09-16 | Staircase Area | 100 | 100 |  | 2024-09-11 | 2024-09-11 | 2024-09-16 | 2024-09-16 | Tower A | Super Structure | L14
40211 | Tower A - Super Structure - Finishes & MEP - L15 to L16 | Complete | Partition Wall-Blockwork | 2024-09-11 | 2024-09-19 | Partition Walls | 100 | 100 |  | 2024-09-11 | 2024-09-11 | 2024-09-19 | 2024-09-19 | Tower A | Super Structure | L15
44773 | Tower B - Sub Structure - B3 to B2 - Pour 1A & 2 | Complete | RCC Works - Slab | 2024-09-11 | 2024-09-19 | Slab & Staircase Reinf. | 100 | 100 |  | 2024-09-11 | 2024-09-11 | 2024-09-19 | 2024-09-19 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
44816 | Tower B - Sub Structure - B3 to B2 - Pour 4 | Complete | RCC Works - Slab | 2024-09-11 | 2024-09-12 | Slab & Staircase Casting | 100 | 100 |  | 2024-09-11 | 2024-09-11 | 2024-09-12 | 2024-09-12 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
48147 |  | Started |  | 2024-09-11 | 2025-02-11 | Pour RT-5 | 100 | 38 |  | 2024-09-11 | 2024-09-11 | 2025-09-29
48148 | Retail - Foundation P5 | Complete |  | 2024-09-11 | 2024-09-14 | Dressing & PCC | 100 | 100 |  | 2024-09-11 | 2024-09-11 | 2024-09-14 | 2024-09-14 | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48148 | Retail - Foundation P5 | Complete |  | 2024-09-11 | 2024-09-14 | Dressing & PCC | 100 | 100 |  | 2024-09-11 | 2024-09-11 | 2024-09-14 | 2024-09-14 | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48148 | Retail - Foundation P5 | Complete |  | 2024-09-11 | 2024-09-14 | Dressing & PCC | 100 | 100 |  | 2024-09-11 | 2024-09-11 | 2024-09-14 | 2024-09-14 | Retail | Foundation
8370 | T-14-Sub structure Footings | Complete | RCC | 2024-09-12 | 2025-03-11 | RCC | 713 | 713 | CUM | 2024-09-12 | 2024-09-12 | 2025-10-04 | 2024-10-03
8370 | T-14-Sub structure Footings | Complete | RCC | 2024-09-12 | 2025-03-11 | RCC | 713 | 713 | CUM | 2024-09-12 | 2024-09-12 | 2025-10-04 | 2024-10-03
9959 |  | Complete |  | 2024-09-12 | 2025-03-15 | Isolated & Combined Footings | 100 | 100 |  | 2024-09-12 | 2024-09-12 | 2025-10-08 | 2024-10-07
9960 | T-21-Sub structure Footings | Complete | PCC | 2024-09-12 | 2025-03-11 | PCC | 98 | 98 | CUM | 2024-09-12 | 2024-09-12 | 2025-10-01 | 2024-10-04
39498 | Tower A - Super Structure - Core Wall Low Rise L32-33 | Complete | Core Wall RCC Works | 2024-09-12 | 2024-09-12 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-09-12 | 2024-09-12 | 2024-09-12 | 2024-09-12 | Tower A | Super Structure | L32 | RCC Super Structure | Core Wall RCC Works
44800 | Tower B - Sub Structure - B3 to B2 - Pour 8 | Complete | RCC Works - Slab | 2024-09-12 | 2024-09-26 | Slab & Staircase Fwk. | 100 | 100 |  | 2024-09-12 | 2024-09-12 | 2024-09-26 | 2024-09-26 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
47545 |  | Started |  | 2024-09-12 | 2028-09-28 | CONSTRUCTION_NON TOWER AREA_Zone 3 | 100 | 19 |  | 2024-09-12 | 2024-09-12 | 2028-09-21
47546 |  | Started |  | 2024-09-12 | 2026-04-01 | Foundation_NTA Zone 3 | 100 | 37 |  | 2024-09-12 | 2024-09-12 | 2026-11-03
47565 |  | Complete |  | 2024-09-12 | 2024-11-06 | Pour 9 (grid PB-06 to PB-D) | 100 | 100 |  | 2024-09-12 | 2024-09-12 | 2024-11-06 | 2024-11-06
47566 |  | Complete |  | 2024-09-12 | 2024-09-12 | Dressing & PCC | 100 | 100 |  | 2024-09-12 | 2024-09-12 | 2024-09-12 | 2024-09-12
47566 |  | Complete |  | 2024-09-12 | 2024-09-12 | Dressing & PCC | 100 | 100 |  | 2024-09-12 | 2024-09-12 | 2024-09-12 | 2024-09-12 |  |  |  | RCC Sub Structure | Raft RCC Works
47566 |  | Complete |  | 2024-09-12 | 2024-09-12 | Dressing & PCC | 100 | 100 |  | 2024-09-12 | 2024-09-12 | 2024-09-12 | 2024-09-12 |  |  |  | RCC Super Structure | Foundation RCC Works
8937 | T-15-Sub structure Water proofing NTA | Not Ready |  | 2025-03-06 | 2025-04-30 | Water Proofing Outside-NTA | 100 | 0 |  | 2024-09-13 |  | 2024-11-04
39499 |  | Complete |  | 2024-09-13 | 2024-09-20 | Core Wall L33-34 | 100 | 100 |  | 2024-09-13 | 2024-09-13 | 2024-09-20 | 2024-09-20
39500 | Tower A - Super Structure - Core Wall Low Rise L33-34 | Complete | Core Wall RCC Works | 2024-09-13 | 2024-09-13 | Scaffolding & platform | 100 | 100 |  | 2024-09-13 | 2024-09-13 | 2024-09-13 | 2024-09-13 | Tower A | Super Structure | L33 | RCC Super Structure | Core Wall RCC Works
44789 |  | Complete |  | 2024-09-13 | 2024-10-23 | Pour 7_B3 to B2 | 100 | 100 |  | 2024-09-13 | 2024-09-13 | 2024-10-23 | 2024-10-23
44790 | Tower B - Sub Structure - B3 to B2 - Pour 7 | Complete | RCC Works - Vertical | 2024-09-13 | 2024-09-21 | Col/ Wall Reinf. | 100 | 100 |  | 2024-09-13 | 2024-09-13 | 2024-09-21 | 2024-09-21 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
44790 | Tower B - Sub Structure - B3 to B2 - Pour 7 | Complete | RCC Works - Vertical | 2024-09-13 | 2024-09-21 | Col/ Wall Reinf. | 100 | 100 |  | 2024-09-13 | 2024-09-13 | 2024-09-21 | 2024-09-21 | Tower B | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
44817 |  | Complete |  | 2024-09-13 | 2024-12-14 | B2 to B1 | 100 | 100 |  | 2024-09-13 | 2024-09-13 | 2024-12-14 | 2024-12-14
44817 |  | Complete |  | 2024-09-13 | 2024-12-14 | B2 to B1 | 100 | 100 |  | 2024-09-13 | 2024-09-13 | 2024-12-14 | 2024-12-14
44817 |  | Complete |  | 2024-09-13 | 2024-12-14 | B2 to B1 | 100 | 100 |  | 2024-09-13 | 2024-09-13 | 2024-12-14 | 2024-12-14
44864 |  | Complete |  | 2024-09-13 | 2024-12-14 | Pour 4_B2 to B1 | 100 | 100 |  | 2024-09-13 | 2024-09-13 | 2024-12-14 | 2024-12-14
44865 | Tower B - Sub Structure - B2 to B1 - Pour 4 | Complete | RCC Works - Vertical | 2024-09-13 | 2024-09-21 | Col/ Wall Reinf. | 100 | 100 |  | 2024-09-13 | 2024-09-13 | 2024-09-21 | 2024-09-21 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
44865 | Tower B - Sub Structure - B2 to B1 - Pour 4 | Complete | RCC Works - Vertical | 2024-09-13 | 2024-09-21 | Col/ Wall Reinf. | 100 | 100 |  | 2024-09-13 | 2024-09-13 | 2024-09-21 | 2024-09-21 | Tower B | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
44866 | Tower B - Sub Structure - B2 to B1 - Pour 4 | Complete | RCC Works - Vertical | 2024-09-13 | 2024-09-25 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-09-13 | 2024-09-13 | 2024-09-25 | 2024-09-25 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
44866 | Tower B - Sub Structure - B2 to B1 - Pour 4 | Complete | RCC Works - Vertical | 2024-09-13 | 2024-09-25 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-09-13 | 2024-09-13 | 2024-09-25 | 2024-09-25 | Tower B | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
47567 |  | Complete |  | 2024-09-13 | 2024-09-24 | Liner Wall | 100 | 100 |  | 2024-09-13 | 2024-09-13 | 2024-09-24 | 2024-09-24
47567 |  | Complete |  | 2024-09-13 | 2024-09-24 | Liner Wall | 100 | 100 |  | 2024-09-13 | 2024-09-13 | 2024-09-24 | 2024-09-24 |  |  |  | RCC Sub Structure | Raft RCC Works
47567 |  | Complete |  | 2024-09-13 | 2024-09-24 | Liner Wall | 100 | 100 |  | 2024-09-13 | 2024-09-13 | 2024-09-24 | 2024-09-24 |  |  |  | RCC Super Structure | Foundation RCC Works
47568 |  | Complete |  | 2024-09-13 | 2024-09-25 | Waterproofing Horizontal-toe area | 100 | 100 |  | 2024-09-13 | 2024-09-13 | 2024-09-25 | 2024-09-25
47574 |  | Complete |  | 2024-09-13 | 2024-11-04 | Pour 10 (PB-K to PA-B / RT-08 to PB-06) | 100 | 100 |  | 2024-09-13 | 2024-09-13 | 2024-11-04 | 2024-11-04
47575 |  | Complete |  | 2024-09-13 | 2024-09-16 | Dressing & PCC | 100 | 100 |  | 2024-09-13 | 2024-09-13 | 2024-09-16 | 2024-09-16
47575 |  | Complete |  | 2024-09-13 | 2024-09-16 | Dressing & PCC | 100 | 100 |  | 2024-09-13 | 2024-09-13 | 2024-09-16 | 2024-09-16 |  |  |  | RCC Sub Structure | Raft RCC Works
47575 |  | Complete |  | 2024-09-13 | 2024-09-16 | Dressing & PCC | 100 | 100 |  | 2024-09-13 | 2024-09-13 | 2024-09-16 | 2024-09-16 |  |  |  | RCC Super Structure | Foundation RCC Works
9961 | T-21-Sub structure Footings | Complete | Reinforcement | 2024-09-14 | 2025-03-14 | Reinforcement | 71 | 71 | MT | 2024-09-14 | 2024-09-14 | 2025-10-06 | 2024-10-05
39501 | Tower A - Super Structure - Core Wall Low Rise L33-34 | Complete | Core Wall RCC Works | 2024-09-14 | 2024-09-18 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-09-14 | 2024-09-14 | 2024-09-18 | 2024-09-18 | Tower A | Super Structure | L33 | RCC Super Structure | Core Wall RCC Works
48141 | Retail - Foundation P3 | Complete |  | 2024-09-14 | 2025-01-19 | Fwk & Casting_NTA | 100 | 100 |  | 2024-09-14 | 2024-09-14 | 2025-01-19 | 2025-01-19 | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48141 | Retail - Foundation P3 | Complete |  | 2024-09-14 | 2025-01-19 | Fwk & Casting_NTA | 100 | 100 |  | 2024-09-14 | 2024-09-14 | 2025-01-19 | 2025-01-19 | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48141 | Retail - Foundation P3 | Complete |  | 2024-09-14 | 2025-01-19 | Fwk & Casting_NTA | 100 | 100 |  | 2024-09-14 | 2024-09-14 | 2025-01-19 | 2025-01-19 | Retail | Foundation
48331 | Retail - Sub structure - B3 to B2 - P2 | Complete |  | 2024-09-14 | 2024-09-23 | Section 6_lift 2 | 100 | 100 |  | 2024-09-14 | 2024-09-14 | 2024-09-23 | 2024-09-23 | Retail | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
48331 | Retail - Sub structure - B3 to B2 - P2 | Complete |  | 2024-09-14 | 2024-09-23 | Section 6_lift 2 | 100 | 100 |  | 2024-09-14 | 2024-09-14 | 2024-09-23 | 2024-09-23 | Retail | Sub Structure | B3
48353 |  | Complete |  | 2024-09-14 | 2024-09-26 | Pour RT-3 | 100 | 100 |  | 2024-09-14 | 2024-09-14 | 2024-09-26 | 2024-09-26
48354 | Retail - Sub structure - B3 to B2 - P3 | Complete |  | 2024-09-14 | 2024-09-23 | Section 8_lift 1 | 100 | 100 |  | 2024-09-14 | 2024-09-14 | 2024-09-23 | 2024-09-23 | Retail | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
48354 | Retail - Sub structure - B3 to B2 - P3 | Complete |  | 2024-09-14 | 2024-09-23 | Section 8_lift 1 | 100 | 100 |  | 2024-09-14 | 2024-09-14 | 2024-09-23 | 2024-09-23 | Retail | Sub Structure | B3
48365 | Retail - Sub structure - B3 to B2 - P1 | Complete |  | 2024-09-14 | 2025-01-30 | Slab_NTA | 100 | 100 |  | 2024-09-14 | 2024-09-14 | 2025-01-30 | 2025-01-30 | Retail | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
48365 | Retail - Sub structure - B3 to B2 - P1 | Complete |  | 2024-09-14 | 2025-01-30 | Slab_NTA | 100 | 100 |  | 2024-09-14 | 2024-09-14 | 2025-01-30 | 2025-01-30 | Retail | Sub Structure | B3
9966 | T-21-Sub structure Retaining Wall | Complete | Reinforcement | 2024-09-15 | 2025-03-14 | Reinforcement | 11.41 | 11.41 | MT | 2024-09-15 | 2024-09-15 | 2025-05-18 | 2025-06-19
8384 | T-14-Sub structure Water proofing NTA | Started |  | 2025-03-06 | 2025-04-30 | Water Proofing Outside-NTA | 100 | 0 |  | 2024-09-16 | 2025-07-07 | 2024-11-09
9457 | T-16-Sub structure Water proofing NTA | Forced Ready |  | 2025-03-06 | 2025-04-30 | Water Proofing Outside-NTA | 100 | 0 |  | 2024-09-16 |  | 2024-11-09
39502 | Tower A - Super Structure - Core Wall Low Rise L33-34 | Complete | Core Wall RCC Works | 2024-09-16 | 2024-09-19 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-09-16 | 2024-09-16 | 2024-09-19 | 2024-09-19 | Tower A | Super Structure | L33 | RCC Super Structure | Core Wall RCC Works
39890 |  | Complete |  | 2024-09-16 | 2024-09-23 | L29-30 | 100 | 100 |  | 2024-09-16 | 2024-09-16 | 2024-09-23 | 2024-09-23
39890 |  | Complete |  | 2024-09-16 | 2024-09-23 | L29-30 | 100 | 100 |  | 2024-09-16 | 2024-09-16 | 2024-09-23 | 2024-09-23 |  |  |  | Finishes | Gypsum Plastering Works
39891 | Tower A - Super Structure - Core & Outer Slab L29-30 | Complete | RCC Works - Vertical | 2024-09-16 | 2024-09-23 | Outer Columns_TA | 100 | 100 |  | 2024-09-16 | 2024-09-16 | 2024-09-23 | 2024-09-23 | Tower A | Super Structure | L29 | RCC Sub Structure | RCC Works - Vertical
40253 |  | Complete |  | 2024-09-16 | 2025-02-03 | L26-27 | 100 | 100 |  | 2024-09-16 | 2024-09-16 | 2025-02-03 | 2025-02-03
40253 |  | Complete |  | 2024-09-16 | 2025-02-03 | L26-27 | 100 | 100 |  | 2024-09-16 | 2024-09-16 | 2025-02-03 | 2025-02-03 |  |  |  | Finishes | Gypsum Plastering Works
40254 | Tower A - Super Structure - Finishes & MEP - L26 to L27 | Complete | Partition Wall-Blockwork | 2024-09-16 | 2024-10-04 | De-shuttering & Area clearance | 100 | 100 |  | 2024-09-16 | 2024-09-16 | 2024-10-04 | 2024-10-04 | Tower A | Super Structure | L26
44791 | Tower B - Sub Structure - B3 to B2 - Pour 7 | Complete | RCC Works - Vertical | 2024-09-16 | 2024-09-27 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-09-16 | 2024-09-16 | 2024-09-27 | 2024-09-27 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
44791 | Tower B - Sub Structure - B3 to B2 - Pour 7 | Complete | RCC Works - Vertical | 2024-09-16 | 2024-09-27 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-09-16 | 2024-09-16 | 2024-09-27 | 2024-09-27 | Tower B | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
44867 | Tower B - Sub Structure - B2 to B1 - Pour 4 | Complete | RCC Works - Vertical | 2024-09-16 | 2024-09-27 | Col/ Wall Casting | 100 | 100 |  | 2024-09-16 | 2024-09-16 | 2024-09-27 | 2024-09-27 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
44867 | Tower B - Sub Structure - B2 to B1 - Pour 4 | Complete | RCC Works - Vertical | 2024-09-16 | 2024-09-27 | Col/ Wall Casting | 100 | 100 |  | 2024-09-16 | 2024-09-16 | 2024-09-27 | 2024-09-27 | Tower B | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
9962 | T-21-Sub structure Footings | Complete | Shuttering | 2024-09-18 | 2025-03-15 | Shuttering | 673 | 673 | Sqm | 2024-09-18 | 2024-09-18 | 2025-10-07 | 2024-10-06
40487 | Tower A - Super Structure - Finishes & MEP - L13 to L14 | Complete | Gypsum Plastering Works | 2024-09-18 | 2025-04-15 | L13-14 | 100 | 100 |  | 2024-09-18 | 2024-09-18 | 2025-04-15 | 2025-04-15 | Tower A | Super Structure | L13 | Finishes | Gypsum Plastering Works
40487 | Tower A - Super Structure - Finishes & MEP - L13 to L14 | Complete | Gypsum Plastering Works | 2024-09-18 | 2025-04-15 | L13-14 | 100 | 100 |  | 2024-09-18 | 2024-09-18 | 2025-04-15 | 2025-04-15 | Tower A | Super Structure | L13
42326 |  | Started |  | 2024-09-18 | 2026-06-05 | L14-15 | 100 | 82 |  | 2024-09-18 | 2024-09-18 | 2026-06-03 |  |  |  |  | Finishes | Gypsum Plastering Works
42326 |  | Started |  | 2024-09-18 | 2026-06-05 | L14-15 | 100 | 82 |  | 2024-09-18 | 2024-09-18 | 2026-06-03
42327 |  | Started |  | 2024-09-18 | 2024-10-14 | MEP 1st Fixes | 100 | 86 |  | 2024-09-18 | 2024-09-18 | 2025-09-13
42328 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Apartment Area | Started | FPS 1st Fix - MEP & Finishes | 2024-09-18 | 2024-09-19 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 80 |  | 2024-09-18 | 2024-09-18 | 2025-09-12 |  | Tower A | Super Structure | L14 | MEP | FPS 1st Fix - MEP & Finishes
42329 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Apartment Area | Started | Electrical 1st Fix - MEP & Finishes | 2024-09-18 | 2024-09-18 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 90 |  | 2024-09-18 | 2024-09-18 | 2025-09-11 |  | Tower A | Super Structure | L14 | MEP | Electrical 1st Fixes
42330 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Apartment Area | Started | PHE 1st Fix - MEP & Finishes | 2024-09-18 | 2024-09-19 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 80 |  | 2024-09-18 | 2024-09-18 | 2025-09-12 |  | Tower A | Super Structure | L14
10476 |  | Started |  | 2024-09-19 | 2027-01-07 | Tower 20 | 100 | 25 |  | 2024-09-19 | 2024-09-19 | 2026-12-01
10477 |  | Started |  | 2024-09-19 | 2025-05-12 | Sub Structure Up to Podium | 100 | 44 |  | 2024-09-19 | 2024-09-19 | 2025-10-29
10478 |  | Started |  | 2024-09-19 | 2025-04-26 | Footings | 100 | 77 |  | 2024-09-19 | 2024-09-19 | 2025-10-29
10479 |  | Complete |  | 2024-09-19 | 2025-03-17 | Isolated & Combined Footings | 100 | 100 |  | 2024-09-19 | 2024-09-19 | 2025-10-29 | 2024-10-28
10480 | T-20-Sub structure Footings | Complete | PCC | 2024-09-19 | 2025-03-11 | PCC | 98 | 98 | CUM | 2024-09-19 | 2024-09-19 | 2025-10-26 | 2024-10-25
39503 | Tower A - Super Structure - Core Wall Low Rise L33-34 | Complete | Core Wall RCC Works | 2024-09-19 | 2024-09-19 | Casting | 100 | 100 |  | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2024-09-19 | Tower A | Super Structure | L33 | RCC Super Structure | Core Wall RCC Works
39892 | Tower A - Super Structure - Core & Outer Slab L29-30 | Complete | RCC Works - Slab | 2024-09-19 | 2024-09-22 | Outer Slab_TA | 100 | 100 |  | 2024-09-19 | 2024-09-19 | 2024-09-22 | 2024-09-22 | Tower A | Super Structure | L29 | RCC Sub Structure | RCC Works - Slab
42296 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Apartment Area | Started | Cement Plastering in Wet Areas - MEP & Finishes | 2024-09-19 | 2024-09-19 | Cement Plastering in wet areas | 100 | 90 |  | 2024-09-19 | 2024-09-19 | 2025-09-13 |  | Tower A | Super Structure | L12
44764 |  | Complete |  | 2024-09-19 | 2024-10-04 | Core Wall B3-B2 | 100 | 100 |  | 2024-09-19 | 2024-09-19 | 2024-10-04 | 2024-10-04
44765 | Tower B - Sub Structure - B3 to B2 | Complete | Core Wall RCC Works | 2024-09-19 | 2024-09-25 | CW Reinf | 100 | 100 |  | 2024-09-19 | 2024-09-19 | 2024-09-25 | 2024-09-25 | Tower B | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
44782 |  | Complete |  | 2024-09-19 | 2024-10-15 | Pour 1B & 6_B3 to B2 | 100 | 100 |  | 2024-09-19 | 2024-09-19 | 2024-10-15 | 2024-10-15
44783 | Tower B - Sub Structure - B3 to B2 - Pour 1B & 6 | Complete | RCC Works - Vertical | 2024-09-19 | 2024-09-26 | Col/ Wall Reinf. | 100 | 100 |  | 2024-09-19 | 2024-09-19 | 2024-09-26 | 2024-09-26 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
44783 | Tower B - Sub Structure - B3 to B2 - Pour 1B & 6 | Complete | RCC Works - Vertical | 2024-09-19 | 2024-09-26 | Col/ Wall Reinf. | 100 | 100 |  | 2024-09-19 | 2024-09-19 | 2024-09-26 | 2024-09-26 | Tower B | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
44784 | Tower B - Sub Structure - B3 to B2 - Pour 1B & 6 | Complete | RCC Works - Vertical | 2024-09-19 | 2024-09-30 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-09-19 | 2024-09-19 | 2024-09-30 | 2024-09-30 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
44784 | Tower B - Sub Structure - B3 to B2 - Pour 1B & 6 | Complete | RCC Works - Vertical | 2024-09-19 | 2024-09-30 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-09-19 | 2024-09-19 | 2024-09-30 | 2024-09-30 | Tower B | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
44868 | Tower B - Sub Structure - B2 to B1 - Pour 4 | Complete | RCC Works - Slab | 2024-09-19 | 2024-10-03 | Slab & Staircase Fwk. | 100 | 100 |  | 2024-09-19 | 2024-09-19 | 2024-10-03 | 2024-10-03 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
48332 | Retail - Sub structure - B3 to B2 - P2 | Complete |  | 2024-09-19 | 2024-09-26 | Section 7_lift 2 | 100 | 100 |  | 2024-09-19 | 2024-09-19 | 2024-09-26 | 2024-09-26 | Retail | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
48332 | Retail - Sub structure - B3 to B2 - P2 | Complete |  | 2024-09-19 | 2024-09-26 | Section 7_lift 2 | 100 | 100 |  | 2024-09-19 | 2024-09-19 | 2024-09-26 | 2024-09-26 | Retail | Sub Structure | B3
48355 | Retail - Sub structure - B3 to B2 - P3 | Complete |  | 2024-09-19 | 2024-09-26 | Section 9_lift 1 | 100 | 100 |  | 2024-09-19 | 2024-09-19 | 2024-09-26 | 2024-09-26 | Retail | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
48355 | Retail - Sub structure - B3 to B2 - P3 | Complete |  | 2024-09-19 | 2024-09-26 | Section 9_lift 1 | 100 | 100 |  | 2024-09-19 | 2024-09-19 | 2024-09-26 | 2024-09-26 | Retail | Sub Structure | B3
39504 | Tower A - Super Structure - Core Wall Low Rise L33-34 | Complete | Core Wall RCC Works | 2024-09-20 | 2024-09-20 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-09-20 | Tower A | Super Structure | L33 | RCC Super Structure | Core Wall RCC Works
40212 | Tower A - Super Structure - Finishes & MEP - L15 to L16 | Complete | Partition Wall-Blockwork | 2024-09-20 | 2024-09-25 | Staircase Area | 100 | 100 |  | 2024-09-20 | 2024-09-20 | 2024-09-25 | 2024-09-25 | Tower A | Super Structure | L15
40215 | Tower A - Super Structure - Finishes & MEP - L16 to L17 | Complete | Partition Wall-Blockwork | 2024-09-20 | 2024-09-27 | Partition Walls | 100 | 100 |  | 2024-09-20 | 2024-09-20 | 2024-09-27 | 2024-09-27 | Tower A | Super Structure | L16
44766 | Tower B - Sub Structure - B3 to B2 | Complete | Core Wall RCC Works | 2024-09-20 | 2024-09-30 | CW Fwk (3.5m lift) | 100 | 100 |  | 2024-09-20 | 2024-09-20 | 2024-09-30 | 2024-09-30 | Tower B | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
44774 | Tower B - Sub Structure - B3 to B2 - Pour 1A & 2 | Complete | RCC Works - Slab | 2024-09-20 | 2024-09-21 | Slab & Staircase Casting | 100 | 100 |  | 2024-09-20 | 2024-09-20 | 2024-09-21 | 2024-09-21 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
9441 | T-16-Sub structure Footings | Complete | Reinforcement | 2024-09-21 | 2025-03-28 | Reinforcement | 71 | 71 | MT | 2024-09-21 | 2024-09-21 | 2025-03-28 | 2024-11-13
10481 | T-20-Sub structure Footings | Complete | Reinforcement | 2024-09-21 | 2025-03-15 | Reinforcement | 71 | 71 | MT | 2024-09-21 | 2024-09-21 | 2025-10-27 | 2024-10-26
39505 |  | Complete |  | 2024-09-21 | 2024-09-27 | Core Wall L34-35 | 100 | 100 |  | 2024-09-21 | 2024-09-21 | 2024-09-27 | 2024-09-27
39506 | Tower A - Super Structure - Core Wall Low Rise L34-35 | Complete | Core Wall RCC Works | 2024-09-21 | 2024-09-21 | Scaffolding & platform | 100 | 100 |  | 2024-09-21 | 2024-09-21 | 2024-09-21 | 2024-09-21 | Tower A | Super Structure | L34 | RCC Super Structure | Core Wall RCC Works
44785 | Tower B - Sub Structure - B3 to B2 - Pour 1B & 6 | Complete | RCC Works - Vertical | 2024-09-21 | 2024-09-26 | Col/ Wall Casting | 100 | 100 |  | 2024-09-21 | 2024-09-21 | 2024-09-26 | 2024-09-26 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
44785 | Tower B - Sub Structure - B3 to B2 - Pour 1B & 6 | Complete | RCC Works - Vertical | 2024-09-21 | 2024-09-26 | Col/ Wall Casting | 100 | 100 |  | 2024-09-21 | 2024-09-21 | 2024-09-26 | 2024-09-26 | Tower B | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
9963 | T-21-Sub structure Footings | Complete | RCC | 2024-09-22 | 2025-03-14 | RCC | 713 | 713 | CUM | 2024-09-22 | 2024-09-22 | 2025-10-08 | 2024-10-07
9963 | T-21-Sub structure Footings | Complete | RCC | 2024-09-22 | 2025-03-14 | RCC | 713 | 713 | CUM | 2024-09-22 | 2024-09-22 | 2025-10-08 | 2024-10-07
9967 | T-21-Sub structure Retaining Wall | Complete | Shuttering | 2024-09-22 | 2025-03-14 | Shuttering | 1426 | 1426 | Sqm | 2024-09-22 | 2024-09-22 | 2025-05-18 | 2025-06-19
9442 | T-16-Sub structure Footings | Complete | Shuttering | 2024-09-23 | 2025-03-29 | Shuttering | 673 | 673 | Sqm | 2024-09-23 | 2024-09-23 | 2025-03-29 | 2024-11-14
39507 | Tower A - Super Structure - Core Wall Low Rise L34-35 | Complete | Core Wall RCC Works | 2024-09-23 | 2024-09-25 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-09-23 | 2024-09-23 | 2024-09-25 | 2024-09-25 | Tower A | Super Structure | L34 | RCC Super Structure | Core Wall RCC Works
39893 |  | Complete |  | 2024-09-23 | 2024-10-01 | L30-31 | 100 | 100 |  | 2024-09-23 | 2024-09-23 | 2024-10-01 | 2024-10-01
39893 |  | Complete |  | 2024-09-23 | 2024-10-01 | L30-31 | 100 | 100 |  | 2024-09-23 | 2024-09-23 | 2024-10-01 | 2024-10-01 |  |  |  | Finishes | Gypsum Plastering Works
39894 | Tower A - Super Structure - Core & Outer Slab L30-31 | Complete | RCC Works - Vertical | 2024-09-23 | 2024-09-28 | Outer Columns_TA | 100 | 100 |  | 2024-09-23 | 2024-09-23 | 2024-09-28 | 2024-09-28 | Tower A | Super Structure | L30 | RCC Sub Structure | RCC Works - Vertical
40257 |  | Complete |  | 2024-09-23 | 2025-02-11 | L27-28 | 100 | 100 |  | 2024-09-23 | 2024-09-23 | 2025-02-11 | 2025-02-11
40257 |  | Complete |  | 2024-09-23 | 2025-02-11 | L27-28 | 100 | 100 |  | 2024-09-23 | 2024-09-23 | 2025-02-11 | 2025-02-11 |  |  |  | Finishes | Gypsum Plastering Works
40258 | Tower A - Super Structure - Finishes & MEP - L27 to L28 | Complete | Partition Wall-Blockwork | 2024-09-23 | 2024-10-10 | De-shuttering & Area clearance | 100 | 100 |  | 2024-09-23 | 2024-09-23 | 2024-10-10 | 2024-10-10 | Tower A | Super Structure | L27
44792 | Tower B - Sub Structure - B3 to B2 - Pour 7 | Complete | RCC Works - Vertical | 2024-09-23 | 2024-10-04 | Col/ Wall Casting | 100 | 100 |  | 2024-09-23 | 2024-09-23 | 2024-10-04 | 2024-10-04 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
44792 | Tower B - Sub Structure - B3 to B2 - Pour 7 | Complete | RCC Works - Vertical | 2024-09-23 | 2024-10-04 | Col/ Wall Casting | 100 | 100 |  | 2024-09-23 | 2024-09-23 | 2024-10-04 | 2024-10-04 | Tower B | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
10482 | T-20-Sub structure Footings | Complete | Shuttering | 2024-09-24 | 2025-03-17 | Shuttering | 673 | 673 | Sqm | 2024-09-24 | 2024-09-24 | 2025-10-28 | 2024-10-27
39508 | Tower A - Super Structure - Core Wall Low Rise L34-35 | Complete | Core Wall RCC Works | 2024-09-24 | 2024-09-26 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-09-24 | 2024-09-24 | 2024-09-26 | 2024-09-26 | Tower A | Super Structure | L34 | RCC Super Structure | Core Wall RCC Works
42331 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Apartment Area | Started | Wet Area Waterproofing - MEP & Finishes | 2024-09-24 | 2024-09-25 | Wet Area Waterproofing | 100 | 90 |  | 2024-09-24 | 2024-09-24 | 2025-09-12 |  | Tower A | Super Structure | L14
44786 | Tower B - Sub Structure - B3 to B2 - Pour 1B & 6 | Complete | RCC Works - Slab | 2024-09-24 | 2024-10-08 | Slab & Staircase Fwk. | 100 | 100 |  | 2024-09-24 | 2024-09-24 | 2024-10-08 | 2024-10-08 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
48333 |  | Started |  | 2024-09-24 | 2024-10-05 | Pour RT-3 | 100 | 47 |  | 2024-09-24 | 2024-09-24 | 2025-09-19
48334 | Retail - Sub structure - B3 to B2 - P3 | Complete |  | 2024-09-24 | 2024-10-01 | Section 8_lift 2 | 100 | 100 |  | 2024-09-24 | 2024-09-24 | 2024-10-01 | 2024-10-01 | Retail | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
48334 | Retail - Sub structure - B3 to B2 - P3 | Complete |  | 2024-09-24 | 2024-10-01 | Section 8_lift 2 | 100 | 100 |  | 2024-09-24 | 2024-09-24 | 2024-10-01 | 2024-10-01 | Retail | Sub Structure | B3
9443 | T-16-Sub structure Footings | Complete | RCC | 2024-09-25 | 2025-03-30 | RCC | 713 | 713 | CUM | 2024-09-25 | 2024-09-25 | 2025-03-30 | 2024-11-15
9443 | T-16-Sub structure Footings | Complete | RCC | 2024-09-25 | 2025-03-30 | RCC | 713 | 713 | CUM | 2024-09-25 | 2024-09-25 | 2025-03-30 | 2024-11-15
39895 | Tower A - Super Structure - Core & Outer Slab L30-31 | Complete | RCC Works - Slab | 2024-09-25 | 2024-10-01 | Outer Slab_TA | 100 | 100 |  | 2024-09-25 | 2024-09-25 | 2024-10-01 | 2024-10-01 | Tower A | Super Structure | L30 | RCC Sub Structure | RCC Works - Slab
47569 |  | Complete |  | 2024-09-25 | 2024-10-03 | Waterproofing vertical - toe ht. | 100 | 100 |  | 2024-09-25 | 2024-09-25 | 2024-10-03 | 2024-10-03
47569 |  | Complete |  | 2024-09-25 | 2024-10-03 | Waterproofing vertical - toe ht. | 100 | 100 |  | 2024-09-25 | 2024-09-25 | 2024-10-03 | 2024-10-03 |  |  |  | RCC Sub Structure | Raft RCC Works
47569 |  | Complete |  | 2024-09-25 | 2024-10-03 | Waterproofing vertical - toe ht. | 100 | 100 |  | 2024-09-25 | 2024-09-25 | 2024-10-03 | 2024-10-03 |  |  |  | RCC Super Structure | Foundation RCC Works
9968 | T-21-Sub structure Retaining Wall | Started | RCC | 2024-09-26 | 2025-03-16 | RCC | 142.6 | 91.26 | CUM | 2024-09-26 | 2024-09-26 | 2025-05-20
9968 | T-21-Sub structure Retaining Wall | Started | RCC | 2024-09-26 | 2025-03-16 | RCC | 142.6 | 91.26 | CUM | 2024-09-26 | 2024-09-26 | 2025-05-20
39509 | Tower A - Super Structure - Core Wall Low Rise L34-35 | Complete | Core Wall RCC Works | 2024-09-26 | 2024-09-26 | Casting | 100 | 100 |  | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2024-09-26 | Tower A | Super Structure | L34 | RCC Super Structure | Core Wall RCC Works
40488 | Tower A - Super Structure - Finishes & MEP - L14 to L15 | Complete | Gypsum Plastering Works | 2024-09-26 | 2024-11-02 | L14-15 | 100 | 100 | Units | 2024-09-26 | 2025-05-21 | 2024-11-02 | 2025-07-16 | Tower A | Super Structure | L14 | Finishes | Gypsum Plastering Works
40488 | Tower A - Super Structure - Finishes & MEP - L14 to L15 | Complete | Gypsum Plastering Works | 2024-09-26 | 2024-11-02 | L14-15 | 100 | 100 | Units | 2024-09-26 | 2025-05-21 | 2024-11-02 | 2025-07-16 | Tower A | Super Structure | L14
42344 |  | Started |  | 2024-09-26 | 2026-06-05 | L15-16 | 100 | 82 |  | 2024-09-26 | 2024-09-26 | 2026-06-03 |  |  |  |  | Finishes | Gypsum Plastering Works
42344 |  | Started |  | 2024-09-26 | 2026-06-05 | L15-16 | 100 | 82 |  | 2024-09-26 | 2024-09-26 | 2026-06-03
42345 |  | Started |  | 2024-09-26 | 2024-10-22 | MEP 1st Fixes | 100 | 86 |  | 2024-09-26 | 2024-09-26 | 2025-09-13
42346 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Apartment Area | Started | FPS 1st Fix - MEP & Finishes | 2024-09-26 | 2024-09-27 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 80 |  | 2024-09-26 | 2024-09-26 | 2025-09-12 |  | Tower A | Super Structure | L15 | MEP | FPS 1st Fix - MEP & Finishes
42347 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Apartment Area | Started | Electrical 1st Fix - MEP & Finishes | 2024-09-26 | 2024-09-26 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 90 |  | 2024-09-26 | 2024-09-26 | 2025-09-11 |  | Tower A | Super Structure | L15 | MEP | Electrical 1st Fixes
42348 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Apartment Area | Started | PHE 1st Fix - MEP & Finishes | 2024-09-26 | 2024-09-27 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 80 |  | 2024-09-26 | 2024-09-26 | 2025-09-12 |  | Tower A | Super Structure | L15
44801 | Tower B - Sub Structure - B3 to B2 - Pour 8 | Complete | RCC Works - Slab | 2024-09-26 | 2024-10-25 | Slab & Staircase Reinf. | 100 | 100 |  | 2024-09-26 | 2024-09-26 | 2024-10-25 | 2024-10-25 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
44809 | Tower B - Sub Structure - B3 to B2 - Pour 5 | Complete | RCC Works - Slab | 2024-09-26 | 2024-09-28 | Slab & Staircase Casting | 100 | 100 |  | 2024-09-26 | 2024-09-26 | 2024-09-28 | 2024-09-28 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
47589 |  | Started |  | 2024-09-26 | 2026-11-07 | Sub-Structure_NTA Zone 3 | 100 | 44 |  | 2024-09-26 | 2024-09-26 | 2027-02-19
47590 |  | Started |  | 2024-09-26 | 2026-04-30 | B3 to B2 | 100 | 45 |  | 2024-09-26 | 2024-09-26 | 2026-12-02
47590 |  | Started |  | 2024-09-26 | 2026-04-30 | B3 to B2 | 100 | 45 |  | 2024-09-26 | 2024-09-26 | 2026-12-02
47590 |  | Started |  | 2024-09-26 | 2026-04-30 | B3 to B2 | 100 | 45 |  | 2024-09-26 | 2024-09-26 | 2026-12-02
47591 |  | Started |  | 2024-09-26 | 2025-10-06 | Retaining Wall_lift 1 (Grid PB-N onwards) | 100 | 74 |  | 2024-09-26 | 2024-09-26 | 2025-10-06
47592 |  | Complete |  | 2024-09-26 | 2024-09-26 | Section 1_lift 1 | 100 | 100 |  | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2024-09-26
47592 |  | Complete |  | 2024-09-26 | 2024-09-26 | Section 1_lift 1 | 100 | 100 |  | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2024-09-26 |  |  |  | RCC Super Structure | Retaining Wall RCC Works
39510 | Tower A - Super Structure - Core Wall Low Rise L34-35 | Complete | Core Wall RCC Works | 2024-09-27 | 2024-09-27 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2024-09-27 | Tower A | Super Structure | L34 | RCC Super Structure | Core Wall RCC Works
42314 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Apartment Area | Started | Cement Plastering in Wet Areas - MEP & Finishes | 2024-09-27 | 2024-09-27 | Cement Plastering in wet areas | 100 | 90 |  | 2024-09-27 | 2024-09-27 | 2025-09-13 |  | Tower A | Super Structure | L13
47593 |  | Complete |  | 2024-09-27 | 2024-10-05 | Section 2_lift 1 | 100 | 100 |  | 2024-09-27 | 2024-09-27 | 2024-10-05 | 2024-10-05
47593 |  | Complete |  | 2024-09-27 | 2024-10-05 | Section 2_lift 1 | 100 | 100 |  | 2024-09-27 | 2024-09-27 | 2024-10-05 | 2024-10-05 |  |  |  | RCC Super Structure | Retaining Wall RCC Works
8376 |  | Started |  | 2024-09-28 | 2025-03-17 | Columns | 100 | 58 |  | 2024-09-28 | 2024-09-28 | 2025-12-09
8377 | T-14-Sub structure Columns | Started | Reinforcement | 2024-09-28 | 2025-03-09 | Reinforcement | 25 | 24 | Units | 2024-09-28 | 2024-09-28 | 2025-12-07
8385 |  | Started | Backfilling | 2024-09-28 | 2025-04-30 | Backfilling | 100 | 20 |  | 2024-09-28 | 2024-09-28 | 2025-07-03
10483 | T-20-Sub structure Footings | Complete | RCC | 2024-09-28 | 2025-03-14 | RCC | 713 | 713 | CUM | 2024-09-28 | 2024-09-28 | 2025-10-29 | 2024-10-28
10483 | T-20-Sub structure Footings | Complete | RCC | 2024-09-28 | 2025-03-14 | RCC | 713 | 713 | CUM | 2024-09-28 | 2024-09-28 | 2025-10-29 | 2024-10-28
39511 |  | Complete |  | 2024-09-28 | 2024-10-08 | Core Wall L35-36 | 100 | 100 |  | 2024-09-28 | 2024-09-28 | 2024-10-08 | 2024-10-08
39512 | Tower A - Super Structure - Core Wall Low Rise L35-36 | Complete | Core Wall RCC Works | 2024-09-28 | 2024-09-28 | Scaffolding & platform | 100 | 100 |  | 2024-09-28 | 2024-09-28 | 2024-09-28 | 2024-09-28 | Tower A | Super Structure | L35 | RCC Super Structure | Core Wall RCC Works
40216 | Tower A - Super Structure - Finishes & MEP - L16 to L17 | Complete | Partition Wall-Blockwork | 2024-09-28 | 2024-11-04 | Staircase Area | 100 | 100 |  | 2024-09-28 | 2024-09-28 | 2024-11-04 | 2024-11-04 | Tower A | Super Structure | L16
40219 | Tower A - Super Structure - Finishes & MEP - L17 to L18 | Complete | Partition Wall-Blockwork | 2024-09-28 | 2024-10-07 | Partition Walls | 100 | 100 |  | 2024-09-28 | 2024-09-28 | 2024-10-07 | 2024-10-07 | Tower A | Super Structure | L17
44793 | Tower B - Sub Structure - B3 to B2 - Pour 7 | Complete | RCC Works - Slab | 2024-09-28 | 2024-10-14 | Slab & Staircase Fwk. | 100 | 100 |  | 2024-09-28 | 2024-09-28 | 2024-10-14 | 2024-10-14 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
39513 | Tower A - Super Structure - Core Wall Low Rise L35-36 | Complete | Core Wall RCC Works | 2024-09-30 | 2024-10-03 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-09-30 | 2024-09-30 | 2024-10-03 | 2024-10-03 | Tower A | Super Structure | L35 | RCC Super Structure | Core Wall RCC Works
44857 |  | Complete |  | 2024-09-30 | 2024-10-25 | Pour 5_B2 to B1 | 100 | 100 |  | 2024-09-30 | 2024-09-30 | 2024-10-25 | 2024-10-25
44858 | Tower B - Sub Structure - B2 to B1 - Pour 5 | Complete | RCC Works - Vertical | 2024-09-30 | 2024-10-08 | Col/ Wall Reinf. | 100 | 100 |  | 2024-09-30 | 2024-09-30 | 2024-10-08 | 2024-10-08 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
44858 | Tower B - Sub Structure - B2 to B1 - Pour 5 | Complete | RCC Works - Vertical | 2024-09-30 | 2024-10-08 | Col/ Wall Reinf. | 100 | 100 |  | 2024-09-30 | 2024-09-30 | 2024-10-08 | 2024-10-08 | Tower B | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
44859 | Tower B - Sub Structure - B2 to B1 - Pour 5 | Complete | RCC Works - Vertical | 2024-09-30 | 2024-10-11 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-09-30 | 2024-09-30 | 2024-10-11 | 2024-10-11 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
44859 | Tower B - Sub Structure - B2 to B1 - Pour 5 | Complete | RCC Works - Vertical | 2024-09-30 | 2024-10-11 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-09-30 | 2024-09-30 | 2024-10-11 | 2024-10-11 | Tower B | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
8378 | T-14-Sub structure Columns | Started | Shuttering | 2024-10-01 | 2025-03-14 | Shuttering | 319 | 19.14 | Sqm | 2024-10-01 | 2024-10-01 | 2025-12-08
8919 |  | Complete |  | 2024-10-01 | 2025-03-15 | Isolated & Combined Footings | 100 | 100 |  | 2024-10-01 | 2024-10-01 | 2025-11-20 | 2024-11-19
8920 | T-15-Sub structure Footings | Complete | PCC | 2024-10-01 | 2025-03-12 | PCC | 98 | 98 | CUM | 2024-10-01 | 2024-10-01 | 2025-11-10 | 2024-11-16
39155 |  | Complete |  | 2024-10-01 | 2024-10-14 | Blockwork for Transformer Room | 100 | 100 |  | 2024-10-01 | 2024-10-01 | 2024-10-14 | 2024-10-14
39178 |  | Complete |  | 2024-10-01 | 2024-10-14 | Lightweight Filling in the Parking Pits | 100 | 100 |  | 2024-10-01 | 2024-10-01 | 2024-10-14 | 2024-10-14
39514 | Tower A - Super Structure - Core Wall Low Rise L35-36 | Complete | Core Wall RCC Works | 2024-10-01 | 2024-10-04 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-10-01 | 2024-10-01 | 2024-10-04 | 2024-10-04 | Tower A | Super Structure | L35 | RCC Super Structure | Core Wall RCC Works
44767 | Tower B - Sub Structure - B3 to B2 | Complete | Core Wall RCC Works | 2024-10-01 | 2024-10-04 | CW Casting | 100 | 100 |  | 2024-10-01 | 2024-10-01 | 2024-10-04 | 2024-10-04 | Tower B | Sub Structure | B3 | RCC Super Structure | Core Wall RCC Works
44802 | Tower B - Sub Structure - B3 to B2 - Pour 8 | Complete | RCC Works - Slab | 2024-10-01 | 2024-10-29 | Slab & Staircase Casting | 100 | 100 |  | 2024-10-01 | 2024-10-01 | 2024-10-29 | 2024-10-29 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
8921 | T-15-Sub structure Footings | Complete | Reinforcement | 2024-10-03 | 2025-03-15 | Reinforcement | 71 | 71 | MT | 2024-10-03 | 2024-10-03 | 2025-11-18 | 2024-11-17
9969 |  | Started |  | 2024-10-03 | 2025-03-23 | Columns | 100 | 28 |  | 2024-10-03 | 2024-10-03 | 2025-05-27
9970 | T-21-Sub structure Columns | Started | Reinforcement | 2024-10-03 | 2025-03-23 | Reinforcement | 100 | 20 | Units | 2024-10-03 | 2024-10-03 | 2025-05-27
39896 |  | Complete |  | 2024-10-03 | 2024-10-10 | L31-32 | 100 | 100 |  | 2024-10-03 | 2024-10-03 | 2024-10-10 | 2024-10-10
39896 |  | Complete |  | 2024-10-03 | 2024-10-10 | L31-32 | 100 | 100 |  | 2024-10-03 | 2024-10-03 | 2024-10-10 | 2024-10-10 |  |  |  | Finishes | Gypsum Plastering Works
39897 | Tower A - Super Structure - Core & Outer Slab L31-32 | Complete | RCC Works - Vertical | 2024-10-03 | 2024-10-09 | Outer Columns_TA | 100 | 100 |  | 2024-10-03 | 2024-10-03 | 2024-10-09 | 2024-10-09 | Tower A | Super Structure | L31 | RCC Sub Structure | RCC Works - Vertical
40261 |  | Complete |  | 2024-10-03 | 2025-02-19 | L28-29 | 100 | 100 |  | 2024-10-03 | 2024-10-03 | 2025-02-19 | 2025-02-19
40261 |  | Complete |  | 2024-10-03 | 2025-02-19 | L28-29 | 100 | 100 |  | 2024-10-03 | 2024-10-03 | 2025-02-19 | 2025-02-19 |  |  |  | Finishes | Gypsum Plastering Works
40262 | Tower A - Super Structure - Finishes & MEP - L28 to L29 | Complete | Partition Wall-Blockwork | 2024-10-03 | 2024-10-21 | De-shuttering & Area clearance | 100 | 100 |  | 2024-10-03 | 2024-10-03 | 2024-10-21 | 2024-10-21 | Tower A | Super Structure | L28
42349 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Apartment Area | Started | Wet Area Waterproofing - MEP & Finishes | 2024-10-03 | 2024-10-04 | Wet Area Waterproofing | 100 | 90 |  | 2024-10-03 | 2024-10-03 | 2025-09-12 |  | Tower A | Super Structure | L15
44860 | Tower B - Sub Structure - B2 to B1 - Pour 5 | Complete | RCC Works - Vertical | 2024-10-03 | 2024-10-15 | Col/ Wall Casting | 100 | 100 |  | 2024-10-03 | 2024-10-03 | 2024-10-15 | 2024-10-15 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
44860 | Tower B - Sub Structure - B2 to B1 - Pour 5 | Complete | RCC Works - Vertical | 2024-10-03 | 2024-10-15 | Col/ Wall Casting | 100 | 100 |  | 2024-10-03 | 2024-10-03 | 2024-10-15 | 2024-10-15 | Tower B | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
44869 | Tower B - Sub Structure - B2 to B1 - Pour 4 | Complete | RCC Works - Slab | 2024-10-03 | 2024-10-07 | Slab & Staircase Reinf. | 100 | 100 |  | 2024-10-03 | 2024-10-03 | 2024-10-07 | 2024-10-07 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
8379 | T-14-Sub structure Columns | Started | RCC | 2024-10-04 | 2025-03-17 | RCC | 35 | 25 | CUM | 2024-10-04 | 2024-10-04 | 2025-12-09
8379 | T-14-Sub structure Columns | Started | RCC | 2024-10-04 | 2025-03-17 | RCC | 35 | 25 | CUM | 2024-10-04 | 2024-10-04 | 2025-12-09
44787 | Tower B - Sub Structure - B3 to B2 - Pour 1B & 6 | Complete | RCC Works - Slab | 2024-10-04 | 2024-10-11 | Slab & Staircase Reinf. | 100 | 100 |  | 2024-10-04 | 2024-10-04 | 2024-10-11 | 2024-10-11 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
47570 |  | Complete |  | 2024-10-04 | 2024-10-11 | RW toe foundation | 100 | 100 |  | 2024-10-04 | 2024-10-04 | 2024-10-11 | 2024-10-11
47570 |  | Complete |  | 2024-10-04 | 2024-10-11 | RW toe foundation | 100 | 100 |  | 2024-10-04 | 2024-10-04 | 2024-10-11 | 2024-10-11 |  |  |  | RCC Sub Structure | Raft RCC Works
47570 |  | Complete |  | 2024-10-04 | 2024-10-11 | RW toe foundation | 100 | 100 |  | 2024-10-04 | 2024-10-04 | 2024-10-11 | 2024-10-11 |  |  |  | RCC Super Structure | Foundation RCC Works
47571 |  | Complete |  | 2024-10-04 | 2024-10-09 | Waterproofing-Raft Area | 100 | 100 |  | 2024-10-04 | 2024-10-04 | 2024-10-09 | 2024-10-09
48378 |  | Started |  | 2024-10-04 | 2025-04-14 | B2 to B1 | 100 | 55 |  | 2024-10-04 | 2024-10-04 | 2025-10-30
48378 |  | Started |  | 2024-10-04 | 2025-04-14 | B2 to B1 | 100 | 55 |  | 2024-10-04 | 2024-10-04 | 2025-10-30
48378 |  | Started |  | 2024-10-04 | 2025-04-14 | B2 to B1 | 100 | 55 |  | 2024-10-04 | 2024-10-04 | 2025-10-30
48379 |  | Started |  | 2024-10-04 | 2025-03-31 | Retaining Wall_lift 1 (Grid PA-A onwards) | 100 | 64 |  | 2024-10-04 | 2024-10-04 | 2025-10-04
48380 |  | Complete |  | 2024-10-04 | 2024-10-25 | Pour RT-1 | 100 | 100 |  | 2024-10-04 | 2024-10-04 | 2024-10-25 | 2024-10-25
48381 | Retail - Sub structure - B2 to B1 - P1 | Complete |  | 2024-10-04 | 2024-10-11 | Section 1_lift 1 | 100 | 100 |  | 2024-10-04 | 2024-10-04 | 2024-10-11 | 2024-10-11 | Retail | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
48381 | Retail - Sub structure - B2 to B1 - P1 | Complete |  | 2024-10-04 | 2024-10-11 | Section 1_lift 1 | 100 | 100 |  | 2024-10-04 | 2024-10-04 | 2024-10-11 | 2024-10-11 | Retail | Sub Structure | B2
8922 | T-15-Sub structure Footings | Complete | Shuttering | 2024-10-05 | 2025-03-14 | Shuttering | 673 | 673 | Sqm | 2024-10-05 | 2024-10-05 | 2025-11-19 | 2024-11-18
9971 | T-21-Sub structure Columns | Started | Shuttering | 2024-10-05 | 2025-03-23 | Shuttering | 319 | 20 | Sqm | 2024-10-05 | 2024-10-05 | 2025-05-27
39515 | Tower A - Super Structure - Core Wall Low Rise L35-36 | Complete | Core Wall RCC Works | 2024-10-05 | 2024-10-07 | Casting | 100 | 100 |  | 2024-10-05 | 2024-10-05 | 2024-10-07 | 2024-10-07 | Tower A | Super Structure | L35 | RCC Super Structure | Core Wall RCC Works
39898 | Tower A - Super Structure - Core & Outer Slab L31-32 | Complete | RCC Works - Slab | 2024-10-05 | 2024-10-10 | Outer Slab_TA | 100 | 100 |  | 2024-10-05 | 2024-10-05 | 2024-10-10 | 2024-10-10 | Tower A | Super Structure | L31 | RCC Sub Structure | RCC Works - Slab
40489 | Tower A - Super Structure - Finishes & MEP - L15 to L16 | Complete | Gypsum Plastering Works | 2024-10-05 | 2024-11-11 | L15-16 | 100 | 100 | Units | 2024-10-05 | 2025-05-26 | 2024-11-11 | 2025-08-02 | Tower A | Super Structure | L15 | Finishes | Gypsum Plastering Works
40489 | Tower A - Super Structure - Finishes & MEP - L15 to L16 | Complete | Gypsum Plastering Works | 2024-10-05 | 2024-11-11 | L15-16 | 100 | 100 | Units | 2024-10-05 | 2025-05-26 | 2024-11-11 | 2025-08-02 | Tower A | Super Structure | L15
44861 | Tower B - Sub Structure - B2 to B1 - Pour 5 | Complete | RCC Works - Slab | 2024-10-05 | 2024-10-19 | Slab & Staircase Fwk. | 100 | 100 |  | 2024-10-05 | 2024-10-05 | 2024-10-19 | 2024-10-19 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
47603 |  | Started |  | 2024-10-06 | 2025-01-10 | Retaining Wall_lift 2 | 100 | 39 |  | 2024-10-06 | 2024-10-07 | 2025-10-07 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47603 |  | Started |  | 2024-10-06 | 2025-01-10 | Retaining Wall_lift 2 | 100 | 39 |  | 2024-10-06 | 2024-10-07 | 2025-10-07
47604 |  | Milestone Started |  | 2024-10-06 |  | Section 1_lift 2 | 100 | 100 |  | 2024-10-06 | 2024-11-14 | [5 empty] | RCC Super Structure | Retaining Wall RCC Works
47604 |  | Milestone Started |  | 2024-10-06 |  | Section 1_lift 2 | 100 | 100 |  | 2024-10-06 | 2024-11-14
47606 |  | Milestone Started |  | 2024-10-06 |  | Section 3_lift 2 | 100 | 100 |  | 2024-10-06 | 2024-10-14 | [5 empty] | RCC Super Structure | Retaining Wall RCC Works
47606 |  | Milestone Started |  | 2024-10-06 |  | Section 3_lift 2 | 100 | 100 |  | 2024-10-06 | 2024-10-14
8923 | T-15-Sub structure Footings | Complete | RCC | 2024-10-07 | 2025-03-14 | RCC | 713 | 713 | CUM | 2024-10-07 | 2024-10-07 | 2025-11-20 | 2024-11-19
8923 | T-15-Sub structure Footings | Complete | RCC | 2024-10-07 | 2025-03-14 | RCC | 713 | 713 | CUM | 2024-10-07 | 2024-10-07 | 2025-11-20 | 2024-11-19
9972 | T-21-Sub structure Columns | Started | RCC | 2024-10-07 | 2025-03-23 | RCC | 35 | 20 | CUM | 2024-10-07 | 2024-10-07 | 2025-05-27
9972 | T-21-Sub structure Columns | Started | RCC | 2024-10-07 | 2025-03-23 | RCC | 35 | 20 | CUM | 2024-10-07 | 2024-10-07 | 2025-05-27
10996 |  | Started |  | 2024-10-07 | 2027-02-20 | Tower 19 | 100 | 26 |  | 2024-10-07 | 2024-10-07 | 2027-01-20
10997 |  | Started |  | 2024-10-07 | 2025-07-07 | Sub Structure Up to Podium | 100 | 47 |  | 2024-10-07 | 2024-10-07 | 2025-10-26
10998 |  | Started |  | 2024-10-07 | 2025-04-30 | Footings | 100 | 71 |  | 2024-10-07 | 2024-10-07 | 2025-10-26
10999 |  | Quality checked |  | 2024-10-07 | 2025-03-21 | Isolated & Combined Footings | 100 | 100 |  | 2024-10-07 | 2024-10-07 | 2025-10-26 | 2024-10-25
11000 | T-19-Sub structure Footings | Quality checked | PCC | 2024-10-07 | 2025-03-14 | PCC | 98 | 98 | CUM | 2024-10-07 | 2024-10-07 | 2025-10-01 | 2024-10-22
47596 |  | Complete |  | 2024-10-07 | 2024-10-15 | Section 5_lift 1 | 100 | 100 |  | 2024-10-07 | 2024-10-07 | 2024-10-15 | 2024-10-15
47596 |  | Complete |  | 2024-10-07 | 2024-10-15 | Section 5_lift 1 | 100 | 100 |  | 2024-10-07 | 2024-10-07 | 2024-10-15 | 2024-10-15 |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47605 |  | Complete |  | 2024-10-07 | 2024-10-15 | Section 2_lift 2 | 100 | 100 |  | 2024-10-07 | 2024-10-07 | 2024-10-15 | 2024-10-15
47605 |  | Complete |  | 2024-10-07 | 2024-10-15 | Section 2_lift 2 | 100 | 100 |  | 2024-10-07 | 2024-10-07 | 2024-10-15 | 2024-10-15 |  |  |  | RCC Super Structure | Retaining Wall RCC Works
39156 |  | Complete |  | 2024-10-08 | 2024-10-11 | Foundation for Transformers | 100 | 100 |  | 2024-10-08 | 2024-10-08 | 2024-10-11 | 2024-10-11
39516 | Tower A - Super Structure - Core Wall Low Rise L35-36 | Complete | Core Wall RCC Works | 2024-10-08 | 2024-10-08 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-08 | Tower A | Super Structure | L35 | RCC Super Structure | Core Wall RCC Works
39517 |  | Complete |  | 2024-10-08 | 2024-10-21 | Core Wall L36-37 | 100 | 100 |  | 2024-10-08 | 2024-10-08 | 2024-10-21 | 2024-10-21
39518 | Tower A - Super Structure - Core Wall Low Rise L36-37 | Complete | Core Wall RCC Works | 2024-10-08 | 2024-10-08 | Scaffolding & platform | 100 | 100 |  | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-08 | Tower A | Super Structure | L36 | RCC Super Structure | Core Wall RCC Works
40220 | Tower A - Super Structure - Finishes & MEP - L17 to L18 | Complete | Partition Wall-Blockwork | 2024-10-08 | 2024-10-14 | Staircase Area | 100 | 100 |  | 2024-10-08 | 2024-10-08 | 2024-10-14 | 2024-10-14 | Tower A | Super Structure | L17
40223 | Tower A - Super Structure - Finishes & MEP - L18 to L19 | Complete | Partition Wall-Blockwork | 2024-10-08 | 2024-10-16 | Partition Walls | 100 | 100 |  | 2024-10-08 | 2024-10-08 | 2024-10-16 | 2024-10-16 | Tower A | Super Structure | L18
44870 | Tower B - Sub Structure - B2 to B1 - Pour 4 | Complete | RCC Works - Slab | 2024-10-08 | 2024-12-14 | Slab & Staircase Casting | 100 | 100 |  | 2024-10-08 | 2024-10-08 | 2024-12-14 | 2024-12-14 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
48399 |  | Complete |  | 2024-10-08 | 2025-01-30 | Pour RT-1 | 100 | 100 |  | 2024-10-08 | 2024-10-08 | 2025-01-30 | 2025-01-30
48400 | Retail - Sub structure - B2 to B1 - P1 | Complete |  | 2024-10-08 | 2024-10-26 | Columns/ Walls_NTA | 100 | 100 |  | 2024-10-08 | 2024-10-08 | 2024-10-26 | 2024-10-26 | Retail | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
48400 | Retail - Sub structure - B2 to B1 - P1 | Complete |  | 2024-10-08 | 2024-10-26 | Columns/ Walls_NTA | 100 | 100 |  | 2024-10-08 | 2024-10-08 | 2024-10-26 | 2024-10-26 | Retail | Sub Structure | B2
11001 | T-19-Sub structure Footings | Quality checked | Reinforcement | 2024-10-09 | 2025-03-21 | Reinforcement | 71 | 71 | MT | 2024-10-09 | 2024-10-09 | 2025-10-24 | 2024-10-23
39519 | Tower A - Super Structure - Core Wall Low Rise L36-37 | Complete | Core Wall RCC Works | 2024-10-09 | 2024-10-11 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-10-09 | 2024-10-09 | 2024-10-11 | 2024-10-11 | Tower A | Super Structure | L36 | RCC Super Structure | Core Wall RCC Works
48382 | Retail - Sub structure - B2 to B1 - P1 | Complete |  | 2024-10-09 | 2024-10-17 | Section 2_lift 1 | 100 | 100 |  | 2024-10-09 | 2024-10-09 | 2024-10-17 | 2024-10-17 | Retail | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
48382 | Retail - Sub structure - B2 to B1 - P1 | Complete |  | 2024-10-09 | 2024-10-17 | Section 2_lift 1 | 100 | 100 |  | 2024-10-09 | 2024-10-09 | 2024-10-17 | 2024-10-17 | Retail | Sub Structure | B2
39520 | Tower A - Super Structure - Core Wall Low Rise L36-37 | Complete | Core Wall RCC Works | 2024-10-10 | 2024-10-14 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-10-10 | 2024-10-10 | 2024-10-14 | 2024-10-14 | Tower A | Super Structure | L36 | RCC Super Structure | Core Wall RCC Works
41139 |  | Started |  | 2024-10-10 | 2026-01-01 | L12-13 | 100 | 66 |  | 2024-10-10 | 2024-10-10 | 2026-01-22 |  |  |  |  | Finishes | Gypsum Plastering Works
41139 |  | Started |  | 2024-10-10 | 2026-01-01 | L12-13 | 100 | 66 |  | 2024-10-10 | 2024-10-10 | 2026-01-22
41140 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2024-10-10 | 2024-10-10 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 80 |  | 2024-10-10 | 2024-10-10 | 2025-12-11 |  | Tower A | Super Structure | L12 | MEP | FPS 1st Fix - MEP & Finishes
47572 |  | Complete |  | 2024-10-10 | 2024-10-28 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2024-10-10 | 2024-10-10 | 2024-10-28 | 2024-10-28
47572 |  | Complete |  | 2024-10-10 | 2024-10-28 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2024-10-10 | 2024-10-10 | 2024-10-28 | 2024-10-28 |  |  |  | RCC Sub Structure | Raft RCC Works
47572 |  | Complete |  | 2024-10-10 | 2024-10-28 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2024-10-10 | 2024-10-10 | 2024-10-28 | 2024-10-28 |  |  |  | RCC Super Structure | Foundation RCC Works
47576 |  | Complete |  | 2024-10-10 | 2024-10-16 | Waterproofing-Raft Area | 100 | 100 |  | 2024-10-10 | 2024-10-10 | 2024-10-16 | 2024-10-16
11002 | T-19-Sub structure Footings | Quality checked | Shuttering | 2024-10-11 | 2025-03-21 | Shuttering | 673 | 673 | Sqm | 2024-10-11 | 2024-10-11 | 2025-10-25 | 2024-10-24
39899 |  | Complete |  | 2024-10-11 | 2024-10-20 | L32-33 | 100 | 100 |  | 2024-10-11 | 2024-10-11 | 2024-10-20 | 2024-10-20
39899 |  | Complete |  | 2024-10-11 | 2024-10-20 | L32-33 | 100 | 100 |  | 2024-10-11 | 2024-10-11 | 2024-10-20 | 2024-10-20 |  |  |  | Finishes | Gypsum Plastering Works
39900 | Tower A - Super Structure - Core & Outer Slab L32-33 | Complete | RCC Works - Vertical | 2024-10-11 | 2024-10-18 | Outer Columns_TA | 100 | 100 |  | 2024-10-11 | 2024-10-11 | 2024-10-18 | 2024-10-18 | Tower A | Super Structure | L32 | RCC Sub Structure | RCC Works - Vertical
40265 |  | Started |  | 2024-10-11 | 2025-02-27 | L29-30 | 100 | 55 |  | 2024-10-11 | 2024-10-11 | 2025-09-25 |  |  |  |  | Finishes | Gypsum Plastering Works
40265 |  | Started |  | 2024-10-11 | 2025-02-27 | L29-30 | 100 | 55 |  | 2024-10-11 | 2024-10-11 | 2025-09-25
40266 | Tower A - Super Structure - Finishes & MEP - L29 to L30 | Complete | Partition Wall-Blockwork | 2024-10-11 | 2024-10-29 | De-shuttering & Area clearance | 100 | 100 |  | 2024-10-11 | 2024-10-11 | 2024-10-29 | 2024-10-29 | Tower A | Super Structure | L29
42332 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Apartment Area | Started | Cement Plastering in Wet Areas - MEP & Finishes | 2024-10-14 | 2024-10-14 | Cement Plastering in wet areas | 100 | 90 |  | 2024-10-14 | 2024-10-14 | 2025-09-13 |  | Tower A | Super Structure | L14
44794 | Tower B - Sub Structure - B3 to B2 - Pour 7 | Complete | RCC Works - Slab | 2024-10-14 | 2024-10-17 | Slab & Staircase Reinf. | 100 | 100 |  | 2024-10-14 | 2024-10-14 | 2024-10-17 | 2024-10-17 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
47607 |  | Complete |  | 2024-10-14 | 2024-10-14 | Section 4_lift 2 | 100 | 100 |  | 2024-10-14 | 2024-10-14 | 2024-10-14 | 2024-10-14
47607 |  | Complete |  | 2024-10-14 | 2024-10-14 | Section 4_lift 2 | 100 | 100 |  | 2024-10-14 | 2024-10-14 | 2024-10-14 | 2024-10-14 |  |  |  | RCC Super Structure | Retaining Wall RCC Works
48383 | Retail - Sub structure - B2 to B1 - P1 | Complete |  | 2024-10-14 | 2024-10-21 | Section 3_lift 1 | 100 | 100 |  | 2024-10-14 | 2024-10-14 | 2024-10-21 | 2024-10-21 | Retail | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
48383 | Retail - Sub structure - B2 to B1 - P1 | Complete |  | 2024-10-14 | 2024-10-21 | Section 3_lift 1 | 100 | 100 |  | 2024-10-14 | 2024-10-14 | 2024-10-21 | 2024-10-21 | Retail | Sub Structure | B2
39179 |  | Complete |  | 2024-10-15 | 2024-10-25 | Blockwork for Chiller Room | 100 | 100 |  | 2024-10-15 | 2024-10-15 | 2024-10-25 | 2024-10-25
39521 | Tower A - Super Structure - Core Wall Low Rise L36-37 | Complete | Core Wall RCC Works | 2024-10-15 | 2024-10-19 | Casting | 100 | 100 |  | 2024-10-15 | 2024-10-15 | 2024-10-19 | 2024-10-19 | Tower A | Super Structure | L36 | RCC Super Structure | Core Wall RCC Works
39901 | Tower A - Super Structure - Core & Outer Slab L32-33 | Complete | RCC Works - Slab | 2024-10-15 | 2024-10-20 | Outer Slab_TA | 100 | 100 |  | 2024-10-15 | 2024-10-15 | 2024-10-20 | 2024-10-20 | Tower A | Super Structure | L32 | RCC Sub Structure | RCC Works - Slab
42380 |  | Started |  | 2024-10-15 | 2026-06-11 | L17-18 | 100 | 71 |  | 2024-10-15 | 2024-10-15 | 2026-06-09 |  |  |  |  | Finishes | Gypsum Plastering Works
42380 |  | Started |  | 2024-10-15 | 2026-06-11 | L17-18 | 100 | 71 |  | 2024-10-15 | 2024-10-15 | 2026-06-09
42381 |  | Started |  | 2024-10-15 | 2024-11-09 | MEP 1st Fixes | 100 | 74 |  | 2024-10-15 | 2024-10-15 | 2025-09-22
42382 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Apartment Area | Started | FPS 1st Fix - MEP & Finishes | 2024-10-15 | 2024-10-16 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 80 |  | 2024-10-15 | 2024-10-15 | 2025-09-12 |  | Tower A | Super Structure | L17 | MEP | FPS 1st Fix - MEP & Finishes
42383 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Apartment Area | Started | Electrical 1st Fix - MEP & Finishes | 2024-10-15 | 2024-10-15 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 90 |  | 2024-10-15 | 2024-10-15 | 2025-09-11 |  | Tower A | Super Structure | L17 | MEP | Electrical 1st Fixes
42384 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Apartment Area | Started | PHE 1st Fix - MEP & Finishes | 2024-10-15 | 2024-10-16 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 80 |  | 2024-10-15 | 2024-10-15 | 2025-09-12 |  | Tower A | Super Structure | L17
42385 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Apartment Area | Started | Wet Area Waterproofing - MEP & Finishes | 2024-10-15 | 2024-10-16 | Wet Area Waterproofing | 100 | 90 |  | 2024-10-15 | 2024-10-15 | 2025-09-12 |  | Tower A | Super Structure | L17
44788 | Tower B - Sub Structure - B3 to B2 - Pour 1B & 6 | Complete | RCC Works - Slab | 2024-10-15 | 2024-10-15 | Slab & Staircase Casting | 100 | 100 |  | 2024-10-15 | 2024-10-15 | 2024-10-15 | 2024-10-15 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
11003 | T-19-Sub structure Footings | Quality checked | RCC | 2024-10-16 | 2025-03-21 | RCC | 713 | 713 | CUM | 2024-10-16 | 2024-10-16 | 2025-10-26 | 2024-10-25
11003 | T-19-Sub structure Footings | Quality checked | RCC | 2024-10-16 | 2025-03-21 | RCC | 713 | 713 | CUM | 2024-10-16 | 2024-10-16 | 2025-10-26 | 2024-10-25
41155 |  | Started |  | 2024-10-16 | 2026-01-07 | L13-14 | 100 | 66 |  | 2024-10-16 | 2024-10-16 | 2026-01-29 |  |  |  |  | Finishes | Gypsum Plastering Works
41155 |  | Started |  | 2024-10-16 | 2026-01-07 | L13-14 | 100 | 66 |  | 2024-10-16 | 2024-10-16 | 2026-01-29
41156 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2024-10-16 | 2024-10-16 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 80 |  | 2024-10-16 | 2024-10-16 | 2025-12-17 |  | Tower A | Super Structure | L13 | MEP | FPS 1st Fix - MEP & Finishes
44818 |  | Complete |  | 2024-10-16 | 2024-11-06 | Core Wall B2-B1 | 100 | 100 |  | 2024-10-16 | 2024-10-16 | 2024-11-06 | 2024-11-06
44819 | Tower B - Sub Structure - B2 to B1 | Complete | Core Wall RCC Works | 2024-10-16 | 2024-10-29 | CW Reinf | 100 | 100 |  | 2024-10-16 | 2024-10-16 | 2024-10-29 | 2024-10-29 | Tower B | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
47597 |  | Complete |  | 2024-10-16 | 2024-10-23 | Section 6_lift 1 | 100 | 100 |  | 2024-10-16 | 2024-10-16 | 2024-10-23 | 2024-10-23
47597 |  | Complete |  | 2024-10-16 | 2024-10-23 | Section 6_lift 1 | 100 | 100 |  | 2024-10-16 | 2024-10-16 | 2024-10-23 | 2024-10-23 |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47608 |  | Complete |  | 2024-10-16 | 2024-10-23 | Section 5_lift 2 | 100 | 100 |  | 2024-10-16 | 2024-10-16 | 2024-10-23 | 2024-10-23
47608 |  | Complete |  | 2024-10-16 | 2024-10-23 | Section 5_lift 2 | 100 | 100 |  | 2024-10-16 | 2024-10-16 | 2024-10-23 | 2024-10-23 |  |  |  | RCC Super Structure | Retaining Wall RCC Works
8380 |  | Quality checked |  | 2024-10-17 | 2024-12-11 | Shear Walls | 100 | 100 |  | 2024-10-17 | 2024-10-17 | 2024-12-11 | 2024-12-11
8381 | T-14-Sub structure Shear Walls | Quality checked | Reinforcement | 2024-10-17 | 2024-12-04 | Reinforcement | 9.9 | 9.9 | MTon | 2024-10-17 | 2024-10-17 | 2024-12-04 | 2024-12-04
39523 |  | Complete |  | 2024-10-17 | 2024-10-28 | Core Wall L37-38 | 100 | 100 |  | 2024-10-17 | 2024-10-17 | 2024-10-28 | 2024-10-28
39524 | Tower A - Super Structure - Core Wall Low Rise L37-38 | Complete | Core Wall RCC Works | 2024-10-17 | 2024-10-17 | Scaffolding & platform | 100 | 100 |  | 2024-10-17 | 2024-10-17 | 2024-10-17 | 2024-10-17 | Tower A | Super Structure | L37 | RCC Super Structure | Core Wall RCC Works
40224 | Tower A - Super Structure - Finishes & MEP - L18 to L19 | Complete | Partition Wall-Blockwork | 2024-10-17 | 2024-10-22 | Staircase Area | 100 | 100 |  | 2024-10-17 | 2024-10-17 | 2024-10-22 | 2024-10-22 | Tower A | Super Structure | L18
40227 | Tower A - Super Structure - Finishes & MEP - L19 to L20 | Complete | Partition Wall-Blockwork | 2024-10-17 | 2024-12-10 | Partition Walls | 100 | 100 |  | 2024-10-17 | 2024-10-17 | 2024-12-10 | 2024-12-10 | Tower A | Super Structure | L19
47577 |  | Complete |  | 2024-10-17 | 2024-10-28 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2024-10-17 | 2024-10-17 | 2024-10-28 | 2024-10-28
47577 |  | Complete |  | 2024-10-17 | 2024-10-28 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2024-10-17 | 2024-10-17 | 2024-10-28 | 2024-10-28 |  |  |  | RCC Sub Structure | Raft RCC Works
47577 |  | Complete |  | 2024-10-17 | 2024-10-28 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2024-10-17 | 2024-10-17 | 2024-10-28 | 2024-10-28 |  |  |  | RCC Super Structure | Foundation RCC Works
39525 | Tower A - Super Structure - Core Wall Low Rise L37-38 | Complete | Core Wall RCC Works | 2024-10-18 | 2024-10-21 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-10-18 | 2024-10-18 | 2024-10-21 | 2024-10-21 | Tower A | Super Structure | L37 | RCC Super Structure | Core Wall RCC Works
44862 | Tower B - Sub Structure - B2 to B1 - Pour 5 | Complete | RCC Works - Slab | 2024-10-18 | 2024-10-23 | Slab & Staircase Reinf. | 100 | 100 |  | 2024-10-18 | 2024-10-18 | 2024-10-23 | 2024-10-23 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
48384 | Retail - Sub structure - B2 to B1 - P1 | Complete |  | 2024-10-18 | 2024-10-25 | Section 4_lift 1 | 100 | 100 |  | 2024-10-18 | 2024-10-18 | 2024-10-25 | 2024-10-25 | Retail | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
48384 | Retail - Sub structure - B2 to B1 - P1 | Complete |  | 2024-10-18 | 2024-10-25 | Section 4_lift 1 | 100 | 100 |  | 2024-10-18 | 2024-10-18 | 2024-10-25 | 2024-10-25 | Retail | Sub Structure | B2
8382 | T-14-Sub structure Shear Walls | Quality checked | Shuttering | 2024-10-19 | 2024-12-10 | Shuttering | 100 | 100 |  | 2024-10-19 | 2024-10-19 | 2024-12-10 | 2024-12-10
39526 | Tower A - Super Structure - Core Wall Low Rise L37-38 | Complete | Core Wall RCC Works | 2024-10-19 | 2024-10-22 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-10-19 | 2024-10-19 | 2024-10-22 | 2024-10-22 | Tower A | Super Structure | L37 | RCC Super Structure | Core Wall RCC Works
9977 | T-21-Sub structure Water proofing NTA | Started |  | 2024-10-21 | 2025-03-28 | Water Proofing Outside-NTA | 100 | 60 |  | 2024-10-21 | 2024-10-21 | 2025-06-01
10484 |  | Started |  | 2024-10-21 | 2025-04-26 | Retaining Wall | 100 | 38 |  | 2024-10-21 | 2024-10-21 | 2025-06-30
10485 | T-20-Sub structure Retaining Wall | Started | PCC | 2024-10-21 | 2025-03-26 | PCC | 100 | 30 | Units | 2024-10-21 | 2024-10-21 | 2025-05-29
39157 |  | Complete |  | 2024-10-21 | 2024-10-30 | Flooring | 100 | 100 |  | 2024-10-21 | 2024-10-21 | 2024-10-30 | 2024-10-30
39522 | Tower A - Super Structure - Core Wall Low Rise L36-37 | Complete | Core Wall RCC Works | 2024-10-21 | 2024-10-21 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-10-21 | 2024-10-21 | 2024-10-21 | 2024-10-21 | Tower A | Super Structure | L36 | RCC Super Structure | Core Wall RCC Works
39902 |  | Complete |  | 2024-10-21 | 2024-10-28 | L33-34 | 100 | 100 |  | 2024-10-21 | 2024-10-21 | 2024-10-28 | 2024-10-28
39902 |  | Complete |  | 2024-10-21 | 2024-10-28 | L33-34 | 100 | 100 |  | 2024-10-21 | 2024-10-21 | 2024-10-28 | 2024-10-28 |  |  |  | Finishes | Gypsum Plastering Works
39903 | Tower A - Super Structure - Core & Outer Slab L33-34 | Complete | RCC Works - Vertical | 2024-10-21 | 2024-10-26 | Outer Columns_TA | 100 | 100 |  | 2024-10-21 | 2024-10-21 | 2024-10-26 | 2024-10-26 | Tower A | Super Structure | L33 | RCC Sub Structure | RCC Works - Vertical
40269 |  | Started |  | 2024-10-21 | 2025-03-07 | L30-31 | 100 | 55 |  | 2024-10-21 | 2024-10-21 | 2025-10-04 |  |  |  |  | Finishes | Gypsum Plastering Works
40269 |  | Started |  | 2024-10-21 | 2025-03-07 | L30-31 | 100 | 55 |  | 2024-10-21 | 2024-10-21 | 2025-10-04
40270 | Tower A - Super Structure - Finishes & MEP - L30 to L31 | Complete | Partition Wall-Blockwork | 2024-10-21 | 2024-11-07 | De-shuttering & Area clearance | 100 | 100 |  | 2024-10-21 | 2024-10-21 | 2024-11-07 | 2024-11-07 | Tower A | Super Structure | L30
42350 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Apartment Area | Started | Cement Plastering in Wet Areas - MEP & Finishes | 2024-10-22 | 2024-10-22 | Cement Plastering in wet areas | 100 | 90 |  | 2024-10-22 | 2024-10-22 | 2025-09-13 |  | Tower A | Super Structure | L15
44795 | Tower B - Sub Structure - B3 to B2 - Pour 7 | Complete | RCC Works - Slab | 2024-10-22 | 2024-10-23 | Slab & Staircase Casting | 100 | 100 |  | 2024-10-22 | 2024-10-22 | 2024-10-23 | 2024-10-23 | Tower B | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
39527 | Tower A - Super Structure - Core Wall Low Rise L37-38 | Complete | Core Wall RCC Works | 2024-10-23 | 2024-10-26 | Casting | 100 | 100 |  | 2024-10-23 | 2024-10-23 | 2024-10-26 | 2024-10-26 | Tower A | Super Structure | L37 | RCC Super Structure | Core Wall RCC Works
39904 | Tower A - Super Structure - Core & Outer Slab L33-34 | Complete | RCC Works - Slab | 2024-10-23 | 2024-10-28 | Outer Slab_TA | 100 | 100 |  | 2024-10-23 | 2024-10-23 | 2024-10-28 | 2024-10-28 | Tower A | Super Structure | L33 | RCC Sub Structure | RCC Works - Slab
40491 | Tower A - Super Structure - Finishes & MEP - L17 to L18 | Complete | Gypsum Plastering Works | 2024-10-23 | 2024-11-27 | L17-18 | 100 | 100 | Units | 2024-10-23 | 2025-09-05 | 2024-11-27 | 2025-09-05 | Tower A | Super Structure | L17 | Finishes | Gypsum Plastering Works
40491 | Tower A - Super Structure - Finishes & MEP - L17 to L18 | Complete | Gypsum Plastering Works | 2024-10-23 | 2024-11-27 | L17-18 | 100 | 100 | Units | 2024-10-23 | 2025-09-05 | 2024-11-27 | 2025-09-05 | Tower A | Super Structure | L17
42398 |  | Started |  | 2024-10-23 | 2026-06-11 | L18-19 | 100 | 70 |  | 2024-10-23 | 2024-10-23 | 2026-06-09 |  |  |  |  | Finishes | Gypsum Plastering Works
42398 |  | Started |  | 2024-10-23 | 2026-06-11 | L18-19 | 100 | 70 |  | 2024-10-23 | 2024-10-23 | 2026-06-09
42399 |  | Started |  | 2024-10-23 | 2024-11-18 | MEP 1st Fixes | 100 | 74 |  | 2024-10-23 | 2024-10-23 | 2025-09-22
42400 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Apartment Area | Started | FPS 1st Fix - MEP & Finishes | 2024-10-23 | 2024-10-24 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 80 |  | 2024-10-23 | 2024-10-23 | 2025-09-12 |  | Tower A | Super Structure | L18 | MEP | FPS 1st Fix - MEP & Finishes
42401 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Apartment Area | Started | Electrical 1st Fix - MEP & Finishes | 2024-10-23 | 2024-10-23 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 90 |  | 2024-10-23 | 2024-10-23 | 2025-09-11 |  | Tower A | Super Structure | L18 | MEP | Electrical 1st Fixes
42402 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Apartment Area | Started | PHE 1st Fix - MEP & Finishes | 2024-10-23 | 2024-10-24 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 80 |  | 2024-10-23 | 2024-10-23 | 2025-09-12 |  | Tower A | Super Structure | L18
42403 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Apartment Area | Started | Wet Area Waterproofing - MEP & Finishes | 2024-10-23 | 2024-10-24 | Wet Area Waterproofing | 100 | 90 |  | 2024-10-23 | 2024-10-23 | 2025-09-12 |  | Tower A | Super Structure | L18
10486 | T-20-Sub structure Retaining Wall | Started | Reinforcement | 2024-10-24 | 2025-04-26 | Reinforcement | 4.55 | 4 | MT | 2024-10-24 | 2024-10-24 | 2025-06-30
44820 | Tower B - Sub Structure - B2 to B1 | Complete | Core Wall RCC Works | 2024-10-24 | 2024-11-02 | CW Fwk (3.5m lift) | 100 | 100 |  | 2024-10-24 | 2024-10-24 | 2024-11-02 | 2024-11-02 | Tower B | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
44843 |  | Complete |  | 2024-10-24 | 2024-12-04 | Pour 7_B2 to B1 | 100 | 100 |  | 2024-10-24 | 2024-10-24 | 2024-12-04 | 2024-12-04
44844 | Tower B - Sub Structure - B2 to B1 - Pour 7 | Complete | RCC Works - Vertical | 2024-10-24 | 2024-10-26 | Col/ Wall Reinf. | 100 | 100 |  | 2024-10-24 | 2024-10-24 | 2024-10-26 | 2024-10-26 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
44844 | Tower B - Sub Structure - B2 to B1 - Pour 7 | Complete | RCC Works - Vertical | 2024-10-24 | 2024-10-26 | Col/ Wall Reinf. | 100 | 100 |  | 2024-10-24 | 2024-10-24 | 2024-10-26 | 2024-10-26 | Tower B | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
44863 | Tower B - Sub Structure - B2 to B1 - Pour 5 | Complete | RCC Works - Slab | 2024-10-24 | 2024-10-25 | Slab & Staircase Casting | 100 | 100 |  | 2024-10-24 | 2024-10-24 | 2024-10-25 | 2024-10-25 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
47609 |  | Complete |  | 2024-10-24 | 2024-11-01 | Section 6_lift 2 | 100 | 100 |  | 2024-10-24 | 2024-10-24 | 2024-11-01 | 2024-11-01
47609 |  | Complete |  | 2024-10-24 | 2024-11-01 | Section 6_lift 2 | 100 | 100 |  | 2024-10-24 | 2024-10-24 | 2024-11-01 | 2024-11-01 |  |  |  | RCC Super Structure | Retaining Wall RCC Works
40228 | Tower A - Super Structure - Finishes & MEP - L19 to L20 | Complete | Partition Wall-Blockwork | 2024-10-25 | 2024-12-15 | Staircase Area | 100 | 100 |  | 2024-10-25 | 2024-10-25 | 2024-12-15 | 2024-12-15 | Tower A | Super Structure | L19
40231 | Tower A - Super Structure - Finishes & MEP - L20 to L21 | Complete | Partition Wall-Blockwork | 2024-10-25 | 2024-12-12 | Partition Walls | 100 | 100 |  | 2024-10-25 | 2024-10-25 | 2024-12-12 | 2024-12-12 | Tower A | Super Structure | L20
8383 | T-14-Sub structure Shear Walls | Quality checked | RCC | 2024-10-26 | 2024-12-11 | RCC | 208 | 208 | CUM | 2024-10-26 | 2024-10-26 | 2024-12-11 | 2024-12-11
8383 | T-14-Sub structure Shear Walls | Quality checked | RCC | 2024-10-26 | 2024-12-11 | RCC | 208 | 208 | CUM | 2024-10-26 | 2024-10-26 | 2024-12-11 | 2024-12-11
39180 |  | Complete |  | 2024-10-26 | 2024-11-04 | Foundation for Pumps & Chillers | 100 | 100 |  | 2024-10-26 | 2024-10-26 | 2024-11-04 | 2024-11-04
48401 | Retail - Sub structure - B2 to B1 - P1 | Complete |  | 2024-10-26 | 2025-01-30 | Slab_NTA | 100 | 100 |  | 2024-10-26 | 2024-10-26 | 2025-01-30 | 2025-01-30 | Retail | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
48401 | Retail - Sub structure - B2 to B1 - P1 | Complete |  | 2024-10-26 | 2025-01-30 | Slab_NTA | 100 | 100 |  | 2024-10-26 | 2024-10-26 | 2025-01-30 | 2025-01-30 | Retail | Sub Structure | B2
10487 | T-20-Sub structure Retaining Wall | Started | Shuttering | 2024-10-27 | 2025-04-12 | Shuttering | 570.4 | 15 | Sqm | 2024-10-27 | 2024-10-27 | 2025-06-15
39528 | Tower A - Super Structure - Core Wall Low Rise L37-38 | Complete | Core Wall RCC Works | 2024-10-28 | 2024-10-28 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-10-28 | 2024-10-28 | 2024-10-28 | 2024-10-28 | Tower A | Super Structure | L37 | RCC Super Structure | Core Wall RCC Works
44845 | Tower B - Sub Structure - B2 to B1 - Pour 7 | Complete | RCC Works - Vertical | 2024-10-28 | 2024-11-08 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-10-28 | 2024-10-28 | 2024-11-08 | 2024-11-08 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
44845 | Tower B - Sub Structure - B2 to B1 - Pour 7 | Complete | RCC Works - Vertical | 2024-10-28 | 2024-11-08 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-10-28 | 2024-10-28 | 2024-11-08 | 2024-11-08 | Tower B | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
39529 |  | Complete |  | 2024-10-29 | 2024-11-05 | Core Wall L38-39 | 100 | 100 |  | 2024-10-29 | 2024-10-29 | 2024-11-05 | 2024-11-05
39530 | Tower A - Super Structure - Core Wall Low Rise L38-39 | Complete | Core Wall RCC Works | 2024-10-29 | 2024-10-29 | Scaffolding & platform | 100 | 100 |  | 2024-10-29 | 2024-10-29 | 2024-10-29 | 2024-10-29 | Tower A | Super Structure | L38 | RCC Super Structure | Core Wall RCC Works
39905 |  | Complete |  | 2024-10-29 | 2024-11-06 | L34-35 | 100 | 100 |  | 2024-10-29 | 2024-10-29 | 2024-11-06 | 2024-11-06
39905 |  | Complete |  | 2024-10-29 | 2024-11-06 | L34-35 | 100 | 100 |  | 2024-10-29 | 2024-10-29 | 2024-11-06 | 2024-11-06 |  |  |  | Finishes | Gypsum Plastering Works
39906 | Tower A - Super Structure - Core & Outer Slab L34-35 | Complete | RCC Works - Vertical | 2024-10-29 | 2024-11-05 | Outer Columns_TA | 100 | 100 |  | 2024-10-29 | 2024-10-29 | 2024-11-05 | 2024-11-05 | Tower A | Super Structure | L34 | RCC Sub Structure | RCC Works - Vertical
40273 |  | Complete |  | 2024-10-29 | 2025-04-16 | L31-32 | 100 | 100 |  | 2024-10-29 | 2024-10-29 | 2025-04-16 | 2025-04-16
40273 |  | Complete |  | 2024-10-29 | 2025-04-16 | L31-32 | 100 | 100 |  | 2024-10-29 | 2024-10-29 | 2025-04-16 | 2025-04-16 |  |  |  | Finishes | Gypsum Plastering Works
40274 | Tower A - Super Structure - Finishes & MEP - L31 to L32 | Complete | Partition Wall-Blockwork | 2024-10-29 | 2024-11-15 | De-shuttering & Area clearance | 100 | 100 |  | 2024-10-29 | 2024-10-29 | 2024-11-15 | 2024-11-15 | Tower A | Super Structure | L31
44850 |  | Complete |  | 2024-10-29 | 2024-11-22 | Pour 8_B2 to B1 | 100 | 100 |  | 2024-10-29 | 2024-10-29 | 2024-11-22 | 2024-11-22
44852 | Tower B - Sub Structure - B2 to B1 - Pour 8 | Complete | RCC Works - Vertical | 2024-10-29 | 2024-11-09 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-10-29 | 2024-10-29 | 2024-11-09 | 2024-11-09 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
44852 | Tower B - Sub Structure - B2 to B1 - Pour 8 | Complete | RCC Works - Vertical | 2024-10-29 | 2024-11-09 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-10-29 | 2024-10-29 | 2024-11-09 | 2024-11-09 | Tower B | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
47573 |  | Complete |  | 2024-10-29 | 2024-11-06 | Fwk & Casting_NTA | 100 | 100 |  | 2024-10-29 | 2024-10-29 | 2024-11-06 | 2024-11-06
47573 |  | Complete |  | 2024-10-29 | 2024-11-06 | Fwk & Casting_NTA | 100 | 100 |  | 2024-10-29 | 2024-10-29 | 2024-11-06 | 2024-11-06 |  |  |  | RCC Sub Structure | Raft RCC Works
47573 |  | Complete |  | 2024-10-29 | 2024-11-06 | Fwk & Casting_NTA | 100 | 100 |  | 2024-10-29 | 2024-10-29 | 2024-11-06 | 2024-11-06 |  |  |  | RCC Super Structure | Foundation RCC Works
47578 |  | Complete |  | 2024-10-29 | 2024-11-04 | Fwk & Casting_NTA | 100 | 100 |  | 2024-10-29 | 2024-10-29 | 2024-11-04 | 2024-11-04
47578 |  | Complete |  | 2024-10-29 | 2024-11-04 | Fwk & Casting_NTA | 100 | 100 |  | 2024-10-29 | 2024-10-29 | 2024-11-04 | 2024-11-04 |  |  |  | RCC Sub Structure | Raft RCC Works
47578 |  | Complete |  | 2024-10-29 | 2024-11-04 | Fwk & Casting_NTA | 100 | 100 |  | 2024-10-29 | 2024-10-29 | 2024-11-04 | 2024-11-04 |  |  |  | RCC Super Structure | Foundation RCC Works
39531 | Tower A - Super Structure - Core Wall Low Rise L38-39 | Complete | Core Wall RCC Works | 2024-10-30 | 2024-11-02 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-10-30 | 2024-10-30 | 2024-11-02 | 2024-11-02 | Tower A | Super Structure | L38 | RCC Super Structure | Core Wall RCC Works
44851 | Tower B - Sub Structure - B2 to B1 - Pour 8 | Complete | RCC Works - Vertical | 2024-10-30 | 2024-11-06 | Col/ Wall Reinf. | 100 | 100 |  | 2024-10-30 | 2024-10-30 | 2024-11-06 | 2024-11-06 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
44851 | Tower B - Sub Structure - B2 to B1 - Pour 8 | Complete | RCC Works - Vertical | 2024-10-30 | 2024-11-06 | Col/ Wall Reinf. | 100 | 100 |  | 2024-10-30 | 2024-10-30 | 2024-11-06 | 2024-11-06 | Tower B | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
39532 | Tower A - Super Structure - Core Wall Low Rise L38-39 | Complete | Core Wall RCC Works | 2024-11-01 | 2024-11-04 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-11-01 | 2024-11-01 | 2024-11-04 | 2024-11-04 | Tower A | Super Structure | L38 | RCC Super Structure | Core Wall RCC Works
39907 | Tower A - Super Structure - Core & Outer Slab L34-35 | Complete | RCC Works - Slab | 2024-11-01 | 2024-11-06 | Outer Slab_TA | 100 | 100 |  | 2024-11-01 | 2024-11-01 | 2024-11-06 | 2024-11-06 | Tower A | Super Structure | L34 | RCC Sub Structure | RCC Works - Slab
40492 | Tower A - Super Structure - Finishes & MEP - L18 to L19 | Complete | Gypsum Plastering Works | 2024-11-01 | 2024-12-05 | L18-19 | 100 | 100 | Units | 2024-11-01 | 2025-08-04 | 2024-12-05 | 2025-09-08 | Tower A | Super Structure | L18 | Finishes | Gypsum Plastering Works
40492 | Tower A - Super Structure - Finishes & MEP - L18 to L19 | Complete | Gypsum Plastering Works | 2024-11-01 | 2024-12-05 | L18-19 | 100 | 100 | Units | 2024-11-01 | 2025-08-04 | 2024-12-05 | 2025-09-08 | Tower A | Super Structure | L18
44853 | Tower B - Sub Structure - B2 to B1 - Pour 8 | Complete | RCC Works - Vertical | 2024-11-01 | 2024-11-12 | Col/ Wall Casting | 100 | 100 |  | 2024-11-01 | 2024-11-01 | 2024-11-12 | 2024-11-12 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
44853 | Tower B - Sub Structure - B2 to B1 - Pour 8 | Complete | RCC Works - Vertical | 2024-11-01 | 2024-11-12 | Col/ Wall Casting | 100 | 100 |  | 2024-11-01 | 2024-11-01 | 2024-11-12 | 2024-11-12 | Tower B | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
39158 |  | Complete |  | 2024-11-02 | 2024-11-07 | Wall Plaster | 100 | 100 |  | 2024-11-02 | 2024-11-02 | 2024-11-07 | 2024-11-07
42386 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Apartment Area | Started | Cement Plastering in Wet Areas - MEP & Finishes | 2024-11-02 | 2024-11-09 | Cement Plastering in wet areas | 100 | 30 |  | 2024-11-02 | 2024-11-02 | 2025-09-22 |  | Tower A | Super Structure | L17
44829 |  | Complete |  | 2024-11-02 | 2024-11-26 | Pour 3_B2 to B1 | 100 | 100 |  | 2024-11-02 | 2024-11-02 | 2024-11-26 | 2024-11-26
44831 | Tower B - Sub Structure - B2 to B1 - Pour 3 | Complete | RCC Works - Vertical | 2024-11-02 | 2024-11-13 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-11-02 | 2024-11-02 | 2024-11-13 | 2024-11-13 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
44831 | Tower B - Sub Structure - B2 to B1 - Pour 3 | Complete | RCC Works - Vertical | 2024-11-02 | 2024-11-13 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-11-02 | 2024-11-02 | 2024-11-13 | 2024-11-13 | Tower B | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
9973 |  | Complete |  | 2024-11-03 | 2024-12-10 | Shear Walls | 100 | 100 |  | 2024-11-03 | 2024-11-03 | 2024-12-10 | 2024-12-10
9974 | T-21-Sub structure Shear Walls | Complete | Reinforcement | 2024-11-03 | 2024-11-30 | Reinforcement | 5.4 | 5.4 | MTon | 2024-11-03 | 2024-11-03 | 2024-11-30 | 2024-11-30
10488 | T-20-Sub structure Retaining Wall | Started | RCC | 2024-11-03 | 2025-04-11 | RCC | 57 | 15 | CUM | 2024-11-03 | 2024-11-03 | 2025-06-14
10488 | T-20-Sub structure Retaining Wall | Started | RCC | 2024-11-03 | 2025-04-11 | RCC | 57 | 15 | CUM | 2024-11-03 | 2024-11-03 | 2025-06-14
39533 | Tower A - Super Structure - Core Wall Low Rise L38-39 | Complete | Core Wall RCC Works | 2024-11-04 | 2024-11-04 | Casting | 100 | 100 |  | 2024-11-04 | 2024-11-04 | 2024-11-04 | 2024-11-04 | Tower A | Super Structure | L38 | RCC Super Structure | Core Wall RCC Works
40232 | Tower A - Super Structure - Finishes & MEP - L20 to L21 | Complete | Partition Wall-Blockwork | 2024-11-04 | 2024-12-30 | Staircase Area | 100 | 100 |  | 2024-11-04 | 2024-11-04 | 2024-12-30 | 2024-12-30 | Tower A | Super Structure | L20
40235 | Tower A - Super Structure - Finishes & MEP - L21 to L22 | Complete | Partition Wall-Blockwork | 2024-11-04 | 2024-12-17 | Partition Walls | 100 | 100 |  | 2024-11-04 | 2024-11-04 | 2024-12-17 | 2024-12-17 | Tower A | Super Structure | L21
44821 | Tower B - Sub Structure - B2 to B1 | Complete | Core Wall RCC Works | 2024-11-04 | 2024-11-06 | CW Casting | 100 | 100 |  | 2024-11-04 | 2024-11-04 | 2024-11-06 | 2024-11-06 | Tower B | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
44846 | Tower B - Sub Structure - B2 to B1 - Pour 7 | Complete | RCC Works - Vertical | 2024-11-04 | 2024-11-14 | Col/ Wall Casting | 100 | 100 |  | 2024-11-04 | 2024-11-04 | 2024-11-14 | 2024-11-14 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
44846 | Tower B - Sub Structure - B2 to B1 - Pour 7 | Complete | RCC Works - Vertical | 2024-11-04 | 2024-11-14 | Col/ Wall Casting | 100 | 100 |  | 2024-11-04 | 2024-11-04 | 2024-11-14 | 2024-11-14 | Tower B | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
44854 | Tower B - Sub Structure - B2 to B1 - Pour 8 | Complete | RCC Works - Slab | 2024-11-04 | 2024-11-16 | Slab & Staircase Fwk. | 100 | 100 |  | 2024-11-04 | 2024-11-04 | 2024-11-16 | 2024-11-16 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
39181 |  | Complete |  | 2024-11-05 | 2024-11-12 | Flooring | 100 | 100 |  | 2024-11-05 | 2024-11-05 | 2024-11-12 | 2024-11-12
39534 | Tower A - Super Structure - Core Wall Low Rise L38-39 | Complete | Core Wall RCC Works | 2024-11-05 | 2024-11-05 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-11-05 | 2024-11-05 | 2024-11-05 | 2024-11-05 | Tower A | Super Structure | L38 | RCC Super Structure | Core Wall RCC Works
42362 |  | Started |  | 2024-11-05 | 2026-06-11 | L16-17 | 100 | 70 |  | 2024-11-05 | 2024-11-05 | 2026-06-09 |  |  |  |  | Finishes | Gypsum Plastering Works
42362 |  | Started |  | 2024-11-05 | 2026-06-11 | L16-17 | 100 | 70 |  | 2024-11-05 | 2024-11-05 | 2026-06-09
42363 |  | Started |  | 2024-11-05 | 2024-11-29 | MEP 1st Fixes | 100 | 74 |  | 2024-11-05 | 2024-11-05 | 2025-09-22
42364 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Apartment Area | Started | FPS 1st Fix - MEP & Finishes | 2024-11-05 | 2024-11-06 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 80 |  | 2024-11-05 | 2024-11-05 | 2025-09-12 |  | Tower A | Super Structure | L16 | MEP | FPS 1st Fix - MEP & Finishes
42365 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Apartment Area | Started | Electrical 1st Fix - MEP & Finishes | 2024-11-05 | 2024-11-05 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 90 |  | 2024-11-05 | 2024-11-05 | 2025-09-11 |  | Tower A | Super Structure | L16 | MEP | Electrical 1st Fixes
42366 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Apartment Area | Started | PHE 1st Fix - MEP & Finishes | 2024-11-05 | 2024-11-06 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 80 |  | 2024-11-05 | 2024-11-05 | 2025-09-12 |  | Tower A | Super Structure | L16
42367 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Apartment Area | Started | Wet Area Waterproofing - MEP & Finishes | 2024-11-05 | 2024-11-06 | Wet Area Waterproofing | 100 | 90 |  | 2024-11-05 | 2024-11-05 | 2025-09-12 |  | Tower A | Super Structure | L16
44832 | Tower B - Sub Structure - B2 to B1 - Pour 3 | Complete | RCC Works - Vertical | 2024-11-05 | 2024-11-15 | Col/ Wall Casting | 100 | 100 |  | 2024-11-05 | 2024-11-05 | 2024-11-15 | 2024-11-15 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
44832 | Tower B - Sub Structure - B2 to B1 - Pour 3 | Complete | RCC Works - Vertical | 2024-11-05 | 2024-11-15 | Col/ Wall Casting | 100 | 100 |  | 2024-11-05 | 2024-11-05 | 2024-11-15 | 2024-11-15 | Tower B | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
44836 |  | Complete |  | 2024-11-05 | 2024-11-28 | Pour 1B & 6_B2 to B1 | 100 | 100 |  | 2024-11-05 | 2024-11-05 | 2024-11-28 | 2024-11-28
44838 | Tower B - Sub Structure - B2 to B1 - Pour 1B & 6 | Complete | RCC Works - Vertical | 2024-11-05 | 2024-11-15 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-11-05 | 2024-11-05 | 2024-11-15 | 2024-11-15 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
44838 | Tower B - Sub Structure - B2 to B1 - Pour 1B & 6 | Complete | RCC Works - Vertical | 2024-11-05 | 2024-11-15 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-11-05 | 2024-11-05 | 2024-11-15 | 2024-11-15 | Tower B | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
44871 |  | Complete |  | 2024-11-05 | 2025-01-28 | B1 to GF | 100 | 100 |  | 2024-11-05 | 2024-11-05 | 2025-01-28 | 2025-01-28
44871 |  | Complete |  | 2024-11-05 | 2025-01-28 | B1 to GF | 100 | 100 |  | 2024-11-05 | 2024-11-05 | 2025-01-28 | 2025-01-28
44871 |  | Complete |  | 2024-11-05 | 2025-01-28 | B1 to GF | 100 | 100 |  | 2024-11-05 | 2024-11-05 | 2025-01-28 | 2025-01-28
44899 |  | Complete |  | 2024-11-05 | 2024-12-28 | Pour 1B & 6_B1 to GF | 100 | 100 |  | 2024-11-05 | 2024-11-05 | 2024-12-28 | 2024-12-28
44900 | Tower B - Sub Structure - B1 to GF - Pour 1B & 6 | Complete | RCC Works - Vertical | 2024-11-05 | 2024-11-15 | Col/ Wall Reinf. | 100 | 100 |  | 2024-11-05 | 2024-11-05 | 2024-11-15 | 2024-11-15 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44900 | Tower B - Sub Structure - B1 to GF - Pour 1B & 6 | Complete | RCC Works - Vertical | 2024-11-05 | 2024-11-15 | Col/ Wall Reinf. | 100 | 100 |  | 2024-11-05 | 2024-11-05 | 2024-11-15 | 2024-11-15 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44929 |  | Complete |  | 2024-11-05 | 2024-12-19 | Pour 5_B1 to GF | 100 | 100 |  | 2024-11-05 | 2024-11-05 | 2024-12-19 | 2024-12-19
44930 | Tower B - Sub Structure - B1 to GF - Pour 5 | Complete | RCC Works - Vertical | 2024-11-05 | 2024-11-12 | Col/ Wall Reinf. | 100 | 100 |  | 2024-11-05 | 2024-11-05 | 2024-11-12 | 2024-11-12 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44930 | Tower B - Sub Structure - B1 to GF - Pour 5 | Complete | RCC Works - Vertical | 2024-11-05 | 2024-11-12 | Col/ Wall Reinf. | 100 | 100 |  | 2024-11-05 | 2024-11-05 | 2024-11-12 | 2024-11-12 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44931 | Tower B - Sub Structure - B1 to GF - Pour 5 | Complete | RCC Works - Vertical | 2024-11-05 | 2024-11-15 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-11-05 | 2024-11-05 | 2024-11-15 | 2024-11-15 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44931 | Tower B - Sub Structure - B1 to GF - Pour 5 | Complete | RCC Works - Vertical | 2024-11-05 | 2024-11-15 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-11-05 | 2024-11-05 | 2024-11-15 | 2024-11-15 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
47624 |  | Complete |  | 2024-11-05 | 2024-12-03 | Pour 10 (PB-K to PA-B / RT-08 to PB-06) | 100 | 100 |  | 2024-11-05 | 2024-11-05 | 2024-12-03 | 2024-12-03
47625 |  | Complete |  | 2024-11-05 | 2024-11-21 | Columns/ Walls_NTA | 100 | 100 |  | 2024-11-05 | 2024-11-05 | 2024-11-21 | 2024-11-21
47625 |  | Complete |  | 2024-11-05 | 2024-11-21 | Columns/ Walls_NTA | 100 | 100 |  | 2024-11-05 | 2024-11-05 | 2024-11-21 | 2024-11-21 |  |  |  | RCC Sub Structure | RCC Works - Vertical
9975 | T-21-Sub structure Shear Walls | Complete | Shuttering | 2024-11-06 | 2024-12-09 | Shuttering | 100 | 100 |  | 2024-11-06 | 2024-11-06 | 2024-12-09 | 2024-12-09
39535 |  | Complete |  | 2024-11-06 | 2024-11-15 | Core Wall L39-40 | 100 | 100 |  | 2024-11-06 | 2024-11-06 | 2024-11-15 | 2024-11-15
39536 | Tower A - Super Structure - Core Wall Low Rise L39-40 | Complete | Core Wall RCC Works | 2024-11-06 | 2024-11-06 | Scaffolding & platform | 100 | 100 |  | 2024-11-06 | 2024-11-06 | 2024-11-06 | 2024-11-06 | Tower A | Super Structure | L39 | RCC Super Structure | Core Wall RCC Works
39537 | Tower A - Super Structure - Core Wall Low Rise L39-40 | Complete | Core Wall RCC Works | 2024-11-07 | 2024-11-09 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-11-07 | 2024-11-07 | 2024-11-09 | 2024-11-09 | Tower A | Super Structure | L39 | RCC Super Structure | Core Wall RCC Works
39908 |  | Complete |  | 2024-11-07 | 2024-11-17 | L35-36 | 100 | 100 |  | 2024-11-07 | 2024-11-07 | 2024-11-17 | 2024-11-17
39908 |  | Complete |  | 2024-11-07 | 2024-11-17 | L35-36 | 100 | 100 |  | 2024-11-07 | 2024-11-07 | 2024-11-17 | 2024-11-17 |  |  |  | Finishes | Gypsum Plastering Works
39909 | Tower A - Super Structure - Core & Outer Slab L35-36 | Complete | RCC Works - Vertical | 2024-11-07 | 2024-11-15 | Outer Columns_TA | 100 | 100 |  | 2024-11-07 | 2024-11-07 | 2024-11-15 | 2024-11-15 | Tower A | Super Structure | L35 | RCC Sub Structure | RCC Works - Vertical
40277 |  | Complete |  | 2024-11-07 | 2025-04-24 | L32-33 | 100 | 100 |  | 2024-11-07 | 2024-11-07 | 2025-04-24 | 2025-04-24
40277 |  | Complete |  | 2024-11-07 | 2025-04-24 | L32-33 | 100 | 100 |  | 2024-11-07 | 2024-11-07 | 2025-04-24 | 2025-04-24 |  |  |  | Finishes | Gypsum Plastering Works
40278 | Tower A - Super Structure - Finishes & MEP - L32 to L33 | Complete | Partition Wall-Blockwork | 2024-11-07 | 2024-11-23 | De-shuttering & Area clearance | 100 | 100 |  | 2024-11-07 | 2024-11-07 | 2024-11-23 | 2024-11-23 | Tower A | Super Structure | L32
44822 |  | Complete |  | 2024-11-07 | 2024-11-30 | Pour 1A & 2_B2 to B1 | 100 | 100 |  | 2024-11-07 | 2024-11-07 | 2024-11-30 | 2024-11-30
44823 | Tower B - Sub Structure - B2 to B1 - Pour 1A & 2 | Complete | RCC Works - Vertical | 2024-11-07 | 2024-11-14 | Col/ Wall Reinf. | 100 | 100 |  | 2024-11-07 | 2024-11-07 | 2024-11-14 | 2024-11-14 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
44823 | Tower B - Sub Structure - B2 to B1 - Pour 1A & 2 | Complete | RCC Works - Vertical | 2024-11-07 | 2024-11-14 | Col/ Wall Reinf. | 100 | 100 |  | 2024-11-07 | 2024-11-07 | 2024-11-14 | 2024-11-14 | Tower B | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
44824 | Tower B - Sub Structure - B2 to B1 - Pour 1A & 2 | Complete | RCC Works - Vertical | 2024-11-07 | 2024-11-18 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-11-07 | 2024-11-07 | 2024-11-18 | 2024-11-18 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
44824 | Tower B - Sub Structure - B2 to B1 - Pour 1A & 2 | Complete | RCC Works - Vertical | 2024-11-07 | 2024-11-18 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-11-07 | 2024-11-07 | 2024-11-18 | 2024-11-18 | Tower B | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
44830 | Tower B - Sub Structure - B2 to B1 - Pour 3 | Complete | RCC Works - Vertical | 2024-11-07 | 2024-11-09 | Col/ Wall Reinf. | 100 | 100 |  | 2024-11-07 | 2024-11-07 | 2024-11-09 | 2024-11-09 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
44830 | Tower B - Sub Structure - B2 to B1 - Pour 3 | Complete | RCC Works - Vertical | 2024-11-07 | 2024-11-09 | Col/ Wall Reinf. | 100 | 100 |  | 2024-11-07 | 2024-11-07 | 2024-11-09 | 2024-11-09 | Tower B | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
44833 | Tower B - Sub Structure - B2 to B1 - Pour 3 | Complete | RCC Works - Slab | 2024-11-07 | 2024-11-20 | Slab & Staircase Fwk. | 100 | 100 |  | 2024-11-07 | 2024-11-07 | 2024-11-20 | 2024-11-20 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
44837 | Tower B - Sub Structure - B2 to B1 - Pour 1B & 6 | Complete | RCC Works - Vertical | 2024-11-07 | 2024-11-12 | Col/ Wall Reinf. | 100 | 100 |  | 2024-11-07 | 2024-11-07 | 2024-11-12 | 2024-11-12 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
44837 | Tower B - Sub Structure - B2 to B1 - Pour 1B & 6 | Complete | RCC Works - Vertical | 2024-11-07 | 2024-11-12 | Col/ Wall Reinf. | 100 | 100 |  | 2024-11-07 | 2024-11-07 | 2024-11-12 | 2024-11-12 | Tower B | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
44839 | Tower B - Sub Structure - B2 to B1 - Pour 1B & 6 | Complete | RCC Works - Vertical | 2024-11-07 | 2024-11-18 | Col/ Wall Casting | 100 | 100 |  | 2024-11-07 | 2024-11-07 | 2024-11-18 | 2024-11-18 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
44839 | Tower B - Sub Structure - B2 to B1 - Pour 1B & 6 | Complete | RCC Works - Vertical | 2024-11-07 | 2024-11-18 | Col/ Wall Casting | 100 | 100 |  | 2024-11-07 | 2024-11-07 | 2024-11-18 | 2024-11-18 | Tower B | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
44932 | Tower B - Sub Structure - B1 to GF - Pour 5 | Complete | RCC Works - Vertical | 2024-11-07 | 2024-11-18 | Col/ Wall Casting | 100 | 100 |  | 2024-11-07 | 2024-11-07 | 2024-11-18 | 2024-11-18 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44932 | Tower B - Sub Structure - B1 to GF - Pour 5 | Complete | RCC Works - Vertical | 2024-11-07 | 2024-11-18 | Col/ Wall Casting | 100 | 100 |  | 2024-11-07 | 2024-11-07 | 2024-11-18 | 2024-11-18 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
47621 |  | Complete |  | 2024-11-07 | 2025-12-10 | Pour 9 (grid PB-06 to PB-D) | 100 | 100 |  | 2024-11-07 | 2024-11-07 | 2025-12-10 | 2025-12-10
47622 |  | Complete |  | 2024-11-07 | 2024-11-29 | Columns/ Walls_NTA | 100 | 100 |  | 2024-11-07 | 2024-11-07 | 2024-11-29 | 2024-11-29
47622 |  | Complete |  | 2024-11-07 | 2024-11-29 | Columns/ Walls_NTA | 100 | 100 |  | 2024-11-07 | 2024-11-07 | 2024-11-29 | 2024-11-29 |  |  |  | RCC Sub Structure | RCC Works - Vertical
8929 |  | Started |  | 2024-11-08 | 2025-03-28 | Columns | 100 | 14 |  | 2024-11-08 | 2024-11-08 | 2025-05-31
8930 | T-15-Sub structure Columns | Started | Reinforcement | 2024-11-08 | 2025-03-28 | Reinforcement | 3 | 1 | MTon | 2024-11-08 | 2024-11-08 | 2025-05-31
8933 |  | Complete |  | 2024-11-08 | 2025-01-10 | Shear Walls | 100 | 100 |  | 2024-11-08 | 2024-11-08 | 2025-01-10 | 2025-01-10
8934 | T-15-Sub structure Shear Walls | Complete | Reinforcement | 2024-11-08 | 2024-12-11 | Reinforcement | 0.18 | 0.18 |  | 2024-11-08 | 2024-11-08 | 2024-12-11 | 2024-12-11
9449 |  | Complete |  | 2024-11-08 | 2025-03-28 | Columns | 100 | 100 |  | 2024-11-08 | 2024-11-08 | 2025-05-31 | 2025-06-02
9450 | T-16-Sub structure Columns | Complete | Reinforcement | 2024-11-08 | 2025-03-28 | Reinforcement | 3 | 3 | MTon | 2024-11-08 | 2024-11-08 | 2025-05-31 | 2025-05-30
9453 |  | Complete |  | 2024-11-08 | 2026-02-22 | Shear Walls | 100 | 100 |  | 2024-11-08 | 2024-11-08 | 2025-03-13 | 2025-03-14
9454 | T-16-Sub structure Shear Walls | Complete | Reinforcement | 2024-11-08 | 2026-02-22 | Reinforcement | 18 | 18 | MTon | 2024-11-08 | 2024-11-08 | 2025-03-01 | 2025-03-02
9995 |  | Started |  | 2024-11-08 | 2026-11-21 | Superstructure | 100 | 4 |  | 2024-11-08 | 2024-11-08 | 2026-10-19
9996 |  | Complete |  | 2024-11-08 | 2024-11-11 | Reciept of Aluminium Materials | 100 | 100 |  | 2024-11-08 | 2024-11-08 | 2024-11-11 | 2024-11-11
10489 |  | Started |  | 2024-11-08 | 2025-03-28 | Columns | 100 | 25 |  | 2024-11-08 | 2024-11-08 | 2025-05-31
10490 | T-20-Sub structure Columns | Started | Reinforcement | 2024-11-08 | 2025-03-28 | Reinforcement | 3 | 2 | MTon | 2024-11-08 | 2024-11-08 | 2025-05-31
11516 |  | Started |  | 2024-11-08 | 2027-03-18 | Tower 18 | 100 | 34 |  | 2024-11-08 | 2024-11-08 | 2026-12-19
11517 |  | Started |  | 2024-11-08 | 2025-08-01 | Sub Structure Up to Podium | 100 | 66 |  | 2024-11-08 | 2024-11-08 | 2025-09-05
11518 |  | Started |  | 2024-11-08 | 2025-04-08 | Footings | 100 | 76 |  | 2024-11-08 | 2024-11-08 | 2025-06-12
11519 |  | Complete |  | 2024-11-08 | 2025-04-03 | Isolated & Combined Footings | 100 | 100 |  | 2024-11-08 | 2024-11-08 | 2025-04-03 | 2025-02-15
11520 | T-18-Sub structure Footings | Quality checked | PCC | 2024-11-08 | 2025-03-19 | PCC | 98 | 98 | CUM | 2024-11-08 | 2024-11-08 | 2025-03-19 | 2025-02-12
39159 |  | Complete |  | 2024-11-08 | 2024-11-13 | Painting Woks | 100 | 100 |  | 2024-11-08 | 2024-11-08 | 2024-11-13 | 2024-11-13 |  |  |  | Finishes | Painting Works
39538 | Tower A - Super Structure - Core Wall Low Rise L39-40 | Complete | Core Wall RCC Works | 2024-11-08 | 2024-11-11 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-11-08 | 2024-11-08 | 2024-11-11 | 2024-11-11 | Tower A | Super Structure | L39 | RCC Super Structure | Core Wall RCC Works
48135 | Retail - Foundation P3 | Complete |  | 2024-11-08 | 2024-11-11 | Dressing & PCC | 100 | 100 |  | 2024-11-08 | 2024-11-08 | 2024-11-11 | 2024-11-11 | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48135 | Retail - Foundation P3 | Complete |  | 2024-11-08 | 2024-11-11 | Dressing & PCC | 100 | 100 |  | 2024-11-08 | 2024-11-08 | 2024-11-11 | 2024-11-11 | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48135 | Retail - Foundation P3 | Complete |  | 2024-11-08 | 2024-11-11 | Dressing & PCC | 100 | 100 |  | 2024-11-08 | 2024-11-08 | 2024-11-11 | 2024-11-11 | Retail | Foundation
8402 |  | Started |  | 2024-11-09 | 2025-12-11 | Superstructure | 100 | 72 |  | 2024-11-09 | 2024-11-09 | 2025-12-13
8403 |  | Quality checked |  | 2024-11-09 | 2024-11-23 | Reciept of Aluminium Materials | 100 | 100 |  | 2024-11-09 | 2024-11-09 | 2024-11-23 | 2024-11-23
39910 | Tower A - Super Structure - Core & Outer Slab L35-36 | Complete | RCC Works - Slab | 2024-11-09 | 2024-11-17 | Outer Slab_TA | 100 | 100 |  | 2024-11-09 | 2024-11-09 | 2024-11-17 | 2024-11-17 | Tower A | Super Structure | L35 | RCC Sub Structure | RCC Works - Slab
44825 | Tower B - Sub Structure - B2 to B1 - Pour 1A & 2 | Complete | RCC Works - Vertical | 2024-11-09 | 2024-11-20 | Col/ Wall Casting | 100 | 100 |  | 2024-11-09 | 2024-11-09 | 2024-11-20 | 2024-11-20 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
44825 | Tower B - Sub Structure - B2 to B1 - Pour 1A & 2 | Complete | RCC Works - Vertical | 2024-11-09 | 2024-11-20 | Col/ Wall Casting | 100 | 100 |  | 2024-11-09 | 2024-11-09 | 2024-11-20 | 2024-11-20 | Tower B | Sub Structure | B2 | RCC Super Structure | Core Wall RCC Works
44840 | Tower B - Sub Structure - B2 to B1 - Pour 1B & 6 | Complete | RCC Works - Slab | 2024-11-09 | 2024-11-22 | Slab & Staircase Fwk. | 100 | 100 |  | 2024-11-09 | 2024-11-09 | 2024-11-22 | 2024-11-22 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
44847 | Tower B - Sub Structure - B2 to B1 - Pour 7 | Complete | RCC Works - Slab | 2024-11-09 | 2024-11-22 | Slab & Staircase Fwk. | 100 | 100 |  | 2024-11-09 | 2024-11-09 | 2024-11-22 | 2024-11-22 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
10491 | T-20-Sub structure Columns | Started | Shuttering | 2024-11-10 | 2025-03-28 | Shuttering | 319 | 2 | Sqm | 2024-11-10 | 2024-11-10 | 2025-05-31
9976 | T-21-Sub structure Shear Walls | Complete | RCC | 2024-11-11 | 2024-12-10 | RCC | 208 | 208 | CUM | 2024-11-11 | 2024-11-11 | 2024-12-10 | 2024-12-10
9976 | T-21-Sub structure Shear Walls | Complete | RCC | 2024-11-11 | 2024-12-10 | RCC | 208 | 208 | CUM | 2024-11-11 | 2024-11-11 | 2024-12-10 | 2024-12-10
42404 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Apartment Area | Started | Cement Plastering in Wet Areas - MEP & Finishes | 2024-11-11 | 2024-11-18 | Cement Plastering in wet areas | 100 | 30 |  | 2024-11-11 | 2024-11-11 | 2025-09-22 |  | Tower A | Super Structure | L18
44901 | Tower B - Sub Structure - B1 to GF - Pour 1B & 6 | Complete | RCC Works - Vertical | 2024-11-11 | 2024-11-21 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-11-11 | 2024-11-11 | 2024-11-21 | 2024-11-21 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44901 | Tower B - Sub Structure - B1 to GF - Pour 1B & 6 | Complete | RCC Works - Vertical | 2024-11-11 | 2024-11-21 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-11-11 | 2024-11-11 | 2024-11-21 | 2024-11-21 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
11521 | T-18-Sub structure Footings | Quality checked | Reinforcement | 2024-11-12 | 2025-04-02 | Reinforcement | 71 | 71 | MT | 2024-11-12 | 2024-11-12 | 2025-04-03 | 2025-02-14
39539 | Tower A - Super Structure - Core Wall Low Rise L39-40 | Complete | Core Wall RCC Works | 2024-11-12 | 2024-11-14 | Casting | 100 | 100 |  | 2024-11-12 | 2024-11-12 | 2024-11-14 | 2024-11-14 | Tower A | Super Structure | L39 | RCC Super Structure | Core Wall RCC Works
40236 | Tower A - Super Structure - Finishes & MEP - L21 to L22 | Complete | Partition Wall-Blockwork | 2024-11-12 | 2024-12-19 | Staircase Area | 100 | 100 |  | 2024-11-12 | 2024-11-12 | 2024-12-19 | 2024-12-19 | Tower A | Super Structure | L21
44826 | Tower B - Sub Structure - B2 to B1 - Pour 1A & 2 | Complete | RCC Works - Slab | 2024-11-12 | 2024-11-25 | Slab & Staircase Fwk. | 100 | 100 |  | 2024-11-12 | 2024-11-12 | 2024-11-25 | 2024-11-25 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
48136 | Retail - Foundation P3 | Complete |  | 2024-11-12 | 2024-11-14 | Liner Wall | 100 | 100 |  | 2024-11-12 | 2024-11-12 | 2024-11-14 | 2024-11-14 | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48136 | Retail - Foundation P3 | Complete |  | 2024-11-12 | 2024-11-14 | Liner Wall | 100 | 100 |  | 2024-11-12 | 2024-11-12 | 2024-11-14 | 2024-11-14 | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48136 | Retail - Foundation P3 | Complete |  | 2024-11-12 | 2024-11-14 | Liner Wall | 100 | 100 |  | 2024-11-12 | 2024-11-12 | 2024-11-14 | 2024-11-14 | Retail | Foundation
39182 |  | Complete |  | 2024-11-13 | 2024-11-14 | Wall Plaster | 100 | 100 |  | 2024-11-13 | 2024-11-13 | 2024-11-14 | 2024-11-14
40490 | Tower A - Super Structure - Finishes & MEP - L16 to L17 | Complete | Gypsum Plastering Works | 2024-11-13 | 2024-12-17 | L16-17 | 100 | 100 | Units | 2024-11-13 | 2025-05-30 | 2024-12-17 | 2025-09-01 | Tower A | Super Structure | L16 | Finishes | Gypsum Plastering Works
40490 | Tower A - Super Structure - Finishes & MEP - L16 to L17 | Complete | Gypsum Plastering Works | 2024-11-13 | 2024-12-17 | L16-17 | 100 | 100 | Units | 2024-11-13 | 2025-05-30 | 2024-12-17 | 2025-09-01 | Tower A | Super Structure | L16
44902 | Tower B - Sub Structure - B1 to GF - Pour 1B & 6 | Complete | RCC Works - Vertical | 2024-11-13 | 2024-11-23 | Col/ Wall Casting | 100 | 100 |  | 2024-11-13 | 2024-11-13 | 2024-11-23 | 2024-11-23 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44902 | Tower B - Sub Structure - B1 to GF - Pour 1B & 6 | Complete | RCC Works - Vertical | 2024-11-13 | 2024-11-23 | Col/ Wall Casting | 100 | 100 |  | 2024-11-13 | 2024-11-13 | 2024-11-23 | 2024-11-23 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
47633 |  | Started |  | 2024-11-14 | 2026-06-01 | B2 to B1 | 100 | 61 |  | 2024-11-14 | 2024-11-14 | 2026-12-28
47633 |  | Started |  | 2024-11-14 | 2026-06-01 | B2 to B1 | 100 | 61 |  | 2024-11-14 | 2024-11-14 | 2026-12-28
47633 |  | Started |  | 2024-11-14 | 2026-06-01 | B2 to B1 | 100 | 61 |  | 2024-11-14 | 2024-11-14 | 2026-12-28
47634 |  | Started |  | 2024-11-14 | 2026-05-26 | Retaining Wall_lift 1 | 100 | 10 |  | 2024-11-14 | 2024-11-14 | 2026-12-28 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47634 |  | Started |  | 2024-11-14 | 2026-05-26 | Retaining Wall_lift 1 | 100 | 10 |  | 2024-11-14 | 2024-11-14 | 2026-12-28
47635 |  | Complete |  | 2024-11-14 | 2024-11-14 | Section 1_lift 1 | 100 | 100 |  | 2024-11-14 | 2024-11-14 | 2024-11-14 | 2024-11-14
47635 |  | Complete |  | 2024-11-14 | 2024-11-14 | Section 1_lift 1 | 100 | 100 |  | 2024-11-14 | 2024-11-14 | 2024-11-14 | 2024-11-14 |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47636 |  | Complete |  | 2024-11-14 | 2024-11-14 | Section 2_lift 1 | 100 | 100 |  | 2024-11-14 | 2024-11-14 | 2024-11-14 | 2024-11-14
47636 |  | Complete |  | 2024-11-14 | 2024-11-14 | Section 2_lift 1 | 100 | 100 |  | 2024-11-14 | 2024-11-14 | 2024-11-14 | 2024-11-14 |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47637 |  | Complete |  | 2024-11-14 | 2024-11-14 | Section 3_lift 1 | 100 | 100 |  | 2024-11-14 | 2024-11-14 | 2024-11-14 | 2024-11-14
47637 |  | Complete |  | 2024-11-14 | 2024-11-14 | Section 3_lift 1 | 100 | 100 |  | 2024-11-14 | 2024-11-14 | 2024-11-14 | 2024-11-14 |  |  |  | RCC Super Structure | Retaining Wall RCC Works
48265 |  | Started |  | 2024-11-14 | 2025-06-17 | B1 to GF | 100 | 43 |  | 2024-11-14 | 2024-11-14 | 2025-10-31
48265 |  | Started |  | 2024-11-14 | 2025-06-17 | B1 to GF | 100 | 43 |  | 2024-11-14 | 2024-11-14 | 2025-10-31
48265 |  | Started |  | 2024-11-14 | 2025-06-17 | B1 to GF | 100 | 43 |  | 2024-11-14 | 2024-11-14 | 2025-10-31
48267 |  | Started |  | 2024-11-14 | 2025-05-09 | Retaining Wall_lift 1 (Grid PA-A onwards) | 100 | 49 |  | 2024-11-14 | 2024-11-14 | 2025-10-22
48268 |  | Complete |  | 2024-11-14 | 2024-12-04 | Pour RT-1 | 100 | 100 |  | 2024-11-14 | 2024-11-14 | 2024-12-04 | 2024-12-04
48269 | Retail - Sub structure - B1 to GF - P1 | Complete |  | 2024-11-14 | 2024-11-21 | Section 1_lift 1 | 100 | 100 |  | 2024-11-14 | 2024-11-14 | 2024-11-21 | 2024-11-21 | Retail | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
48269 | Retail - Sub structure - B1 to GF - P1 | Complete |  | 2024-11-14 | 2024-11-21 | Section 1_lift 1 | 100 | 100 |  | 2024-11-14 | 2024-11-14 | 2024-11-21 | 2024-11-21 | Retail | Sub Structure | B1
8389 |  | Started |  | 2024-11-15 | 2025-03-22 | Basement Roof/Podium Structure Works | 100 | 16 |  | 2024-11-15 | 2024-11-15 | 2025-05-26
8390 |  | Quality checked |  | 2024-11-15 | 2024-12-29 | Part-1 - TA | 100 | 100 |  | 2024-11-15 | 2024-11-15 | 2024-12-29 | 2024-12-29
8391 | T-14-Sub structure Basement Part 1 TA | Quality checked | Staging | 2024-11-15 | 2024-12-21 | Staging | 100 | 100 |  | 2024-11-15 | 2024-11-15 | 2024-12-21 | 2024-12-21
9978 |  | Started | Backfilling | 2024-11-15 | 2025-04-30 | Backfilling | 100 | 2 |  | 2024-11-15 | 2024-11-15 | 2025-07-03
39540 | Tower A - Super Structure - Core Wall Low Rise L39-40 | Complete | Core Wall RCC Works | 2024-11-15 | 2024-11-15 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-11-15 | 2024-11-15 | 2024-11-15 | 2024-11-15 | Tower A | Super Structure | L39 | RCC Super Structure | Core Wall RCC Works
40281 |  | Complete |  | 2024-11-15 | 2025-05-03 | L33-34 | 100 | 100 |  | 2024-11-15 | 2024-11-15 | 2025-05-03 | 2025-05-22
40281 |  | Complete |  | 2024-11-15 | 2025-05-03 | L33-34 | 100 | 100 |  | 2024-11-15 | 2024-11-15 | 2025-05-03 | 2025-05-22 |  |  |  | Finishes | Gypsum Plastering Works
40282 | Tower A - Super Structure - Finishes & MEP - L33 to L34 | Complete | Partition Wall-Blockwork | 2024-11-15 | 2024-12-02 | De-shuttering & Area clearance | 100 | 100 |  | 2024-11-15 | 2024-11-15 | 2024-12-02 | 2024-12-02 | Tower A | Super Structure | L33
48137 | Retail - Foundation P3 | Complete |  | 2024-11-15 | 2024-11-20 | Waterproofing Horizontal | 100 | 100 |  | 2024-11-15 | 2024-11-15 | 2024-11-20 | 2024-11-20 | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48137 | Retail - Foundation P3 | Complete |  | 2024-11-15 | 2024-11-20 | Waterproofing Horizontal | 100 | 100 |  | 2024-11-15 | 2024-11-15 | 2024-11-20 | 2024-11-20 | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48137 | Retail - Foundation P3 | Complete |  | 2024-11-15 | 2024-11-20 | Waterproofing Horizontal | 100 | 100 |  | 2024-11-15 | 2024-11-15 | 2024-11-20 | 2024-11-20 | Retail | Foundation
8955 |  | Started |  | 2024-11-16 | 2026-12-09 | Superstructure | 100 | 4 |  | 2024-11-16 | 2024-11-16 | 2026-12-04
8956 |  | Complete |  | 2024-11-16 | 2024-11-23 | Reciept of Aluminium Materials | 100 | 100 |  | 2024-11-16 | 2024-11-16 | 2024-11-23 | 2024-11-23
39541 |  | Complete |  | 2024-11-16 | 2024-11-23 | Core Wall L40-41 | 100 | 100 |  | 2024-11-16 | 2024-11-16 | 2024-11-23 | 2024-11-23
39542 | Tower A - Super Structure - Core Wall Low Rise L40-41 | Complete | Core Wall RCC Works | 2024-11-16 | 2024-11-16 | Scaffolding & platform | 100 | 100 |  | 2024-11-16 | 2024-11-16 | 2024-11-16 | 2024-11-16 | Tower A | Super Structure | L40 | RCC Super Structure | Core Wall RCC Works
44855 | Tower B - Sub Structure - B2 to B1 - Pour 8 | Complete | RCC Works - Slab | 2024-11-16 | 2024-11-20 | Slab & Staircase Reinf. | 100 | 100 |  | 2024-11-16 | 2024-11-16 | 2024-11-20 | 2024-11-20 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
47626 |  | Complete |  | 2024-11-16 | 2024-12-03 | Slab_NTA | 100 | 100 |  | 2024-11-16 | 2024-11-16 | 2024-12-03 | 2024-12-03
47626 |  | Complete |  | 2024-11-16 | 2024-12-03 | Slab_NTA | 100 | 100 |  | 2024-11-16 | 2024-11-16 | 2024-12-03 | 2024-12-03 |  |  |  | RCC Sub Structure | RCC Works - Slab
8931 | T-15-Sub structure Columns | Started | Shuttering | 2024-11-18 | 2025-03-28 | Shuttering | 319 | 2 | Sqm | 2024-11-18 | 2024-11-18 | 2025-05-31
9982 |  | Started |  | 2024-11-18 | 2025-03-14 | Basement Roof/Podium Structure Works | 100 | 94 |  | 2024-11-18 | 2024-11-18 | 2025-05-19
9983 |  | Complete |  | 2024-11-18 | 2025-01-09 | Part-1 - TA | 100 | 100 |  | 2024-11-18 | 2024-11-18 | 2025-01-09 | 2025-01-09
9984 | T-21-Sub structure Basement Part 1 TA | Complete | Staging | 2024-11-18 | 2025-01-05 | Staging | 100 | 100 |  | 2024-11-18 | 2024-11-18 | 2025-01-05 | 2025-01-05
10493 |  | Complete |  | 2024-11-18 | 2024-12-24 | Shear Walls | 100 | 100 |  | 2024-11-18 | 2024-11-18 | 2024-12-24 | 2024-12-24
10494 | T-20-Sub structure Shear Walls | Complete | Reinforcement | 2024-11-18 | 2024-12-20 | Reinforcement | 18 | 18 | MTon | 2024-11-18 | 2024-11-18 | 2024-12-20 | 2024-12-20
10515 |  | Started |  | 2024-11-18 | 2026-12-03 | Superstructure | 100 | 3 |  | 2024-11-18 | 2024-11-18 | 2026-10-27
10516 |  | Complete |  | 2024-11-18 | 2024-11-23 | Reciept of Aluminium Materials | 100 | 100 |  | 2024-11-18 | 2024-11-18 | 2024-11-23 | 2024-11-23
39543 | Tower A - Super Structure - Core Wall Low Rise L40-41 | Complete | Core Wall RCC Works | 2024-11-18 | 2024-11-20 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-11-18 | 2024-11-18 | 2024-11-20 | 2024-11-20 | Tower A | Super Structure | L40 | RCC Super Structure | Core Wall RCC Works
39911 |  | Complete |  | 2024-11-18 | 2024-11-26 | L36-37 | 100 | 100 |  | 2024-11-18 | 2024-11-18 | 2024-11-26 | 2024-11-26
39911 |  | Complete |  | 2024-11-18 | 2024-11-26 | L36-37 | 100 | 100 |  | 2024-11-18 | 2024-11-18 | 2024-11-26 | 2024-11-26 |  |  |  | Finishes | Gypsum Plastering Works
39912 | Tower A - Super Structure - Core & Outer Slab L36-37 | Complete | RCC Works - Vertical | 2024-11-18 | 2024-11-25 | Outer Columns_TA | 100 | 100 |  | 2024-11-18 | 2024-11-18 | 2024-11-25 | 2024-11-25 | Tower A | Super Structure | L36 | RCC Sub Structure | RCC Works - Vertical
8932 | T-15-Sub structure Columns | Started | RCC | 2024-11-19 | 2025-03-28 | RCC | 35 | 2 | CUM | 2024-11-19 | 2024-11-19 | 2025-05-31
8932 | T-15-Sub structure Columns | Started | RCC | 2024-11-19 | 2025-03-28 | RCC | 35 | 2 | CUM | 2024-11-19 | 2024-11-19 | 2025-05-31
11522 | T-18-Sub structure Footings | Quality checked | Shuttering | 2024-11-19 | 2025-04-03 | Shuttering | 673 | 673 | Sqm | 2024-11-19 | 2024-11-19 | 2025-02-14 | 2025-02-15
39544 | Tower A - Super Structure - Core Wall Low Rise L40-41 | Complete | Core Wall RCC Works | 2024-11-19 | 2024-11-21 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-11-19 | 2024-11-19 | 2024-11-21 | 2024-11-21 | Tower A | Super Structure | L40 | RCC Super Structure | Core Wall RCC Works
44834 | Tower B - Sub Structure - B2 to B1 - Pour 3 | Complete | RCC Works - Slab | 2024-11-19 | 2024-11-23 | Slab & Staircase Reinf. | 100 | 100 |  | 2024-11-19 | 2024-11-19 | 2024-11-23 | 2024-11-23 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
44841 | Tower B - Sub Structure - B2 to B1 - Pour 1B & 6 | Complete | RCC Works - Slab | 2024-11-19 | 2024-11-26 | Slab & Staircase Reinf. | 100 | 100 |  | 2024-11-19 | 2024-11-19 | 2024-11-26 | 2024-11-26 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
44933 | Tower B - Sub Structure - B1 to GF - Pour 5 | Complete | RCC Works - Vertical | 2024-11-19 | 2024-11-21 | Col/ Wall Reinf. | 100 | 100 |  | 2024-11-19 | 2024-11-19 | 2024-11-21 | 2024-11-21 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44933 | Tower B - Sub Structure - B1 to GF - Pour 5 | Complete | RCC Works - Vertical | 2024-11-19 | 2024-11-21 | Col/ Wall Reinf. | 100 | 100 |  | 2024-11-19 | 2024-11-19 | 2024-11-21 | 2024-11-21 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
48270 | Retail - Sub structure - B1 to GF - P1 | Complete |  | 2024-11-19 | 2024-11-26 | Section 2_lift 1 | 100 | 100 |  | 2024-11-19 | 2024-11-19 | 2024-11-26 | 2024-11-26 | Retail | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
48270 | Retail - Sub structure - B1 to GF - P1 | Complete |  | 2024-11-19 | 2024-11-26 | Section 2_lift 1 | 100 | 100 |  | 2024-11-19 | 2024-11-19 | 2024-11-26 | 2024-11-26 | Retail | Sub Structure | B1
8392 | T-14-Sub structure Basement Part 1 TA | Quality checked | Formwork | 2024-11-20 | 2024-12-26 | Formwork | 100 | 100 | Sqm | 2024-11-20 | 2024-11-20 | 2024-12-26 | 2024-12-26
8935 | T-15-Sub structure Shear Walls | Complete | Shuttering | 2024-11-20 | 2025-01-09 | Shuttering | 100 | 100 |  | 2024-11-20 | 2024-11-20 | 2025-01-09 | 2025-01-09
9985 | T-21-Sub structure Basement Part 1 TA | Complete | Formwork | 2024-11-20 | 2025-01-07 | Formwork | 100 | 100 | Sqm | 2024-11-20 | 2024-11-20 | 2025-01-07 | 2025-01-07
11013 |  | Complete |  | 2024-11-20 | 2025-04-03 | Shear Walls | 100 | 100 |  | 2024-11-20 | 2024-11-20 | 2025-02-07 | 2025-02-08
11014 | T-19-Sub structure Shear Walls | Complete | Reinforcement | 2024-11-20 | 2024-12-23 | Reinforcement | 18 | 18 | MTon | 2024-11-20 | 2024-11-20 | 2024-12-23 | 2024-12-23
39913 | Tower A - Super Structure - Core & Outer Slab L36-37 | Complete | RCC Works - Slab | 2024-11-20 | 2024-11-26 | Outer Slab_TA | 100 | 100 |  | 2024-11-20 | 2024-11-20 | 2024-11-26 | 2024-11-26 | Tower A | Super Structure | L36 | RCC Sub Structure | RCC Works - Slab
11523 | T-18-Sub structure Footings | Complete | RCC | 2024-11-21 | 2025-04-03 | RCC | 713 | 713 | CUM | 2024-11-21 | 2024-11-21 | 2025-02-15 | 2025-02-15
11523 | T-18-Sub structure Footings | Complete | RCC | 2024-11-21 | 2025-04-03 | RCC | 713 | 713 | CUM | 2024-11-21 | 2024-11-21 | 2025-02-15 | 2025-02-15
39183 |  | Complete |  | 2024-11-21 | 2024-11-27 | Painting Woks | 100 | 100 |  | 2024-11-21 | 2024-11-21 | 2024-11-27 | 2024-11-27 |  |  |  | Finishes | Painting Works
44856 | Tower B - Sub Structure - B2 to B1 - Pour 8 | Complete | RCC Works - Slab | 2024-11-21 | 2024-11-22 | Slab & Staircase Casting | 100 | 100 |  | 2024-11-21 | 2024-11-21 | 2024-11-22 | 2024-11-22 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
39545 | Tower A - Super Structure - Core Wall Low Rise L40-41 | Complete | Core Wall RCC Works | 2024-11-22 | 2024-11-22 | Casting | 100 | 100 |  | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 | Tower A | Super Structure | L40 | RCC Super Structure | Core Wall RCC Works
41171 |  | Started |  | 2024-11-22 | 2026-01-13 | L14-15 | 100 | 65 |  | 2024-11-22 | 2024-11-22 | 2026-02-04 |  |  |  |  | Finishes | Gypsum Plastering Works
41171 |  | Started |  | 2024-11-22 | 2026-01-13 | L14-15 | 100 | 65 |  | 2024-11-22 | 2024-11-22 | 2026-02-04
41172 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2024-11-22 | 2024-11-22 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 80 |  | 2024-11-22 | 2024-11-22 | 2025-12-23 |  | Tower A | Super Structure | L14 | MEP | FPS 1st Fix - MEP & Finishes
42368 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Apartment Area | Started | Cement Plastering in Wet Areas - MEP & Finishes | 2024-11-22 | 2024-11-29 | Cement Plastering in wet areas | 100 | 30 |  | 2024-11-22 | 2024-11-22 | 2025-09-22 |  | Tower A | Super Structure | L16
44919 |  | Complete |  | 2024-11-22 | 2024-12-31 | Pour 8_B1 to GF | 100 | 100 |  | 2024-11-22 | 2024-11-22 | 2024-12-31 | 2024-12-31
44921 | Tower B - Sub Structure - B1 to GF - Pour 8 | Complete | RCC Works - Vertical | 2024-11-22 | 2024-12-03 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-11-22 | 2024-11-22 | 2024-12-03 | 2024-12-03 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44921 | Tower B - Sub Structure - B1 to GF - Pour 8 | Complete | RCC Works - Vertical | 2024-11-22 | 2024-12-03 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-11-22 | 2024-11-22 | 2024-12-03 | 2024-12-03 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44934 | Tower B - Sub Structure - B1 to GF - Pour 5 | Complete | RCC Works - Vertical | 2024-11-22 | 2024-11-25 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2024-11-22 | 2024-11-22 | 2024-11-25 | 2024-11-25 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44934 | Tower B - Sub Structure - B1 to GF - Pour 5 | Complete | RCC Works - Vertical | 2024-11-22 | 2024-11-25 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2024-11-22 | 2024-11-22 | 2024-11-25 | 2024-11-25 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
47638 |  | Complete |  | 2024-11-22 | 2024-11-22 | Section 4_lift 1 | 100 | 100 |  | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
47638 |  | Complete |  | 2024-11-22 | 2024-11-22 | Section 4_lift 1 | 100 | 100 |  | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47639 |  | Complete |  | 2024-11-22 | 2024-11-22 | Section 5_lift 1 | 100 | 100 |  | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
47639 |  | Complete |  | 2024-11-22 | 2024-11-22 | Section 5_lift 1 | 100 | 100 |  | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 |  |  |  | RCC Super Structure | Retaining Wall RCC Works
48271 | Retail - Sub structure - B1 to GF - P1 | Complete |  | 2024-11-22 | 2024-11-29 | Section 3_lift 1 | 100 | 100 |  | 2024-11-22 | 2024-11-22 | 2024-11-29 | 2024-11-29 | Retail | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
48271 | Retail - Sub structure - B1 to GF - P1 | Complete |  | 2024-11-22 | 2024-11-29 | Section 3_lift 1 | 100 | 100 |  | 2024-11-22 | 2024-11-22 | 2024-11-29 | 2024-11-29 | Retail | Sub Structure | B1
48287 |  | Complete |  | 2024-11-22 | 2025-05-28 | Retaining Wall_lift 2 (Grid PA-A onwards) | 100 | 100 |  | 2024-11-22 | 2024-11-22 | 2025-05-28 | 2025-05-28
48288 |  | Complete |  | 2024-11-22 | 2024-12-12 | Pour RT-1 | 100 | 100 |  | 2024-11-22 | 2024-11-22 | 2024-12-12 | 2024-12-12
48289 | Retail - Sub structure - B1 to GF - P1 | Complete |  | 2024-11-22 | 2024-11-29 | Section 1_lift 2 | 100 | 100 |  | 2024-11-22 | 2024-11-22 | 2024-11-29 | 2024-11-29 | Retail | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
48289 | Retail - Sub structure - B1 to GF - P1 | Complete |  | 2024-11-22 | 2024-11-29 | Section 1_lift 2 | 100 | 100 |  | 2024-11-22 | 2024-11-22 | 2024-11-29 | 2024-11-29 | Retail | Sub Structure | B1
39546 | Tower A - Super Structure - Core Wall Low Rise L40-41 | Complete | Core Wall RCC Works | 2024-11-23 | 2024-11-23 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-11-23 | 2024-11-23 | 2024-11-23 | 2024-11-23 | Tower A | Super Structure | L40 | RCC Super Structure | Core Wall RCC Works
44920 | Tower B - Sub Structure - B1 to GF - Pour 8 | Complete | RCC Works - Vertical | 2024-11-23 | 2024-11-29 | Col/ Wall Reinf. | 100 | 100 |  | 2024-11-23 | 2024-11-23 | 2024-11-29 | 2024-11-29 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44920 | Tower B - Sub Structure - B1 to GF - Pour 8 | Complete | RCC Works - Vertical | 2024-11-23 | 2024-11-29 | Col/ Wall Reinf. | 100 | 100 |  | 2024-11-23 | 2024-11-23 | 2024-11-29 | 2024-11-29 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
47598 |  | Milestone Started |  | 2024-11-24 |  | Section 7_lift 1 | 100 | 100 |  | 2024-11-24 | 2024-11-25 | [5 empty] | RCC Super Structure | Retaining Wall RCC Works
47598 |  | Milestone Started |  | 2024-11-24 |  | Section 7_lift 1 | 100 | 100 |  | 2024-11-24 | 2024-11-25
10497 | T-20-Sub structure Water proofing NTA | Forced Ready |  | 2025-03-06 | 2025-04-30 | Water Proofing Outside-NTA | 100 | 0 |  | 2024-11-25 |  | 2025-01-18
10498 |  | Started | Backfilling | 2024-11-25 | 2025-05-12 | Backfilling | 100 | 2 |  | 2024-11-25 | 2024-11-25 | 2025-07-15
11538 |  | Quality checked | Backfilling | 2024-11-25 | 2025-05-12 | Backfilling | 100 | 100 |  | 2024-11-25 | 2024-11-25 | 2025-07-15 | 2025-06-03
39547 |  | Complete |  | 2024-11-25 | 2024-12-02 | Core Wall L41-42 | 100 | 100 |  | 2024-11-25 | 2024-11-25 | 2024-12-02 | 2024-12-02
39548 | Tower A - Super Structure - Core Wall Low Rise L41-42 | Complete | Core Wall RCC Works | 2024-11-25 | 2024-11-25 | Scaffolding & platform | 100 | 100 |  | 2024-11-25 | 2024-11-25 | 2024-11-25 | 2024-11-25 | Tower A | Super Structure | L41 | RCC Super Structure | Core Wall RCC Works
44827 | Tower B - Sub Structure - B2 to B1 - Pour 1A & 2 | Complete | RCC Works - Slab | 2024-11-25 | 2024-11-28 | Slab & Staircase Reinf. | 100 | 100 |  | 2024-11-25 | 2024-11-25 | 2024-11-28 | 2024-11-28 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
44835 | Tower B - Sub Structure - B2 to B1 - Pour 3 | Complete | RCC Works - Slab | 2024-11-25 | 2024-11-26 | Slab & Staircase Casting | 100 | 100 |  | 2024-11-25 | 2024-11-25 | 2024-11-26 | 2024-11-26 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
44848 | Tower B - Sub Structure - B2 to B1 - Pour 7 | Complete | RCC Works - Slab | 2024-11-25 | 2024-11-28 | Slab & Staircase Reinf. | 100 | 100 |  | 2024-11-25 | 2024-11-25 | 2024-11-28 | 2024-11-28 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
44903 | Tower B - Sub Structure - B1 to GF - Pour 1B & 6 | Complete | RCC Works - Vertical | 2024-11-25 | 2024-12-02 | Col/ Wall Reinf. | 100 | 100 |  | 2024-11-25 | 2024-11-25 | 2024-12-02 | 2024-12-02 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44903 | Tower B - Sub Structure - B1 to GF - Pour 1B & 6 | Complete | RCC Works - Vertical | 2024-11-25 | 2024-12-02 | Col/ Wall Reinf. | 100 | 100 |  | 2024-11-25 | 2024-11-25 | 2024-12-02 | 2024-12-02 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44922 | Tower B - Sub Structure - B1 to GF - Pour 8 | Complete | RCC Works - Vertical | 2024-11-25 | 2024-12-05 | Col/ Wall Casting | 100 | 100 |  | 2024-11-25 | 2024-11-25 | 2024-12-05 | 2024-12-05 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44922 | Tower B - Sub Structure - B1 to GF - Pour 8 | Complete | RCC Works - Vertical | 2024-11-25 | 2024-12-05 | Col/ Wall Casting | 100 | 100 |  | 2024-11-25 | 2024-11-25 | 2024-12-05 | 2024-12-05 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44935 | Tower B - Sub Structure - B1 to GF - Pour 5 | Complete | RCC Works - Vertical | 2024-11-25 | 2024-11-26 | Col/ Wall Casting | 100 | 100 |  | 2024-11-25 | 2024-11-25 | 2024-11-26 | 2024-11-26 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44935 | Tower B - Sub Structure - B1 to GF - Pour 5 | Complete | RCC Works - Vertical | 2024-11-25 | 2024-11-26 | Col/ Wall Casting | 100 | 100 |  | 2024-11-25 | 2024-11-25 | 2024-11-26 | 2024-11-26 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
47599 |  | Complete |  | 2024-11-25 | 2024-12-24 | Section 8_lift 1 | 100 | 100 |  | 2024-11-25 | 2024-11-25 | 2024-12-24 | 2024-12-24
47599 |  | Complete |  | 2024-11-25 | 2024-12-24 | Section 8_lift 1 | 100 | 100 |  | 2024-11-25 | 2024-11-25 | 2024-12-24 | 2024-12-24 |  |  |  | RCC Super Structure | Retaining Wall RCC Works
10495 | T-20-Sub structure Shear Walls | Complete | Shuttering | 2024-11-26 | 2024-12-23 | Shuttering | 100 | 100 |  | 2024-11-26 | 2024-11-26 | 2024-12-23 | 2024-12-23
39549 | Tower A - Super Structure - Core Wall Low Rise L41-42 | Complete | Core Wall RCC Works | 2024-11-26 | 2024-11-28 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-11-26 | 2024-11-26 | 2024-11-28 | 2024-11-28 | Tower A | Super Structure | L41 | RCC Super Structure | Core Wall RCC Works
10496 | T-20-Sub structure Shear Walls | Complete | RCC | 2024-11-27 | 2024-12-24 | RCC | 208 | 208 | CUM | 2024-11-27 | 2024-11-27 | 2024-12-24 | 2024-12-24
10496 | T-20-Sub structure Shear Walls | Complete | RCC | 2024-11-27 | 2024-12-24 | RCC | 208 | 208 | CUM | 2024-11-27 | 2024-11-27 | 2024-12-24 | 2024-12-24
39232 |  | Started |  | 2024-11-27 | 2024-12-10 | Low Side Installation - Installation of Condenser Water Piping (GF to B02) | 100 | 80 |  | 2024-11-27 | 2024-11-27 | 2025-09-23
39550 | Tower A - Super Structure - Core Wall Low Rise L41-42 | Complete | Core Wall RCC Works | 2024-11-27 | 2024-11-29 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-11-27 | 2024-11-27 | 2024-11-29 | 2024-11-29 | Tower A | Super Structure | L41 | RCC Super Structure | Core Wall RCC Works
39914 |  | Complete |  | 2024-11-27 | 2024-12-05 | L37-38 | 100 | 100 |  | 2024-11-27 | 2024-11-27 | 2024-12-05 | 2024-12-05
39914 |  | Complete |  | 2024-11-27 | 2024-12-05 | L37-38 | 100 | 100 |  | 2024-11-27 | 2024-11-27 | 2024-12-05 | 2024-12-05 |  |  |  | Finishes | Gypsum Plastering Works
39915 | Tower A - Super Structure - Core & Outer Slab L37-38 | Complete | RCC Works - Vertical | 2024-11-27 | 2024-12-03 | Outer Columns_TA | 100 | 100 |  | 2024-11-27 | 2024-11-27 | 2024-12-03 | 2024-12-03 | Tower A | Super Structure | L37 | RCC Sub Structure | RCC Works - Vertical
40285 |  | Complete |  | 2024-11-27 | 2025-05-12 | L34-35 | 100 | 100 |  | 2024-11-27 | 2024-11-27 | 2025-05-12 | 2025-06-05
40285 |  | Complete |  | 2024-11-27 | 2025-05-12 | L34-35 | 100 | 100 |  | 2024-11-27 | 2024-11-27 | 2025-05-12 | 2025-06-05 |  |  |  | Finishes | Gypsum Plastering Works
40286 | Tower A - Super Structure - Finishes & MEP - L34 to L35 | Complete | Partition Wall-Blockwork | 2024-11-27 | 2024-12-13 | De-shuttering & Area clearance | 100 | 100 |  | 2024-11-27 | 2024-11-27 | 2024-12-13 | 2024-12-13 | Tower A | Super Structure | L34
44842 | Tower B - Sub Structure - B2 to B1 - Pour 1B & 6 | Complete | RCC Works - Slab | 2024-11-27 | 2024-11-28 | Slab & Staircase Casting | 100 | 100 |  | 2024-11-27 | 2024-11-27 | 2024-11-28 | 2024-11-28 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
44936 | Tower B - Sub Structure - B1 to GF - Pour 5 | Complete | RCC Works - Slab | 2024-11-27 | 2024-12-10 | Slab & Staircase Fwk. | 100 | 100 |  | 2024-11-27 | 2024-11-27 | 2024-12-10 | 2024-12-10 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
48272 | Retail - Sub structure - B1 to GF - P1 | Complete |  | 2024-11-27 | 2024-12-04 | Section 4_lift 1 | 100 | 100 |  | 2024-11-27 | 2024-11-27 | 2024-12-04 | 2024-12-04 | Retail | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
48272 | Retail - Sub structure - B1 to GF - P1 | Complete |  | 2024-11-27 | 2024-12-04 | Section 4_lift 1 | 100 | 100 |  | 2024-11-27 | 2024-11-27 | 2024-12-04 | 2024-12-04 | Retail | Sub Structure | B1
48290 | Retail - Sub structure - B1 to GF - P1 | Complete |  | 2024-11-27 | 2024-12-04 | Section 2_lift 2 | 100 | 100 |  | 2024-11-27 | 2024-11-27 | 2024-12-04 | 2024-12-04 | Retail | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
48290 | Retail - Sub structure - B1 to GF - P1 | Complete |  | 2024-11-27 | 2024-12-04 | Section 2_lift 2 | 100 | 100 |  | 2024-11-27 | 2024-11-27 | 2024-12-04 | 2024-12-04 | Retail | Sub Structure | B1
9986 | T-21-Sub structure Basement Part 1 TA | Complete | Reinforcement | 2024-11-28 | 2025-01-08 | Reinforcement | 28 | 28 | MT | 2024-11-28 | 2024-11-28 | 2025-01-08 | 2025-01-08
10492 | T-20-Sub structure Columns | Started | RCC | 2024-11-28 | 2025-03-28 | RCC | 35 | 2 | CUM | 2024-11-28 | 2024-11-28 | 2025-05-31
10492 | T-20-Sub structure Columns | Started | RCC | 2024-11-28 | 2025-03-28 | RCC | 35 | 2 | CUM | 2024-11-28 | 2024-11-28 | 2025-05-31
8386 |  | Started |  | 2024-11-29 | 2025-06-10 | Grade Slab | 100 | 1 |  | 2024-11-29 | 2024-11-29 | 2025-08-01
8387 | T-14-Sub structure Grade slab | Started | Grade Slab PCC | 2024-11-29 | 2025-04-03 | Grade Slab PCC | 212 | 2 | CUM | 2024-11-29 | 2024-11-29 | 2025-06-06
39916 | Tower A - Super Structure - Core & Outer Slab L37-38 | Complete | RCC Works - Slab | 2024-11-29 | 2024-12-05 | Outer Slab_TA | 100 | 100 |  | 2024-11-29 | 2024-11-29 | 2024-12-05 | 2024-12-05 | Tower A | Super Structure | L37 | RCC Sub Structure | RCC Works - Slab
44828 | Tower B - Sub Structure - B2 to B1 - Pour 1A & 2 | Complete | RCC Works - Slab | 2024-11-29 | 2024-11-30 | Slab & Staircase Casting | 100 | 100 |  | 2024-11-29 | 2024-11-29 | 2024-11-30 | 2024-11-30 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
39551 | Tower A - Super Structure - Core Wall Low Rise L41-42 | Complete | Core Wall RCC Works | 2024-11-30 | 2024-11-30 | Casting | 100 | 100 |  | 2024-11-30 | 2024-11-30 | 2024-11-30 | 2024-11-30 | Tower A | Super Structure | L41 | RCC Super Structure | Core Wall RCC Works
44909 |  | Complete |  | 2024-11-30 | 2025-01-10 | Pour 7_B1 to GF | 100 | 100 |  | 2024-11-30 | 2024-11-30 | 2025-01-10 | 2025-01-10
44911 | Tower B - Sub Structure - B1 to GF - Pour 7 | Complete | RCC Works - Vertical | 2024-11-30 | 2024-12-11 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-11-30 | 2024-11-30 | 2024-12-11 | 2024-12-11 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44911 | Tower B - Sub Structure - B1 to GF - Pour 7 | Complete | RCC Works - Vertical | 2024-11-30 | 2024-12-11 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-11-30 | 2024-11-30 | 2024-12-11 | 2024-12-11 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
48273 |  | Complete |  | 2024-11-30 | 2025-02-13 | Pour RT-2 | 100 | 100 |  | 2024-11-30 | 2024-11-30 | 2025-02-13 | 2025-02-13
48274 | Retail - Sub structure - B1 to GF - P2 | Complete |  | 2024-11-30 | 2024-12-07 | Section 5_lift 1 | 100 | 100 |  | 2024-11-30 | 2024-11-30 | 2024-12-07 | 2024-12-07 | Retail | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
48274 | Retail - Sub structure - B1 to GF - P2 | Complete |  | 2024-11-30 | 2024-12-07 | Section 5_lift 1 | 100 | 100 |  | 2024-11-30 | 2024-11-30 | 2024-12-07 | 2024-12-07 | Retail | Sub Structure | B1
48291 | Retail - Sub structure - B1 to GF - P1 | Complete |  | 2024-11-30 | 2024-12-07 | Section 3_lift 2 | 100 | 100 |  | 2024-11-30 | 2024-11-30 | 2024-12-07 | 2024-12-07 | Retail | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
48291 | Retail - Sub structure - B1 to GF - P1 | Complete |  | 2024-11-30 | 2024-12-07 | Section 3_lift 2 | 100 | 100 |  | 2024-11-30 | 2024-11-30 | 2024-12-07 | 2024-12-07 | Retail | Sub Structure | B1
8393 | T-14-Sub structure Basement Part 1 TA | Quality checked | Reinforcement | 2024-12-02 | 2024-12-27 | Reinforcement | 28 | 28 | MT | 2024-12-02 | 2024-12-02 | 2024-12-27 | 2024-12-27
39552 | Tower A - Super Structure - Core Wall Low Rise L41-42 | Complete | Core Wall RCC Works | 2024-12-02 | 2024-12-02 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-12-02 | 2024-12-02 | 2024-12-02 | 2024-12-02 | Tower A | Super Structure | L41 | RCC Super Structure | Core Wall RCC Works
44872 |  | Complete |  | 2024-12-02 | 2025-01-01 | Core Wall B1 to GF | 100 | 100 |  | 2024-12-02 | 2024-12-02 | 2025-01-01 | 2025-01-01
44873 | Tower B - Sub Structure - B1 to GF | Complete | Core Wall RCC Works | 2024-12-02 | 2024-12-12 | CW Reinf_lift 1 | 100 | 100 |  | 2024-12-02 | 2024-12-02 | 2024-12-12 | 2024-12-12 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
39553 |  | Complete |  | 2024-12-03 | 2024-12-09 | Core Wall L42-43 | 100 | 100 |  | 2024-12-03 | 2024-12-03 | 2024-12-09 | 2024-12-09
39554 | Tower A - Super Structure - Core Wall Low Rise L42-43 | Complete | Core Wall RCC Works | 2024-12-03 | 2024-12-03 | Scaffolding & platform | 100 | 100 |  | 2024-12-03 | 2024-12-03 | 2024-12-03 | 2024-12-03 | Tower A | Super Structure | L42 | RCC Super Structure | Core Wall RCC Works
44849 | Tower B - Sub Structure - B2 to B1 - Pour 7 | Complete | RCC Works - Slab | 2024-12-03 | 2024-12-04 | Slab & Staircase Casting | 100 | 100 |  | 2024-12-03 | 2024-12-03 | 2024-12-04 | 2024-12-04 | Tower B | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
44912 | Tower B - Sub Structure - B1 to GF - Pour 7 | Complete | RCC Works - Vertical | 2024-12-03 | 2024-12-13 | Col/ Wall Casting | 100 | 100 |  | 2024-12-03 | 2024-12-03 | 2024-12-13 | 2024-12-13 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44912 | Tower B - Sub Structure - B1 to GF - Pour 7 | Complete | RCC Works - Vertical | 2024-12-03 | 2024-12-13 | Col/ Wall Casting | 100 | 100 |  | 2024-12-03 | 2024-12-03 | 2024-12-13 | 2024-12-13 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
39555 | Tower A - Super Structure - Core Wall Low Rise L42-43 | Complete | Core Wall RCC Works | 2024-12-04 | 2024-12-06 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-12-04 | 2024-12-04 | 2024-12-06 | 2024-12-06 | Tower A | Super Structure | L42 | RCC Super Structure | Core Wall RCC Works
47655 |  | Complete |  | 2024-12-04 | 2025-01-02 | Pour 10 (PB-K to PA-B / RT-08 to PB-06) | 100 | 100 |  | 2024-12-04 | 2024-12-04 | 2025-01-02 | 2025-01-02
47656 |  | Complete |  | 2024-12-04 | 2024-12-10 | Columns/ Walls_NTA | 100 | 100 |  | 2024-12-04 | 2024-12-04 | 2024-12-10 | 2024-12-10
47656 |  | Complete |  | 2024-12-04 | 2024-12-10 | Columns/ Walls_NTA | 100 | 100 |  | 2024-12-04 | 2024-12-04 | 2024-12-10 | 2024-12-10 |  |  |  | RCC Sub Structure | RCC Works - Vertical
39556 | Tower A - Super Structure - Core Wall Low Rise L42-43 | Complete | Core Wall RCC Works | 2024-12-05 | 2024-12-07 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-12-05 | 2024-12-05 | 2024-12-07 | 2024-12-07 | Tower A | Super Structure | L42 | RCC Super Structure | Core Wall RCC Works
40289 |  | Complete |  | 2024-12-05 | 2025-05-20 | L35-36 | 100 | 100 |  | 2024-12-05 | 2024-12-05 | 2025-05-20 | 2025-06-05
40289 |  | Complete |  | 2024-12-05 | 2025-05-20 | L35-36 | 100 | 100 |  | 2024-12-05 | 2024-12-05 | 2025-05-20 | 2025-06-05 |  |  |  | Finishes | Gypsum Plastering Works
40290 | Tower A - Super Structure - Finishes & MEP - L35 to L36 | Complete | Partition Wall-Blockwork | 2024-12-05 | 2024-12-21 | De-shuttering & Area clearance | 100 | 100 |  | 2024-12-05 | 2024-12-05 | 2024-12-21 | 2024-12-21 | Tower A | Super Structure | L35
44904 | Tower B - Sub Structure - B1 to GF - Pour 1B & 6 | Complete | RCC Works - Vertical | 2024-12-05 | 2024-12-07 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2024-12-05 | 2024-12-05 | 2024-12-07 | 2024-12-07 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44904 | Tower B - Sub Structure - B1 to GF - Pour 1B & 6 | Complete | RCC Works - Vertical | 2024-12-05 | 2024-12-07 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2024-12-05 | 2024-12-05 | 2024-12-07 | 2024-12-07 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44910 | Tower B - Sub Structure - B1 to GF - Pour 7 | Complete | RCC Works - Vertical | 2024-12-05 | 2024-12-07 | Col/ Wall Reinf. | 100 | 100 |  | 2024-12-05 | 2024-12-05 | 2024-12-07 | 2024-12-07 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44910 | Tower B - Sub Structure - B1 to GF - Pour 7 | Complete | RCC Works - Vertical | 2024-12-05 | 2024-12-07 | Col/ Wall Reinf. | 100 | 100 |  | 2024-12-05 | 2024-12-05 | 2024-12-07 | 2024-12-07 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
48275 | Retail - Sub structure - B1 to GF - P2 | Complete |  | 2024-12-05 | 2024-12-12 | Section 6_lift 1 | 100 | 100 |  | 2024-12-05 | 2024-12-05 | 2024-12-12 | 2024-12-12 | Retail | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
48275 | Retail - Sub structure - B1 to GF - P2 | Complete |  | 2024-12-05 | 2024-12-12 | Section 6_lift 1 | 100 | 100 |  | 2024-12-05 | 2024-12-05 | 2024-12-12 | 2024-12-12 | Retail | Sub Structure | B1
48292 | Retail - Sub structure - B1 to GF - P1 | Complete |  | 2024-12-05 | 2024-12-12 | Section 4_lift 2 | 100 | 100 |  | 2024-12-05 | 2024-12-05 | 2024-12-12 | 2024-12-12 | Retail | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
48292 | Retail - Sub structure - B1 to GF - P1 | Complete |  | 2024-12-05 | 2024-12-12 | Section 4_lift 2 | 100 | 100 |  | 2024-12-05 | 2024-12-05 | 2024-12-12 | 2024-12-12 | Retail | Sub Structure | B1
39917 |  | Complete |  | 2024-12-06 | 2024-12-14 | L38-39 | 100 | 100 |  | 2024-12-06 | 2024-12-06 | 2024-12-14 | 2024-12-14
39917 |  | Complete |  | 2024-12-06 | 2024-12-14 | L38-39 | 100 | 100 |  | 2024-12-06 | 2024-12-06 | 2024-12-14 | 2024-12-14 |  |  |  | Finishes | Gypsum Plastering Works
39918 | Tower A - Super Structure - Core & Outer Slab L38-39 | Complete | RCC Works - Vertical | 2024-12-06 | 2024-12-12 | Outer Columns_TA | 100 | 100 |  | 2024-12-06 | 2024-12-06 | 2024-12-12 | 2024-12-12 | Tower A | Super Structure | L38 | RCC Sub Structure | RCC Works - Vertical
44923 | Tower B - Sub Structure - B1 to GF - Pour 8 | Complete | RCC Works - Vertical | 2024-12-06 | 2024-12-09 | Col/ Wall Reinf. | 100 | 100 |  | 2024-12-06 | 2024-12-06 | 2024-12-09 | 2024-12-09 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44923 | Tower B - Sub Structure - B1 to GF - Pour 8 | Complete | RCC Works - Vertical | 2024-12-06 | 2024-12-09 | Col/ Wall Reinf. | 100 | 100 |  | 2024-12-06 | 2024-12-06 | 2024-12-09 | 2024-12-09 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
39557 | Tower A - Super Structure - Core Wall Low Rise L42-43 | Complete | Core Wall RCC Works | 2024-12-07 | 2024-12-07 | Casting | 100 | 100 |  | 2024-12-07 | 2024-12-07 | 2024-12-07 | 2024-12-07 | Tower A | Super Structure | L42 | RCC Super Structure | Core Wall RCC Works
44874 | Tower B - Sub Structure - B1 to GF | Complete | Core Wall RCC Works | 2024-12-07 | 2024-12-16 | CW Fwk (3.5m lift)_lift 1 | 100 | 100 |  | 2024-12-07 | 2024-12-07 | 2024-12-16 | 2024-12-16 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
39558 | Tower A - Super Structure - Core Wall Low Rise L42-43 | Complete | Core Wall RCC Works | 2024-12-09 | 2024-12-09 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-12-09 | 2024-12-09 | 2024-12-09 | 2024-12-09 | Tower A | Super Structure | L42 | RCC Super Structure | Core Wall RCC Works
39919 | Tower A - Super Structure - Core & Outer Slab L38-39 | Complete | RCC Works - Slab | 2024-12-09 | 2024-12-14 | Outer Slab_TA | 100 | 100 |  | 2024-12-09 | 2024-12-09 | 2024-12-14 | 2024-12-14 | Tower A | Super Structure | L38 | RCC Sub Structure | RCC Works - Slab
48293 |  | Complete |  | 2024-12-09 | 2025-02-21 | Pour RT-2 | 100 | 100 |  | 2024-12-09 | 2024-12-09 | 2025-02-21 | 2025-02-21
48294 | Retail - Sub structure - B1 to GF - P2 | Complete |  | 2024-12-09 | 2024-12-16 | Section 5_lift 2 | 100 | 100 |  | 2024-12-09 | 2024-12-09 | 2024-12-16 | 2024-12-16 | Retail | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
48294 | Retail - Sub structure - B1 to GF - P2 | Complete |  | 2024-12-09 | 2024-12-16 | Section 5_lift 2 | 100 | 100 |  | 2024-12-09 | 2024-12-09 | 2024-12-16 | 2024-12-16 | Retail | Sub Structure | B1
39559 |  | Complete |  | 2024-12-10 | 2024-12-16 | Core Wall L43-44 | 100 | 100 |  | 2024-12-10 | 2024-12-10 | 2024-12-16 | 2024-12-16
39560 | Tower A - Super Structure - Core Wall Low Rise L43-44 | Complete | Core Wall RCC Works | 2024-12-10 | 2024-12-10 | Scaffolding & platform | 100 | 100 |  | 2024-12-10 | 2024-12-10 | 2024-12-10 | 2024-12-10 | Tower A | Super Structure | L43 | RCC Super Structure | Core Wall RCC Works
44879 |  | Complete |  | 2024-12-10 | 2025-01-09 | Pour 1A & 2_B1 to GF | 100 | 100 |  | 2024-12-10 | 2024-12-10 | 2025-01-09 | 2025-01-09
44880 | Tower B - Sub Structure - B1 to GF - Pour 1A & 2 | Complete | RCC Works - Vertical | 2024-12-10 | 2024-12-21 | Col/ Wall Reinf. | 100 | 100 |  | 2024-12-10 | 2024-12-10 | 2024-12-21 | 2024-12-21 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44880 | Tower B - Sub Structure - B1 to GF - Pour 1A & 2 | Complete | RCC Works - Vertical | 2024-12-10 | 2024-12-21 | Col/ Wall Reinf. | 100 | 100 |  | 2024-12-10 | 2024-12-10 | 2024-12-21 | 2024-12-21 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44924 | Tower B - Sub Structure - B1 to GF - Pour 8 | Complete | RCC Works - Vertical | 2024-12-10 | 2024-12-12 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2024-12-10 | 2024-12-10 | 2024-12-12 | 2024-12-12 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44924 | Tower B - Sub Structure - B1 to GF - Pour 8 | Complete | RCC Works - Vertical | 2024-12-10 | 2024-12-12 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2024-12-10 | 2024-12-10 | 2024-12-12 | 2024-12-12 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44937 | Tower B - Sub Structure - B1 to GF - Pour 5 | Complete | RCC Works - Slab | 2024-12-10 | 2024-12-16 | Slab & Staircase Reinf. | 100 | 100 |  | 2024-12-10 | 2024-12-10 | 2024-12-16 | 2024-12-16 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
8936 | T-15-Sub structure Shear Walls | Complete | RCC | 2024-12-11 | 2025-01-10 | RCC | 208 | 208 | CUM | 2024-12-11 | 2024-12-11 | 2025-01-10 | 2025-01-10
8936 | T-15-Sub structure Shear Walls | Complete | RCC | 2024-12-11 | 2025-01-10 | RCC | 208 | 208 | CUM | 2024-12-11 | 2024-12-11 | 2025-01-10 | 2025-01-10
11004 |  | Started |  | 2024-12-11 | 2025-04-30 | Retaining Wall | 100 | 12 |  | 2024-12-11 | 2024-12-11 | 2025-07-03
11005 | T-19-Sub structure Retaining Wall | Started | PCC | 2024-12-11 | 2025-04-03 | PCC | 14 | 2 | CUM | 2024-12-11 | 2024-12-11 | 2025-06-06
11524 |  | Started |  | 2024-12-11 | 2025-04-08 | Retaining Wall | 100 | 61 |  | 2024-12-11 | 2024-12-11 | 2025-06-12
11525 | T-18-Sub structure Retaining Wall | Started | PCC | 2024-12-11 | 2025-03-28 | PCC | 14 | 2 | CUM | 2024-12-11 | 2024-12-11 | 2025-05-31
39561 | Tower A - Super Structure - Core Wall Low Rise L43-44 | Complete | Core Wall RCC Works | 2024-12-11 | 2024-12-13 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-12-11 | 2024-12-11 | 2024-12-13 | 2024-12-13 | Tower A | Super Structure | L43 | RCC Super Structure | Core Wall RCC Works
44905 | Tower B - Sub Structure - B1 to GF - Pour 1B & 6 | Complete | RCC Works - Vertical | 2024-12-11 | 2024-12-12 | Col/ Wall Casting | 100 | 100 |  | 2024-12-11 | 2024-12-11 | 2024-12-12 | 2024-12-12 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44905 | Tower B - Sub Structure - B1 to GF - Pour 1B & 6 | Complete | RCC Works - Vertical | 2024-12-11 | 2024-12-12 | Col/ Wall Casting | 100 | 100 |  | 2024-12-11 | 2024-12-11 | 2024-12-12 | 2024-12-12 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
39562 | Tower A - Super Structure - Core Wall Low Rise L43-44 | Complete | Core Wall RCC Works | 2024-12-12 | 2024-12-14 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-12-12 | 2024-12-12 | 2024-12-14 | 2024-12-14 | Tower A | Super Structure | L43 | RCC Super Structure | Core Wall RCC Works
44925 | Tower B - Sub Structure - B1 to GF - Pour 8 | Complete | RCC Works - Vertical | 2024-12-12 | 2024-12-13 | Col/ Wall Casting | 100 | 100 |  | 2024-12-12 | 2024-12-12 | 2024-12-13 | 2024-12-13 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44925 | Tower B - Sub Structure - B1 to GF - Pour 8 | Complete | RCC Works - Vertical | 2024-12-12 | 2024-12-13 | Col/ Wall Casting | 100 | 100 |  | 2024-12-12 | 2024-12-12 | 2024-12-13 | 2024-12-13 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
11006 | T-19-Sub structure Retaining Wall | Started | Reinforcement | 2024-12-13 | 2025-04-30 | Reinforcement | 6.86 | 2 | MT | 2024-12-13 | 2024-12-13 | 2025-07-03
11035 |  | Started |  | 2024-12-13 | 2027-01-14 | Superstructure | 100 | 3 |  | 2024-12-13 | 2024-12-13 | 2026-11-25
11036 |  | Complete |  | 2024-12-13 | 2024-12-18 | Reciept of Aluminium Materials | 100 | 100 |  | 2024-12-13 | 2024-12-13 | 2024-12-18 | 2024-12-18
11526 | T-18-Sub structure Retaining Wall | Started | Reinforcement | 2024-12-13 | 2025-03-28 | Reinforcement | 7.55 | 2 | MT | 2024-12-13 | 2024-12-13 | 2025-05-31
40293 |  | Complete |  | 2024-12-13 | 2025-05-28 | L36-37 | 100 | 100 |  | 2024-12-13 | 2024-12-13 | 2025-05-28 | 2025-05-28
40293 |  | Complete |  | 2024-12-13 | 2025-05-28 | L36-37 | 100 | 100 |  | 2024-12-13 | 2024-12-13 | 2025-05-28 | 2025-05-28 |  |  |  | Finishes | Gypsum Plastering Works
40294 | Tower A - Super Structure - Finishes & MEP - L36 to L37 | Complete | Partition Wall-Blockwork | 2024-12-13 | 2024-12-31 | De-shuttering & Area clearance | 100 | 100 |  | 2024-12-13 | 2024-12-13 | 2024-12-31 | 2024-12-31 | Tower A | Super Structure | L36
44906 | Tower B - Sub Structure - B1 to GF - Pour 1B & 6 | Complete | RCC Works - Slab | 2024-12-13 | 2024-12-21 | Slab & Staircase Fwk. | 100 | 100 |  | 2024-12-13 | 2024-12-13 | 2024-12-21 | 2024-12-21 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
48295 | Retail - Sub structure - B1 to GF - P2 | Complete |  | 2024-12-13 | 2024-12-20 | Section 6_lift 2 | 100 | 100 |  | 2024-12-13 | 2024-12-13 | 2024-12-20 | 2024-12-20 | Retail | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
48295 | Retail - Sub structure - B1 to GF - P2 | Complete |  | 2024-12-13 | 2024-12-20 | Section 6_lift 2 | 100 | 100 |  | 2024-12-13 | 2024-12-13 | 2024-12-20 | 2024-12-20 | Retail | Sub Structure | B1
8394 | T-14-Sub structure Basement Part 1 TA | Quality checked | Conduiting | 2024-12-14 | 2024-12-27 | Conduiting | 100 | 100 |  | 2024-12-14 | 2024-12-14 | 2024-12-27 | 2024-12-27
44881 | Tower B - Sub Structure - B1 to GF - Pour 1A & 2 | Complete | RCC Works - Vertical | 2024-12-14 | 2024-12-26 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-12-14 | 2024-12-14 | 2024-12-26 | 2024-12-26 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44881 | Tower B - Sub Structure - B1 to GF - Pour 1A & 2 | Complete | RCC Works - Vertical | 2024-12-14 | 2024-12-26 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-12-14 | 2024-12-14 | 2024-12-26 | 2024-12-26 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44913 | Tower B - Sub Structure - B1 to GF - Pour 7 | Complete | RCC Works - Vertical | 2024-12-14 | 2024-12-16 | Col/ Wall Reinf. | 100 | 100 |  | 2024-12-14 | 2024-12-14 | 2024-12-16 | 2024-12-16 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44913 | Tower B - Sub Structure - B1 to GF - Pour 7 | Complete | RCC Works - Vertical | 2024-12-14 | 2024-12-16 | Col/ Wall Reinf. | 100 | 100 |  | 2024-12-14 | 2024-12-14 | 2024-12-16 | 2024-12-16 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44926 | Tower B - Sub Structure - B1 to GF - Pour 8 | Complete | RCC Works - Slab | 2024-12-14 | 2024-12-24 | Slab & Staircase Fwk. | 100 | 100 |  | 2024-12-14 | 2024-12-14 | 2024-12-24 | 2024-12-24 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
44938 | Tower B - Sub Structure - B1 to GF - Pour 5 | Complete | RCC Works - Slab | 2024-12-14 | 2024-12-19 | Slab & Staircase Casting | 100 | 100 |  | 2024-12-14 | 2024-12-14 | 2024-12-19 | 2024-12-19 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
11007 | T-19-Sub structure Retaining Wall | Started | Shuttering | 2024-12-15 | 2025-04-03 | Shuttering | 857.4 | 2 | Sqm | 2024-12-15 | 2024-12-15 | 2025-06-06
11018 |  | Started | Backfilling | 2024-12-15 | 2025-05-12 | Backfilling | 100 | 2 |  | 2024-12-15 | 2024-12-15 | 2025-07-15
39563 | Tower A - Super Structure - Core Wall Low Rise L43-44 | Milestone Started | Core Wall RCC Works | 2024-12-15 |  | Casting | 100 | 100 |  | 2024-12-15 | 2024-12-16 |  |  | Tower A | Super Structure | L43 | RCC Super Structure | Core Wall RCC Works
47652 |  | Complete |  | 2024-12-15 | 2024-12-31 | Pour 9 (grid PB-06 to PB-D) | 100 | 100 |  | 2024-12-15 | 2024-12-31 | 2024-12-31 | 2024-12-31
47653 |  | Milestone Started |  | 2024-12-15 |  | Columns/ Walls_NTA | 100 | 100 |  | 2024-12-15 | 2024-12-31 | [5 empty] | RCC Sub Structure | RCC Works - Vertical
47653 |  | Milestone Started |  | 2024-12-15 |  | Columns/ Walls_NTA | 100 | 100 |  | 2024-12-15 | 2024-12-31
9451 | T-16-Sub structure Columns | Complete | Shuttering | 2024-12-16 | 2025-03-28 | Shuttering | 319 | 319 | Sqm | 2024-12-16 | 2024-12-16 | 2025-05-31 | 2025-06-01
11008 | T-19-Sub structure Retaining Wall | Started | RCC | 2024-12-16 | 2025-04-08 | RCC | 85.7 | 2 | CUM | 2024-12-16 | 2024-12-16 | 2025-06-12
11008 | T-19-Sub structure Retaining Wall | Started | RCC | 2024-12-16 | 2025-04-08 | RCC | 85.7 | 2 | CUM | 2024-12-16 | 2024-12-16 | 2025-06-12
39234 |  | Started |  | 2024-12-16 | 2025-02-14 | Low Side Installation - Insulation of Chilled Water Piping (B02) | 100 | 50 |  | 2024-12-16 | 2025-07-10 | 2025-10-13
39564 | Tower A - Super Structure - Core Wall Low Rise L43-44 | Complete | Core Wall RCC Works | 2024-12-16 | 2024-12-16 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-12-16 | 2024-12-16 | 2024-12-16 | 2024-12-16 | Tower A | Super Structure | L43 | RCC Super Structure | Core Wall RCC Works
39920 |  | Complete |  | 2024-12-16 | 2024-12-22 | L39-40 | 100 | 100 |  | 2024-12-16 | 2024-12-16 | 2024-12-22 | 2024-12-22
39920 |  | Complete |  | 2024-12-16 | 2024-12-22 | L39-40 | 100 | 100 |  | 2024-12-16 | 2024-12-16 | 2024-12-22 | 2024-12-22 |  |  |  | Finishes | Gypsum Plastering Works
39921 | Tower A - Super Structure - Core & Outer Slab L39-40 | Complete | RCC Works - Vertical | 2024-12-16 | 2024-12-21 | Outer Columns_TA | 100 | 100 |  | 2024-12-16 | 2024-12-16 | 2024-12-21 | 2024-12-21 | Tower A | Super Structure | L39 | RCC Sub Structure | RCC Works - Vertical
42416 |  | Started |  | 2024-12-16 | 2026-06-17 | L19-20 | 100 | 70 |  | 2024-12-16 | 2024-12-16 | 2026-06-15 |  |  |  |  | Finishes | Gypsum Plastering Works
42416 |  | Started |  | 2024-12-16 | 2026-06-17 | L19-20 | 100 | 70 |  | 2024-12-16 | 2024-12-16 | 2026-06-15
42417 |  | Started |  | 2024-12-16 | 2025-01-10 | MEP 1st Fixes | 100 | 74 |  | 2024-12-16 | 2024-12-16 | 2025-09-22
42418 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Apartment Area | Started | FPS 1st Fix - MEP & Finishes | 2024-12-16 | 2024-12-17 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 80 |  | 2024-12-16 | 2024-12-16 | 2025-09-12 |  | Tower A | Super Structure | L19 | MEP | FPS 1st Fix - MEP & Finishes
42419 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Apartment Area | Started | Electrical 1st Fix - MEP & Finishes | 2024-12-16 | 2024-12-16 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 90 |  | 2024-12-16 | 2024-12-16 | 2025-09-11 |  | Tower A | Super Structure | L19 | MEP | Electrical 1st Fixes
42420 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Apartment Area | Started | PHE 1st Fix - MEP & Finishes | 2024-12-16 | 2024-12-17 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 80 |  | 2024-12-16 | 2024-12-16 | 2025-09-12 |  | Tower A | Super Structure | L19
42421 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Apartment Area | Started | Wet Area Waterproofing - MEP & Finishes | 2024-12-16 | 2024-12-17 | Wet Area Waterproofing | 100 | 90 |  | 2024-12-16 | 2024-12-16 | 2025-09-12 |  | Tower A | Super Structure | L19
44939 |  | Complete |  | 2024-12-16 | 2025-01-24 | Pour 4_B1 to GF | 100 | 100 |  | 2024-12-16 | 2024-12-16 | 2025-01-24 | 2025-01-24
44940 | Tower B - Sub Structure - B1 to GF - Pour 4 | Complete | RCC Works - Vertical | 2024-12-16 | 2024-12-23 | Col/ Wall Reinf. | 100 | 100 |  | 2024-12-16 | 2024-12-16 | 2024-12-23 | 2024-12-23 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44940 | Tower B - Sub Structure - B1 to GF - Pour 4 | Complete | RCC Works - Vertical | 2024-12-16 | 2024-12-23 | Col/ Wall Reinf. | 100 | 100 |  | 2024-12-16 | 2024-12-16 | 2024-12-23 | 2024-12-23 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44941 | Tower B - Sub Structure - B1 to GF - Pour 4 | Complete | RCC Works - Vertical | 2024-12-16 | 2024-12-27 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-12-16 | 2024-12-16 | 2024-12-27 | 2024-12-27 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44941 | Tower B - Sub Structure - B1 to GF - Pour 4 | Complete | RCC Works - Vertical | 2024-12-16 | 2024-12-27 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-12-16 | 2024-12-16 | 2024-12-27 | 2024-12-27 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
47657 |  | Complete |  | 2024-12-16 | 2025-01-02 | Slab_NTA | 100 | 100 |  | 2024-12-16 | 2024-12-16 | 2025-01-02 | 2025-01-02
47657 |  | Complete |  | 2024-12-16 | 2025-01-02 | Slab_NTA | 100 | 100 |  | 2024-12-16 | 2024-12-16 | 2025-01-02 | 2025-01-02 |  |  |  | RCC Sub Structure | RCC Works - Slab
9452 | T-16-Sub structure Columns | Complete | RCC | 2024-12-17 | 2025-03-28 | RCC | 35 | 35 | CUM | 2024-12-17 | 2024-12-17 | 2025-05-31 | 2025-06-02
9452 | T-16-Sub structure Columns | Complete | RCC | 2024-12-17 | 2025-03-28 | RCC | 35 | 35 | CUM | 2024-12-17 | 2024-12-17 | 2025-05-31 | 2025-06-02
11527 | T-18-Sub structure Retaining Wall | Stopped | Shuttering | 2024-12-17 | 2025-04-08 | Shuttering | 943.9 | 943.9 | Sqm | 2024-12-17 | 2024-12-17 | 2025-06-12
39565 |  | Complete |  | 2024-12-17 | 2024-12-26 | Core Wall L44-45 | 100 | 100 |  | 2024-12-17 | 2024-12-17 | 2024-12-26 | 2024-12-26
39566 | Tower A - Super Structure - Core Wall Low Rise L44-45 | Complete | Core Wall RCC Works | 2024-12-17 | 2024-12-17 | Scaffolding & platform | 100 | 100 |  | 2024-12-17 | 2024-12-17 | 2024-12-17 | 2024-12-17 | Tower A | Super Structure | L44 | RCC Super Structure | Core Wall RCC Works
40239 | Tower A - Super Structure - Finishes & MEP - L22 to L23 | Complete | Partition Wall-Blockwork | 2024-12-17 | 2024-12-26 | Partition Walls | 100 | 100 |  | 2024-12-17 | 2024-12-17 | 2024-12-26 | 2024-12-26 | Tower A | Super Structure | L22
44875 | Tower B - Sub Structure - B1 to GF | Complete | Core Wall RCC Works | 2024-12-17 | 2024-12-19 | CW Casting_lift 1 | 100 | 100 |  | 2024-12-17 | 2024-12-17 | 2024-12-19 | 2024-12-19 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44882 | Tower B - Sub Structure - B1 to GF - Pour 1A & 2 | Complete | RCC Works - Vertical | 2024-12-17 | 2024-12-28 | Col/ Wall Casting | 100 | 100 |  | 2024-12-17 | 2024-12-17 | 2024-12-28 | 2024-12-28 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44882 | Tower B - Sub Structure - B1 to GF - Pour 1A & 2 | Complete | RCC Works - Vertical | 2024-12-17 | 2024-12-28 | Col/ Wall Casting | 100 | 100 |  | 2024-12-17 | 2024-12-17 | 2024-12-28 | 2024-12-28 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44914 | Tower B - Sub Structure - B1 to GF - Pour 7 | Complete | RCC Works - Vertical | 2024-12-17 | 2024-12-19 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2024-12-17 | 2024-12-17 | 2024-12-19 | 2024-12-19 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44914 | Tower B - Sub Structure - B1 to GF - Pour 7 | Complete | RCC Works - Vertical | 2024-12-17 | 2024-12-19 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2024-12-17 | 2024-12-17 | 2024-12-19 | 2024-12-19 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
39567 | Tower A - Super Structure - Core Wall Low Rise L44-45 | Complete | Core Wall RCC Works | 2024-12-18 | 2024-12-20 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-12-18 | 2024-12-18 | 2024-12-20 | 2024-12-20 | Tower A | Super Structure | L44 | RCC Super Structure | Core Wall RCC Works
39922 | Tower A - Super Structure - Core & Outer Slab L39-40 | Complete | RCC Works - Slab | 2024-12-18 | 2024-12-22 | Outer Slab_TA | 100 | 100 |  | 2024-12-18 | 2024-12-18 | 2024-12-22 | 2024-12-22 | Tower A | Super Structure | L39 | RCC Sub Structure | RCC Works - Slab
44907 | Tower B - Sub Structure - B1 to GF - Pour 1B & 6 | Complete | RCC Works - Slab | 2024-12-18 | 2024-12-26 | Slab & Staircase Reinf. | 100 | 100 |  | 2024-12-18 | 2024-12-18 | 2024-12-26 | 2024-12-26 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
44942 | Tower B - Sub Structure - B1 to GF - Pour 4 | Complete | RCC Works - Vertical | 2024-12-18 | 2024-12-30 | Col/ Wall Casting | 100 | 100 |  | 2024-12-18 | 2024-12-18 | 2024-12-30 | 2024-12-30 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44942 | Tower B - Sub Structure - B1 to GF - Pour 4 | Complete | RCC Works - Vertical | 2024-12-18 | 2024-12-30 | Col/ Wall Casting | 100 | 100 |  | 2024-12-18 | 2024-12-18 | 2024-12-30 | 2024-12-30 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
9979 |  | Started |  | 2024-12-19 | 2025-06-12 | Grade Slab | 100 | 1 |  | 2024-12-19 | 2024-12-19 | 2025-08-04
9980 | T-21-Sub structure- Grade slab | Started | Grade Slab PCC | 2024-12-19 | 2025-04-03 | Grade Slab PCC | 212 | 2 | CUM | 2024-12-19 | 2024-12-19 | 2025-06-06
11528 | T-18-Sub structure Retaining Wall | Started | RCC | 2024-12-19 | 2025-04-08 | RCC | 94.4 | 94.4 | CUM | 2024-12-19 | 2024-12-19 | 2025-06-12
11528 | T-18-Sub structure Retaining Wall | Started | RCC | 2024-12-19 | 2025-04-08 | RCC | 94.4 | 94.4 | CUM | 2024-12-19 | 2024-12-19 | 2025-06-12
39568 | Tower A - Super Structure - Core Wall Low Rise L44-45 | Complete | Core Wall RCC Works | 2024-12-19 | 2024-12-21 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-12-19 | 2024-12-19 | 2024-12-21 | 2024-12-21 | Tower A | Super Structure | L44 | RCC Super Structure | Core Wall RCC Works
44915 | Tower B - Sub Structure - B1 to GF - Pour 7 | Complete | RCC Works - Vertical | 2024-12-19 | 2024-12-20 | Col/ Wall Casting | 100 | 100 |  | 2024-12-19 | 2024-12-19 | 2024-12-20 | 2024-12-20 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44915 | Tower B - Sub Structure - B1 to GF - Pour 7 | Complete | RCC Works - Vertical | 2024-12-19 | 2024-12-20 | Col/ Wall Casting | 100 | 100 |  | 2024-12-19 | 2024-12-19 | 2024-12-20 | 2024-12-20 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
10502 |  | Complete |  | 2024-12-20 | 2025-02-01 | Basement Roof/Podium Structure Works | 100 | 100 |  | 2024-12-20 | 2024-12-20 | 2025-02-01 | 2025-02-01
10503 |  | Complete |  | 2024-12-20 | 2025-02-01 | Part-1 | 100 | 100 |  | 2024-12-20 | 2024-12-20 | 2025-02-01 | 2025-02-01
10504 | T-20-Sub structure Basement Part 1 TA | Complete | Staging | 2024-12-20 | 2025-01-29 | Staging | 100 | 100 |  | 2024-12-20 | 2024-12-20 | 2025-01-29 | 2025-01-29
42452 |  | Started |  | 2024-12-20 | 2026-06-17 | L21-22 | 100 | 59 |  | 2024-12-20 | 2024-12-20 | 2026-06-15 |  |  |  |  | Finishes | Gypsum Plastering Works
42452 |  | Started |  | 2024-12-20 | 2026-06-17 | L21-22 | 100 | 59 |  | 2024-12-20 | 2024-12-20 | 2026-06-15
42453 |  | Started |  | 2024-12-20 | 2025-01-18 | MEP 1st Fixes | 100 | 64 |  | 2024-12-20 | 2024-12-20 | 2025-10-11
42454 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Apartment Area | Started | FPS 1st Fix - MEP & Finishes | 2024-12-20 | 2024-12-23 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 70 |  | 2024-12-20 | 2024-12-20 | 2025-09-13 |  | Tower A | Super Structure | L21 | MEP | FPS 1st Fix - MEP & Finishes
42455 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Apartment Area | Started | Electrical 1st Fix - MEP & Finishes | 2024-12-20 | 2024-12-20 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 90 |  | 2024-12-20 | 2024-12-20 | 2025-09-11 |  | Tower A | Super Structure | L21 | MEP | Electrical 1st Fixes
42456 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Apartment Area | Started | PHE 1st Fix - MEP & Finishes | 2024-12-20 | 2024-12-26 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 40 |  | 2024-12-20 | 2024-12-20 | 2025-09-16 |  | Tower A | Super Structure | L21
44876 | Tower B - Sub Structure - B1 to GF | Complete | Core Wall RCC Works | 2024-12-20 | 2024-12-28 | CW Reinf_lift 2 | 100 | 100 |  | 2024-12-20 | 2024-12-20 | 2024-12-28 | 2024-12-28 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
10505 | T-20-Sub structure Basement Part 1 TA | Complete | Formwork | 2024-12-21 | 2025-01-30 | Formwork | 100 | 100 | Sqm | 2024-12-21 | 2024-12-21 | 2025-01-30 | 2025-01-30
40297 |  | Complete |  | 2024-12-21 | 2025-06-05 | L37-38 | 100 | 100 |  | 2024-12-21 | 2024-12-21 | 2025-06-05 | 2025-07-10
40297 |  | Complete |  | 2024-12-21 | 2025-06-05 | L37-38 | 100 | 100 |  | 2024-12-21 | 2024-12-21 | 2025-06-05 | 2025-07-10 |  |  |  | Finishes | Gypsum Plastering Works
40298 | Tower A - Super Structure - Finishes & MEP - L37 to L38 | Complete | Partition Wall-Blockwork | 2024-12-21 | 2025-01-08 | De-shuttering & Area clearance | 100 | 100 |  | 2024-12-21 | 2024-12-21 | 2025-01-08 | 2025-01-08 | Tower A | Super Structure | L37
44916 | Tower B - Sub Structure - B1 to GF - Pour 7 | Complete | RCC Works - Slab | 2024-12-21 | 2025-01-04 | Slab & Staircase Fwk. | 100 | 100 |  | 2024-12-21 | 2024-12-21 | 2025-01-04 | 2025-01-04 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
39569 | Tower A - Super Structure - Core Wall Low Rise L44-45 | Complete | Core Wall RCC Works | 2024-12-23 | 2024-12-24 | Casting | 100 | 100 |  | 2024-12-23 | 2024-12-23 | 2024-12-24 | 2024-12-24 | Tower A | Super Structure | L44 | RCC Super Structure | Core Wall RCC Works
39923 |  | Complete |  | 2024-12-23 | 2024-12-30 | L40-41 | 100 | 100 |  | 2024-12-23 | 2024-12-23 | 2024-12-30 | 2024-12-30
39923 |  | Complete |  | 2024-12-23 | 2024-12-30 | L40-41 | 100 | 100 |  | 2024-12-23 | 2024-12-23 | 2024-12-30 | 2024-12-30 |  |  |  | Finishes | Gypsum Plastering Works
39924 | Tower A - Super Structure - Core & Outer Slab L40-41 | Complete | RCC Works - Vertical | 2024-12-23 | 2024-12-29 | Outer Columns_TA | 100 | 100 |  | 2024-12-23 | 2024-12-23 | 2024-12-29 | 2024-12-29 | Tower A | Super Structure | L40 | RCC Sub Structure | RCC Works - Vertical
44877 | Tower B - Sub Structure - B1 to GF | Complete | Core Wall RCC Works | 2024-12-23 | 2024-12-28 | CW Fwk (1.2m lift)_lift 2 | 100 | 100 |  | 2024-12-23 | 2024-12-23 | 2024-12-28 | 2024-12-28 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
11015 | T-19-Sub structure Shear Walls | Complete | Shuttering | 2024-12-24 | 2025-04-03 | Shuttering | 100 | 100 |  | 2024-12-24 | 2024-12-24 | 2025-02-06 | 2025-02-07
11533 |  | Quality checked |  | 2024-12-24 | 2025-04-01 | Shear Walls | 100 | 100 |  | 2024-12-24 | 2024-12-24 | 2025-04-01 | 2025-04-01
11534 | T-18-Sub structure Shear Walls | Quality checked | Reinforcement | 2024-12-24 | 2025-02-21 | Reinforcement | 100 | 100 |  | 2024-12-24 | 2024-12-24 | 2025-02-21 | 2025-02-21
39925 | Tower A - Super Structure - Core & Outer Slab L40-41 | Complete | RCC Works - Slab | 2024-12-24 | 2024-12-30 | Outer Slab_TA | 100 | 100 |  | 2024-12-24 | 2024-12-24 | 2024-12-30 | 2024-12-30 | Tower A | Super Structure | L40 | RCC Sub Structure | RCC Works - Slab
44927 | Tower B - Sub Structure - B1 to GF - Pour 8 | Complete | RCC Works - Slab | 2024-12-24 | 2024-12-28 | Slab & Staircase Reinf. | 100 | 100 |  | 2024-12-24 | 2024-12-24 | 2024-12-28 | 2024-12-28 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
8396 |  | Started |  | 2024-12-26 | 2025-03-22 | Part-2 - NTA | 100 | 2 |  | 2024-12-26 | 2024-12-26 | 2025-05-26
8397 | T-14-Sub structure Basement Part 2 NTA | Started | Staging | 2024-12-26 | 2025-03-22 | Staging | 100 | 2 |  | 2024-12-26 | 2024-12-26 | 2025-05-26
11016 | T-19-Sub structure Shear Walls | Complete | RCC | 2024-12-26 | 2025-04-03 | RCC | 208 | 208 | CUM | 2024-12-26 | 2024-12-26 | 2025-02-07 | 2025-02-08
11016 | T-19-Sub structure Shear Walls | Complete | RCC | 2024-12-26 | 2025-04-03 | RCC | 208 | 208 | CUM | 2024-12-26 | 2024-12-26 | 2025-02-07 | 2025-02-08
11540 | T-18-Sub structure- Grade slab | Forced Ready | Grade Slab PCC | 2025-03-06 | 2025-04-08 | Grade Slab PCC | 212 | 0 | CUM | 2024-12-26 |  | 2025-01-25
11555 |  | Started |  | 2024-12-26 | 2027-02-11 | Superstructure | 100 | 2 |  | 2024-12-26 | 2024-12-26 | 2026-12-07
11556 |  | Complete |  | 2024-12-26 | 2024-12-31 | Reciept of Aluminium Materials | 100 | 100 |  | 2024-12-26 | 2024-12-26 | 2024-12-31 | 2024-12-31
39570 | Tower A - Super Structure - Core Wall Low Rise L44-45 | Complete | Core Wall RCC Works | 2024-12-26 | 2024-12-26 | ACS Form Release & jump to next level | 100 | 100 |  | 2024-12-26 | 2024-12-26 | 2024-12-26 | 2024-12-26 | Tower A | Super Structure | L44 | RCC Super Structure | Core Wall RCC Works
40240 | Tower A - Super Structure - Finishes & MEP - L22 to L23 | Complete | Partition Wall-Blockwork | 2024-12-26 | 2025-01-01 | Staircase Area | 100 | 100 |  | 2024-12-26 | 2024-12-26 | 2025-01-01 | 2025-01-01 | Tower A | Super Structure | L22
40243 | Tower A - Super Structure - Finishes & MEP - L23 to L24 | Complete | Partition Wall-Blockwork | 2024-12-26 | 2025-01-03 | Partition Walls | 100 | 100 |  | 2024-12-26 | 2024-12-26 | 2025-01-03 | 2025-01-03 | Tower A | Super Structure | L23
8398 | T-14-Sub structure Basement Part 2 NTA | Started | Formwork | 2024-12-27 | 2025-03-22 | Formwork | 2200 | 2 | Sqm | 2024-12-27 | 2024-12-27 | 2025-05-26
9475 |  | Started |  | 2024-12-27 | 2027-02-06 | Superstructure | 100 | 3 |  | 2024-12-27 | 2024-12-27 | 2026-12-08
9476 |  | Complete |  | 2024-12-27 | 2024-12-31 | Reciept of Aluminium Materials | 100 | 100 |  | 2024-12-27 | 2024-12-27 | 2024-12-31 | 2024-12-31
39571 |  | Complete |  | 2024-12-27 | 2025-01-03 | Core Wall L45-46 | 100 | 100 |  | 2024-12-27 | 2024-12-27 | 2025-01-03 | 2025-01-03
39572 | Tower A - Super Structure - Core Wall Low Rise L45-46 | Complete | Core Wall RCC Works | 2024-12-27 | 2024-12-27 | Scaffolding & platform | 100 | 100 |  | 2024-12-27 | 2024-12-27 | 2024-12-27 | 2024-12-27 | Tower A | Super Structure | L45 | RCC Super Structure | Core Wall RCC Works
44886 | Tower B - Sub Structure - B1 to GF - Pour 1A & 2 | Complete | RCC Works - Slab | 2024-12-27 | 2025-01-07 | Slab & Staircase Fwk. | 100 | 100 |  | 2024-12-27 | 2024-12-27 | 2025-01-07 | 2025-01-07 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
44908 | Tower B - Sub Structure - B1 to GF - Pour 1B & 6 | Complete | RCC Works - Slab | 2024-12-27 | 2024-12-28 | Slab & Staircase Casting | 100 | 100 |  | 2024-12-27 | 2024-12-27 | 2024-12-28 | 2024-12-28 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
8395 | T-14-GF | Quality checked | Concrete | 2024-12-28 | 2024-12-29 | Concrete | 276 | 276 | CUM | 2024-12-28 | 2024-12-28 | 2024-12-29 | 2024-12-29
39573 | Tower A - Super Structure - Core Wall Low Rise L45-46 | Complete | Core Wall RCC Works | 2024-12-28 | 2024-12-31 | Reinf & Guide shoes fixing | 100 | 100 |  | 2024-12-28 | 2024-12-28 | 2024-12-31 | 2024-12-31 | Tower A | Super Structure | L45 | RCC Super Structure | Core Wall RCC Works
41187 |  | Started |  | 2024-12-28 | 2026-01-19 | L15-16 | 100 | 64 |  | 2024-12-28 | 2024-12-28 | 2026-02-10 |  |  |  |  | Finishes | Gypsum Plastering Works
41187 |  | Started |  | 2024-12-28 | 2026-01-19 | L15-16 | 100 | 64 |  | 2024-12-28 | 2024-12-28 | 2026-02-10
41188 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2024-12-28 | 2024-12-28 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 80 |  | 2024-12-28 | 2024-12-28 | 2025-12-30 |  | Tower A | Super Structure | L15 | MEP | FPS 1st Fix - MEP & Finishes
44889 |  | Complete |  | 2024-12-28 | 2025-01-28 | Pour 3_B1 to GF | 100 | 100 |  | 2024-12-28 | 2024-12-28 | 2025-01-28 | 2025-01-28
44891 | Tower B - Sub Structure - B1 to GF - Pour 3 | Complete | RCC Works - Vertical | 2024-12-28 | 2025-01-08 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-12-28 | 2024-12-28 | 2025-01-08 | 2025-01-08 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44891 | Tower B - Sub Structure - B1 to GF - Pour 3 | Complete | RCC Works - Vertical | 2024-12-28 | 2025-01-08 | Col/ Wall Fwk. (3.5m lift) | 100 | 100 |  | 2024-12-28 | 2024-12-28 | 2025-01-08 | 2025-01-08 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
8404 |  | Started |  | 2024-12-30 | 2025-12-11 | RCC Structure | 100 | 74 |  | 2024-12-30 | 2024-12-30 | 2025-12-13
8405 | T-14-1st Floor | Quality checked |  | 2024-12-30 | 2025-03-05 | Ground Floor Roof | 100 | 100 |  | 2024-12-30 | 2024-12-30 | 2025-03-05 | 2025-03-05
8406 | T-14-1st Floor | Quality checked | AL - Shear Walls/Corewalls Steel | 2024-12-30 | 2025-01-10 | AL - Shear Walls/Corewalls Steel | 100 | 100 | MT | 2024-12-30 | 2024-12-30 | 2025-01-10 | 2025-01-10
8942 |  | Started |  | 2024-12-30 | 2025-04-03 | Basement Roof/Podium Structure Works | 100 | 21 |  | 2024-12-30 | 2024-12-30 | 2025-06-06
8943 |  | Complete |  | 2024-12-30 | 2025-02-23 | Part-1 | 100 | 100 |  | 2024-12-30 | 2024-12-30 | 2025-02-23 | 2025-02-23
8944 | T-15-Sub structure Basement Part 1 TA | Complete | Staging | 2024-12-30 | 2025-01-14 | Staging | 100 | 100 |  | 2024-12-30 | 2024-12-30 | 2025-01-14 | 2025-01-14
39574 | Tower A - Super Structure - Core Wall Low Rise L45-46 | Complete | Core Wall RCC Works | 2024-12-30 | 2025-01-01 | ACS Form Closing & Alignment | 100 | 100 |  | 2024-12-30 | 2024-12-30 | 2025-01-01 | 2025-01-01 | Tower A | Super Structure | L45 | RCC Super Structure | Core Wall RCC Works
40495 | Tower A - Super Structure - Finishes & MEP - L21 to L22 | Started | Gypsum Plastering Works | 2024-12-30 | 2025-01-27 | L21-22 | 100 | 0 |  | 2024-12-30 | 2025-09-09 | 2025-10-11 |  | Tower A | Super Structure | L21 | Finishes | Gypsum Plastering Works
40495 | Tower A - Super Structure - Finishes & MEP - L21 to L22 | Started | Gypsum Plastering Works | 2024-12-30 | 2025-01-27 | L21-22 | 100 | 0 |  | 2024-12-30 | 2025-09-09 | 2025-10-11 |  | Tower A | Super Structure | L21
44878 | Tower B - Sub Structure - B1 to GF | Complete | Core Wall RCC Works | 2024-12-30 | 2025-01-01 | CW Casting_lift 2 | 100 | 100 |  | 2024-12-30 | 2024-12-30 | 2025-01-01 | 2025-01-01 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44883 | Tower B - Sub Structure - B1 to GF - Pour 1A & 2 | Complete | RCC Works - Vertical | 2024-12-30 | 2025-01-01 | Col/ Wall Reinf. | 100 | 100 |  | 2024-12-30 | 2024-12-30 | 2025-01-01 | 2025-01-01 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44883 | Tower B - Sub Structure - B1 to GF - Pour 1A & 2 | Complete | RCC Works - Vertical | 2024-12-30 | 2025-01-01 | Col/ Wall Reinf. | 100 | 100 |  | 2024-12-30 | 2024-12-30 | 2025-01-01 | 2025-01-01 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44928 | Tower B - Sub Structure - B1 to GF - Pour 8 | Complete | RCC Works - Slab | 2024-12-30 | 2024-12-31 | Slab & Staircase Casting | 100 | 100 |  | 2024-12-30 | 2024-12-30 | 2024-12-31 | 2024-12-31 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
8938 |  | Started | Backfilling | 2024-12-31 | 2025-05-12 | Backfilling | 100 | 2 |  | 2024-12-31 | 2024-12-31 | 2025-07-15
8945 | T-15-Sub structure Basement Part 1 TA | Complete | Formwork | 2024-12-31 | 2025-02-21 | Formwork | 100 | 100 | Sqm | 2024-12-31 | 2024-12-31 | 2025-02-21 | 2025-02-21
9458 |  | Started | Backfilling | 2024-12-31 | 2025-05-12 | Backfilling | 100 | 2 |  | 2024-12-31 | 2024-12-31 | 2025-07-15
39926 |  | Complete |  | 2024-12-31 | 2025-01-08 | L41-42 | 100 | 100 |  | 2024-12-31 | 2024-12-31 | 2025-01-08 | 2025-01-08
39926 |  | Complete |  | 2024-12-31 | 2025-01-08 | L41-42 | 100 | 100 |  | 2024-12-31 | 2024-12-31 | 2025-01-08 | 2025-01-08 |  |  |  | Finishes | Gypsum Plastering Works
39927 | Tower A - Super Structure - Core & Outer Slab L41-42 | Complete | RCC Works - Vertical | 2024-12-31 | 2025-01-06 | Outer Columns_TA | 100 | 100 |  | 2024-12-31 | 2024-12-31 | 2025-01-06 | 2025-01-06 | Tower A | Super Structure | L41 | RCC Sub Structure | RCC Works - Vertical
40301 |  | Complete |  | 2024-12-31 | 2025-06-14 | L38-39 | 100 | 100 |  | 2024-12-31 | 2024-12-31 | 2025-06-14 | 2025-07-15
40301 |  | Complete |  | 2024-12-31 | 2025-06-14 | L38-39 | 100 | 100 |  | 2024-12-31 | 2024-12-31 | 2025-06-14 | 2025-07-15 |  |  |  | Finishes | Gypsum Plastering Works
40302 | Tower A - Super Structure - Finishes & MEP - L38 to L39 | Complete | Partition Wall-Blockwork | 2024-12-31 | 2025-01-16 | De-shuttering & Area clearance | 100 | 100 |  | 2024-12-31 | 2024-12-31 | 2025-01-16 | 2025-01-16 | Tower A | Super Structure | L38
42434 |  | Started |  | 2024-12-31 | 2026-06-17 | L20-21 (Refuge) | 100 | 70 |  | 2024-12-31 | 2024-12-31 | 2026-06-15
42435 |  | Started |  | 2024-12-31 | 2025-01-24 | MEP 1st Fixes | 100 | 74 |  | 2024-12-31 | 2024-12-31 | 2025-09-22
42436 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Apartment Area | Started | FPS 1st Fix - MEP & Finishes | 2024-12-31 | 2025-01-01 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 80 |  | 2024-12-31 | 2024-12-31 | 2025-09-12 |  | Tower A | Super Structure | L20 | MEP | FPS 1st Fix - MEP & Finishes
42437 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Apartment Area | Started | Electrical 1st Fix - MEP & Finishes | 2024-12-31 | 2024-12-31 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 90 |  | 2024-12-31 | 2024-12-31 | 2025-09-11 |  | Tower A | Super Structure | L20 | MEP | Electrical 1st Fixes
42438 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Apartment Area | Started | PHE 1st Fix - MEP & Finishes | 2024-12-31 | 2025-01-01 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 80 |  | 2024-12-31 | 2024-12-31 | 2025-09-12 |  | Tower A | Super Structure | L20
42439 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Apartment Area | Started | Wet Area Waterproofing - MEP & Finishes | 2024-12-31 | 2025-01-01 | Wet Area Waterproofing | 100 | 90 |  | 2024-12-31 | 2024-12-31 | 2025-09-12 |  | Tower A | Super Structure | L20
44892 | Tower B - Sub Structure - B1 to GF - Pour 3 | Complete | RCC Works - Vertical | 2024-12-31 | 2025-01-10 | Col/ Wall Casting | 100 | 100 |  | 2024-12-31 | 2024-12-31 | 2025-01-10 | 2025-01-10 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44892 | Tower B - Sub Structure - B1 to GF - Pour 3 | Complete | RCC Works - Vertical | 2024-12-31 | 2025-01-10 | Col/ Wall Casting | 100 | 100 |  | 2024-12-31 | 2024-12-31 | 2025-01-10 | 2025-01-10 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44943 | Tower B - Sub Structure - B1 to GF - Pour 4 | Complete | RCC Works - Vertical | 2024-12-31 | 2025-01-02 | Col/ Wall Reinf. | 100 | 100 |  | 2024-12-31 | 2024-12-31 | 2025-01-02 | 2025-01-02 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44943 | Tower B - Sub Structure - B1 to GF - Pour 4 | Complete | RCC Works - Vertical | 2024-12-31 | 2025-01-02 | Col/ Wall Reinf. | 100 | 100 |  | 2024-12-31 | 2024-12-31 | 2025-01-02 | 2025-01-02 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
47654 |  | Complete |  | 2024-12-31 | 2024-12-31 | Slab_NTA | 100 | 100 |  | 2024-12-31 | 2024-12-31 | 2024-12-31 | 2024-12-31
47654 |  | Complete |  | 2024-12-31 | 2024-12-31 | Slab_NTA | 100 | 100 |  | 2024-12-31 | 2024-12-31 | 2024-12-31 | 2024-12-31 |  |  |  | RCC Sub Structure | RCC Works - Slab
47658 |  | Complete |  | 2024-12-31 | 2025-02-08 | Pour 11 (PB-E to PB-K) | 100 | 100 |  | 2024-12-31 | 2024-12-31 | 2025-02-08 | 2025-02-08
47659 |  | Complete |  | 2024-12-31 | 2025-01-10 | Columns/ Walls_NTA | 100 | 100 |  | 2024-12-31 | 2024-12-31 | 2025-01-10 | 2025-01-10
47659 |  | Complete |  | 2024-12-31 | 2025-01-10 | Columns/ Walls_NTA | 100 | 100 |  | 2024-12-31 | 2024-12-31 | 2025-01-10 | 2025-01-10 |  |  |  | RCC Sub Structure | RCC Works - Vertical
47664 |  | Started |  | 2025-01-01 | 2026-11-07 | B1 to GF | 100 | 32 |  | 2025-01-01 | 2025-01-01 | 2027-02-19
47664 |  | Started |  | 2025-01-01 | 2026-11-07 | B1 to GF | 100 | 32 |  | 2025-01-01 | 2025-01-01 | 2027-02-19
47664 |  | Started |  | 2025-01-01 | 2026-11-07 | B1 to GF | 100 | 32 |  | 2025-01-01 | 2025-01-01 | 2027-02-19
47696 |  | Complete |  | 2025-01-01 | 2026-10-07 | Pour 9 (grid PB-06 to PB-D) | 100 | 100 |  | 2025-01-01 | 2025-01-01 | 2026-10-07 | 2025-01-31
47697 |  | Complete |  | 2025-01-01 | 2025-01-23 | Columns/ Walls_NTA | 100 | 100 |  | 2025-01-01 | 2025-01-01 | 2025-01-23 | 2025-01-23
47697 |  | Complete |  | 2025-01-01 | 2025-01-23 | Columns/ Walls_NTA | 100 | 100 |  | 2025-01-01 | 2025-01-01 | 2025-01-23 | 2025-01-23 |  |  |  | RCC Sub Structure | RCC Works - Vertical
9987 | T-21-Sub structure Basement Part 1 TA | Complete | Conduiting | 2025-01-02 | 2025-01-07 | Conduiting | 100 | 100 |  | 2025-01-02 | 2025-01-02 | 2025-01-07 | 2025-01-07
10499 |  | Started |  | 2025-01-02 | 2025-04-30 | Grade Slab | 100 | 1 |  | 2025-01-02 | 2025-01-02 | 2025-06-12
10500 | T-20-Sub structure- Grade slab | Started | Grade Slab PCC | 2025-01-02 | 2025-04-03 | Grade Slab PCC | 212 | 2 | CUM | 2025-01-02 | 2025-01-02 | 2025-06-06
10506 | T-20-Sub structure Basement Part 1 TA | Complete | Reinforcement | 2025-01-02 | 2025-01-31 | Reinforcement | 28 | 28 | MT | 2025-01-02 | 2025-01-02 | 2025-01-31 | 2025-01-31
39166 |  | Started |  | 2025-01-02 | 2025-06-24 | Construction of DG Room and Cooling Tower Terrace | 100 | 79 |  | 2025-01-02 | 2025-01-02 | 2025-09-22
39167 |  | Complete |  | 2025-01-02 | 2025-01-13 | Excavation for Footing | 100 | 100 |  | 2025-01-02 | 2025-01-02 | 2025-01-13 | 2025-01-13
39575 | Tower A - Super Structure - Core Wall Low Rise L45-46 | Complete | Core Wall RCC Works | 2025-01-02 | 2025-01-02 | Casting | 100 | 100 |  | 2025-01-02 | 2025-01-02 | 2025-01-02 | 2025-01-02 | Tower A | Super Structure | L45 | RCC Super Structure | Core Wall RCC Works
39928 | Tower A - Super Structure - Core & Outer Slab L41-42 | Complete | RCC Works - Slab | 2025-01-02 | 2025-01-08 | Outer Slab_TA | 100 | 100 |  | 2025-01-02 | 2025-01-02 | 2025-01-08 | 2025-01-08 | Tower A | Super Structure | L41 | RCC Sub Structure | RCC Works - Slab
42470 |  | Started |  | 2025-01-02 | 2026-06-23 | L22-23 | 100 | 58 |  | 2025-01-02 | 2025-01-02 | 2026-06-20 |  |  |  |  | Finishes | Gypsum Plastering Works
42470 |  | Started |  | 2025-01-02 | 2026-06-23 | L22-23 | 100 | 58 |  | 2025-01-02 | 2025-01-02 | 2026-06-20
42471 |  | Started |  | 2025-01-02 | 2025-02-05 | MEP 1st Fixes | 100 | 62 |  | 2025-01-02 | 2025-01-02 | 2025-10-03
42472 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Apartment Area | Started | FPS 1st Fix - MEP & Finishes | 2025-01-02 | 2025-01-04 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 70 |  | 2025-01-02 | 2025-01-02 | 2025-09-13 |  | Tower A | Super Structure | L22 | MEP | FPS 1st Fix - MEP & Finishes
42473 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Apartment Area | Started | Electrical 1st Fix - MEP & Finishes | 2025-01-02 | 2025-01-02 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 90 |  | 2025-01-02 | 2025-01-02 | 2025-09-11 |  | Tower A | Super Structure | L22 | MEP | Electrical 1st Fixes
42474 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Apartment Area | Started | PHE 1st Fix - MEP & Finishes | 2025-01-02 | 2025-01-07 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 40 |  | 2025-01-02 | 2025-01-02 | 2025-09-16 |  | Tower A | Super Structure | L22
44884 | Tower B - Sub Structure - B1 to GF - Pour 1A & 2 | Complete | RCC Works - Vertical | 2025-01-02 | 2025-01-04 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2025-01-02 | 2025-01-02 | 2025-01-04 | 2025-01-04 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44884 | Tower B - Sub Structure - B1 to GF - Pour 1A & 2 | Complete | RCC Works - Vertical | 2025-01-02 | 2025-01-04 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2025-01-02 | 2025-01-02 | 2025-01-04 | 2025-01-04 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44890 | Tower B - Sub Structure - B1 to GF - Pour 3 | Complete | RCC Works - Vertical | 2025-01-02 | 2025-01-04 | Col/ Wall Reinf. | 100 | 100 |  | 2025-01-02 | 2025-01-02 | 2025-01-04 | 2025-01-04 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44890 | Tower B - Sub Structure - B1 to GF - Pour 3 | Complete | RCC Works - Vertical | 2025-01-02 | 2025-01-04 | Col/ Wall Reinf. | 100 | 100 |  | 2025-01-02 | 2025-01-02 | 2025-01-04 | 2025-01-04 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
8407 | T-14-1st Floor | Quality checked | Shear Walls/Corewalls Shuttering | 2025-01-03 | 2025-03-04 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-01-03 | 2025-01-03 | 2025-03-04 | 2025-03-04
39576 | Tower A - Super Structure - Core Wall Low Rise L45-46 | Complete | Core Wall RCC Works | 2025-01-03 | 2025-01-03 | ACS Form Release & jump to next level | 100 | 100 |  | 2025-01-03 | 2025-01-03 | 2025-01-03 | 2025-01-03 | Tower A | Super Structure | L45 | RCC Super Structure | Core Wall RCC Works
40244 | Tower A - Super Structure - Finishes & MEP - L23 to L24 | Complete | Partition Wall-Blockwork | 2025-01-03 | 2025-01-09 | Staircase Area | 100 | 100 |  | 2025-01-03 | 2025-01-03 | 2025-01-09 | 2025-01-09 | Tower A | Super Structure | L23
40247 | Tower A - Super Structure - Finishes & MEP - L24 to L25 | Complete | Partition Wall-Blockwork | 2025-01-03 | 2025-01-11 | Partition Walls | 100 | 100 |  | 2025-01-03 | 2025-01-03 | 2025-01-11 | 2025-01-11 | Tower A | Super Structure | L24
42422 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Apartment Area | Started | Cement Plastering in Wet Areas - MEP & Finishes | 2025-01-03 | 2025-01-10 | Cement Plastering in wet areas | 100 | 30 |  | 2025-01-03 | 2025-01-03 | 2025-09-22 |  | Tower A | Super Structure | L19
44944 | Tower B - Sub Structure - B1 to GF - Pour 4 | Complete | RCC Works - Vertical | 2025-01-03 | 2025-01-06 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2025-01-03 | 2025-01-03 | 2025-01-06 | 2025-01-06 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44944 | Tower B - Sub Structure - B1 to GF - Pour 4 | Complete | RCC Works - Vertical | 2025-01-03 | 2025-01-06 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2025-01-03 | 2025-01-03 | 2025-01-06 | 2025-01-06 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
47699 |  | Complete |  | 2025-01-03 | 2025-01-31 | Pour 10 (PB-K to PA-B / RT-08 to PB-06) | 100 | 100 |  | 2025-01-03 | 2025-01-03 | 2025-01-31 | 2025-01-31
47700 |  | Complete |  | 2025-01-03 | 2025-01-20 | Columns/ Walls_NTA | 100 | 100 |  | 2025-01-03 | 2025-01-03 | 2025-01-20 | 2025-01-20
47700 |  | Complete |  | 2025-01-03 | 2025-01-20 | Columns/ Walls_NTA | 100 | 100 |  | 2025-01-03 | 2025-01-03 | 2025-01-20 | 2025-01-20 |  |  |  | RCC Sub Structure | RCC Works - Vertical
9455 | T-16-Sub structure Shear Walls | Complete | Shuttering | 2025-01-04 | 2025-04-08 | Shuttering | 100 | 100 |  | 2025-01-04 | 2025-01-04 | 2025-03-12 | 2025-03-13
39577 |  | Complete |  | 2025-01-04 | 2025-01-13 | Core Wall L46-47 | 100 | 100 |  | 2025-01-04 | 2025-01-04 | 2025-01-13 | 2025-01-13
39578 | Tower A - Super Structure - Core Wall Low Rise L46-47 | Complete | Core Wall RCC Works | 2025-01-04 | 2025-01-04 | Scaffolding & platform | 100 | 100 |  | 2025-01-04 | 2025-01-04 | 2025-01-04 | 2025-01-04 | Tower A | Super Structure | L46 | RCC Super Structure | Core Wall RCC Works
44885 | Tower B - Sub Structure - B1 to GF - Pour 1A & 2 | Complete | RCC Works - Vertical | 2025-01-04 | 2025-01-06 | Col/ Wall Casting | 100 | 100 |  | 2025-01-04 | 2025-01-04 | 2025-01-06 | 2025-01-06 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44885 | Tower B - Sub Structure - B1 to GF - Pour 1A & 2 | Complete | RCC Works - Vertical | 2025-01-04 | 2025-01-06 | Col/ Wall Casting | 100 | 100 |  | 2025-01-04 | 2025-01-04 | 2025-01-06 | 2025-01-06 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
44917 | Tower B - Sub Structure - B1 to GF - Pour 7 | Complete | RCC Works - Slab | 2025-01-04 | 2025-01-08 | Slab & Staircase Reinf. | 100 | 100 |  | 2025-01-04 | 2025-01-04 | 2025-01-08 | 2025-01-08 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
48142 |  | Complete |  | 2025-01-04 | 2025-01-30 | Pour RT-4 | 100 | 100 |  | 2025-01-04 | 2025-01-04 | 2025-01-30 | 2025-01-30
48143 | Retail - Foundation P4 | Complete |  | 2025-01-04 | 2025-01-08 | Dressing & PCC | 100 | 100 |  | 2025-01-04 | 2025-01-04 | 2025-01-08 | 2025-01-08 | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48143 | Retail - Foundation P4 | Complete |  | 2025-01-04 | 2025-01-08 | Dressing & PCC | 100 | 100 |  | 2025-01-04 | 2025-01-04 | 2025-01-08 | 2025-01-08 | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48143 | Retail - Foundation P4 | Complete |  | 2025-01-04 | 2025-01-08 | Dressing & PCC | 100 | 100 |  | 2025-01-04 | 2025-01-04 | 2025-01-08 | 2025-01-08 | Retail | Foundation
8399 | T-14-Sub structure Basement Part 2 NTA | Started | Reinforcement | 2025-01-05 | 2025-03-22 | Reinforcement | 32 | 2 | MT | 2025-01-05 | 2025-01-05 | 2025-05-26
8409 | T-14-1st Floor | Quality checked | Shuttering | 2025-01-05 | 2025-03-02 | Slab and Beam Shuttering | 100 | 100 | Sqm | 2025-01-05 | 2025-01-05 | 2025-03-02 | 2025-03-02
9989 |  | Started |  | 2025-01-05 | 2025-03-14 | Part-2 - NTA | 100 | 92 |  | 2025-01-05 | 2025-01-05 | 2025-05-19
9990 | T-21-Sub structure Basement Part 2 NTA | Complete | Staging | 2025-01-05 | 2025-03-06 | Staging | 100 | 100 |  | 2025-01-05 | 2025-01-05 | 2025-05-10 | 2025-06-19
10509 |  | Complete |  | 2025-01-05 | 2025-01-31 | Part-2 | 100 | 100 |  | 2025-01-05 | 2025-01-05 | 2025-01-31 | 2025-01-31
10510 | T-20-Sub structure Basement Part 2 NTA | Complete | Staging | 2025-01-05 | 2025-01-15 | Staging | 100 | 100 |  | 2025-01-05 | 2025-01-05 | 2025-01-15 | 2025-01-15
41203 |  | Started |  | 2025-01-05 | 2026-01-24 | L16-17 | 100 | 64 |  | 2025-01-05 | 2025-01-05 | 2026-02-16 |  |  |  |  | Finishes | Gypsum Plastering Works
41203 |  | Started |  | 2025-01-05 | 2026-01-24 | L16-17 | 100 | 64 |  | 2025-01-05 | 2025-01-05 | 2026-02-16
41204 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2025-01-05 | 2025-01-06 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 80 |  | 2025-01-05 | 2025-01-05 | 2026-01-05 |  | Tower A | Super Structure | L16 | MEP | FPS 1st Fix - MEP & Finishes
9456 | T-16-Sub structure Shear Walls | Complete | RCC | 2025-01-06 | 2025-04-08 | RCC | 208 | 208 | CUM | 2025-01-06 | 2025-01-06 | 2025-03-13 | 2025-03-14
9456 | T-16-Sub structure Shear Walls | Complete | RCC | 2025-01-06 | 2025-04-08 | RCC | 208 | 208 | CUM | 2025-01-06 | 2025-01-06 | 2025-03-13 | 2025-03-14
39579 | Tower A - Super Structure - Core Wall Low Rise L46-47 | Complete | Core Wall RCC Works | 2025-01-06 | 2025-01-08 | Reinf & Guide shoes fixing | 100 | 100 |  | 2025-01-06 | 2025-01-06 | 2025-01-08 | 2025-01-08 | Tower A | Super Structure | L46 | RCC Super Structure | Core Wall RCC Works
44945 | Tower B - Sub Structure - B1 to GF - Pour 4 | Complete | RCC Works - Vertical | 2025-01-06 | 2025-01-07 | Col/ Wall Casting | 100 | 100 |  | 2025-01-06 | 2025-01-06 | 2025-01-07 | 2025-01-07 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44945 | Tower B - Sub Structure - B1 to GF - Pour 4 | Complete | RCC Works - Vertical | 2025-01-06 | 2025-01-07 | Col/ Wall Casting | 100 | 100 |  | 2025-01-06 | 2025-01-06 | 2025-01-07 | 2025-01-07 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
11017 | T-19-Sub structure Water proofing NTA | Not Ready |  | 2025-03-06 | 2025-04-30 | Water Proofing Outside-NTA | 100 | 0 |  | 2025-01-07 |  | 2025-01-19
39580 | Tower A - Super Structure - Core Wall Low Rise L46-47 | Complete | Core Wall RCC Works | 2025-01-07 | 2025-01-09 | ACS Form Closing & Alignment | 100 | 100 |  | 2025-01-07 | 2025-01-07 | 2025-01-09 | 2025-01-09 | Tower A | Super Structure | L46 | RCC Super Structure | Core Wall RCC Works
44887 | Tower B - Sub Structure - B1 to GF - Pour 1A & 2 | Complete | RCC Works - Slab | 2025-01-07 | 2025-01-08 | Slab & Staircase Reinf. | 100 | 100 |  | 2025-01-07 | 2025-01-07 | 2025-01-08 | 2025-01-08 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
10511 | T-20-Sub structure Basement Part 2 NTA | Complete | Formwork | 2025-01-08 | 2025-01-29 | Formwork | 946 | 946 | Sqm | 2025-01-08 | 2025-01-08 | 2025-01-29 | 2025-01-29
40494 | Tower A - Super Structure - Finishes & MEP - L20 to L21 | Started | Gypsum Plastering Works | 2025-01-08 | 2025-02-05 | L20-21 | 100 | 0 |  | 2025-01-08 | 2025-09-06 | 2025-10-11 |  | Tower A | Super Structure | L20 | Finishes | Gypsum Plastering Works
40494 | Tower A - Super Structure - Finishes & MEP - L20 to L21 | Started | Gypsum Plastering Works | 2025-01-08 | 2025-02-05 | L20-21 | 100 | 0 |  | 2025-01-08 | 2025-09-06 | 2025-10-11 |  | Tower A | Super Structure | L20
42475 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Apartment Area | Started | Wet Area Waterproofing - MEP & Finishes | 2025-01-08 | 2025-01-16 | Wet Area Waterproofing | 100 | 50 |  | 2025-01-08 | 2025-01-08 | 2025-09-20 |  | Tower A | Super Structure | L22
44946 | Tower B - Sub Structure - B1 to GF - Pour 4 | Complete | RCC Works - Slab | 2025-01-08 | 2025-01-18 | Slab & Staircase Fwk. | 100 | 100 |  | 2025-01-08 | 2025-01-08 | 2025-01-18 | 2025-01-18 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
48144 | Retail - Foundation P4 | Complete |  | 2025-01-08 | 2025-01-14 | Waterproofing Horizontal | 100 | 100 |  | 2025-01-08 | 2025-01-08 | 2025-01-14 | 2025-01-14 | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48144 | Retail - Foundation P4 | Complete |  | 2025-01-08 | 2025-01-14 | Waterproofing Horizontal | 100 | 100 |  | 2025-01-08 | 2025-01-08 | 2025-01-14 | 2025-01-14 | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48144 | Retail - Foundation P4 | Complete |  | 2025-01-08 | 2025-01-14 | Waterproofing Horizontal | 100 | 100 |  | 2025-01-08 | 2025-01-08 | 2025-01-14 | 2025-01-14 | Retail | Foundation
9988 | T-21-GF | Complete | Concrete | 2025-01-09 | 2025-01-09 | Concrete | 276 | 276 | CUM | 2025-01-09 | 2025-01-09 | 2025-01-09 | 2025-01-09
10507 | T-20-Sub structure Basement Part 1 TA | Complete | Conduiting | 2025-01-09 | 2025-01-30 | Conduiting | 100 | 100 |  | 2025-01-09 | 2025-01-09 | 2025-01-30 | 2025-01-30
39929 |  | Complete |  | 2025-01-09 | 2025-01-17 | L42-43 | 100 | 100 |  | 2025-01-09 | 2025-01-09 | 2025-01-17 | 2025-01-17
39929 |  | Complete |  | 2025-01-09 | 2025-01-17 | L42-43 | 100 | 100 |  | 2025-01-09 | 2025-01-09 | 2025-01-17 | 2025-01-17 |  |  |  | Finishes | Gypsum Plastering Works
39930 | Tower A - Super Structure - Core & Outer Slab L42-43 | Complete | RCC Works - Vertical | 2025-01-09 | 2025-01-15 | Outer Columns_TA | 100 | 100 |  | 2025-01-09 | 2025-01-09 | 2025-01-15 | 2025-01-15 | Tower A | Super Structure | L42 | RCC Sub Structure | RCC Works - Vertical
40305 |  | Complete |  | 2025-01-09 | 2025-06-23 | L39-40 | 100 | 100 |  | 2025-01-09 | 2025-01-09 | 2025-06-23 | 2025-08-12
40305 |  | Complete |  | 2025-01-09 | 2025-06-23 | L39-40 | 100 | 100 |  | 2025-01-09 | 2025-01-09 | 2025-06-23 | 2025-08-12 |  |  |  | Finishes | Gypsum Plastering Works
40306 | Tower A - Super Structure - Finishes & MEP - L39 to L40 | Complete | Partition Wall-Blockwork | 2025-01-09 | 2025-01-25 | De-shuttering & Area clearance | 100 | 100 |  | 2025-01-09 | 2025-01-09 | 2025-01-25 | 2025-01-25 | Tower A | Super Structure | L39
44888 | Tower B - Sub Structure - B1 to GF - Pour 1A & 2 | Complete | RCC Works - Slab | 2025-01-09 | 2025-01-09 | Slab & Staircase Casting | 100 | 100 |  | 2025-01-09 | 2025-01-09 | 2025-01-09 | 2025-01-09 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
44918 | Tower B - Sub Structure - B1 to GF - Pour 7 | Complete | RCC Works - Slab | 2025-01-09 | 2025-01-10 | Slab & Staircase Casting | 100 | 100 |  | 2025-01-09 | 2025-01-09 | 2025-01-10 | 2025-01-10 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
11537 | T-18-Sub structure Water proofing NTA | Not Ready |  | 2025-03-06 | 2025-04-30 | Water Proofing Outside-NTA | 100 | 0 |  | 2025-01-10 |  | 2025-03-04
39581 | Tower A - Super Structure - Core Wall Low Rise L46-47 | Complete | Core Wall RCC Works | 2025-01-10 | 2025-01-11 | Casting | 100 | 100 |  | 2025-01-10 | 2025-01-10 | 2025-01-11 | 2025-01-11 | Tower A | Super Structure | L46 | RCC Super Structure | Core Wall RCC Works
41219 |  | Started |  | 2025-01-10 | 2026-01-31 | L17-18 | 100 | 64 |  | 2025-01-10 | 2025-01-10 | 2026-02-21 |  |  |  |  | Finishes | Gypsum Plastering Works
41219 |  | Started |  | 2025-01-10 | 2026-01-31 | L17-18 | 100 | 64 |  | 2025-01-10 | 2025-01-10 | 2026-02-21
41220 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2025-01-10 | 2025-01-10 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 80 |  | 2025-01-10 | 2025-01-10 | 2026-01-10 |  | Tower A | Super Structure | L17 | MEP | FPS 1st Fix - MEP & Finishes
42488 |  | Started |  | 2025-01-10 | 2026-06-23 | L23-24 | 100 | 57 |  | 2025-01-10 | 2025-01-10 | 2026-06-20 |  |  |  |  | Finishes | Gypsum Plastering Works
42488 |  | Started |  | 2025-01-10 | 2026-06-23 | L23-24 | 100 | 57 |  | 2025-01-10 | 2025-01-10 | 2026-06-20
42489 |  | Started |  | 2025-01-10 | 2025-02-07 | MEP 1st Fixes | 100 | 61 |  | 2025-01-10 | 2025-01-10 | 2025-10-03
42490 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Apartment Area | Started | FPS 1st Fix - MEP & Finishes | 2025-01-10 | 2025-01-13 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 70 |  | 2025-01-10 | 2025-01-10 | 2025-09-13 |  | Tower A | Super Structure | L23 | MEP | FPS 1st Fix - MEP & Finishes
42491 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Apartment Area | Started | Electrical 1st Fix - MEP & Finishes | 2025-01-10 | 2025-01-10 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 90 |  | 2025-01-10 | 2025-01-10 | 2025-09-11 |  | Tower A | Super Structure | L23 | MEP | Electrical 1st Fixes
42492 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Apartment Area | Started | PHE 1st Fix - MEP & Finishes | 2025-01-10 | 2025-01-15 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 40 |  | 2025-01-10 | 2025-01-10 | 2025-09-16 |  | Tower A | Super Structure | L23
42493 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Apartment Area | Started | Wet Area Waterproofing - MEP & Finishes | 2025-01-10 | 2025-01-18 | Wet Area Waterproofing | 100 | 50 |  | 2025-01-10 | 2025-01-10 | 2025-09-20 |  | Tower A | Super Structure | L23
9991 | T-21-Sub structure Basement Part 2 NTA | Warning | Formwork | 2025-01-11 | 2025-03-06 | Formwork | 2120 | 1314.4 | Sqm | 2025-01-11 | 2025-01-11 | 2025-05-10
9997 |  | Started |  | 2025-01-11 | 2025-12-09 | RCC Structure | 100 | 72 |  | 2025-01-11 | 2025-01-11 | 2025-11-07
9998 | T-21-1st Floor | Complete |  | 2025-01-11 | 2025-03-24 | Ground Floor Roof | 100 | 100 |  | 2025-01-11 | 2025-01-11 | 2025-03-24 | 2025-03-24
9999 | T-21-1st Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-01-11 | 2025-01-31 | AL - Shear Walls/Corewalls Steel | 32 | 32 | MT | 2025-01-11 | 2025-01-11 | 2025-01-31 | 2025-01-31
39205 |  | Started |  | 2025-01-11 | 2025-01-28 | Low Side Installation - Cable Trays and Cable Laying (majorly B01) | 100 | 80 |  | 2025-01-11 | 2025-01-11 | 2025-09-26
39931 | Tower A - Super Structure - Core & Outer Slab L42-43 | Complete | RCC Works - Slab | 2025-01-11 | 2025-01-17 | Outer Slab_TA | 100 | 100 |  | 2025-01-11 | 2025-01-11 | 2025-01-17 | 2025-01-17 | Tower A | Super Structure | L42 | RCC Sub Structure | RCC Works - Slab
40248 | Tower A - Super Structure - Finishes & MEP - L24 to L25 | Complete | Partition Wall-Blockwork | 2025-01-11 | 2025-01-17 | Staircase Area | 100 | 100 |  | 2025-01-11 | 2025-01-11 | 2025-01-17 | 2025-01-17 | Tower A | Super Structure | L24
40251 | Tower A - Super Structure - Finishes & MEP - L25 to L26 | Complete | Partition Wall-Blockwork | 2025-01-11 | 2025-01-20 | Partition Walls | 100 | 100 |  | 2025-01-11 | 2025-01-11 | 2025-01-20 | 2025-01-20 | Tower A | Super Structure | L25
44893 | Tower B - Sub Structure - B1 to GF - Pour 3 | Complete | RCC Works - Vertical | 2025-01-11 | 2025-01-14 | Col/ Wall Reinf. | 100 | 100 |  | 2025-01-11 | 2025-01-11 | 2025-01-14 | 2025-01-14 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44893 | Tower B - Sub Structure - B1 to GF - Pour 3 | Complete | RCC Works - Vertical | 2025-01-11 | 2025-01-14 | Col/ Wall Reinf. | 100 | 100 |  | 2025-01-11 | 2025-01-11 | 2025-01-14 | 2025-01-14 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
8400 | T-14-Sub structure Basement Part 2 NTA | Started | Conduiting | 2025-01-13 | 2025-03-11 | Conduiting | 100 | 2 |  | 2025-01-13 | 2025-01-13 | 2025-05-15
39582 | Tower A - Super Structure - Core Wall Low Rise L46-47 | Complete | Core Wall RCC Works | 2025-01-13 | 2025-01-13 | ACS Form Release & jump to next level | 100 | 100 |  | 2025-01-13 | 2025-01-13 | 2025-01-13 | 2025-01-13 | Tower A | Super Structure | L46 | RCC Super Structure | Core Wall RCC Works
10000 | T-21-1st Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-01-14 | 2025-03-21 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-01-14 | 2025-01-14 | 2025-03-21 | 2025-03-21
11019 |  | Started |  | 2025-01-14 | 2025-07-07 | Grade Slab | 100 | 1 |  | 2025-01-14 | 2025-01-14 | 2025-08-07
11020 | T-19-Sub structure- Grade slab | Started | Grade Slab PCC | 2025-01-14 | 2025-04-08 | Grade Slab PCC | 212 | 2 | CUM | 2025-01-14 | 2025-01-14 | 2025-06-12
39168 |  | Complete |  | 2025-01-14 | 2025-01-30 | Footing for DG Room | 100 | 100 |  | 2025-01-14 | 2025-01-14 | 2025-01-30 | 2025-01-30
39583 |  | Complete |  | 2025-01-14 | 2025-01-21 | Core Wall L47-48 | 100 | 100 |  | 2025-01-14 | 2025-01-14 | 2025-01-21 | 2025-01-21
39584 | Tower A - Super Structure - Core Wall Low Rise L47-48 | Complete | Core Wall RCC Works | 2025-01-14 | 2025-01-14 | Scaffolding & platform | 100 | 100 |  | 2025-01-14 | 2025-01-14 | 2025-01-14 | 2025-01-14 | Tower A | Super Structure | L47 | RCC Super Structure | Core Wall RCC Works
48145 | Retail - Foundation P4 | Complete |  | 2025-01-14 | 2025-01-24 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2025-01-14 | 2025-01-14 | 2025-01-24 | 2025-01-24 | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48145 | Retail - Foundation P4 | Complete |  | 2025-01-14 | 2025-01-24 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2025-01-14 | 2025-01-14 | 2025-01-24 | 2025-01-24 | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48145 | Retail - Foundation P4 | Complete |  | 2025-01-14 | 2025-01-24 | Raft & Footing Reinf_NTA | 100 | 100 |  | 2025-01-14 | 2025-01-14 | 2025-01-24 | 2025-01-24 | Retail | Foundation
48149 | Retail - Foundation P5 | Complete |  | 2025-01-14 | 2025-01-17 | Liner Wall | 100 | 100 |  | 2025-01-14 | 2025-01-14 | 2025-01-17 | 2025-01-17 | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48149 | Retail - Foundation P5 | Complete |  | 2025-01-14 | 2025-01-17 | Liner Wall | 100 | 100 |  | 2025-01-14 | 2025-01-14 | 2025-01-17 | 2025-01-17 | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48149 | Retail - Foundation P5 | Complete |  | 2025-01-14 | 2025-01-17 | Liner Wall | 100 | 100 |  | 2025-01-14 | 2025-01-14 | 2025-01-17 | 2025-01-17 | Retail | Foundation
8946 | T-15-Sub structure Basement Part 1 TA | Complete | Reinforcement | 2025-01-15 | 2025-02-20 | Reinforcement | 28 | 28 | MT | 2025-01-15 | 2025-01-15 | 2025-02-20 | 2025-02-20
10512 | T-20-Sub structure Basement Part 2 NTA | Complete | Reinforcement | 2025-01-15 | 2025-01-30 | Reinforcement | 12 | 12 | MT | 2025-01-15 | 2025-01-15 | 2025-01-30 | 2025-01-30
39160 |  | Complete |  | 2025-01-15 | 2025-03-07 | Construction of Electrical Room at B1 level | 100 | 100 |  | 2025-01-15 | 2025-01-15 | 2025-03-07 | 2025-03-07
39161 |  | Complete |  | 2025-01-15 | 2025-01-31 | Blockwork for Transform Room | 100 | 100 |  | 2025-01-15 | 2025-01-15 | 2025-01-31 | 2025-01-31
39585 | Tower A - Super Structure - Core Wall Low Rise L47-48 | Complete | Core Wall RCC Works | 2025-01-15 | 2025-01-17 | Reinf & Guide shoes fixing | 100 | 100 |  | 2025-01-15 | 2025-01-15 | 2025-01-17 | 2025-01-17 | Tower A | Super Structure | L47 | RCC Super Structure | Core Wall RCC Works
44894 | Tower B - Sub Structure - B1 to GF - Pour 3 | Complete | RCC Works - Vertical | 2025-01-15 | 2025-01-17 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2025-01-15 | 2025-01-15 | 2025-01-17 | 2025-01-17 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44894 | Tower B - Sub Structure - B1 to GF - Pour 3 | Complete | RCC Works - Vertical | 2025-01-15 | 2025-01-17 | Col/ Wall Fwk. (1.2m lift) | 100 | 100 |  | 2025-01-15 | 2025-01-15 | 2025-01-17 | 2025-01-17 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
47701 |  | Complete |  | 2025-01-15 | 2025-01-31 | Slab_NTA | 100 | 100 |  | 2025-01-15 | 2025-01-15 | 2025-01-31 | 2025-01-31
47701 |  | Complete |  | 2025-01-15 | 2025-01-31 | Slab_NTA | 100 | 100 |  | 2025-01-15 | 2025-01-15 | 2025-01-31 | 2025-01-31 |  |  |  | RCC Sub Structure | RCC Works - Slab
47705 |  | Complete |  | 2025-01-15 | 2025-02-12 | Pour 12 (PB-A to PB-E) | 100 | 100 |  | 2025-01-15 | 2025-01-15 | 2025-02-12 | 2025-02-12
47706 |  | Complete |  | 2025-01-15 | 2025-01-31 | Columns/ Walls_NTA | 100 | 100 |  | 2025-01-15 | 2025-01-15 | 2025-01-31 | 2025-01-31
47706 |  | Complete |  | 2025-01-15 | 2025-01-31 | Columns/ Walls_NTA | 100 | 100 |  | 2025-01-15 | 2025-01-15 | 2025-01-31 | 2025-01-31 |  |  |  | RCC Sub Structure | RCC Works - Vertical
10001 | T-21-1st Floor | Complete | Conduiting | 2025-01-16 | 2025-03-22 | Conduiting works | 100 | 100 |  | 2025-01-16 | 2025-01-16 | 2025-03-22 | 2025-03-22
39586 | Tower A - Super Structure - Core Wall Low Rise L47-48 | Complete | Core Wall RCC Works | 2025-01-16 | 2025-01-18 | ACS Form Closing & Alignment | 100 | 100 |  | 2025-01-16 | 2025-01-16 | 2025-01-18 | 2025-01-18 | Tower A | Super Structure | L47 | RCC Super Structure | Core Wall RCC Works
10002 | T-21-1st Floor | Complete | Shuttering | 2025-01-17 | 2025-03-22 | Slab and Beam Shuttering | 100 | 100 | Sqm | 2025-01-17 | 2025-01-17 | 2025-03-22 | 2025-03-22
41235 |  | Started |  | 2025-01-17 | 2026-02-07 | L18-19 | 100 | 64 |  | 2025-01-17 | 2025-01-17 | 2026-02-28 |  |  |  |  | Finishes | Gypsum Plastering Works
41235 |  | Started |  | 2025-01-17 | 2026-02-07 | L18-19 | 100 | 64 |  | 2025-01-17 | 2025-01-17 | 2026-02-28
41236 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2025-01-17 | 2025-01-17 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 80 |  | 2025-01-17 | 2025-01-17 | 2026-01-17 |  | Tower A | Super Structure | L18 | MEP | FPS 1st Fix - MEP & Finishes
42440 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Apartment Area | Started | Cement Plastering in Wet Areas - MEP & Finishes | 2025-01-17 | 2025-01-24 | Cement Plastering in wet areas | 100 | 30 |  | 2025-01-17 | 2025-01-17 | 2025-09-22 |  | Tower A | Super Structure | L20
44895 | Tower B - Sub Structure - B1 to GF - Pour 3 | Complete | RCC Works - Vertical | 2025-01-17 | 2025-01-18 | Col/ Wall Casting | 100 | 100 |  | 2025-01-17 | 2025-01-17 | 2025-01-18 | 2025-01-18 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
44895 | Tower B - Sub Structure - B1 to GF - Pour 3 | Complete | RCC Works - Vertical | 2025-01-17 | 2025-01-18 | Col/ Wall Casting | 100 | 100 |  | 2025-01-17 | 2025-01-17 | 2025-01-18 | 2025-01-18 | Tower B | Sub Structure | B1 | RCC Super Structure | Core Wall RCC Works
47660 |  | Complete |  | 2025-01-17 | 2025-02-08 | Slab_NTA | 100 | 100 |  | 2025-01-17 | 2025-01-17 | 2025-02-08 | 2025-02-08
47660 |  | Complete |  | 2025-01-17 | 2025-02-08 | Slab_NTA | 100 | 100 |  | 2025-01-17 | 2025-01-17 | 2025-02-08 | 2025-02-08 |  |  |  | RCC Sub Structure | RCC Works - Slab
9992 | T-21-Sub structure Basement Part 2 NTA | Complete | Reinforcement | 2025-01-18 | 2025-03-06 | Reinforcement | 39.5 | 39.5 | MT | 2025-01-18 | 2025-01-18 | 2025-05-10 | 2025-06-19
39932 |  | Complete |  | 2025-01-18 | 2025-01-25 | L43-44 | 100 | 100 |  | 2025-01-18 | 2025-01-18 | 2025-01-25 | 2025-01-25
39932 |  | Complete |  | 2025-01-18 | 2025-01-25 | L43-44 | 100 | 100 |  | 2025-01-18 | 2025-01-18 | 2025-01-25 | 2025-01-25 |  |  |  | Finishes | Gypsum Plastering Works
39933 | Tower A - Super Structure - Core & Outer Slab L43-44 | Complete | RCC Works - Vertical | 2025-01-18 | 2025-01-24 | Outer Columns_TA | 100 | 100 |  | 2025-01-18 | 2025-01-18 | 2025-01-24 | 2025-01-24 | Tower A | Super Structure | L43 | RCC Sub Structure | RCC Works - Vertical
40309 |  | Complete |  | 2025-01-18 | 2025-07-01 | L40-41 | 100 | 100 |  | 2025-01-18 | 2025-01-18 | 2025-07-01 | 2025-08-12
40309 |  | Complete |  | 2025-01-18 | 2025-07-01 | L40-41 | 100 | 100 |  | 2025-01-18 | 2025-01-18 | 2025-07-01 | 2025-08-12 |  |  |  | Finishes | Gypsum Plastering Works
40310 | Tower A - Super Structure - Finishes & MEP - L40 to L41 | Complete | Partition Wall-Blockwork | 2025-01-18 | 2025-02-04 | De-shuttering & Area clearance | 100 | 100 |  | 2025-01-18 | 2025-01-18 | 2025-02-04 | 2025-02-04 | Tower A | Super Structure | L40
42506 |  | Started |  | 2025-01-18 | 2026-06-16 | L24-25 (MEP Transfer) | 100 | 38 |  | 2025-01-18 | 2025-01-18 | 2026-06-13
42507 |  | Started |  | 2025-01-18 | 2025-02-10 | MEP 1st Fixes | 100 | 41 |  | 2025-01-18 | 2025-01-18 | 2025-09-26
42508 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Apartment Area | Started | FPS 1st Fix - MEP & Finishes | 2025-01-18 | 2025-01-25 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 35 | Units | 2025-01-18 | 2025-04-15 | 2025-09-16 |  | Tower A | Super Structure | L24 | MEP | FPS 1st Fix - MEP & Finishes
42509 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Apartment Area | Started | Electrical 1st Fix - MEP & Finishes | 2025-01-18 | 2025-01-21 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 40 |  | 2025-01-18 | 2025-01-18 | 2025-09-13 |  | Tower A | Super Structure | L24 | MEP | Electrical 1st Fixes
42510 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Apartment Area | Started | PHE 1st Fix - MEP & Finishes | 2025-01-18 | 2025-01-23 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 40 |  | 2025-01-18 | 2025-01-18 | 2025-09-16 |  | Tower A | Super Structure | L24
42511 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Apartment Area | Started | Wet Area Waterproofing - MEP & Finishes | 2025-01-18 | 2025-01-27 | Wet Area Waterproofing | 100 | 50 |  | 2025-01-18 | 2025-01-18 | 2025-09-20 |  | Tower A | Super Structure | L24
44947 | Tower B - Sub Structure - B1 to GF - Pour 4 | Complete | RCC Works - Slab | 2025-01-18 | 2025-01-22 | Slab & Staircase Reinf. | 100 | 100 |  | 2025-01-18 | 2025-01-18 | 2025-01-22 | 2025-01-22 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
8401 | T-14-Sub structure Basement Part 2 NTA | Started | Concrete | 2025-01-19 | 2025-03-12 | Concrete | 495 | 2 | CUM | 2025-01-19 | 2025-01-19 | 2025-05-16
8408 | T-14-1st Floor | Quality checked | Conduiting | 2025-01-20 | 2025-03-03 | Conduiting works | 100 | 100 |  | 2025-01-20 | 2025-01-20 | 2025-03-03 | 2025-03-03
8939 |  | Started |  | 2025-01-20 | 2025-06-24 | Grade Slab | 100 | 1 |  | 2025-01-20 | 2025-01-20 | 2025-08-16
8940 | T-15-Sub structure- Grade slab | Started | Grade Slab PCC | 2025-01-20 | 2025-04-03 | Grade Slab PCC | 212 | 2 | CUM | 2025-01-20 | 2025-01-20 | 2025-06-06
39587 | Tower A - Super Structure - Core Wall Low Rise L47-48 | Complete | Core Wall RCC Works | 2025-01-20 | 2025-01-20 | Casting | 100 | 100 |  | 2025-01-20 | 2025-01-20 | 2025-01-20 | 2025-01-20 | Tower A | Super Structure | L47 | RCC Super Structure | Core Wall RCC Works
40252 | Tower A - Super Structure - Finishes & MEP - L25 to L26 | Complete | Partition Wall-Blockwork | 2025-01-20 | 2025-01-25 | Staircase Area | 100 | 100 |  | 2025-01-20 | 2025-01-20 | 2025-01-25 | 2025-01-25 | Tower A | Super Structure | L25
40255 | Tower A - Super Structure - Finishes & MEP - L26 to L27 | Complete | Partition Wall-Blockwork | 2025-01-20 | 2025-01-28 | Partition Walls | 100 | 100 |  | 2025-01-20 | 2025-01-20 | 2025-01-28 | 2025-01-28 | Tower A | Super Structure | L26
44896 | Tower B - Sub Structure - B1 to GF - Pour 3 | Complete | RCC Works - Slab | 2025-01-20 | 2025-01-21 | Slab & Staircase Fwk. | 100 | 100 |  | 2025-01-20 | 2025-01-20 | 2025-01-21 | 2025-01-21 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
47951 |  | Started |  | 2021-04-01 | 2027-07-22 | Award of Contract | 100 | 9 |  | 2025-01-20 | 2025-01-20 | 2027-07-23
47953 | Tower B | Started | Award of Packages | 2025-01-20 | 2025-05-05 | Façade Package | 100 | 50 |  | 2025-01-20 | 2025-01-20 | 2025-12-24 |  | Tower B | --
48150 | Retail - Foundation P5 | Complete |  | 2025-01-20 | 2025-01-25 | Waterproofing Horizontal | 100 | 100 |  | 2025-01-20 | 2025-01-20 | 2025-01-25 | 2025-01-25 | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48150 | Retail - Foundation P5 | Complete |  | 2025-01-20 | 2025-01-25 | Waterproofing Horizontal | 100 | 100 |  | 2025-01-20 | 2025-01-20 | 2025-01-25 | 2025-01-25 | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48150 | Retail - Foundation P5 | Complete |  | 2025-01-20 | 2025-01-25 | Waterproofing Horizontal | 100 | 100 |  | 2025-01-20 | 2025-01-20 | 2025-01-25 | 2025-01-25 | Retail | Foundation
8949 |  | Started |  | 2025-01-21 | 2025-04-03 | Part-2 | 100 | 2 |  | 2025-01-21 | 2025-01-21 | 2025-06-06
8950 | T-15-Sub structure Basement Part 2 NTA | Started | Staging | 2025-01-21 | 2025-04-03 | Staging | 100 | 2 |  | 2025-01-21 | 2025-01-21 | 2025-06-06
39588 | Tower A - Super Structure - Core Wall Low Rise L47-48 | Complete | Core Wall RCC Works | 2025-01-21 | 2025-01-21 | ACS Form Release & jump to next level | 100 | 100 |  | 2025-01-21 | 2025-01-21 | 2025-01-21 | 2025-01-21 | Tower A | Super Structure | L47 | RCC Super Structure | Core Wall RCC Works
39934 | Tower A - Super Structure - Core & Outer Slab L43-44 | Complete | RCC Works - Slab | 2025-01-21 | 2025-01-25 | Outer Slab_TA | 100 | 100 |  | 2025-01-21 | 2025-01-21 | 2025-01-25 | 2025-01-25 | Tower A | Super Structure | L43 | RCC Sub Structure | RCC Works - Slab
39589 |  | Complete |  | 2025-01-22 | 2025-02-03 | Core Wall L48-49 | 100 | 100 |  | 2025-01-22 | 2025-01-22 | 2025-02-03 | 2025-02-03
39590 | Tower A - Super Structure - Core Wall Low Rise L48-49 | Complete | Core Wall RCC Works | 2025-01-22 | 2025-01-22 | Scaffolding & platform | 100 | 100 |  | 2025-01-22 | 2025-01-22 | 2025-01-22 | 2025-01-22 | Tower A | Super Structure | L48 | RCC Super Structure | Core Wall RCC Works
44897 | Tower B - Sub Structure - B1 to GF - Pour 3 | Complete | RCC Works - Slab | 2025-01-22 | 2025-01-25 | Slab & Staircase Reinf. | 100 | 100 |  | 2025-01-22 | 2025-01-22 | 2025-01-25 | 2025-01-25 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
39591 | Tower A - Super Structure - Core Wall Low Rise L48-49 | Complete | Core Wall RCC Works | 2025-01-23 | 2025-01-25 | Reinf & Guide shoes fixing | 100 | 100 |  | 2025-01-23 | 2025-01-23 | 2025-01-25 | 2025-01-25 | Tower A | Super Structure | L48 | RCC Super Structure | Core Wall RCC Works
44948 | Tower B - Sub Structure - B1 to GF - Pour 4 | Complete | RCC Works - Slab | 2025-01-23 | 2025-01-24 | Slab & Staircase Casting | 100 | 100 |  | 2025-01-23 | 2025-01-23 | 2025-01-24 | 2025-01-24 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
8410 | T-14-1st Floor | Quality checked | Slab& Beam Steel & Conduting | 2025-01-24 | 2025-03-02 | Slab& Beam Steel & Conduting | 100 | 100 | MT | 2025-01-24 | 2025-01-24 | 2025-03-02 | 2025-03-02
8951 | T-15-Sub structure Basement Part 2 NTA | Started | Formwork | 2025-01-24 | 2025-04-03 | Formwork | 2225 | 2 | Sqm | 2025-01-24 | 2025-01-24 | 2025-06-06
39592 | Tower A - Super Structure - Core Wall Low Rise L48-49 | Complete | Core Wall RCC Works | 2025-01-24 | 2025-01-27 | ACS Form Closing & Alignment | 100 | 100 |  | 2025-01-24 | 2025-01-24 | 2025-01-27 | 2025-01-27 | Tower A | Super Structure | L48 | RCC Super Structure | Core Wall RCC Works
41251 |  | Started |  | 2025-01-24 | 2026-02-14 | L19-20 | 100 | 64 |  | 2025-01-24 | 2025-01-24 | 2026-03-09 |  |  |  |  | Finishes | Gypsum Plastering Works
41251 |  | Started |  | 2025-01-24 | 2026-02-14 | L19-20 | 100 | 64 |  | 2025-01-24 | 2025-01-24 | 2026-03-09
41252 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2025-01-24 | 2025-01-24 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 80 |  | 2025-01-24 | 2025-01-24 | 2026-01-24 |  | Tower A | Super Structure | L19 | MEP | FPS 1st Fix - MEP & Finishes
8947 | T-15-Sub structure Basement Part 1 TA | Complete | Conduiting | 2025-01-25 | 2025-02-20 | Conduiting | 100 | 100 |  | 2025-01-25 | 2025-01-25 | 2025-02-20 | 2025-02-20
9993 | T-21-Sub structure Basement Part 2 NTA | Complete | Conduiting | 2025-01-25 | 2025-03-12 | Conduiting | 100 | 100 |  | 2025-01-25 | 2025-01-25 | 2025-05-16 | 2025-06-19
10513 | T-20-Sub structure Basement Part 2 NTA | Complete | Conduiting | 2025-01-25 | 2025-01-30 | Conduiting | 100 | 100 |  | 2025-01-25 | 2025-01-25 | 2025-01-30 | 2025-01-30
48146 | Retail - Foundation P4 | Complete |  | 2025-01-25 | 2025-01-30 | Fwk & Casting_NTA | 100 | 100 |  | 2025-01-25 | 2025-01-25 | 2025-01-30 | 2025-01-30 | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48146 | Retail - Foundation P4 | Complete |  | 2025-01-25 | 2025-01-30 | Fwk & Casting_NTA | 100 | 100 |  | 2025-01-25 | 2025-01-25 | 2025-01-30 | 2025-01-30 | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48146 | Retail - Foundation P4 | Complete |  | 2025-01-25 | 2025-01-30 | Fwk & Casting_NTA | 100 | 100 |  | 2025-01-25 | 2025-01-25 | 2025-01-30 | 2025-01-30 | Retail | Foundation
48356 |  | Complete |  | 2025-01-25 | 2025-02-18 | Pour RT-5 | 100 | 100 |  | 2025-01-25 | 2025-01-25 | 2025-02-18 | 2025-02-18
48357 | Retail - Sub structure - B3 to B2 - P5 | Complete |  | 2025-01-25 | 2025-02-01 | Section 10_lift 1 | 100 | 100 |  | 2025-01-25 | 2025-01-25 | 2025-02-01 | 2025-02-01 | Retail | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
48357 | Retail - Sub structure - B3 to B2 - P5 | Complete |  | 2025-01-25 | 2025-02-01 | Section 10_lift 1 | 100 | 100 |  | 2025-01-25 | 2025-01-25 | 2025-02-01 | 2025-02-01 | Retail | Sub Structure | B3
48358 | Retail - Sub structure - B3 to B2 - P5 | Complete |  | 2025-01-25 | 2025-02-01 | Section 11_lift 1 | 100 | 100 |  | 2025-01-25 | 2025-01-25 | 2025-02-01 | 2025-02-01 | Retail | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
48358 | Retail - Sub structure - B3 to B2 - P5 | Complete |  | 2025-01-25 | 2025-02-01 | Section 11_lift 1 | 100 | 100 |  | 2025-01-25 | 2025-01-25 | 2025-02-01 | 2025-02-01 | Retail | Sub Structure | B3
39935 |  | Complete |  | 2025-01-27 | 2025-02-03 | L44-45 | 100 | 100 |  | 2025-01-27 | 2025-01-27 | 2025-02-03 | 2025-02-03
39935 |  | Complete |  | 2025-01-27 | 2025-02-03 | L44-45 | 100 | 100 |  | 2025-01-27 | 2025-01-27 | 2025-02-03 | 2025-02-03 |  |  |  | Finishes | Gypsum Plastering Works
39936 | Tower A - Super Structure - Core & Outer Slab L44-45 | Complete | RCC Works - Vertical | 2025-01-27 | 2025-02-01 | Outer Columns_TA | 100 | 100 |  | 2025-01-27 | 2025-01-27 | 2025-02-01 | 2025-02-01 | Tower A | Super Structure | L44 | RCC Sub Structure | RCC Works - Vertical
40317 |  | Complete |  | 2025-01-27 | 2025-07-09 | L41-42 | 100 | 100 |  | 2025-01-27 | 2025-01-27 | 2025-07-09 | 2025-08-09
40317 |  | Complete |  | 2025-01-27 | 2025-07-09 | L41-42 | 100 | 100 |  | 2025-01-27 | 2025-01-27 | 2025-07-09 | 2025-08-09 |  |  |  | Finishes | Gypsum Plastering Works
40318 | Tower A - Super Structure - Finishes & MEP - L41 to L42 | Complete | Partition Wall-Blockwork | 2025-01-27 | 2025-02-12 | De-shuttering & Area clearance | 100 | 100 |  | 2025-01-27 | 2025-01-27 | 2025-02-12 | 2025-02-12 | Tower A | Super Structure | L41
42524 |  | Started |  | 2025-01-27 | 2026-06-29 | L25-26 | 100 | 49 |  | 2025-01-27 | 2025-01-27 | 2026-06-26 |  |  |  |  | Finishes | Gypsum Plastering Works
42524 |  | Started |  | 2025-01-27 | 2026-06-29 | L25-26 | 100 | 49 |  | 2025-01-27 | 2025-01-27 | 2026-06-26
42525 |  | Started |  | 2025-01-27 | 2025-02-14 | MEP 1st Fixes | 100 | 53 |  | 2025-01-27 | 2025-01-27 | 2025-09-29
42526 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Apartment Area | Started | FPS 1st Fix - MEP & Finishes | 2025-01-27 | 2025-02-03 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 35 | Units | 2025-01-27 | 2025-04-21 | 2025-09-16 |  | Tower A | Super Structure | L25 | MEP | FPS 1st Fix - MEP & Finishes
42527 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Apartment Area | Started | Electrical 1st Fix - MEP & Finishes | 2025-01-27 | 2025-01-27 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 90 |  | 2025-01-27 | 2025-01-27 | 2025-09-11 |  | Tower A | Super Structure | L25 | MEP | Electrical 1st Fixes
42528 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Apartment Area | Started | PHE 1st Fix - MEP & Finishes | 2025-01-27 | 2025-01-31 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 40 |  | 2025-01-27 | 2025-01-27 | 2025-09-16 |  | Tower A | Super Structure | L25
42529 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Apartment Area | Started | Wet Area Waterproofing - MEP & Finishes | 2025-01-27 | 2025-02-04 | Wet Area Waterproofing | 100 | 50 |  | 2025-01-27 | 2025-01-27 | 2025-09-20 |  | Tower A | Super Structure | L25
47707 |  | Complete |  | 2025-01-27 | 2025-02-12 | Slab_NTA | 100 | 100 |  | 2025-01-27 | 2025-01-27 | 2025-02-12 | 2025-02-12
47707 |  | Complete |  | 2025-01-27 | 2025-02-12 | Slab_NTA | 100 | 100 |  | 2025-01-27 | 2025-01-27 | 2025-02-12 | 2025-02-12 |  |  |  | RCC Sub Structure | RCC Works - Slab
39593 | Tower A - Super Structure - Core Wall Low Rise L48-49 | Complete | Core Wall RCC Works | 2025-01-28 | 2025-02-01 | Casting | 100 | 100 |  | 2025-01-28 | 2025-01-28 | 2025-02-01 | 2025-02-01 | Tower A | Super Structure | L48 | RCC Super Structure | Core Wall RCC Works
40256 | Tower A - Super Structure - Finishes & MEP - L26 to L27 | Complete | Partition Wall-Blockwork | 2025-01-28 | 2025-02-03 | Staircase Area | 100 | 100 |  | 2025-01-28 | 2025-01-28 | 2025-02-03 | 2025-02-03 | Tower A | Super Structure | L26
44898 | Tower B - Sub Structure - B1 to GF - Pour 3 | Complete | RCC Works - Slab | 2025-01-28 | 2025-01-28 | Slab & Staircase Casting | 100 | 100 |  | 2025-01-28 | 2025-01-28 | 2025-01-28 | 2025-01-28 | Tower B | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
9994 | T-21-Sub structure Basement Part 2 NTA | Complete | Concrete | 2025-01-29 | 2025-03-14 | Concrete | 477 | 477 | CUM | 2025-01-29 | 2025-01-29 | 2025-05-19 | 2025-06-19
39937 | Tower A - Super Structure - Core & Outer Slab L44-45 | Complete | RCC Works - Slab | 2025-01-29 | 2025-02-03 | Outer Slab_TA | 100 | 100 |  | 2025-01-29 | 2025-01-29 | 2025-02-03 | 2025-02-03 | Tower A | Super Structure | L44 | RCC Sub Structure | RCC Works - Slab
40259 | Tower A - Super Structure - Finishes & MEP - L27 to L28 | Complete | Partition Wall-Blockwork | 2025-01-29 | 2025-02-05 | Partition Walls | 100 | 100 |  | 2025-01-29 | 2025-01-29 | 2025-02-05 | 2025-02-05 | Tower A | Super Structure | L27
44762 |  | Complete |  | 2025-01-29 | 2025-02-18 | Plinth Checking (30 calendar days) | 100 | 100 |  | 2025-01-29 | 2025-01-29 | 2025-02-18 | 2025-02-18
44762 |  | Complete |  | 2025-01-29 | 2025-02-18 | Plinth Checking (30 calendar days) | 100 | 100 |  | 2025-01-29 | 2025-01-29 | 2025-02-18 | 2025-02-18
11022 |  | Started |  | 2025-01-30 | 2025-04-09 | Basement Roof/Podium Structure Works | 100 | 44 |  | 2025-01-30 | 2025-01-30 | 2025-05-31
11023 |  | Complete |  | 2025-01-30 | 2025-03-26 | Part-1 | 100 | 100 |  | 2025-01-30 | 2025-01-30 | 2025-03-26 | 2025-03-26
11024 | T-19-Sub structure Basement Part 1 TA | Complete | Staging | 2025-01-30 | 2025-02-15 | Staging | 100 | 100 |  | 2025-01-30 | 2025-01-30 | 2025-02-15 | 2025-02-15
10508 | T-20-GF | Complete | Concrete | 2025-01-31 | 2025-02-01 | Concrete | 276 | 276 | CUM | 2025-01-31 | 2025-01-31 | 2025-02-01 | 2025-02-01
10514 | T-20-Sub structure Basement Part 2 NTA | Complete | Concrete | 2025-01-31 | 2025-01-31 | Concrete | 118 | 118 | CUM | 2025-01-31 | 2025-01-31 | 2025-01-31 | 2025-01-31
11025 | T-19-Sub structure Basement Part 1 TA | Complete | Formwork | 2025-01-31 | 2025-03-25 | Formwork | 100 | 100 | Sqm | 2025-01-31 | 2025-01-31 | 2025-03-25 | 2025-03-25
39169 |  | Complete |  | 2025-01-31 | 2025-02-17 | Columns for DG Room | 100 | 100 |  | 2025-01-31 | 2025-01-31 | 2025-02-17 | 2025-02-17
41267 |  | Started |  | 2025-01-31 | 2026-02-21 | L20-21 | 100 | 52 |  | 2025-01-31 | 2025-01-31 | 2026-03-16 |  |  |  |  | Finishes | Gypsum Plastering Works
41267 |  | Started |  | 2025-01-31 | 2026-02-21 | L20-21 | 100 | 52 |  | 2025-01-31 | 2025-01-31 | 2026-03-16
41268 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2025-01-31 | 2025-02-01 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 65 |  | 2025-01-31 | 2025-01-31 | 2026-02-02 |  | Tower A | Super Structure | L20 | MEP | FPS 1st Fix - MEP & Finishes
48385 |  | Started |  | 2025-01-31 | 2025-02-12 | Pour RT-2 | 100 | 53 |  | 2025-01-31 | 2025-01-31 | 2025-10-04
48386 | Retail - Sub structure - B2 to B1 - P2 | Complete |  | 2025-01-31 | 2025-02-07 | Section 5_lift 1 | 100 | 100 |  | 2025-01-31 | 2025-01-31 | 2025-02-07 | 2025-02-07 | Retail | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
48386 | Retail - Sub structure - B2 to B1 - P2 | Complete |  | 2025-01-31 | 2025-02-07 | Section 5_lift 1 | 100 | 100 |  | 2025-01-31 | 2025-01-31 | 2025-02-07 | 2025-02-07 | Retail | Sub Structure | B2
48387 | Retail - Sub structure - B2 to B1 - P2 | Complete |  | 2025-01-31 | 2025-02-07 | Section 6_lift 1 | 100 | 100 |  | 2025-01-31 | 2025-01-31 | 2025-02-07 | 2025-02-07 | Retail | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
48387 | Retail - Sub structure - B2 to B1 - P2 | Complete |  | 2025-01-31 | 2025-02-07 | Section 6_lift 1 | 100 | 100 |  | 2025-01-31 | 2025-01-31 | 2025-02-07 | 2025-02-07 | Retail | Sub Structure | B2
39162 |  | Complete |  | 2025-02-01 | 2025-02-04 | Pedestals for Panels | 100 | 100 |  | 2025-02-01 | 2025-02-01 | 2025-02-04 | 2025-02-04
10517 |  | Started |  | 2025-02-03 | 2025-12-20 | RCC Structure | 100 | 66 |  | 2025-02-03 | 2025-02-03 | 2025-11-15
10518 | T-20-1st Floor | Complete |  | 2025-02-03 | 2025-03-29 | Ground Floor Roof | 100 | 100 |  | 2025-02-03 | 2025-02-03 | 2025-03-29 | 2025-03-29
10519 | T-20-1st Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-02-03 | 2025-02-13 | AL - Shear Walls/Corewalls Steel | 32 | 32 | MT | 2025-02-03 | 2025-02-03 | 2025-02-13 | 2025-02-13
39594 | Tower A - Super Structure - Core Wall Low Rise L48-49 | Complete | Core Wall RCC Works | 2025-02-03 | 2025-02-03 | ACS Form Release & jump to next level | 100 | 100 |  | 2025-02-03 | 2025-02-03 | 2025-02-03 | 2025-02-03 | Tower A | Super Structure | L48 | RCC Super Structure | Core Wall RCC Works
48359 | Retail - Sub structure - B3 to B2 - P5 | Complete |  | 2025-02-03 | 2025-02-10 | Section 12_lift 1 | 100 | 100 |  | 2025-02-03 | 2025-02-03 | 2025-02-10 | 2025-02-10 | Retail | Sub Structure | B3
48360 | Retail - Sub structure - B3 to B2 - P5 | Complete |  | 2025-02-03 | 2025-02-10 | Section 13_lift 1 | 100 | 100 |  | 2025-02-03 | 2025-02-03 | 2025-02-10 | 2025-02-10 | Retail | Sub Structure | B3
39595 |  | Complete |  | 2025-02-04 | 2025-02-12 | Core Wall L49-50 | 100 | 100 |  | 2025-02-04 | 2025-02-04 | 2025-02-12 | 2025-02-12
39596 | Tower A - Super Structure - Core Wall Low Rise L49-50 | Complete | Core Wall RCC Works | 2025-02-04 | 2025-02-04 | Scaffolding & platform | 100 | 100 |  | 2025-02-04 | 2025-02-04 | 2025-02-04 | 2025-02-04 | Tower A | Super Structure | L49 | RCC Super Structure | Core Wall RCC Works
39938 |  | Complete |  | 2025-02-04 | 2025-02-12 | L45-46 | 100 | 100 |  | 2025-02-04 | 2025-02-04 | 2025-02-12 | 2025-02-12
39938 |  | Complete |  | 2025-02-04 | 2025-02-12 | L45-46 | 100 | 100 |  | 2025-02-04 | 2025-02-04 | 2025-02-12 | 2025-02-12 |  |  |  | Finishes | Gypsum Plastering Works
39939 | Tower A - Super Structure - Core & Outer Slab L45-46 | Complete | RCC Works - Vertical | 2025-02-04 | 2025-02-10 | Outer Columns_TA | 100 | 100 |  | 2025-02-04 | 2025-02-04 | 2025-02-10 | 2025-02-10 | Tower A | Super Structure | L45 | RCC Sub Structure | RCC Works - Vertical
40325 |  | Complete |  | 2025-02-04 | 2025-07-18 | L42-43 | 100 | 100 |  | 2025-02-04 | 2025-02-04 | 2025-07-18 | 2025-08-30
40325 |  | Complete |  | 2025-02-04 | 2025-07-18 | L42-43 | 100 | 100 |  | 2025-02-04 | 2025-02-04 | 2025-07-18 | 2025-08-30 |  |  |  | Finishes | Gypsum Plastering Works
40326 | Tower A - Super Structure - Finishes & MEP - L42 to L43 | Complete | Partition Wall-Blockwork | 2025-02-04 | 2025-02-20 | De-shuttering & Area clearance | 100 | 100 |  | 2025-02-04 | 2025-02-04 | 2025-02-20 | 2025-02-20 | Tower A | Super Structure | L42
42542 |  | Started |  | 2025-02-04 | 2026-06-29 | L26-27 | 100 | 40 |  | 2025-02-04 | 2025-02-04 | 2026-06-26 |  |  |  |  | Finishes | Gypsum Plastering Works
42542 |  | Started |  | 2025-02-04 | 2026-06-29 | L26-27 | 100 | 40 |  | 2025-02-04 | 2025-02-04 | 2026-06-26
42543 |  | Started |  | 2025-02-04 | 2025-03-04 | MEP 1st Fixes | 100 | 44 |  | 2025-02-04 | 2025-02-04 | 2025-10-03
42544 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Apartment Area | Started | FPS 1st Fix - MEP & Finishes | 2025-02-04 | 2025-02-11 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-02-04 | 2025-04-30 | 2025-09-19 |  | Tower A | Super Structure | L26 | MEP | FPS 1st Fix - MEP & Finishes
42545 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Apartment Area | Started | Electrical 1st Fix - MEP & Finishes | 2025-02-04 | 2025-02-04 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 90 |  | 2025-02-04 | 2025-02-04 | 2025-09-11 |  | Tower A | Super Structure | L26 | MEP | Electrical 1st Fixes
42546 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Apartment Area | Started | PHE 1st Fix - MEP & Finishes | 2025-02-04 | 2025-02-08 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 40 |  | 2025-02-04 | 2025-02-04 | 2025-09-16 |  | Tower A | Super Structure | L26
42547 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Apartment Area | Started | Wet Area Waterproofing - MEP & Finishes | 2025-02-04 | 2025-02-12 | Wet Area Waterproofing | 100 | 50 |  | 2025-02-04 | 2025-02-04 | 2025-09-20 |  | Tower A | Super Structure | L26
39597 | Tower A - Super Structure - Core Wall Low Rise L49-50 | Complete | Core Wall RCC Works | 2025-02-05 | 2025-02-07 | Reinf & Guide shoes fixing | 100 | 100 |  | 2025-02-05 | 2025-02-05 | 2025-02-07 | 2025-02-07 | Tower A | Super Structure | L49 | RCC Super Structure | Core Wall RCC Works
39598 | Tower A - Super Structure - Core Wall Low Rise L49-50 | Complete | Core Wall RCC Works | 2025-02-06 | 2025-02-08 | ACS Form Closing & Alignment | 100 | 100 |  | 2025-02-06 | 2025-02-06 | 2025-02-08 | 2025-02-08 | Tower A | Super Structure | L49 | RCC Super Structure | Core Wall RCC Works
39940 | Tower A - Super Structure - Core & Outer Slab L45-46 | Complete | RCC Works - Slab | 2025-02-06 | 2025-02-12 | Outer Slab_TA | 100 | 100 |  | 2025-02-06 | 2025-02-06 | 2025-02-12 | 2025-02-12 | Tower A | Super Structure | L45 | RCC Sub Structure | RCC Works - Slab
40260 | Tower A - Super Structure - Finishes & MEP - L27 to L28 | Complete | Partition Wall-Blockwork | 2025-02-06 | 2025-02-11 | Staircase Area | 100 | 100 |  | 2025-02-06 | 2025-02-06 | 2025-02-11 | 2025-02-11 | Tower A | Super Structure | L27
40263 | Tower A - Super Structure - Finishes & MEP - L28 to L29 | Complete | Partition Wall-Blockwork | 2025-02-06 | 2025-02-13 | Partition Walls | 100 | 100 |  | 2025-02-06 | 2025-02-06 | 2025-02-13 | 2025-02-13 | Tower A | Super Structure | L28
10520 | T-20-1st Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-02-07 | 2025-03-28 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-02-07 | 2025-02-07 | 2025-03-28 | 2025-03-28
48388 | Retail - Sub structure - B2 to B1 - P2 | Started |  | 2025-02-08 | 2025-02-12 | Section 7_lift 1 | 100 | 50 |  | 2025-02-08 | 2025-02-08 | 2025-10-04 |  | Retail | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
48388 | Retail - Sub structure - B2 to B1 - P2 | Started |  | 2025-02-08 | 2025-02-12 | Section 7_lift 1 | 100 | 50 |  | 2025-02-08 | 2025-02-08 | 2025-10-04 |  | Retail | Sub Structure | B2
48389 |  | Complete |  | 2025-02-08 | 2025-02-24 | Pour RT-3 | 100 | 100 |  | 2025-02-08 | 2025-02-08 | 2025-02-24 | 2025-02-24
48390 | Retail - Sub structure - B2 to B1 - P3 | Complete |  | 2025-02-08 | 2025-02-15 | Section 8_lift 1 | 100 | 100 |  | 2025-02-08 | 2025-02-08 | 2025-02-15 | 2025-02-15 | Retail | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
48390 | Retail - Sub structure - B2 to B1 - P3 | Complete |  | 2025-02-08 | 2025-02-15 | Section 8_lift 1 | 100 | 100 |  | 2025-02-08 | 2025-02-08 | 2025-02-15 | 2025-02-15 | Retail | Sub Structure | B2
41283 |  | Started |  | 2025-02-09 | 2026-02-28 | L21-22 | 100 | 52 |  | 2025-02-09 | 2025-02-09 | 2026-03-23 |  |  |  |  | Finishes | Gypsum Plastering Works
41283 |  | Started |  | 2025-02-09 | 2026-02-28 | L21-22 | 100 | 52 |  | 2025-02-09 | 2025-02-09 | 2026-03-23
41284 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2025-02-09 | 2025-02-11 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 65 |  | 2025-02-09 | 2025-02-09 | 2026-02-09 |  | Tower A | Super Structure | L21 | MEP | FPS 1st Fix - MEP & Finishes
8952 | T-15-Sub structure Basement Part 2 NTA | Started | Reinforcement | 2025-02-10 | 2025-03-22 | Reinforcement | 39 | 2 | MT | 2025-02-10 | 2025-02-10 | 2025-05-26
39599 | Tower A - Super Structure - Core Wall Low Rise L49-50 | Complete | Core Wall RCC Works | 2025-02-10 | 2025-02-11 | Casting | 100 | 100 |  | 2025-02-10 | 2025-02-10 | 2025-02-11 | 2025-02-11 | Tower A | Super Structure | L49 | RCC Super Structure | Core Wall RCC Works
47702 |  | Complete |  | 2025-02-10 | 2025-03-22 | Pour 11 (PB-E to PB-K) | 100 | 100 |  | 2025-02-10 | 2025-02-10 | 2025-03-22 | 2025-03-22
47703 |  | Complete |  | 2025-02-10 | 2025-03-04 | Columns/ Walls_NTA | 100 | 100 |  | 2025-02-10 | 2025-02-10 | 2025-03-04 | 2025-03-04
47703 |  | Complete |  | 2025-02-10 | 2025-03-04 | Columns/ Walls_NTA | 100 | 100 |  | 2025-02-10 | 2025-02-10 | 2025-03-04 | 2025-03-04 |  |  |  | RCC Sub Structure | RCC Works - Vertical
9462 |  | Started |  | 2025-02-11 | 2025-04-14 | Basement Roof/Podium Structure Works | 100 | 39 |  | 2025-02-11 | 2025-02-11 | 2025-05-26
9463 |  | Complete |  | 2025-02-11 | 2025-04-05 | Part-1 | 100 | 100 |  | 2025-02-11 | 2025-02-11 | 2025-04-21 | 2025-04-22
9464 | T-16-Sub structure Basement Part 1 TA | Complete | Staging | 2025-02-11 | 2025-04-01 | Staging | 100 | 100 |  | 2025-02-11 | 2025-02-11 | 2025-04-12 | 2025-04-13
48361 | Retail - Sub structure - B3 to B2 - P5 | Complete |  | 2025-02-11 | 2025-02-18 | Section 14_lift 1 | 100 | 100 |  | 2025-02-11 | 2025-02-11 | 2025-02-18 | 2025-02-18 | Retail | Sub Structure | B3
48362 | Retail - Sub structure - B3 to B2 - P5 | Complete |  | 2025-02-11 | 2025-02-18 | Section 15_lift 1 | 100 | 100 |  | 2025-02-11 | 2025-02-11 | 2025-02-18 | 2025-02-18 | Retail | Sub Structure | B3
9465 | T-16-Sub structure Basement Part 1 TA | Complete | Formwork | 2025-02-12 | 2025-03-28 | Formwork | 100 | 100 | Sqm | 2025-02-12 | 2025-02-12 | 2025-04-17 | 2025-04-18
39600 | Tower A - Super Structure - Core Wall Low Rise L49-50 | Complete | Core Wall RCC Works | 2025-02-12 | 2025-02-12 | ACS Form Release & jump to next level | 100 | 100 |  | 2025-02-12 | 2025-02-12 | 2025-02-12 | 2025-02-12 | Tower A | Super Structure | L49 | RCC Super Structure | Core Wall RCC Works
40329 |  | Complete |  | 2025-02-12 | 2025-08-06 | L43-44 | 100 | 100 |  | 2025-02-12 | 2025-02-12 | 2025-08-06 | 2025-09-03
40329 |  | Complete |  | 2025-02-12 | 2025-08-06 | L43-44 | 100 | 100 |  | 2025-02-12 | 2025-02-12 | 2025-08-06 | 2025-09-03 |  |  |  | Finishes | Gypsum Plastering Works
40330 | Tower A - Super Structure - Finishes & MEP - L43 to L44 | Complete | Partition Wall-Blockwork | 2025-02-12 | 2025-02-28 | De-shuttering & Area clearance | 100 | 100 |  | 2025-02-12 | 2025-02-12 | 2025-02-28 | 2025-02-28 | Tower A | Super Structure | L43
42560 |  | Started |  | 2025-02-12 | 2026-06-29 | L27-28 | 100 | 39 |  | 2025-02-12 | 2025-02-12 | 2026-06-26 |  |  |  |  | Finishes | Gypsum Plastering Works
42560 |  | Started |  | 2025-02-12 | 2026-06-29 | L27-28 | 100 | 39 |  | 2025-02-12 | 2025-02-12 | 2026-06-26
42561 |  | Started |  | 2025-02-12 | 2025-03-12 | MEP 1st Fixes | 100 | 43 |  | 2025-02-12 | 2025-02-12 | 2025-10-07
42562 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Apartment Area | Started | FPS 1st Fix - MEP & Finishes | 2025-02-12 | 2025-02-19 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 35 | Units | 2025-02-12 | 2025-05-05 | 2025-09-16 |  | Tower A | Super Structure | L27 | MEP | FPS 1st Fix - MEP & Finishes
42563 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Apartment Area | Started | Electrical 1st Fix - MEP & Finishes | 2025-02-12 | 2025-02-13 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 70 |  | 2025-02-12 | 2025-02-12 | 2025-09-12 |  | Tower A | Super Structure | L27 | MEP | Electrical 1st Fixes
42564 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Apartment Area | Started | PHE 1st Fix - MEP & Finishes | 2025-02-12 | 2025-02-17 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 40 |  | 2025-02-12 | 2025-02-12 | 2025-09-16 |  | Tower A | Super Structure | L27
42565 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Apartment Area | Started | Wet Area Waterproofing - MEP & Finishes | 2025-02-12 | 2025-02-24 | Wet Area Waterproofing | 100 | 30 |  | 2025-02-12 | 2025-02-12 | 2025-09-24 |  | Tower A | Super Structure | L27
10522 | T-20-1st Floor | Complete | Shuttering | 2025-02-13 | 2025-03-28 | Slab and Beam Shuttering | 100 | 100 | Sqm | 2025-02-13 | 2025-02-13 | 2025-03-28 | 2025-03-28
39163 |  | Complete |  | 2025-02-13 | 2025-02-18 | Flooring | 100 | 100 |  | 2025-02-13 | 2025-02-13 | 2025-02-18 | 2025-02-18
39601 |  | Complete |  | 2025-02-13 | 2025-02-24 | Core Wall L50-51 (MEP Transfer Floor) | 100 | 100 |  | 2025-02-13 | 2025-02-13 | 2025-02-24 | 2025-02-24
39602 | Tower A - Super Structure - Core Wall Low Rise L50-51 | Complete | Core Wall RCC Works | 2025-02-13 | 2025-02-13 | Scaffolding & platform | 100 | 100 |  | 2025-02-13 | 2025-02-13 | 2025-02-13 | 2025-02-13 | Tower A | Super Structure | L50 | RCC Super Structure | Core Wall RCC Works
39941 |  | Complete |  | 2025-02-13 | 2025-02-21 | L46-47 | 100 | 100 |  | 2025-02-13 | 2025-02-13 | 2025-02-21 | 2025-02-21
39941 |  | Complete |  | 2025-02-13 | 2025-02-21 | L46-47 | 100 | 100 |  | 2025-02-13 | 2025-02-13 | 2025-02-21 | 2025-02-21 |  |  |  | Finishes | Gypsum Plastering Works
39942 | Tower A - Super Structure - Core & Outer Slab L46-47 | Complete | RCC Works - Vertical | 2025-02-13 | 2025-02-19 | Outer Columns_TA | 100 | 100 |  | 2025-02-13 | 2025-02-13 | 2025-02-19 | 2025-02-19 | Tower A | Super Structure | L46 | RCC Sub Structure | RCC Works - Vertical
48276 | Retail - Sub structure - B1 to GF - P2 | Complete |  | 2025-02-13 | 2025-02-13 | Section 7_lift 1 | 100 | 100 |  | 2025-02-13 | 2025-02-13 | 2025-02-13 | 2025-02-13 | Retail | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
48276 | Retail - Sub structure - B1 to GF - P2 | Complete |  | 2025-02-13 | 2025-02-13 | Section 7_lift 1 | 100 | 100 |  | 2025-02-13 | 2025-02-13 | 2025-02-13 | 2025-02-13 | Retail | Sub Structure | B1
10003 | T-21-1st Floor | Complete | Slab& Beam Steel & Conduting | 2025-02-14 | 2025-03-23 | Slab& Beam Steel & Conduting | 100 | 100 | MT | 2025-02-14 | 2025-02-14 | 2025-03-23 | 2025-03-23
39603 | Tower A - Super Structure - Core Wall Low Rise L50-51 | Complete | Core Wall RCC Works | 2025-02-14 | 2025-02-17 | Reinf & Guide shoes fixing | 100 | 100 |  | 2025-02-14 | 2025-02-14 | 2025-02-17 | 2025-02-17 | Tower A | Super Structure | L50 | RCC Super Structure | Core Wall RCC Works
40264 | Tower A - Super Structure - Finishes & MEP - L28 to L29 | Complete | Partition Wall-Blockwork | 2025-02-14 | 2025-02-19 | Staircase Area | 100 | 100 |  | 2025-02-14 | 2025-02-14 | 2025-02-19 | 2025-02-19 | Tower A | Super Structure | L28
48296 | Retail - Sub structure - B1 to GF - P2 | Complete |  | 2025-02-14 | 2025-02-21 | Section 7_lift 2 | 100 | 100 |  | 2025-02-14 | 2025-02-14 | 2025-02-21 | 2025-02-21 | Retail | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
48296 | Retail - Sub structure - B1 to GF - P2 | Complete |  | 2025-02-14 | 2025-02-21 | Section 7_lift 2 | 100 | 100 |  | 2025-02-14 | 2025-02-14 | 2025-02-21 | 2025-02-21 | Retail | Sub Structure | B1
9469 |  | Started |  | 2025-02-15 | 2025-04-14 | Part-2 | 100 | 1 |  | 2025-02-15 | 2025-02-15 | 2025-05-26
9470 | T-16-Sub structure Basement Part 2 NTA | Started | Staging | 2025-02-15 | 2025-03-19 | Staging | 100 | 2 |  | 2025-02-15 | 2025-02-15 | 2025-05-23
39604 | Tower A - Super Structure - Core Wall Low Rise L50-51 | Complete | Core Wall RCC Works | 2025-02-15 | 2025-02-18 | ACS Form Closing & Alignment | 100 | 100 |  | 2025-02-15 | 2025-02-15 | 2025-02-18 | 2025-02-18 | Tower A | Super Structure | L50 | RCC Super Structure | Core Wall RCC Works
39943 | Tower A - Super Structure - Core & Outer Slab L46-47 | Complete | RCC Works - Slab | 2025-02-15 | 2025-02-21 | Outer Slab_TA | 100 | 100 |  | 2025-02-15 | 2025-02-15 | 2025-02-21 | 2025-02-21 | Tower A | Super Structure | L46 | RCC Sub Structure | RCC Works - Slab
41299 |  | Started |  | 2025-02-16 | 2026-03-09 | L22-23 | 100 | 52 |  | 2025-02-16 | 2025-02-16 | 2026-03-30 |  |  |  |  | Finishes | Gypsum Plastering Works
41299 |  | Started |  | 2025-02-16 | 2026-03-09 | L22-23 | 100 | 52 |  | 2025-02-16 | 2025-02-16 | 2026-03-30
41300 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2025-02-16 | 2025-02-18 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 65 |  | 2025-02-16 | 2025-02-16 | 2026-02-16 |  | Tower A | Super Structure | L22 | MEP | FPS 1st Fix - MEP & Finishes
48391 | Retail - Sub structure - B2 to B1 - P3 | Complete |  | 2025-02-17 | 2025-02-24 | Section 9_lift 1 | 100 | 100 |  | 2025-02-17 | 2025-02-17 | 2025-02-24 | 2025-02-24 | Retail | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
48391 | Retail - Sub structure - B2 to B1 - P3 | Complete |  | 2025-02-17 | 2025-02-24 | Section 9_lift 1 | 100 | 100 |  | 2025-02-17 | 2025-02-17 | 2025-02-24 | 2025-02-24 | Retail | Sub Structure | B2
8953 | T-15-Sub structure Basement Part 2 NTA | Started | Conduiting | 2025-02-18 | 2025-03-26 | Conduiting | 100 | 2 |  | 2025-02-18 | 2025-02-18 | 2025-05-29
39170 |  | Complete |  | 2025-02-18 | 2025-03-19 | RCC SlabSlab at 6m Ht | 100 | 100 |  | 2025-02-18 | 2025-02-18 | 2025-03-19 | 2025-03-19
39605 | Tower A - Super Structure - Core Wall Low Rise L50-51 | Complete | Core Wall RCC Works | 2025-02-19 | 2025-02-22 | Casting | 100 | 100 |  | 2025-02-19 | 2025-02-19 | 2025-02-22 | 2025-02-22 | Tower A | Super Structure | L50 | RCC Super Structure | Core Wall RCC Works
42578 |  | Started |  | 2025-02-20 | 2026-07-04 | L28-29 (Refuge) | 100 | 39 |  | 2025-02-20 | 2025-02-20 | 2026-07-02
42579 |  | Started |  | 2025-02-20 | 2025-03-11 | MEP 1st Fixes | 100 | 43 |  | 2025-02-20 | 2025-02-20 | 2025-09-29
42580 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Apartment Area | Started | FPS 1st Fix - MEP & Finishes | 2025-02-20 | 2025-02-27 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 35 | Units | 2025-02-20 | 2025-05-12 | 2025-09-16 |  | Tower A | Super Structure | L28 | MEP | FPS 1st Fix - MEP & Finishes
42581 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Apartment Area | Started | Electrical 1st Fix - MEP & Finishes | 2025-02-20 | 2025-02-21 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 70 |  | 2025-02-20 | 2025-02-20 | 2025-09-12 |  | Tower A | Super Structure | L28 | MEP | Electrical 1st Fixes
42582 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Apartment Area | Started | PHE 1st Fix - MEP & Finishes | 2025-02-20 | 2025-02-25 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 40 |  | 2025-02-20 | 2025-02-20 | 2025-09-16 |  | Tower A | Super Structure | L28
42583 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Apartment Area | Started | Wet Area Waterproofing - MEP & Finishes | 2025-02-20 | 2025-03-04 | Wet Area Waterproofing | 100 | 30 |  | 2025-02-20 | 2025-02-20 | 2025-09-24 |  | Tower A | Super Structure | L28
8954 | T-15-Sub structure Basement Part 2 NTA | Started | Concrete | 2025-02-22 | 2025-03-27 | Concrete | 500.6 | 2 | CUM | 2025-02-22 | 2025-02-22 | 2025-05-30
11535 | T-18-Sub structure Shear Walls | Quality checked | Shuttering | 2025-02-22 | 2025-03-31 | Shuttering | 100 | 100 |  | 2025-02-22 | 2025-02-22 | 2025-03-31 | 2025-03-31
39944 |  | Complete |  | 2025-02-22 | 2025-02-28 | L47-48 | 100 | 100 |  | 2025-02-22 | 2025-02-22 | 2025-02-28 | 2025-02-28
39944 |  | Complete |  | 2025-02-22 | 2025-02-28 | L47-48 | 100 | 100 |  | 2025-02-22 | 2025-02-22 | 2025-02-28 | 2025-02-28 |  |  |  | Finishes | Gypsum Plastering Works
39945 | Tower A - Super Structure - Core & Outer Slab L47-48 | Complete | RCC Works - Vertical | 2025-02-22 | 2025-02-27 | Outer Columns_TA | 100 | 100 |  | 2025-02-22 | 2025-02-22 | 2025-02-27 | 2025-02-27 | Tower A | Super Structure | L47 | RCC Sub Structure | RCC Works - Vertical
40333 |  | Complete |  | 2025-02-22 | 2025-08-19 | L44-45 | 100 | 100 |  | 2025-02-22 | 2025-01-03 | 2025-08-19 | 2025-09-10
40333 |  | Complete |  | 2025-02-22 | 2025-08-19 | L44-45 | 100 | 100 |  | 2025-02-22 | 2025-01-03 | 2025-08-19 | 2025-09-10 |  |  |  | Finishes | Gypsum Plastering Works
40334 | Tower A - Super Structure - Finishes & MEP - L44 to L45 | Complete | Partition Wall-Blockwork | 2025-02-22 | 2025-03-11 | De-shuttering & Area clearance | 100 | 100 |  | 2025-02-22 | 2025-01-03 | 2025-03-11 | 2025-02-24 | Tower A | Super Structure | L44
48277 |  | Complete |  | 2025-02-22 | 2025-02-23 | Pour RT-3 | 100 | 100 |  | 2025-02-22 | 2025-02-22 | 2025-02-23 | 2025-02-22
48278 | Retail - Sub structure - B1 to GF - P3 | Complete |  | 2025-02-22 | 2025-02-22 | Section 8_lift 1 | 100 | 100 |  | 2025-02-22 | 2025-02-22 | 2025-02-22 | 2025-02-22 | Retail | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
48278 | Retail - Sub structure - B1 to GF - P3 | Complete |  | 2025-02-22 | 2025-02-22 | Section 8_lift 1 | 100 | 100 |  | 2025-02-22 | 2025-02-22 | 2025-02-22 | 2025-02-22 | Retail | Sub Structure | B1
8948 | T-15-GF | Complete | Concrete | 2025-02-23 | 2025-02-23 | Concrete | 100 | 100 | CUM | 2025-02-23 | 2025-02-23 | 2025-02-23 | 2025-02-23
41315 |  | Started |  | 2025-02-23 | 2026-03-16 | L23-24 | 100 | 52 |  | 2025-02-23 | 2025-02-23 | 2026-04-06 |  |  |  |  | Finishes | Gypsum Plastering Works
41315 |  | Started |  | 2025-02-23 | 2026-03-16 | L23-24 | 100 | 52 |  | 2025-02-23 | 2025-02-23 | 2026-04-06
41316 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2025-02-23 | 2025-02-25 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 65 |  | 2025-02-23 | 2025-02-23 | 2026-02-23 |  | Tower A | Super Structure | L23 | MEP | FPS 1st Fix - MEP & Finishes
48279 | Retail - Sub structure - B1 to GF - P3 | Milestone Started |  | 2025-02-23 |  | Section 9_lift 1 | 100 | 100 |  | 2025-02-23 | 2025-02-24 |  |  | Retail | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
48279 | Retail - Sub structure - B1 to GF - P3 | Milestone Started |  | 2025-02-23 |  | Section 9_lift 1 | 100 | 100 |  | 2025-02-23 | 2025-02-24 |  |  | Retail | Sub Structure | B1
39606 | Tower A - Super Structure - Core Wall Low Rise L50-51 | Complete | Core Wall RCC Works | 2025-02-24 | 2025-02-24 | ACS Form Release & jump to next level | 100 | 100 |  | 2025-02-24 | 2025-02-24 | 2025-02-24 | 2025-02-24 | Tower A | Super Structure | L50 | RCC Super Structure | Core Wall RCC Works
48297 |  | Complete |  | 2025-02-24 | 2025-03-03 | Pour RT-3 | 100 | 100 |  | 2025-02-24 | 2025-02-24 | 2025-03-03 | 2025-03-03
48298 | Retail - Sub structure - B1 to GF - P3 | Complete |  | 2025-02-24 | 2025-03-03 | Section 8_lift 2 | 100 | 100 |  | 2025-02-24 | 2025-02-24 | 2025-03-03 | 2025-03-03 | Retail | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
48298 | Retail - Sub structure - B1 to GF - P3 | Complete |  | 2025-02-24 | 2025-03-03 | Section 8_lift 2 | 100 | 100 |  | 2025-02-24 | 2025-02-24 | 2025-03-03 | 2025-03-03 | Retail | Sub Structure | B1
48299 | Retail - Sub structure - B1 to GF - P3 | Complete |  | 2025-02-24 | 2025-03-03 | Section 9_lift 2 | 100 | 100 |  | 2025-02-24 | 2025-02-24 | 2025-03-03 | 2025-03-03 | Retail | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
48299 | Retail - Sub structure - B1 to GF - P3 | Complete |  | 2025-02-24 | 2025-03-03 | Section 9_lift 2 | 100 | 100 |  | 2025-02-24 | 2025-02-24 | 2025-03-03 | 2025-03-03 | Retail | Sub Structure | B1
9471 | T-16-Sub structure Basement Part 2 NTA | Started | Formwork | 2025-02-25 | 2025-03-22 | Formwork | 2633 | 2 | Sqm | 2025-02-25 | 2025-02-25 | 2025-05-26
10521 | T-20-1st Floor | Complete | Conduiting | 2025-02-25 | 2025-03-27 | Conduiting works | 100 | 100 |  | 2025-02-25 | 2025-02-25 | 2025-03-27 | 2025-03-27
11536 | T-18-Sub structure Shear Walls | Quality checked | RCC | 2025-02-25 | 2025-04-01 | RCC | 208 | 208 | CUM | 2025-02-25 | 2025-02-25 | 2025-04-01 | 2025-04-01
11536 | T-18-Sub structure Shear Walls | Quality checked | RCC | 2025-02-25 | 2025-04-01 | RCC | 208 | 208 | CUM | 2025-02-25 | 2025-02-25 | 2025-04-01 | 2025-04-01
39164 |  | Complete |  | 2025-02-25 | 2025-02-27 | Wall Plaster | 100 | 100 |  | 2025-02-25 | 2025-02-25 | 2025-02-27 | 2025-02-27
39607 |  | Complete |  | 2025-02-25 | 2025-08-13 | Core Wall_Mid Rise | 100 | 100 |  | 2025-02-25 | 2025-02-19 | 2025-08-13 | 2025-09-10
39608 |  | Complete |  | 2025-02-25 | 2025-03-01 | Core Wall L51-52 | 100 | 100 |  | 2025-02-25 | 2025-02-19 | 2025-03-01 | 2025-02-23
39609 | Tower A - Super Structure - Core Wall Mid Rise L51-52 | Complete | Core Wall RCC Works | 2025-02-25 | 2025-02-25 | Scaffolding & platform | 100 | 100 | Units | 2025-02-25 | 2025-02-19 | 2025-02-25 | 2025-02-19 | Tower A | Super Structure | L51 | RCC Super Structure | Core Wall RCC Works
39611 | Tower A - Super Structure - Core Wall Mid Rise L51-52 | Complete | Core Wall RCC Works | 2025-02-25 | 2025-02-27 | ACS Form Closing & Alignment | 100 | 100 | Units | 2025-02-25 | 2025-02-21 | 2025-02-27 | 2025-02-21 | Tower A | Super Structure | L51 | RCC Super Structure | Core Wall RCC Works
39946 | Tower A - Super Structure - Core & Outer Slab L47-48 | Complete | RCC Works - Slab | 2025-02-25 | 2025-02-28 | Outer Slab_TA | 100 | 100 |  | 2025-02-25 | 2025-02-25 | 2025-02-28 | 2025-02-28 | Tower A | Super Structure | L47 | RCC Sub Structure | RCC Works - Slab
48011 |  | Started |  | 2025-02-25 | 2025-04-28 | Demolition + Segregation & Carting Away of Debris | 100 | 30 |  | 2025-02-25 | 2025-02-25 | 2025-11-20
39610 | Tower A - Super Structure - Core Wall Mid Rise L51-52 | Complete | Core Wall RCC Works | 2025-02-26 | 2025-02-26 | Reinf & Guide shoes fixing | 100 | 100 | Units | 2025-02-26 | 2025-02-20 | 2025-02-26 | 2025-02-20 | Tower A | Super Structure | L51 | RCC Super Structure | Core Wall RCC Works
8957 |  | Started |  | 2025-02-25 | 2025-12-26 | RCC Structure | 100 | 71 |  | 2025-02-27 | 2025-02-25 | 2025-12-22
8958 | T-15-1st Floor | Complete |  | 2025-02-25 | 2025-05-09 | Ground Floor Roof | 100 | 100 |  | 2025-02-27 | 2025-02-25 | 2025-05-29 | 2025-05-10
8959 | T-15-1st Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-02-25 | 2025-04-28 | AL - Shear Walls/Corewalls Steel | 32 | 32 | MTon | 2025-02-27 | 2025-02-25 | 2025-05-18 | 2025-03-16
47704 |  | Complete |  | 2025-02-27 | 2025-03-22 | Slab_NTA | 100 | 100 |  | 2025-02-27 | 2025-02-27 | 2025-03-22 | 2025-03-22
47704 |  | Complete |  | 2025-02-27 | 2025-03-22 | Slab_NTA | 100 | 100 |  | 2025-02-27 | 2025-02-27 | 2025-03-22 | 2025-03-22 |  |  |  | RCC Sub Structure | RCC Works - Slab
8961 | T-15-1st Floor | Complete | Conduiting | 2025-02-28 | 2025-05-09 | Conduiting works | 100 | 100 |  | 2025-02-28 | 2025-02-28 | 2025-05-29 | 2025-05-03
39612 | Tower A - Super Structure - Core Wall Mid Rise L51-52 | Complete | Core Wall RCC Works | 2025-02-28 | 2025-02-28 | Casting | 100 | 100 | Units | 2025-02-28 | 2025-02-22 | 2025-02-28 | 2025-02-22 | Tower A | Super Structure | L51 | RCC Super Structure | Core Wall RCC Works
11529 |  | Started |  | 2025-03-06 | 2025-04-04 | Columns | 100 | 35 |  | 2025-03-01 | 2025-03-01 | 2025-05-31
11530 | T-18-Sub structure Columns | Started | Reinforcement | 2025-03-06 | 2025-03-28 | Reinforcement | 3 | 2.85 | MTon | 2025-03-01 | 2025-03-01 | 2025-05-31
39613 | Tower A - Super Structure - Core Wall Mid Rise L51-52 | Complete | Core Wall RCC Works | 2025-03-01 | 2025-03-01 | ACS Form Release & jump to next level | 100 | 100 | Units | 2025-03-01 | 2025-02-23 | 2025-03-01 | 2025-02-23 | Tower A | Super Structure | L51 | RCC Super Structure | Core Wall RCC Works
39947 |  | Complete |  | 2025-03-01 | 2025-03-13 | L48-49 | 100 | 100 |  | 2025-03-01 | 2025-03-01 | 2025-03-13 | 2025-03-13
39947 |  | Complete |  | 2025-03-01 | 2025-03-13 | L48-49 | 100 | 100 |  | 2025-03-01 | 2025-03-01 | 2025-03-13 | 2025-03-13 |  |  |  | Finishes | Gypsum Plastering Works
39948 | Tower A - Super Structure - Core & Outer Slab L48-49 | Complete | RCC Works - Vertical | 2025-03-01 | 2025-03-07 | Outer Columns_TA | 100 | 100 |  | 2025-03-01 | 2025-03-01 | 2025-03-07 | 2025-03-07 | Tower A | Super Structure | L48 | RCC Sub Structure | RCC Works - Vertical
40337 |  | Started |  | 2025-03-01 | 2025-09-01 | L45-46 | 100 | 32 |  | 2025-03-01 | 2025-03-16 | 2025-09-25 |  |  |  |  | Finishes | Gypsum Plastering Works
40337 |  | Started |  | 2025-03-01 | 2025-09-01 | L45-46 | 100 | 32 |  | 2025-03-01 | 2025-03-16 | 2025-09-25
40338 | Tower A - Super Structure - Finishes & MEP - L45 to L46 | Complete | Partition Wall-Blockwork | 2025-03-01 | 2025-03-19 | De-shuttering & Area clearance | 100 | 100 |  | 2025-03-01 | 2025-03-16 | 2025-03-19 | 2025-03-16 | Tower A | Super Structure | L45
40558 | Tower A - Super Structure - Finishes & MEP | Complete | MEP Shaft Masonry | 2025-03-01 | 2025-03-31 | L45-L55 | 100 | 100 |  | 2025-03-01 | 2025-03-01 | 2025-03-31 | 2025-03-31 | Tower A | Super Structure
41331 |  | Started |  | 2025-03-01 | 2026-03-23 | L24-25 | 100 | 52 |  | 2025-03-01 | 2025-03-01 | 2026-04-13 |  |  |  |  | Finishes | Gypsum Plastering Works
41331 |  | Started |  | 2025-03-01 | 2026-03-23 | L24-25 | 100 | 52 |  | 2025-03-01 | 2025-03-01 | 2026-04-13
41332 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2025-03-01 | 2025-03-03 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 65 |  | 2025-03-01 | 2025-03-01 | 2026-03-02 |  | Tower A | Super Structure | L24 | MEP | FPS 1st Fix - MEP & Finishes
11026 | T-19-Sub structure Basement Part 1 TA | Complete | Reinforcement | 2025-03-02 | 2025-03-25 | Reinforcement | 28 | 28 | MT | 2025-03-02 | 2025-03-02 | 2025-03-25 | 2025-03-25
39614 |  | Complete |  | 2025-03-03 | 2025-03-17 | Core Wall L52-53 | 100 | 100 |  | 2025-03-03 | 2025-03-03 | 2025-03-17 | 2025-03-17
39615 | Tower A - Super Structure - Core Wall Mid Rise L52-53 | Complete | Core Wall RCC Works | 2025-03-03 | 2025-03-03 | Scaffolding & platform | 100 | 100 | Units | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-03 | Tower A | Super Structure | L52 | RCC Super Structure | Core Wall RCC Works
40275 | Tower A - Super Structure - Finishes & MEP - L31 to L32 | Complete | Partition Wall-Blockwork | 2025-03-03 | 2025-04-10 | Partition Walls | 100 | 100 |  | 2025-03-03 | 2025-03-03 | 2025-04-10 | 2025-04-10 | Tower A | Super Structure | L31
9459 |  | Started |  | 2025-03-04 | 2025-07-11 | Grade Slab | 100 | 1 |  | 2025-03-04 | 2025-03-04 | 2025-07-30
9460 | T-16-Sub structure- Grade slab | Started | Grade Slab PCC | 2025-03-04 | 2025-04-03 | Grade Slab PCC | 212 | 2 | CUM | 2025-03-04 | 2025-03-04 | 2025-06-06
10523 | T-20-1st Floor | Complete | Slab& Beam Steel & Conduting | 2025-03-04 | 2025-03-26 | Slab& Beam Steel & Conduting | 100 | 100 | MT | 2025-03-04 | 2025-03-04 | 2025-03-26 | 2025-03-26
11531 | T-18-Sub structure Columns | Started | Shuttering | 2025-03-09 | 2025-04-01 | Shuttering | 319 | 2 | Sqm | 2025-03-04 | 2025-03-04 | 2025-05-31
39616 | Tower A - Super Structure - Core Wall Mid Rise L52-53 | Complete | Core Wall RCC Works | 2025-03-04 | 2025-03-06 | Reinf & Guide shoes fixing | 100 | 100 | Units | 2025-03-04 | 2025-03-04 | 2025-03-06 | 2025-03-06 | Tower A | Super Structure | L52 | RCC Super Structure | Core Wall RCC Works
39949 | Tower A - Super Structure - Core & Outer Slab L48-49 | Complete | RCC Works - Slab | 2025-03-04 | 2025-03-13 | Outer Slab_TA | 100 | 100 |  | 2025-03-04 | 2025-03-04 | 2025-03-13 | 2025-03-13 | Tower A | Super Structure | L48 | RCC Sub Structure | RCC Works - Slab
8411 | T-14-1st Floor | Quality checked | RCC | 2025-03-05 | 2025-03-05 | Slab& Beam RCC | 315 | 315 | CUM | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2025-03-05
8960 | T-15-1st Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-03-05 | 2025-04-04 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-03-05 | 2025-03-05 | 2025-05-27 | 2025-05-03
39165 |  | Complete |  | 2025-03-05 | 2025-03-07 | Painting Woks | 100 | 100 |  | 2025-03-05 | 2025-03-05 | 2025-03-07 | 2025-03-07 |  |  |  | Finishes | Painting Works
39617 | Tower A - Super Structure - Core Wall Mid Rise L52-53 | Complete | Core Wall RCC Works | 2025-03-05 | 2025-03-07 | ACS Form Closing & Alignment | 100 | 100 | Units | 2025-03-05 | 2025-03-05 | 2025-03-07 | 2025-03-07 | Tower A | Super Structure | L52 | RCC Super Structure | Core Wall RCC Works
11532 | T-18-Sub structure Columns | Started | RCC | 2025-03-12 | 2025-04-04 | RCC | 35 | 2 | CUM | 2025-03-06 | 2025-03-06 | 2025-05-31
11532 | T-18-Sub structure Columns | Started | RCC | 2025-03-12 | 2025-04-04 | RCC | 35 | 2 | CUM | 2025-03-06 | 2025-03-06 | 2025-05-31
39206 |  | Started |  | 2025-03-07 | 2025-03-28 | Low Side Installation - Wiring Works If any (B01) | 100 | 50 |  | 2025-03-07 | 2025-03-07 | 2025-10-01
41347 |  | Started |  | 2025-03-07 | 2026-03-30 | L25-26 | 100 | 52 |  | 2025-03-07 | 2025-03-07 | 2026-04-20 |  |  |  |  | Finishes | Gypsum Plastering Works
41347 |  | Started |  | 2025-03-07 | 2026-03-30 | L25-26 | 100 | 52 |  | 2025-03-07 | 2025-03-07 | 2026-04-20
41348 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2025-03-07 | 2025-03-08 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 65 |  | 2025-03-07 | 2025-03-07 | 2026-03-10 |  | Tower A | Super Structure | L25 | MEP | FPS 1st Fix - MEP & Finishes
39618 | Tower A - Super Structure - Core Wall Mid Rise L52-53 | Complete | Core Wall RCC Works | 2025-03-08 | 2025-03-15 | Casting | 100 | 100 | Units | 2025-03-08 | 2025-03-08 | 2025-03-15 | 2025-03-15 | Tower A | Super Structure | L52 | RCC Super Structure | Core Wall RCC Works
8412 | T-14-2nd Floor | Quality checked |  | 2025-03-10 | 2025-04-11 | 1st Floor Roof | 100 | 100 |  | 2025-03-10 | 2025-03-10 | 2025-05-25 | 2025-05-16
8413 | T-14-2nd Floor | Quality checked | AL - Shear Walls/Corewalls Steel | 2025-03-10 | 2025-03-18 | AL - Shear Walls/Corewalls Steel | 100 | 100 | MT | 2025-03-10 | 2025-03-10 | 2025-03-18 | 2025-03-18
8414 | T-14-2nd Floor | Quality checked | Shear Walls/Corewalls Shuttering | 2025-03-14 | 2025-03-28 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-03-14 | 2025-03-14 | 2025-05-23 | 2025-03-29
8962 | T-15-1st Floor | Complete | Shuttering | 2025-03-15 | 2025-04-06 | Slab and Beam Shuttering | 100 | 100 | Sqm | 2025-03-15 | 2025-03-15 | 2025-05-16 | 2025-05-07
11027 | T-19-Sub structure Basement Part 1 TA | Complete | Conduiting | 2025-03-15 | 2025-03-25 | Conduiting | 100 | 100 |  | 2025-03-15 | 2025-03-15 | 2025-03-25 | 2025-03-25
39950 |  | Complete |  | 2025-03-15 | 2025-03-31 | L49-50 | 100 | 100 |  | 2025-03-15 | 2025-03-15 | 2025-03-31 | 2025-03-31
39950 |  | Complete |  | 2025-03-15 | 2025-03-31 | L49-50 | 100 | 100 |  | 2025-03-15 | 2025-03-15 | 2025-03-31 | 2025-03-31 |  |  |  | Finishes | Gypsum Plastering Works
39951 | Tower A - Super Structure - Core & Outer Slab L49-50 | Complete | RCC Works - Vertical | 2025-03-15 | 2025-03-25 | Outer Columns_TA | 100 | 100 |  | 2025-03-15 | 2025-03-15 | 2025-03-25 | 2025-03-25 | Tower A | Super Structure | L49 | RCC Sub Structure | RCC Works - Vertical
40341 |  | Started |  | 2025-03-15 | 2025-09-11 | L46-47 | 100 | 45 |  | 2025-03-15 | 2025-03-13 | 2025-10-01 |  |  |  |  | Finishes | Gypsum Plastering Works
40341 |  | Started |  | 2025-03-15 | 2025-09-11 | L46-47 | 100 | 45 |  | 2025-03-15 | 2025-03-13 | 2025-10-01
40342 | Tower A - Super Structure - Finishes & MEP - L46 to L47 | Complete | Partition Wall-Blockwork | 2025-03-15 | 2025-04-01 | De-shuttering & Area clearance | 100 | 100 |  | 2025-03-15 | 2025-03-13 | 2025-04-01 | 2025-03-13 | Tower A | Super Structure | L46
39619 | Tower A - Super Structure - Core Wall Mid Rise L52-53 | Complete | Core Wall RCC Works | 2025-03-17 | 2025-03-17 | ACS Form Release & jump to next level | 100 | 100 | Units | 2025-03-17 | 2025-03-17 | 2025-03-17 | 2025-03-17 | Tower A | Super Structure | L52 | RCC Super Structure | Core Wall RCC Works
41363 |  | Started |  | 2025-03-17 | 2026-04-06 | L26-27 | 100 | 52 |  | 2025-03-17 | 2025-03-17 | 2026-04-27 |  |  |  |  | Finishes | Gypsum Plastering Works
41363 |  | Started |  | 2025-03-17 | 2026-04-06 | L26-27 | 100 | 52 |  | 2025-03-17 | 2025-03-17 | 2026-04-27
41364 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2025-03-17 | 2025-03-18 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 65 |  | 2025-03-17 | 2025-03-17 | 2026-03-17 |  | Tower A | Super Structure | L26 | MEP | FPS 1st Fix - MEP & Finishes
8416 | T-14-2nd Floor | Quality checked | Shuttering | 2025-03-18 | 2025-04-09 | Slab and Beam Shuttering | 3605 | 3605 | Sqm | 2025-03-18 | 2025-03-18 | 2025-05-25 | 2025-05-14
39620 |  | Complete |  | 2025-03-18 | 2025-03-24 | Core Wall L53-54 | 100 | 100 |  | 2025-03-18 | 2025-03-18 | 2025-03-24 | 2025-03-24
39621 | Tower A - Super Structure - Core Wall Mid Rise L53-54 | Complete | Core Wall RCC Works | 2025-03-18 | 2025-03-18 | Scaffolding & platform | 100 | 100 |  | 2025-03-18 | 2025-03-18 | 2025-03-18 | 2025-03-18 | Tower A | Super Structure | L53 | RCC Super Structure | Core Wall RCC Works
48392 |  | Complete |  | 2025-03-18 | 2025-03-31 | Pour RT-5 | 100 | 100 |  | 2025-03-18 | 2025-03-18 | 2025-03-31 | 2025-03-31
48393 | Retail - Sub structure - B2 to B1 - P5 | Complete |  | 2025-03-18 | 2025-03-25 | Section 10_lift 1 | 100 | 100 |  | 2025-03-18 | 2025-03-18 | 2025-03-25 | 2025-03-25 | Retail | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
48393 | Retail - Sub structure - B2 to B1 - P5 | Complete |  | 2025-03-18 | 2025-03-25 | Section 10_lift 1 | 100 | 100 |  | 2025-03-18 | 2025-03-18 | 2025-03-25 | 2025-03-25 | Retail | Sub Structure | B2
48394 | Retail - Sub structure - B2 to B1 - P5 | Complete |  | 2025-03-18 | 2025-03-25 | Section 11_lift 1 | 100 | 100 |  | 2025-03-18 | 2025-03-18 | 2025-03-25 | 2025-03-25 | Retail | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
48394 | Retail - Sub structure - B2 to B1 - P5 | Complete |  | 2025-03-18 | 2025-03-25 | Section 11_lift 1 | 100 | 100 |  | 2025-03-18 | 2025-03-18 | 2025-03-25 | 2025-03-25 | Retail | Sub Structure | B2
9466 | T-16-Sub structure Basement Part 1 TA | Complete | Reinforcement | 2025-03-19 | 2025-04-05 | Reinforcement | 28 | 28 | MT | 2025-03-19 | 2025-03-19 | 2025-04-18 | 2025-04-19
39622 | Tower A - Super Structure - Core Wall Mid Rise L53-54 | Complete | Core Wall RCC Works | 2025-03-19 | 2025-03-21 | Reinf & Guide shoes fixing | 100 | 100 |  | 2025-03-19 | 2025-03-19 | 2025-03-21 | 2025-03-21 | Tower A | Super Structure | L53 | RCC Super Structure | Core Wall RCC Works
39171 |  | Complete |  | 2025-03-20 | 2025-04-17 | RCC SlabSlab at 6.5m Ht | 100 | 100 |  | 2025-03-20 | 2025-03-20 | 2025-04-17 | 2025-04-17
39623 | Tower A - Super Structure - Core Wall Mid Rise L53-54 | Complete | Core Wall RCC Works | 2025-03-20 | 2025-03-22 | ACS Form Closing & Alignment | 100 | 100 |  | 2025-03-20 | 2025-03-20 | 2025-03-22 | 2025-03-22 | Tower A | Super Structure | L53 | RCC Super Structure | Core Wall RCC Works
44016 |  | Started |  | 2025-03-20 | 2026-09-25 | Façade Works_TA | 100 | 48 |  | 2025-03-20 | 2025-03-20 | 2026-07-04
44040 |  | Started |  | 2025-03-20 | 2026-06-29 | Typical Floors | 100 | 40 |  | 2025-03-20 | 2025-03-20 | 2026-05-30
44041 |  | Started |  | 2025-03-20 | 2025-09-12 | L7-13 | 100 | 61 |  | 2025-03-20 | 2025-03-20 | 2025-10-07
44042 | Tower A - Super Structure - Finishes & MEP - L7 to L13 | Started | Façade Works - MEP & Finishes | 2025-03-20 | 2025-04-03 | Al. Frame section (Mullion & Transom) Installation | 100 | 61 | Units | 2025-03-20 | 2025-03-20 | 2025-09-22 |  | Tower A | Super Structure | L7 | Façade | Façade Works
39952 | Tower A - Super Structure - Core & Outer Slab L49-50 | Complete | RCC Works - Slab | 2025-03-21 | 2025-03-31 | Outer Slab_TA | 100 | 100 |  | 2025-03-21 | 2025-03-21 | 2025-03-31 | 2025-03-31 | Tower A | Super Structure | L49 | RCC Sub Structure | RCC Works - Slab
10501 | T-20-Sub structure- Grade slab | Forced Ready | Grade Slab RCC | 2025-03-28 | 2025-04-30 | Grade Slab RCC | 356 | 0 | CUM | 2025-03-23 |  | 2025-04-23
39624 | Tower A - Super Structure - Core Wall Mid Rise L53-54 | Milestone Started | Core Wall RCC Works | 2025-03-23 |  | Casting | 100 | 100 |  | 2025-03-23 | 2025-03-24 |  |  | Tower A | Super Structure | L53 | RCC Super Structure | Core Wall RCC Works
10004 | T-21-1st Floor | Complete | RCC | 2025-03-24 | 2025-03-24 | Slab& Beam RCC | 315 | 315 | CUM | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2025-03-24
39625 | Tower A - Super Structure - Core Wall Mid Rise L53-54 | Complete | Core Wall RCC Works | 2025-03-24 | 2025-03-24 | ACS Form Release & jump to next level | 100 | 100 |  | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2025-03-24 | Tower A | Super Structure | L53 | RCC Super Structure | Core Wall RCC Works
8415 | T-14-2nd Floor | Quality checked | Conduiting | 2025-03-25 | 2025-04-01 | Conduiting works | 100 | 100 |  | 2025-03-25 | 2025-03-25 | 2025-05-14 | 2025-03-27
39626 |  | Complete |  | 2025-03-25 | 2025-04-01 | Core Wall L54-55 | 100 | 100 |  | 2025-03-25 | 2025-03-25 | 2025-04-01 | 2025-03-29
39627 | Tower A - Super Structure - Core Wall Mid Rise L54-55 | Complete | Core Wall RCC Works | 2025-03-25 | 2025-03-25 | Scaffolding & platform | 100 | 100 |  | 2025-03-25 | 2025-03-25 | 2025-03-25 | 2025-03-25 | Tower A | Super Structure | L54 | RCC Super Structure | Core Wall RCC Works
10005 | T-21-2nd Floor | Complete |  | 2025-03-26 | 2025-04-25 | 1st Floor Roof | 100 | 100 |  | 2025-03-26 | 2025-03-26 | 2025-04-19 | 2025-04-20
10006 | T-21-2nd Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-03-26 | 2025-04-02 | AL - Shear Walls/Corewalls Steel | 100 | 100 | MT | 2025-03-26 | 2025-03-26 | 2025-04-02 | 2025-04-02
11028 | T-19-GF | Complete | Concrete | 2025-03-26 | 2025-03-26 | Concrete | 276 | 276 | CUM | 2025-03-26 | 2025-03-26 | 2025-03-26 | 2025-03-26
39207 |  | Started |  | 2025-03-26 | 2025-04-16 | Low Side Installation - Cable Terminations (B01) | 100 | 50 |  | 2025-03-26 | 2025-03-26 | 2025-10-01
39628 | Tower A - Super Structure - Core Wall Mid Rise L54-55 | Complete | Core Wall RCC Works | 2025-03-26 | 2025-03-28 | Reinf & Guide shoes fixing | 100 | 100 |  | 2025-03-26 | 2025-03-26 | 2025-03-28 | 2025-03-28 | Tower A | Super Structure | L54 | RCC Super Structure | Core Wall RCC Works
41379 |  | Started |  | 2025-03-26 | 2026-04-08 | L27-28 | 100 | 52 |  | 2025-03-26 | 2025-03-26 | 2026-04-29 |  |  |  |  | Finishes | Gypsum Plastering Works
41379 |  | Started |  | 2025-03-26 | 2026-04-08 | L27-28 | 100 | 52 |  | 2025-03-26 | 2025-03-26 | 2026-04-29
41380 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2025-03-26 | 2025-03-27 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 65 |  | 2025-03-26 | 2025-03-26 | 2026-03-19 |  | Tower A | Super Structure | L27 | MEP | FPS 1st Fix - MEP & Finishes
44017 |  | Started |  | 2026-03-12 | 2026-09-25 | Podium Floors at Tower periphery | 100 | 57 |  | 2025-03-26 | 2025-03-26 | 2026-07-04
44026 |  | Started |  | 2026-03-12 | 2026-09-24 | P1-P3 | 100 | 62 |  | 2025-03-26 | 2025-03-26 | 2026-06-19
44028 | Tower A - Super Structure - Finishes & MEP - P1 to P3 | Started | Façade Works - MEP & Finishes | 2026-08-28 | 2026-09-01 | DGU Assembly Installation | 100 | 62 | Units | 2025-03-26 | 2025-03-26 | 2026-06-15 |  | Tower A | Super Structure |  | Façade | Façade Works
44029 | Tower A - Super Structure - Finishes & MEP - P1 to P3 | Started | Façade Works - MEP & Finishes | 2026-08-28 | 2026-09-03 | Installation of highly reflective metal sheet | 100 | 62 | Units | 2025-03-26 | 2025-03-26 | 2026-06-17 |  | Tower A | Super Structure |  | Façade | Façade Works
44030 | Tower A - Super Structure - Finishes & MEP - P1 to P3 | Started | Façade Works - MEP & Finishes | 2026-08-28 | 2026-09-01 | Fixing of Backlit Laminated Glass assembly & ACP Panels | 100 | 62 | Units | 2025-03-26 | 2025-03-26 | 2025-09-16 |  | Tower A | Super Structure |  | Façade | Façade Works
44031 | Tower A - Super Structure - Finishes & MEP - P1 to P3 | Started | Façade Works - MEP & Finishes | 2026-08-28 | 2026-09-01 | Fixing of Louvers | 100 | 62 | Units | 2025-03-26 | 2025-03-26 | 2026-06-15 |  | Tower A | Super Structure |  | Façade | Façade Works
44031 | Tower A - Super Structure - Finishes & MEP - P1 to P3 | Started | Façade Works - MEP & Finishes | 2026-08-28 | 2026-09-01 | Fixing of Louvers | 100 | 62 | Units | 2025-03-26 | 2025-03-26 | 2026-06-15 |  | Tower A | Super Structure
48395 | Retail - Sub structure - B2 to B1 - P5 | Complete |  | 2025-03-26 | 2025-03-31 | Section 12_lift 1 | 100 | 100 |  | 2025-03-26 | 2025-03-26 | 2025-03-31 | 2025-03-31 | Retail | Sub Structure | B2
48396 | Retail - Sub structure - B2 to B1 - P5 | Complete |  | 2025-03-26 | 2025-03-31 | Section 13_lift 1 | 100 | 100 |  | 2025-03-26 | 2025-03-26 | 2025-03-31 | 2025-03-31 | Retail | Sub Structure | B2
10008 | T-21-2nd Floor | Complete | Conduiting | 2025-04-02 | 2025-04-07 | Conduiting works | 100 | 100 |  | 2025-03-27 | 2025-03-27 | 2025-04-12 | 2025-04-13
39629 | Tower A - Super Structure - Core Wall Mid Rise L54-55 | Complete | Core Wall RCC Works | 2025-03-27 | 2025-03-29 | ACS Form Closing & Alignment | 100 | 100 |  | 2025-03-27 | 2025-03-27 | 2025-03-29 | 2025-03-29 | Tower A | Super Structure | L54 | RCC Super Structure | Core Wall RCC Works
9467 | T-16-Sub structure Basement Part 1 TA | Complete | Conduiting | 2025-03-28 | 2025-04-03 | Conduiting | 100 | 100 |  | 2025-03-28 | 2025-03-28 | 2025-04-19 | 2025-04-20
10007 | T-21-2nd Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-03-27 | 2025-04-12 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-03-28 | 2025-03-28 | 2025-04-14 | 2025-04-15
11037 |  | Started |  | 2025-03-28 | 2026-02-03 | RCC Structure | 100 | 55 |  | 2025-03-28 | 2025-03-28 | 2025-12-13
11038 | T-19-1st Floor | Complete |  | 2025-03-28 | 2025-05-09 | Ground Floor Roof | 100 | 100 |  | 2025-03-28 | 2025-03-28 | 2025-05-26 | 2025-05-27
11039 | T-19-1st Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-03-28 | 2025-04-15 | AL - Shear Walls/Corewalls Steel | 32 | 32 | MT | 2025-03-28 | 2025-03-28 | 2025-04-06 | 2025-04-07
44033 |  | Started |  | 2026-06-30 | 2026-08-20 | P3-L7 (from typ. apt.) | 100 | 55 |  | 2025-03-28 | 2025-03-28 | 2026-06-15
44034 | Tower A - Super Structure - Finishes & MEP - P3 to L7 | Started | Façade Works - MEP & Finishes | 2026-06-30 | 2026-07-10 | Al. Frame section (Mullion & Transom) Installation | 100 | 55 | Unit59s | 2025-03-28 | 2025-03-28 | 2026-06-04 |  | Tower A | Super Structure |  | Façade | Façade Works
44035 | Tower A - Super Structure - Finishes & MEP - P3 to L7 | Started | Façade Works - MEP & Finishes | 2026-07-11 | 2026-07-24 | DGU Assembly Installation | 100 | 55 | Units | 2025-03-28 | 2025-03-28 | 2026-06-10 |  | Tower A | Super Structure |  | Façade | Façade Works
44036 | Tower A - Super Structure - Finishes & MEP - P3 to L7 | Started | Façade Works - MEP & Finishes | 2026-07-11 | 2026-07-31 | Installation of highly reflective metal sheet | 100 | 55 | Units | 2025-03-28 | 2025-03-28 | 2026-06-12 |  | Tower A | Super Structure |  | Façade | Façade Works
44037 | Tower A - Super Structure - Finishes & MEP - P3 to L7 | Started | Façade Works - MEP & Finishes | 2026-07-11 | 2026-07-24 | Fixing of Backlit Laminated Glass assembly & ACP Panels | 100 | 55 | Units | 2025-03-28 | 2025-03-28 | 2025-09-16 |  | Tower A | Super Structure |  | Façade | Façade Works
44038 | Tower A - Super Structure - Finishes & MEP - P3 to L7 | Started | Façade Works - MEP & Finishes | 2026-07-11 | 2026-07-24 | Fixing of Louvers | 100 | 55 | Units | 2025-03-28 | 2025-03-28 | 2026-06-10 |  | Tower A | Super Structure |  | Façade | Façade Works
44038 | Tower A - Super Structure - Finishes & MEP - P3 to L7 | Started | Façade Works - MEP & Finishes | 2026-07-11 | 2026-07-24 | Fixing of Louvers | 100 | 55 | Units | 2025-03-28 | 2025-03-28 | 2026-06-10 |  | Tower A | Super Structure
10524 | T-20-1st Floor | Complete | RCC | 2025-03-29 | 2025-03-29 | Slab& Beam RCC | 315 | 315 | CUM | 2025-03-29 | 2025-03-29 | 2025-03-29 | 2025-03-29
10009 | T-21-2nd Floor | Complete | Shuttering | 2025-04-05 | 2025-04-21 | Slab and Beam Shuttering | 100 | 100 | Sqm | 2025-03-30 | 2025-03-30 | 2025-04-15 | 2025-04-16
11542 |  | Started |  | 2025-03-31 | 2025-05-06 | Basement Roof/Podium Structure Works | 100 | 72 |  | 2025-03-31 | 2025-03-31 | 2025-06-09
11543 |  | Complete |  | 2025-03-31 | 2025-04-26 | Part-1 | 100 | 100 |  | 2025-03-31 | 2025-03-31 | 2025-05-31 | 2025-06-03
11544 | T-18-Sub structure Basement Part 1 TA | Quality checked | Staging | 2025-03-31 | 2025-04-21 | Staging | 100 | 100 |  | 2025-03-31 | 2025-03-31 | 2025-04-25 | 2025-04-26
44032 | Tower A - Super Structure - Finishes & MEP - P1 to P3 | Started | Façade Works - MEP & Finishes | 2026-09-10 | 2026-09-24 | Accessories & Alignment | 100 | 62 | Units | 2025-03-31 | 2025-03-31 | 2026-06-19 |  | Tower A | Super Structure |  | Façade | Façade Works
44032 | Tower A - Super Structure - Finishes & MEP - P1 to P3 | Started | Façade Works - MEP & Finishes | 2026-09-10 | 2026-09-24 | Accessories & Alignment | 100 | 62 | Units | 2025-03-31 | 2025-03-31 | 2026-06-19 |  | Tower A | Super Structure
44039 | Tower A - Super Structure - Finishes & MEP - P3 to L7 | Started | Façade Works - MEP & Finishes | 2026-08-06 | 2026-08-20 | Accessories & Alignment | 100 | 55 | Units | 2025-03-31 | 2025-03-31 | 2026-06-15 |  | Tower A | Super Structure |  | Façade | Façade Works
44039 | Tower A - Super Structure - Finishes & MEP - P3 to L7 | Started | Façade Works - MEP & Finishes | 2026-08-06 | 2026-08-20 | Accessories & Alignment | 100 | 55 | Units | 2025-03-31 | 2025-03-31 | 2026-06-15 |  | Tower A | Super Structure
48397 | Retail - Sub structure - B2 to B1 - P5 | Milestone Started |  | 2025-03-31 |  | Section 14_lift 1 | 100 | 100 |  | 2025-03-31 | 2025-03-31 |  |  | Retail | Sub Structure | B2
48398 | Retail - Sub structure - B2 to B1 - P5 | Milestone Started |  | 2025-03-31 |  | Section 15_lift 1 | 100 | 100 |  | 2025-03-31 | 2025-03-31 |  |  | Retail | Sub Structure | B2
11545 | T-18-Sub structure Basement Part 1 TA | Complete | Formwork | 2025-04-01 | 2025-04-26 | Formwork | 1054.334 | 1054.334 | Sqm | 2025-04-01 | 2025-04-01 | 2025-05-31 | 2025-05-10
39630 | Tower A - Super Structure - Core Wall Mid Rise L54-55 | Milestone Started | Core Wall RCC Works | 2025-04-01 |  | Casting | 100 | 100 |  | 2025-04-01 | 2025-04-01 |  |  | Tower A | Super Structure | L54 | RCC Super Structure | Core Wall RCC Works
39631 | Tower A - Super Structure - Core Wall Mid Rise L54-55 | Complete | Core Wall RCC Works | 2025-04-01 | 2025-04-01 | ACS Form Release & jump to next level | 100 | 100 |  | 2025-04-01 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Tower A | Super Structure | L54 | RCC Super Structure | Core Wall RCC Works
39638 |  | Complete |  | 2025-04-15 | 2025-04-30 | Core Wall L56-57 | 100 | 100 |  | 2025-04-01 | 2025-04-01 | 2025-04-30 | 2025-04-30
39953 |  | Complete |  | 2025-04-01 | 2025-04-27 | L50-51 | 100 | 100 |  | 2025-04-01 | 2025-04-01 | 2025-04-27 | 2025-04-27
39953 |  | Complete |  | 2025-04-01 | 2025-04-27 | L50-51 | 100 | 100 |  | 2025-04-01 | 2025-04-01 | 2025-04-27 | 2025-04-27 |  |  |  | Finishes | Gypsum Plastering Works
39954 | Tower A - Super Structure - Core & Outer Slab L50-51 | Complete | RCC Works - Vertical | 2025-04-01 | 2025-04-20 | Outer Columns_TA | 100 | 100 |  | 2025-04-01 | 2025-04-01 | 2025-04-20 | 2025-04-20 | Tower A | Super Structure | L50 | RCC Sub Structure | RCC Works - Vertical
44043 | Tower A - Super Structure - Finishes & MEP - L7 to L13 | Started | Façade Works - MEP & Finishes | 2025-04-01 | 2025-04-11 | DGU Assembly Installation | 100 | 61 | Units | 2025-04-01 | 2025-04-01 | 2025-09-30 |  | Tower A | Super Structure | L7 | Façade | Façade Works
44045 | Tower A - Super Structure - Finishes & MEP - L7 to L13 | Started | Façade Works - MEP & Finishes | 2025-04-01 | 2025-04-08 | Fixing of Backlit Laminated Glass assembly & ACP Panels | 100 | 61 | Units | 2025-04-01 | 2025-04-01 | 2025-09-16 |  | Tower A | Super Structure | L7 | Façade | Façade Works
8417 | T-14-2nd Floor | Quality checked | Slab& Beam Steel & Conduting | 2025-04-02 | 2025-04-10 | Slab& Beam Steel & Conduting | 10 | 10 | MT | 2025-04-02 | 2025-04-02 | 2025-05-19 | 2025-05-15
9472 | T-16-Sub structure Basement Part 2 NTA | Started | Reinforcement | 2025-04-02 | 2025-04-12 | Reinforcement | 59 | 2 | MT | 2025-04-02 | 2025-04-02 | 2025-05-21
10525 | T-20-2nd Floor | Complete |  | 2025-04-02 | 2025-05-06 | 1st Floor Roof | 100 | 100 |  | 2025-04-02 | 2025-04-02 | 2025-04-22 | 2025-04-23
10526 | T-20-2nd Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-04-02 | 2025-04-15 | AL - Shear Walls/Corewalls Steel | 100 | 100 | MT | 2025-04-02 | 2025-04-02 | 2025-04-09 | 2025-04-10
39632 |  | Complete |  | 2025-04-02 | 2025-04-14 | Core Wall L55-56 | 100 | 100 |  | 2025-04-02 | 2025-04-02 | 2025-04-14 | 2025-04-14
39633 | Tower A - Super Structure - Core Wall Mid Rise L55-56 | Complete | Core Wall RCC Works | 2025-04-02 | 2025-04-02 | Scaffolding & platform | 100 | 100 |  | 2025-04-02 | 2025-04-02 | 2025-04-02 | 2025-04-02 | Tower A | Super Structure | L55 | RCC Super Structure | Core Wall RCC Works
10528 | T-20-2nd Floor | Complete | Conduiting | 2025-04-15 | 2025-04-19 | Conduiting works | 100 | 100 |  | 2025-04-03 | 2025-04-03 | 2025-04-10 | 2025-04-11
11041 | T-19-1st Floor | Quality checked | Conduiting | 2025-04-15 | 2025-04-26 | Conduiting works | 100 | 100 | Units | 2025-04-03 | 2025-04-03 | 2025-05-21 | 2025-05-14
39634 | Tower A - Super Structure - Core Wall Mid Rise L55-56 | Complete | Core Wall RCC Works | 2025-04-03 | 2025-04-05 | Reinf & Guide shoes fixing | 100 | 100 |  | 2025-04-03 | 2025-04-03 | 2025-04-05 | 2025-04-05 | Tower A | Super Structure | L55 | RCC Super Structure | Core Wall RCC Works
39955 | Tower A - Super Structure - Core & Outer Slab L50-51 | Complete | RCC Works - Slab | 2025-04-03 | 2025-04-27 | Outer Slab_TA | 100 | 100 |  | 2025-04-03 | 2025-04-03 | 2025-04-27 | 2025-04-27 | Tower A | Super Structure | L50 | RCC Sub Structure | RCC Works - Slab
10527 | T-20-2nd Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-04-06 | 2025-04-19 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-04-04 | 2025-04-04 | 2025-04-10 | 2025-04-11
11040 | T-19-1st Floor | Quality checked | Shear Walls/Corewalls Shuttering | 2025-04-02 | 2025-04-29 | Shear Walls/Corewalls Shuttering | 100 | 100 | Units | 2025-04-04 | 2025-04-04 | 2025-04-26 | 2025-05-16
39635 | Tower A - Super Structure - Core Wall Mid Rise L55-56 | Complete | Core Wall RCC Works | 2025-04-04 | 2025-04-07 | ACS Form Closing & Alignment | 100 | 100 |  | 2025-04-04 | 2025-04-04 | 2025-04-07 | 2025-04-07 | Tower A | Super Structure | L55 | RCC Super Structure | Core Wall RCC Works
8418 | T-14-2nd Floor | Quality checked | RCC | 2025-04-10 | 2025-04-11 | Slab& Beam RCC(Pour 1 & Pour 2 | 307 | 307 | CUM | 2025-04-05 | 2025-04-05 | 2025-05-20 | 2025-05-16
11550 | T-18-Sub structure Basement Part 2 NTA | Not Ready | Staging | 2025-04-05 | 2025-04-21 | Staging | 100 | 0 |  | 2025-04-05 |  | 2025-04-19
10529 | T-20-2nd Floor | Complete | Shuttering | 2025-04-16 | 2025-05-02 | Slab and Beam Shuttering | 100 | 100 | Sqm | 2025-04-06 | 2025-04-06 | 2025-04-14 | 2025-04-15
44949 |  | Started |  | 2024-12-27 | 2027-05-28 | Super-Structure_TB | 100 | 18 |  | 2025-04-08 | 2025-04-08 | 2027-06-29
45248 |  | Started |  | 2025-04-08 | 2027-05-28 | TB_Core & Outer Slab | 100 | 18 |  | 2025-04-08 | 2025-04-08 | 2027-06-29
45249 |  | Complete |  | 2025-04-08 | 2025-04-15 | GF-P1 | 100 | 100 |  | 2025-04-08 | 2025-04-08 | 2025-04-15 | 2025-05-21
45250 | Tower B - Super Structure - Core & Outer Slab GF-P1 | Complete | RCC Works - Vertical | 2025-04-08 | 2025-04-08 | Outer Columns & Reckli Wall Sections_TB | 100 | 100 |  | 2025-04-08 | 2025-04-08 | 2025-04-08 | 2025-05-21 | Tower B | Super Structure | GF | RCC Sub Structure | RCC Works - Vertical
39636 | Tower A - Super Structure - Core Wall Mid Rise L55-56 | Complete | Core Wall RCC Works | 2025-04-09 | 2025-04-12 | Casting | 100 | 100 |  | 2025-04-09 | 2025-04-09 | 2025-04-12 | 2025-04-12 | Tower A | Super Structure | L55 | RCC Super Structure | Core Wall RCC Works
11551 | T-18-Sub structure Basement Part 2 NTA | Not Ready | Formwork | 2025-04-10 | 2025-04-26 | Formwork | 3050 | 0 | Sqm | 2025-04-10 |  | 2025-04-25
11042 | T-19-1st Floor | Quality checked | Shuttering | 2025-04-18 | 2025-05-06 | Slab and Beam Shuttering | 3548 | 3548 | Sqm | 2025-04-11 | 2025-05-11 | 2025-05-26 | 2025-05-17
40276 | Tower A - Super Structure - Finishes & MEP - L31 to L32 | Complete | Partition Wall-Blockwork | 2025-04-11 | 2025-04-16 | Staircase Area | 100 | 100 |  | 2025-04-11 | 2025-04-11 | 2025-04-16 | 2025-04-16 | Tower A | Super Structure | L31
40279 | Tower A - Super Structure - Finishes & MEP - L32 to L33 | Complete | Partition Wall-Blockwork | 2025-04-11 | 2025-04-18 | Partition Walls | 100 | 100 |  | 2025-04-11 | 2025-04-11 | 2025-04-18 | 2025-04-18 | Tower A | Super Structure | L32
10530 | T-20-2nd Floor | Complete | Slab& Beam Steel & Conduting | 2025-04-25 | 2025-05-05 | Slab& Beam Steel & Conduting | 100 | 100 | MT | 2025-04-12 | 2025-04-12 | 2025-04-21 | 2025-04-22
11029 |  | Started |  | 2025-03-06 | 2025-04-09 | Part-2 | 100 | 2 |  | 2025-04-12 | 2025-04-12 | 2025-05-31
11030 | T-19-Sub structure Basement Part 2 NTA | Started | Staging | 2025-03-06 | 2025-03-22 | Staging | 100 | 2 |  | 2025-04-12 | 2025-04-12 | 2025-05-26
44044 | Tower A - Super Structure - Finishes & MEP - L7 to L13 | Started | Façade Works - MEP & Finishes | 2025-04-12 | 2025-04-26 | Installation of highly reflective metal sheet | 100 | 61 | Units | 2025-04-12 | 2025-04-12 | 2025-10-01 |  | Tower A | Super Structure | L7 | Façade | Façade Works
44046 | Tower A - Super Structure - Finishes & MEP - L7 to L13 | Started | Façade Works - MEP & Finishes | 2025-04-12 | 2025-04-23 | Fixing of Louvers | 100 | 61 | Units | 2025-04-12 | 2025-07-03 | 2025-09-27 |  | Tower A | Super Structure | L7 | Façade | Façade Works
44046 | Tower A - Super Structure - Finishes & MEP - L7 to L13 | Started | Façade Works - MEP & Finishes | 2025-04-12 | 2025-04-23 | Fixing of Louvers | 100 | 61 | Units | 2025-04-12 | 2025-07-03 | 2025-09-27 |  | Tower A | Super Structure | L7
10010 | T-21-2nd Floor | Complete | Slab& Beam Steel & Conduting | 2025-04-15 | 2025-04-24 | Slab& Beam Steel & Conduting | 100 | 100 | MT | 2025-04-13 | 2025-04-13 | 2025-04-18 | 2025-04-19
39637 | Tower A - Super Structure - Core Wall Mid Rise L55-56 | Complete | Core Wall RCC Works | 2025-04-14 | 2025-04-14 | ACS Form Release & jump to next level | 100 | 100 |  | 2025-04-14 | 2025-04-14 | 2025-04-14 | 2025-04-14 | Tower A | Super Structure | L55 | RCC Super Structure | Core Wall RCC Works
11031 | T-19-Sub structure Basement Part 2 NTA | Started | Formwork | 2025-03-11 | 2025-04-03 | Formwork | 1920 | 2 | Sqm | 2025-04-15 | 2025-04-15 | 2025-05-31
11552 | T-18-Sub structure Basement Part 2 NTA | Not Ready | Reinforcement | 2025-04-16 | 2025-05-03 | Reinforcement | 49 | 0 | MT | 2025-04-15 |  | 2025-04-30
39639 | Tower A - Super Structure - Core Wall Mid Rise L56-57 | Complete | Core Wall RCC Works | 2025-04-15 | 2025-04-15 | Scaffolding & platform | 100 | 100 | Units | 2025-04-15 | 2025-04-15 | 2025-04-15 | 2025-04-15 | Tower A | Super Structure | L56 | RCC Super Structure | Core Wall RCC Works
45251 | Tower B - Super Structure - Core & Outer Slab GF-P1 | Complete | RCC Works - Slab | 2025-04-15 | 2025-04-15 | Outer Slab_TB | 100 | 100 |  | 2025-04-15 | 2025-04-15 | 2025-04-15 | 2025-05-21 | Tower B | Super Structure | GF | RCC Sub Structure | RCC Works - Slab
39640 | Tower A - Super Structure - Core Wall Mid Rise L56-57 | Complete | Core Wall RCC Works | 2025-04-16 | 2025-04-18 | Reinf & Guide shoes fixing | 100 | 100 | Units | 2025-04-16 | 2025-04-16 | 2025-04-18 | 2025-04-18 | Tower A | Super Structure | L56 | RCC Super Structure | Core Wall RCC Works
39641 | Tower A - Super Structure - Core Wall Mid Rise L56-57 | Complete | Core Wall RCC Works | 2025-04-17 | 2025-04-24 | ACS Form Closing & Alignment | 100 | 100 | Units | 2025-04-17 | 2025-04-17 | 2025-04-24 | 2025-04-24 | Tower A | Super Structure | L56 | RCC Super Structure | Core Wall RCC Works
42632 |  | Started |  | 2025-04-17 | 2026-07-10 | L31-32 | 100 | 37 |  | 2025-04-17 | 2025-04-17 | 2026-07-08 |  |  |  |  | Finishes | Gypsum Plastering Works
42632 |  | Started |  | 2025-04-17 | 2026-07-10 | L31-32 | 100 | 37 |  | 2025-04-17 | 2025-04-17 | 2026-07-08
42633 |  | Started |  | 2025-04-17 | 2025-05-16 | MEP 1st Fixes | 100 | 42 |  | 2025-04-17 | 2025-04-17 | 2025-10-07
42634 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Apartment Area | Started | FPS 1st Fix - MEP & Finishes | 2025-04-17 | 2025-04-24 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 35 | Units | 2025-04-17 | 2025-04-17 | 2025-09-16 |  | Tower A | Super Structure | L31 | MEP | FPS 1st Fix - MEP & Finishes
42635 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Apartment Area | Started | Electrical 1st Fix - MEP & Finishes | 2025-04-17 | 2025-04-18 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 70 |  | 2025-04-17 | 2025-04-17 | 2025-09-12 |  | Tower A | Super Structure | L31 | MEP | Electrical 1st Fixes
42636 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Apartment Area | Started | PHE 1st Fix - MEP & Finishes | 2025-04-17 | 2025-04-22 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 40 |  | 2025-04-17 | 2025-04-17 | 2025-09-16 |  | Tower A | Super Structure | L31
42637 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Apartment Area | Started | Wet Area Waterproofing - MEP & Finishes | 2025-04-17 | 2025-04-29 | Wet Area Waterproofing | 100 | 30 |  | 2025-04-17 | 2025-04-17 | 2025-09-24 |  | Tower A | Super Structure | L31
9473 | T-16-Sub structure Basement Part 2 NTA | Started | Conduiting | 2025-04-09 | 2025-04-11 | Conduiting | 100 | 2 |  | 2025-04-18 | 2025-04-18 | 2025-05-12
39172 |  | Complete |  | 2025-04-18 | 2025-05-08 | Parapet Wall Casting | 100 | 100 |  | 2025-04-18 | 2025-05-30 | 2025-05-08 | 2025-05-30
10011 | T-21-2nd Floor | Complete | RCC | 2025-04-24 | 2025-04-25 | Slab& Beam RCC | 100 | 100 | CUM | 2025-04-19 | 2025-04-19 | 2025-04-19 | 2025-04-20
40280 | Tower A - Super Structure - Finishes & MEP - L32 to L33 | Complete | Partition Wall-Blockwork | 2025-04-19 | 2025-04-24 | Staircase Area | 100 | 100 |  | 2025-04-19 | 2025-04-19 | 2025-04-24 | 2025-04-24 | Tower A | Super Structure | L32
40283 | Tower A - Super Structure - Finishes & MEP - L33 to L34 | Complete | Partition Wall-Blockwork | 2025-04-19 | 2025-04-22 | Partition Walls | 100 | 100 |  | 2025-04-19 | 2025-04-19 | 2025-04-22 | 2025-05-22 | Tower A | Super Structure | L33
9468 | T-16-GF | Complete | Concrete | 2025-04-03 | 2025-04-05 | Concrete | 276 | 276 | CUM | 2025-04-20 | 2025-04-20 | 2025-04-21 | 2025-04-22
9474 | T-16-Sub structure Basement Part 2 NTA | Started | Concrete | 2025-04-11 | 2025-04-14 | Concrete | 592.4 | 2 | CUM | 2025-04-20 | 2025-04-20 | 2025-05-14
10012 | T-21-3rd Floor | Complete |  | 2025-04-27 | 2025-06-01 | 2nd Floor Roof | 100 | 100 |  | 2025-04-20 | 2025-04-20 | 2025-05-17 | 2025-05-01
10013 | T-21-3rd Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-04-27 | 2025-05-12 | AL - Shear Walls/Corewalls Steel | 100 | 100 | MT | 2025-04-20 | 2025-04-20 | 2025-05-13 | 2025-04-26
11032 | T-19-Sub structure Basement Part 2 NTA | Started | Reinforcement | 2025-03-22 | 2025-04-05 | Reinforcement | 49.8 | 2 | MT | 2025-04-20 | 2025-04-20 | 2025-05-23
10015 | T-21-3rd Floor | Complete | Conduiting | 2025-05-12 | 2025-05-16 | Conduiting works | 100 | 100 |  | 2025-04-21 | 2025-04-21 | 2025-05-17 | 2025-04-28
39642 | Tower A - Super Structure - Core Wall Mid Rise L56-57 | Complete | Core Wall RCC Works | 2025-04-21 | 2025-04-29 | Casting | 100 | 100 | Units | 2025-04-21 | 2025-04-29 | 2025-04-29 | 2025-04-29 | Tower A | Super Structure | L56 | RCC Super Structure | Core Wall RCC Works
10014 | T-21-3rd Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-05-02 | 2025-05-16 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-04-22 | 2025-04-22 | 2025-05-13 | 2025-04-28
10531 | T-20-2nd Floor | Complete | RCC | 2025-05-05 | 2025-05-06 | Slab& Beam RCC | 100 | 100 | CUM | 2025-04-22 | 2025-04-22 | 2025-04-22 | 2025-04-23
9477 |  | Started |  | 2025-04-08 | 2026-02-24 | RCC Structure | 100 | 55 |  | 2025-04-23 | 2025-04-23 | 2025-12-26
9478 | T-16-1st Floor | Complete |  | 2025-04-08 | 2025-05-29 | Ground Floor Roof | 100 | 100 |  | 2025-04-23 | 2025-04-23 | 2025-06-06 | 2025-06-16
9479 | T-16-1st Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-04-08 | 2025-04-24 | AL - Shear Walls/Corewalls Steel | 32 | 32 | MT | 2025-04-23 | 2025-04-23 | 2025-05-16 | 2025-05-10
10016 | T-21-3rd Floor | Complete | Shuttering | 2025-05-13 | 2025-05-28 | Slab and Beam Shuttering | 100 | 100 | Sqm | 2025-04-24 | 2025-04-24 | 2025-05-17 | 2025-04-29
10532 | T-20-3rd Floor | Complete |  | 2025-05-09 | 2025-06-12 | 2nd Floor Roof | 100 | 100 |  | 2025-04-24 | 2025-04-24 | 2025-05-22 | 2025-05-10
10533 | T-20-3rd Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-05-09 | 2025-05-23 | AL - Shear Walls/Corewalls Steel | 100 | 100 | MT | 2025-04-24 | 2025-04-24 | 2025-05-13 | 2025-05-03
10611 | T-20-Basement Floor | Forced Ready | Masonry Works | 2025-05-06 | 2025-08-13 | Masonry Works | 100 | 0 |  | 2025-04-24 |  | 2025-07-30
11009 |  | Started |  | 2025-03-06 | 2025-04-06 | Columns | 100 | 25 |  | 2025-04-24 | 2025-04-24 | 2025-05-31
11010 | T-19-Sub structure Columns | Started | Reinforcement | 2025-03-06 | 2025-03-28 | Reinforcement | 3 | 2 | MTon | 2025-04-24 | 2025-04-24 | 2025-05-31
8963 | T-15-1st Floor | Complete | Slab& Beam Steel & Conduting | 2025-03-26 | 2025-04-05 | Slab& Beam Steel & Conduting | 100 | 100 |  | 2025-04-25 | 2025-04-25 | 2025-05-10 | 2025-05-08
9481 | T-16-1st Floor | Complete | Conduiting | 2025-04-24 | 2025-05-07 | Conduiting works | 100 | 100 |  | 2025-04-25 | 2025-04-25 | 2025-05-29 | 2025-06-10
10017 | T-21-3rd Floor | Complete | Slab& Beam Steel & Conduting | 2025-05-22 | 2025-05-31 | Slab& Beam Steel & Conduting | 100 | 100 | MT | 2025-04-25 | 2025-04-25 | 2025-05-13 | 2025-04-30
10535 | T-20-3rd Floor | Complete | Conduiting | 2025-05-09 | 2025-05-14 | Conduiting works | 100 | 100 |  | 2025-04-25 | 2025-04-25 | 2025-05-04 | 2025-05-04
10536 | T-20-3rd Floor | Complete | Shuttering | 2025-05-24 | 2025-06-08 | Slab and Beam Shuttering | 100 | 100 | Sqm | 2025-04-25 | 2025-04-25 | 2025-05-22 | 2025-05-07
11011 | T-19-Sub structure Columns | Started | Shuttering | 2025-03-10 | 2025-04-02 | Shuttering | 319 | 2 | Sqm | 2025-04-25 | 2025-04-25 | 2025-05-31
11546 | T-18-Sub structure Basement Part 1 TA | Complete | Reinforcement | 2025-04-08 | 2025-04-24 | Reinforcement | 18 | 18 | MT | 2025-04-25 | 2025-04-25 | 2025-05-26 | 2025-05-11
42650 |  | Started |  | 2025-04-25 | 2026-07-10 | L32-33 | 100 | 35 |  | 2025-04-25 | 2025-04-24 | 2026-07-08 |  |  |  |  | Finishes | Gypsum Plastering Works
42650 |  | Started |  | 2025-04-25 | 2026-07-10 | L32-33 | 100 | 35 |  | 2025-04-25 | 2025-04-24 | 2026-07-08
42651 |  | Started |  | 2025-04-25 | 2025-05-24 | MEP 1st Fixes | 100 | 40 |  | 2025-04-25 | 2025-04-24 | 2025-10-08
42652 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Apartment Area | Started | FPS 1st Fix - MEP & Finishes | 2025-04-25 | 2025-05-03 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 35 | Units | 2025-04-25 | 2025-04-24 | 2025-09-16 |  | Tower A | Super Structure | L32 | MEP | FPS 1st Fix - MEP & Finishes
42653 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Apartment Area | Started | Electrical 1st Fix - MEP & Finishes | 2025-04-25 | 2025-04-26 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 70 |  | 2025-04-25 | 2025-04-25 | 2025-09-12 |  | Tower A | Super Structure | L32 | MEP | Electrical 1st Fixes
42654 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Apartment Area | Started | PHE 1st Fix - MEP & Finishes | 2025-04-25 | 2025-04-30 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 40 |  | 2025-04-25 | 2025-04-25 | 2025-09-16 |  | Tower A | Super Structure | L32
42655 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Apartment Area | Started | Wet Area Waterproofing - MEP & Finishes | 2025-04-25 | 2025-05-09 | Wet Area Waterproofing | 100 | 20 |  | 2025-04-25 | 2025-04-25 | 2025-09-25 |  | Tower A | Super Structure | L32
9480 | T-16-1st Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-04-14 | 2025-05-12 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-04-26 | 2025-04-26 | 2025-06-06 | 2025-06-11
10534 | T-20-3rd Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-05-14 | 2025-05-27 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-04-26 | 2025-04-26 | 2025-05-13 | 2025-05-04
11012 | T-19-Sub structure Columns | Started | RCC | 2025-03-14 | 2025-04-06 | RCC | 35 | 2 | CUM | 2025-04-26 | 2025-04-26 | 2025-05-31
11012 | T-19-Sub structure Columns | Started | RCC | 2025-03-14 | 2025-04-06 | RCC | 35 | 2 | CUM | 2025-04-26 | 2025-04-26 | 2025-05-31
45252 |  | Complete |  | 2025-04-26 | 2025-05-10 | P1-P2 | 100 | 100 |  | 2025-04-26 | 2025-05-10 | 2025-05-10 | 2025-07-18
45253 | Tower B - Super Structure - Core & Outer Slab P1-P2 | Complete | RCC Works - Vertical | 2025-04-26 | 2025-05-06 | Outer Columns & Reckli Wall Sections_TA | 100 | 100 | Units | 2025-04-26 | 2025-05-10 | 2025-05-06 | 2025-07-12 | Tower B | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
9482 | T-16-1st Floor | Complete | Shuttering | 2025-04-30 | 2025-05-23 | Slab and Beam Shuttering | 4183 | 4183 | Sqm | 2025-04-28 | 2025-04-28 | 2025-06-05 | 2025-06-14
11033 | T-19-Sub structure Basement Part 2 NTA | Started | Conduiting | 2025-04-03 | 2025-04-07 | Conduiting | 100 | 2 |  | 2025-04-28 | 2025-04-28 | 2025-05-14
11547 | T-18-Sub structure Basement Part 1 TA | Quality checked | Conduiting | 2025-04-19 | 2025-04-25 | Conduiting | 100 | 100 |  | 2025-04-28 | 2025-04-28 | 2025-05-16 | 2025-06-03
39956 |  | Complete |  | 2025-04-28 | 2025-05-06 | L51-52 | 100 | 100 |  | 2025-04-28 | 2025-05-20 | 2025-05-06 | 2025-05-20
39956 |  | Complete |  | 2025-04-28 | 2025-05-06 | L51-52 | 100 | 100 |  | 2025-04-28 | 2025-05-20 | 2025-05-06 | 2025-05-20 |  |  |  | Finishes | Gypsum Plastering Works
39957 | Tower A - Super Structure - Core & Outer Slab L51-52 | Complete | RCC Works - Vertical | 2025-04-28 | 2025-05-05 | Outer Columns_TA | 100 | 100 |  | 2025-04-28 | 2025-05-20 | 2025-05-05 | 2025-05-20 | Tower A | Super Structure | L51 | RCC Sub Structure | RCC Works - Vertical
40284 | Tower A - Super Structure - Finishes & MEP - L33 to L34 | Complete | Partition Wall-Blockwork | 2025-04-28 | 2025-05-03 | Staircase Area | 100 | 100 |  | 2025-04-28 | 2025-05-22 | 2025-05-03 | 2025-05-22 | Tower A | Super Structure | L33
40287 | Tower A - Super Structure - Finishes & MEP - L34 to L35 | Complete | Partition Wall-Blockwork | 2025-04-28 | 2025-05-02 | Partition Walls | 100 | 100 |  | 2025-04-28 | 2025-04-28 | 2025-05-02 | 2025-05-02 | Tower A | Super Structure | L34
10537 | T-20-3rd Floor | Complete | Slab& Beam Steel & Conduting | 2025-06-03 | 2025-06-11 | Slab& Beam Steel & Conduting | 100 | 100 | MT | 2025-04-29 | 2025-04-29 | 2025-05-07 | 2025-05-08
10018 | T-21-3rd Floor | Complete | RCC | 2025-05-31 | 2025-06-01 | Slab& Beam RCC | 100 | 100 | CUM | 2025-04-30 | 2025-05-01 | 2025-04-30 | 2025-05-01
39643 | Tower A - Super Structure - Core Wall Mid Rise L56-57 | Complete | Core Wall RCC Works | 2025-04-30 | 2025-04-30 | ACS Form Release & jump to next level | 100 | 100 | Units | 2025-04-30 | 2025-04-30 | 2025-04-30 | 2025-04-30 | Tower A | Super Structure | L56 | RCC Super Structure | Core Wall RCC Works
39958 | Tower A - Super Structure - Core & Outer Slab L51-52 | Complete | RCC Works - Slab | 2025-04-30 | 2025-05-06 | Outer Slab_TA | 100 | 100 |  | 2025-04-30 | 2025-05-20 | 2025-05-06 | 2025-05-20 | Tower A | Super Structure | L51 | RCC Sub Structure | RCC Works - Slab
10019 | T-21-4th Floor | Complete |  | 2025-06-02 | 2025-06-15 | 3rd Floor Roof | 100 | 100 |  | 2025-05-02 | 2025-05-02 | 2025-05-14 | 2025-05-15
10020 | T-21-4th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-06-02 | 2025-06-06 | AL - Shear Walls/Corewalls Steel | 100 | 100 | MT | 2025-05-02 | 2025-05-02 | 2025-05-05 | 2025-05-06
39644 |  | Complete |  | 2025-05-02 | 2025-05-16 | Core Wall L57-58 | 100 | 100 |  | 2025-05-02 | 2025-05-01 | 2025-05-16 | 2025-05-30
39645 | Tower A - Super Structure - Core Wall Mid Rise L57-58 | Complete | Core Wall RCC Works | 2025-05-02 | 2025-05-02 | Scaffolding & platform | 100 | 100 |  | 2025-05-02 | 2025-05-01 | 2025-05-02 | 2025-05-24 | Tower A | Super Structure | L57 | RCC Super Structure | Core Wall RCC Works
45254 | Tower B - Super Structure - Core & Outer Slab P1-P2 | Complete | RCC Works - Slab | 2025-05-02 | 2025-05-10 | Outer Slab_TA | 100 | 100 | Units | 2025-05-02 | 2025-05-13 | 2025-05-10 | 2025-07-18 | Tower B | Super Structure |  | RCC Sub Structure | RCC Works - Slab
10022 | T-21-4th Floor | Complete | Conduiting | 2025-06-04 | 2025-06-07 | Conduiting works | 100 | 100 |  | 2025-05-03 | 2025-05-03 | 2025-05-09 | 2025-05-10
39646 | Tower A - Super Structure - Core Wall Mid Rise L57-58 | Complete | Core Wall RCC Works | 2025-05-03 | 2025-05-06 | Reinf & Guide shoes fixing | 100 | 100 |  | 2025-05-03 | 2025-05-08 | 2025-05-06 | 2025-05-27 | Tower A | Super Structure | L57 | RCC Super Structure | Core Wall RCC Works
10021 | T-21-4th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-06-05 | 2025-06-10 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-05-04 | 2025-05-04 | 2025-05-09 | 2025-05-10
10023 | T-21-4th Floor | Complete | Shuttering | 2025-06-09 | 2025-06-13 | Slab and Beam Shuttering | 3264 | 3264 | Sqm | 2025-05-05 | 2025-05-05 | 2025-05-14 | 2025-05-10
39647 | Tower A - Super Structure - Core Wall Mid Rise L57-58 | Complete | Core Wall RCC Works | 2025-05-05 | 2025-05-07 | ACS Form Closing & Alignment | 100 | 100 |  | 2025-05-05 | 2025-05-17 | 2025-05-07 | 2025-05-28 | Tower A | Super Structure | L57 | RCC Super Structure | Core Wall RCC Works
42668 |  | Started |  | 2025-05-05 | 2026-07-10 | L33-34 | 100 | 10 |  | 2025-05-05 | 2025-05-05 | 2026-07-08 |  |  |  |  | Finishes | Gypsum Plastering Works
42668 |  | Started |  | 2025-05-05 | 2026-07-10 | L33-34 | 100 | 10 |  | 2025-05-05 | 2025-05-05 | 2026-07-08
42669 |  | Started |  | 2025-05-05 | 2025-06-02 | MEP 1st Fixes | 100 | 12 |  | 2025-05-05 | 2025-05-05 | 2025-10-11
42670 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Apartment Area | Started | FPS 1st Fix - MEP & Finishes | 2025-05-05 | 2025-05-12 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 25 | Units | 2025-05-05 | 2025-05-05 | 2025-09-18 |  | Tower A | Super Structure | L33 | MEP | FPS 1st Fix - MEP & Finishes
42671 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Apartment Area | Started | Electrical 1st Fix - MEP & Finishes | 2025-05-05 | 2025-05-09 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 15 | Units | 2025-05-05 | 2025-05-05 | 2025-09-16 |  | Tower A | Super Structure | L33 | MEP | Electrical 1st Fixes
42672 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Apartment Area | Started | PHE 1st Fix - MEP & Finishes | 2025-05-05 | 2025-05-12 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2025-05-05 | 2025-05-05 | 2025-09-19 |  | Tower A | Super Structure | L33
48300 |  | Complete |  | 2025-05-05 | 2025-05-28 | Pour RT-5 | 100 | 100 |  | 2025-05-05 | 2025-05-05 | 2025-05-28 | 2025-05-28
48301 | Retail - Sub structure - B1 to GF - P5 | Complete |  | 2025-05-05 | 2025-05-12 | Section 10_lift 2 | 100 | 100 |  | 2025-05-05 | 2025-05-05 | 2025-05-12 | 2025-05-12 | Retail | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
48301 | Retail - Sub structure - B1 to GF - P5 | Complete |  | 2025-05-05 | 2025-05-12 | Section 10_lift 2 | 100 | 100 |  | 2025-05-05 | 2025-05-05 | 2025-05-12 | 2025-05-12 | Retail | Sub Structure | B1
48302 | Retail - Sub structure - B1 to GF - P5 | Complete |  | 2025-05-05 | 2025-05-12 | Section 11_lift 2 | 100 | 100 |  | 2025-05-05 | 2025-05-05 | 2025-05-12 | 2025-05-12 | Retail | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
48302 | Retail - Sub structure - B1 to GF - P5 | Complete |  | 2025-05-05 | 2025-05-12 | Section 11_lift 2 | 100 | 100 |  | 2025-05-05 | 2025-05-05 | 2025-05-12 | 2025-05-12 | Retail | Sub Structure | B1
39173 |  | Complete |  | 2025-05-06 | 2025-05-26 | Deshuttering & Staging Removal | 100 | 100 |  | 2025-05-06 | 2025-05-22 | 2025-05-26 | 2025-05-22
8419 | T-14-3rd Floor | Quality checked |  | 2025-04-14 | 2025-05-19 | 2nd Floor Roof | 100 | 100 |  | 2025-05-07 | 2025-05-07 | 2025-06-06 | 2025-06-26
8420 | T-14-3rd Floor | Quality checked | AL - Shear Walls/Corewalls Steel | 2025-04-14 | 2025-04-26 | AL - Shear Walls/Corewalls Steel | 22 | 22 | MT | 2025-05-07 | 2025-05-07 | 2025-06-04 | 2025-05-30
39959 |  | Complete |  | 2025-05-07 | 2025-05-14 | L52-53 | 100 | 100 |  | 2025-05-07 | 2025-05-13 | 2025-05-14 | 2025-05-31
39959 |  | Complete |  | 2025-05-07 | 2025-05-14 | L52-53 | 100 | 100 |  | 2025-05-07 | 2025-05-13 | 2025-05-14 | 2025-05-31 |  |  |  | Finishes | Gypsum Plastering Works
39960 | Tower A - Super Structure - Core & Outer Slab L52-53 | Complete | RCC Works - Vertical | 2025-05-07 | 2025-05-13 | Outer Columns_TA | 100 | 100 |  | 2025-05-07 | 2025-05-13 | 2025-05-13 | 2025-05-29 | Tower A | Super Structure | L52 | RCC Sub Structure | RCC Works - Vertical
40288 | Tower A - Super Structure - Finishes & MEP - L34 to L35 | Complete | Partition Wall-Blockwork | 2025-05-07 | 2025-05-12 | Staircase Area | 100 | 100 |  | 2025-05-07 | 2025-05-22 | 2025-05-12 | 2025-06-05 | Tower A | Super Structure | L34
40291 | Tower A - Super Structure - Finishes & MEP - L35 to L36 | Complete | Partition Wall-Blockwork | 2025-05-07 | 2025-05-14 | Partition Walls | 100 | 100 |  | 2025-05-07 | 2025-05-22 | 2025-05-14 | 2025-06-05 | Tower A | Super Structure | L35
8964 | T-15-1st Floor | Complete | RCC | 2025-04-05 | 2025-04-07 | Slab& Beam RCC | 315 | 315 | CUM | 2025-05-08 | 2025-05-08 | 2025-05-09 | 2025-05-10
10024 | T-21-4th Floor | Quality checked | Slab& Beam Steel & Conduting | 2025-06-11 | 2025-06-14 | Slab& Beam Steel & Conduting | 19.5 | 19.5 | MT | 2025-05-08 | 2025-05-08 | 2025-05-13 | 2025-05-13
10538 | T-20-3rd Floor | Complete | RCC | 2025-06-11 | 2025-06-12 | Slab& Beam RCC | 100 | 100 | CUM | 2025-05-08 | 2025-05-08 | 2025-05-09 | 2025-05-10
39961 | Tower A - Super Structure - Core & Outer Slab L52-53 | Complete | RCC Works - Slab | 2025-05-09 | 2025-05-14 | Outer Slab_TA | 100 | 100 |  | 2025-05-09 | 2025-05-15 | 2025-05-14 | 2025-05-31 | Tower A | Super Structure | L52 | RCC Sub Structure | RCC Works - Slab
8424 | T-14-3rd Floor | Quality checked | Slab& Beam Steel & Conduting | 2025-05-08 | 2025-05-17 | Slab& Beam Steel & Conduting | 10 | 10 | MT | 2025-05-10 | 2025-05-24 | 2025-05-19 | 2025-06-25
8433 | T-14-5th Floor | Complete |  | 2025-06-04 | 2025-06-18 | 4th Floor Roof | 100 | 100 |  | 2025-05-10 | 2025-07-20 | 2025-06-19 | 2025-08-08
8965 | T-15-2nd Floor | Complete |  | 2025-04-09 | 2025-05-14 | 1st Floor Roof | 100 | 100 |  | 2025-05-10 | 2025-05-12 | 2025-05-28 | 2025-05-31
8966 | T-15-2nd Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-04-09 | 2025-04-22 | AL - Shear Walls/Corewalls Steel | 24.5 | 24.5 | MT | 2025-05-10 | 2025-05-12 | 2025-05-19 | 2025-05-15
8967 | T-15-2nd Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-04-13 | 2025-04-26 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-05-10 | 2025-05-14 | 2025-05-19 | 2025-05-26
9483 | T-16-1st Floor | Complete | Slab& Beam Steel & Conduting | 2025-05-11 | 2025-05-27 | Slab& Beam Steel & Conduting | 14 | 14 | MT | 2025-05-10 | 2025-05-10 | 2025-05-26 | 2025-06-15
10089 |  | Started |  | 2025-04-25 | 2026-11-21 | Finishing Works | 100 | 0 |  | 2025-05-10 | 2025-05-30 | 2026-10-19
10090 |  | Started |  | 2025-04-25 | 2026-09-03 | Basement Floor | 100 | 0 |  | 2025-05-10 | 2025-06-18 | 2026-08-01
10091 | T-21-Basement Floor | Started | Masonry Works | 2025-04-25 | 2025-08-02 | Masonry Works | 100 | 0 |  | 2025-05-10 | 2025-06-18 | 2025-08-17
10095 |  | Started |  | 2025-06-01 | 2026-08-13 | Ground Floor | 100 | 0 |  | 2025-05-10 | 2025-05-30 | 2026-07-13
10096 |  | Started |  | 2025-06-01 | 2026-07-26 | Flat Area | 100 | 0 |  | 2025-05-10 | 2025-05-30 | 2026-06-24
10110 | T-21-GF Flat Area | Started | Railing | 2025-06-01 | 2025-06-16 | Balcony Railing | 100 | 0 |  | 2025-05-10 | 2025-05-30 | 2025-05-25
10539 | T-20-4th Floor | Complete |  | 2025-06-13 | 2025-06-26 | 3rd Floor Roof | 100 | 100 |  | 2025-05-10 | 2025-05-10 | 2025-05-23 | 2025-05-24
10540 | T-20-4th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-06-13 | 2025-06-18 | AL - Shear Walls/Corewalls Steel | 20.54 | 20.54 | MT | 2025-05-10 | 2025-05-10 | 2025-05-15 | 2025-05-14
10609 |  | Started |  | 2025-05-06 | 2026-12-03 | Finishing Works | 100 | 0 |  | 2025-05-10 | 2025-05-30 | 2026-10-27
10610 |  | Not Ready |  | 2025-05-06 | 2026-09-15 | Basement Floor | 100 | 0 |  | 2025-05-10 |  | 2026-08-10
10615 |  | Started |  | 2025-06-12 | 2026-08-26 | Ground Floor | 100 | 0 |  | 2025-05-10 | 2025-05-30 | 2026-07-21
10616 |  | Started |  | 2025-06-12 | 2026-08-06 | Flat Area | 100 | 0 |  | 2025-05-10 | 2025-05-30 | 2026-07-02
10630 | T-20-GF Flat Area | Started | Railing | 2025-06-12 | 2025-06-27 | Balcony Railing | 100 | 0 |  | 2025-05-10 | 2025-05-30 | 2025-05-25
11043 | T-19-1st Floor | Quality checked | Slab& Beam Steel & Conduting | 2025-04-29 | 2025-05-08 | Slab& Beam Steel & Conduting | 11.3 | 11.3 | MT | 2025-05-10 | 2025-05-16 | 2025-05-19 | 2025-05-25
11539 |  | Not Committed |  | 2025-03-06 | 2025-08-01 | Grade Slab | 100 | 0 |  | 2025-05-10 |  | 2025-09-05
11549 |  | Started |  | 2025-04-05 | 2025-05-06 | Part-2 | 100 | 5 |  | 2025-05-10 | 2025-05-05 | 2025-06-09
8422 | T-14-3rd Floor | Quality checked | Conduiting | 2025-04-14 | 2025-04-18 | Conduiting works | 100 | 100 | Units | 2025-05-12 | 2025-05-12 | 2025-05-15 | 2025-06-12
10542 | T-20-4th Floor | Complete | Conduiting | 2025-06-16 | 2025-06-19 | Conduiting works | 100 | 100 |  | 2025-05-12 | 2025-05-14 | 2025-05-15 | 2025-05-17
8421 | T-14-3rd Floor | Quality checked | Shear Walls/Corewalls Shuttering | 2025-04-18 | 2025-05-02 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-05-13 | 2025-05-13 | 2025-05-27 | 2025-06-18
10025 | T-21-4th Floor | Quality checked | RCC | 2025-06-14 | 2025-06-15 | Slab& Beam RCC | 318 | 318 | CUM | 2025-05-13 | 2025-05-14 | 2025-05-14 | 2025-05-15
10541 | T-20-4th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-06-17 | 2025-06-21 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-05-13 | 2025-05-13 | 2025-05-17 | 2025-05-17
42686 |  | Started |  | 2025-05-13 | 2026-07-21 | L34-35 | 100 | 12 |  | 2025-05-13 | 2025-05-13 | 2026-07-15 |  |  |  |  | Finishes | Gypsum Plastering Works
42686 |  | Started |  | 2025-05-13 | 2026-07-21 | L34-35 | 100 | 12 |  | 2025-05-13 | 2025-05-13 | 2026-07-15
42687 |  | Started |  | 2025-05-13 | 2025-06-11 | MEP 1st Fixes | 100 | 15 |  | 2025-05-13 | 2025-05-13 | 2025-10-11
42688 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Apartment Area | Started | FPS 1st Fix - MEP & Finishes | 2025-05-13 | 2025-05-20 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 20 | Units | 2025-05-13 | 2025-05-13 | 2025-09-18 |  | Tower A | Super Structure | L34 | MEP | FPS 1st Fix - MEP & Finishes
42689 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Apartment Area | Started | Electrical 1st Fix - MEP & Finishes | 2025-05-13 | 2025-05-17 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 15 | Units | 2025-05-13 | 2025-05-13 | 2025-09-16 |  | Tower A | Super Structure | L34 | MEP | Electrical 1st Fixes
48303 | Retail - Sub structure - B1 to GF - P5 | Complete |  | 2025-05-13 | 2025-05-20 | Section 12_lift 2 | 100 | 100 |  | 2025-05-13 | 2025-05-13 | 2025-05-20 | 2025-05-20 | Retail | Sub Structure | B1
48304 | Retail - Sub structure - B1 to GF - P5 | Complete |  | 2025-05-13 | 2025-05-20 | Section 13_lift 2 | 100 | 100 |  | 2025-05-13 | 2025-05-13 | 2025-05-20 | 2025-05-20 | Retail | Sub Structure | B1
10097 | T-21-GF Flat Area | Started | Blockwork | 2025-06-16 | 2025-07-07 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-05-14 | 2025-06-18 | 2025-06-05
10130 |  | Started |  | 2025-06-16 | 2026-09-05 | First Floor | 100 | 0 |  | 2025-05-14 | 2025-06-18 | 2026-08-03
10131 |  | Started |  | 2025-06-16 | 2026-07-10 | Flat Area | 100 | 0 |  | 2025-05-14 | 2025-06-18 | 2026-06-08
10145 | T-21-1st Floor Flat Area | Started | Railing | 2025-06-16 | 2025-07-18 | Balcony Railing | 100 | 0 |  | 2025-05-14 | 2025-06-18 | 2025-06-16
8969 | T-15-2nd Floor | Complete | Shuttering | 2025-04-23 | 2025-05-09 | Slab and Beam Shuttering | 3715 | 3715 | Sqm | 2025-05-15 | 2025-05-19 | 2025-05-22 | 2025-05-23
10026 | T-21-5th Floor | Complete |  | 2025-06-17 | 2025-06-30 | 4th Floor Roof | 100 | 100 |  | 2025-05-15 | 2025-05-16 | 2025-05-28 | 2025-05-28
10027 | T-21-5th Floor | Quality checked | AL - Shear Walls/Corewalls Steel | 2025-06-17 | 2025-06-20 | AL - Shear Walls/Corewalls Steel | 19.5 | 19.5 | MT | 2025-05-15 | 2025-05-16 | 2025-05-20 | 2025-05-19
11034 | T-19-Sub structure Basement Part 2 NTA | Not Ready | Concrete | 2025-04-07 | 2025-04-09 | Concrete | 432 | 0 | CUM | 2025-05-15 |  | 2025-05-15
39648 | Tower A - Super Structure - Core Wall Mid Rise L57-58 | Complete | Core Wall RCC Works | 2025-05-15 | 2025-05-15 | Casting | 100 | 100 |  | 2025-05-15 | 2025-05-29 | 2025-05-15 | 2025-05-29 | Tower A | Super Structure | L57 | RCC Super Structure | Core Wall RCC Works
39962 |  | Complete |  | 2025-05-15 | 2025-05-22 | L53-54 | 100 | 100 |  | 2025-05-15 | 2025-06-01 | 2025-05-22 | 2025-06-09
39962 |  | Complete |  | 2025-05-15 | 2025-05-22 | L53-54 | 100 | 100 |  | 2025-05-15 | 2025-06-01 | 2025-05-22 | 2025-06-09 |  |  |  | Finishes | Gypsum Plastering Works
39963 | Tower A - Super Structure - Core & Outer Slab L53-54 | Complete | RCC Works - Vertical | 2025-05-15 | 2025-05-21 | Outer Columns_TA | 100 | 100 | Units | 2025-05-15 | 2025-06-01 | 2025-05-21 | 2025-06-09 | Tower A | Super Structure | L53 | RCC Sub Structure | RCC Works - Vertical
40292 | Tower A - Super Structure - Finishes & MEP - L35 to L36 | Complete | Partition Wall-Blockwork | 2025-05-15 | 2025-05-20 | Staircase Area | 100 | 100 |  | 2025-05-15 | 2025-05-22 | 2025-05-20 | 2025-06-05 | Tower A | Super Structure | L35
40295 | Tower A - Super Structure - Finishes & MEP - L36 to L37 | Complete | Partition Wall-Blockwork | 2025-05-15 | 2025-05-22 | Partition Walls | 100 | 100 |  | 2025-05-15 | 2025-05-15 | 2025-05-22 | 2025-05-22 | Tower A | Super Structure | L36
8423 | T-14-3rd Floor | Quality checked | Shuttering | 2025-04-28 | 2025-05-14 | Slab and Beam Shuttering | 3605 | 3605 | Sqm | 2025-05-16 | 2025-05-16 | 2025-06-06 | 2025-06-21
10543 | T-20-4th Floor | Complete | Shuttering | 2025-06-20 | 2025-06-24 | Slab and Beam Shuttering | 3583 | 3583 | Sqm | 2025-05-16 | 2025-05-15 | 2025-05-21 | 2025-05-19
11548 | T-18-GF | Quality checked | Concrete | 2025-04-25 | 2025-04-26 | Concrete | 134.88 | 134.88 | CUM | 2025-05-16 | 2025-05-13 | 2025-05-17 | 2025-05-13
39649 | Tower A - Super Structure - Core Wall Mid Rise L57-58 | Complete | Core Wall RCC Works | 2025-05-16 | 2025-05-16 | ACS Form Release & jump to next level | 100 | 100 |  | 2025-05-16 | 2025-05-30 | 2025-05-16 | 2025-05-30 | Tower A | Super Structure | L57 | RCC Super Structure | Core Wall RCC Works
10029 | T-21-5th Floor | Complete | Conduiting | 2025-06-19 | 2025-06-21 | Conduiting works | 100 | 100 |  | 2025-05-17 | 2025-05-21 | 2025-05-21 | 2025-05-26
10113 |  | Not Ready |  | 2025-06-09 | 2026-08-13 | Common Area | 100 | 0 |  | 2025-05-17 |  | 2026-07-13
10633 |  | Not Ready |  | 2025-06-20 | 2026-08-26 | Common Area | 100 | 0 |  | 2025-05-17 |  | 2026-07-21
11557 |  | Started |  | 2025-04-30 | 2026-03-01 | RCC Structure | 100 | 51 |  | 2025-05-17 | 2025-05-15 | 2025-12-25
11558 | T-18-1st Floor | Complete |  | 2025-04-30 | 2025-06-09 | Ground Floor Roof | 100 | 100 |  | 2025-05-17 | 2025-05-15 | 2025-06-26 | 2025-07-10
11559 | T-18-1st Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-04-30 | 2025-05-17 | AL - Shear Walls/Corewalls Steel | 20.5 | 20.5 | MT | 2025-05-17 | 2025-05-15 | 2025-06-03 | 2025-05-30
39650 |  | Complete |  | 2025-05-17 | 2025-05-24 | Core Wall L58-59 | 100 | 100 |  | 2025-05-17 | 2025-05-30 | 2025-05-24 | 2025-06-18
39651 | Tower A - Super Structure - Core Wall Mid Rise L58-59 | Complete | Core Wall RCC Works | 2025-05-17 | 2025-05-17 | Scaffolding & platform | 100 | 100 | Units | 2025-05-17 | 2025-05-30 | 2025-05-17 | 2025-06-18 | Tower A | Super Structure | L58 | RCC Super Structure | Core Wall RCC Works
39964 | Tower A - Super Structure - Core & Outer Slab L53-54 | Complete | RCC Works - Slab | 2025-05-17 | 2025-05-22 | Outer Slab_TA | 100 | 100 |  | 2025-05-17 | 2025-06-09 | 2025-05-22 | 2025-06-09 | Tower A | Super Structure | L53 | RCC Sub Structure | RCC Works - Slab
8425 | T-14-3rd Floor | Quality checked | RCC | 2025-05-17 | 2025-05-19 | Slab& Beam RCC | 307 | 307 | CUM | 2025-05-19 | 2025-05-30 | 2025-05-20 | 2025-06-26
8968 | T-15-2nd Floor | Complete | Conduiting | 2025-04-22 | 2025-04-25 | Conduiting works | 100 | 100 |  | 2025-05-19 | 2025-05-15 | 2025-05-22 | 2025-05-19
10028 | T-21-5th Floor | Quality checked | Shear Walls/Corewalls Shuttering | 2025-06-20 | 2025-06-24 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-05-19 | 2025-05-18 | 2025-05-23 | 2025-05-23
10544 | T-20-4th Floor | Complete | Slab& Beam Steel & Conduting | 2025-06-23 | 2025-06-25 | Slab& Beam Steel & Conduting | 10.8 | 10.8 | MT | 2025-05-19 | 2025-05-16 | 2025-05-22 | 2025-05-22
11044 | T-19-1st Floor | Quality checked | RCC | 2025-05-08 | 2025-05-09 | Slab& Beam RCC | 315 | 315 | CUM | 2025-05-19 | 2025-05-26 | 2025-05-20 | 2025-05-27
39652 | Tower A - Super Structure - Core Wall Mid Rise L58-59 | Complete | Core Wall RCC Works | 2025-05-19 | 2025-05-21 | Reinf & Guide shoes fixing | 100 | 100 | Units | 2025-05-19 | 2025-06-02 | 2025-05-21 | 2025-06-18 | Tower A | Super Structure | L58 | RCC Super Structure | Core Wall RCC Works
8503 |  | Not Ready |  | 2025-05-19 | 2026-12-05 | Finishing Works | 100 | 0 |  | 2025-05-20 |  | 2026-12-06
8504 |  | Not Ready |  | 2025-05-19 | 2026-08-22 | Basement Floor | 100 | 0 |  | 2025-05-20 |  | 2026-08-24
8509 |  | Not Ready |  | 2025-05-19 | 2026-08-02 | Ground Floor | 100 | 0 |  | 2025-05-20 |  | 2026-08-03
8510 |  | Not Ready |  | 2025-05-19 | 2026-07-15 | Flat Area | 100 | 0 |  | 2025-05-20 |  | 2026-07-16
11045 | T-19-2nd Floor | Complete |  | 2025-05-12 | 2025-06-16 | 1st Floor Roof | 100 | 100 |  | 2025-05-20 | 2025-06-01 | 2025-06-04 | 2025-06-20
11046 | T-19-2nd Floor | Quality checked | AL - Shear Walls/Corewalls Steel | 2025-05-12 | 2025-05-24 | AL - Shear Walls/Corewalls Steel | 28.4 | 28.4 | MT | 2025-05-20 | 2025-06-01 | 2025-05-30 | 2025-06-09
11047 | T-19-2nd Floor | Quality checked | Shear Walls/Corewalls Shuttering | 2025-05-16 | 2025-05-29 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-05-20 | 2025-06-02 | 2025-05-30 | 2025-06-10
11049 | T-19-2nd Floor | Complete | Shuttering | 2025-05-27 | 2025-06-11 | Slab and Beam Shuttering | 3548 | 3548 | Sqm | 2025-05-20 | 2025-06-08 | 2025-06-04 | 2025-06-15
11050 | T-19-2nd Floor | Complete | Slab& Beam Steel & Conduting | 2025-06-06 | 2025-06-15 | Slab& Beam Steel & Conduting | 11.3 | 11.3 | MT | 2025-05-20 | 2025-06-11 | 2025-05-25 | 2025-06-19
39653 | Tower A - Super Structure - Core Wall Mid Rise L58-59 | Complete | Core Wall RCC Works | 2025-05-20 | 2025-05-22 | ACS Form Closing & Alignment | 100 | 100 | Units | 2025-05-20 | 2025-06-03 | 2025-05-22 | 2025-06-06 | Tower A | Super Structure | L58 | RCC Super Structure | Core Wall RCC Works
44048 |  | Started |  | 2025-08-12 | 2025-10-08 | L13-18 | 100 | 55 |  | 2025-05-20 | 2025-05-10 | 2025-10-06
44052 | Tower A - Super Structure - Finishes & MEP - L13 to L18 | Started | Façade Works - MEP & Finishes | 2025-09-08 | 2025-09-19 | Fixing of Backlit Laminated Glass assembly & ACP Panels | 100 | 55 | Units | 2025-05-20 | 2025-05-20 | 2025-09-16 |  | Tower A | Super Structure | L13 | Façade | Façade Works
44055 |  | Started |  | 2025-09-20 | 2025-11-07 | L18-23 | 100 | 54 |  | 2025-05-20 | 2025-05-20 | 2025-10-10
44056 | Tower A - Super Structure - Finishes & MEP - L18 to L23 | Started | Façade Works - MEP & Finishes | 2025-09-20 | 2025-10-08 | Al. Frame section (Mullion & Transom) Installation | 100 | 54 | Units | 2025-05-20 | 2025-05-20 | 2025-09-25 |  | Tower A | Super Structure | L18 | Façade | Façade Works
44057 | Tower A - Super Structure - Finishes & MEP - L18 to L23 | Started | Façade Works - MEP & Finishes | 2025-10-09 | 2025-10-27 | DGU Assembly Installation | 100 | 54 | Units | 2025-05-20 | 2025-05-20 | 2025-10-06 |  | Tower A | Super Structure | L18 | Façade | Façade Works
8426 | T-14-4th Floor | Complete |  | 2025-05-20 | 2025-06-03 | 3rd Floor Roof | 100 | 100 |  | 2025-05-21 | 2025-06-01 | 2025-06-04 | 2025-07-19
8427 | T-14-4th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-05-20 | 2025-05-24 | AL - Shear Walls/Corewalls Steel | 22 | 22 | MT | 2025-05-21 | 2025-06-01 | 2025-05-25 | 2025-07-06
8970 | T-15-2nd Floor | Complete | Slab& Beam Steel & Conduting | 2025-05-04 | 2025-05-13 | Slab& Beam Steel & Conduting | 13 | 13 | MT | 2025-05-21 | 2025-05-25 | 2025-05-27 | 2025-05-30
45255 |  | Complete |  | 2025-05-21 | 2025-06-04 | P2-P3 | 100 | 100 |  | 2025-05-21 | 2025-05-26 | 2025-06-04 | 2025-08-10
45256 | Tower B - Super Structure - Core & Outer Slab P2-P3 | Complete | RCC Works - Vertical | 2025-05-21 | 2025-05-28 | Outer Columns_TA | 100 | 100 | Units | 2025-05-21 | 2025-05-26 | 2025-05-28 | 2025-08-10 | Tower B | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
48305 | Retail - Sub structure - B1 to GF - P5 | Complete |  | 2025-05-21 | 2025-05-28 | Section 14_lift 2 | 100 | 100 |  | 2025-05-21 | 2025-05-21 | 2025-05-28 | 2025-05-28 | Retail | Sub Structure | B1
48306 | Retail - Sub structure - B1 to GF - P5 | Complete |  | 2025-05-21 | 2025-05-28 | Section 15_lift 2 | 100 | 100 |  | 2025-05-21 | 2025-05-21 | 2025-05-28 | 2025-05-28 | Retail | Sub Structure | B1
10030 | T-21-5th Floor | Quality checked | Shuttering | 2025-06-23 | 2025-06-27 | Slab and Beam Shuttering | 3264 | 3264 | Sqm | 2025-05-22 | 2025-05-22 | 2025-05-26 | 2025-05-25
10545 | T-20-4th Floor | Complete | RCC | 2025-06-26 | 2025-06-26 | Slab& Beam RCC | 321 | 321 | CUM | 2025-05-22 | 2025-05-23 | 2025-05-23 | 2025-05-24
39174 |  | Started |  | 2025-05-22 | 2025-06-12 | DG Foundation | 100 | 50 |  | 2025-05-22 | 2025-06-03 | 2025-09-22
8429 | T-14-4th Floor | Complete | Conduiting | 2025-05-22 | 2025-05-25 | Conduiting works | 100 | 100 |  | 2025-05-23 | 2025-06-07 | 2025-05-26 | 2025-07-14
10650 |  | Not Committed |  | 2025-06-27 | 2026-09-17 | First Floor | 100 | 0 |  | 2025-05-23 |  | 2026-08-12
10651 |  | Not Committed |  | 2025-06-27 | 2026-07-21 | Flat Area | 100 | 0 |  | 2025-05-23 |  | 2026-06-16
11560 | T-18-1st Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-05-06 | 2025-06-03 | Shear Walls/Corewalls Shuttering | 100 | 100 | Units | 2025-05-23 | 2025-05-19 | 2025-06-19 | 2025-06-28
39654 | Tower A - Super Structure - Core Wall Mid Rise L58-59 | Complete | Core Wall RCC Works | 2025-05-23 | 2025-05-23 | Casting | 100 | 100 | Units | 2025-05-23 | 2025-06-06 | 2025-05-23 | 2025-06-13 | Tower A | Super Structure | L58 | RCC Super Structure | Core Wall RCC Works
39965 |  | Complete |  | 2025-05-23 | 2025-05-30 | L54-55 | 100 | 100 |  | 2025-05-23 | 2025-06-10 | 2025-05-30 | 2025-06-19
39965 |  | Complete |  | 2025-05-23 | 2025-05-30 | L54-55 | 100 | 100 |  | 2025-05-23 | 2025-06-10 | 2025-05-30 | 2025-06-19 |  |  |  | Finishes | Gypsum Plastering Works
39966 | Tower A - Super Structure - Core & Outer Slab L54-55 | Complete | RCC Works - Vertical | 2025-05-23 | 2025-05-29 | Outer Columns_TA | 100 | 100 | Units | 2025-05-23 | 2025-06-10 | 2025-05-29 | 2025-06-19 | Tower A | Super Structure | L54 | RCC Sub Structure | RCC Works - Vertical
40296 | Tower A - Super Structure - Finishes & MEP - L36 to L37 | Complete | Partition Wall-Blockwork | 2025-05-23 | 2025-05-28 | Staircase Area | 100 | 100 |  | 2025-05-23 | 2025-05-23 | 2025-05-28 | 2025-05-28 | Tower A | Super Structure | L36
40299 | Tower A - Super Structure - Finishes & MEP - L37 to L38 | Complete | Partition Wall-Blockwork | 2025-05-23 | 2025-05-30 | Partition Walls | 100 | 100 | Units | 2025-05-23 | 2025-05-23 | 2025-05-30 | 2025-07-10 | Tower A | Super Structure | L37
8428 | T-14-4th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-05-23 | 2025-05-27 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-05-24 | 2025-06-03 | 2025-05-28 | 2025-07-15
10031 | T-21-5th Floor | Complete | Slab& Beam Steel & Conduting | 2025-06-25 | 2025-06-28 | Slab& Beam Steel & Conduting | 19.5 | 19.5 | MT | 2025-05-24 | 2025-05-24 | 2025-05-27 | 2025-05-27
10546 | T-20-5th Floor | Complete |  | 2025-06-28 | 2025-07-11 | 4th Floor Roof | 100 | 100 |  | 2025-05-24 | 2025-05-24 | 2025-06-06 | 2025-06-09
10547 | T-20-5th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-06-28 | 2025-07-02 | AL - Shear Walls/Corewalls Steel | 20.54 | 20.54 | MT | 2025-05-24 | 2025-05-24 | 2025-05-28 | 2025-05-29
39655 | Tower A - Super Structure - Core Wall Mid Rise L58-59 | Quality checked | Core Wall RCC Works | 2025-05-24 | 2025-05-24 | ACS Form Release & jump to next level | 100 | 100 | Units | 2025-05-24 | 2025-06-12 | 2025-05-24 | 2025-06-14 | Tower A | Super Structure | L58 | RCC Super Structure | Core Wall RCC Works
45257 | Tower B - Super Structure - Core & Outer Slab P2-P3 | Complete | RCC Works - Slab | 2025-05-24 | 2025-06-04 | Outer Slab_TA | 100 | 100 | Units | 2025-05-24 | 2025-06-27 | 2025-06-04 | 2025-08-10 | Tower B | Super Structure |  | RCC Sub Structure | RCC Works - Slab
10612 | T-20-Basement Floor | Forced Ready | Plastering | 2025-06-08 | 2025-09-15 | Plastering | 100 | 0 |  | 2025-05-25 |  | 2025-09-04
10617 | T-20-GF Flat Area | Forced Ready | Blockwork | 2025-06-27 | 2025-07-18 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-05-25 |  | 2025-06-15
10665 | T-20-1st Floor Flat Area | Forced Ready | Railing | 2025-06-27 | 2025-07-29 | Balcony Railing | 100 | 0 |  | 2025-05-25 |  | 2025-06-25
11051 | T-19-2nd Floor | Complete | RCC | 2025-06-16 | 2025-06-16 | Slab& Beam RCC | 340 | 340 | CUM | 2025-05-25 | 2025-06-20 | 2025-05-26 | 2025-06-20
9484 | T-16-1st Floor | Complete | RCC | 2025-05-27 | 2025-05-29 | Slab& Beam RCC | 315 | 315 | CUM | 2025-05-26 | 2025-06-16 | 2025-05-28 | 2025-06-16
10549 | T-20-5th Floor | Complete | Conduiting | 2025-06-30 | 2025-07-03 | Conduiting works | 100 | 100 |  | 2025-05-26 | 2025-05-26 | 2025-05-29 | 2025-06-02
11052 | T-19-3rd Floor | Complete |  | 2025-06-19 | 2025-07-24 | 2nd Floor Roof | 100 | 100 |  | 2025-05-26 | 2025-06-23 | 2025-06-13 | 2025-07-22
11053 | T-19-3rd Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-06-19 | 2025-07-02 | AL - Shear Walls/Corewalls Steel | 28.4 | 28.4 | MT | 2025-05-26 | 2025-06-23 | 2025-06-09 | 2025-06-30
11054 | T-19-3rd Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-06-23 | 2025-07-06 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-05-26 | 2025-06-25 | 2025-06-09 | 2025-07-15
11129 |  | Not Ready |  | 2025-06-17 | 2027-01-14 | Finishing Works | 100 | 0 |  | 2025-05-26 |  | 2026-11-25
11130 |  | Not Ready |  | 2025-06-17 | 2026-10-28 | Basement Floor | 100 | 0 |  | 2025-05-26 |  | 2026-09-07
39656 |  | Complete |  | 2025-05-26 | 2025-06-02 | Core Wall L59-60 | 100 | 100 |  | 2025-05-26 | 2025-06-12 | 2025-06-02 | 2025-06-26
39657 | Tower A - Super Structure - Core Wall Mid Rise L59-60 | Complete | Core Wall RCC Works | 2025-05-26 | 2025-05-26 | Scaffolding & platform | 100 | 100 | Units | 2025-05-26 | 2025-06-12 | 2025-05-26 | 2025-06-15 | Tower A | Super Structure | L59 | RCC Super Structure | Core Wall RCC Works
39967 | Tower A - Super Structure - Core & Outer Slab L54-55 | Complete | RCC Works - Slab | 2025-05-26 | 2025-05-30 | Outer Slab_TA | 100 | 100 | Units | 2025-05-26 | 2025-06-19 | 2025-05-30 | 2025-06-19 | Tower A | Super Structure | L54 | RCC Sub Structure | RCC Works - Slab
44058 | Tower A - Super Structure - Finishes & MEP - L18 to L23 | Started | Façade Works - MEP & Finishes | 2025-10-09 | 2025-11-01 | Installation of highly reflective metal sheet | 100 | 54 | Units | 2025-05-26 | 2025-05-26 | 2025-10-08 |  | Tower A | Super Structure | L18 | Façade | Façade Works
8430 | T-14-4th Floor | Complete | Shuttering | 2025-05-26 | 2025-05-30 | Slab and Beam Shuttering | 3605 | 3605 | Sqm | 2025-05-27 | 2025-06-06 | 2025-05-31 | 2025-07-17
8527 |  | Not Ready |  | 2025-05-26 | 2026-08-02 | Common Area | 100 | 0 |  | 2025-05-27 |  | 2026-08-03
8971 | T-15-2nd Floor | Quality checked | RCC | 2025-05-13 | 2025-05-14 | Slab& Beam RCC | 318 | 318 | CUM | 2025-05-27 | 2025-05-30 | 2025-05-28 | 2025-05-31
10032 | T-21-5th Floor | Complete | RCC | 2025-06-28 | 2025-06-30 | Slab& Beam RCC | 318 | 318 | CUM | 2025-05-27 | 2025-05-28 | 2025-05-28 | 2025-05-28
10548 | T-20-5th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-07-01 | 2025-07-05 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-05-27 | 2025-05-27 | 2025-05-31 | 2025-06-03
10621 | T-20-GF Flat Area | Forced Ready | Electrical DB Fixing | 2025-06-29 | 2025-07-07 | Electrical DB Fixing | 100 | 0 |  | 2025-05-27 |  | 2025-06-03
39658 | Tower A - Super Structure - Core Wall Mid Rise L59-60 | Quality checked | Core Wall RCC Works | 2025-05-27 | 2025-05-29 | Reinf & Guide shoes fixing | 100 | 100 | Units | 2025-05-27 | 2025-06-18 | 2025-05-29 | 2025-06-21 | Tower A | Super Structure | L59 | RCC Super Structure | Core Wall RCC Works
44059 | Tower A - Super Structure - Finishes & MEP - L18 to L23 | Started | Façade Works - MEP & Finishes | 2025-10-09 | 2025-10-21 | Fixing of Backlit Laminated Glass assembly & ACP Panels | 100 | 54 | Units | 2025-05-27 | 2025-05-27 | 2025-09-16 |  | Tower A | Super Structure | L18 | Façade | Façade Works
8972 | T-15-3rd Floor | Quality checked |  | 2025-05-16 | 2025-06-19 | 2nd Floor Roof | 100 | 100 |  | 2025-05-28 | 2025-06-01 | 2025-06-13 | 2025-06-19
8973 | T-15-3rd Floor | Quality checked | AL - Shear Walls/Corewalls Steel | 2025-05-16 | 2025-05-29 | AL - Shear Walls/Corewalls Steel | 24.5 | 24.5 | MT | 2025-05-28 | 2025-06-01 | 2025-06-06 | 2025-06-07
8974 | T-15-3rd Floor | Quality checked | Shear Walls/Corewalls Shuttering | 2025-05-20 | 2025-06-02 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-05-28 | 2025-06-03 | 2025-06-06 | 2025-06-09
9049 |  | Not Ready |  | 2025-05-14 | 2026-12-09 | Finishing Works | 100 | 0 |  | 2025-05-28 |  | 2026-12-04
9050 |  | Not Ready |  | 2025-05-14 | 2026-09-21 | Basement Floor | 100 | 0 |  | 2025-05-28 |  | 2026-09-16
9485 | T-16-2nd Floor | Complete |  | 2025-05-31 | 2025-07-08 | 1st Floor Roof | 100 | 100 |  | 2025-05-28 | 2025-06-19 | 2025-06-12 | 2025-07-12
9487 | T-16-2nd Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-06-06 | 2025-06-19 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-05-28 | 2025-06-22 | 2025-06-08 | 2025-07-01
10156 |  | Not Ready |  | 2025-06-30 | 2026-08-20 | Second Floor Flat Area | 100 | 0 |  | 2025-05-28 |  | 2026-07-18
10157 |  | Not Ready |  | 2025-06-30 | 2026-06-29 | Flat Area | 100 | 0 |  | 2025-05-28 |  | 2026-05-28
10634 | T-20-GF Common Area | Not Ready | Blockwork | 2025-06-30 | 2025-07-22 | Blockwork | 100 | 0 |  | 2025-05-28 |  | 2025-06-19
39659 | Tower A - Super Structure - Core Wall Mid Rise L59-60 | Complete | Core Wall RCC Works | 2025-05-28 | 2025-05-30 | ACS Form Closing & Alignment | 100 | 100 |  | 2025-05-28 | 2025-06-23 | 2025-05-30 | 2025-06-23 | Tower A | Super Structure | L59 | RCC Super Structure | Core Wall RCC Works
44060 | Tower A - Super Structure - Finishes & MEP - L18 to L23 | Started | Façade Works - MEP & Finishes | 2025-10-09 | 2025-10-21 | Fixing of Louvers | 100 | 54 | Units | 2025-05-28 | 2025-05-28 | 2025-10-01 |  | Tower A | Super Structure | L18 | Façade | Façade Works
44060 | Tower A - Super Structure - Finishes & MEP - L18 to L23 | Started | Façade Works - MEP & Finishes | 2025-10-09 | 2025-10-21 | Fixing of Louvers | 100 | 54 | Units | 2025-05-28 | 2025-05-28 | 2025-10-01 |  | Tower A | Super Structure | L18
10033 | T-21-6th Floor | Quality checked |  | 2025-07-01 | 2025-07-14 | 5th Floor Roof | 100 | 100 |  | 2025-05-29 | 2025-05-30 | 2025-06-11 | 2025-06-12
10034 | T-21-6th Floor | Quality checked | AL - Shear Walls/Corewalls Steel | 2025-07-01 | 2025-07-05 | AL - Shear Walls/Corewalls Steel | 19.5 | 19.5 | MT | 2025-05-29 | 2025-05-30 | 2025-06-03 | 2025-06-02
10132 | T-21-1st Floor Flat Area | Not Ready | Blockwork | 2025-06-30 | 2025-07-30 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-05-29 |  | 2025-06-30
10171 | T-21-2nd Floor Flat Area | Not Ready | Railing | 2025-06-30 | 2025-08-01 | Balcony Railing | 100 | 0 |  | 2025-05-29 |  | 2025-07-01
11563 | T-18-1st Floor | Complete | Slab& Beam Steel & Conduting | 2025-05-31 | 2025-06-08 | Slab& Beam Steel & Conduting | 10.8 | 10.8 | MT | 2025-05-29 | 2025-07-06 | 2025-06-06 | 2025-07-09
8431 | T-14-4th Floor | Complete | Slab& Beam Steel & Conduting | 2025-05-29 | 2025-06-02 | Slab& Beam Steel & Conduting | 10 | 10 | MT | 2025-05-30 | 2025-06-23 | 2025-06-03 | 2025-07-18
9486 | T-16-2nd Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-05-31 | 2025-06-13 | AL - Shear Walls/Corewalls Steel | 25 | 25 | MT | 2025-05-30 | 2025-06-19 | 2025-06-12 | 2025-06-26
10550 | T-20-5th Floor | Complete | Shuttering | 2025-07-04 | 2025-07-09 | Slab and Beam Shuttering | 3583 | 3583 | Sqm | 2025-05-30 | 2025-05-29 | 2025-06-04 | 2025-06-05
10638 | T-20-GF Common Area | Not Ready | Electrical DB Fixing | 2025-07-02 | 2025-07-10 | Electrical DB Fixing | 100 | 0 |  | 2025-05-30 |  | 2025-06-07
11048 | T-19-2nd Floor | Quality checked | Conduiting | 2025-05-24 | 2025-05-29 | Conduiting works | 100 | 100 |  | 2025-05-30 | 2025-06-05 | 2025-06-04 | 2025-06-08
10036 | T-21-6th Floor | Quality checked | Conduiting | 2025-07-03 | 2025-07-06 | Conduiting works | 100 | 100 |  | 2025-05-31 | 2025-05-30 | 2025-06-04 | 2025-06-04
10136 | T-21-1st Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-07-02 | 2025-07-18 | Electrical DB Fixing | 100 | 0 |  | 2025-05-31 |  | 2025-06-15
11553 | T-18-Sub structure Basement Part 2 NTA | Started | Conduiting | 2025-04-26 | 2025-05-04 | Conduiting | 100 | 32 |  | 2025-05-31 | 2025-06-03 | 2025-06-07
39660 | Tower A - Super Structure - Core Wall Mid Rise L59-60 | Complete | Core Wall RCC Works | 2025-05-31 | 2025-05-31 | Casting | 100 | 100 |  | 2025-05-31 | 2025-06-24 | 2025-05-31 | 2025-06-24 | Tower A | Super Structure | L59 | RCC Super Structure | Core Wall RCC Works
39968 |  | Complete |  | 2025-05-31 | 2025-06-09 | L55-56 | 100 | 100 |  | 2025-05-31 | 2025-06-12 | 2025-06-09 | 2025-06-28
39968 |  | Complete |  | 2025-05-31 | 2025-06-09 | L55-56 | 100 | 100 |  | 2025-05-31 | 2025-06-12 | 2025-06-09 | 2025-06-28 |  |  |  | Finishes | Gypsum Plastering Works
39969 | Tower A - Super Structure - Core & Outer Slab L55-56 | Complete | RCC Works - Vertical | 2025-05-31 | 2025-06-06 | Outer Columns_TA | 100 | 100 | Units | 2025-05-31 | 2025-06-12 | 2025-06-06 | 2025-06-28 | Tower A | Super Structure | L55 | RCC Sub Structure | RCC Works - Vertical
40300 | Tower A - Super Structure - Finishes & MEP - L37 to L38 | Complete | Partition Wall-Blockwork | 2025-05-31 | 2025-06-05 | Staircase Area | 100 | 100 |  | 2025-05-31 | 2025-06-05 | 2025-06-05 | 2025-06-05 | Tower A | Super Structure | L37
40303 | Tower A - Super Structure - Finishes & MEP - L38 to L39 | Complete | Partition Wall-Blockwork | 2025-05-31 | 2025-06-09 | Partition Walls | 100 | 100 | Units | 2025-05-31 | 2025-05-31 | 2025-06-09 | 2025-07-15 | Tower A | Super Structure | L38
44054 | Tower A - Super Structure - Finishes & MEP - L13 to L18 | Started | Façade Works - MEP & Finishes | 2025-09-26 | 2025-10-08 | Accessories & Alignment | 100 | 55 | Units | 2025-05-31 | 2025-05-31 | 2025-10-06 |  | Tower A | Super Structure | L13 | Façade | Façade Works
44054 | Tower A - Super Structure - Finishes & MEP - L13 to L18 | Started | Façade Works - MEP & Finishes | 2025-09-26 | 2025-10-08 | Accessories & Alignment | 100 | 55 | Units | 2025-05-31 | 2025-05-31 | 2025-10-06 |  | Tower A | Super Structure | L13
44061 | Tower A - Super Structure - Finishes & MEP - L18 to L23 | Started | Façade Works - MEP & Finishes | 2025-10-28 | 2025-11-07 | Accessories & Alignment | 100 | 54 | Units | 2025-05-31 | 2025-05-31 | 2025-10-10 |  | Tower A | Super Structure | L18 | Façade | Façade Works
44061 | Tower A - Super Structure - Finishes & MEP - L18 to L23 | Started | Façade Works - MEP & Finishes | 2025-10-28 | 2025-11-07 | Accessories & Alignment | 100 | 54 | Units | 2025-05-31 | 2025-05-31 | 2025-10-10 |  | Tower A | Super Structure | L18
9051 | T-15-Basement Floor | Not Ready | Masonry Works | 2025-05-14 | 2025-08-21 | Masonry Works | 100 | 0 |  | 2025-06-01 |  | 2025-09-08
10618 | T-20-GF Flat Area | Forced Ready | Plumbing Pipe Line | 2025-07-04 | 2025-07-21 | Plumbing Pipe Line | 100 | 0 |  | 2025-06-01 |  | 2025-06-16
8976 | T-15-3rd Floor | Quality checked | Shuttering | 2025-05-30 | 2025-06-14 | Slab and Beam Shuttering | 3715 | 3715 | Sqm | 2025-06-02 | 2025-06-06 | 2025-06-07 | 2025-06-15
10035 | T-21-6th Floor | Quality checked | Shear Walls/Corewalls Shuttering | 2025-07-04 | 2025-07-08 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-06-02 | 2025-05-31 | 2025-06-06 | 2025-06-06
10551 | T-20-5th Floor | Complete | Slab& Beam Steel & Conduting | 2025-07-07 | 2025-07-10 | Slab& Beam Steel & Conduting | 10.8 | 10.8 | MT | 2025-06-02 | 2025-06-02 | 2025-06-05 | 2025-06-07
39661 | Tower A - Super Structure - Core Wall Mid Rise L59-60 | Complete | Core Wall RCC Works | 2025-06-02 | 2025-06-02 | ACS Form Release & jump to next level | 100 | 100 |  | 2025-06-02 | 2025-06-26 | 2025-06-02 | 2025-06-26 | Tower A | Super Structure | L59 | RCC Super Structure | Core Wall RCC Works
9489 | T-16-2nd Floor | Complete | Shuttering | 2025-06-17 | 2025-07-02 | Slab and Beam Shuttering | 4183 | 4183 | Sqm | 2025-06-03 | 2025-06-25 | 2025-06-10 | 2025-07-09
11561 | T-18-1st Floor | Complete | Conduiting | 2025-05-17 | 2025-05-28 | Conduiting works | 100 | 100 | Units | 2025-06-03 | 2025-05-17 | 2025-06-14 | 2025-06-24
39662 |  | Complete |  | 2025-06-03 | 2025-06-11 | Core Wall L60-61 | 100 | 100 |  | 2025-06-03 | 2025-07-01 | 2025-06-11 | 2025-07-08
39663 | Tower A - Super Structure - Core Wall Mid Rise L60-61 | Complete | Core Wall RCC Works | 2025-06-03 | 2025-06-03 | Scaffolding & platform | 100 | 100 |  | 2025-06-03 | 2025-07-01 | 2025-06-03 | 2025-07-01 | Tower A | Super Structure | L60 | RCC Super Structure | Core Wall RCC Works
39970 | Tower A - Super Structure - Core & Outer Slab L55-56 | Complete | RCC Works - Slab | 2025-06-03 | 2025-06-09 | Outer Slab_TA | 100 | 100 | Units | 2025-06-03 | 2025-06-28 | 2025-06-09 | 2025-06-28 | Tower A | Super Structure | L55 | RCC Sub Structure | RCC Works - Slab
8544 |  | Not Ready |  | 2025-06-03 | 2026-08-25 | First Floor | 100 | 0 |  | 2025-06-04 |  | 2026-08-26
8545 |  | Not Ready |  | 2025-06-03 | 2026-06-28 | Flat Area | 100 | 0 |  | 2025-06-04 |  | 2026-06-29
10635 | T-20-GF Common Area | Forced Ready | Plumbing Pipe Line | 2025-07-08 | 2025-07-24 | Plumbing Pipe Line | 100 | 0 |  | 2025-06-04 |  | 2025-06-20
39664 | Tower A - Super Structure - Core Wall Mid Rise L60-61 | Complete | Core Wall RCC Works | 2025-06-04 | 2025-06-06 | Reinf & Guide shoes fixing | 100 | 100 |  | 2025-06-04 | 2025-07-03 | 2025-06-06 | 2025-07-03 | Tower A | Super Structure | L60 | RCC Super Structure | Core Wall RCC Works
10037 | T-21-6th Floor | Quality checked | Shuttering | 2025-07-07 | 2025-07-11 | Slab and Beam Shuttering | 3264 | 3264 | Sqm | 2025-06-05 | 2025-06-02 | 2025-06-09 | 2025-06-07
10133 | T-21-1st Floor Flat Area | Forced Ready | Plumbing Pipe Line | 2025-07-07 | 2025-08-04 | Plumbing Pipe Line | 100 | 0 |  | 2025-06-05 |  | 2025-06-30
10552 | T-20-5th Floor | Quality checked | RCC | 2025-07-10 | 2025-07-11 | Slab& Beam RCC | 321 | 321 | CUM | 2025-06-05 | 2025-06-08 | 2025-06-06 | 2025-06-09
10622 | T-20-GF Flat Area | Not Ready | Plastering | 2025-07-08 | 2025-08-09 | Plastering-Gypsum | 100 | 0 |  | 2025-06-05 |  | 2025-07-08
11135 |  | Not Ready |  | 2025-07-24 | 2026-10-08 | Ground Floor | 100 | 0 |  | 2025-06-05 |  | 2026-08-19
11136 |  | Not Ready |  | 2025-07-24 | 2026-09-18 | Flat Area | 100 | 0 |  | 2025-06-05 |  | 2026-07-30
39665 | Tower A - Super Structure - Core Wall Mid Rise L60-61 | Complete | Core Wall RCC Works | 2025-06-05 | 2025-06-09 | ACS Form Closing & Alignment | 100 | 100 |  | 2025-06-05 | 2025-07-05 | 2025-06-09 | 2025-07-05 | Tower A | Super Structure | L60 | RCC Super Structure | Core Wall RCC Works
45258 |  | Started |  | 2025-06-05 | 2025-06-20 | P3-P4 | 100 | 90 |  | 2025-06-05 | 2025-07-21 | 2025-09-18
45259 | Tower B - Super Structure - Core & Outer Slab P3-P4 | Complete | RCC Works - Vertical | 2025-06-05 | 2025-06-13 | Outer Columns_TA | 100 | 100 | Units | 2025-06-05 | 2025-07-21 | 2025-09-13 | 2025-10-07 | Tower B | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
8975 | T-15-3rd Floor | Quality checked | Conduiting | 2025-05-29 | 2025-06-01 | Conduiting works | 100 | 100 |  | 2025-06-06 | 2025-06-02 | 2025-06-09 | 2025-06-08
8977 | T-15-3rd Floor | Quality checked | Slab& Beam Steel & Conduting | 2025-06-09 | 2025-06-18 | Slab& Beam Steel & Conduting | 13 | 13 | MT | 2025-06-06 | 2025-06-10 | 2025-06-12 | 2025-06-18
10127 | T-21-GF Common Area | Forced Ready | Railing | 2025-06-09 | 2025-06-24 | Balcony Railing | 100 | 0 |  | 2025-06-06 |  | 2025-06-20
10647 | T-20-GF Common Area | Forced Ready | Railing | 2025-06-20 | 2025-07-05 | Balcony Railing | 100 | 0 |  | 2025-06-06 |  | 2025-06-20
10676 |  | Not Ready |  | 2025-07-11 | 2026-09-01 | Second Floor Flat Area | 100 | 0 |  | 2025-06-06 |  | 2026-07-27
10677 |  | Not Ready |  | 2025-07-11 | 2026-07-10 | Flat Area | 100 | 0 |  | 2025-06-06 |  | 2026-06-05
10038 | T-21-6th Floor | Quality checked | Slab& Beam Steel & Conduting | 2025-07-09 | 2025-07-12 | Slab& Beam Steel & Conduting | 19.5 | 19.5 | MT | 2025-06-07 | 2025-06-05 | 2025-06-10 | 2025-06-10
10137 | T-21-1st Floor Flat Area | Not Ready | Plastering | 2025-07-09 | 2025-08-28 | Plastering-Gypsum | 100 | 0 |  | 2025-06-07 |  | 2025-07-25
10553 | T-20-6th Floor | Quality checked |  | 2025-07-12 | 2025-07-25 | 5th Floor Roof | 100 | 100 |  | 2025-06-07 | 2025-06-10 | 2025-06-20 | 2025-06-22
10554 | T-20-6th Floor | Quality checked | AL - Shear Walls/Corewalls Steel | 2025-07-12 | 2025-07-16 | AL - Shear Walls/Corewalls Steel | 20.54 | 20.54 | MT | 2025-06-07 | 2025-06-10 | 2025-06-11 | 2025-06-16
11562 | T-18-1st Floor | Complete | Shuttering | 2025-05-22 | 2025-06-07 | Slab and Beam Shuttering | 3527 | 3527 | Sqm | 2025-06-07 | 2025-05-20 | 2025-06-24 | 2025-07-05
11564 | T-18-1st Floor | Complete | RCC | 2025-06-08 | 2025-06-09 | Slab& Beam RCC | 330.8 | 330.8 | CUM | 2025-06-07 | 2025-07-09 | 2025-06-08 | 2025-07-10
9488 | T-16-2nd Floor | Complete | Conduiting | 2025-06-14 | 2025-06-18 | Conduiting works | 100 | 100 |  | 2025-06-08 | 2025-06-20 | 2025-06-12 | 2025-06-30
10619 | T-20-GF Flat Area | Not Ready | Plastering | 2025-07-12 | 2025-07-28 | Plastering-Cement | 100 | 0 |  | 2025-06-08 |  | 2025-06-25
10556 | T-20-6th Floor | Quality checked | Conduiting | 2025-07-14 | 2025-07-17 | Conduiting works | 100 | 100 | Units | 2025-06-09 | 2025-06-12 | 2025-06-12 | 2025-06-17
11566 | T-18-2nd Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-06-11 | 2025-06-24 | AL - Shear Walls/Corewalls Steel | 20.5 | 20.5 | MT | 2025-06-09 | 2025-07-14 | 2025-06-15 | 2025-07-19
11567 | T-18-2nd Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-06-16 | 2025-06-28 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-06-09 | 2025-07-15 | 2025-06-20 | 2025-07-25
11569 | T-18-2nd Floor | Complete | Shuttering | 2025-06-26 | 2025-07-11 | Slab and Beam Shuttering | 3527 | 3527 | Sqm | 2025-06-09 | 2025-07-17 | 2025-06-20 | 2025-07-27
11570 | T-18-2nd Floor | Quality checked | Slab& Beam Steel & Conduting | 2025-07-05 | 2025-07-14 | Slab& Beam Steel & Conduting | 10.8 | 10.8 | MT | 2025-06-09 | 2025-07-26 | 2025-06-13 | 2025-07-31
10039 | T-21-6th Floor | Quality checked | RCC | 2025-07-12 | 2025-07-14 | Slab& Beam RCC | 318 | 318 | CUM | 2025-06-10 | 2025-06-11 | 2025-06-11 | 2025-06-12
10555 | T-20-6th Floor | Quality checked | Shear Walls/Corewalls Shuttering | 2025-07-15 | 2025-07-19 | Shear Walls/Corewalls Shuttering | 100 | 100 | Units | 2025-06-10 | 2025-06-13 | 2025-06-14 | 2025-06-18
10652 | T-20-1st Floor Flat Area | Forced Ready | Blockwork | 2025-07-11 | 2025-08-11 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-06-10 |  | 2025-07-09
10691 | T-20-2nd Floor Flat Area | Not Ready | Railing | 2025-07-11 | 2025-08-13 | Balcony Railing | 100 | 0 |  | 2025-06-10 |  | 2025-07-11
39175 |  | Complete |  | 2025-06-10 | 2025-06-24 | Pedestals for Cooling Towers | 100 | 100 |  | 2025-06-10 | 2025-05-31 | 2025-06-24 | 2025-05-31
39221 |  | Started |  | 2025-06-10 | 2025-08-12 | Low Side Installation - Cable Trays and Cable Laying (B01) | 100 | 60 |  | 2025-06-10 | 2025-07-09 | 2025-10-16
39666 | Tower A - Super Structure - Core Wall Mid Rise L60-61 | Complete | Core Wall RCC Works | 2025-06-10 | 2025-06-10 | Casting | 100 | 100 |  | 2025-06-10 | 2025-07-06 | 2025-06-10 | 2025-07-06 | Tower A | Super Structure | L60 | RCC Super Structure | Core Wall RCC Works
39971 |  | Complete |  | 2025-06-10 | 2025-06-17 | L56-57 | 100 | 100 |  | 2025-06-10 | 2025-07-04 | 2025-06-17 | 2025-07-07
39971 |  | Complete |  | 2025-06-10 | 2025-06-17 | L56-57 | 100 | 100 |  | 2025-06-10 | 2025-07-04 | 2025-06-17 | 2025-07-07 |  |  |  | Finishes | Gypsum Plastering Works
39972 | Tower A - Super Structure - Core & Outer Slab L56-57 | Complete | RCC Works - Vertical | 2025-06-10 | 2025-06-16 | Outer Columns_TA | 100 | 100 |  | 2025-06-10 | 2025-07-04 | 2025-06-16 | 2025-07-04 | Tower A | Super Structure | L56 | RCC Sub Structure | RCC Works - Vertical
40304 | Tower A - Super Structure - Finishes & MEP - L38 to L39 | Complete | Partition Wall-Blockwork | 2025-06-10 | 2025-06-14 | Staircase Area | 100 | 100 | Units | 2025-06-10 | 2025-06-10 | 2025-06-14 | 2025-06-27 | Tower A | Super Structure | L38
40307 | Tower A - Super Structure - Finishes & MEP - L39 to L40 | Complete | Partition Wall-Blockwork | 2025-06-10 | 2025-06-17 | Partition Walls | 100 | 100 |  | 2025-06-10 | 2025-08-12 | 2025-06-17 | 2025-08-12 | Tower A | Super Structure | L39
45260 | Tower B - Super Structure - Core & Outer Slab P3-P4 | Started | RCC Works - Slab | 2025-06-10 | 2025-06-20 | Outer Slab_TA | 100 | 79 | Units | 2025-06-10 | 2025-08-21 | 2025-09-18 |  | Tower B | Super Structure |  | RCC Sub Structure | RCC Works - Slab
10182 |  | Not Ready |  | 2025-07-14 | 2026-07-28 | Third Floor | 100 | 0 |  | 2025-06-11 |  | 2026-06-26
10183 |  | Not Ready |  | 2025-07-14 | 2026-05-16 | Flat Area | 100 | 0 |  | 2025-06-11 |  | 2026-04-13
10636 | T-20-GF Common Area | Forced Ready | Plastering | 2025-07-15 | 2025-08-06 | Plastering-Cement | 100 | 0 |  | 2025-06-11 |  | 2025-07-03
11554 | T-18-Sub structure Basement Part 2 NTA | Not Ready | Concrete | 2025-05-04 | 2025-05-06 | Concrete | 686.3 | 0 | CUM | 2025-06-11 |  | 2025-06-11
39667 | Tower A - Super Structure - Core Wall Mid Rise L60-61 | Complete | Core Wall RCC Works | 2025-06-11 | 2025-06-11 | ACS Form Release & jump to next level | 100 | 100 |  | 2025-06-11 | 2025-07-08 | 2025-06-11 | 2025-07-08 | Tower A | Super Structure | L60 | RCC Super Structure | Core Wall RCC Works
8978 | T-15-3rd Floor | Quality checked | RCC | 2025-06-18 | 2025-06-19 | Slab& Beam RCC | 318 | 318 | CUM | 2025-06-12 | 2025-06-19 | 2025-06-13 | 2025-06-19
9492 | T-16-3rd Floor | Complete |  | 2025-07-10 | 2025-08-16 | 2nd Floor Roof | 100 | 100 |  | 2025-06-12 | 2025-07-14 | 2025-06-28 | 2025-07-30
9569 |  | Not Ready |  | 2025-07-08 | 2027-02-06 | Finishing Works | 100 | 0 |  | 2025-06-12 |  | 2026-12-08
9570 |  | Not Ready |  | 2025-07-08 | 2026-11-20 | Basement Floor | 100 | 0 |  | 2025-06-12 |  | 2026-09-20
10040 | T-21-7th Floor | Quality checked |  | 2025-07-15 | 2025-07-28 | 6th Floor Roof | 100 | 100 |  | 2025-06-12 | 2025-06-18 | 2025-06-26 | 2025-06-30
10041 | T-21-7th Floor | Quality checked | AL - Shear Walls/Corewalls Steel | 2025-07-15 | 2025-07-19 | AL - Shear Walls/Corewalls Steel | 19.5 | 19.5 | MT | 2025-06-12 | 2025-06-18 | 2025-06-17 | 2025-06-22
10134 | T-21-1st Floor Flat Area | Forced Ready | Plastering | 2025-07-15 | 2025-08-06 | Plastering-Cement | 100 | 0 |  | 2025-06-12 |  | 2025-07-04
10656 | T-20-1st Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-07-13 | 2025-07-29 | Electrical DB Fixing | 100 | 0 |  | 2025-06-12 |  | 2025-06-30
39668 |  | Complete |  | 2025-06-12 | 2025-06-19 | Core Wall L61-62 | 100 | 100 |  | 2025-06-12 | 2025-07-09 | 2025-06-19 | 2025-07-19
39669 | Tower A - Super Structure - Core Wall Mid Rise L61-62 | Complete | Core Wall RCC Works | 2025-06-12 | 2025-06-12 | Scaffolding & platform | 100 | 100 | Units | 2025-06-12 | 2025-07-09 | 2025-06-12 | 2025-07-17 | Tower A | Super Structure | L61 | RCC Super Structure | Core Wall RCC Works
39973 | Tower A - Super Structure - Core & Outer Slab L56-57 | Complete | RCC Works - Slab | 2025-06-12 | 2025-06-17 | Outer Slab_TA | 100 | 100 |  | 2025-06-12 | 2025-07-07 | 2025-06-17 | 2025-07-07 | Tower A | Super Structure | L56 | RCC Sub Structure | RCC Works - Slab
9055 |  | Not Ready |  | 2025-06-19 | 2026-09-01 | Ground Floor | 100 | 0 |  | 2025-06-13 |  | 2026-08-27
9056 |  | Not Ready |  | 2025-06-19 | 2026-08-13 | Flat Area | 100 | 0 |  | 2025-06-13 |  | 2026-08-07
10158 | T-21-2nd Floor Flat Area | Forced Ready | Blockwork | 2025-07-14 | 2025-08-05 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-06-13 |  | 2025-07-07
10197 | T-21-3rd Floor Flat Area | Forced Ready | Railing | 2025-07-14 | 2025-08-16 | Balcony Railing | 100 | 0 |  | 2025-06-13 |  | 2025-07-16
10557 | T-20-6th Floor | Quality checked | Shuttering | 2025-07-18 | 2025-07-23 | Slab and Beam Shuttering | 3583 | 3583 | Sqm | 2025-06-13 | 2025-06-15 | 2025-06-18 | 2025-06-19
11153 |  | Not Ready |  | 2025-08-01 | 2026-10-08 | Common Area | 100 | 0 |  | 2025-06-13 |  | 2026-08-19
39670 | Tower A - Super Structure - Core Wall Mid Rise L61-62 | Complete | Core Wall RCC Works | 2025-06-13 | 2025-06-16 | Reinf & Guide shoes fixing | 100 | 100 |  | 2025-06-13 | 2025-07-10 | 2025-06-16 | 2025-07-16 | Tower A | Super Structure | L61 | RCC Super Structure | Core Wall RCC Works
8979 | T-15-4th Floor | Complete |  | 2025-06-20 | 2025-07-03 | 3rd Floor Roof | 100 | 100 |  | 2025-06-14 | 2025-06-20 | 2025-06-28 | 2025-07-09
8980 | T-15-4th Floor | Quality checked | AL - Shear Walls/Corewalls Steel | 2025-06-20 | 2025-06-24 | AL - Shear Walls/Corewalls Steel | 24.5 | 24.5 | MT | 2025-06-14 | 2025-06-20 | 2025-06-19 | 2025-06-25
10043 | T-21-7th Floor | Quality checked | Conduiting | 2025-07-17 | 2025-07-20 | Conduiting works | 100 | 100 |  | 2025-06-14 | 2025-06-19 | 2025-06-18 | 2025-06-24
10148 |  | Not Ready |  | 2025-07-17 | 2026-09-05 | Common Area | 100 | 0 |  | 2025-06-14 |  | 2026-08-03
10149 | T-21-1st Floor Common Area | Forced Ready | Plastering | 2025-07-17 | 2025-08-20 | Plastering-Gypsum | 100 | 0 |  | 2025-06-14 |  | 2025-07-17
11571 | T-18-2nd Floor | Complete | RCC | 2025-07-14 | 2025-07-15 | Slab& Beam RCC | 330.8 | 330.8 | CUM | 2025-06-14 | 2025-07-31 | 2025-06-15 | 2025-08-01
39671 | Tower A - Super Structure - Core Wall Mid Rise L61-62 | Complete | Core Wall RCC Works | 2025-06-14 | 2025-06-17 | ACS Form Closing & Alignment | 100 | 100 |  | 2025-06-14 | 2025-07-13 | 2025-06-17 | 2025-07-17 | Tower A | Super Structure | L61 | RCC Super Structure | Core Wall RCC Works
10162 | T-21-2nd Floor Flat Area | Forced Ready | Electrical DB Fixing | 2025-07-16 | 2025-08-01 | Electrical DB Fixing | 100 | 0 |  | 2025-06-15 |  | 2025-06-30
10042 | T-21-7th Floor | Quality checked | Shear Walls/Corewalls Shuttering | 2025-07-18 | 2025-07-22 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-06-16 | 2025-06-20 | 2025-06-20 | 2025-06-25
10558 | T-20-6th Floor | Quality checked | Slab& Beam Steel & Conduting | 2025-07-21 | 2025-07-24 | Slab& Beam Steel & Conduting | 10.8 | 10.8 | MT | 2025-06-16 | 2025-06-17 | 2025-06-19 | 2025-06-21
11568 | T-18-2nd Floor | Complete | Conduiting | 2025-06-25 | 2025-06-28 | Conduiting works | 100 | 100 |  | 2025-06-16 | 2025-07-15 | 2025-06-21 | 2025-07-23
11573 | T-18-3rd Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-07-17 | 2025-07-30 | AL - Shear Walls/Corewalls Steel | 20.5 | 20.5 | MT | 2025-06-16 | 2025-08-02 | 2025-06-23 | 2025-08-05
11574 | T-18-3rd Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-07-22 | 2025-08-04 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-06-16 | 2025-08-05 | 2025-06-28 | 2025-08-17
11575 | T-18-3rd Floor | Complete | Conduiting | 2025-07-17 | 2025-07-22 | Conduiting works | 100 | 100 |  | 2025-06-16 | 2025-08-06 | 2025-06-21 | 2025-08-16
11576 | T-18-3rd Floor | Complete | Shuttering | 2025-07-31 | 2025-08-17 | Slab and Beam Shuttering | 3527 | 3527 | Sqm | 2025-06-16 | 2025-08-08 | 2025-06-28 | 2025-08-16
11651 | T-18-Basement Floor | Forced Ready | Masonry Works | 2025-07-15 | 2025-10-23 | Masonry Works | 100 | 0 |  | 2025-06-16 |  | 2025-09-26
8982 | T-15-4th Floor | Quality checked | Conduiting | 2025-06-22 | 2025-06-25 | Conduiting works | 100 | 100 |  | 2025-06-17 | 2025-06-22 | 2025-06-20 | 2025-06-27
10653 | T-20-1st Floor Flat Area | Forced Ready | Plumbing Pipe Line | 2025-07-18 | 2025-08-16 | Plumbing Pipe Line | 100 | 0 |  | 2025-06-17 |  | 2025-07-15
48204 |  | Started |  | 2025-04-15 | 2026-06-06 | Blockwork & Plaster Works | 100 | 0 |  | 2025-06-17 | 2025-01-05 | 2026-12-04
48212 |  | Started |  | 2025-04-15 | 2025-12-10 | Basement Masonry (incl. de-shutt, PT mark, area clear) for MEP rooms, shafts & staircases | 100 | 0 |  | 2025-06-17 | 2025-01-05 | 2026-05-20
48215 | Retail & Clubhouse - Sub structure - B1 to GF | Started |  | 2025-06-17 | 2025-07-30 | B1 to GF | 100 | 0 |  | 2025-06-17 | 2025-01-05 | 2025-12-10 |  | Club House | Sub Structure | B1
48215 | Retail & Clubhouse - Sub structure - B1 to GF | Started |  | 2025-06-17 | 2025-07-30 | B1 to GF | 100 | 0 |  | 2025-06-17 | 2025-01-05 | 2025-12-10 |  | Club House | Sub Structure | B1
48215 | Retail & Clubhouse - Sub structure - B1 to GF | Started |  | 2025-06-17 | 2025-07-30 | B1 to GF | 100 | 0 |  | 2025-06-17 | 2025-01-05 | 2025-12-10 |  | Club House | Sub Structure | B1
8981 | T-15-4th Floor | Quality checked | Shear Walls/Corewalls Shuttering | 2025-06-23 | 2025-06-27 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-06-18 | 2025-06-23 | 2025-06-23 | 2025-06-29
9575 |  | Not Ready |  | 2025-08-16 | 2026-10-29 | Ground Floor | 100 | 0 |  | 2025-06-18 |  | 2026-09-01
9576 |  | Not Ready |  | 2025-08-16 | 2026-10-11 | Flat Area | 100 | 0 |  | 2025-06-18 |  | 2026-08-12
39672 | Tower A - Super Structure - Core Wall Mid Rise L61-62 | Complete | Core Wall RCC Works | 2025-06-18 | 2025-06-18 | Casting | 100 | 100 |  | 2025-06-18 | 2025-07-17 | 2025-06-18 | 2025-07-17 | Tower A | Super Structure | L61 | RCC Super Structure | Core Wall RCC Works
39974 |  | Complete |  | 2025-06-18 | 2025-06-25 | L57-58 | 100 | 100 |  | 2025-06-18 | 2025-06-19 | 2025-06-25 | 2025-07-14
39974 |  | Complete |  | 2025-06-18 | 2025-06-25 | L57-58 | 100 | 100 |  | 2025-06-18 | 2025-06-19 | 2025-06-25 | 2025-07-14 |  |  |  | Finishes | Gypsum Plastering Works
39975 | Tower A - Super Structure - Core & Outer Slab L57-58 | Complete | RCC Works - Vertical | 2025-06-18 | 2025-06-24 | Outer Columns_TA | 100 | 100 |  | 2025-06-18 | 2025-06-19 | 2025-06-24 | 2025-07-14 | Tower A | Super Structure | L57 | RCC Sub Structure | RCC Works - Vertical
40308 | Tower A - Super Structure - Finishes & MEP - L39 to L40 | Complete | Partition Wall-Blockwork | 2025-06-18 | 2025-06-23 | Staircase Area | 100 | 100 |  | 2025-06-18 | 2025-07-12 | 2025-06-23 | 2025-07-12 | Tower A | Super Structure | L39
40311 | Tower A - Super Structure - Finishes & MEP - L40 to L41 | Complete | Partition Wall-Blockwork | 2025-06-18 | 2025-06-25 | Partition Walls | 100 | 100 |  | 2025-06-18 | 2025-06-18 | 2025-06-25 | 2025-08-12 | Tower A | Super Structure | L40
8570 |  | Not Ready |  | 2025-06-18 | 2026-08-07 | Second Floor Flat Area | 100 | 0 |  | 2025-06-19 |  | 2026-08-08
8571 |  | Not Ready |  | 2025-06-18 | 2026-06-17 | Flat Area | 100 | 0 |  | 2025-06-19 |  | 2026-06-18
9499 | T-16-4th Floor | Complete |  | 2025-08-17 | 2025-08-30 | 3rd Floor Roof | 100 | 100 |  | 2025-06-19 | 2025-08-01 | 2025-07-02 | 2025-08-18
10044 | T-21-7th Floor | Quality checked | Shuttering | 2025-07-21 | 2025-07-25 | Slab and Beam Shuttering | 3264 | 3264 | Sqm | 2025-06-19 | 2025-06-21 | 2025-06-24 | 2025-06-28
10559 | T-20-6th Floor | Quality checked | RCC | 2025-07-24 | 2025-07-25 | Slab& Beam RCC | 321 | 321 | CUM | 2025-06-19 | 2025-06-21 | 2025-06-20 | 2025-06-22
10657 | T-20-1st Floor Flat Area | Forced Ready | Plastering | 2025-07-21 | 2025-09-09 | Plastering-Gypsum | 100 | 0 |  | 2025-06-19 |  | 2025-08-07
11170 |  | Not Committed |  | 2025-08-08 | 2026-10-30 | First Floor | 100 | 0 |  | 2025-06-19 |  | 2026-09-09
11171 |  | Not Committed |  | 2025-08-08 | 2026-09-02 | Flat Area | 100 | 0 |  | 2025-06-19 |  | 2026-07-14
39673 | Tower A - Super Structure - Core Wall Mid Rise L61-62 | Complete | Core Wall RCC Works | 2025-06-19 | 2025-06-19 | ACS Form Release & jump to next level | 100 | 100 |  | 2025-06-19 | 2025-07-19 | 2025-06-19 | 2025-07-19 | Tower A | Super Structure | L61 | RCC Super Structure | Core Wall RCC Works
8440 | T-14-6th Floor | Complete |  | 2025-06-19 | 2025-07-02 | 5th Floor Roof | 100 | 100 |  | 2025-06-20 | 2025-08-10 | 2025-07-03 | 2025-08-26
9070 | T-15-GF Flat Area | Not Ready | Railing | 2025-06-19 | 2025-07-04 | Balcony Railing | 100 | 0 |  | 2025-06-20 |  | 2025-07-04
10101 | T-21-GF Flat Area | Forced Ready | Electrical DB Fixing | 2025-06-18 | 2025-06-25 | Electrical DB Fixing | 100 | 0 |  | 2025-06-20 |  | 2025-06-27
10159 | T-21-2nd Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-07-21 | 2025-08-12 | Plumbing Pipe Line | 100 | 0 |  | 2025-06-20 |  | 2025-07-12
10702 |  | Not Ready |  | 2025-07-25 | 2026-08-08 | Third Floor | 100 | 0 |  | 2025-06-20 |  | 2026-07-04
10703 |  | Not Ready |  | 2025-07-25 | 2026-05-27 | Flat Area | 100 | 0 |  | 2025-06-20 |  | 2026-04-22
11066 | T-19-5th Floor | Complete |  | 2025-08-09 | 2025-08-23 | 4th Floor Roof | 100 | 100 |  | 2025-06-20 | 2025-08-13 | 2025-07-03 | 2025-08-30
39674 |  | Complete |  | 2025-06-20 | 2025-06-27 | Core Wall L62-63 | 100 | 100 |  | 2025-06-20 | 2025-07-21 | 2025-06-27 | 2025-07-27
39675 | Tower A - Super Structure - Core Wall Mid Rise L62-63 | Complete | Core Wall RCC Works | 2025-06-20 | 2025-06-20 | Scaffolding & platform | 100 | 100 |  | 2025-06-20 | 2025-07-21 | 2025-06-20 | 2025-07-21 | Tower A | Super Structure | L62 | RCC Super Structure | Core Wall RCC Works
39976 | Tower A - Super Structure - Core & Outer Slab L57-58 | Complete | RCC Works - Slab | 2025-06-20 | 2025-06-25 | Outer Slab_TA | 100 | 100 |  | 2025-06-20 | 2025-07-14 | 2025-06-25 | 2025-07-14 | Tower A | Super Structure | L57 | RCC Sub Structure | RCC Works - Slab
8983 | T-15-4th Floor | Quality checked | Shuttering | 2025-06-26 | 2025-07-01 | Slab and Beam Shuttering | 3715 | 3715 | Sqm | 2025-06-21 | 2025-06-26 | 2025-06-26 | 2025-07-01
9073 |  | Not Ready |  | 2025-06-26 | 2026-09-01 | Common Area | 100 | 0 |  | 2025-06-21 |  | 2026-08-27
10045 | T-21-7th Floor | Quality checked | Slab& Beam Steel & Conduting | 2025-07-23 | 2025-07-26 | Slab& Beam Steel & Conduting | 19.5 | 19.5 | MT | 2025-06-21 | 2025-06-23 | 2025-06-25 | 2025-06-29
10114 | T-21-GF Common Area | Forced Ready | Blockwork | 2025-06-19 | 2025-07-10 | Blockwork | 100 | 0 |  | 2025-06-21 |  | 2025-07-09
10560 | T-20-7th Floor | Complete |  | 2025-07-26 | 2025-08-08 | 6th Floor Roof | 100 | 100 |  | 2025-06-21 | 2025-06-25 | 2025-07-04 | 2025-07-06
10561 | T-20-7th Floor | Quality checked | AL - Shear Walls/Corewalls Steel | 2025-07-26 | 2025-07-30 | AL - Shear Walls/Corewalls Steel | 20.54 | 20.54 | MT | 2025-06-21 | 2025-06-25 | 2025-06-26 | 2025-06-30
11131 | T-19-Basement Floor | Forced Ready | Masonry Works | 2025-06-17 | 2025-09-24 | Masonry Works | 100 | 0 |  | 2025-06-21 |  | 2025-09-29
39676 | Tower A - Super Structure - Core Wall Mid Rise L62-63 | Complete | Core Wall RCC Works | 2025-06-21 | 2025-06-24 | Reinf & Guide shoes fixing | 100 | 100 |  | 2025-06-21 | 2025-07-24 | 2025-06-24 | 2025-07-24 | Tower A | Super Structure | L62 | RCC Super Structure | Core Wall RCC Works
10163 | T-21-2nd Floor Flat Area | Forced Ready | Plastering | 2025-07-23 | 2025-09-06 | Plastering-Gypsum | 100 | 0 |  | 2025-06-22 |  | 2025-08-03
10118 | T-21-GF Common Area | Forced Ready | Electrical DB Fixing | 2025-06-21 | 2025-06-28 | Electrical DB Fixing | 100 | 0 |  | 2025-06-23 |  | 2025-06-30
10678 | T-20-2nd Floor Flat Area | Not Ready | Blockwork | 2025-07-25 | 2025-08-17 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-06-23 |  | 2025-07-14
10717 | T-20-3rd Floor Flat Area | Not Ready | Railing | 2025-07-25 | 2025-08-28 | Balcony Railing | 100 | 0 |  | 2025-06-23 |  | 2025-07-24
39236 |  | Started |  | 2025-06-23 | 2025-08-01 | High Side Installation - Installation of Condensor Water Pumps and Cooling Towers (GF) | 100 | 65 |  | 2025-06-23 | 2025-06-27 | 2025-10-27
39677 | Tower A - Super Structure - Core Wall Mid Rise L62-63 | Complete | Core Wall RCC Works | 2025-06-23 | 2025-06-25 | ACS Form Closing & Alignment | 100 | 100 |  | 2025-06-23 | 2025-07-22 | 2025-06-25 | 2025-07-25 | Tower A | Super Structure | L62 | RCC Super Structure | Core Wall RCC Works
8984 | T-15-4th Floor | Complete | Slab& Beam Steel & Conduting | 2025-06-28 | 2025-07-02 | Slab& Beam Steel & Conduting | 13 | 13 | MT | 2025-06-24 | 2025-06-30 | 2025-06-27 | 2025-07-08
10563 | T-20-7th Floor | Complete | Conduiting | 2025-07-28 | 2025-07-31 | Conduiting works | 100 | 100 |  | 2025-06-24 | 2025-06-27 | 2025-06-27 | 2025-07-01
10654 | T-20-1st Floor Flat Area | Not Ready | Plastering | 2025-07-26 | 2025-08-18 | Plastering-Cement | 100 | 0 |  | 2025-06-24 |  | 2025-07-12
10668 |  | Not Ready |  | 2025-07-28 | 2026-09-17 | Common Area | 100 | 0 |  | 2025-06-24 |  | 2026-08-12
10046 | T-21-7th Floor | Quality checked | RCC | 2025-07-26 | 2025-07-28 | Slab& Beam RCC | 318 | 318 | CUM | 2025-06-25 | 2025-06-29 | 2025-06-26 | 2025-06-30
10098 | T-21-GF Flat Area | Forced Ready | Plumbing Pipe Line | 2025-06-23 | 2025-07-09 | Plumbing Pipe Line | 100 | 0 |  | 2025-06-25 |  | 2025-07-12
10562 | T-20-7th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-07-29 | 2025-08-02 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-06-25 | 2025-06-28 | 2025-06-29 | 2025-07-02
10682 | T-20-2nd Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-07-27 | 2025-08-13 | Electrical DB Fixing | 100 | 0 |  | 2025-06-25 |  | 2025-07-11
11056 | T-19-3rd Floor | Complete | Shuttering | 2025-07-04 | 2025-07-19 | Slab and Beam Shuttering | 3548 | 3548 | Sqm | 2025-06-25 | 2025-07-02 | 2025-07-11 | 2025-07-16
11057 | T-19-3rd Floor | Complete | Slab& Beam Steel & Conduting | 2025-07-15 | 2025-07-23 | Slab& Beam Steel & Conduting | 11.3 | 11.3 | MT | 2025-06-25 | 2025-07-17 | 2025-07-04 | 2025-07-21
11577 | T-18-3rd Floor | Complete | Slab& Beam Steel & Conduting | 2025-08-11 | 2025-08-20 | Slab& Beam Steel & Conduting | 10.8 | 10.8 | MT | 2025-06-25 | 2025-08-14 | 2025-06-30 | 2025-08-21
9593 |  | Not Ready |  | 2025-08-23 | 2026-10-29 | Common Area | 100 | 0 |  | 2025-06-26 |  | 2026-09-01
10208 |  | Not Ready |  | 2025-07-28 | 2026-06-25 | Fourth Floor | 100 | 0 |  | 2025-06-26 |  | 2026-05-25
10209 |  | Not Ready |  | 2025-07-28 | 2026-05-14 | Flat Area | 100 | 0 |  | 2025-06-26 |  | 2026-04-10
10620 | T-20-GF Flat Area | Not Ready | Waterproofing | 2025-07-28 | 2025-08-20 | Waterproofing | 100 | 0 |  | 2025-06-26 |  | 2025-07-17
10669 | T-20-1st Floor Common Area | Not Ready | Plastering | 2025-07-28 | 2025-08-31 | Plastering-Gypsum | 100 | 0 |  | 2025-06-26 |  | 2025-07-29
11565 | T-18-2nd Floor | Complete |  | 2025-06-11 | 2025-07-15 | 1st Floor Roof | 100 | 100 |  | 2025-06-26 | 2025-07-14 | 2025-07-07 | 2025-08-01
39678 | Tower A - Super Structure - Core Wall Mid Rise L62-63 | Complete | Core Wall RCC Works | 2025-06-26 | 2025-06-26 | Casting | 100 | 100 |  | 2025-06-26 | 2025-07-26 | 2025-06-26 | 2025-07-26 | Tower A | Super Structure | L62 | RCC Super Structure | Core Wall RCC Works
39977 |  | Complete |  | 2025-06-26 | 2025-07-03 | L58-59 | 100 | 100 |  | 2025-06-26 | 2025-07-26 | 2025-07-03 | 2025-07-26
39977 |  | Complete |  | 2025-06-26 | 2025-07-03 | L58-59 | 100 | 100 |  | 2025-06-26 | 2025-07-26 | 2025-07-03 | 2025-07-26 |  |  |  | Finishes | Gypsum Plastering Works
39978 | Tower A - Super Structure - Core & Outer Slab L58-59 | Complete | RCC Works - Vertical | 2025-06-26 | 2025-07-02 | Outer Columns_TA | 100 | 100 | Units | 2025-06-26 | 2025-07-26 | 2025-07-02 | 2025-07-26 | Tower A | Super Structure | L58 | RCC Sub Structure | RCC Works - Vertical
40312 | Tower A - Super Structure - Finishes & MEP - L40 to L41 | Complete | Partition Wall-Blockwork | 2025-06-26 | 2025-07-01 | Staircase Area | 100 | 100 |  | 2025-06-26 | 2025-07-17 | 2025-07-01 | 2025-07-17 | Tower A | Super Structure | L40
40319 | Tower A - Super Structure - Finishes & MEP - L41 to L42 | Complete | Partition Wall-Blockwork | 2025-06-26 | 2025-07-03 | Partition Walls | 100 | 100 |  | 2025-06-26 | 2025-08-09 | 2025-07-03 | 2025-08-09 | Tower A | Super Structure | L41
8505 | T-14-Basement Floor | Not Ready | Masonry Works | 2025-05-19 | 2025-08-26 | Masonry Works | 100 | 0 |  | 2025-06-27 |  | 2025-10-06
8524 | T-14-GF Flat Area | Not Ready | Railing | 2025-05-19 | 2025-06-03 | Balcony Railing | 100 | 0 |  | 2025-06-27 |  | 2025-07-14
9087 | T-15-GF Common Area | Not Ready | Railing | 2025-06-26 | 2025-07-11 | Balcony Railing | 100 | 0 |  | 2025-06-27 |  | 2025-07-11
10047 | T-21-8th Floor | Complete |  | 2025-07-29 | 2025-08-11 | 7th Floor Roof | 100 | 100 |  | 2025-06-27 | 2025-07-01 | 2025-07-10 | 2025-07-20
10160 | T-21-2nd Floor Flat Area | Forced Ready | Plastering | 2025-07-29 | 2025-08-21 | Plastering-Cement | 100 | 0 |  | 2025-06-27 |  | 2025-07-18
39679 | Tower A - Super Structure - Core Wall Mid Rise L62-63 | Complete | Core Wall RCC Works | 2025-06-27 | 2025-06-27 | ACS Form Release & jump to next level | 100 | 100 |  | 2025-06-27 | 2025-07-27 | 2025-06-27 | 2025-07-27 | Tower A | Super Structure | L62 | RCC Super Structure | Core Wall RCC Works
8432 | T-14-4th Floor | Complete | RCC | 2025-06-02 | 2025-06-03 | Slab& Beam RCC | 307 | 307 | CUM | 2025-06-28 | 2025-07-18 | 2025-06-29 | 2025-07-19
9090 |  | Not Ready |  | 2025-07-03 | 2026-09-23 | First Floor | 100 | 0 |  | 2025-06-28 |  | 2026-09-18
9091 |  | Not Ready |  | 2025-07-03 | 2026-07-27 | Flat Area | 100 | 0 |  | 2025-06-28 |  | 2026-07-22
10115 | T-21-GF Common Area | Forced Ready | Plumbing Pipe Line | 2025-06-26 | 2025-07-12 | Plumbing Pipe Line | 100 | 0 |  | 2025-06-28 |  | 2025-07-13
39680 |  | Complete |  | 2025-06-28 | 2025-07-17 | Core Wall L63-64 (MEP Transfer Floor) | 100 | 100 |  | 2025-06-28 | 2025-07-31 | 2025-07-17 | 2025-08-07
39681 | Tower A - Super Structure - Core Wall Mid Rise L63-64 | Complete | Core Wall RCC Works | 2025-06-28 | 2025-07-05 | Core Wall Modification | 100 | 100 |  | 2025-06-28 | 2025-07-31 | 2025-07-05 | 2025-07-31 | Tower A | Super Structure | L63 | RCC Super Structure | Core Wall RCC Works
39979 | Tower A - Super Structure - Core & Outer Slab L58-59 | Complete | RCC Works - Slab | 2025-06-28 | 2025-07-03 | Outer Slab_TA | 100 | 100 | Units | 2025-06-28 | 2025-07-26 | 2025-07-03 | 2025-07-26 | Tower A | Super Structure | L58 | RCC Sub Structure | RCC Works - Slab
8986 | T-15-5th Floor | Complete |  | 2025-07-04 | 2025-07-17 | 4th Floor Roof | 100 | 100 |  | 2025-06-29 | 2025-07-10 | 2025-07-12 | 2025-07-26
10102 | T-21-GF Flat Area | Forced Ready | Plastering | 2025-06-26 | 2025-07-29 | Plastering-Gypsum | 100 | 0 |  | 2025-06-29 |  | 2025-08-02
10174 |  | Not Ready |  | 2025-07-31 | 2026-08-20 | Common Area | 100 | 0 |  | 2025-06-29 |  | 2026-07-18
10175 | T-21-2nd Floor Common Area | Forced Ready | Plastering | 2025-07-31 | 2025-09-03 | Plastering-Gypsum | 100 | 0 |  | 2025-06-29 |  | 2025-07-30
8511 | T-14-GF Flat Area | Not Ready | Blockwork | 2025-06-03 | 2025-06-24 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-06-30 |  | 2025-07-22
8559 | T-14-1st Floor Flat Area | Not Ready | Railing | 2025-06-03 | 2025-07-05 | Balcony Railing | 100 | 0 |  | 2025-06-30 |  | 2025-07-31
9490 | T-16-2nd Floor | Complete | Slab& Beam Steel & Conduting | 2025-06-28 | 2025-07-07 | Slab& Beam Steel & Conduting | 14 | 14 | MT | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-11
10679 | T-20-2nd Floor Flat Area | Forced Ready | Plumbing Pipe Line | 2025-08-01 | 2025-08-25 | Plumbing Pipe Line | 100 | 0 |  | 2025-06-30 |  | 2025-07-20
8434 | T-14-5th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-06-04 | 2025-06-08 | AL - Shear Walls/Corewalls Steel | 22 | 22 | MT | 2025-07-01 | 2025-07-20 | 2025-07-03 | 2025-07-26
9052 | T-15-Basement Floor | Not Ready | Plastering | 2025-06-16 | 2025-09-23 | Plastering | 100 | 0 |  | 2025-07-01 |  | 2025-10-09
10184 | T-21-3rd Floor Flat Area | Forced Ready | Blockwork | 2025-07-28 | 2025-08-20 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-07-01 |  | 2025-07-22
10223 | T-21-4th Floor Flat Area | Forced Ready | Railing | 2025-07-28 | 2025-08-30 | Balcony Railing | 100 | 0 |  | 2025-07-01 |  | 2025-07-31
10564 | T-20-7th Floor | Complete | Shuttering | 2025-08-01 | 2025-08-06 | Slab and Beam Shuttering | 3583 | 3583 | Sqm | 2025-07-01 | 2025-06-30 | 2025-07-05 | 2025-07-03
11055 | T-19-3rd Floor | Complete | Conduiting | 2025-07-02 | 2025-07-06 | Conduiting works | 100 | 100 |  | 2025-07-01 | 2025-06-25 | 2025-07-07 | 2025-07-14
11572 | T-18-3rd Floor | Complete |  | 2025-07-17 | 2025-08-21 | 2nd Floor Roof | 100 | 100 |  | 2025-07-01 | 2025-08-02 | 2025-07-12 | 2025-08-22
11578 | T-18-3rd Floor | Complete | RCC | 2025-08-20 | 2025-08-21 | Slab& Beam RCC | 330.8 | 330.8 | CUM | 2025-07-01 | 2025-08-21 | 2025-07-01 | 2025-08-22
11649 |  | Not Ready |  | 2025-07-15 | 2027-02-11 | Finishing Works | 100 | 0 |  | 2025-07-01 |  | 2026-12-07
11650 |  | Not Ready |  | 2025-07-15 | 2026-11-25 | Basement Floor | 100 | 0 |  | 2025-07-01 |  | 2026-09-24
8515 | T-14-GF Flat Area | Not Ready | Electrical DB Fixing | 2025-06-05 | 2025-06-12 | Electrical DB Fixing | 100 | 0 |  | 2025-07-02 |  | 2025-07-09
9610 |  | Not Ready |  | 2025-08-30 | 2026-11-22 | First Floor | 100 | 0 |  | 2025-07-02 |  | 2026-09-22
9611 |  | Not Ready |  | 2025-08-30 | 2026-09-24 | Flat Area | 100 | 0 |  | 2025-07-02 |  | 2026-07-27
10048 | T-21-8th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-07-29 | 2025-08-02 | AL - Shear Walls/Corewalls Steel | 19.5 | 19.5 | MT | 2025-07-02 | 2025-07-01 | 2025-07-04 | 2025-07-04
10099 | T-21-GF Flat Area | Not Ready | Plastering | 2025-07-01 | 2025-07-17 | Plastering-Cement | 100 | 0 |  | 2025-07-02 |  | 2025-07-17
10141 | T-21-1st Floor Flat Area | Forced Ready | Flooring & skirting | 2025-08-06 | 2025-09-19 | Flooring & skirting | 100 | 0 |  | 2025-07-02 |  | 2025-08-14
10683 | T-20-2nd Floor Flat Area | Not Ready | Plastering | 2025-08-04 | 2025-09-17 | Plastering-Gypsum | 100 | 0 |  | 2025-07-02 |  | 2025-08-17
11670 | T-18-GF Flat Area | Not Ready | Railing | 2025-08-21 | 2025-09-05 | Balcony Railing | 100 | 0 |  | 2025-07-02 |  | 2025-07-17
8436 | T-14-5th Floor | Complete | Conduiting | 2025-06-06 | 2025-06-09 | Conduiting works | 100 | 100 |  | 2025-07-03 | 2025-07-22 | 2025-07-04 | 2025-07-28
8528 | T-14-GF Common Area | Not Ready | Blockwork | 2025-06-06 | 2025-06-27 | Blockwork | 100 | 0 |  | 2025-07-03 |  | 2025-07-23
8596 |  | Not Ready |  | 2025-07-02 | 2026-07-17 | Third Floor | 100 | 0 |  | 2025-07-03 |  | 2026-07-18
8597 |  | Not Ready |  | 2025-07-02 | 2026-05-05 | Flat Area | 100 | 0 |  | 2025-07-03 |  | 2026-05-06
9491 | T-16-2nd Floor | Complete | RCC | 2025-07-07 | 2025-07-08 | Slab& Beam RCC | 387 | 387 | CUM | 2025-07-03 | 2025-07-11 | 2025-07-04 | 2025-07-12
9506 | T-16-5th Floor | Complete |  | 2025-09-01 | 2025-09-13 | 4th Floor Roof | 100 | 100 |  | 2025-07-03 | 2025-08-25 | 2025-07-16 | 2025-09-06
10188 | T-21-3rd Floor Flat Area | Forced Ready | Electrical DB Fixing | 2025-07-30 | 2025-08-16 | Electrical DB Fixing | 100 | 0 |  | 2025-07-03 |  | 2025-07-17
10565 | T-20-7th Floor | Complete | Slab& Beam Steel & Conduting | 2025-08-04 | 2025-08-07 | Slab& Beam Steel & Conduting | 10.8 | 10.8 | MT | 2025-07-03 | 2025-07-02 | 2025-07-06 | 2025-07-05
11196 |  | Not Ready |  | 2025-08-23 | 2026-10-14 | Second Floor Flat Area | 100 | 0 |  | 2025-07-03 |  | 2026-08-24
11197 |  | Not Ready |  | 2025-08-23 | 2026-08-22 | Flat Area | 100 | 0 |  | 2025-07-03 |  | 2026-07-03
11579 | T-18-4th Floor | Complete |  | 2025-08-22 | 2025-09-04 | 3rd Floor Roof | 100 | 100 |  | 2025-07-03 | 2025-08-24 | 2025-07-12 | 2025-09-10
11580 | T-18-4th Floor | Quality checked | AL - Shear Walls/Corewalls Steel | 2025-08-22 | 2025-08-27 | AL - Shear Walls/Corewalls Steel | 20.5 | 20.5 | MT | 2025-07-03 | 2025-08-24 | 2025-07-08 | 2025-08-29
8435 | T-14-5th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-06-07 | 2025-06-11 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-07-04 | 2025-07-23 | 2025-07-09 | 2025-07-29
8447 | T-14-7th Floor | Complete |  | 2025-07-03 | 2025-07-16 | 6th Floor Roof | 100 | 100 |  | 2025-07-04 | 2025-08-29 | 2025-07-17 | 2025-09-13
8541 | T-14-GF Common Area | Not Ready | Railing | 2025-05-26 | 2025-06-10 | Balcony Railing | 100 | 0 |  | 2025-07-04 |  | 2025-07-19
8985 | T-15-4th Floor | Complete | RCC | 2025-07-02 | 2025-07-03 | Slab& Beam RCC | 318 | 318 | CUM | 2025-07-04 | 2025-07-08 | 2025-07-04 | 2025-07-09
9461 | T-16-Sub structure- Grade slab | Not Ready | Grade Slab RCC | 2025-06-08 | 2025-07-11 | Grade Slab RCC | 356 | 0 | CUM | 2025-07-04 |  | 2025-08-06
10050 | T-21-8th Floor | Complete | Conduiting | 2025-07-31 | 2025-08-04 | Conduiting works | 100 | 100 |  | 2025-07-04 | 2025-07-03 | 2025-07-08 | 2025-07-11
10637 | T-20-GF Common Area | Forced Ready | Waterproofing | 2025-08-06 | 2025-08-29 | Waterproofing | 100 | 0 |  | 2025-07-04 |  | 2025-07-28
10728 |  | Not Ready |  | 2025-08-08 | 2026-07-07 | Fourth Floor | 100 | 0 |  | 2025-07-04 |  | 2026-06-02
10729 |  | Not Ready |  | 2025-08-08 | 2026-05-25 | Flat Area | 100 | 0 |  | 2025-07-04 |  | 2026-04-20
11073 | T-19-6th Floor | Complete |  | 2025-08-24 | 2025-09-06 | 5th Floor Roof | 100 | 100 |  | 2025-07-04 | 2025-09-01 | 2025-07-17 | 2025-09-21
39980 |  | Complete |  | 2025-07-04 | 2025-07-10 | L59-60 | 100 | 100 |  | 2025-07-04 | 2025-07-25 | 2025-07-10 | 2025-08-06
39980 |  | Complete |  | 2025-07-04 | 2025-07-10 | L59-60 | 100 | 100 |  | 2025-07-04 | 2025-07-25 | 2025-07-10 | 2025-08-06 |  |  |  | Finishes | Gypsum Plastering Works
39981 | Tower A - Super Structure - Core & Outer Slab L59-60 | Complete | RCC Works - Vertical | 2025-07-04 | 2025-07-10 | Outer Columns_TA | 100 | 100 |  | 2025-07-04 | 2025-07-25 | 2025-07-10 | 2025-08-06 | Tower A | Super Structure | L59 | RCC Sub Structure | RCC Works - Vertical
40320 | Tower A - Super Structure - Finishes & MEP - L41 to L42 | Complete | Partition Wall-Blockwork | 2025-07-04 | 2025-07-09 | Staircase Area | 100 | 100 |  | 2025-07-04 | 2025-08-09 | 2025-07-09 | 2025-08-09 | Tower A | Super Structure | L41
40327 | Tower A - Super Structure - Finishes & MEP - L42 to L43 | Complete | Partition Wall-Blockwork | 2025-07-04 | 2025-07-11 | Partition Walls | 100 | 100 | Units | 2025-07-04 | 2025-07-23 | 2025-07-11 | 2025-08-30 | Tower A | Super Structure | L42
8532 | T-14-GF Common Area | Not Ready | Electrical DB Fixing | 2025-06-08 | 2025-06-16 | Electrical DB Fixing | 100 | 0 |  | 2025-07-05 |  | 2025-07-13
9057 | T-15-GF Flat Area | Not Ready | Blockwork | 2025-07-03 | 2025-07-25 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-07-05 |  | 2025-07-23
9105 | T-15-1st Floor Flat Area | Not Ready | Railing | 2025-07-03 | 2025-08-05 | Balcony Railing | 100 | 0 |  | 2025-07-05 |  | 2025-08-04
9571 | T-16-Basement Floor | Not Ready | Masonry Works | 2025-07-08 | 2025-10-16 | Masonry Works | 100 | 0 |  | 2025-07-05 |  | 2025-10-12
10049 | T-21-8th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-08-01 | 2025-08-06 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-07-05 | 2025-07-04 | 2025-07-09 | 2025-07-11
10116 | T-21-GF Common Area | Forced Ready | Plastering | 2025-07-04 | 2025-07-25 | Plastering-Cement | 100 | 0 |  | 2025-07-05 |  | 2025-07-29
10135 | T-21-1st Floor Flat Area | Forced Ready | Waterproofing | 2025-08-06 | 2025-09-25 | Waterproofing | 100 | 0 |  | 2025-07-05 |  | 2025-08-23
10567 | T-20-8th Floor | Complete |  | 2025-08-09 | 2025-08-23 | 7th Floor Roof | 100 | 100 |  | 2025-07-05 | 2025-07-09 | 2025-07-18 | 2025-07-24
10639 | T-20-GF Common Area | Forced Ready | Plastering | 2025-08-06 | 2025-09-09 | Plastering-Gypsum | 100 | 0 |  | 2025-07-05 |  | 2025-08-07
11021 | T-19-Sub structure- Grade slab | Forced Ready | Grade Slab RCC | 2025-06-04 | 2025-07-07 | Grade Slab RCC | 356 | 0 | CUM | 2025-07-05 |  | 2025-08-07
11058 | T-19-3rd Floor | Complete | RCC | 2025-07-23 | 2025-07-24 | Slab& Beam RCC | 340 | 340 | CUM | 2025-07-05 | 2025-07-22 | 2025-07-06 | 2025-07-22
11582 | T-18-4th Floor | Complete | Conduiting | 2025-08-25 | 2025-08-28 | Conduiting works | 100 | 100 |  | 2025-07-05 | 2025-08-26 | 2025-07-06 | 2025-08-31
39982 | Tower A - Super Structure - Core & Outer Slab L59-60 | Complete | RCC Works - Slab | 2025-07-05 | 2025-07-10 | Outer Slab_TA | 100 | 100 |  | 2025-07-05 | 2025-08-06 | 2025-07-10 | 2025-08-06 | Tower A | Super Structure | L59 | RCC Sub Structure | RCC Works - Slab
8388 | T-14-Sub structure Grade slab | Started | Grade Slab RCC | 2025-05-08 | 2025-06-10 | Grade Slab RCC | 356 | 0 | CUM | 2025-07-06 | 2025-09-10 | 2025-08-07
8987 | T-15-5th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-07-04 | 2025-07-08 | AL - Shear Walls/Corewalls Steel | 24.5 | 24.5 | MT | 2025-07-06 | 2025-07-10 | 2025-07-09 | 2025-07-15
11581 | T-18-4th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-08-26 | 2025-08-30 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-07-06 | 2025-08-26 | 2025-07-08 | 2025-08-28
8437 | T-14-5th Floor | Complete | Shuttering | 2025-06-10 | 2025-06-14 | Slab and Beam Shuttering | 3605 | 3605 | Sqm | 2025-07-07 | 2025-07-30 | 2025-07-12 | 2025-08-02
8512 | T-14-GF Flat Area | Not Ready | Plumbing Pipe Line | 2025-06-10 | 2025-06-26 | Plumbing Pipe Line | 100 | 0 |  | 2025-07-07 |  | 2025-07-23
8562 |  | Not Ready |  | 2025-07-05 | 2026-08-25 | Common Area | 100 | 0 |  | 2025-07-07 |  | 2026-08-26
9061 | T-15-GF Flat Area | Not Ready | Electrical DB Fixing | 2025-07-05 | 2025-07-12 | Electrical DB Fixing | 100 | 0 |  | 2025-07-07 |  | 2025-07-15
9493 | T-16-3rd Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-07-10 | 2025-07-23 | AL - Shear Walls/Corewalls Steel | 25 | 25 | MT | 2025-07-07 | 2025-07-14 | 2025-07-19 | 2025-07-18
10566 | T-20-7th Floor | Complete | RCC | 2025-08-07 | 2025-08-08 | Slab& Beam RCC | 321 | 321 | CUM | 2025-07-07 | 2025-07-06 | 2025-07-10 | 2025-07-06
10680 | T-20-2nd Floor Flat Area | Not Ready | Plastering | 2025-08-09 | 2025-09-01 | Plastering-Cement | 100 | 0 |  | 2025-07-07 |  | 2025-07-27
11150 | T-19-GF Flat Area | Not Ready | Railing | 2025-07-24 | 2025-08-09 | Balcony Railing | 100 | 0 |  | 2025-07-07 |  | 2025-07-22
11655 |  | Not Ready |  | 2025-08-21 | 2026-11-05 | Ground Floor | 100 | 0 |  | 2025-07-07 |  | 2026-09-04
11656 |  | Not Ready |  | 2025-08-21 | 2026-10-16 | Flat Area | 100 | 0 |  | 2025-07-07 |  | 2026-08-17
39682 | Tower A - Super Structure - Core Wall Mid Rise L63-64 | Complete | Core Wall RCC Works | 2025-07-07 | 2025-07-07 | Scaffolding & platform | 100 | 100 |  | 2025-07-07 | 2025-08-02 | 2025-07-07 | 2025-08-02 | Tower A | Super Structure | L63 | RCC Super Structure | Core Wall RCC Works
8989 | T-15-5th Floor | Complete | Conduiting | 2025-07-06 | 2025-07-09 | Conduiting works | 100 | 100 |  | 2025-07-08 | 2025-07-11 | 2025-07-13 | 2025-07-14
9074 | T-15-GF Common Area | Not Ready | Blockwork | 2025-07-06 | 2025-07-28 | Blockwork | 100 | 0 |  | 2025-07-08 |  | 2025-07-30
10051 | T-21-8th Floor | Complete | Shuttering | 2025-08-05 | 2025-08-09 | Slab and Beam Shuttering | 3264 | 3264 | Sqm | 2025-07-08 | 2025-07-06 | 2025-07-13 | 2025-07-15
10185 | T-21-3rd Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-08-05 | 2025-08-27 | Plumbing Pipe Line | 100 | 0 |  | 2025-07-08 |  | 2025-07-30
10694 |  | Not Ready |  | 2025-08-12 | 2026-09-01 | Common Area | 100 | 0 |  | 2025-07-08 |  | 2026-07-27
11059 | T-19-4th Floor | Complete |  | 2025-07-25 | 2025-08-08 | 3rd Floor Roof | 100 | 100 |  | 2025-07-08 | 2025-07-24 | 2025-07-22 | 2025-08-11
11060 | T-19-4th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-07-25 | 2025-07-30 | AL - Shear Walls/Corewalls Steel | 28.4 | 28.4 | MT | 2025-07-08 | 2025-07-24 | 2025-07-13 | 2025-07-30
39683 | Tower A - Super Structure - Core Wall Mid Rise L63-64 | Complete | Core Wall RCC Works | 2025-07-08 | 2025-07-10 | Reinf & Guide shoes fixing | 100 | 100 |  | 2025-07-08 | 2025-08-04 | 2025-07-10 | 2025-08-04 | Tower A | Super Structure | L63 | RCC Super Structure | Core Wall RCC Works
8988 | T-15-5th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-07-07 | 2025-07-11 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-07-09 | 2025-07-12 | 2025-07-14 | 2025-07-17
10695 | T-20-2nd Floor Common Area | Not Ready | Plastering | 2025-08-12 | 2025-09-14 | Plastering-Gypsum | 100 | 0 |  | 2025-07-09 |  | 2025-08-09
11583 | T-18-4th Floor | Complete | Shuttering | 2025-08-29 | 2025-09-02 | Slab and Beam Shuttering | 3527 | 3527 | Sqm | 2025-07-09 | 2025-08-28 | 2025-07-11 | 2025-09-06
11687 | T-18-GF Common Area | Not Ready | Railing | 2025-08-29 | 2025-09-13 | Balcony Railing | 100 | 0 |  | 2025-07-09 |  | 2025-07-24
39684 | Tower A - Super Structure - Core Wall Mid Rise L63-64 | Complete | Core Wall RCC Works | 2025-07-09 | 2025-07-11 | ACS Form Closing & Alignment | 100 | 100 |  | 2025-07-09 | 2025-08-05 | 2025-07-11 | 2025-08-05 | Tower A | Super Structure | L63 | RCC Super Structure | Core Wall RCC Works
8438 | T-14-5th Floor | Complete |  | 2025-06-13 | 2025-06-17 | Slab& Beam Steel & Conduting | 100 | 100 | MT | 2025-07-10 | 2025-08-01 | 2025-07-17 | 2025-08-07
8529 | T-14-GF Common Area | Not Ready | Plumbing Pipe Line | 2025-06-13 | 2025-06-30 | Plumbing Pipe Line | 100 | 0 |  | 2025-07-10 |  | 2025-07-25
9078 | T-15-GF Common Area | Not Ready | Electrical DB Fixing | 2025-07-08 | 2025-07-16 | Electrical DB Fixing | 100 | 0 |  | 2025-07-10 |  | 2025-07-18
10052 | T-21-8th Floor | Complete | Slab& Beam Steel & Conduting | 2025-08-07 | 2025-08-10 | Slab& Beam Steel & Conduting | 19.5 | 19.5 | MT | 2025-07-10 | 2025-07-16 | 2025-07-12 | 2025-07-19
10189 | T-21-3rd Floor Flat Area | Not Ready | Plastering | 2025-08-07 | 2025-09-20 | Plastering-Gypsum | 100 | 0 |  | 2025-07-10 |  | 2025-08-22
10234 |  | Not Ready |  | 2025-08-11 | 2026-05-23 | Fifth Floor | 100 | 0 |  | 2025-07-10 |  | 2026-04-21
10235 |  | Not Ready |  | 2025-08-11 | 2026-04-16 | Flat Area | 100 | 0 |  | 2025-07-10 |  | 2026-03-13
11062 | T-19-4th Floor | Complete | Conduiting | 2025-07-28 | 2025-07-31 | Conduiting works | 100 | 100 | Units | 2025-07-10 | 2025-07-29 | 2025-07-13 | 2025-08-02
8516 | T-14-GF Flat Area | Not Ready | Plastering | 2025-06-13 | 2025-07-16 | Plastering-Gypsum | 100 | 0 |  | 2025-07-11 |  | 2025-08-13
10623 | T-20-GF Flat Area | Not Ready | Dado | 2025-08-14 | 2025-09-05 | Dado | 100 | 0 |  | 2025-07-11 |  | 2025-08-01
10704 | T-20-3rd Floor Flat Area | Forced Ready | Blockwork | 2025-08-08 | 2025-08-31 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-07-11 |  | 2025-08-01
10743 | T-20-4th Floor Flat Area | Not Ready | Railing | 2025-08-08 | 2025-09-11 | Balcony Railing | 100 | 0 |  | 2025-07-11 |  | 2025-08-11
11061 | T-19-4th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-07-29 | 2025-08-02 | Shear Walls/Corewalls Shuttering | 100 | 100 | Units | 2025-07-11 | 2025-07-29 | 2025-07-14 | 2025-08-03
11584 | T-18-4th Floor | Complete | Slab& Beam Steel & Conduting | 2025-08-31 | 2025-09-03 | Slab& Beam Steel & Conduting | 10.8 | 10.8 | MT | 2025-07-11 | 2025-09-02 | 2025-07-11 | 2025-09-09
39983 |  | Complete |  | 2025-07-11 | 2025-07-24 | L60-61 | 100 | 100 |  | 2025-07-11 | 2025-08-07 | 2025-07-24 | 2025-08-14
39983 |  | Complete |  | 2025-07-11 | 2025-07-24 | L60-61 | 100 | 100 |  | 2025-07-11 | 2025-08-07 | 2025-07-24 | 2025-08-14 |  |  |  | Finishes | Gypsum Plastering Works
39984 | Tower A - Super Structure - Core & Outer Slab L60-61 | Complete | RCC Works - Vertical | 2025-07-11 | 2025-07-18 | Outer Columns_TA | 100 | 100 |  | 2025-07-11 | 2025-08-07 | 2025-07-18 | 2025-08-11 | Tower A | Super Structure | L60 | RCC Sub Structure | RCC Works - Vertical
8990 | T-15-5th Floor | Complete | Shuttering | 2025-07-10 | 2025-07-15 | Slab and Beam Shuttering | 3715 | 3715 | Sqm | 2025-07-12 | 2025-07-14 | 2025-07-17 | 2025-07-21
9058 | T-15-GF Flat Area | Not Ready | Plumbing Pipe Line | 2025-07-10 | 2025-07-27 | Plumbing Pipe Line | 100 | 0 |  | 2025-07-12 |  | 2025-07-27
9116 |  | Not Ready |  | 2025-07-17 | 2026-09-07 | Second Floor Flat Area | 100 | 0 |  | 2025-07-12 |  | 2026-09-02
9117 |  | Not Ready |  | 2025-07-17 | 2026-07-16 | Flat Area | 100 | 0 |  | 2025-07-12 |  | 2026-07-11
9494 | T-16-3rd Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-07-15 | 2025-07-29 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-07-12 | 2025-07-16 | 2025-07-24 | 2025-07-25
9496 | T-16-3rd Floor | Complete | Shuttering | 2025-07-26 | 2025-08-11 | Slab and Beam Shuttering | 4183 | 4183 | Sqm | 2025-07-12 | 2025-07-17 | 2025-07-24 | 2025-07-27
10138 | T-21-1st Floor Flat Area | Not Ready | Dado | 2025-08-13 | 2025-09-10 | Dado | 100 | 0 |  | 2025-07-12 |  | 2025-08-08
10568 | T-20-8th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-08-09 | 2025-08-14 | AL - Shear Walls/Corewalls Steel | 20.54 | 20.54 | MT | 2025-07-12 | 2025-07-09 | 2025-07-17 | 2025-07-11
11585 | T-18-4th Floor | Complete | RCC | 2025-09-03 | 2025-09-04 | Slab& Beam RCC | 330.8 | 330.8 | CUM | 2025-07-12 | 2025-09-09 | 2025-07-12 | 2025-09-10
39685 | Tower A - Super Structure - Core Wall Mid Rise L63-64 | Complete | Core Wall RCC Works | 2025-07-12 | 2025-07-12 | Casting | 100 | 100 |  | 2025-07-12 | 2025-08-06 | 2025-07-12 | 2025-08-06 | Tower A | Super Structure | L63 | RCC Super Structure | Core Wall RCC Works
40328 | Tower A - Super Structure - Finishes & MEP - L42 to L43 | Complete | Partition Wall-Blockwork | 2025-07-12 | 2025-07-18 | Staircase Area | 100 | 100 | Units | 2025-07-12 | 2025-07-26 | 2025-07-18 | 2025-08-30 | Tower A | Super Structure | L42
40331 | Tower A - Super Structure - Finishes & MEP - L43 to L44 | Complete | Partition Wall-Blockwork | 2025-07-12 | 2025-07-22 | Partition Walls | 100 | 100 | Units | 2025-07-12 | 2025-08-01 | 2025-07-22 | 2025-09-03 | Tower A | Super Structure | L43
8993 | T-15-6th Floor | Complete |  | 2025-07-18 | 2025-07-31 | 5th Floor Roof | 100 | 100 |  | 2025-07-13 | 2025-07-29 | 2025-07-26 | 2025-08-13
10053 | T-21-8th Floor | Complete | RCC | 2025-08-10 | 2025-08-11 | Slab& Beam RCC | 318 | 318 | CUM | 2025-07-13 | 2025-07-19 | 2025-07-14 | 2025-07-20
10200 |  | Not Ready |  | 2025-08-14 | 2026-07-28 | Common Area | 100 | 0 |  | 2025-07-13 |  | 2026-06-26
10655 | T-20-1st Floor Flat Area | Forced Ready | Waterproofing | 2025-08-18 | 2025-10-07 | Waterproofing | 100 | 0 |  | 2025-07-13 |  | 2025-08-31
10708 | T-20-3rd Floor Flat Area | Forced Ready | Electrical DB Fixing | 2025-08-11 | 2025-08-28 | Electrical DB Fixing | 100 | 0 |  | 2025-07-13 |  | 2025-07-31
11657 | T-18-GF Flat Area | Not Ready | Blockwork | 2025-09-04 | 2025-09-26 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-07-13 |  | 2025-08-02
11705 | T-18-1st Floor Flat Area | Not Ready | Railing | 2025-09-04 | 2025-10-08 | Balcony Railing | 100 | 0 |  | 2025-07-13 |  | 2025-08-15
8513 | T-14-GF Flat Area | Not Ready | Plastering | 2025-06-18 | 2025-07-04 | Plastering-Cement | 100 | 0 |  | 2025-07-14 |  | 2025-07-31
8991 | T-15-5th Floor | Complete | Slab& Beam Steel & Conduting | 2025-07-12 | 2025-07-16 | Slab& Beam Steel & Conduting | 13 | 13 | MT | 2025-07-14 | 2025-07-18 | 2025-07-19 | 2025-07-25
10570 | T-20-8th Floor | Complete | Conduiting | 2025-08-12 | 2025-08-16 | Conduiting works | 100 | 100 |  | 2025-07-14 | 2025-07-10 | 2025-07-19 | 2025-07-15
10661 | T-20-1st Floor Flat Area | Not Ready | Flooring & skirting | 2025-08-18 | 2025-10-01 | Flooring & skirting | 100 | 0 |  | 2025-07-14 |  | 2025-08-27
11063 | T-19-4th Floor | Complete | Shuttering | 2025-08-01 | 2025-08-06 | Slab and Beam Shuttering | 3548 | 3548 | Sqm | 2025-07-14 | 2025-08-01 | 2025-07-18 | 2025-08-05
11167 | T-19-GF Common Area | Not Ready | Railing | 2025-08-01 | 2025-08-18 | Balcony Railing | 100 | 0 |  | 2025-07-14 |  | 2025-07-28
11587 | T-18-5th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-09-05 | 2025-09-10 | AL - Shear Walls/Corewalls Steel | 20.5 | 20.5 | MT | 2025-07-14 | 2025-09-11 | 2025-07-17 | 2025-09-19
9075 | T-15-GF Common Area | Not Ready | Plumbing Pipe Line | 2025-07-14 | 2025-07-30 | Plumbing Pipe Line | 100 | 0 |  | 2025-07-15 |  | 2025-07-31
10186 | T-21-3rd Floor Flat Area | Not Ready | Plastering | 2025-08-12 | 2025-09-04 | Plastering-Cement | 100 | 0 |  | 2025-07-15 |  | 2025-08-05
10210 | T-21-4th Floor Flat Area | Not Ready | Blockwork | 2025-08-11 | 2025-09-03 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-07-15 |  | 2025-08-05
10249 | T-21-5th Floor Flat Area | Not Ready | Railing | 2025-08-11 | 2025-09-13 | Balcony Railing | 100 | 0 |  | 2025-07-15 |  | 2025-08-15
10569 | T-20-8th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-08-13 | 2025-08-18 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-07-15 | 2025-07-11 | 2025-07-17 | 2025-07-16
11661 | T-18-GF Flat Area | Not Ready | Electrical DB Fixing | 2025-09-06 | 2025-09-14 | Electrical DB Fixing | 100 | 0 |  | 2025-07-15 |  | 2025-07-23
11673 |  | Not Ready |  | 2025-08-29 | 2026-11-05 | Common Area | 100 | 0 |  | 2025-07-15 |  | 2026-09-04
9636 |  | Not Ready |  | 2025-09-13 | 2026-11-05 | Second Floor Flat Area | 100 | 0 |  | 2025-07-16 |  | 2026-09-06
9637 |  | Not Ready |  | 2025-09-13 | 2026-09-12 | Flat Area | 100 | 0 |  | 2025-07-16 |  | 2026-07-16
10054 | T-21-9th Floor | Complete |  | 2025-08-12 | 2025-08-26 | 8th Floor Roof | 100 | 100 |  | 2025-07-16 | 2025-07-25 | 2025-07-27 | 2025-08-12
10055 | T-21-9th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-08-12 | 2025-08-18 | AL - Shear Walls/Corewalls Steel | 19.5 | 19.5 | MT | 2025-07-16 | 2025-07-25 | 2025-07-18 | 2025-07-31
10626 | T-20-GF Flat Area | Not Ready | Flooring & skirting | 2025-08-18 | 2025-09-19 | Flooring & skirting | 100 | 0 |  | 2025-07-16 |  | 2025-08-17
11064 | T-19-4th Floor | Complete | Slab& Beam Steel & Conduting | 2025-08-04 | 2025-08-07 | Slab& Beam Steel & Conduting | 11.3 | 11.3 | MT | 2025-07-16 | 2025-08-06 | 2025-07-18 | 2025-08-09
11589 | T-18-5th Floor | Complete | Conduiting | 2025-09-08 | 2025-09-11 | Conduiting works | 100 | 100 | Units | 2025-07-16 | 2025-09-20 | 2025-07-18 | 2025-09-21
11652 | T-18-Basement Floor | Not Ready | Plastering | 2025-08-18 | 2025-11-27 | Plastering | 100 | 0 |  | 2025-07-16 |  | 2025-10-27
11674 | T-18-GF Common Area | Not Ready | Blockwork | 2025-09-08 | 2025-09-30 | Blockwork | 100 | 0 |  | 2025-07-16 |  | 2025-08-07
8530 | T-14-GF Common Area | Not Ready | Plastering | 2025-06-21 | 2025-07-13 | Plastering-Cement | 100 | 0 |  | 2025-07-17 |  | 2025-08-07
8622 |  | Not Ready |  | 2025-07-16 | 2026-06-14 | Fourth Floor | 100 | 0 |  | 2025-07-17 |  | 2026-06-15
8623 |  | Not Ready |  | 2025-07-16 | 2026-05-02 | Flat Area | 100 | 0 |  | 2025-07-17 |  | 2026-05-04
9062 | T-15-GF Flat Area | Not Ready | Plastering | 2025-07-14 | 2025-08-16 | Plastering-Gypsum | 100 | 0 |  | 2025-07-17 |  | 2025-08-17
10167 | T-21-2nd Floor Flat Area | Forced Ready | Flooring & skirting | 2025-08-21 | 2025-10-04 | Flooring & skirting | 100 | 0 |  | 2025-07-17 |  | 2025-08-29
10201 | T-21-3rd Floor Common Area | Not Ready | Plastering | 2025-08-14 | 2025-09-17 | Plastering-Gypsum | 100 | 0 |  | 2025-07-17 |  | 2025-08-20
10214 | T-21-4th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-08-13 | 2025-08-30 | Electrical DB Fixing | 100 | 0 |  | 2025-07-17 |  | 2025-07-31
11588 | T-18-5th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-09-09 | 2025-09-13 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-07-17 | 2025-09-13 | 2025-07-22 | 2025-09-21
39686 | Tower A - Super Structure - Core Wall Mid Rise L63-64 | Complete | Core Wall RCC Works | 2025-07-17 | 2025-07-17 | ACS Form Release & jump to next level | 100 | 100 |  | 2025-07-17 | 2025-08-07 | 2025-07-17 | 2025-08-07 | Tower A | Super Structure | L63 | RCC Super Structure | Core Wall RCC Works
44062 |  | Started |  | 2025-10-22 | 2025-12-01 | L23-28 | 100 | 40 |  | 2025-07-17 | 2025-07-17 | 2025-11-01
44063 | Tower A - Super Structure - Finishes & MEP - L23 to L28 | Started | Façade Works - MEP & Finishes | 2025-10-22 | 2025-11-01 | Al. Frame section (Mullion & Transom) Installation | 100 | 40 | Units | 2025-07-17 | 2025-07-17 | 2025-10-04 |  | Tower A | Super Structure | L23 | Façade | Façade Works
44064 | Tower A - Super Structure - Finishes & MEP - L23 to L28 | Started | Façade Works - MEP & Finishes | 2025-11-03 | 2025-11-19 | DGU Assembly Installation | 100 | 40 | Units | 2025-07-17 | 2025-07-17 | 2025-10-22 |  | Tower A | Super Structure | L23 | Façade | Façade Works
8439 | T-14-5th Floor | Complete | RCC | 2025-06-17 | 2025-06-18 | Slab& Beam RCC | 307 | 307 | CUM | 2025-07-18 | 2025-08-07 | 2025-07-19 | 2025-08-08
8454 | T-14-8th Floor | Complete |  | 2025-07-17 | 2025-07-30 | 7th Floor Roof | 100 | 100 |  | 2025-07-18 | 2025-08-29 | 2025-07-31 | 2025-10-05
10057 | T-21-9th Floor | Complete | Conduiting | 2025-08-14 | 2025-08-19 | Conduiting works | 100 | 100 |  | 2025-07-18 | 2025-08-01 | 2025-07-22 | 2025-08-04
10092 | T-21-Basement Floor | Forced Ready | Plastering | 2025-05-29 | 2025-09-05 | Plastering | 100 | 0 |  | 2025-07-18 |  | 2025-10-26
10100 | T-21-GF Flat Area | Forced Ready | Waterproofing | 2025-07-17 | 2025-08-08 | Waterproofing | 100 | 0 |  | 2025-07-18 |  | 2025-08-08
10571 | T-20-8th Floor | Complete | Shuttering | 2025-08-17 | 2025-08-21 | Slab and Beam Shuttering | 3583 | 3583 | Sqm | 2025-07-18 | 2025-07-13 | 2025-07-22 | 2025-07-19
10705 | T-20-3rd Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-08-17 | 2025-09-08 | Plumbing Pipe Line | 100 | 0 |  | 2025-07-18 |  | 2025-08-07
10754 |  | Not Ready |  | 2025-08-23 | 2026-06-04 | Fifth Floor | 100 | 0 |  | 2025-07-18 |  | 2026-04-29
10755 |  | Not Ready |  | 2025-08-23 | 2026-04-27 | Flat Area | 100 | 0 |  | 2025-07-18 |  | 2026-03-22
11222 |  | Not Ready |  | 2025-09-06 | 2026-09-21 | Third Floor | 100 | 0 |  | 2025-07-18 |  | 2026-08-01
11223 |  | Not Ready |  | 2025-09-06 | 2026-07-09 | Flat Area | 100 | 0 |  | 2025-07-18 |  | 2026-05-20
11678 | T-18-GF Common Area | Not Ready | Electrical DB Fixing | 2025-09-10 | 2025-09-17 | Electrical DB Fixing | 100 | 0 |  | 2025-07-18 |  | 2025-07-28
39687 |  | Complete |  | 2025-07-18 | 2025-08-01 | Core Wall L64-65 (Clubhouse) | 100 | 100 |  | 2025-07-18 | 2025-08-08 | 2025-08-01 | 2025-09-10
39688 | Tower A - Super Structure - Core Wall Mid Rise L64-65 | Complete | Core Wall RCC Works | 2025-07-18 | 2025-07-18 | Scaffolding & platform | 100 | 100 |  | 2025-07-18 | 2025-08-08 | 2025-07-18 | 2025-08-08 | Tower A | Super Structure | L64 | RCC Super Structure | Core Wall RCC Works
39985 | Tower A - Super Structure - Core & Outer Slab L60-61 | Complete | RCC Works - Slab | 2025-07-18 | 2025-07-24 | Outer Slab_TA | 100 | 100 |  | 2025-07-18 | 2025-08-07 | 2025-07-24 | 2025-08-14 | Tower A | Super Structure | L60 | RCC Sub Structure | RCC Works - Slab
9059 | T-15-GF Flat Area | Not Ready | Plastering | 2025-07-18 | 2025-08-04 | Plastering-Cement | 100 | 0 |  | 2025-07-19 |  | 2025-08-05
10056 | T-21-9th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-08-16 | 2025-08-21 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-07-19 | 2025-08-01 | 2025-07-25 | 2025-08-05
10059 | T-21-9th Floor | Complete | Slab& Beam Steel & Conduting | 2025-08-22 | 2025-08-25 | Slab& Beam Steel & Conduting | 19.5 | 19.5 | MT | 2025-07-19 | 2025-08-03 | 2025-07-23 | 2025-08-11
10139 | T-21-1st Floor Flat Area | Forced Ready | Toilet flooring | 2025-08-22 | 2025-09-24 | Toilet flooring | 100 | 0 |  | 2025-07-19 |  | 2025-08-22
10161 | T-21-2nd Floor Flat Area | Forced Ready | Waterproofing | 2025-08-21 | 2025-10-10 | Waterproofing | 100 | 0 |  | 2025-07-19 |  | 2025-09-06
10640 | T-20-GF Common Area | Forced Ready | Dado | 2025-08-23 | 2025-09-14 | Dado | 100 | 0 |  | 2025-07-19 |  | 2025-08-09
11065 | T-19-4th Floor | Complete | RCC | 2025-08-07 | 2025-08-08 | Slab& Beam RCC | 340 | 340 | CUM | 2025-07-19 | 2025-08-10 | 2025-07-22 | 2025-08-11
11080 | T-19-7th Floor | Complete |  | 2025-09-08 | 2025-09-20 | 6th Floor Roof | 100 | 100 |  | 2025-07-19 | 2025-09-23 | 2025-08-01 | 2025-10-10
11690 |  | Not Ready |  | 2025-09-04 | 2026-11-27 | First Floor | 100 | 0 |  | 2025-07-19 |  | 2026-09-26
11691 |  | Not Ready |  | 2025-09-04 | 2026-09-29 | Flat Area | 100 | 0 |  | 2025-07-19 |  | 2026-07-30
39689 | Tower A - Super Structure - Core Wall Mid Rise L64-65 | Complete | Core Wall RCC Works | 2025-07-19 | 2025-07-23 | Reinf & Guide shoes fixing | 100 | 100 |  | 2025-07-19 | 2025-08-09 | 2025-07-23 | 2025-08-18 | Tower A | Super Structure | L64 | RCC Super Structure | Core Wall RCC Works
8546 | T-14-1st Floor Flat Area | Not Ready | Blockwork | 2025-06-18 | 2025-07-18 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-07-20 |  | 2025-08-18
8585 | T-14-2nd Floor Flat Area | Not Ready | Railing | 2025-06-18 | 2025-07-21 | Balcony Railing | 100 | 0 |  | 2025-07-20 |  | 2025-08-22
8941 | T-15-Sub structure- Grade slab | Not Ready | Grade Slab RCC | 2025-05-22 | 2025-06-24 | Grade Slab RCC | 356 | 0 | CUM | 2025-07-20 |  | 2025-08-21
8992 | T-15-5th Floor | Complete | RCC | 2025-07-16 | 2025-07-17 | Slab& Beam RCC | 318 | 318 | CUM | 2025-07-20 | 2025-07-25 | 2025-07-20 | 2025-07-26
9495 | T-16-3rd Floor | Complete | Conduiting | 2025-07-23 | 2025-07-28 | Conduiting works | 100 | 100 |  | 2025-07-20 | 2025-07-15 | 2025-07-25 | 2025-07-24
10572 | T-20-8th Floor | Complete | Slab& Beam Steel & Conduting | 2025-08-19 | 2025-08-22 | Slab& Beam Steel & Conduting | 10.8 | 10.8 | MT | 2025-07-20 | 2025-07-20 | 2025-07-23 | 2025-07-23
10658 | T-20-1st Floor Flat Area | Not Ready | Dado | 2025-08-26 | 2025-09-22 | Dado | 100 | 0 |  | 2025-07-20 |  | 2025-08-17
10709 | T-20-3rd Floor Flat Area | Forced Ready | Plastering | 2025-08-19 | 2025-10-03 | Plastering-Gypsum | 100 | 0 |  | 2025-07-20 |  | 2025-09-03
11586 | T-18-5th Floor | Complete |  | 2025-09-05 | 2025-09-18 | 4th Floor Roof | 100 | 100 |  | 2025-07-20 | 2025-09-11 | 2025-07-31 | 2025-09-26
11590 | T-18-5th Floor | Complete | Shuttering | 2025-09-12 | 2025-09-16 | Slab and Beam Shuttering | 3527 | 3527 | Sqm | 2025-07-20 | 2025-09-16 | 2025-07-22 | 2025-09-22
11658 | T-18-GF Flat Area | Not Ready | Plumbing Pipe Line | 2025-09-12 | 2025-09-29 | Plumbing Pipe Line | 100 | 0 |  | 2025-07-20 |  | 2025-08-04
44065 | Tower A - Super Structure - Finishes & MEP - L23 to L28 | Started | Façade Works - MEP & Finishes | 2025-11-03 | 2025-11-25 | Installation of highly reflective metal sheet | 100 | 40 | Units | 2025-07-20 | 2025-07-20 | 2025-10-27 |  | Tower A | Super Structure | L23 | Façade | Façade Works
8441 | T-14-6th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-06-19 | 2025-06-23 | AL - Shear Walls/Corewalls Steel | 22 | 22 | MT | 2025-07-21 | 2025-08-10 | 2025-07-26 | 2025-08-16
8588 |  | Not Ready |  | 2025-07-19 | 2026-08-07 | Common Area | 100 | 0 |  | 2025-07-21 |  | 2026-08-08
9092 | T-15-1st Floor Flat Area | Not Ready | Blockwork | 2025-07-17 | 2025-08-18 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-07-21 |  | 2025-08-21
9131 | T-15-2nd Floor Flat Area | Not Ready | Railing | 2025-07-17 | 2025-08-20 | Balcony Railing | 100 | 0 |  | 2025-07-21 |  | 2025-08-23
9497 | T-16-3rd Floor | Complete | Slab& Beam Steel & Conduting | 2025-08-05 | 2025-08-14 | Slab& Beam Steel & Conduting | 14 | 14 | MT | 2025-07-21 | 2025-07-24 | 2025-07-26 | 2025-07-29
10624 | T-20-GF Flat Area | Not Ready | Toilet flooring | 2025-08-26 | 2025-09-11 | Toilet flooring | 100 | 0 |  | 2025-07-21 |  | 2025-08-06
11132 | T-19-Basement Floor | Forced Ready | Plastering | 2025-07-19 | 2025-10-28 | Plastering | 100 | 0 |  | 2025-07-21 |  | 2025-10-27
11188 |  | Not Ready |  | 2025-09-10 | 2026-10-30 | Common Area | 100 | 0 |  | 2025-07-21 |  | 2026-09-09
8550 | T-14-1st Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-06-20 | 2025-07-07 | Electrical DB Fixing | 100 | 0 |  | 2025-07-22 |  | 2025-08-06
8994 | T-15-6th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-07-18 | 2025-07-23 | AL - Shear Walls/Corewalls Steel | 24.5 | 24.5 | MT | 2025-07-22 | 2025-07-29 | 2025-07-25 | 2025-08-01
9076 | T-15-GF Common Area | Not Ready | Plastering | 2025-07-22 | 2025-08-12 | Plastering-Cement | 100 | 0 |  | 2025-07-22 |  | 2025-08-13
10058 | T-21-9th Floor | Complete | Shuttering | 2025-08-20 | 2025-08-24 | Slab and Beam Shuttering | 3264 | 3264 | Sqm | 2025-07-22 | 2025-08-02 | 2025-07-27 | 2025-08-07
10142 | T-21-1st Floor Flat Area | Not Ready | Putty | 2025-08-28 | 2025-11-21 | Putty | 100 | 0 |  | 2025-07-22 |  | 2025-10-13
10211 | T-21-4th Floor Flat Area | Forced Ready | Plumbing Pipe Line | 2025-08-20 | 2025-09-10 | Plumbing Pipe Line | 100 | 0 |  | 2025-07-22 |  | 2025-08-13
10581 | T-20-10th Floor | Complete |  | 2025-09-08 | 2025-09-20 | 9th Floor Roof | 100 | 100 |  | 2025-07-22 | 2025-08-17 | 2025-08-03 | 2025-09-02
10720 |  | Not Ready |  | 2025-08-27 | 2026-08-08 | Common Area | 100 | 0 |  | 2025-07-22 |  | 2026-07-04
11591 | T-18-5th Floor | Complete | Slab& Beam Steel & Conduting | 2025-09-15 | 2025-09-17 | Slab& Beam Steel & Conduting | 10.8 | 10.8 | MT | 2025-07-22 | 2025-09-17 | 2025-07-23 | 2025-09-24
8443 | T-14-6th Floor | Complete | Conduiting | 2025-06-21 | 2025-06-24 | Conduiting works | 100 | 100 |  | 2025-07-23 | 2025-08-13 | 2025-07-26 | 2025-08-19
9096 | T-15-1st Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-07-19 | 2025-08-05 | Electrical DB Fixing | 100 | 0 |  | 2025-07-23 |  | 2025-08-08
11137 | T-19-GF Flat Area | Not Ready | Blockwork | 2025-08-08 | 2025-08-30 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-07-23 |  | 2025-08-14
11185 | T-19-1st Floor Flat Area | Forced Ready | Railing | 2025-08-08 | 2025-09-10 | Balcony Railing | 100 | 0 |  | 2025-07-23 |  | 2025-08-23
11675 | T-18-GF Common Area | Not Ready | Plumbing Pipe Line | 2025-09-16 | 2025-10-03 | Plumbing Pipe Line | 100 | 0 |  | 2025-07-23 |  | 2025-08-10
44066 | Tower A - Super Structure - Finishes & MEP - L23 to L28 | Started | Façade Works - MEP & Finishes | 2025-11-03 | 2025-11-13 | Fixing of Backlit Laminated Glass assembly & ACP Panels | 100 | 40 | Units | 2025-07-23 | 2025-07-23 | 2025-09-23 |  | Tower A | Super Structure | L23 | Façade | Façade Works
8442 | T-14-6th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-06-23 | 2025-06-26 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-07-24 | 2025-08-12 | 2025-07-29 | 2025-08-19
8996 | T-15-6th Floor | Complete | Conduiting | 2025-07-21 | 2025-07-24 | Conduiting works | 100 | 100 |  | 2025-07-24 | 2025-07-31 | 2025-07-29 | 2025-08-02
10060 | T-21-9th Floor | Complete | RCC | 2025-08-25 | 2025-08-26 | Slab& Beam RCC | 318 | 318 | CUM | 2025-07-24 | 2025-08-11 | 2025-07-27 | 2025-08-12
10215 | T-21-4th Floor Flat Area | Forced Ready | Plastering | 2025-08-22 | 2025-10-06 | Plastering-Gypsum | 100 | 0 |  | 2025-07-24 |  | 2025-09-07
10260 |  | Not Committed |  | 2025-08-26 | 2026-04-20 | Sixth Floor | 100 | 0 |  | 2025-07-24 |  | 2026-03-18
10261 |  | Not Ready |  | 2025-08-26 | 2026-03-18 | Flat Area | 100 | 0 |  | 2025-07-24 |  | 2026-02-14
10573 | T-20-8th Floor | Complete | RCC | 2025-08-22 | 2025-08-23 | Slab& Beam RCC | 321 | 321 | CUM | 2025-07-24 | 2025-07-23 | 2025-07-27 | 2025-07-24
11067 | T-19-5th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-08-09 | 2025-08-13 | AL - Shear Walls/Corewalls Steel | 28.4 | 28.4 | MT | 2025-07-24 | 2025-08-13 | 2025-07-29 | 2025-08-17
11592 | T-18-5th Floor | Complete | RCC | 2025-09-18 | 2025-09-18 | Slab& Beam RCC | 330.8 | 330.8 | CUM | 2025-07-24 | 2025-09-25 | 2025-07-25 | 2025-09-26
39690 | Tower A - Super Structure - Core Wall Mid Rise L64-65 | Complete | Core Wall RCC Works | 2025-07-24 | 2025-07-26 | ACS Form Closing & Alignment | 100 | 100 |  | 2025-07-24 | 2025-08-19 | 2025-07-26 | 2025-08-19 | Tower A | Super Structure | L64 | RCC Super Structure | Core Wall RCC Works
8995 | T-15-6th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-07-22 | 2025-07-26 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-07-25 | 2025-07-30 | 2025-07-30 | 2025-08-03
10061 | T-21-10th Floor | Complete |  | 2025-08-27 | 2025-09-09 | 9th Floor Roof | 100 | 100 |  | 2025-07-25 | 2025-08-17 | 2025-08-07 | 2025-09-12
10643 | T-20-GF Common Area | Not Ready | Flooring & skirting | 2025-08-29 | 2025-10-13 | Flooring & skirting | 100 | 0 |  | 2025-07-25 |  | 2025-09-08
10706 | T-20-3rd Floor Flat Area | Forced Ready | Plastering | 2025-08-25 | 2025-09-15 | Plastering-Cement | 100 | 0 |  | 2025-07-25 |  | 2025-08-15
11141 | T-19-GF Flat Area | Not Ready | Electrical DB Fixing | 2025-08-10 | 2025-08-19 | Electrical DB Fixing | 100 | 0 |  | 2025-07-25 |  | 2025-07-31
11662 | T-18-GF Flat Area | Not Ready | Plastering | 2025-09-16 | 2025-10-19 | Plastering-Gypsum | 100 | 0 |  | 2025-07-25 |  | 2025-08-28
9142 |  | Not Ready |  | 2025-07-31 | 2026-08-16 | Third Floor | 100 | 0 |  | 2025-07-26 |  | 2026-08-10
9143 |  | Not Ready |  | 2025-07-31 | 2026-06-03 | Flat Area | 100 | 0 |  | 2025-07-26 |  | 2026-05-29
10164 | T-21-2nd Floor Flat Area | Not Ready | Dado | 2025-08-28 | 2025-09-25 | Dado | 100 | 0 |  | 2025-07-26 |  | 2025-08-22
10625 | T-20-GF Flat Area | Not Ready | Toilets False Celing | 2025-08-31 | 2025-09-16 | Toilets-False Celing | 100 | 0 |  | 2025-07-26 |  | 2025-08-10
11069 | T-19-5th Floor | Complete | Conduiting | 2025-08-11 | 2025-08-14 | Conduiting works | 100 | 100 |  | 2025-07-26 | 2025-08-17 | 2025-07-31 | 2025-08-23
11154 | T-19-GF Common Area | Not Ready | Blockwork | 2025-08-11 | 2025-09-03 | Blockwork | 100 | 0 |  | 2025-07-26 |  | 2025-08-16
11692 | T-18-1st Floor Flat Area | Not Ready | Blockwork | 2025-09-19 | 2025-10-20 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-07-26 |  | 2025-08-25
11731 | T-18-2nd Floor Flat Area | Not Ready | Railing | 2025-09-19 | 2025-10-22 | Balcony Railing | 100 | 0 |  | 2025-07-26 |  | 2025-08-29
8444 | T-14-6th Floor | Complete | Shuttering | 2025-06-26 | 2025-06-28 | Slab and Beam Shuttering | 3605 | 3605 | Sqm | 2025-07-27 | 2025-08-13 | 2025-07-28 | 2025-08-23
8506 | T-14-Basement Floor | Not Ready | Plastering | 2025-06-20 | 2025-09-27 | Plastering | 100 | 0 |  | 2025-07-27 |  | 2025-11-02
8547 | T-14-1st Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-06-26 | 2025-07-23 | Plumbing Pipe Line | 100 | 0 |  | 2025-07-27 |  | 2025-08-21
9498 | T-16-3rd Floor | Complete | RCC | 2025-08-14 | 2025-08-16 | Slab& Beam RCC | 387 | 387 | CUM | 2025-07-27 | 2025-07-29 | 2025-07-28 | 2025-07-30
10140 | T-21-1st Floor Flat Area | Not Ready | Toilets False Celing | 2025-08-30 | 2025-10-03 | Toilets False Celing | 100 | 0 |  | 2025-07-27 |  | 2025-08-27
10659 | T-20-1st Floor Flat Area | Not Ready | Toilet flooring | 2025-09-02 | 2025-10-06 | Toilet flooring | 100 | 0 |  | 2025-07-27 |  | 2025-08-29
10687 | T-20-2nd Floor Flat Area | Not Ready | Flooring & skirting | 2025-09-01 | 2025-10-16 | Flooring & skirting | 100 | 0 |  | 2025-07-27 |  | 2025-09-11
10721 | T-20-3rd Floor Common Area | Not Ready | Plastering | 2025-08-27 | 2025-09-29 | Plastering-Gypsum | 100 | 0 |  | 2025-07-27 |  | 2025-08-30
11068 | T-19-5th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-08-12 | 2025-08-18 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-07-27 | 2025-08-16 | 2025-07-30 | 2025-08-23
11594 | T-18-6th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-09-20 | 2025-09-24 | AL - Shear Walls/Corewalls Steel | 20.5 | 20.5 | MT | 2025-07-27 | 2025-09-27 | 2025-07-31 | 2025-10-04
11659 | T-18-GF Flat Area | Not Ready | Plastering | 2025-09-20 | 2025-10-07 | Plastering-Cement | 100 | 0 |  | 2025-07-27 |  | 2025-08-14
8997 | T-15-6th Floor | Complete | Shuttering | 2025-07-25 | 2025-07-29 | Slab and Beam Shuttering | 3715 | 3715 | Sqm | 2025-07-28 | 2025-08-02 | 2025-07-31 | 2025-08-04
9000 | T-15-7th Floor | Complete |  | 2025-08-01 | 2025-08-14 | 6th Floor Roof | 100 | 100 |  | 2025-07-28 | 2025-08-14 | 2025-08-09 | 2025-08-31
9093 | T-15-1st Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-07-25 | 2025-08-22 | Plumbing Pipe Line | 100 | 0 |  | 2025-07-28 |  | 2025-08-24
10226 |  | Not Ready |  | 2025-08-29 | 2026-06-25 | Common Area | 100 | 0 |  | 2025-07-28 |  | 2026-05-25
10236 | T-21-5th Floor Flat Area | Not Ready | Blockwork | 2025-08-26 | 2025-09-17 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-07-28 |  | 2025-08-19
10275 | T-21-6th Floor Flat Area | Not Ready | Railing | 2025-08-26 | 2025-09-28 | Balcony Railing | 100 | 0 |  | 2025-07-28 |  | 2025-08-31
10681 | T-20-2nd Floor Flat Area | Not Ready | Waterproofing | 2025-09-01 | 2025-10-21 | Waterproofing | 100 | 0 |  | 2025-07-28 |  | 2025-09-18
10730 | T-20-4th Floor Flat Area | Forced Ready | Blockwork | 2025-08-23 | 2025-09-14 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-07-28 |  | 2025-08-18
10769 | T-20-5th Floor Flat Area | Forced Ready | Railing | 2025-08-23 | 2025-09-25 | Balcony Railing | 100 | 0 |  | 2025-07-28 |  | 2025-08-31
11158 | T-19-GF Common Area | Not Ready | Electrical DB Fixing | 2025-08-13 | 2025-08-22 | Electrical DB Fixing | 100 | 0 |  | 2025-07-28 |  | 2025-08-04
11696 | T-18-1st Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-09-21 | 2025-10-08 | Electrical DB Fixing | 100 | 0 |  | 2025-07-28 |  | 2025-08-14
8445 | T-14-6th Floor | Complete | Slab& Beam Steel & Conduting | 2025-06-28 | 2025-07-01 | Slab& Beam Steel & Conduting | 10 | 10 | MT | 2025-07-29 | 2025-08-16 | 2025-07-31 | 2025-08-25
8551 | T-14-1st Floor Flat Area | Not Ready | Plastering | 2025-06-28 | 2025-08-17 | Plastering-Gypsum | 100 | 0 |  | 2025-07-29 |  | 2025-09-16
9590 | T-16-GF Flat Area | Not Ready | Railing | 2025-08-16 | 2025-08-31 | Balcony Railing | 100 | 0 |  | 2025-07-29 |  | 2025-08-15
10062 | T-21-10th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-08-27 | 2025-09-01 | AL - Shear Walls/Corewalls Steel | 19.5 | 19.5 | MT | 2025-07-29 | 2025-08-17 | 2025-07-31 | 2025-08-24
10212 | T-21-4th Floor Flat Area | Not Ready | Plastering | 2025-08-27 | 2025-09-18 | Plastering-Cement | 100 | 0 |  | 2025-07-29 |  | 2025-08-19
10574 | T-20-9th Floor | Complete |  | 2025-08-25 | 2025-09-06 | 8th Floor Roof | 100 | 100 |  | 2025-07-29 | 2025-07-26 | 2025-08-11 | 2025-08-15
10575 | T-20-9th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-08-25 | 2025-08-29 | AL - Shear Walls/Corewalls Steel | 20.54 | 20.54 | MT | 2025-07-29 | 2025-07-26 | 2025-08-03 | 2025-07-30
10641 | T-20-GF Common Area | Not Ready | Toilet flooring | 2025-09-03 | 2025-09-19 | Toilet flooring | 100 | 0 |  | 2025-07-29 |  | 2025-08-16
11596 | T-18-6th Floor | Complete | Conduiting | 2025-09-22 | 2025-09-25 | Conduiting works | 100 | 100 |  | 2025-07-29 | 2025-10-07 | 2025-07-30 | 2025-10-08
8998 | T-15-6th Floor | Complete | Slab& Beam Steel & Conduting | 2025-07-27 | 2025-07-30 | Slab& Beam Steel & Conduting | 13 | 13 | MT | 2025-07-30 | 2025-08-05 | 2025-08-04 | 2025-08-12
9097 | T-15-1st Floor Flat Area | Not Ready | Plastering | 2025-07-27 | 2025-09-15 | Plastering-Gypsum | 100 | 0 |  | 2025-07-30 |  | 2025-09-18
9108 |  | Not Ready |  | 2025-08-04 | 2026-09-23 | Common Area | 100 | 0 |  | 2025-07-30 |  | 2026-09-18
9500 | T-16-4th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-08-17 | 2025-08-21 | AL - Shear Walls/Corewalls Steel | 25 | 25 | MT | 2025-07-30 | 2025-08-01 | 2025-08-02 | 2025-08-04
10117 | T-21-GF Common Area | Not Ready | Waterproofing | 2025-07-25 | 2025-08-18 | Waterproofing | 100 | 0 |  | 2025-07-30 |  | 2025-08-20
10240 | T-21-5th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-08-28 | 2025-09-13 | Electrical DB Fixing | 100 | 0 |  | 2025-07-30 |  | 2025-08-14
10734 | T-20-4th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-08-26 | 2025-09-11 | Electrical DB Fixing | 100 | 0 |  | 2025-07-30 |  | 2025-08-17
11070 | T-19-5th Floor | Complete | Shuttering | 2025-08-16 | 2025-08-21 | Slab and Beam Shuttering | 3548 | 3548 | Sqm | 2025-07-30 | 2025-08-18 | 2025-08-03 | 2025-08-25
11138 | T-19-GF Flat Area | Not Ready | Plumbing Pipe Line | 2025-08-16 | 2025-09-02 | Plumbing Pipe Line | 100 | 0 |  | 2025-07-30 |  | 2025-08-13
11595 | T-18-6th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-09-23 | 2025-09-27 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-07-30 | 2025-10-02 | 2025-08-05 | 2025-10-08
11676 | T-18-GF Common Area | Not Ready | Plastering | 2025-09-23 | 2025-10-16 | Plastering-Cement | 100 | 0 |  | 2025-07-30 |  | 2025-08-22
9662 |  | Not Ready |  | 2025-09-27 | 2026-10-13 | Third Floor | 100 | 0 |  | 2025-07-31 |  | 2026-08-14
9663 |  | Not Ready |  | 2025-09-27 | 2026-07-30 | Flat Area | 100 | 0 |  | 2025-07-31 |  | 2026-06-02
10064 | T-21-10th Floor | Complete | Conduiting | 2025-08-29 | 2025-09-02 | Conduiting works | 100 | 100 | Units | 2025-07-31 | 2025-08-19 | 2025-08-04 | 2025-08-25
10119 | T-21-GF Common Area | Not Ready | Plastering | 2025-07-25 | 2025-08-28 | Plastering-Gypsum | 100 | 0 |  | 2025-07-31 |  | 2025-08-31
10227 | T-21-4th Floor Common Area | Not Ready | Plastering | 2025-08-29 | 2025-10-01 | Plastering-Gypsum | 100 | 0 |  | 2025-07-31 |  | 2025-09-03
10577 | T-20-9th Floor | Complete | Conduiting | 2025-08-27 | 2025-08-30 | Conduiting works | 100 | 100 | Units | 2025-07-31 | 2025-07-30 | 2025-08-05 | 2025-08-03
11716 |  | Not Ready |  | 2025-09-19 | 2026-11-11 | Second Floor Flat Area | 100 | 0 |  | 2025-07-31 |  | 2026-09-09
11717 |  | Not Committed |  | 2025-09-19 | 2026-09-18 | Flat Area | 100 | 0 |  | 2025-07-31 |  | 2026-07-19
39691 | Tower A - Super Structure - Core Wall Mid Rise L64-65 | Complete | Core Wall RCC Works | 2025-07-31 | 2025-07-31 | Casting | 100 | 100 |  | 2025-07-31 | 2025-08-20 | 2025-07-31 | 2025-08-20 | Tower A | Super Structure | L64 | RCC Super Structure | Core Wall RCC Works
39986 |  | Complete |  | 2025-07-31 | 2025-08-08 | L61-62 | 100 | 100 |  | 2025-07-31 | 2025-08-24 | 2025-08-08 | 2025-08-27
39986 |  | Complete |  | 2025-07-31 | 2025-08-08 | L61-62 | 100 | 100 |  | 2025-07-31 | 2025-08-24 | 2025-08-08 | 2025-08-27 |  |  |  | Finishes | Gypsum Plastering Works
39987 | Tower A - Super Structure - Core & Outer Slab L61-62 | Complete | RCC Works - Vertical | 2025-07-31 | 2025-08-07 | Outer Columns_TA | 100 | 100 |  | 2025-07-31 | 2025-08-24 | 2025-08-07 | 2025-08-24 | Tower A | Super Structure | L61 | RCC Sub Structure | RCC Works - Vertical
40332 | Tower A - Super Structure - Finishes & MEP - L43 to L44 | Complete | Partition Wall-Blockwork | 2025-07-31 | 2025-08-06 | Staircase Area | 100 | 100 | Units | 2025-07-31 | 2025-08-02 | 2025-08-06 | 2025-09-03 | Tower A | Super Structure | L43
40335 | Tower A - Super Structure - Finishes & MEP - L44 to L45 | Complete | Partition Wall-Blockwork | 2025-07-31 | 2025-08-08 | Partition Walls | 100 | 100 | Units | 2025-07-31 | 2025-08-08 | 2025-08-08 | 2025-09-10 | Tower A | Super Structure | L44
8446 | T-14-6th Floor | Complete | RCC | 2025-07-01 | 2025-07-02 | Slab& Beam RCC | 307 | 307 | CUM | 2025-08-01 | 2025-08-25 | 2025-08-02 | 2025-08-26
8514 | T-14-GF Flat Area | Not Ready | Waterproofing | 2025-07-04 | 2025-07-26 | Waterproofing | 100 | 0 |  | 2025-08-01 |  | 2025-08-21
8648 |  | Not Ready |  | 2025-07-30 | 2026-05-12 | Fifth Floor | 100 | 0 |  | 2025-08-01 |  | 2026-05-13
8649 |  | Not Ready |  | 2025-07-30 | 2026-04-04 | Flat Area | 100 | 0 |  | 2025-08-01 |  | 2026-04-05
9502 | T-16-4th Floor | Complete | Conduiting | 2025-08-19 | 2025-08-22 | Conduiting works | 100 | 100 |  | 2025-08-01 | 2025-08-03 | 2025-08-03 | 2025-08-05
9520 | T-16-7th Floor | Complete |  | 2025-09-29 | 2025-10-13 | 6th Floor Roof | 100 | 100 |  | 2025-08-01 | 2025-09-29 | 2025-08-14 | 2025-10-27
10063 | T-21-10th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-08-30 | 2025-09-04 | Shear Walls/Corewalls Shuttering | 100 | 100 | Units | 2025-08-01 | 2025-08-19 | 2025-08-04 | 2025-08-26
10576 | T-20-9th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-08-28 | 2025-09-01 | Shear Walls/Corewalls Shuttering | 100 | 100 | Units | 2025-08-01 | 2025-07-31 | 2025-08-05 | 2025-08-04
11071 | T-19-5th Floor | Complete | Slab& Beam Steel & Conduting | 2025-08-19 | 2025-08-22 | Slab& Beam Steel & Conduting | 11.3 | 11.3 | MT | 2025-08-01 | 2025-08-25 | 2025-08-03 | 2025-08-29
11248 |  | Not Ready |  | 2025-09-20 | 2026-08-19 | Fourth Floor | 100 | 0 |  | 2025-08-01 |  | 2026-06-30
11249 |  | Not Ready |  | 2025-09-20 | 2026-07-07 | Flat Area | 100 | 0 |  | 2025-08-01 |  | 2026-05-18
11541 | T-18-Sub structure- Grade slab | Forced Ready | Grade Slab RCC | 2025-06-30 | 2025-08-01 | Grade Slab RCC | 356 | 0 | CUM | 2025-08-01 |  | 2025-09-04
11593 | T-18-6th Floor | Complete |  | 2025-09-20 | 2025-10-04 | 5th Floor Roof | 100 | 100 |  | 2025-08-01 | 2025-09-27 | 2025-08-12 | 2025-10-20
39692 | Tower A - Super Structure - Core Wall Mid Rise L64-65 | Complete | Core Wall RCC Works | 2025-08-01 | 2025-08-01 | ACS Form Release & jump to next level | 100 | 100 |  | 2025-08-01 | 2025-09-10 | 2025-08-01 | 2025-09-10 | Tower A | Super Structure | L64 | RCC Super Structure | Core Wall RCC Works
41395 |  | Started |  | 2025-05-15 | 2026-04-10 | L28-29 | 100 | 48 |  | 2025-08-01 | 2025-08-01 | 2026-04-30 |  |  |  |  | Finishes | Gypsum Plastering Works
41395 |  | Started |  | 2025-05-15 | 2026-04-10 | L28-29 | 100 | 48 |  | 2025-08-01 | 2025-08-01 | 2026-04-30
41396 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2025-08-01 | 2025-08-05 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 65 |  | 2025-08-01 | 2025-08-01 | 2026-03-20 |  | Tower A | Super Structure | L28 | MEP | FPS 1st Fix - MEP & Finishes
8461 | T-14-9th Floor | Complete |  | 2025-07-31 | 2025-08-14 | 8th Floor Roof | 100 | 100 |  | 2025-08-02 | 2025-10-06 | 2025-08-16 | 2025-10-29
9501 | T-16-4th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-08-20 | 2025-08-25 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-08-02 | 2025-08-03 | 2025-08-08 | 2025-08-06
10103 | T-21-GF Flat Area | Not Ready | Dado | 2025-08-02 | 2025-08-25 | Dado | 100 | 0 |  | 2025-08-02 |  | 2025-08-24
10165 | T-21-2nd Floor Flat Area | Not Ready | Toilet flooring | 2025-09-05 | 2025-10-09 | Toilet flooring | 100 | 0 |  | 2025-08-02 |  | 2025-09-05
10780 |  | Not Ready |  | 2025-09-06 | 2026-05-02 | Sixth Floor | 100 | 0 |  | 2025-08-02 |  | 2026-03-27
10781 |  | Not Ready |  | 2025-09-06 | 2026-03-31 | Flat Area | 100 | 0 |  | 2025-08-02 |  | 2026-02-23
11087 | T-19-8th Floor | Complete |  | 2025-09-22 | 2025-10-06 | 7th Floor Roof | 100 | 100 |  | 2025-08-02 | 2025-10-11 | 2025-08-16 | 2025-11-02
11142 | T-19-GF Flat Area | Not Ready | Plastering | 2025-08-20 | 2025-09-22 | Plastering-Gypsum | 100 | 0 |  | 2025-08-02 |  | 2025-09-05
11155 | T-19-GF Common Area | Not Ready | Plumbing Pipe Line | 2025-08-20 | 2025-09-05 | Plumbing Pipe Line | 100 | 0 |  | 2025-08-02 |  | 2025-08-18
11597 | T-18-6th Floor | Complete | Shuttering | 2025-09-26 | 2025-09-30 | Slab and Beam Shuttering | 3527 | 3527 | Sqm | 2025-08-02 | 2025-10-06 | 2025-08-06 | 2025-10-13
11693 | T-18-1st Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-09-26 | 2025-10-24 | Plumbing Pipe Line | 100 | 0 |  | 2025-08-02 |  | 2025-09-02
39693 |  | Complete |  | 2025-08-02 | 2025-08-13 | Core Wall L65-66 (Clubhouse) | 100 | 100 |  | 2025-08-02 | 2025-08-16 | 2025-08-13 | 2025-09-01
39694 | Tower A - Super Structure - Core Wall Mid Rise L65-66 | Complete | Core Wall RCC Works | 2025-08-02 | 2025-08-02 | Scaffolding & platform | 100 | 100 |  | 2025-08-02 | 2025-08-16 | 2025-08-02 | 2025-08-16 | Tower A | Super Structure | L65 | RCC Super Structure | Core Wall RCC Works
39988 | Tower A - Super Structure - Core & Outer Slab L61-62 | Complete | RCC Works - Slab | 2025-08-02 | 2025-08-08 | Outer Slab_TA | 100 | 100 |  | 2025-08-02 | 2025-08-27 | 2025-08-08 | 2025-08-27 | Tower A | Super Structure | L61 | RCC Sub Structure | RCC Works - Slab
8548 | T-14-1st Floor Flat Area | Not Ready | Plastering | 2025-07-03 | 2025-07-25 | Plastering-Cement | 100 | 0 |  | 2025-08-03 |  | 2025-08-24
8572 | T-14-2nd Floor Flat Area | Not Ready | Blockwork | 2025-07-02 | 2025-07-24 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-08-03 |  | 2025-08-25
8611 | T-14-3rd Floor Flat Area | Not Ready | Railing | 2025-07-02 | 2025-08-04 | Balcony Railing | 100 | 0 |  | 2025-08-03 |  | 2025-09-05
9628 |  | Not Ready |  | 2025-10-01 | 2026-11-22 | Common Area | 100 | 0 |  | 2025-08-03 |  | 2026-09-22
10642 | T-20-GF Common Area | Not Ready | Toilets False Celing | 2025-09-09 | 2025-09-25 | Toilets False Celing | 100 | 0 |  | 2025-08-03 |  | 2025-08-22
10662 | T-20-1st Floor Flat Area | Not Ready | Putty | 2025-09-09 | 2025-12-03 | Putty | 100 | 0 |  | 2025-08-03 |  | 2025-10-26
8448 | T-14-7th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-07-03 | 2025-07-08 | AL - Shear Walls/Corewalls Steel | 22 | 22 | MT | 2025-08-04 | 2025-08-29 | 2025-08-09 | 2025-09-03
8614 |  | Not Ready |  | 2025-08-02 | 2026-07-17 | Common Area | 100 | 0 |  | 2025-08-04 |  | 2026-07-18
9094 | T-15-1st Floor Flat Area | Not Ready | Plastering | 2025-08-01 | 2025-08-24 | Plastering-Cement | 100 | 0 |  | 2025-08-04 |  | 2025-08-26
9572 | T-16-Basement Floor | Not Ready | Plastering | 2025-08-09 | 2025-11-20 | Plastering | 100 | 0 |  | 2025-08-04 |  | 2025-11-12
10065 | T-21-10th Floor | Complete | Shuttering | 2025-09-03 | 2025-09-07 | Slab and Beam Shuttering | 3264 | 3264 | Sqm | 2025-08-04 | 2025-08-21 | 2025-08-08 | 2025-09-08
10193 | T-21-3rd Floor Flat Area | Not Ready | Flooring & skirting | 2025-09-04 | 2025-10-18 | Flooring & skirting | 100 | 0 |  | 2025-08-04 |  | 2025-09-16
10237 | T-21-5th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-09-03 | 2025-09-25 | Plumbing Pipe Line | 100 | 0 |  | 2025-08-04 |  | 2025-08-25
10578 | T-20-9th Floor | Complete | Shuttering | 2025-08-31 | 2025-09-04 | Slab and Beam Shuttering | 3583 | 3583 | Sqm | 2025-08-04 | 2025-08-02 | 2025-08-06 | 2025-08-05
10660 | T-20-1st Floor Flat Area | Not Ready | Toilets False Celing | 2025-09-11 | 2025-10-15 | Toilets False Celing | 100 | 0 |  | 2025-08-04 |  | 2025-09-07
10684 | T-20-2nd Floor Flat Area | Not Ready | Dado | 2025-09-09 | 2025-10-07 | Dado | 100 | 0 |  | 2025-08-04 |  | 2025-09-01
10731 | T-20-4th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-08-31 | 2025-09-22 | Plumbing Pipe Line | 100 | 0 |  | 2025-08-04 |  | 2025-08-25
11072 | T-19-5th Floor | Complete | RCC | 2025-08-22 | 2025-08-23 | Slab& Beam RCC | 340 | 340 | CUM | 2025-08-04 | 2025-08-29 | 2025-08-05 | 2025-08-30
11214 |  | Not Ready |  | 2025-09-24 | 2026-10-14 | Common Area | 100 | 0 |  | 2025-08-04 |  | 2026-08-24
11598 | T-18-6th Floor | Complete | Slab& Beam Steel & Conduting | 2025-09-29 | 2025-10-03 | Slab& Beam Steel & Conduting | 10.8 | 10.8 | MT | 2025-08-04 | 2025-10-12 | 2025-08-04 | 2025-10-18
11697 | T-18-1st Floor Flat Area | Not Ready | Plastering | 2025-09-29 | 2025-11-20 | Plastering-Gypsum | 100 | 0 |  | 2025-08-04 |  | 2025-09-22
8563 | T-14-1st Floor Common Area | Not Ready | Plastering | 2025-07-05 | 2025-08-07 | Plastering-Gypsum | 100 | 0 |  | 2025-08-05 |  | 2025-09-08
8576 | T-14-2nd Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-07-04 | 2025-07-21 | Electrical DB Fixing | 100 | 0 |  | 2025-08-05 |  | 2025-08-22
8999 | T-15-6th Floor | Complete | RCC | 2025-07-30 | 2025-07-31 | Slab& Beam RCC | 318 | 318 | CUM | 2025-08-05 | 2025-08-12 | 2025-08-05 | 2025-08-13
9503 | T-16-4th Floor | Complete | Shuttering | 2025-08-23 | 2025-08-28 | Slab and Beam Shuttering | 4183 | 4183 | Sqm | 2025-08-05 | 2025-08-05 | 2025-08-07 | 2025-08-12
9607 | T-16-GF Common Area | Not Ready | Railing | 2025-08-23 | 2025-09-08 | Balcony Railing | 100 | 0 |  | 2025-08-05 |  | 2025-08-20
10746 |  | Not Ready |  | 2025-09-10 | 2026-07-07 | Common Area | 100 | 0 |  | 2025-08-05 |  | 2026-06-02
11599 | T-18-6th Floor | Complete | RCC | 2025-10-03 | 2025-10-04 | Slab& Beam RCC | 330.8 | 330.8 | CUM | 2025-08-05 | 2025-10-19 | 2025-08-06 | 2025-10-20
8450 | T-14-7th Floor | Complete | Conduiting | 2025-07-05 | 2025-07-09 | Conduiting works | 100 | 100 |  | 2025-08-06 | 2025-09-02 | 2025-08-09 | 2025-09-05
9060 | T-15-GF Flat Area | Not Ready | Waterproofing | 2025-08-04 | 2025-08-26 | Waterproofing | 100 | 0 |  | 2025-08-06 |  | 2025-08-28
9109 | T-15-1st Floor Common Area | Not Ready | Plastering | 2025-08-04 | 2025-09-06 | Plastering-Gypsum | 100 | 0 |  | 2025-08-06 |  | 2025-09-06
9118 | T-15-2nd Floor Flat Area | Not Ready | Blockwork | 2025-07-31 | 2025-08-23 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-08-06 |  | 2025-08-27
9157 | T-15-3rd Floor Flat Area | Not Ready | Railing | 2025-07-31 | 2025-09-03 | Balcony Railing | 100 | 0 |  | 2025-08-06 |  | 2025-09-09
10066 | T-21-10th Floor | Complete | Slab& Beam Steel & Conduting | 2025-09-05 | 2025-09-08 | Slab& Beam Steel & Conduting | 19.5 | 19.5 | MT | 2025-08-06 | 2025-08-30 | 2025-08-08 | 2025-09-11
10187 | T-21-3rd Floor Flat Area | Not Ready | Waterproofing | 2025-09-04 | 2025-10-24 | Waterproofing | 100 | 0 |  | 2025-08-06 |  | 2025-09-23
10241 | T-21-5th Floor Flat Area | Not Ready | Plastering | 2025-09-05 | 2025-10-20 | Plastering-Gypsum | 100 | 0 |  | 2025-08-06 |  | 2025-09-19
10579 | T-20-9th Floor | Complete | Slab& Beam Steel & Conduting | 2025-09-02 | 2025-09-05 | Slab& Beam Steel & Conduting | 10.8 | 10.8 | MT | 2025-08-06 | 2025-08-06 | 2025-08-10 | 2025-08-14
10735 | T-20-4th Floor Flat Area | Not Ready | Plastering | 2025-09-02 | 2025-10-17 | Plastering-Gypsum | 100 | 0 |  | 2025-08-06 |  | 2025-09-19
11139 | T-19-GF Flat Area | Not Ready | Plastering | 2025-08-24 | 2025-09-09 | Plastering-Cement | 100 | 0 |  | 2025-08-06 |  | 2025-08-21
11172 | T-19-1st Floor Flat Area | Not Ready | Blockwork | 2025-08-23 | 2025-09-23 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-08-06 |  | 2025-09-04
11211 | T-19-2nd Floor Flat Area | Not Ready | Railing | 2025-08-23 | 2025-09-25 | Balcony Railing | 100 | 0 |  | 2025-08-06 |  | 2025-09-06
8449 | T-14-7th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-07-07 | 2025-07-11 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-08-07 | 2025-09-01 | 2025-08-10 | 2025-09-06
9001 | T-15-7th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-08-01 | 2025-08-06 | AL - Shear Walls/Corewalls Steel | 24.5 | 24.5 | MT | 2025-08-07 | 2025-08-14 | 2025-08-12 | 2025-08-21
9504 | T-16-4th Floor | Complete | Slab& Beam Steel & Conduting | 2025-08-26 | 2025-08-29 | Slab& Beam Steel & Conduting | 14 | 14 | MT | 2025-08-07 | 2025-08-13 | 2025-08-08 | 2025-08-17
10286 |  | Not Ready |  | 2025-09-10 | 2026-05-13 | Seventh Floor | 100 | 0 |  | 2025-08-07 |  | 2026-04-09
10287 |  | Not Ready |  | 2025-09-10 | 2026-04-16 | Flat Area | 100 | 0 |  | 2025-08-07 |  | 2026-03-13
11074 | T-19-6th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-08-24 | 2025-08-28 | AL - Shear Walls/Corewalls Steel | 28.4 | 28.4 | MT | 2025-08-07 | 2025-09-01 | 2025-08-10 | 2025-09-09
11718 | T-18-2nd Floor Flat Area | Not Ready | Blockwork | 2025-10-04 | 2025-10-25 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-08-07 |  | 2025-09-01
11757 | T-18-3rd Floor Flat Area | Not Ready | Railing | 2025-10-04 | 2025-11-08 | Balcony Railing | 100 | 0 |  | 2025-08-07 |  | 2025-09-10
39695 | Tower A - Super Structure - Core Wall Mid Rise L65-66 | Complete | Core Wall RCC Works | 2025-08-07 | 2025-08-09 | Reinf & Guide shoes fixing | 100 | 100 |  | 2025-08-07 | 2025-08-27 | 2025-08-09 | 2025-08-27 | Tower A | Super Structure | L65 | RCC Super Structure | Core Wall RCC Works
8531 | T-14-GF Common Area | Not Ready | Waterproofing | 2025-07-13 | 2025-08-04 | Waterproofing | 100 | 0 |  | 2025-08-08 |  | 2025-08-30
9122 | T-15-2nd Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-08-02 | 2025-08-20 | Electrical DB Fixing | 100 | 0 |  | 2025-08-08 |  | 2025-08-24
10068 | T-21-11th Floor | Complete |  | 2025-09-11 | 2025-09-24 | 10th Floor Roof | 100 | 100 |  | 2025-08-08 | 2025-09-13 | 2025-08-22 | 2025-11-30
11176 | T-19-1st Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-08-25 | 2025-09-10 | Electrical DB Fixing | 100 | 0 |  | 2025-08-08 |  | 2025-08-23
11601 | T-18-7th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-10-05 | 2025-10-09 | AL - Shear Walls/Corewalls Steel | 20.5 | 20.5 | MT | 2025-08-08 | 2025-10-21 | 2025-08-11 | 2025-10-28
39696 | Tower A - Super Structure - Core Wall Mid Rise L65-66 | Complete | Core Wall RCC Works | 2025-08-08 | 2025-08-11 | ACS Form Closing & Alignment | 100 | 100 |  | 2025-08-08 | 2025-08-28 | 2025-08-11 | 2025-08-28 | Tower A | Super Structure | L65 | RCC Super Structure | Core Wall RCC Works
44067 | Tower A - Super Structure - Finishes & MEP - L23 to L28 | Started | Façade Works - MEP & Finishes | 2025-11-03 | 2025-11-13 | Fixing of Louvers | 100 | 40 | Units | 2025-08-08 | 2025-08-08 | 2025-10-15 |  | Tower A | Super Structure | L23 | Façade | Façade Works
44067 | Tower A - Super Structure - Finishes & MEP - L23 to L28 | Started | Façade Works - MEP & Finishes | 2025-11-03 | 2025-11-13 | Fixing of Louvers | 100 | 40 | Units | 2025-08-08 | 2025-08-08 | 2025-10-15 |  | Tower A | Super Structure | L23
8533 | T-14-GF Common Area | Not Ready | Plastering | 2025-07-13 | 2025-08-16 | Plastering-Gypsum | 100 | 0 |  | 2025-08-09 |  | 2025-09-12
9003 | T-15-7th Floor | Complete | Conduiting | 2025-08-04 | 2025-08-07 | Conduiting works | 100 | 100 |  | 2025-08-09 | 2025-08-16 | 2025-08-11 | 2025-08-22
9168 |  | Not Ready |  | 2025-08-14 | 2026-07-13 | Fourth Floor | 100 | 0 |  | 2025-08-09 |  | 2026-07-08
9169 |  | Not Ready |  | 2025-08-14 | 2026-06-01 | Flat Area | 100 | 0 |  | 2025-08-09 |  | 2026-05-27
9505 | T-16-4th Floor | Complete | RCC | 2025-08-29 | 2025-08-30 | Slab& Beam RCC | 387 | 387 | CUM | 2025-08-09 | 2025-08-17 | 2025-08-10 | 2025-08-18
9981 | T-21-Sub structure- Grade slab | Forced Ready | Grade Slab RCC | 2025-05-10 | 2025-06-12 | Grade Slab RCC | 356 | 0 | CUM | 2025-08-09 |  | 2025-09-11
10067 | T-21-10th Floor | Complete | RCC | 2025-09-09 | 2025-09-09 | Slab& Beam RCC | 318 | 318 | CUM | 2025-08-09 | 2025-09-11 | 2025-08-10 | 2025-09-12
11076 | T-19-6th Floor | Complete | Conduiting | 2025-08-26 | 2025-08-29 | Conduiting works | 100 | 100 |  | 2025-08-09 | 2025-09-05 | 2025-08-14 | 2025-09-11
11156 | T-19-GF Common Area | Not Ready | Plastering | 2025-08-27 | 2025-09-18 | Plastering-Cement | 100 | 0 |  | 2025-08-09 |  | 2025-08-31
11694 | T-18-1st Floor Flat Area | Not Ready | Plastering | 2025-10-05 | 2025-10-27 | Plastering-Cement | 100 | 0 |  | 2025-08-09 |  | 2025-08-29
11722 | T-18-2nd Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-10-06 | 2025-10-22 | Electrical DB Fixing | 100 | 0 |  | 2025-08-09 |  | 2025-08-25
8451 | T-14-7th Floor | Complete | Shuttering | 2025-07-10 | 2025-07-13 | Slab and Beam Shuttering | 3605 | 3605 | Sqm | 2025-08-10 | 2025-09-04 | 2025-08-13 | 2025-09-09
8573 | T-14-2nd Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-07-10 | 2025-07-31 | Plumbing Pipe Line | 100 | 0 |  | 2025-08-10 |  | 2025-08-31
9002 | T-15-7th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-08-05 | 2025-08-09 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-08-10 | 2025-08-16 | 2025-08-12 | 2025-08-23
10106 | T-21-GF Flat Area | Forced Ready | Flooring & skirting | 2025-08-06 | 2025-09-08 | Flooring & skirting | 100 | 0 |  | 2025-08-10 |  | 2025-09-12
10166 | T-21-2nd Floor Flat Area | Not Ready |  | 2025-09-14 | 2025-10-17 | Toilets False Celing | 100 | 0 |  | 2025-08-10 |  | 2025-09-13
11075 | T-19-6th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-08-27 | 2025-09-01 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-08-10 | 2025-09-04 | 2025-08-15 | 2025-09-11
11603 | T-18-7th Floor | Complete | Conduiting | 2025-10-07 | 2025-10-10 | Conduiting works | 100 | 100 |  | 2025-08-10 | 2025-10-31 | 2025-08-10 | 2025-11-01
44068 | Tower A - Super Structure - Finishes & MEP - L23 to L28 | Started | Façade Works - MEP & Finishes | 2025-11-20 | 2025-12-01 | Accessories & Alignment | 100 | 40 | Units | 2025-08-10 | 2025-08-10 | 2025-11-01 |  | Tower A | Super Structure | L23 | Façade | Façade Works
44068 | Tower A - Super Structure - Finishes & MEP - L23 to L28 | Started | Façade Works - MEP & Finishes | 2025-11-20 | 2025-12-01 | Accessories & Alignment | 100 | 40 | Units | 2025-08-10 | 2025-08-10 | 2025-11-01 |  | Tower A | Super Structure | L23
9007 | T-15-8th Floor | Complete |  | 2025-08-16 | 2025-08-29 | 7th Floor Roof | 100 | 100 |  | 2025-08-11 | 2025-09-03 | 2025-08-25 | 2025-09-19
9577 | T-16-GF Flat Area | Not Ready | Blockwork | 2025-08-30 | 2025-09-21 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-08-11 |  | 2025-09-02
9625 | T-16-1st Floor Flat Area | Not Ready | Railing | 2025-08-30 | 2025-10-03 | Balcony Railing | 100 | 0 |  | 2025-08-11 |  | 2025-09-13
10238 | T-21-5th Floor Flat Area | Not Ready | Plastering | 2025-09-11 | 2025-10-03 | Plastering-Cement | 100 | 0 |  | 2025-08-11 |  | 2025-09-01
10252 |  | Not Ready |  | 2025-09-13 | 2026-05-23 | Common Area | 100 | 0 |  | 2025-08-11 |  | 2026-04-21
10262 | T-21-6th Floor Flat Area | Not Ready | Blockwork | 2025-09-10 | 2025-10-01 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-08-11 |  | 2025-09-02
10301 | T-21-7th Floor Flat Area | Not Ready | Railing | 2025-09-10 | 2025-10-13 | Balcony Railing | 100 | 0 |  | 2025-08-11 |  | 2025-09-12
10580 | T-20-9th Floor | Complete | RCC | 2025-09-05 | 2025-09-06 | Slab& Beam RCC | 321 | 321 | CUM | 2025-08-11 | 2025-08-14 | 2025-08-11 | 2025-08-15
10685 | T-20-2nd Floor Flat Area | Not Ready | Toilet flooring | 2025-09-17 | 2025-10-20 | Toilet flooring | 100 | 0 |  | 2025-08-11 |  | 2025-09-14
10732 | T-20-4th Floor Flat Area | Not Ready | Plastering | 2025-09-08 | 2025-09-30 | Plastering-Cement | 100 | 0 |  | 2025-08-11 |  | 2025-09-02
11602 | T-18-7th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-10-08 | 2025-10-13 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-08-11 | 2025-10-26 | 2025-08-16 | 2025-10-31
11709 | T-18-1st Floor Common Area | Not Ready | Plastering | 2025-10-07 | 2025-11-11 | Plastering-Gypsum | 100 | 0 |  | 2025-08-11 |  | 2025-09-14
41411 |  | Started |  | 2025-05-19 | 2026-04-13 | L29-30 | 100 | 46 |  | 2025-08-11 | 2025-08-11 | 2026-05-04 |  |  |  |  | Finishes | Gypsum Plastering Works
41411 |  | Started |  | 2025-05-19 | 2026-04-13 | L29-30 | 100 | 46 |  | 2025-08-11 | 2025-08-11 | 2026-05-04
41412 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2025-08-11 | 2025-08-13 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 65 |  | 2025-08-11 | 2025-08-11 | 2026-03-23 |  | Tower A | Super Structure | L29 | MEP | FPS 1st Fix - MEP & Finishes
8452 | T-14-7th Floor | Complete | Slab& Beam Steel & Conduting | 2025-07-12 | 2025-07-15 | Slab& Beam Steel & Conduting | 10 | 10 | MT | 2025-08-12 | 2025-09-06 | 2025-08-14 | 2025-09-12
8577 | T-14-2nd Floor Flat Area | Not Ready | Plastering | 2025-07-12 | 2025-08-26 | Plastering-Gypsum | 100 | 0 |  | 2025-08-12 |  | 2025-09-25
9507 | T-16-5th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-09-01 | 2025-09-04 | AL - Shear Walls/Corewalls Steel | 25 | 25 | MT | 2025-08-12 | 2025-08-25 | 2025-08-17 | 2025-08-28
10069 | T-21-11th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-09-11 | 2025-09-15 | AL - Shear Walls/Corewalls Steel | 19.5 | 19.5 | MT | 2025-08-12 | 2025-09-13 | 2025-08-15 | 2025-09-30
10104 | T-21-GF Flat Area | Not Ready | Toilet flooring | 2025-08-13 | 2025-08-30 | Toilet flooring | 100 | 0 |  | 2025-08-12 |  | 2025-08-26
10756 | T-20-5th Floor Flat Area | Not Ready | Blockwork | 2025-09-06 | 2025-09-29 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-08-12 |  | 2025-09-02
10795 | T-20-6th Floor Flat Area | Not Ready | Railing | 2025-09-06 | 2025-10-10 | Balcony Railing | 100 | 0 |  | 2025-08-12 |  | 2025-09-14
11742 |  | Not Committed |  | 2025-10-04 | 2026-10-19 | Third Floor | 100 | 0 |  | 2025-08-12 |  | 2026-08-19
11743 |  | Not Committed |  | 2025-10-04 | 2026-08-04 | Flat Area | 100 | 0 |  | 2025-08-12 |  | 2026-06-05
39697 | Tower A - Super Structure - Core Wall Mid Rise L65-66 | Complete | Core Wall RCC Works | 2025-08-12 | 2025-08-12 | Casting | 100 | 100 |  | 2025-08-12 | 2025-08-29 | 2025-08-12 | 2025-08-29 | Tower A | Super Structure | L65 | RCC Super Structure | Core Wall RCC Works
39989 |  | Complete |  | 2025-08-12 | 2025-08-29 | L62-63 | 100 | 100 |  | 2025-08-12 | 2025-09-04 | 2025-08-29 | 2025-09-07
39989 |  | Complete |  | 2025-08-12 | 2025-08-29 | L62-63 | 100 | 100 |  | 2025-08-12 | 2025-09-04 | 2025-08-29 | 2025-09-07 |  |  |  | Finishes | Gypsum Plastering Works
39990 | Tower A - Super Structure - Core & Outer Slab L62-63 | Complete | RCC Works - Vertical | 2025-08-12 | 2025-08-23 | Outer Columns_TA | 100 | 100 |  | 2025-08-12 | 2025-09-04 | 2025-08-23 | 2025-09-04 | Tower A | Super Structure | L62 | RCC Sub Structure | RCC Works - Vertical
40336 | Tower A - Super Structure - Finishes & MEP - L44 to L45 | Complete | Partition Wall-Blockwork | 2025-08-12 | 2025-08-19 | Staircase Area | 100 | 100 | Units | 2025-08-12 | 2025-08-05 | 2025-08-19 | 2025-09-10 | Tower A | Super Structure | L44
40339 | Tower A - Super Structure - Finishes & MEP - L45 to L46 | Started | Partition Wall-Blockwork | 2025-08-12 | 2025-08-21 | Partition Walls | 100 | 5 | Units | 2025-08-12 | 2025-08-11 | 2025-09-19 |  | Tower A | Super Structure | L45
44049 | Tower A - Super Structure - Finishes & MEP - L13 to L18 | Started | Façade Works - MEP & Finishes | 2025-08-12 | 2025-09-02 | Al. Frame section (Mullion & Transom) Installation | 100 | 55 | Units | 2025-08-12 | 2025-05-10 | 2025-09-20 |  | Tower A | Super Structure | L13 | Façade | Façade Works
9004 | T-15-7th Floor | Complete | Shuttering | 2025-08-08 | 2025-08-12 | Slab and Beam Shuttering | 3715 | 3715 | Sqm | 2025-08-13 | 2025-08-19 | 2025-08-16 | 2025-08-28
9119 | T-15-2nd Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-08-08 | 2025-08-30 | Plumbing Pipe Line | 100 | 0 |  | 2025-08-13 |  | 2025-09-04
9134 |  | Not Ready |  | 2025-08-19 | 2026-09-07 | Common Area | 100 | 0 |  | 2025-08-13 |  | 2026-09-02
9581 | T-16-GF Flat Area | Not Ready | Electrical DB Fixing | 2025-09-02 | 2025-09-09 | Electrical DB Fixing | 100 | 0 |  | 2025-08-13 |  | 2025-08-20
10190 | T-21-3rd Floor Flat Area | Not Ready | Dado | 2025-09-12 | 2025-10-10 | Dado | 100 | 0 |  | 2025-08-13 |  | 2025-09-09
10253 | T-21-5th Floor Common Area | Not Ready | Plastering | 2025-09-13 | 2025-10-16 | Plastering-Gypsum | 100 | 0 |  | 2025-08-13 |  | 2025-09-16
10266 | T-21-6th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-09-12 | 2025-09-28 | Electrical DB Fixing | 100 | 0 |  | 2025-08-13 |  | 2025-08-29
10582 | T-20-10th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-09-08 | 2025-09-12 | AL - Shear Walls/Corewalls Steel | 20.54 | 20.54 | MT | 2025-08-13 | 2025-08-17 | 2025-08-18 | 2025-08-23
10747 | T-20-4th Floor Common Area | Not Ready | Plastering | 2025-09-10 | 2025-10-14 | Plastering-Gypsum | 100 | 0 |  | 2025-08-13 |  | 2025-09-16
11077 | T-19-6th Floor | Complete | Shuttering | 2025-08-30 | 2025-09-04 | Slab and Beam Shuttering | 3548 | 3548 | Sqm | 2025-08-13 | 2025-09-06 | 2025-08-15 | 2025-09-14
11173 | T-19-1st Floor Flat Area | Forced Ready | Plumbing Pipe Line | 2025-08-30 | 2025-09-27 | Plumbing Pipe Line | 100 | 0 |  | 2025-08-13 |  | 2025-09-09
11600 | T-18-7th Floor | Complete |  | 2025-10-05 | 2025-10-18 | 6th Floor Roof | 100 | 100 |  | 2025-08-13 | 2025-10-21 | 2025-08-25 | 2025-11-10
39698 | Tower A - Super Structure - Core Wall Mid Rise L65-66 | Complete | Core Wall RCC Works | 2025-08-13 | 2025-08-13 | ACS Form Release & jump to next level | 100 | 100 |  | 2025-08-13 | 2025-09-01 | 2025-08-13 | 2025-09-01 | Tower A | Super Structure | L65 | RCC Super Structure | Core Wall RCC Works
9077 | T-15-GF Common Area | Not Ready | Waterproofing | 2025-08-12 | 2025-09-04 | Waterproofing | 100 | 0 |  | 2025-08-14 |  | 2025-09-07
9079 | T-15-GF Common Area | Not Ready | Plastering | 2025-08-12 | 2025-09-15 | Plastering-Gypsum | 100 | 0 |  | 2025-08-14 |  | 2025-09-17
9509 | T-16-5th Floor | Complete | Conduiting | 2025-09-03 | 2025-09-05 | Conduiting works | 100 | 100 |  | 2025-08-14 | 2025-08-26 | 2025-08-16 | 2025-08-31
9594 | T-16-GF Common Area | Not Ready | Blockwork | 2025-09-03 | 2025-09-24 | Blockwork | 100 | 0 |  | 2025-08-14 |  | 2025-09-01
9688 |  | Not Ready |  | 2025-10-13 | 2026-09-09 | Fourth Floor | 100 | 0 |  | 2025-08-14 |  | 2026-07-13
9689 |  | Not Ready |  | 2025-10-13 | 2026-07-28 | Flat Area | 100 | 0 |  | 2025-08-14 |  | 2026-05-31
10071 | T-21-11th Floor | Complete | Conduiting | 2025-09-13 | 2025-09-16 | Conduiting works | 100 | 100 |  | 2025-08-14 | 2025-10-06 | 2025-08-19 | 2025-10-08
10120 | T-21-GF Common Area | Not Ready | Dado | 2025-08-11 | 2025-09-03 | Dado | 100 | 0 |  | 2025-08-14 |  | 2025-09-04
10713 | T-20-3rd Floor Flat Area | Not Ready | Flooring & skirting | 2025-09-16 | 2025-10-30 | Flooring & skirting | 100 | 0 |  | 2025-08-14 |  | 2025-09-27
10760 | T-20-5th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-09-09 | 2025-09-25 | Electrical DB Fixing | 100 | 0 |  | 2025-08-14 |  | 2025-09-02
11604 | T-18-7th Floor | Complete | Shuttering | 2025-10-11 | 2025-10-15 | Slab and Beam Shuttering | 3527 | 3527 | Sqm | 2025-08-14 | 2025-10-31 | 2025-08-16 | 2025-11-08
11719 | T-18-2nd Floor Flat Area | Forced Ready | Plumbing Pipe Line | 2025-10-11 | 2025-11-05 | Plumbing Pipe Line | 100 | 0 |  | 2025-08-14 |  | 2025-09-05
39699 |  | Started |  | 2025-08-14 | 2026-01-08 | Core Wall_High Rise (3.5m f/f) | 100 | 49 |  | 2025-08-14 | 2025-09-03 | 2026-02-07
39701 |  | Complete |  | 2025-08-14 | 2025-08-30 | Core Wall L66-67 | 100 | 100 |  | 2025-08-14 | 2025-09-03 | 2025-09-11 | 2025-09-11
39702 | Tower A - Super Structure - Core Wall High Rise L66-67 | Complete | Core Wall RCC Works | 2025-08-14 | 2025-08-14 | Scaffolding & platform | 100 | 100 |  | 2025-08-14 | 2025-09-03 | 2025-08-14 | 2025-09-03 | Tower A | Super Structure | L66 | RCC Super Structure | Core Wall RCC Works
8453 | T-14-7th Floor | Complete | RCC | 2025-07-15 | 2025-07-16 | Slab& Beam RCC | 307 | 307 | CUM | 2025-08-15 | 2025-09-12 | 2025-08-18 | 2025-09-13
9005 | T-15-7th Floor | Complete | Slab& Beam Steel & Conduting | 2025-08-10 | 2025-08-13 | Slab& Beam Steel & Conduting | 13 | 13 | MT | 2025-08-15 | 2025-08-21 | 2025-08-20 | 2025-08-30
9123 | T-15-2nd Floor Flat Area | Not Ready | Plastering | 2025-08-10 | 2025-09-24 | Plastering-Gypsum | 100 | 0 |  | 2025-08-15 |  | 2025-10-01
9508 | T-16-5th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-09-04 | 2025-09-08 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-08-15 | 2025-08-26 | 2025-08-21 | 2025-08-31
10070 | T-21-11th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-09-14 | 2025-09-18 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-08-15 | 2025-09-27 | 2025-08-20 | 2025-10-06
10584 | T-20-10th Floor | Complete | Conduiting | 2025-09-10 | 2025-09-13 | Conduiting works | 100 | 100 | Units | 2025-08-15 | 2025-08-19 | 2025-08-18 | 2025-08-25
11078 | T-19-6th Floor | Complete | Slab& Beam Steel & Conduting | 2025-09-02 | 2025-09-05 | Slab& Beam Steel & Conduting | 11.3 | 11.3 | MT | 2025-08-15 | 2025-09-13 | 2025-08-19 | 2025-09-20
11177 | T-19-1st Floor Flat Area | Not Ready | Plastering | 2025-09-02 | 2025-10-22 | Plastering-Gypsum | 100 | 0 |  | 2025-08-15 |  | 2025-10-06
11660 | T-18-GF Flat Area | Not Ready | Waterproofing | 2025-10-07 | 2025-10-29 | Waterproofing | 100 | 0 |  | 2025-08-15 |  | 2025-09-06
8517 | T-14-GF Flat Area | Not Ready | Dado | 2025-07-21 | 2025-08-12 | Dado | 100 | 0 |  | 2025-08-16 |  | 2025-09-07
8674 |  | Not Ready |  | 2025-08-14 | 2026-04-08 | Sixth Floor | 100 | 0 |  | 2025-08-16 |  | 2026-04-09
8675 |  | Not Ready |  | 2025-08-14 | 2026-03-06 | Flat Area | 100 | 0 |  | 2025-08-16 |  | 2026-03-08
9527 | T-16-8th Floor | Complete |  | 2025-10-14 | 2025-10-27 | 7th Floor Roof | 100 | 100 |  | 2025-08-16 | 2025-10-28 | 2025-08-29 | 2025-11-18
9598 | T-16-GF Common Area | Not Ready | Electrical DB Fixing | 2025-09-05 | 2025-09-12 | Electrical DB Fixing | 100 | 0 |  | 2025-08-16 |  | 2025-08-23
10168 | T-21-2nd Floor Flat Area | Not Ready | Putty | 2025-09-23 | 2025-12-17 | Putty | 100 | 0 |  | 2025-08-16 |  | 2025-11-09
10583 | T-20-10th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-09-11 | 2025-09-15 | Shear Walls/Corewalls Shuttering | 100 | 100 | Units | 2025-08-16 | 2025-08-18 | 2025-08-19 | 2025-08-25
10707 | T-20-3rd Floor Flat Area | Not Ready | Waterproofing | 2025-09-16 | 2025-11-07 | Waterproofing | 100 | 0 |  | 2025-08-16 |  | 2025-10-05
11274 |  | Not Ready |  | 2025-10-06 | 2026-07-16 | Fifth Floor | 100 | 0 |  | 2025-08-16 |  | 2026-05-28
11275 |  | Not Ready |  | 2025-10-06 | 2026-06-09 | Flat Area | 100 | 0 |  | 2025-08-16 |  | 2026-04-20
11605 | T-18-7th Floor | Complete | Slab& Beam Steel & Conduting | 2025-10-14 | 2025-10-17 | Slab& Beam Steel & Conduting | 10.8 | 10.8 | MT | 2025-08-16 | 2025-11-06 | 2025-08-16 | 2025-11-08
11723 | T-18-2nd Floor Flat Area | Not Ready | Plastering | 2025-10-14 | 2025-11-28 | Plastering-Gypsum | 100 | 0 |  | 2025-08-16 |  | 2025-09-28
39703 | Tower A - Super Structure - Core Wall High Rise L66-67 | Complete | Core Wall RCC Works | 2025-08-16 | 2025-08-20 | Reinf & Guide shoes fixing | 100 | 100 |  | 2025-08-16 | 2025-09-07 | 2025-08-20 | 2025-09-07 | Tower A | Super Structure | L66 | RCC Super Structure | Core Wall RCC Works
8468 | T-14-10th Floor | Complete |  | 2025-08-16 | 2025-08-29 | 9th Floor Roof | 100 | 100 |  | 2025-08-17 | 2025-10-30 | 2025-08-30 | 2025-11-20
8574 | T-14-2nd Floor Flat Area | Not Ready | Plastering | 2025-07-17 | 2025-08-08 | Plastering-Cement | 100 | 0 |  | 2025-08-17 |  | 2025-09-07
10105 | T-21-GF Flat Area | Forced Ready | Toilets False Celing | 2025-08-20 | 2025-09-05 | Toilets-False Celing | 100 | 0 |  | 2025-08-17 |  | 2025-09-01
10806 |  | Not Ready |  | 2025-09-21 | 2026-05-24 | Seventh Floor | 100 | 0 |  | 2025-08-17 |  | 2026-04-18
10807 |  | Not Ready |  | 2025-09-21 | 2026-04-27 | Flat Area | 100 | 0 |  | 2025-08-17 |  | 2026-03-22
11094 | T-19-9th Floor | Complete |  | 2025-10-07 | 2025-10-20 | 8th Floor Roof | 100 | 100 |  | 2025-08-17 | 2025-11-03 | 2025-08-30 | 2025-11-22
11606 | T-18-7th Floor | Complete | RCC | 2025-10-17 | 2025-10-18 | Slab& Beam RCC | 330.8 | 330.8 | CUM | 2025-08-17 | 2025-11-09 | 2025-08-17 | 2025-11-10
9510 | T-16-5th Floor | Complete | Shuttering | 2025-09-07 | 2025-09-11 | Slab and Beam Shuttering | 4183 | 4183 | Sqm | 2025-08-18 | 2025-08-29 | 2025-08-22 | 2025-09-02
9578 | T-16-GF Flat Area | Not Ready | Plumbing Pipe Line | 2025-09-07 | 2025-09-23 | Plumbing Pipe Line | 100 | 0 |  | 2025-08-18 |  | 2025-09-04
9654 |  | Not Ready |  | 2025-10-16 | 2026-11-05 | Common Area | 100 | 0 |  | 2025-08-18 |  | 2026-09-06
10072 | T-21-11th Floor | Complete | Shuttering | 2025-09-17 | 2025-09-22 | Slab and Beam Shuttering | 3264 | 3264 | Sqm | 2025-08-18 | 2025-10-09 | 2025-08-20 | 2025-10-25
10219 | T-21-4th Floor Flat Area | Not Ready | Flooring & skirting | 2025-09-18 | 2025-11-04 | Flooring & skirting | 100 | 0 |  | 2025-08-18 |  | 2025-10-02
10263 | T-21-6th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-09-17 | 2025-10-10 | Plumbing Pipe Line | 100 | 0 |  | 2025-08-18 |  | 2025-09-07
10588 | T-20-11th Floor | Complete |  | 2025-09-22 | 2025-10-06 | 10th Floor Roof | 100 | 100 |  | 2025-08-18 | 2025-09-14 | 2025-08-31 | 2025-09-30
10627 | T-20-GF Flat Area | Not Ready | Putty | 2025-09-20 | 2025-10-13 | Putty | 100 | 0 |  | 2025-08-18 |  | 2025-09-05
11708 |  | Not Ready |  | 2025-10-07 | 2026-11-27 | Common Area | 100 | 0 |  | 2025-08-18 |  | 2026-09-26
11744 | T-18-3rd Floor Flat Area | Not Ready | Blockwork | 2025-10-18 | 2025-11-11 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-08-18 |  | 2025-09-09
11783 | T-18-4th Floor Flat Area | Not Ready | Railing | 2025-10-18 | 2025-11-22 | Balcony Railing | 100 | 0 |  | 2025-08-18 |  | 2025-09-19
8589 | T-14-2nd Floor Common Area | Not Ready | Plastering | 2025-07-19 | 2025-08-22 | Plastering-Gypsum | 100 | 0 |  | 2025-08-19 |  | 2025-09-22
8598 | T-14-3rd Floor Flat Area | Not Ready | Blockwork | 2025-07-16 | 2025-08-07 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-08-19 |  | 2025-09-10
8637 | T-14-4th Floor Flat Area | Not Ready | Railing | 2025-07-16 | 2025-08-19 | Balcony Railing | 100 | 0 |  | 2025-08-19 |  | 2025-09-22
8640 |  | Not Ready |  | 2025-08-18 | 2026-06-14 | Common Area | 100 | 0 |  | 2025-08-19 |  | 2026-06-15
10585 | T-20-10th Floor | Complete | Shuttering | 2025-09-15 | 2025-09-18 | Slab and Beam Shuttering | 3583 | 3583 | Sqm | 2025-08-19 | 2025-08-20 | 2025-08-24 | 2025-08-26
10686 | T-20-2nd Floor Flat Area | Not Ready |  | 2025-09-25 | 2025-10-29 | Toilets False Celing | 100 | 0 |  | 2025-08-19 |  | 2025-09-19
10757 | T-20-5th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-09-15 | 2025-10-07 | Plumbing Pipe Line | 100 | 0 |  | 2025-08-19 |  | 2025-09-09
11240 |  | Not Ready |  | 2025-10-09 | 2026-09-21 | Common Area | 100 | 0 |  | 2025-08-19 |  | 2026-08-01
11607 | T-18-8th Floor | Complete |  | 2025-10-19 | 2025-11-04 | 7th Floor Roof | 100 | 100 |  | 2025-08-19 | 2025-11-11 | 2025-08-31 | 2025-12-29
11608 | T-18-8th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-10-19 | 2025-10-23 | AL - Shear Walls/Corewalls Steel | 20.5 | 20.5 | MT | 2025-08-19 | 2025-11-11 | 2025-08-22 | 2025-11-18
8455 | T-14-8th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-07-17 | 2025-07-22 | AL - Shear Walls/Corewalls Steel | 22 | 22 | MT | 2025-08-20 | 2025-09-20 | 2025-08-25 | 2025-09-24
9120 | T-15-2nd Floor Flat Area | Not Ready | Plastering | 2025-08-16 | 2025-09-08 | Plastering-Cement | 100 | 0 |  | 2025-08-20 |  | 2025-09-11
9511 | T-16-5th Floor | Complete | Slab& Beam Steel & Conduting | 2025-09-09 | 2025-09-12 | Slab& Beam Steel & Conduting | 14 | 14 | MT | 2025-08-20 | 2025-09-02 | 2025-08-21 | 2025-09-05
10073 | T-21-11th Floor | Complete | Slab& Beam Steel & Conduting | 2025-09-19 | 2025-09-23 | Slab& Beam Steel & Conduting | 19.5 | 19.5 | MT | 2025-08-20 | 2025-10-23 | 2025-08-25 | 2025-11-30
10123 | T-21-GF Common Area | Forced Ready | Flooring & skirting | 2025-08-18 | 2025-09-30 | Flooring & skirting | 100 | 0 |  | 2025-08-20 |  | 2025-10-04
10191 | T-21-3rd Floor Flat Area | Not Ready | Toilet flooring | 2025-09-19 | 2025-10-23 | Toilet flooring | 100 | 0 |  | 2025-08-20 |  | 2025-09-21
10213 | T-21-4th Floor Flat Area | Not Ready | Waterproofing | 2025-09-18 | 2025-11-10 | Waterproofing | 100 | 0 |  | 2025-08-20 |  | 2025-10-08
10267 | T-21-6th Floor Flat Area | Not Ready | Plastering | 2025-09-19 | 2025-11-05 | Plastering-Gypsum | 100 | 0 |  | 2025-08-20 |  | 2025-10-05
10772 |  | Not Ready |  | 2025-09-24 | 2026-06-04 | Common Area | 100 | 0 |  | 2025-08-20 |  | 2026-04-29
11079 | T-19-6th Floor | Complete | RCC | 2025-09-05 | 2025-09-06 | Slab& Beam RCC | 340 | 340 | CUM | 2025-08-20 | 2025-09-20 | 2025-08-20 | 2025-09-21
11174 | T-19-1st Floor Flat Area | Not Ready | Plastering | 2025-09-08 | 2025-09-29 | Plastering-Cement | 100 | 0 |  | 2025-08-20 |  | 2025-09-09
11748 | T-18-3rd Floor Flat Area | Forced Ready | Electrical DB Fixing | 2025-10-20 | 2025-11-08 | Electrical DB Fixing | 100 | 0 |  | 2025-08-20 |  | 2025-09-05
8520 | T-14-GF Flat Area | Not Ready | Flooring & skirting | 2025-07-24 | 2025-08-27 | Flooring & skirting | 100 | 0 |  | 2025-08-21 |  | 2025-09-22
8602 | T-14-3rd Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-07-18 | 2025-08-04 | Electrical DB Fixing | 100 | 0 |  | 2025-08-21 |  | 2025-09-05
9006 | T-15-7th Floor | Complete | RCC | 2025-08-13 | 2025-08-14 | Slab& Beam RCC | 318 | 318 | CUM | 2025-08-21 | 2025-08-30 | 2025-08-21 | 2025-08-31
9063 | T-15-GF Flat Area | Not Ready | Dado | 2025-08-21 | 2025-09-12 | Dado | 100 | 0 |  | 2025-08-21 |  | 2025-09-10
9595 | T-16-GF Common Area | Not Ready | Plumbing Pipe Line | 2025-09-10 | 2025-09-26 | Plumbing Pipe Line | 100 | 0 |  | 2025-08-21 |  | 2025-09-05
10146 | T-21-1st Floor Flat Area | Not Ready | 1st Coat Painting | 2025-09-30 | 2025-12-24 | 1st Coat Painting | 100 | 0 |  | 2025-08-21 |  | 2025-11-13
10586 | T-20-10th Floor | Complete | Slab& Beam Steel & Conduting | 2025-09-17 | 2025-09-19 | Slab& Beam Steel & Conduting | 10.8 | 10.8 | MT | 2025-08-21 | 2025-08-27 | 2025-08-24 | 2025-08-30
10761 | T-20-5th Floor Flat Area | Not Ready | Plastering | 2025-09-17 | 2025-11-03 | Plastering-Gypsum | 100 | 0 |  | 2025-08-21 |  | 2025-10-04
11198 | T-19-2nd Floor Flat Area | Not Ready | Blockwork | 2025-09-06 | 2025-09-28 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-08-21 |  | 2025-09-11
11237 | T-19-3rd Floor Flat Area | Not Ready | Railing | 2025-09-06 | 2025-10-10 | Balcony Railing | 100 | 0 |  | 2025-08-21 |  | 2025-09-23
11610 | T-18-8th Floor | Complete | Conduiting | 2025-10-21 | 2025-10-24 | Conduiting works | 100 | 100 |  | 2025-08-21 | 2025-11-20 | 2025-08-22 | 2025-11-21
11720 | T-18-2nd Floor Flat Area | Not Ready | Plastering | 2025-10-19 | 2025-11-12 | Plastering-Cement | 100 | 0 |  | 2025-08-21 |  | 2025-09-12
39704 | Tower A - Super Structure - Core Wall High Rise L66-67 | Complete | Core Wall RCC Works | 2025-08-21 | 2025-08-23 | ACS Form Closing & Alignment | 100 | 100 |  | 2025-08-21 | 2025-09-09 | 2025-08-23 | 2025-09-09 | Tower A | Super Structure | L66 | RCC Super Structure | Core Wall RCC Works
39991 | Tower A - Super Structure - Core & Outer Slab L62-63 | Complete | RCC Works - Slab | 2025-08-21 | 2025-08-29 | Outer Slab_TA | 100 | 100 |  | 2025-08-21 | 2025-09-07 | 2025-08-29 | 2025-09-07 | Tower A | Super Structure | L62 | RCC Sub Structure | RCC Works - Slab
41427 |  | Started |  | 2025-05-22 | 2026-04-14 | L30-31 | 100 | 46 |  | 2025-08-21 | 2025-08-21 | 2026-05-06 |  |  |  |  | Finishes | Gypsum Plastering Works
41427 |  | Started |  | 2025-05-22 | 2026-04-14 | L30-31 | 100 | 46 |  | 2025-08-21 | 2025-08-21 | 2026-05-06
41428 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2025-08-21 | 2025-08-23 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 65 |  | 2025-08-21 | 2025-08-21 | 2026-03-25 |  | Tower A | Super Structure | L30 | MEP | FPS 1st Fix - MEP & Finishes
8457 | T-14-8th Floor | Complete | Conduiting | 2025-07-19 | 2025-07-23 | Conduiting works | 100 | 100 | Units | 2025-08-22 | 2025-08-29 | 2025-08-27 | 2025-08-29
9135 | T-15-2nd Floor Common Area | Not Ready | Plastering | 2025-08-19 | 2025-09-20 | Plastering-Gypsum | 100 | 0 |  | 2025-08-22 |  | 2025-09-25
9144 | T-15-3rd Floor Flat Area | Not Ready | Blockwork | 2025-08-14 | 2025-09-06 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-08-22 |  | 2025-09-12
9183 | T-15-4th Floor Flat Area | Not Ready | Railing | 2025-08-14 | 2025-09-17 | Balcony Railing | 100 | 0 |  | 2025-08-22 |  | 2025-09-25
9512 | T-16-5th Floor | Complete | RCC | 2025-09-12 | 2025-09-13 | Slab& Beam RCC | 387 | 387 | CUM | 2025-08-22 | 2025-09-05 | 2025-08-23 | 2025-09-06
9582 | T-16-GF Flat Area | Not Ready | Plastering | 2025-09-10 | 2025-10-14 | Plastering-Gypsum | 100 | 0 |  | 2025-08-22 |  | 2025-09-25
10312 |  | Not Ready |  | 2025-09-24 | 2026-06-04 | Eighth Floor | 100 | 0 |  | 2025-08-22 |  | 2026-05-02
10313 |  | Not Ready |  | 2025-09-24 | 2026-05-14 | Flat Area | 100 | 0 |  | 2025-08-22 |  | 2026-04-10
11081 | T-19-7th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-09-08 | 2025-09-11 | AL - Shear Walls/Corewalls Steel | 28.4 | 28.4 | MT | 2025-08-22 | 2025-09-23 | 2025-08-26 | 2025-09-29
11140 | T-19-GF Flat Area | Not Ready | Waterproofing | 2025-09-10 | 2025-10-01 | Waterproofing | 100 | 0 |  | 2025-08-22 |  | 2025-09-13
11189 | T-19-1st Floor Common Area | Not Ready | Plastering | 2025-09-10 | 2025-10-13 | Plastering-Gypsum | 100 | 0 |  | 2025-08-22 |  | 2025-09-25
11609 | T-18-8th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-10-22 | 2025-10-27 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-08-22 | 2025-11-16 | 2025-08-27 | 2025-11-21
8456 | T-14-8th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-07-21 | 2025-07-25 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-08-23 | 2025-09-21 | 2025-08-26 | 2025-09-27
8534 | T-14-GF Common Area | Not Ready | Dado | 2025-07-29 | 2025-08-21 | Dado | 100 | 0 |  | 2025-08-23 |  | 2025-09-14
8555 | T-14-1st Floor Flat Area | Not Ready | Flooring & skirting | 2025-07-25 | 2025-09-08 | Flooring & skirting | 100 | 0 |  | 2025-08-23 |  | 2025-10-05
9008 | T-15-8th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-08-16 | 2025-08-21 | AL - Shear Walls/Corewalls Steel | 24.5 | 24.5 | MT | 2025-08-23 | 2025-09-03 | 2025-08-29 | 2025-09-07
10075 | T-21-Terrace | Complete |  | 2025-09-25 | 2025-10-09 | 11th Floor Roof | 100 | 100 |  | 2025-08-23 | 2025-12-01 | 2025-09-05 | 2025-12-17
10710 | T-20-3rd Floor Flat Area | Not Ready | Dado | 2025-09-23 | 2025-10-21 | Dado | 100 | 0 |  | 2025-08-23 |  | 2025-09-20
11202 | T-19-2nd Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-09-09 | 2025-09-25 | Electrical DB Fixing | 100 | 0 |  | 2025-08-23 |  | 2025-09-07
11677 | T-18-GF Common Area | Not Ready | Waterproofing | 2025-10-16 | 2025-11-09 | Waterproofing | 100 | 0 |  | 2025-08-23 |  | 2025-09-13
11735 | T-18-2nd Floor Common Area | Not Ready | Plastering | 2025-10-21 | 2025-11-25 | Plastering-Gypsum | 100 | 0 |  | 2025-08-23 |  | 2025-09-24
9101 | T-15-1st Floor Flat Area | Not Ready | Flooring & skirting | 2025-08-25 | 2025-10-08 | Flooring & skirting | 100 | 0 |  | 2025-08-24 |  | 2025-10-10
9148 | T-15-3rd Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-08-18 | 2025-09-03 | Electrical DB Fixing | 100 | 0 |  | 2025-08-24 |  | 2025-09-12
9612 | T-16-1st Floor Flat Area | Not Ready | Blockwork | 2025-09-13 | 2025-10-15 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-08-24 |  | 2025-09-23
9651 | T-16-2nd Floor Flat Area | Not Ready | Railing | 2025-09-13 | 2025-10-17 | Balcony Railing | 100 | 0 |  | 2025-08-24 |  | 2025-09-25
10121 | T-21-GF Common Area | Not Ready | Toilet flooring | 2025-08-23 | 2025-09-08 | Toilet flooring | 100 | 0 |  | 2025-08-24 |  | 2025-09-09
10194 | T-21-3rd Floor Flat Area | Not Ready | Putty | 2025-09-26 | 2025-12-20 | Putty | 100 | 0 |  | 2025-08-24 |  | 2025-11-17
11083 | T-19-7th Floor | Complete | Conduiting | 2025-09-10 | 2025-09-12 | Conduiting works | 100 | 100 |  | 2025-08-24 | 2025-10-02 | 2025-08-27 | 2025-10-04
11679 | T-18-GF Common Area | Not Ready | Plastering | 2025-10-16 | 2025-11-20 | Plastering-Gypsum | 100 | 0 |  | 2025-08-24 |  | 2025-09-26
8549 | T-14-1st Floor Flat Area | Not Ready | Waterproofing | 2025-07-25 | 2025-09-13 | Waterproofing | 100 | 0 |  | 2025-08-25 |  | 2025-10-13
9010 | T-15-8th Floor | Complete | Conduiting | 2025-08-19 | 2025-08-22 | Conduiting works | 100 | 100 |  | 2025-08-25 | 2025-09-06 | 2025-08-27 | 2025-09-10
9066 | T-15-GF Flat Area | Not Ready | Flooring & skirting | 2025-08-25 | 2025-09-26 | Flooring & skirting | 100 | 0 |  | 2025-08-25 |  | 2025-09-25
9194 |  | Not Ready |  | 2025-08-30 | 2026-06-10 | Fifth Floor | 100 | 0 |  | 2025-08-25 |  | 2026-06-05
9195 |  | Not Ready |  | 2025-08-30 | 2026-05-04 | Flat Area | 100 | 0 |  | 2025-08-25 |  | 2026-04-28
9513 | T-16-6th Floor | Complete |  | 2025-09-15 | 2025-09-27 | 5th Floor Roof | 100 | 100 |  | 2025-08-25 | 2025-09-08 | 2025-09-06 | 2025-09-27
9514 | T-16-6th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-09-15 | 2025-09-19 | AL - Shear Walls/Corewalls Steel | 25 | 25 | MT | 2025-08-25 | 2025-09-08 | 2025-08-28 | 2025-09-14
9579 | T-16-GF Flat Area | Not Ready | Plastering | 2025-09-15 | 2025-10-01 | Plastering-Cement | 100 | 0 |  | 2025-08-25 |  | 2025-09-09
10264 | T-21-6th Floor Flat Area | Not Ready | Plastering | 2025-09-25 | 2025-10-17 | Plastering-Cement | 100 | 0 |  | 2025-08-25 |  | 2025-09-15
10587 | T-20-10th Floor | Complete | RCC | 2025-09-20 | 2025-09-20 | Slab& Beam RCC | 321 | 321 | CUM | 2025-08-25 | 2025-08-31 | 2025-08-25 | 2025-09-02
11082 | T-19-7th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-09-11 | 2025-09-15 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-08-25 | 2025-09-27 | 2025-08-30 | 2025-10-04
11611 | T-18-8th Floor | Complete | Shuttering | 2025-10-25 | 2025-10-29 | Slab and Beam Shuttering | 3527 | 3527 | Sqm | 2025-08-25 | 2025-11-22 | 2025-08-30 | 2025-12-29
11745 | T-18-3rd Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-10-25 | 2025-11-19 | Plumbing Pipe Line | 100 | 0 |  | 2025-08-25 |  | 2025-09-15
11768 |  | Not Ready |  | 2025-10-18 | 2026-09-15 | Fourth Floor | 100 | 0 |  | 2025-08-25 |  | 2026-07-16
11769 |  | Not Ready |  | 2025-10-18 | 2026-08-02 | Flat Area | 100 | 0 |  | 2025-08-25 |  | 2026-06-03
39705 | Tower A - Super Structure - Core Wall High Rise L66-67 | Complete | Core Wall RCC Works | 2025-08-25 | 2025-08-25 | Casting | 100 | 100 |  | 2025-08-25 | 2025-09-10 | 2025-08-25 | 2025-09-10 | Tower A | Super Structure | L66 | RCC Super Structure | Core Wall RCC Works
40343 | Tower A - Super Structure - Finishes & MEP - L46 to L47 | Started | Partition Wall-Blockwork | 2025-08-25 | 2025-09-03 | Partition Walls | 100 | 25 | Units | 2025-08-25 | 2025-09-05 | 2025-09-25 |  | Tower A | Super Structure | L46
8458 | T-14-8th Floor | Complete | Shuttering | 2025-07-24 | 2025-07-27 | Slab and Beam Shuttering | 3605 | 3605 | Sqm | 2025-08-26 | 2025-09-22 | 2025-08-27 | 2025-09-29
8518 | T-14-GF Flat Area | Not Ready | Toilet flooring | 2025-07-31 | 2025-08-18 | Toilet flooring | 100 | 0 |  | 2025-08-26 |  | 2025-09-10
8599 | T-14-3rd Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-07-24 | 2025-08-16 | Plumbing Pipe Line | 100 | 0 |  | 2025-08-26 |  | 2025-09-16
9009 | T-15-8th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-08-20 | 2025-08-24 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-08-26 | 2025-09-05 | 2025-08-29 | 2025-09-10
9014 | T-15-9th Floor | Complete |  | 2025-08-31 | 2025-09-13 | 8th Floor Roof | 100 | 100 |  | 2025-08-26 | 2025-09-20 | 2025-09-08 | 2025-10-12
9616 | T-16-1st Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-09-16 | 2025-10-03 | Electrical DB Fixing | 100 | 0 |  | 2025-08-26 |  | 2025-09-10
10074 | T-21-11th Floor | Complete | RCC | 2025-09-23 | 2025-09-24 | Slab& Beam RCC | 318 | 318 | CUM | 2025-08-26 | 2025-11-01 | 2025-08-27 | 2025-11-02
10278 |  | Not Committed |  | 2025-09-27 | 2026-04-20 | Common Area | 100 | 0 |  | 2025-08-26 |  | 2026-03-18
10688 | T-20-2nd Floor Flat Area | Not Ready | Putty | 2025-10-05 | 2025-12-28 | Putty | 100 | 0 |  | 2025-08-26 |  | 2025-11-17
10758 | T-20-5th Floor Flat Area | Not Ready | Plastering | 2025-09-22 | 2025-10-15 | Plastering-Cement | 100 | 0 |  | 2025-08-26 |  | 2025-09-17
10782 | T-20-6th Floor Flat Area | Not Ready | Blockwork | 2025-09-21 | 2025-10-14 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-08-26 |  | 2025-09-16
10821 | T-20-7th Floor Flat Area | Not Ready | Railing | 2025-09-21 | 2025-10-24 | Balcony Railing | 100 | 0 |  | 2025-08-26 |  | 2025-09-27
9095 | T-15-1st Floor Flat Area | Not Ready | Waterproofing | 2025-08-25 | 2025-10-14 | Waterproofing | 100 | 0 |  | 2025-08-27 |  | 2025-10-16
9516 | T-16-6th Floor | Complete | Conduiting | 2025-09-17 | 2025-09-20 | Conduiting works | 100 | 100 |  | 2025-08-27 | 2025-09-11 | 2025-08-31 | 2025-09-19
10216 | T-21-4th Floor Flat Area | Not Ready | Dado | 2025-09-26 | 2025-10-24 | Dado | 100 | 0 |  | 2025-08-27 |  | 2025-09-23
10279 | T-21-6th Floor Common Area | Not Ready | Plastering | 2025-09-27 | 2025-11-02 | Plastering-Gypsum | 100 | 0 |  | 2025-08-27 |  | 2025-09-28
10589 | T-20-11th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-09-22 | 2025-09-26 | AL - Shear Walls/Corewalls Steel | 20.54 | 20.54 | MT | 2025-08-27 | 2025-09-14 | 2025-09-02 | 2025-09-22
11749 | T-18-3rd Floor Flat Area | Not Ready | Plastering | 2025-10-28 | 2025-12-12 | Plastering-Gypsum | 100 | 0 |  | 2025-08-27 |  | 2025-10-11
8459 | T-14-8th Floor | Complete | Slab& Beam Steel & Conduting | 2025-07-26 | 2025-07-29 | Slab& Beam Steel & Conduting | 10 | 10 | MT | 2025-08-28 | 2025-09-26 | 2025-08-30 | 2025-10-04
8603 | T-14-3rd Floor Flat Area | Not Ready | Plastering | 2025-07-26 | 2025-09-09 | Plastering-Gypsum | 100 | 0 |  | 2025-08-28 |  | 2025-10-11
9160 |  | Not Ready |  | 2025-09-02 | 2026-08-16 | Common Area | 100 | 0 |  | 2025-08-28 |  | 2026-08-10
9515 | T-16-6th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-09-18 | 2025-09-22 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-08-28 | 2025-09-11 | 2025-09-03 | 2025-09-19
9596 | T-16-GF Common Area | Not Ready | Plastering | 2025-09-18 | 2025-10-10 | Plastering-Cement | 100 | 0 |  | 2025-08-28 |  | 2025-09-21
10192 | T-21-3rd Floor Flat Area | Not Ready |  | 2025-09-28 | 2025-11-03 | Toilets False Celing | 100 | 0 |  | 2025-08-28 |  | 2025-09-30
10288 | T-21-7th Floor Flat Area | Not Ready | Blockwork | 2025-09-24 | 2025-10-16 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-08-28 |  | 2025-09-18
10327 | T-21-8th Floor Flat Area | Not Ready | Railing | 2025-09-24 | 2025-10-28 | Balcony Railing | 100 | 0 |  | 2025-08-28 |  | 2025-09-28
10773 | T-20-5th Floor Common Area | Not Ready | Plastering | 2025-09-24 | 2025-10-28 | Plastering-Gypsum | 100 | 0 |  | 2025-08-28 |  | 2025-09-30
10786 | T-20-6th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-09-23 | 2025-10-10 | Electrical DB Fixing | 100 | 0 |  | 2025-08-28 |  | 2025-09-13
11084 | T-19-7th Floor | Complete | Shuttering | 2025-09-14 | 2025-09-18 | Slab and Beam Shuttering | 3548 | 3548 | Sqm | 2025-08-28 | 2025-10-02 | 2025-08-31 | 2025-10-06
11199 | T-19-2nd Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-09-14 | 2025-10-07 | Plumbing Pipe Line | 100 | 0 |  | 2025-08-28 |  | 2025-09-18
8537 | T-14-GF Common Area | Not Ready | Flooring & skirting | 2025-08-04 | 2025-09-17 | Flooring & skirting | 100 | 0 |  | 2025-08-29 |  | 2025-10-15
9011 | T-15-8th Floor | Complete | Shuttering | 2025-08-23 | 2025-08-27 | Slab and Beam Shuttering | 3715 | 3715 | Sqm | 2025-08-29 | 2025-09-07 | 2025-09-04 | 2025-09-12
9080 | T-15-GF Common Area | Not Ready | Dado | 2025-08-30 | 2025-09-20 | Dado | 100 | 0 |  | 2025-08-29 |  | 2025-09-22
9145 | T-15-3rd Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-08-23 | 2025-09-14 | Plumbing Pipe Line | 100 | 0 |  | 2025-08-29 |  | 2025-09-22
9714 |  | Not Ready |  | 2025-10-27 | 2026-08-06 | Fifth Floor | 100 | 0 |  | 2025-08-29 |  | 2026-06-10
9715 |  | Not Ready |  | 2025-10-27 | 2026-07-01 | Flat Area | 100 | 0 |  | 2025-08-29 |  | 2026-05-04
10076 | T-21-Terrace | Complete | AL - Shear Walls/Corewalls Steel | 2025-09-25 | 2025-09-29 | AL - Shear Walls/Corewalls Steel | 19.5 | 19.5 | MT | 2025-08-29 | 2025-12-01 | 2025-09-01 | 2025-12-06
10122 | T-21-GF Common Area | Not Ready | Toilets False Celing | 2025-08-28 | 2025-09-13 | Toilets False Celing | 100 | 0 |  | 2025-08-29 |  | 2025-09-13
10591 | T-20-11th Floor | Complete | Conduiting | 2025-09-24 | 2025-09-27 | Conduiting works | 100 | 100 |  | 2025-08-29 | 2025-09-16 | 2025-09-02 | 2025-09-29
11701 | T-18-1st Floor Flat Area | Not Ready | Flooring & skirting | 2025-10-27 | 2025-12-11 | Flooring & skirting | 100 | 0 |  | 2025-08-29 |  | 2025-10-12
8700 |  | Not Ready |  | 2025-08-29 | 2026-04-30 | Seventh Floor | 100 | 0 |  | 2025-08-30 |  | 2026-05-02
8701 |  | Not Ready |  | 2025-08-29 | 2026-04-04 | Flat Area | 100 | 0 |  | 2025-08-30 |  | 2026-04-05
9534 | T-16-9th Floor | Complete |  | 2025-10-28 | 2025-11-12 | 8th Floor Roof | 100 | 100 |  | 2025-08-30 | 2025-11-19 | 2025-09-12 | 2025-12-14
10292 | T-21-7th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-09-26 | 2025-10-13 | Electrical DB Fixing | 100 | 0 |  | 2025-08-30 |  | 2025-09-15
10590 | T-20-11th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-09-25 | 2025-09-30 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-08-30 | 2025-09-23 | 2025-09-04 | 2025-09-29
10711 | T-20-3rd Floor Flat Area | Not Ready | Toilet flooring | 2025-10-01 | 2025-11-06 | Toilet flooring | 100 | 0 |  | 2025-08-30 |  | 2025-09-30
11085 | T-19-7th Floor | Complete | Slab& Beam Steel & Conduting | 2025-09-16 | 2025-09-19 | Slab& Beam Steel & Conduting | 11.3 | 11.3 | MT | 2025-08-30 | 2025-10-04 | 2025-09-04 | 2025-10-08
11203 | T-19-2nd Floor Flat Area | Not Ready | Plastering | 2025-09-16 | 2025-11-02 | Plastering-Gypsum | 100 | 0 |  | 2025-08-30 |  | 2025-10-13
11300 |  | Not Ready |  | 2025-10-20 | 2026-06-13 | Sixth Floor | 100 | 0 |  | 2025-08-30 |  | 2026-04-24
11301 |  | Not Ready |  | 2025-10-20 | 2026-05-13 | Flat Area | 100 | 0 |  | 2025-08-30 |  | 2026-03-22
11663 | T-18-GF Flat Area | Not Ready | Dado | 2025-10-23 | 2025-11-17 | Dado | 100 | 0 |  | 2025-08-30 |  | 2025-09-19
11695 | T-18-1st Floor Flat Area | Not Ready | Waterproofing | 2025-10-27 | 2025-12-17 | Waterproofing | 100 | 0 |  | 2025-08-30 |  | 2025-10-18
11734 |  | Not Ready |  | 2025-10-21 | 2026-11-11 | Common Area | 100 | 0 |  | 2025-08-30 |  | 2026-09-09
8460 | T-14-8th Floor | Complete | RCC | 2025-07-29 | 2025-07-30 | Slab& Beam RCC | 307 | 307 | CUM | 2025-08-31 | 2025-10-05 | 2025-08-31 | 2025-10-05
8475 | T-14-11th Floor | Complete |  | 2025-08-30 | 2025-09-12 | 10th Floor Roof | 100 | 100 |  | 2025-08-31 | 2025-11-21 | 2025-09-13 | 2025-12-20
8519 | T-14-GF Flat Area | Not Ready | Toilets False Celing | 2025-08-06 | 2025-09-09 | Toilets False Celing | 100 | 0 |  | 2025-08-31 |  | 2025-10-04
9012 | T-15-8th Floor | Complete | Slab& Beam Steel & Conduting | 2025-08-26 | 2025-08-28 | Slab& Beam Steel & Conduting | 13 | 13 | MT | 2025-08-31 | 2025-09-13 | 2025-09-02 | 2025-09-18
9064 | T-15-GF Flat Area | Not Ready | Toilet flooring | 2025-09-01 | 2025-09-17 | Toilet flooring | 100 | 0 |  | 2025-08-31 |  | 2025-09-16
9149 | T-15-3rd Floor Flat Area | Not Ready | Plastering | 2025-08-26 | 2025-10-09 | Plastering-Gypsum | 100 | 0 |  | 2025-08-31 |  | 2025-10-14
9517 | T-16-6th Floor | Complete | Shuttering | 2025-09-21 | 2025-09-25 | Slab and Beam Shuttering | 4183 | 4183 | Sqm | 2025-08-31 | 2025-09-17 | 2025-09-02 | 2025-09-25
9613 | T-16-1st Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-09-21 | 2025-10-20 | Plumbing Pipe Line | 100 | 0 |  | 2025-08-31 |  | 2025-09-28
10078 | T-21-Terrace | Complete | Conduiting | 2025-09-27 | 2025-09-30 | Conduiting works | 100 | 100 |  | 2025-08-31 | 2025-12-09 | 2025-09-05 | 2025-12-11
10245 | T-21-5th Floor Flat Area | Not Ready | Flooring & skirting | 2025-10-03 | 2025-11-18 | Flooring & skirting | 100 | 0 |  | 2025-08-31 |  | 2025-10-14
10739 | T-20-4th Floor Flat Area | Not Ready | Flooring & skirting | 2025-09-30 | 2025-11-15 | Flooring & skirting | 100 | 0 |  | 2025-08-31 |  | 2025-10-14
10832 |  | Not Ready |  | 2025-10-06 | 2026-06-15 | Eighth Floor | 100 | 0 |  | 2025-08-31 |  | 2026-05-11
10833 |  | Not Ready |  | 2025-10-06 | 2026-05-25 | Flat Area | 100 | 0 |  | 2025-08-31 |  | 2026-04-20
11612 | T-18-8th Floor | Complete |  | 2025-10-28 | 2025-11-03 | Slab& Beam Steel & Conduting | 100 | 100 | MT | 2025-08-31 | 2025-11-30 | 2025-08-31 | 2025-12-01
11613 | T-18-8th Floor | Complete | RCC | 2025-11-03 | 2025-11-04 | Slab& Beam RCC | 330.8 | 330.8 | CUM | 2025-08-31 | 2025-11-30 | 2025-08-31 | 2025-12-01
8552 | T-14-1st Floor Flat Area | Not Ready | Dado | 2025-08-01 | 2025-08-30 | Dado | 100 | 0 |  | 2025-09-01 |  | 2025-09-26
8624 | T-14-4th Floor Flat Area | Not Ready | Blockwork | 2025-07-30 | 2025-08-22 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-09-01 |  | 2025-09-22
8663 | T-14-5th Floor Flat Area | Not Ready | Railing | 2025-07-30 | 2025-09-02 | Balcony Railing | 100 | 0 |  | 2025-09-01 |  | 2025-10-04
9680 |  | Not Ready |  | 2025-10-30 | 2026-10-13 | Common Area | 100 | 0 |  | 2025-09-01 |  | 2026-08-14
10077 | T-21-Terrace | Complete | Shear Walls/Corewalls Shuttering | 2025-09-28 | 2025-10-03 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-09-01 | 2025-12-04 | 2025-09-05 | 2025-12-10
10595 | T-20-Terrace | Complete |  | 2025-10-07 | 2025-10-20 | 11th Floor Roof | 100 | 100 |  | 2025-09-01 | 2025-09-30 | 2025-09-15 | 2025-11-13
11101 | T-19-10th Floor | Not Ready |  | 2025-10-21 | 2025-11-05 | 9th Floor Roof | 100 | 0 |  | 2025-09-01 |  | 2025-09-13
11157 | T-19-GF Common Area | Not Ready | Waterproofing | 2025-09-18 | 2025-10-11 | Waterproofing | 100 | 0 |  | 2025-09-01 |  | 2025-09-23
11746 | T-18-3rd Floor Flat Area | Not Ready | Plastering | 2025-11-05 | 2025-11-26 | Plastering-Cement | 100 | 0 |  | 2025-09-01 |  | 2025-09-25
11770 | T-18-4th Floor Flat Area | Not Ready | Blockwork | 2025-11-04 | 2025-11-25 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-09-01 |  | 2025-09-21
11809 | T-18-5th Floor Flat Area | Not Ready | Railing | 2025-11-04 | 2025-12-06 | Balcony Railing | 100 | 0 |  | 2025-09-01 |  | 2025-10-04
39707 |  | Complete |  | 2025-09-01 | 2025-09-08 | Core Wall L67-68 | 100 | 100 |  | 2025-09-01 | 2025-09-06 | 2025-09-20 | 2025-09-24
39708 | Tower A - Super Structure - Core Wall High Rise L67-68 | Complete | Core Wall RCC Works | 2025-09-01 | 2025-09-01 | Scaffolding & platform | 100 | 100 | Units | 2025-09-01 | 2025-09-06 | 2025-09-12 | 2025-09-18 | Tower A | Super Structure | L67 | RCC Super Structure | Core Wall RCC Works
41443 |  | Started |  | 2025-05-26 | 2026-04-16 | L31-32 | 100 | 45 |  | 2025-09-01 | 2025-09-01 | 2026-05-08 |  |  |  |  | Finishes | Gypsum Plastering Works
41443 |  | Started |  | 2025-05-26 | 2026-04-16 | L31-32 | 100 | 45 |  | 2025-09-01 | 2025-09-01 | 2026-05-08
41444 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2025-09-01 | 2025-09-03 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 65 |  | 2025-09-01 | 2025-09-01 | 2026-03-27 |  | Tower A | Super Structure | L31 | MEP | FPS 1st Fix - MEP & Finishes
8462 | T-14-9th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-07-31 | 2025-08-05 | AL - Shear Walls/Corewalls Steel | 22 | 22 | MT | 2025-09-02 | 2025-10-06 | 2025-09-04 | 2025-10-18
8535 | T-14-GF Common Area | Not Ready | Toilet flooring | 2025-08-09 | 2025-08-27 | Toilet flooring | 100 | 0 |  | 2025-09-02 |  | 2025-09-21
8600 | T-14-3rd Floor Flat Area | Not Ready | Plastering | 2025-07-31 | 2025-08-23 | Plastering-Cement | 100 | 0 |  | 2025-09-02 |  | 2025-09-23
8666 |  | Not Ready |  | 2025-09-01 | 2026-05-12 | Common Area | 100 | 0 |  | 2025-09-02 |  | 2026-05-13
9518 | T-16-6th Floor | Complete | Slab& Beam Steel & Conduting | 2025-09-23 | 2025-09-26 | Slab& Beam Steel & Conduting | 14 | 14 | MT | 2025-09-02 | 2025-09-23 | 2025-09-05 | 2025-09-25
9617 | T-16-1st Floor Flat Area | Not Ready | Plastering | 2025-09-23 | 2025-11-14 | Plastering-Gypsum | 100 | 0 |  | 2025-09-02 |  | 2025-10-21
10239 | T-21-5th Floor Flat Area | Not Ready | Waterproofing | 2025-10-03 | 2025-11-24 | Waterproofing | 100 | 0 |  | 2025-09-02 |  | 2025-10-21
10592 | T-20-11th Floor | Complete | Shuttering | 2025-09-29 | 2025-10-04 | Slab and Beam Shuttering | 3583 | 3583 | Sqm | 2025-09-02 | 2025-09-26 | 2025-09-08 | 2025-09-29
10628 | T-20-GF Flat Area | Not Ready | Window | 2025-10-07 | 2025-10-29 | Window | 100 | 0 |  | 2025-09-02 |  | 2025-09-24
10666 | T-20-1st Floor Flat Area | Not Ready | 1st Coat Painting | 2025-10-13 | 2026-01-05 | 1st Coat Painting | 100 | 0 |  | 2025-09-02 |  | 2025-11-25
10783 | T-20-6th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-09-29 | 2025-10-21 | Plumbing Pipe Line | 100 | 0 |  | 2025-09-02 |  | 2025-09-24
11159 | T-19-GF Common Area | Not Ready | Plastering | 2025-09-18 | 2025-10-22 | Plastering-Gypsum | 100 | 0 |  | 2025-09-02 |  | 2025-10-04
11615 | T-18-9th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-11-05 | 2025-11-09 | AL - Shear Walls/Corewalls Steel | 20.5 | 20.5 | MT | 2025-09-02 | 2025-12-02 | 2025-09-07 | 2025-12-10
39709 | Tower A - Super Structure - Core Wall High Rise L67-68 | Complete | Core Wall RCC Works | 2025-09-02 | 2025-09-04 | Reinf & Guide shoes fixing | 100 | 100 |  | 2025-09-02 | 2025-09-07 | 2025-09-16 | 2025-09-20 | Tower A | Super Structure | L67 | RCC Super Structure | Core Wall RCC Works
39992 |  | Complete |  | 2025-09-02 | 2025-09-08 | L63-64 | 100 | 100 |  | 2025-09-02 | 2025-09-02 | 2025-09-18 | 2025-09-28
39992 |  | Complete |  | 2025-09-02 | 2025-09-08 | L63-64 | 100 | 100 |  | 2025-09-02 | 2025-09-02 | 2025-09-18 | 2025-09-28 |  |  |  | Finishes | Gypsum Plastering Works
39993 | Tower A - Super Structure - Core & Outer Slab L63-64 | Complete | RCC Works - Vertical | 2025-09-02 | 2025-09-08 | Outer Columns_TA | 100 | 100 | Units | 2025-09-02 | 2025-09-02 | 2025-09-16 | 2025-09-24 | Tower A | Super Structure | L63 | RCC Sub Structure | RCC Works - Vertical
42207 |  | Started |  | 2024-08-10 | 2025-09-19 | Finishes after 1st Fix | 100 | 44 |  | 2025-09-02 | 2025-05-20 | 2025-10-23
42210 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Apartment Area | Started | Flooring & Dado - MEP & Finishes | 2025-09-02 | 2025-09-19 | Flooring & Dado works | 100 | 75.2 | Units | 2025-09-02 | 2025-05-20 | 2025-10-23 |  | Tower A | Super Structure | L7 | Finishes | Flooring & Dado
44047 | Tower A - Super Structure - Finishes & MEP - L7 to L13 | Started | Façade Works - MEP & Finishes | 2025-09-02 | 2025-09-12 | Accessories & Alignment | 100 | 61 | Units | 2025-09-02 | 2025-05-22 | 2025-10-07 |  | Tower A | Super Structure | L7 | Façade | Façade Works
44047 | Tower A - Super Structure - Finishes & MEP - L7 to L13 | Started | Façade Works - MEP & Finishes | 2025-09-02 | 2025-09-12 | Accessories & Alignment | 100 | 61 | Units | 2025-09-02 | 2025-05-22 | 2025-10-07 |  | Tower A | Super Structure | L7
8628 | T-14-4th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-08-01 | 2025-08-19 | Electrical DB Fixing | 100 | 0 |  | 2025-09-03 |  | 2025-09-19
9013 | T-15-8th Floor | Complete | RCC | 2025-08-29 | 2025-08-29 | Slab& Beam RCC | 318 | 318 | CUM | 2025-09-03 | 2025-09-18 | 2025-09-03 | 2025-09-19
9083 | T-15-GF Common Area | Not Ready | Flooring & skirting | 2025-09-04 | 2025-10-19 | Flooring & skirting | 100 | 0 |  | 2025-09-03 |  | 2025-10-18
9098 | T-15-1st Floor Flat Area | Not Ready | Dado | 2025-09-01 | 2025-09-28 | Dado | 100 | 0 |  | 2025-09-03 |  | 2025-09-30
10217 | T-21-4th Floor Flat Area | Not Ready | Toilet flooring | 2025-10-04 | 2025-11-08 | Toilet flooring | 100 | 0 |  | 2025-09-03 |  | 2025-10-07
10714 | T-20-3rd Floor Flat Area | Not Ready | Putty | 2025-10-08 | 2025-12-31 | Putty | 100 | 0 |  | 2025-09-03 |  | 2025-11-27
10733 | T-20-4th Floor Flat Area | Not Ready | Waterproofing | 2025-09-30 | 2025-11-21 | Waterproofing | 100 | 0 |  | 2025-09-03 |  | 2025-10-23
10798 |  | Not Ready |  | 2025-10-09 | 2026-05-02 | Common Area | 100 | 0 |  | 2025-09-03 |  | 2026-03-27
11266 |  | Not Ready |  | 2025-10-23 | 2026-08-19 | Common Area | 100 | 0 |  | 2025-09-03 |  | 2026-06-30
11761 | T-18-3rd Floor Common Area | Not Ready | Plastering | 2025-11-07 | 2025-12-09 | Plastering-Gypsum | 100 | 0 |  | 2025-09-03 |  | 2025-10-07
11774 | T-18-4th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-11-06 | 2025-11-22 | Electrical DB Fixing | 100 | 0 |  | 2025-09-03 |  | 2025-09-21
8464 | T-14-9th Floor | Complete | Conduiting | 2025-08-02 | 2025-08-06 | Conduiting works | 100 | 100 | Units | 2025-09-04 | 2025-10-21 | 2025-09-09 | 2025-10-23
8615 | T-14-3rd Floor Common Area | Not Ready | Plastering | 2025-08-02 | 2025-09-05 | Plastering-Gypsum | 100 | 0 |  | 2025-09-04 |  | 2025-10-08
9170 | T-15-4th Floor Flat Area | Not Ready | Blockwork | 2025-08-30 | 2025-09-20 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-09-04 |  | 2025-09-26
9209 | T-15-5th Floor Flat Area | Not Ready | Railing | 2025-08-30 | 2025-10-01 | Balcony Railing | 100 | 0 |  | 2025-09-04 |  | 2025-10-06
10079 | T-21-Terrace | Complete | Shuttering | 2025-10-01 | 2025-10-07 | Slab and Beam Shuttering | 3264 | 3264 | Sqm | 2025-09-04 | 2025-12-10 | 2025-09-06 | 2025-12-14
10289 | T-21-7th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-10-01 | 2025-10-24 | Plumbing Pipe Line | 100 | 0 |  | 2025-09-04 |  | 2025-09-24
10593 | T-20-11th Floor | Complete | Slab& Beam Steel & Conduting | 2025-10-01 | 2025-10-05 | Slab& Beam Steel & Conduting | 10.8 | 10.8 | MT | 2025-09-04 | 2025-09-29 | 2025-09-08 | 2025-09-29
10787 | T-20-6th Floor Flat Area | Not Ready | Plastering | 2025-10-01 | 2025-11-17 | Plastering-Gypsum | 100 | 0 |  | 2025-09-04 |  | 2025-10-20
11200 | T-19-2nd Floor Flat Area | Not Ready | Plastering | 2025-09-22 | 2025-10-14 | Plastering-Cement | 100 | 0 |  | 2025-09-04 |  | 2025-09-25
11617 | T-18-9th Floor | Complete | Conduiting | 2025-11-07 | 2025-11-10 | Conduiting works | 100 | 100 |  | 2025-09-04 | 2025-12-12 | 2025-09-06 | 2025-12-14
8463 | T-14-9th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-08-04 | 2025-08-08 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-09-05 | 2025-10-16 | 2025-09-10 | 2025-10-23
9015 | T-15-9th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-08-31 | 2025-09-04 | AL - Shear Walls/Corewalls Steel | 24.5 | 24.5 | MT | 2025-09-05 | 2025-09-20 | 2025-09-08 | 2025-09-27
9065 | T-15-GF Flat Area | Not Ready | Toilets False Celing | 2025-09-06 | 2025-09-23 | Toilets-False Celing | 100 | 0 |  | 2025-09-05 |  | 2025-09-22
9146 | T-15-3rd Floor Flat Area | Not Ready | Plastering | 2025-08-31 | 2025-09-22 | Plastering-Cement | 100 | 0 |  | 2025-09-05 |  | 2025-09-27
10338 |  | Not Ready |  | 2025-10-09 | 2026-07-12 | Ninth Floor | 100 | 0 |  | 2025-09-05 |  | 2026-06-10
10339 |  | Not Ready |  | 2025-10-09 | 2026-07-12 | Flat Area | 100 | 0 |  | 2025-09-05 |  | 2026-06-10
10364 |  | Not Ready |  | 2025-10-09 | 2026-07-28 | Tenth Floor | 100 | 0 |  | 2025-09-05 |  | 2026-06-26
10365 |  | Not Ready |  | 2025-10-09 | 2026-07-28 | Flat Area | 100 | 0 |  | 2025-09-05 |  | 2026-06-26
10613 | T-20-Basement Floor | Not Ready | 1st Coat Painting | 2025-09-16 | 2025-10-19 | 1st Coat Painting | 100 | 0 |  | 2025-09-05 |  | 2025-10-06
11086 | T-19-7th Floor | Complete | RCC | 2025-09-19 | 2025-09-20 | Slab& Beam RCC | 340 | 340 | CUM | 2025-09-05 | 2025-10-09 | 2025-09-06 | 2025-10-10
11616 | T-18-9th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-11-08 | 2025-11-12 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-09-05 | 2025-12-08 | 2025-09-08 | 2025-12-14
11666 | T-18-GF Flat Area | Not Ready | Flooring & skirting | 2025-10-27 | 2025-12-01 | Flooring & skirting | 100 | 0 |  | 2025-09-05 |  | 2025-10-09
8581 | T-14-2nd Floor Flat Area | Not Ready | Flooring & skirting | 2025-08-08 | 2025-09-22 | Flooring & skirting | 100 | 0 |  | 2025-09-06 |  | 2025-10-19
9174 | T-15-4th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-09-01 | 2025-09-17 | Electrical DB Fixing | 100 | 0 |  | 2025-09-06 |  | 2025-09-22
9519 | T-16-6th Floor | Complete | RCC | 2025-09-26 | 2025-09-27 | Slab& Beam RCC | 387 | 387 | CUM | 2025-09-06 | 2025-09-26 | 2025-09-06 | 2025-09-27
10080 | T-21-Terrace | Complete | Slab& Beam Steel & Conduting | 2025-10-04 | 2025-10-08 | Slab& Beam Steel & Conduting | 19.5 | 19.5 | MT | 2025-09-06 | 2025-12-12 | 2025-09-11 | 2025-12-15
10293 | T-21-7th Floor Flat Area | Not Ready | Plastering | 2025-10-04 | 2025-11-19 | Plastering-Gypsum | 100 | 0 |  | 2025-09-06 |  | 2025-10-23
11143 | T-19-GF Flat Area | Not Ready | Dado | 2025-09-26 | 2025-10-18 | Dado | 100 | 0 |  | 2025-09-06 |  | 2025-09-29
11215 | T-19-2nd Floor Common Area | Not Ready | Plastering | 2025-09-24 | 2025-10-28 | Plastering-Gypsum | 100 | 0 |  | 2025-09-06 |  | 2025-10-10
11698 | T-18-1st Floor Flat Area | Not Ready | Dado | 2025-11-06 | 2025-12-03 | Dado | 100 | 0 |  | 2025-09-06 |  | 2025-10-04
11794 |  | Not Ready |  | 2025-11-04 | 2026-08-12 | Fifth Floor | 100 | 0 |  | 2025-09-06 |  | 2026-06-13
11795 |  | Not Ready |  | 2025-11-04 | 2026-07-06 | Flat Area | 100 | 0 |  | 2025-09-06 |  | 2026-05-07
41459 |  | Started |  | 2025-05-29 | 2026-04-18 | L32-33 | 100 | 47 |  | 2025-09-06 | 2025-09-06 | 2026-05-09 |  |  |  |  | Finishes | Gypsum Plastering Works
41459 |  | Started |  | 2025-05-29 | 2026-04-18 | L32-33 | 100 | 47 |  | 2025-09-06 | 2025-09-06 | 2026-05-09
41460 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2025-09-06 | 2025-09-09 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 65 |  | 2025-09-06 | 2025-09-06 | 2026-03-28 |  | Tower A | Super Structure | L32 | MEP | FPS 1st Fix - MEP & Finishes
8536 | T-14-GF Common Area | Not Ready | Toilets False Celing | 2025-08-16 | 2025-09-17 | Toilets False Celing | 100 | 0 |  | 2025-09-07 |  | 2025-10-11
9017 | T-15-9th Floor | Complete | Conduiting | 2025-09-02 | 2025-09-05 | Conduiting works | 100 | 100 | Units | 2025-09-07 | 2025-09-30 | 2025-09-08 | 2025-10-02
9161 | T-15-3rd Floor Common Area | Not Ready | Plastering | 2025-09-02 | 2025-10-06 | Plastering-Gypsum | 100 | 0 |  | 2025-09-07 |  | 2025-10-10
9614 | T-16-1st Floor Flat Area | Not Ready | Plastering | 2025-09-29 | 2025-10-22 | Plastering-Cement | 100 | 0 |  | 2025-09-07 |  | 2025-09-28
9638 | T-16-2nd Floor Flat Area | Not Ready | Blockwork | 2025-09-27 | 2025-10-21 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-09-07 |  | 2025-09-29
9677 | T-16-3rd Floor Flat Area | Not Ready | Railing | 2025-09-27 | 2025-11-03 | Balcony Railing | 100 | 0 |  | 2025-09-07 |  | 2025-10-10
10220 | T-21-4th Floor Flat Area | Not Ready | Putty | 2025-10-11 | 2026-01-03 | Putty | 100 | 0 |  | 2025-09-07 |  | 2025-12-03
10629 | T-20-GF Flat Area | Not Ready | Door | 2025-10-13 | 2025-11-06 | Door | 100 | 0 |  | 2025-09-07 |  | 2025-09-28
10712 | T-20-3rd Floor Flat Area | Not Ready |  | 2025-10-10 | 2025-11-14 | Toilets False Celing | 100 | 0 |  | 2025-09-07 |  | 2025-10-11
11224 | T-19-3rd Floor Flat Area | Not Ready | Blockwork | 2025-09-20 | 2025-10-13 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-09-07 |  | 2025-09-28
11263 | T-19-4th Floor Flat Area | Not Ready | Railing | 2025-09-20 | 2025-10-24 | Balcony Railing | 100 | 0 |  | 2025-09-07 |  | 2025-10-11
11614 | T-18-9th Floor | Complete |  | 2025-11-05 | 2025-11-18 | 8th Floor Roof | 100 | 100 |  | 2025-09-07 | 2025-12-02 | 2025-09-18 | 2025-12-25
11680 | T-18-GF Common Area | Not Ready | Dado | 2025-11-04 | 2025-11-25 | Dado | 100 | 0 |  | 2025-09-07 |  | 2025-10-01
8465 | T-14-9th Floor | Complete | Shuttering | 2025-08-07 | 2025-08-11 | Slab and Beam Shuttering | 3605 | 3605 | Sqm | 2025-09-08 | 2025-10-21 | 2025-09-10 | 2025-10-25
8553 | T-14-1st Floor Flat Area | Not Ready | Toilet flooring | 2025-08-09 | 2025-09-12 | Toilet flooring | 100 | 0 |  | 2025-09-08 |  | 2025-10-12
8575 | T-14-2nd Floor Flat Area | Not Ready | Waterproofing | 2025-08-08 | 2025-09-27 | Waterproofing | 100 | 0 |  | 2025-09-08 |  | 2025-10-27
8625 | T-14-4th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-08-07 | 2025-08-30 | Plumbing Pipe Line | 100 | 0 |  | 2025-09-08 |  | 2025-09-29
9016 | T-15-9th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-09-03 | 2025-09-08 | Shear Walls/Corewalls Shuttering | 100 | 100 | Units | 2025-09-08 | 2025-09-25 | 2025-09-12 | 2025-09-30
9081 | T-15-GF Common Area | Not Ready | Toilet flooring | 2025-09-10 | 2025-09-26 | Toilet flooring | 100 | 0 |  | 2025-09-08 |  | 2025-09-25
9220 |  | Not Ready |  | 2025-09-13 | 2026-05-08 | Sixth Floor | 100 | 0 |  | 2025-09-08 |  | 2026-05-04
9221 |  | Not Ready |  | 2025-09-13 | 2026-04-06 | Flat Area | 100 | 0 |  | 2025-09-08 |  | 2026-04-01
9521 | T-16-7th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-09-29 | 2025-10-04 | AL - Shear Walls/Corewalls Steel | 25 | 25 | MT | 2025-09-08 | 2025-09-29 | 2025-09-12 | 2025-10-06
10631 | T-20-GF Flat Area | Not Ready | 1st Coat Painting | 2025-10-15 | 2025-12-05 | 1st Coat Painting | 100 | 0 |  | 2025-09-08 |  | 2025-10-28
11088 | T-19-8th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-09-22 | 2025-09-26 | AL - Shear Walls/Corewalls Steel | 28.4 | 28.4 | MT | 2025-09-08 | 2025-10-11 | 2025-09-12 | 2025-10-17
11618 | T-18-9th Floor | Complete | Shuttering | 2025-11-11 | 2025-11-14 | Slab and Beam Shuttering | 3527 | 3527 | Sqm | 2025-09-08 | 2025-12-12 | 2025-09-12 | 2025-12-18
11771 | T-18-4th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-11-11 | 2025-12-03 | Plumbing Pipe Line | 100 | 0 |  | 2025-09-08 |  | 2025-09-29
42225 |  | Started |  | 2024-08-23 | 2025-09-25 | Finishes after 1st Fix | 100 | 40 |  | 2025-09-08 | 2025-05-15 | 2025-10-23
42228 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Apartment Area | Started | Flooring & Dado - MEP & Finishes | 2025-09-08 | 2025-09-25 | Flooring & Dado works | 100 | 71 | Units | 2025-09-08 | 2025-05-15 | 2025-10-23 |  | Tower A | Super Structure | L8 | Finishes | Flooring & Dado
44050 | Tower A - Super Structure - Finishes & MEP - L13 to L18 | Started | Façade Works - MEP & Finishes | 2025-09-08 | 2025-09-25 | DGU Assembly Installation | 100 | 55 | Units | 2025-09-08 | 2025-05-10 | 2025-09-29 |  | Tower A | Super Structure | L13 | Façade | Façade Works
44051 | Tower A - Super Structure - Finishes & MEP - L13 to L18 | Started | Façade Works - MEP & Finishes | 2025-09-08 | 2025-10-01 | Installation of highly reflective metal sheet | 100 | 55 | Units | 2025-09-08 | 2025-05-15 | 2025-10-03 |  | Tower A | Super Structure | L13 | Façade | Façade Works
44053 | Tower A - Super Structure - Finishes & MEP - L13 to L18 | Started | Façade Works - MEP & Finishes | 2025-09-08 | 2025-09-19 | Fixing of Louvers | 100 | 55 | Units | 2025-09-08 | 2025-05-25 | 2025-09-26 |  | Tower A | Super Structure | L13 | Façade | Façade Works
44053 | Tower A - Super Structure - Finishes & MEP - L13 to L18 | Started | Façade Works - MEP & Finishes | 2025-09-08 | 2025-09-19 | Fixing of Louvers | 100 | 55 | Units | 2025-09-08 | 2025-05-25 | 2025-09-26 |  | Tower A | Super Structure | L13
9021 | T-15-10th Floor | Complete |  | 2025-09-14 | 2025-09-27 | 9th Floor Roof | 100 | 100 |  | 2025-09-09 | 2025-10-13 | 2025-09-22 | 2025-10-27
9127 | T-15-2nd Floor Flat Area | Not Ready | Flooring & skirting | 2025-09-08 | 2025-10-22 | Flooring & skirting | 100 | 0 |  | 2025-09-09 |  | 2025-10-26
9629 | T-16-1st Floor Common Area | Not Ready | Plastering | 2025-10-01 | 2025-11-06 | Plastering-Gypsum | 100 | 0 |  | 2025-09-09 |  | 2025-10-13
9642 | T-16-2nd Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-09-30 | 2025-10-17 | Electrical DB Fixing | 100 | 0 |  | 2025-09-09 |  | 2025-09-26
10082 |  | Not Ready |  | 2025-10-12 | 2025-12-09 | Above Terrace | 100 | 0 |  | 2025-09-09 |  | 2025-11-07
10242 | T-21-5th Floor Flat Area | Not Ready | Dado | 2025-10-11 | 2025-11-10 | Dado | 100 | 0 |  | 2025-09-09 |  | 2025-10-07
10265 | T-21-6th Floor Flat Area | Not Ready | Waterproofing | 2025-10-12 | 2025-11-16 | Waterproofing | 100 | 0 |  | 2025-09-09 |  | 2025-10-13
10304 |  | Not Ready |  | 2025-10-12 | 2026-05-13 | Common Area | 100 | 0 |  | 2025-09-09 |  | 2026-04-09
10594 | T-20-11th Floor | Complete | RCC | 2025-10-05 | 2025-10-06 | Slab& Beam RCC | 321 | 321 | CUM | 2025-09-09 | 2025-09-29 | 2025-09-09 | 2025-09-30
10644 | T-20-GF Common Area | Not Ready | Putty | 2025-10-13 | 2025-11-06 | Putty | 100 | 0 |  | 2025-09-09 |  | 2025-09-30
10784 | T-20-6th Floor Flat Area | Not Ready | Plastering | 2025-10-07 | 2025-10-29 | Plastering-Cement | 100 | 0 |  | 2025-09-09 |  | 2025-10-03
11181 | T-19-1st Floor Flat Area | Not Ready | Flooring & skirting | 2025-09-29 | 2025-11-15 | Flooring & skirting | 100 | 0 |  | 2025-09-09 |  | 2025-10-24
11228 | T-19-3rd Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-09-23 | 2025-10-10 | Electrical DB Fixing | 100 | 0 |  | 2025-09-09 |  | 2025-09-25
11664 | T-18-GF Flat Area | Not Ready | Toilet flooring | 2025-11-06 | 2025-11-22 | Toilet flooring | 100 | 0 |  | 2025-09-09 |  | 2025-09-25
8466 | T-14-9th Floor | Complete | Slab& Beam Steel & Conduting | 2025-08-09 | 2025-08-13 | Slab& Beam Steel & Conduting | 10 | 10 | MT | 2025-09-10 | 2025-10-22 | 2025-09-15 | 2025-10-28
8629 | T-14-4th Floor Flat Area | Not Ready | Plastering | 2025-08-09 | 2025-09-23 | Plastering-Gypsum | 100 | 0 |  | 2025-09-10 |  | 2025-10-26
9099 | T-15-1st Floor Flat Area | Not Ready | Toilet flooring | 2025-09-09 | 2025-10-13 | Toilet flooring | 100 | 0 |  | 2025-09-10 |  | 2025-10-14
9523 | T-16-7th Floor | Complete | Conduiting | 2025-10-01 | 2025-10-05 | Conduiting works | 100 | 100 |  | 2025-09-10 | 2025-10-15 | 2025-09-12 | 2025-10-20
9580 | T-16-GF Flat Area | Not Ready | Waterproofing | 2025-10-01 | 2025-10-24 | Waterproofing | 100 | 0 |  | 2025-09-10 |  | 2025-10-02
10645 | T-20-GF Common Area | Not Ready | Window | 2025-10-15 | 2025-11-08 | Window | 100 | 0 |  | 2025-09-10 |  | 2025-10-02
10736 | T-20-4th Floor Flat Area | Not Ready | Dado | 2025-10-08 | 2025-11-07 | Dado | 100 | 0 |  | 2025-09-10 |  | 2025-10-08
10808 | T-20-7th Floor Flat Area | Not Ready | Blockwork | 2025-10-06 | 2025-10-28 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-09-10 |  | 2025-10-01
10847 | T-20-8th Floor Flat Area | Not Ready | Railing | 2025-10-06 | 2025-11-10 | Balcony Railing | 100 | 0 |  | 2025-09-10 |  | 2025-10-14
11090 | T-19-8th Floor | Complete | Conduiting | 2025-09-24 | 2025-09-27 | Conduiting works | 100 | 100 |  | 2025-09-10 | 2025-10-23 | 2025-09-13 | 2025-10-25
11175 | T-19-1st Floor Flat Area | Not Ready | Waterproofing | 2025-09-29 | 2025-11-20 | Waterproofing | 100 | 0 |  | 2025-09-10 |  | 2025-10-29
11619 | T-18-9th Floor | Complete | Slab& Beam Steel & Conduting | 2025-11-13 | 2025-11-17 | Slab& Beam Steel & Conduting | 10.8 | 10.8 | MT | 2025-09-10 | 2025-12-16 | 2025-09-11 | 2025-12-23
11727 | T-18-2nd Floor Flat Area | Not Ready | Flooring & skirting | 2025-11-12 | 2025-12-26 | Flooring & skirting | 100 | 0 |  | 2025-09-10 |  | 2025-10-27
11775 | T-18-4th Floor Flat Area | Not Ready | Plastering | 2025-11-13 | 2025-12-27 | Plastering-Gypsum | 100 | 0 |  | 2025-09-10 |  | 2025-10-24
9018 | T-15-9th Floor | Complete | Shuttering | 2025-09-06 | 2025-09-11 | Slab and Beam Shuttering | 3715 | 3715 | Sqm | 2025-09-11 | 2025-10-01 | 2025-09-17 | 2025-10-06
9171 | T-15-4th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-09-06 | 2025-09-28 | Plumbing Pipe Line | 100 | 0 |  | 2025-09-11 |  | 2025-10-03
9186 |  | Not Ready |  | 2025-09-16 | 2026-07-13 | Common Area | 100 | 0 |  | 2025-09-11 |  | 2026-07-08
9522 | T-16-7th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-10-03 | 2025-10-07 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-09-11 | 2025-10-06 | 2025-09-17 | 2025-10-14
10218 | T-21-4th Floor Flat Area | Not Ready | Toilets False Celing | 2025-10-13 | 2025-11-17 | Toilets False Celing | 100 | 0 |  | 2025-09-11 |  | 2025-10-15
10290 | T-21-7th Floor Flat Area | Not Ready | Plastering | 2025-10-10 | 2025-11-03 | Plastering-Cement | 100 | 0 |  | 2025-09-11 |  | 2025-10-02
10596 | T-20-Terrace | Complete | AL - Shear Walls/Corewalls Steel | 2025-10-07 | 2025-10-11 | AL - Shear Walls/Corewalls Steel | 20.54 | 20.54 | MT | 2025-09-11 | 2025-09-30 | 2025-09-17 | 2025-10-07
10799 | T-20-6th Floor Common Area | Not Ready | Plastering | 2025-10-09 | 2025-11-13 | Plastering-Gypsum | 100 | 0 |  | 2025-09-11 |  | 2025-10-15
11089 | T-19-8th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-09-25 | 2025-09-29 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-09-11 | 2025-10-18 | 2025-09-16 | 2025-10-25
11760 |  | Not Ready |  | 2025-11-07 | 2026-10-19 | Common Area | 100 | 0 |  | 2025-09-11 |  | 2026-08-19
39127 |  | Not Committed |  | 2023-05-17 |  | Start of Tower B | 100 | 0 |  | 2025-09-11
39194 |  | Not Ready |  | 2024-06-12 | 2024-07-03 | Low Side Material Delivery | 100 | 0 |  | 2025-09-11 |  | 2025-10-01
39208 |  | Not Ready |  | 2024-07-02 | 2024-12-17 | Delivery of High side Materials | 100 | 0 |  | 2025-09-11 |  | 2026-02-25
39219 |  | Not Ready |  | 2024-08-26 | 2024-12-06 | Low Side Installation - Fabrication and Installation of Day Tanks with Fuel Piping (GF) | 100 | 0 |  | 2025-09-11 |  | 2025-12-24
39220 |  | Not Ready |  | 2024-08-26 | 2024-12-27 | Low Side Installation - Fabrication and Installation of DG Stack and Structure (GF) | 100 | 0 |  | 2025-09-11 |  | 2026-01-14
39222 |  | Not Ready |  | 2024-07-02 | 2024-12-17 | Delivery of High side Materials | 100 | 0 |  | 2025-09-11 |  | 2026-02-25
39233 |  | Not Ready |  | 2024-12-16 | 2025-02-14 | Low Side Installation - Installation of Chilled Water Piping (B02) | 100 | 0 |  | 2025-09-11 |  | 2025-11-12
39706 | Tower A - Super Structure - Core Wall High Rise L66-67 | Complete | Core Wall RCC Works | 2025-08-30 | 2025-08-30 | ACS Form Release & jump to next level | 100 | 100 |  | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-11 | Tower A | Super Structure | L66 | RCC Super Structure | Core Wall RCC Works
40045 |  | Not Ready |  | 2025-02-04 | 2026-09-24 | High Side Services | 100 | 0 |  | 2025-09-11 |  | 2026-10-12
40046 |  | Not Committed |  | 2025-02-04 | 2026-07-02 | Elevator (Tower A) | 100 | 0 |  | 2025-09-11 |  | 2026-07-29
40047 |  | Not Committed |  | 2025-02-04 | 2025-06-25 | CTU Elevators Crash Deck at L45 | 100 | 0 |  | 2025-09-11 |  | 2026-02-02
40048 | Tower A - Super Structure - Finishes & MEP - L45 to L46 | Not Ready | CTU Elevators Crash Deck - High Side Services | 2025-02-04 | 2025-02-19 | Crash deck install at L45 (after L45 slab casting) | 100 | 0 |  | 2025-09-11 |  | 2025-09-27 |  | Tower A | Super Structure | L45
40128 |  | Not Committed |  | 2025-07-19 | 2026-08-06 | HVAC at MEP Service Floors | 100 | 0 |  | 2025-09-11 |  | 2026-09-14
40129 | Tower A - Super Structure - Finishes & MEP - MEP Service Floors | Not Ready |  | 2025-07-19 | 2026-02-27 | Staircase Pressurization Fans Installation | 100 | 0 |  | 2025-09-11 |  | 2026-04-15 |  | Tower A | Super Structure
40151 | Tower A - Super Structure - Finishes & MEP - GF to P1 | Not Ready | Partition Wall-Blockwork | 2024-02-19 | 2024-03-06 | Partition Walls | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure | GF
40176 | Tower A - Super Structure - Finishes & MEP - P6 to L7 | Not Ready | Partition Wall-Blockwork | 2024-06-13 | 2024-06-19 | Staircase Area | 100 | 0 |  | 2025-09-11 |  | 2025-09-16 |  | Tower A | Super Structure
40267 | Tower A - Super Structure - Finishes & MEP - L29 to L30 | Not Ready | Partition Wall-Blockwork | 2025-02-14 | 2025-02-21 | Partition Walls | 100 | 0 |  | 2025-09-11 |  | 2025-09-19 |  | Tower A | Super Structure | L29
40345 |  | Not Committed |  | 2025-04-01 | 2025-09-20 | L47-48 | 100 | 0 |  | 2025-09-11 |  | 2025-10-14
40345 |  | Not Committed |  | 2025-04-01 | 2025-09-20 | L47-48 | 100 | 0 |  | 2025-09-11 |  | 2025-10-14 |  |  |  |  | Finishes | Gypsum Plastering Works
40346 | Tower A - Super Structure - Finishes & MEP - L47 to L48 | Not Ready | Partition Wall-Blockwork | 2025-04-01 | 2025-04-17 | De-shuttering & Area clearance | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure | L47
40349 |  | Not Committed |  | 2025-04-28 | 2025-09-29 | L48-49 | 100 | 0 |  | 2025-09-11 |  | 2025-10-23
40349 |  | Not Committed |  | 2025-04-28 | 2025-09-29 | L48-49 | 100 | 0 |  | 2025-09-11 |  | 2025-10-23 |  |  |  |  | Finishes | Gypsum Plastering Works
40350 | Tower A - Super Structure - Finishes & MEP - L48 to L49 | Not Ready | Partition Wall-Blockwork | 2025-04-28 | 2025-05-15 | De-shuttering & Area clearance | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure | L48
40353 |  | Not Committed |  | 2025-05-07 | 2025-10-08 | L49-50 | 100 | 0 |  | 2025-09-11 |  | 2025-10-31
40353 |  | Not Committed |  | 2025-05-07 | 2025-10-08 | L49-50 | 100 | 0 |  | 2025-09-11 |  | 2025-10-31 |  |  |  |  | Finishes | Gypsum Plastering Works
40354 | Tower A - Super Structure - Finishes & MEP - L49 to L50 | Not Ready | Partition Wall-Blockwork | 2025-05-07 | 2025-05-23 | De-shuttering & Area clearance | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure | L49
40357 |  | Not Committed |  | 2025-05-15 | 2025-10-16 | L50-51 | 100 | 0 |  | 2025-09-11 |  | 2025-11-08
40357 |  | Not Committed |  | 2025-05-15 | 2025-10-16 | L50-51 | 100 | 0 |  | 2025-09-11 |  | 2025-11-08 |  |  |  |  | Finishes | Gypsum Plastering Works
40358 | Tower A - Super Structure - Finishes & MEP - L50 to L51 | Not Ready | Partition Wall-Blockwork | 2025-05-15 | 2025-05-31 | De-shuttering & Area clearance | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure | L50
40361 |  | Not Committed |  | 2025-05-23 | 2025-10-25 | L51-52 | 100 | 0 |  | 2025-09-11 |  | 2025-11-17
40361 |  | Not Committed |  | 2025-05-23 | 2025-10-25 | L51-52 | 100 | 0 |  | 2025-09-11 |  | 2025-11-17 |  |  |  |  | Finishes | Gypsum Plastering Works
40362 | Tower A - Super Structure - Finishes & MEP - L51 to L52 | Not Ready | Partition Wall-Blockwork | 2025-05-23 | 2025-06-10 | De-shuttering & Area clearance | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure | L51
40365 |  | Not Committed |  | 2025-05-31 | 2025-11-03 | L52-53 | 100 | 0 |  | 2025-09-11 |  | 2025-11-25
40365 |  | Not Committed |  | 2025-05-31 | 2025-11-03 | L52-53 | 100 | 0 |  | 2025-09-11 |  | 2025-11-25 |  |  |  |  | Finishes | Gypsum Plastering Works
40366 | Tower A - Super Structure - Finishes & MEP - L52 to L53 | Not Ready | Partition Wall-Blockwork | 2025-05-31 | 2025-06-18 | De-shuttering & Area clearance | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure | L52
40369 |  | Not Committed |  | 2025-06-10 | 2025-11-11 | L53-54 | 100 | 0 |  | 2025-09-11 |  | 2025-12-03
40369 |  | Not Committed |  | 2025-06-10 | 2025-11-11 | L53-54 | 100 | 0 |  | 2025-09-11 |  | 2025-12-03 |  |  |  |  | Finishes | Gypsum Plastering Works
40370 | Tower A - Super Structure - Finishes & MEP - L53 to L54 | Forced Ready | Partition Wall-Blockwork | 2025-06-10 | 2025-06-26 | De-shuttering & Area clearance | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure | L53
40373 |  | Not Committed |  | 2025-06-18 | 2025-11-19 | L54-55 | 100 | 0 |  | 2025-09-11 |  | 2025-12-11
40373 |  | Not Committed |  | 2025-06-18 | 2025-11-19 | L54-55 | 100 | 0 |  | 2025-09-11 |  | 2025-12-11 |  |  |  |  | Finishes | Gypsum Plastering Works
40374 | Tower A - Super Structure - Finishes & MEP - L54 to L55 | Not Ready | Partition Wall-Blockwork | 2025-06-18 | 2025-07-04 | De-shuttering & Area clearance | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure | L54
40377 |  | Not Committed |  | 2025-06-26 | 2025-11-27 | L55-56 | 100 | 0 |  | 2025-09-11 |  | 2025-12-19
40377 |  | Not Committed |  | 2025-06-26 | 2025-11-27 | L55-56 | 100 | 0 |  | 2025-09-11 |  | 2025-12-19 |  |  |  |  | Finishes | Gypsum Plastering Works
40378 | Tower A - Super Structure - Finishes & MEP - L55 to L56 | Not Ready | Partition Wall-Blockwork | 2025-06-26 | 2025-07-12 | De-shuttering & Area clearance | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure | L55
40381 |  | Not Committed |  | 2025-07-04 | 2025-12-05 | L56-57 | 100 | 0 |  | 2025-09-11 |  | 2025-12-29
40381 |  | Not Committed |  | 2025-07-04 | 2025-12-05 | L56-57 | 100 | 0 |  | 2025-09-11 |  | 2025-12-29 |  |  |  |  | Finishes | Gypsum Plastering Works
40382 | Tower A - Super Structure - Finishes & MEP - L56 to L57 | Not Ready | Partition Wall-Blockwork | 2025-07-04 | 2025-07-23 | De-shuttering & Area clearance | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure | L56
40385 |  | Not Committed |  | 2025-07-11 | 2025-12-13 | L57-58 | 100 | 0 |  | 2025-09-11 |  | 2026-01-06
40385 |  | Not Committed |  | 2025-07-11 | 2025-12-13 | L57-58 | 100 | 0 |  | 2025-09-11 |  | 2026-01-06 |  |  |  |  | Finishes | Gypsum Plastering Works
40386 | Tower A - Super Structure - Finishes & MEP - L57 to L58 | Not Ready | Partition Wall-Blockwork | 2025-07-11 | 2025-07-31 | De-shuttering & Area clearance | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure | L57
40389 |  | Not Committed |  | 2025-07-31 | 2025-12-22 | L58-59 | 100 | 0 |  | 2025-09-11 |  | 2026-01-14
40389 |  | Not Committed |  | 2025-07-31 | 2025-12-22 | L58-59 | 100 | 0 |  | 2025-09-11 |  | 2026-01-14 |  |  |  |  | Finishes | Gypsum Plastering Works
40390 | Tower A - Super Structure - Finishes & MEP - L58 to L59 | Not Ready | Partition Wall-Blockwork | 2025-07-31 | 2025-08-20 | De-shuttering & Area clearance | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure | L58
40393 |  | Not Committed |  | 2025-08-12 | 2025-12-31 | L59-60 | 100 | 0 |  | 2025-09-11 |  | 2026-01-22
40393 |  | Not Committed |  | 2025-08-12 | 2025-12-31 | L59-60 | 100 | 0 |  | 2025-09-11 |  | 2026-01-22 |  |  |  |  | Finishes | Gypsum Plastering Works
40394 | Tower A - Super Structure - Finishes & MEP - L59 to L60 | Not Ready | Partition Wall-Blockwork | 2025-08-12 | 2025-09-02 | De-shuttering & Area clearance | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure | L59
40397 |  | Not Committed |  | 2025-09-02 | 2026-01-08 | L60-61 | 100 | 0 |  | 2025-09-11 |  | 2026-01-31
40397 |  | Not Committed |  | 2025-09-02 | 2026-01-08 | L60-61 | 100 | 0 |  | 2025-09-11 |  | 2026-01-31 |  |  |  |  | Finishes | Gypsum Plastering Works
40398 | Tower A - Super Structure - Finishes & MEP - L60 to L61 | Not Ready | Partition Wall-Blockwork | 2025-09-02 | 2025-09-19 | De-shuttering & Area clearance | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure | L60
40470 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 | Not Ready | Gypsum Plastering Works | 2024-03-09 | 2024-04-13 | B3 to B2_TA & NTA | 100 | 0 |  | 2025-09-11 |  | 2025-10-17 |  | Tower A | Sub Structure | B3 | Finishes | Gypsum Plastering Works
40470 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 | Not Ready | Gypsum Plastering Works | 2024-03-09 | 2024-04-13 | B3 to B2_TA & NTA | 100 | 0 |  | 2025-09-11 |  | 2025-10-17 |  | Tower A | Sub Structure | B3
40471 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 | Not Ready | Gypsum Plastering Works | 2024-02-21 | 2024-03-27 | B2 to B1_TA & NTA | 100 | 0 |  | 2025-09-11 |  | 2025-10-17 |  | Tower A | Sub Structure | B2 | Finishes | Gypsum Plastering Works
40471 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 | Not Ready | Gypsum Plastering Works | 2024-02-21 | 2024-03-27 | B2 to B1_TA & NTA | 100 | 0 |  | 2025-09-11 |  | 2025-10-17 |  | Tower A | Sub Structure | B2
40472 | Tower A - Sub Structure - Finishes & MEP - B1 to GF | Not Ready | Gypsum Plastering Works | 2024-02-03 | 2024-03-08 | B1 to GF_TA & NTA | 100 | 0 |  | 2025-09-11 |  | 2025-10-17 |  | Tower A | Sub Structure | B1 | Finishes | Gypsum Plastering Works
40472 | Tower A - Sub Structure - Finishes & MEP - B1 to GF | Not Ready | Gypsum Plastering Works | 2024-02-03 | 2024-03-08 | B1 to GF_TA & NTA | 100 | 0 |  | 2025-09-11 |  | 2025-10-17 |  | Tower A | Sub Structure | B1
40476 | Tower A - Super Structure - Finishes & MEP - P3 to P4 | Not Ready | Gypsum Plastering Works | 2024-05-21 | 2024-07-13 | P3 to P4_TA & NTA | 100 | 0 |  | 2025-09-11 |  | 2025-11-05 |  | Tower A | Super Structure |  | Finishes | Gypsum Plastering Works
40493 | Tower A - Super Structure - Finishes & MEP - L19 to L20 | Not Ready | Gypsum Plastering Works | 2024-12-24 | 2025-01-28 | L19-20 | 100 | 0 |  | 2025-09-11 |  | 2025-10-17 |  | Tower A | Super Structure | L19 | Finishes | Gypsum Plastering Works
40493 | Tower A - Super Structure - Finishes & MEP - L19 to L20 | Not Ready | Gypsum Plastering Works | 2024-12-24 | 2025-01-28 | L19-20 | 100 | 0 |  | 2025-09-11 |  | 2025-10-17 |  | Tower A | Super Structure | L19
40496 | Tower A - Super Structure - Finishes & MEP - L22 to L23 | Not Ready | Gypsum Plastering Works | 2025-01-10 | 2025-02-07 | L22-23 | 100 | 0 |  | 2025-09-11 |  | 2025-10-11 |  | Tower A | Super Structure | L22 | Finishes | Gypsum Plastering Works
40496 | Tower A - Super Structure - Finishes & MEP - L22 to L23 | Not Ready | Gypsum Plastering Works | 2025-01-10 | 2025-02-07 | L22-23 | 100 | 0 |  | 2025-09-11 |  | 2025-10-11 |  | Tower A | Super Structure | L22
40497 | Tower A - Super Structure - Finishes & MEP - L23 to L24 | Not Ready | Gypsum Plastering Works | 2025-01-18 | 2025-02-15 | L23-24 | 100 | 0 |  | 2025-09-11 |  | 2025-10-11 |  | Tower A | Super Structure | L23 | Finishes | Gypsum Plastering Works
40497 | Tower A - Super Structure - Finishes & MEP - L23 to L24 | Not Ready | Gypsum Plastering Works | 2025-01-18 | 2025-02-15 | L23-24 | 100 | 0 |  | 2025-09-11 |  | 2025-10-11 |  | Tower A | Super Structure | L23
40498 | Tower A - Super Structure - Finishes & MEP - L24 to L25 | Not Ready | Gypsum Plastering Works | 2025-01-27 | 2025-02-24 | L24-25 | 100 | 0 |  | 2025-09-11 |  | 2025-10-11 |  | Tower A | Super Structure | L24 | Finishes | Gypsum Plastering Works
40498 | Tower A - Super Structure - Finishes & MEP - L24 to L25 | Not Ready | Gypsum Plastering Works | 2025-01-27 | 2025-02-24 | L24-25 | 100 | 0 |  | 2025-09-11 |  | 2025-10-11 |  | Tower A | Super Structure | L24
40499 | Tower A - Super Structure - Finishes & MEP - L25 to L26 | Not Ready | Gypsum Plastering Works | 2025-02-04 | 2025-03-04 | L25-26 | 100 | 0 |  | 2025-09-11 |  | 2025-10-11 |  | Tower A | Super Structure | L25 | Finishes | Gypsum Plastering Works
40499 | Tower A - Super Structure - Finishes & MEP - L25 to L26 | Not Ready | Gypsum Plastering Works | 2025-02-04 | 2025-03-04 | L25-26 | 100 | 0 |  | 2025-09-11 |  | 2025-10-11 |  | Tower A | Super Structure | L25
40500 | Tower A - Super Structure - Finishes & MEP - L26 to L27 | Not Ready | Gypsum Plastering Works | 2025-02-12 | 2025-03-12 | L26-27 | 100 | 0 |  | 2025-09-11 |  | 2025-10-11 |  | Tower A | Super Structure | L26 | Finishes | Gypsum Plastering Works
40500 | Tower A - Super Structure - Finishes & MEP - L26 to L27 | Not Ready | Gypsum Plastering Works | 2025-02-12 | 2025-03-12 | L26-27 | 100 | 0 |  | 2025-09-11 |  | 2025-10-11 |  | Tower A | Super Structure | L26
40501 | Tower A - Super Structure - Finishes & MEP - L27 to L28 | Not Ready | Gypsum Plastering Works | 2025-02-20 | 2025-03-21 | L27-28 | 100 | 0 |  | 2025-09-11 |  | 2025-10-11 |  | Tower A | Super Structure | L27 | Finishes | Gypsum Plastering Works
40501 | Tower A - Super Structure - Finishes & MEP - L27 to L28 | Not Ready | Gypsum Plastering Works | 2025-02-20 | 2025-03-21 | L27-28 | 100 | 0 |  | 2025-09-11 |  | 2025-10-11 |  | Tower A | Super Structure | L27
40502 | Tower A - Super Structure - Finishes & MEP - L28 to L29 | Not Ready | Gypsum Plastering Works | 2025-02-28 | 2025-03-29 | L28-29 | 100 | 0 |  | 2025-09-11 |  | 2025-10-11 |  | Tower A | Super Structure | L28 | Finishes | Gypsum Plastering Works
40502 | Tower A - Super Structure - Finishes & MEP - L28 to L29 | Not Ready | Gypsum Plastering Works | 2025-02-28 | 2025-03-29 | L28-29 | 100 | 0 |  | 2025-09-11 |  | 2025-10-11 |  | Tower A | Super Structure | L28
40505 | Tower A - Super Structure - Finishes & MEP - L31 to L32 | Not Ready | Gypsum Plastering Works | 2025-04-25 | 2025-05-19 | L31-32 | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | L31 | Finishes | Gypsum Plastering Works
40505 | Tower A - Super Structure - Finishes & MEP - L31 to L32 | Not Ready | Gypsum Plastering Works | 2025-04-25 | 2025-05-19 | L31-32 | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | L31
40506 | Tower A - Super Structure - Finishes & MEP - L32 to L33 | Not Ready | Gypsum Plastering Works | 2025-05-05 | 2025-05-27 | L32-33 | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | L32 | Finishes | Gypsum Plastering Works
40506 | Tower A - Super Structure - Finishes & MEP - L32 to L33 | Not Ready | Gypsum Plastering Works | 2025-05-05 | 2025-05-27 | L32-33 | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | L32
40507 | Tower A - Super Structure - Finishes & MEP - L33 to L34 | Not Ready | Gypsum Plastering Works | 2025-05-13 | 2025-06-04 | L33-34 | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | L33 | Finishes | Gypsum Plastering Works
40507 | Tower A - Super Structure - Finishes & MEP - L33 to L34 | Not Ready | Gypsum Plastering Works | 2025-05-13 | 2025-06-04 | L33-34 | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | L33
40508 | Tower A - Super Structure - Finishes & MEP - L34 to L35 | Not Ready | Gypsum Plastering Works | 2025-05-21 | 2025-06-13 | L34-35 | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | L34 | Finishes | Gypsum Plastering Works
40508 | Tower A - Super Structure - Finishes & MEP - L34 to L35 | Not Ready | Gypsum Plastering Works | 2025-05-21 | 2025-06-13 | L34-35 | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | L34
40509 | Tower A - Super Structure - Finishes & MEP - L35 to L36 | Not Ready | Gypsum Plastering Works | 2025-05-29 | 2025-06-21 | L35-36 | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | L35 | Finishes | Gypsum Plastering Works
40509 | Tower A - Super Structure - Finishes & MEP - L35 to L36 | Not Ready | Gypsum Plastering Works | 2025-05-29 | 2025-06-21 | L35-36 | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | L35
40510 | Tower A - Super Structure - Finishes & MEP - L36 to L37 | Not Ready | Gypsum Plastering Works | 2025-06-06 | 2025-06-30 | L36-37 | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | L36 | Finishes | Gypsum Plastering Works
40510 | Tower A - Super Structure - Finishes & MEP - L36 to L37 | Not Ready | Gypsum Plastering Works | 2025-06-06 | 2025-06-30 | L36-37 | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | L36
40511 | Tower A - Super Structure - Finishes & MEP - L37 to L38 | Not Ready | Gypsum Plastering Works | 2025-06-16 | 2025-07-08 | L37-38 | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | L37 | Finishes | Gypsum Plastering Works
40511 | Tower A - Super Structure - Finishes & MEP - L37 to L38 | Not Ready | Gypsum Plastering Works | 2025-06-16 | 2025-07-08 | L37-38 | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | L37
40512 | Tower A - Super Structure - Finishes & MEP - L38 to L39 | Not Ready | Gypsum Plastering Works | 2025-06-24 | 2025-07-17 | L38-39 | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | L38 | Finishes | Gypsum Plastering Works
40512 | Tower A - Super Structure - Finishes & MEP - L38 to L39 | Not Ready | Gypsum Plastering Works | 2025-06-24 | 2025-07-17 | L38-39 | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | L38
40513 | Tower A - Super Structure - Finishes & MEP - L39 to L40 | Not Ready | Gypsum Plastering Works | 2025-07-02 | 2025-07-26 | L39-40 | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | L39 | Finishes | Gypsum Plastering Works
40513 | Tower A - Super Structure - Finishes & MEP - L39 to L40 | Not Ready | Gypsum Plastering Works | 2025-07-02 | 2025-07-26 | L39-40 | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | L39
40514 | Tower A - Super Structure - Finishes & MEP - L40 to L41 | Not Ready | Gypsum Plastering Works | 2025-07-10 | 2025-08-06 | L40-41 | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | L40 | Finishes | Gypsum Plastering Works
40514 | Tower A - Super Structure - Finishes & MEP - L40 to L41 | Not Ready | Gypsum Plastering Works | 2025-07-10 | 2025-08-06 | L40-41 | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | L40
40515 | Tower A - Super Structure - Finishes & MEP - L41 to L42 | Not Ready | Gypsum Plastering Works | 2025-07-25 | 2025-08-21 | L41-42 | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | L41 | Finishes | Gypsum Plastering Works
40515 | Tower A - Super Structure - Finishes & MEP - L41 to L42 | Not Ready | Gypsum Plastering Works | 2025-07-25 | 2025-08-21 | L41-42 | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | L41
40516 | Tower A - Super Structure - Finishes & MEP - L42 to L43 | Not Ready | Gypsum Plastering Works | 2025-08-09 | 2025-09-05 | L42-43 | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | L42 | Finishes | Gypsum Plastering Works
40516 | Tower A - Super Structure - Finishes & MEP - L42 to L43 | Not Ready | Gypsum Plastering Works | 2025-08-09 | 2025-09-05 | L42-43 | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | L42
40517 | Tower A - Super Structure - Finishes & MEP - L43 to L44 | Not Ready | Gypsum Plastering Works | 2025-08-22 | 2025-09-16 | L43-44 | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | L43 | Finishes | Gypsum Plastering Works
40517 | Tower A - Super Structure - Finishes & MEP - L43 to L44 | Not Ready | Gypsum Plastering Works | 2025-08-22 | 2025-09-16 | L43-44 | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | L43
40594 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2024-03-07 | 2024-03-30 | PHE 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Sub Structure | B3
40595 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2024-03-07 | 2024-03-23 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Sub Structure | B3 | MEP | Electrical 1st Fixes
40597 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | HVAC Ducting - MEP & Finishes | 2024-03-13 | 2024-03-30 | HVAC Ducting/ Fan Installations | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Sub Structure | B3 | MEP | HVAC Ducting
40598 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | Hume Pipe Laying & Alied Ground Works - MEP & Finishes | 2024-03-01 | 2024-04-05 | Hume pipe laying & allied ground works | 100 | 0 |  | 2025-09-11 |  | 2025-10-17 |  | Tower A | Sub Structure | B3
40607 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2024-03-01 | 2024-03-04 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  | Tower A | Sub Structure | B3 | MEP | Electrical 1st Fixes
40622 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2024-02-13 | 2024-02-15 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  | Tower A | Sub Structure | B2 | MEP | Electrical 1st Fixes
40637 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2024-02-19 | 2024-03-12 | PHE 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Sub Structure | B2
40638 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2024-02-19 | 2024-03-06 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Sub Structure | B2 | MEP | Electrical 1st Fixes
40640 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | HVAC Ducting - MEP & Finishes | 2024-02-24 | 2024-03-12 | HVAC Ducting/ Fan Installations | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Sub Structure | B2 | MEP | HVAC Ducting
40649 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2024-03-09 | 2024-03-12 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  | Tower A | Sub Structure | B1 | MEP | Electrical 1st Fixes
40664 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2024-03-13 | 2024-04-17 | PHE 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-09-11 |  | 2025-10-17 |  | Tower A | Sub Structure | B1
40665 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2024-03-13 | 2024-04-17 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-10-17 |  | Tower A | Sub Structure | B1 | MEP | Electrical 1st Fixes
40667 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | HVAC Ducting - MEP & Finishes | 2024-03-19 | 2024-04-05 | HVAC Ducting/ Fan Installations | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Sub Structure | B1 | MEP | HVAC Ducting
40691 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2024-04-12 | 2024-05-06 | PHE 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | GF
40692 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2024-04-12 | 2024-04-29 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure | GF | MEP | Electrical 1st Fixes
40694 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | HVAC Ducting - MEP & Finishes | 2024-04-18 | 2024-05-06 | HVAC Ducting/ Fan Installations | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure | GF | MEP | HVAC Ducting
40721 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2024-04-18 | 2024-05-11 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure |  | MEP | FPS 1st Fix - MEP & Finishes
40722 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2024-04-18 | 2024-05-11 | PHE 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure
40723 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2024-04-18 | 2024-05-06 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure |  | MEP | Electrical 1st Fixes
40725 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | HVAC Ducting - MEP & Finishes | 2024-04-24 | 2024-05-11 | HVAC Ducting/ Fan Installations | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure |  | MEP | HVAC Ducting
40734 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2024-04-24 | 2024-04-26 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  | Tower A | Super Structure |  | MEP | Electrical 1st Fixes
40749 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2024-04-30 | 2024-05-23 | PHE 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure
40750 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2024-04-30 | 2024-05-17 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure |  | MEP | Electrical 1st Fixes
40752 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | HVAC Ducting - MEP & Finishes | 2024-05-07 | 2024-05-23 | HVAC Ducting/ Fan Installations | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure |  | MEP | HVAC Ducting
40774 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | Ceiling Painting/ PT Marking - MEP & Finishes | 2024-05-13 | 2024-05-17 | Ceiling Painting/ PT Marking | 100 | 0 |  | 2025-09-11 |  | 2025-09-16 |  | Tower A | Super Structure |  | Finishes | Ceiling Painting/ PT Marking
40856 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2024-06-29 | 2024-07-25 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure |  | MEP | FPS 1st Fix - MEP & Finishes
40858 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2024-06-29 | 2024-07-18 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure |  | MEP | Electrical 1st Fixes
40860 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | HVAC Ducting - MEP & Finishes | 2024-07-05 | 2024-07-25 | HVAC Ducting/ Fan Installations | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure |  | MEP | HVAC Ducting
40867 |  | Not Committed |  | 2024-02-19 | 2024-06-04 | B2-GF-L7 | 100 | 0 |  | 2025-09-11 |  | 2025-12-29
40868 | Tower A - Super Structure - Finishes & MEP - B3 to L7 | Not Ready |  | 2024-02-19 | 2024-03-12 | FHR Shaft Risers | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | B3
40870 | Tower A - Super Structure - Finishes & MEP - B3 to L7 | Not Ready |  | 2024-02-19 | 2024-04-11 | Domestic Water & Flushing Riser in Plumbing Shaft | 100 | 0 |  | 2025-09-11 |  | 2025-11-05 |  | Tower A | Super Structure | B3
40872 | Tower A - Super Structure - Finishes & MEP - B3 to L7 | Not Ready |  | 2024-02-19 | 2024-03-23 | Shaft Cable Tray in Electrical Shaft | 100 | 0 |  | 2025-09-11 |  | 2025-10-17 |  | Tower A | Super Structure | B3
40876 |  | Not Committed |  | 2024-08-12 | 2024-12-07 | L15-25 | 100 | 0 |  | 2025-09-11 |  | 2025-12-29
40876 |  | Not Committed |  | 2024-08-12 | 2024-12-07 | L15-25 | 100 | 0 |  | 2025-09-11 |  | 2025-12-29
40877 | Tower A - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2024-08-12 | 2024-09-07 | FHR Shaft Risers | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | L15
40879 | Tower A - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2024-08-12 | 2024-10-09 | Domestic Water & Flushing Riser in Plumbing Shaft | 100 | 0 |  | 2025-09-11 |  | 2025-11-05 |  | Tower A | Super Structure | L15
40881 | Tower A - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2024-08-12 | 2024-09-20 | Shaft Cable Tray in Electrical Shaft | 100 | 0 |  | 2025-09-11 |  | 2025-10-17 |  | Tower A | Super Structure | L15
40887 | Tower A - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2024-06-04 | 2024-07-30 | FHC & Accessories fixing | 100 | 0 |  | 2025-09-11 |  | 2025-11-05 |  | Tower A | Super Structure | L7
40890 | Tower A - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2024-05-11 | 2024-06-14 | Shaft Cable Tray in Electrical Shaft | 100 | 0 |  | 2025-09-11 |  | 2025-10-17 |  | Tower A | Super Structure | L7
40893 | Tower A - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2024-06-04 | 2024-07-30 | HVAC Shaft Ducting | 100 | 0 |  | 2025-09-11 |  | 2025-11-05 |  | Tower A | Super Structure | L7 | MEP | HVAC Grill Fixing
40894 |  | Not Committed |  | 2024-11-07 | 2025-02-08 | L25-35 | 100 | 0 |  | 2025-09-11 |  | 2025-12-16
40894 |  | Not Committed |  | 2024-11-07 | 2025-02-08 | L25-35 | 100 | 0 |  | 2025-09-11 |  | 2025-12-16
40895 | Tower A - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2024-11-07 | 2024-11-29 | FHR Shaft Risers | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | L25
40897 | Tower A - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2024-11-07 | 2024-12-30 | Domestic Water & Flushing Riser in Plumbing Shaft | 100 | 0 |  | 2025-09-11 |  | 2025-11-05 |  | Tower A | Super Structure | L25
40899 | Tower A - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2024-11-07 | 2024-12-11 | Shaft Cable Tray in Electrical Shaft | 100 | 0 |  | 2025-09-11 |  | 2025-10-17 |  | Tower A | Super Structure | L25
40903 |  | Not Committed |  | 2025-02-04 | 2025-05-09 | L35-45 | 100 | 0 |  | 2025-09-11 |  | 2025-12-16
40903 |  | Not Committed |  | 2025-02-04 | 2025-05-09 | L35-45 | 100 | 0 |  | 2025-09-11 |  | 2025-12-16
40904 | Tower A - Super Structure - Finishes & MEP - L35 to L45 | Not Ready |  | 2025-02-04 | 2025-02-26 | FHR Shaft Risers | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | L35
40906 | Tower A - Super Structure - Finishes & MEP - L35 to L45 | Not Ready |  | 2025-02-04 | 2025-03-28 | Domestic Water & Flushing Riser in Plumbing Shaft | 100 | 0 |  | 2025-09-11 |  | 2025-11-05 |  | Tower A | Super Structure | L35
40908 | Tower A - Super Structure - Finishes & MEP - L35 to L45 | Not Ready |  | 2025-02-04 | 2025-03-10 | Shaft Cable Tray in Electrical Shaft | 100 | 0 |  | 2025-09-11 |  | 2025-10-17 |  | Tower A | Super Structure | L35
40912 |  | Not Committed |  | 2025-05-31 | 2025-09-26 | L45-55 | 100 | 0 |  | 2025-09-11 |  | 2025-12-16
40912 |  | Not Committed |  | 2025-05-31 | 2025-09-26 | L45-55 | 100 | 0 |  | 2025-09-11 |  | 2025-12-16
40913 | Tower A - Super Structure - Finishes & MEP - L45 to L55 | Not Ready |  | 2025-05-31 | 2025-06-24 | FHR Shaft Risers | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower A | Super Structure | L45
40915 | Tower A - Super Structure - Finishes & MEP - L45 to L55 | Not Ready |  | 2025-05-31 | 2025-07-25 | Domestic Water & Flushing Riser in Plumbing Shaft | 100 | 0 |  | 2025-09-11 |  | 2025-11-05 |  | Tower A | Super Structure | L45
40917 | Tower A - Super Structure - Finishes & MEP - L45 to L55 | Not Ready |  | 2025-05-31 | 2025-07-05 | Shaft Cable Tray in Electrical Shaft | 100 | 0 |  | 2025-09-11 |  | 2025-10-17 |  | Tower A | Super Structure | L45
41061 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2024-06-18 | 2024-06-20 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  | Tower A | Super Structure | L7 | MEP | Electrical 1st Fixes
41077 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2024-07-01 | 2024-07-03 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  | Tower A | Super Structure | L8 | MEP | Electrical 1st Fixes
41093 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2024-07-25 | 2024-07-27 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  | Tower A | Super Structure | L9 | MEP | Electrical 1st Fixes
41109 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2024-08-29 | 2024-08-31 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  | Tower A | Super Structure | L10 | MEP | Electrical 1st Fixes
41125 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2024-09-04 | 2024-09-07 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  | Tower A | Super Structure | L11 | MEP | Electrical 1st Fixes
41141 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2024-10-10 | 2024-10-14 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  | Tower A | Super Structure | L12 | MEP | Electrical 1st Fixes
41157 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2024-10-16 | 2024-10-18 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  | Tower A | Super Structure | L13 | MEP | Electrical 1st Fixes
41173 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2024-11-22 | 2024-11-25 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  | Tower A | Super Structure | L14 | MEP | Electrical 1st Fixes
41189 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2024-12-28 | 2024-12-31 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  | Tower A | Super Structure | L15 | MEP | Electrical 1st Fixes
41205 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-01-06 | 2025-01-08 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  | Tower A | Super Structure | L16 | MEP | Electrical 1st Fixes
41221 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-01-10 | 2025-01-13 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  | Tower A | Super Structure | L17 | MEP | Electrical 1st Fixes
41237 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-01-17 | 2025-01-20 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  | Tower A | Super Structure | L18 | MEP | Electrical 1st Fixes
41253 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-01-24 | 2025-01-27 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  | Tower A | Super Structure | L19 | MEP | Electrical 1st Fixes
41269 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-01-31 | 2025-02-03 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  | Tower A | Super Structure | L20 | MEP | Electrical 1st Fixes
41285 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-02-10 | 2025-02-12 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  | Tower A | Super Structure | L21 | MEP | Electrical 1st Fixes
41301 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-02-17 | 2025-02-19 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  | Tower A | Super Structure | L22 | MEP | Electrical 1st Fixes
41317 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-02-24 | 2025-02-26 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  | Tower A | Super Structure | L23 | MEP | Electrical 1st Fixes
41333 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-03-01 | 2025-03-04 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  | Tower A | Super Structure | L24 | MEP | Electrical 1st Fixes
41349 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-03-07 | 2025-03-10 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  | Tower A | Super Structure | L25 | MEP | Electrical 1st Fixes
41365 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-03-17 | 2025-03-19 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  | Tower A | Super Structure | L26 | MEP | Electrical 1st Fixes
41381 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-03-26 | 2025-03-28 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  | Tower A | Super Structure | L27 | MEP | Electrical 1st Fixes
41397 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-08-01 | 2025-08-06 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  | Tower A | Super Structure | L28 | MEP | Electrical 1st Fixes
41413 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-08-11 | 2025-08-14 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  | Tower A | Super Structure | L29 | MEP | Electrical 1st Fixes
41429 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-08-21 | 2025-08-25 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  | Tower A | Super Structure | L30 | MEP | Electrical 1st Fixes
41445 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-09-01 | 2025-09-04 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  | Tower A | Super Structure | L31 | MEP | Electrical 1st Fixes
41461 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-09-06 | 2025-09-10 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  | Tower A | Super Structure | L32 | MEP | Electrical 1st Fixes
42457 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2024-12-20 | 2025-01-07 | Wet Area Waterproofing | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure | L21
42673 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2025-05-05 | 2025-05-21 | Wet Area Waterproofing | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure | L33
42690 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2025-05-13 | 2025-05-20 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2025-09-11 |  | 2025-09-19 |  | Tower A | Super Structure | L34
42691 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2025-05-13 | 2025-05-29 | Wet Area Waterproofing | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure | L34
42704 |  | Not Committed |  | 2025-05-21 | 2026-07-25 | L35-36 (Refuge) | 100 | 0 |  | 2025-09-11 |  | 2026-07-17
42705 |  | Not Committed |  | 2025-05-21 | 2025-06-19 | MEP 1st Fixes | 100 | 0 |  | 2025-09-11 |  | 2025-10-11
42706 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2025-05-21 | 2025-05-28 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-09-11 |  | 2025-09-19 |  | Tower A | Super Structure | L35 | MEP | FPS 1st Fix - MEP & Finishes
42707 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-05-21 | 2025-05-26 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2025-09-11 |  | 2025-09-16 |  | Tower A | Super Structure | L35 | MEP | Electrical 1st Fixes
42708 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2025-05-21 | 2025-05-28 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2025-09-11 |  | 2025-09-19 |  | Tower A | Super Structure | L35
42709 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2025-05-21 | 2025-06-06 | Wet Area Waterproofing | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure | L35
42722 |  | Not Committed |  | 2025-05-29 | 2026-07-21 | L36-37 | 100 | 0 |  | 2025-09-11 |  | 2026-07-15
42722 |  | Not Committed |  | 2025-05-29 | 2026-07-21 | L36-37 | 100 | 0 |  | 2025-09-11 |  | 2026-07-15 |  |  |  |  | Finishes | Gypsum Plastering Works
42723 |  | Not Committed |  | 2025-05-29 | 2025-06-27 | MEP 1st Fixes | 100 | 0 |  | 2025-09-11 |  | 2025-10-11
42724 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2025-05-29 | 2025-06-05 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-09-11 |  | 2025-09-19 |  | Tower A | Super Structure | L36 | MEP | FPS 1st Fix - MEP & Finishes
42725 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-05-29 | 2025-06-03 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2025-09-11 |  | 2025-09-16 |  | Tower A | Super Structure | L36 | MEP | Electrical 1st Fixes
42726 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2025-05-29 | 2025-06-05 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2025-09-11 |  | 2025-09-19 |  | Tower A | Super Structure | L36
42727 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2025-05-29 | 2025-06-16 | Wet Area Waterproofing | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure | L36
42740 |  | Not Committed |  | 2025-06-06 | 2026-08-01 | L37-38 | 100 | 0 |  | 2025-09-11 |  | 2026-07-22
42740 |  | Not Committed |  | 2025-06-06 | 2026-08-01 | L37-38 | 100 | 0 |  | 2025-09-11 |  | 2026-07-22 |  |  |  |  | Finishes | Gypsum Plastering Works
42741 |  | Not Committed |  | 2025-06-06 | 2025-07-05 | MEP 1st Fixes | 100 | 0 |  | 2025-09-11 |  | 2025-10-11
42742 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2025-06-06 | 2025-06-14 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-09-11 |  | 2025-09-19 |  | Tower A | Super Structure | L37 | MEP | FPS 1st Fix - MEP & Finishes
42743 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-06-06 | 2025-06-12 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2025-09-11 |  | 2025-09-16 |  | Tower A | Super Structure | L37 | MEP | Electrical 1st Fixes
42744 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2025-06-06 | 2025-06-14 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2025-09-11 |  | 2025-09-19 |  | Tower A | Super Structure | L37
42745 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2025-06-06 | 2025-06-24 | Wet Area Waterproofing | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure | L37
42758 |  | Not Committed |  | 2025-06-16 | 2026-08-01 | L38-39 | 100 | 0 |  | 2025-09-11 |  | 2026-07-22
42758 |  | Not Committed |  | 2025-06-16 | 2026-08-01 | L38-39 | 100 | 0 |  | 2025-09-11 |  | 2026-07-22 |  |  |  |  | Finishes | Gypsum Plastering Works
42759 |  | Not Committed |  | 2025-06-16 | 2025-07-15 | MEP 1st Fixes | 100 | 0 |  | 2025-09-11 |  | 2025-10-11
42760 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2025-06-16 | 2025-06-23 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-09-11 |  | 2025-09-19 |  | Tower A | Super Structure | L38 | MEP | FPS 1st Fix - MEP & Finishes
42761 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-06-16 | 2025-06-20 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2025-09-11 |  | 2025-09-16 |  | Tower A | Super Structure | L38 | MEP | Electrical 1st Fixes
42762 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2025-06-16 | 2025-06-23 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2025-09-11 |  | 2025-09-19 |  | Tower A | Super Structure | L38
42763 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2025-06-16 | 2025-07-02 | Wet Area Waterproofing | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure | L38
42776 |  | Not Committed |  | 2025-06-24 | 2026-08-01 | L39-40 | 100 | 0 |  | 2025-09-11 |  | 2026-07-22
42776 |  | Not Committed |  | 2025-06-24 | 2026-08-01 | L39-40 | 100 | 0 |  | 2025-09-11 |  | 2026-07-22 |  |  |  |  | Finishes | Gypsum Plastering Works
42777 |  | Not Committed |  | 2025-06-24 | 2025-07-24 | MEP 1st Fixes | 100 | 0 |  | 2025-09-11 |  | 2025-10-11
42778 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2025-06-24 | 2025-07-01 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-09-11 |  | 2025-09-19 |  | Tower A | Super Structure | L39 | MEP | FPS 1st Fix - MEP & Finishes
42779 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-06-24 | 2025-06-28 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2025-09-11 |  | 2025-09-16 |  | Tower A | Super Structure | L39 | MEP | Electrical 1st Fixes
42780 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2025-06-24 | 2025-07-01 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2025-09-11 |  | 2025-09-19 |  | Tower A | Super Structure | L39
42781 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2025-06-24 | 2025-07-10 | Wet Area Waterproofing | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure | L39
42794 |  | Not Committed |  | 2025-07-02 | 2026-08-12 | L40-41 | 100 | 0 |  | 2025-09-11 |  | 2026-07-29
42794 |  | Not Committed |  | 2025-07-02 | 2026-08-12 | L40-41 | 100 | 0 |  | 2025-09-11 |  | 2026-07-29 |  |  |  |  | Finishes | Gypsum Plastering Works
42795 |  | Not Committed |  | 2025-07-02 | 2025-08-08 | MEP 1st Fixes | 100 | 0 |  | 2025-09-11 |  | 2025-10-11
42796 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2025-07-02 | 2025-07-09 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-09-11 |  | 2025-09-19 |  | Tower A | Super Structure | L40 | MEP | FPS 1st Fix - MEP & Finishes
42797 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-07-02 | 2025-07-07 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2025-09-11 |  | 2025-09-16 |  | Tower A | Super Structure | L40 | MEP | Electrical 1st Fixes
42798 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2025-07-02 | 2025-07-09 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2025-09-11 |  | 2025-09-19 |  | Tower A | Super Structure | L40
42799 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2025-07-02 | 2025-07-19 | Wet Area Waterproofing | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure | L40
42812 |  | Not Committed |  | 2025-07-10 | 2026-08-12 | L41-42 | 100 | 0 |  | 2025-09-11 |  | 2026-07-29
42812 |  | Not Committed |  | 2025-07-10 | 2026-08-12 | L41-42 | 100 | 0 |  | 2025-09-11 |  | 2026-07-29 |  |  |  |  | Finishes | Gypsum Plastering Works
42813 |  | Not Committed |  | 2025-07-10 | 2025-08-23 | MEP 1st Fixes | 100 | 0 |  | 2025-09-11 |  | 2025-10-11
42814 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2025-07-10 | 2025-07-18 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-09-11 |  | 2025-09-19 |  | Tower A | Super Structure | L41 | MEP | FPS 1st Fix - MEP & Finishes
42815 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-07-10 | 2025-07-16 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2025-09-11 |  | 2025-09-16 |  | Tower A | Super Structure | L41 | MEP | Electrical 1st Fixes
42816 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2025-07-10 | 2025-07-18 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2025-09-11 |  | 2025-09-19 |  | Tower A | Super Structure | L41
42817 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2025-07-10 | 2025-07-30 | Wet Area Waterproofing | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure | L41
42830 |  | Not Committed |  | 2025-07-25 | 2026-08-12 | L42-43 (Refuge) | 100 | 0 |  | 2025-09-11 |  | 2026-07-29
42831 |  | Not Committed |  | 2025-07-25 | 2025-10-11 | MEP 1st Fixes | 100 | 0 |  | 2025-09-11 |  | 2025-11-13
42832 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2025-07-25 | 2025-08-02 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-09-11 |  | 2025-09-19 |  | Tower A | Super Structure | L42 | MEP | FPS 1st Fix - MEP & Finishes
42833 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-07-25 | 2025-07-31 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2025-09-11 |  | 2025-09-16 |  | Tower A | Super Structure | L42 | MEP | Electrical 1st Fixes
42834 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2025-07-25 | 2025-08-02 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2025-09-11 |  | 2025-09-19 |  | Tower A | Super Structure | L42
42848 |  | Not Committed |  | 2025-08-09 | 2026-08-25 | L43-44 | 100 | 0 |  | 2025-09-11 |  | 2026-08-05
42848 |  | Not Committed |  | 2025-08-09 | 2026-08-25 | L43-44 | 100 | 0 |  | 2025-09-11 |  | 2026-08-05 |  |  |  |  | Finishes | Gypsum Plastering Works
42849 |  | Not Committed |  | 2025-08-09 | 2025-09-04 | MEP 1st Fixes | 100 | 0 |  | 2025-09-11 |  | 2025-10-01
42850 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2025-08-09 | 2025-08-19 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-09-11 |  | 2025-09-19 |  | Tower A | Super Structure | L43 | MEP | FPS 1st Fix - MEP & Finishes
42851 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-08-09 | 2025-08-14 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2025-09-11 |  | 2025-09-16 |  | Tower A | Super Structure | L43 | MEP | Electrical 1st Fixes
42852 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2025-08-09 | 2025-08-19 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2025-09-11 |  | 2025-09-19 |  | Tower A | Super Structure | L43
42853 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2025-08-09 | 2025-08-30 | Wet Area Waterproofing | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure | L43
42866 |  | Not Committed |  | 2025-08-22 | 2026-08-25 | L44-45 | 100 | 0 |  | 2025-09-11 |  | 2026-08-05
42866 |  | Not Committed |  | 2025-08-22 | 2026-08-25 | L44-45 | 100 | 0 |  | 2025-09-11 |  | 2026-08-05 |  |  |  |  | Finishes | Gypsum Plastering Works
42867 |  | Not Committed |  | 2025-08-22 | 2025-09-25 | MEP 1st Fixes | 100 | 0 |  | 2025-09-11 |  | 2025-10-11
42868 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2025-08-22 | 2025-09-01 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-09-11 |  | 2025-09-19 |  | Tower A | Super Structure | L44 | MEP | FPS 1st Fix - MEP & Finishes
42869 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-08-22 | 2025-08-29 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2025-09-11 |  | 2025-09-16 |  | Tower A | Super Structure | L44 | MEP | Electrical 1st Fixes
42870 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2025-08-22 | 2025-09-01 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2025-09-11 |  | 2025-09-19 |  | Tower A | Super Structure | L44
42871 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2025-08-22 | 2025-09-10 | Wet Area Waterproofing | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Tower A | Super Structure | L44
44242 | Tower A | Not Ready | High Side Procurement | 2025-03-31 | 2025-08-04 | HVAC Units | 100 | 0 |  | 2025-09-11 |  | 2026-01-14 |  | Tower A | --
44244 | Tower A | Not Ready | High Side Procurement | 2025-08-21 | 2026-02-05 | Transformers | 100 | 0 |  | 2025-09-11 |  | 2026-02-25 |  | Tower A | --
44510 | NTA_Zone 2 - Super Structure - P3 to P4 - Pour 4 | Not Ready | RCC Works - Slab | 2024-03-29 | 2024-04-20 | Slab_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Slab
44510 | NTA_Zone 2 - Super Structure - P3 to P4 - Pour 4 | Not Ready | RCC Works - Slab | 2024-03-29 | 2024-04-20 | Slab_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | NTA_Zone 2 | Super Structure
44539 | NTA_Zone 2 - Super Structure - GF to P1 | Not Ready | Partition Wall-Blockwork | 2024-04-27 | 2024-06-01 | GF to P1 | 100 | 0 |  | 2025-09-11 |  | 2025-10-17 |  | NTA_Zone 2 | Super Structure | GF
44539 | NTA_Zone 2 - Super Structure - GF to P1 | Not Ready | Partition Wall-Blockwork | 2024-04-27 | 2024-06-01 | GF to P1 | 100 | 0 |  | 2025-09-11 |  | 2025-10-17 |  | NTA_Zone 2 | Super Structure | GF
44539 | NTA_Zone 2 - Super Structure - GF to P1 | Not Ready | Partition Wall-Blockwork | 2024-04-27 | 2024-06-01 | GF to P1 | 100 | 0 |  | 2025-09-11 |  | 2025-10-17 |  | NTA_Zone 2 | Super Structure | GF
44677 | Tower A | Not Committed | Award of Packages | 2025-03-19 | 2025-08-06 | DG | 100 | 0 |  | 2025-09-11 |  | 2026-01-28 |  | Tower A | --
44679 | Tower A | Not Committed | Award of Packages | 2025-03-31 | 2025-07-14 | STP | 100 | 0 |  | 2025-09-11 |  | 2025-12-24 |  | Tower A | --
44679 | Tower A | Not Committed | Award of Packages | 2025-03-31 | 2025-07-14 | STP | 100 | 0 |  | 2025-09-11 |  | 2025-12-24 |  | Tower A | --
44681 | Tower A | Not Committed | Award of Packages | 2024-02-29 | 2024-07-18 | ELV | 100 | 0 |  | 2025-09-11 |  | 2026-01-28 |  | Tower A | --
44682 | Tower A | Not Committed | Award of Packages | 2026-02-23 | 2026-05-18 | External Development | 100 | 0 |  | 2025-09-11 |  | 2025-12-03 |  | Tower A | --
44682 | Tower A | Not Committed | Award of Packages | 2026-02-23 | 2026-05-18 | External Development | 100 | 0 |  | 2025-09-11 |  | 2025-12-03 |  | Tower A | --
45390 |  | Not Ready |  | 2024-10-30 | 2027-08-03 | Civil Finishes | 100 | 0 |  | 2025-09-11 |  | 2027-10-04
45391 |  | Not Committed |  | 2024-10-30 | 2027-08-03 | Partition Walls - Blockwork | 100 | 0 |  | 2025-09-11 |  | 2027-09-16
45392 |  | Not Committed |  | 2024-10-30 | 2025-04-26 | B3 to B2 | 100 | 0 |  | 2025-09-11 |  | 2026-03-05
45392 |  | Not Committed |  | 2024-10-30 | 2025-04-26 | B3 to B2 | 100 | 0 |  | 2025-09-11 |  | 2026-03-05
45392 |  | Not Committed |  | 2024-10-30 | 2025-04-26 | B3 to B2 | 100 | 0 |  | 2025-09-11 |  | 2026-03-05
45393 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 | Not Ready | Partition Wall-Blockwork | 2024-10-30 | 2024-12-04 | De-shuttering & Area clearance | 100 | 0 |  | 2025-09-11 |  | 2025-10-17 |  | Tower B | Sub Structure | B3
45397 |  | Not Committed |  | 2024-12-16 | 2025-04-09 | B2 to B1 | 100 | 0 |  | 2025-09-11 |  | 2025-11-22
45397 |  | Not Committed |  | 2024-12-16 | 2025-04-09 | B2 to B1 | 100 | 0 |  | 2025-09-11 |  | 2025-11-22
45397 |  | Not Committed |  | 2024-12-16 | 2025-04-09 | B2 to B1 | 100 | 0 |  | 2025-09-11 |  | 2025-11-22
45398 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 | Not Ready | Partition Wall-Blockwork | 2024-12-16 | 2025-01-08 | De-shuttering & Area clearance | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower B | Sub Structure | B2
45401 |  | Not Committed |  | 2025-01-29 | 2025-03-22 | B1 to GF | 100 | 0 |  | 2025-09-11 |  | 2025-11-05
45401 |  | Not Committed |  | 2025-01-29 | 2025-03-22 | B1 to GF | 100 | 0 |  | 2025-09-11 |  | 2025-11-05
45401 |  | Not Committed |  | 2025-01-29 | 2025-03-22 | B1 to GF | 100 | 0 |  | 2025-09-11 |  | 2025-11-05
45402 | Tower B - Sub Structure - Finishes & MEP - B1 to GF | Not Ready | Partition Wall-Blockwork | 2025-01-29 | 2025-02-20 | De-shuttering & Area clearance | 100 | 0 |  | 2025-09-11 |  | 2025-10-06 |  | Tower B | Sub Structure | B1
45405 |  | Not Committed |  | 2025-04-26 | 2025-06-19 | GF to P1 | 100 | 0 |  | 2025-09-11 |  | 2025-11-05
45405 |  | Not Committed |  | 2025-04-26 | 2025-06-19 | GF to P1 | 100 | 0 |  | 2025-09-11 |  | 2025-11-05
45405 |  | Not Committed |  | 2025-04-26 | 2025-06-19 | GF to P1 | 100 | 0 |  | 2025-09-11 |  | 2025-11-05
45406 | Tower B - Super Structure - Finishes & MEP - GF to P1 | Not Ready | Partition Wall-Blockwork | 2025-04-26 | 2025-05-08 | De-shuttering & Area clearance | 100 | 0 |  | 2025-09-11 |  | 2025-09-23 |  | Tower B | Super Structure | GF
45409 |  | Not Committed |  | 2025-05-12 | 2025-06-16 | P1 to P2 | 100 | 0 |  | 2025-09-11 |  | 2025-10-17
45409 |  | Not Committed |  | 2025-05-12 | 2025-06-16 | P1 to P2 | 100 | 0 |  | 2025-09-11 |  | 2025-10-17
45409 |  | Not Committed |  | 2025-05-12 | 2025-06-16 | P1 to P2 | 100 | 0 |  | 2025-09-11 |  | 2025-10-17
45410 | Tower B - Super Structure - Finishes & MEP - P1 to P2 | Not Ready | Partition Wall-Blockwork | 2025-05-12 | 2025-05-16 | De-shuttering & Area clearance | 100 | 0 |  | 2025-09-11 |  | 2025-09-16 |  | Tower B | Super Structure
45413 |  | Not Committed |  | 2025-06-05 | 2025-07-10 | P2 to P3 | 100 | 0 |  | 2025-09-11 |  | 2025-10-17
45413 |  | Not Committed |  | 2025-06-05 | 2025-07-10 | P2 to P3 | 100 | 0 |  | 2025-09-11 |  | 2025-10-17
45413 |  | Not Committed |  | 2025-06-05 | 2025-07-10 | P2 to P3 | 100 | 0 |  | 2025-09-11 |  | 2025-10-17
45414 | Tower B - Super Structure - Finishes & MEP - P2 to P3 | Not Ready | Partition Wall-Blockwork | 2025-06-05 | 2025-06-11 | De-shuttering & Area clearance | 100 | 0 |  | 2025-09-11 |  | 2025-09-16 |  | Tower B | Super Structure
46044 |  | Not Committed |  | 2025-12-18 | 2028-07-08 | Typical Floor MEP & Finishes | 100 | 0 |  | 2025-09-11 |  | 2028-07-31
46654 |  | Not Committed |  | 2025-12-18 | 2028-07-08 | Typical Apartment Area | 100 | 0 |  | 2025-09-11 |  | 2028-07-31
47267 |  | Not Committed |  | 2027-03-24 | 2028-05-27 | L41-42 | 100 | 0 |  | 2025-09-11 |  | 2028-06-19
47267 |  | Not Committed |  | 2027-03-24 | 2028-05-27 | L41-42 | 100 | 0 |  | 2025-09-11 |  | 2028-06-19 |  |  |  |  | Finishes | Gypsum Plastering Works
47274 |  | Not Committed |  | 2027-08-26 | 2027-10-20 | Finishes after 1st Fix | 100 | 0 |  | 2025-09-11 |  | 2027-09-06
47275 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2027-08-26 | 2027-09-07 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-09-11 |  | 2025-09-23 |  | Tower B | Super Structure | L41 | Finishes | Blockwork
47579 |  | Not Committed |  | 2024-09-18 | 2024-11-18 | Pour 11 (PB-E to PB-K) | 100 | 0 |  | 2025-09-11 |  | 2025-10-14
47580 |  | Not Ready |  | 2024-09-18 | 2024-09-20 | Dressing & PCC | 100 | 0 |  | 2025-09-11 |  | 2025-09-13
47580 |  | Not Ready |  | 2024-09-18 | 2024-09-20 | Dressing & PCC | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  |  |  |  | RCC Super Structure | Foundation RCC Works
47580 |  | Not Ready |  | 2024-09-18 | 2024-09-20 | Dressing & PCC | 100 | 0 |  | 2025-09-11 |  | 2025-09-13 |  |  |  |  | RCC Sub Structure | Raft RCC Works
47581 |  | Not Ready |  | 2024-10-17 | 2024-10-22 | Waterproofing-Raft Area | 100 | 0 |  | 2025-09-11 |  | 2025-09-16
47600 |  | Not Ready |  | 2024-10-24 | 2024-11-01 | Section 9_lift 1 | 100 | 0 |  | 2025-09-11 |  | 2025-09-19
47600 |  | Not Ready |  | 2024-10-24 | 2024-11-01 | Section 9_lift 1 | 100 | 0 |  | 2025-09-11 |  | 2025-09-19 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47602 |  | Not Ready |  | 2024-12-26 | 2025-01-02 | Section 11_lift 1 | 100 | 0 |  | 2025-09-11 |  | 2025-09-19
47602 |  | Not Ready |  | 2024-12-26 | 2025-01-02 | Section 11_lift 1 | 100 | 0 |  | 2025-09-11 |  | 2025-09-19 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47610 |  | Not Ready |  | 2024-11-25 | 2024-12-02 | Section 7_lift 2 | 100 | 0 |  | 2025-09-11 |  | 2025-09-19
47610 |  | Not Ready |  | 2024-11-25 | 2024-12-02 | Section 7_lift 2 | 100 | 0 |  | 2025-09-11 |  | 2025-09-19 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47952 | Tower B | Not Committed | Award of Packages | 2021-04-01 | 2021-10-28 | RCC | 100 | 0 |  | 2025-09-11 |  | 2026-04-08 |  | Tower B | --
47952 | Tower B | Not Committed | Award of Packages | 2021-04-01 | 2021-10-28 | RCC | 100 | 0 |  | 2025-09-11 |  | 2026-04-08 |  | Tower B | --
47954 | Tower B | Not Committed | Award of Packages | 2025-03-06 | 2025-07-24 | PHE & FF | 100 | 0 |  | 2025-09-11 |  | 2026-01-28 |  | Tower B | --
47955 | Tower B | Not Committed | Award of Packages | 2025-03-06 | 2025-07-24 | Electrical | 100 | 0 |  | 2025-09-11 |  | 2026-01-28 |  | Tower B | --
48090 |  | Not Committed |  | 2026-04-01 | 2026-10-13 | MEP High Side_Retail | 100 | 0 |  | 2025-09-11 |  | 2026-12-21
48098 |  | Not Committed |  | 2026-05-07 | 2026-10-13 | Elevators (MRL) | 100 | 0 |  | 2025-09-11 |  | 2026-12-21
48099 | Retail | Not Ready |  | 2026-05-14 | 2026-10-13 | Retail Lifts (16 Nos.) | 100 | 0 |  | 2025-09-11 |  | 2026-02-03 |  | Retail | --
48151 | Retail - Foundation P5 | Not Ready |  | 2025-01-17 | 2025-01-18 | Waterproofing vertical - toe ht. | 100 | 0 |  | 2025-09-11 |  | 2025-09-12 |  | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48151 | Retail - Foundation P5 | Not Ready |  | 2025-01-17 | 2025-01-18 | Waterproofing vertical - toe ht. | 100 | 0 |  | 2025-09-11 |  | 2025-09-12 |  | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48151 | Retail - Foundation P5 | Not Ready |  | 2025-01-17 | 2025-01-18 | Waterproofing vertical - toe ht. | 100 | 0 |  | 2025-09-11 |  | 2025-09-12 |  | Retail | Foundation
48152 | Retail - Foundation P5 | Not Ready |  | 2025-01-20 | 2025-01-24 | RW toe foundation | 100 | 0 |  | 2025-09-11 |  | 2025-09-16 |  | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48152 | Retail - Foundation P5 | Not Ready |  | 2025-01-20 | 2025-01-24 | RW toe foundation | 100 | 0 |  | 2025-09-11 |  | 2025-09-16 |  | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48152 | Retail - Foundation P5 | Not Ready |  | 2025-01-20 | 2025-01-24 | RW toe foundation | 100 | 0 |  | 2025-09-11 |  | 2025-09-16 |  | Retail | Foundation
48153 | Retail - Foundation P5 | Not Ready |  | 2025-01-25 | 2025-02-05 | Raft & Footing Reinf_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-23 |  | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48153 | Retail - Foundation P5 | Not Ready |  | 2025-01-25 | 2025-02-05 | Raft & Footing Reinf_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-23 |  | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48153 | Retail - Foundation P5 | Not Ready |  | 2025-01-25 | 2025-02-05 | Raft & Footing Reinf_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-23 |  | Retail | Foundation
48229 |  | Not Committed |  | 2025-09-16 | 2026-12-26 | Finishes with MEP Final fixes | 100 | 0 |  | 2025-09-11 |  | 2027-06-03
48252 |  | Not Committed |  | 2026-03-04 | 2026-12-26 | Retail Area Finishes (GF to P4) (FF works + Tap-off for Ele.+HVAC+PHE) | 100 | 0 |  | 2025-09-11 |  | 2027-06-03
48262 |  | Not Committed |  | 2026-05-14 | 2026-10-13 | Spanish Steps Finishes | 100 | 0 |  | 2025-09-11 |  | 2026-02-03
48263 | Retail - Super structure - GF to CH00 | Not Ready |  | 2026-05-14 | 2026-10-13 | GF to CH00 | 100 | 0 |  | 2025-09-11 |  | 2026-02-03 |  | Retail | Super Structure | GF
48307 |  | Not Committed |  | 2024-11-26 | 2024-12-31 | Pour RT-1 (Ramp) | 100 | 0 |  | 2025-09-11 |  | 2025-09-29
48308 | Retail - Sub structure - B1 to GF - P1 | Not Ready |  | 2024-11-26 | 2024-12-12 | Columns/ Walls_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Retail | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
48308 | Retail - Sub structure - B1 to GF - P1 | Not Ready |  | 2024-11-26 | 2024-12-12 | Columns/ Walls_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Retail | Sub Structure | B1
48309 | Retail - Sub structure - B1 to GF - P1 | Not Ready |  | 2024-12-13 | 2024-12-31 | Slab_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Retail | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
48309 | Retail - Sub structure - B1 to GF - P1 | Not Ready |  | 2024-12-13 | 2024-12-31 | Slab_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Retail | Sub Structure | B1
48310 |  | Not Committed |  | 2025-02-05 | 2025-03-11 | Pour RT-2 (Ramp) | 100 | 0 |  | 2025-09-11 |  | 2025-09-29
48311 | Retail - Sub structure - B1 to GF - P2 | Not Ready |  | 2025-02-05 | 2025-02-21 | Columns/ Walls_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Retail | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
48311 | Retail - Sub structure - B1 to GF - P2 | Not Ready |  | 2025-02-05 | 2025-02-21 | Columns/ Walls_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Retail | Sub Structure | B1
48312 | Retail - Sub structure - B1 to GF - P2 | Not Ready |  | 2025-02-22 | 2025-03-11 | Slab_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Retail | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
48312 | Retail - Sub structure - B1 to GF - P2 | Not Ready |  | 2025-02-22 | 2025-03-11 | Slab_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Retail | Sub Structure | B1
48313 |  | Not Committed |  | 2025-02-14 | 2025-03-21 | Pour RT-3 | 100 | 0 |  | 2025-09-11 |  | 2025-09-29
48314 | Retail - Sub structure - B1 to GF - P3 | Not Ready |  | 2025-02-14 | 2025-03-03 | Columns/ Walls_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Retail | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
48314 | Retail - Sub structure - B1 to GF - P3 | Not Ready |  | 2025-02-14 | 2025-03-03 | Columns/ Walls_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Retail | Sub Structure | B1
48315 | Retail - Sub structure - B1 to GF - P3 | Not Ready |  | 2025-03-04 | 2025-03-21 | Slab_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Retail | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
48315 | Retail - Sub structure - B1 to GF - P3 | Not Ready |  | 2025-03-04 | 2025-03-21 | Slab_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Retail | Sub Structure | B1
48319 |  | Not Committed |  | 2025-05-12 | 2025-06-16 | Pour RT-5 | 100 | 0 |  | 2025-09-11 |  | 2025-09-29
48320 | Retail - Sub structure - B1 to GF - P5 | Not Ready |  | 2025-05-12 | 2025-05-28 | Columns/ Walls_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Retail | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
48320 | Retail - Sub structure - B1 to GF - P5 | Not Ready |  | 2025-05-12 | 2025-05-28 | Columns/ Walls_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Retail | Sub Structure | B1
48321 | Retail - Sub structure - B1 to GF - P5 | Not Ready |  | 2025-05-29 | 2025-06-16 | Slab_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Retail | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
48321 | Retail - Sub structure - B1 to GF - P5 | Not Ready |  | 2025-05-29 | 2025-06-16 | Slab_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Retail | Sub Structure | B1
48335 | Retail - Sub structure - B3 to B2 - P3 | Not Ready |  | 2024-09-27 | 2024-10-05 | Section 9_lift 2 | 100 | 0 |  | 2025-09-11 |  | 2025-09-19 |  | Retail | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
48335 | Retail - Sub structure - B3 to B2 - P3 | Not Ready |  | 2024-09-27 | 2024-10-05 | Section 9_lift 2 | 100 | 0 |  | 2025-09-11 |  | 2025-09-19 |  | Retail | Sub Structure | B3
48336 |  | Not Committed |  | 2025-02-03 | 2025-02-26 | Pour RT-5 | 100 | 0 |  | 2025-09-11 |  | 2025-10-15
48337 | Retail - Sub structure - B3 to B2 - P5 | Not Ready |  | 2025-02-03 | 2025-02-10 | Section 10_lift 2 | 100 | 0 |  | 2025-09-11 |  | 2025-09-19 |  | Retail | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
48337 | Retail - Sub structure - B3 to B2 - P5 | Not Ready |  | 2025-02-03 | 2025-02-10 | Section 10_lift 2 | 100 | 0 |  | 2025-09-11 |  | 2025-09-19 |  | Retail | Sub Structure | B3
48366 |  | Not Committed |  | 2024-09-09 | 2024-10-16 | Pour RT-2 | 100 | 0 |  | 2025-09-11 |  | 2025-09-29
48367 | Retail - Sub structure - B3 to B2 - P2 | Not Ready |  | 2024-09-09 | 2024-09-26 | Columns/ Walls_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Retail | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
48367 | Retail - Sub structure - B3 to B2 - P2 | Not Ready |  | 2024-09-09 | 2024-09-26 | Columns/ Walls_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Retail | Sub Structure | B3
48368 | Retail - Sub structure - B3 to B2 - P2 | Not Ready |  | 2024-09-27 | 2024-10-16 | Slab_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Retail | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
48368 | Retail - Sub structure - B3 to B2 - P2 | Not Ready |  | 2024-09-27 | 2024-10-16 | Slab_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Retail | Sub Structure | B3
48369 |  | Not Committed |  | 2024-09-18 | 2024-10-24 | Pour RT-3 | 100 | 0 |  | 2025-09-11 |  | 2025-10-08
48370 | Retail - Sub structure - B3 to B2 - P3 | Not Ready |  | 2024-09-18 | 2024-10-05 | Columns/ Walls_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Retail | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
48370 | Retail - Sub structure - B3 to B2 - P3 | Not Ready |  | 2024-09-18 | 2024-10-05 | Columns/ Walls_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Retail | Sub Structure | B3
48405 |  | Not Committed |  | 2025-02-07 | 2025-03-13 | Pour RT-3 | 100 | 0 |  | 2025-09-11 |  | 2025-09-29
48406 | Retail - Sub structure - B2 to B1 - P3 | Not Ready |  | 2025-02-07 | 2025-02-24 | Columns/ Walls_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Retail | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
48406 | Retail - Sub structure - B2 to B1 - P3 | Not Ready |  | 2025-02-07 | 2025-02-24 | Columns/ Walls_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Retail | Sub Structure | B2
48407 | Retail - Sub structure - B2 to B1 - P3 | Not Ready |  | 2025-02-25 | 2025-03-13 | Slab_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Retail | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
48407 | Retail - Sub structure - B2 to B1 - P3 | Not Ready |  | 2025-02-25 | 2025-03-13 | Slab_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-29 |  | Retail | Sub Structure | B2
48411 |  | Not Committed |  | 2025-03-18 | 2025-04-14 | Pour RT-5 (no slab at tank area) | 100 | 0 |  | 2025-09-11 |  | 2025-09-25
48412 | Retail - Sub structure - B2 to B1 - P5 | Not Ready |  | 2025-03-18 | 2025-03-31 | Columns/ Walls_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-25 |  | Retail | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
48412 | Retail - Sub structure - B2 to B1 - P5 | Not Ready |  | 2025-03-18 | 2025-03-31 | Columns/ Walls_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-25 |  | Retail | Sub Structure | B2
48413 | Retail - Sub structure - B2 to B1 - P5 | Not Ready |  | 2025-04-01 | 2025-04-14 | Slab_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-25 |  | Retail | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
48413 | Retail - Sub structure - B2 to B1 - P5 | Not Ready |  | 2025-04-01 | 2025-04-14 | Slab_NTA | 100 | 0 |  | 2025-09-11 |  | 2025-09-25 |  | Retail | Sub Structure | B2
8556 | T-14-1st Floor Flat Area | Not Ready | Putty | 2025-08-17 | 2025-11-10 | Putty | 100 | 0 |  | 2025-09-12 |  | 2025-12-06
9121 | T-15-2nd Floor Flat Area | Not Ready | Waterproofing | 2025-09-08 | 2025-10-28 | Waterproofing | 100 | 0 |  | 2025-09-12 |  | 2025-11-03
9740 |  | Not Ready |  | 2025-11-12 | 2026-07-05 | Sixth Floor | 100 | 0 |  | 2025-09-12 |  | 2026-05-08
9741 |  | Not Ready |  | 2025-11-12 | 2026-06-03 | Flat Area | 100 | 0 |  | 2025-09-12 |  | 2026-04-05
10081 | T-21-Terrace | Complete | RCC | 2025-10-08 | 2025-10-09 | Slab& Beam RCC | 318 | 318 | CUM | 2025-09-12 | 2025-12-16 | 2025-09-13 | 2025-12-17
10812 | T-20-7th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-10-08 | 2025-10-24 | Electrical DB Fixing | 100 | 0 |  | 2025-09-12 |  | 2025-10-01
11620 | T-18-9th Floor | Complete | RCC | 2025-11-17 | 2025-11-18 | Slab& Beam RCC | 330.8 | 330.8 | CUM | 2025-09-12 | 2025-12-24 | 2025-09-13 | 2025-12-25
39994 | Tower A - Super Structure - Core & Outer Slab L63-64 | Complete | RCC Works - Slab | 2025-09-03 | 2025-09-08 | Outer Slab_TA | 100 | 100 |  | 2025-09-12 | 2025-09-09 | 2025-09-18 | 2025-09-28 | Tower A | Super Structure | L63 | RCC Sub Structure | RCC Works - Slab
41475 |  | Started |  | 2025-06-02 | 2026-04-21 | L33-34 | 100 | 44 |  | 2025-09-12 | 2025-09-12 | 2026-05-12 |  |  |  |  | Finishes | Gypsum Plastering Works
41475 |  | Started |  | 2025-06-02 | 2026-04-21 | L33-34 | 100 | 44 |  | 2025-09-12 | 2025-09-12 | 2026-05-12
41476 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2025-09-12 | 2025-09-15 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 65 |  | 2025-09-12 | 2025-09-12 | 2026-03-31 |  | Tower A | Super Structure | L33 | MEP | FPS 1st Fix - MEP & Finishes
41477 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-09-12 | 2025-09-16 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-12 |  | 2025-09-15 |  | Tower A | Super Structure | L33 | MEP | Electrical 1st Fixes
8726 |  | Not Ready |  | 2025-09-12 | 2026-05-23 | Eighth Floor | 100 | 0 |  | 2025-09-13 |  | 2026-05-25
8727 |  | Not Ready |  | 2025-09-12 | 2026-05-02 | Flat Area | 100 | 0 |  | 2025-09-13 |  | 2026-05-04
9019 | T-15-9th Floor | Complete | Slab& Beam Steel & Conduting | 2025-09-09 | 2025-09-12 | Slab& Beam Steel & Conduting | 13 | 13 | MT | 2025-09-13 | 2025-10-06 | 2025-09-17 | 2025-10-10
9082 | T-15-GF Common Area | Not Ready | Toilets False Celing | 2025-09-15 | 2025-10-01 | Toilets False Celing | 100 | 0 |  | 2025-09-13 |  | 2025-10-01
9102 | T-15-1st Floor Flat Area | Not Ready | Putty | 2025-09-15 | 2025-12-09 | Putty | 100 | 0 |  | 2025-09-13 |  | 2025-12-07
9175 | T-15-4th Floor Flat Area | Not Ready | Plastering | 2025-09-09 | 2025-10-23 | Plastering-Gypsum | 100 | 0 |  | 2025-09-13 |  | 2025-10-29
9541 | T-16-10th Floor | Not Ready |  | 2025-11-13 | 2025-11-26 | 9th Floor Roof | 100 | 0 |  | 2025-09-13 |  | 2025-09-26
10107 | T-21-GF Flat Area | Not Ready | Putty | 2025-09-09 | 2025-09-30 | Putty | 100 | 0 |  | 2025-09-13 |  | 2025-10-06
10305 | T-21-7th Floor Common Area | Not Ready |  | 2025-10-12 | 2025-11-16 | Plastering Gypsum | 100 | 0 |  | 2025-09-13 |  | 2025-10-17
10598 | T-20-Terrace | Complete | Conduiting | 2025-10-09 | 2025-10-13 | Conduiting works | 100 | 100 |  | 2025-09-13 | 2025-10-16 | 2025-09-15 | 2025-11-01
11146 | T-19-GF Flat Area | Not Ready | Flooring & skirting | 2025-09-29 | 2025-11-04 | Flooring & skirting | 100 | 0 |  | 2025-09-13 |  | 2025-10-17
11326 |  | Not Ready |  | 2025-11-05 | 2026-07-06 | Seventh Floor | 100 | 0 |  | 2025-09-13 |  | 2026-05-17
11327 |  | Not Ready |  | 2025-11-05 | 2026-06-09 | Flat Area | 100 | 0 |  | 2025-09-13 |  | 2026-04-20
11683 | T-18-GF Common Area | Not Ready | Flooring & skirting | 2025-11-09 | 2025-12-23 | Flooring & skirting | 100 | 0 |  | 2025-09-13 |  | 2025-10-30
11699 | T-18-1st Floor Flat Area | Not Ready | Toilet flooring | 2025-11-13 | 2025-12-16 | Toilet flooring | 100 | 0 |  | 2025-09-13 |  | 2025-10-15
11721 | T-18-2nd Floor Flat Area | Not Ready | Waterproofing | 2025-11-12 | 2025-12-31 | Waterproofing | 100 | 0 |  | 2025-09-13 |  | 2025-11-02
39710 | Tower A - Super Structure - Core Wall High Rise L67-68 | Complete | Core Wall RCC Works | 2025-09-03 | 2025-09-05 | ACS Form Closing & Alignment | 100 | 100 |  | 2025-09-13 | 2025-09-21 | 2025-09-18 | 2025-09-21 | Tower A | Super Structure | L67 | RCC Super Structure | Core Wall RCC Works
40624 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2024-02-21 | 2024-02-28 | HVAC Ducting | 100 | 0 |  | 2025-09-13 |  | 2025-09-23 |  | Tower A | Sub Structure | B2 | MEP | HVAC Ducting
40625 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2024-02-21 | 2024-03-08 | Flooring & Dado | 100 | 0 |  | 2025-09-13 |  | 2025-10-03 |  | Tower A | Sub Structure | B2 | Finishes | Flooring & Dado
42208 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2024-08-10 | 2024-09-05 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-09-13 |  | 2025-10-09 |  | Tower A | Super Structure | L7 | Finishes | Blockwork
42226 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2024-08-23 | 2024-09-18 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-09-13 |  | 2025-10-09 |  | Tower A | Super Structure | L8 | Finishes | Blockwork
42246 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Apartment Area | Started | Flooring & Dado - MEP & Finishes | 2025-09-13 | 2025-10-01 | Flooring & Dado works | 100 | 70.33 | Units | 2025-09-13 | 2025-07-26 | 2025-10-23 |  | Tower A | Super Structure | L9 | Finishes | Flooring & Dado
42279 |  | Not Committed |  | 2024-09-23 | 2025-10-14 | Finishes after 1st Fix | 100 | 0 |  | 2025-09-13 |  | 2025-11-05
42280 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2024-09-23 | 2024-10-17 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-09-13 |  | 2025-10-09 |  | Tower A | Super Structure | L11 | Finishes | Blockwork
42297 |  | Not Committed |  | 2024-10-01 | 2025-10-21 | Finishes after 1st Fix | 100 | 0 |  | 2025-09-13 |  | 2025-11-11
42298 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2024-10-01 | 2024-10-25 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-09-13 |  | 2025-10-09 |  | Tower A | Super Structure | L12 | Finishes | Blockwork
42315 |  | Not Committed |  | 2024-10-10 | 2025-10-14 | Finishes after 1st Fix | 100 | 0 |  | 2025-09-13 |  | 2025-11-05
42316 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2024-10-10 | 2024-11-04 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-09-13 |  | 2025-10-09 |  | Tower A | Super Structure | L13 | Finishes | Blockwork
9524 | T-16-7th Floor | Complete | Shuttering | 2025-10-06 | 2025-10-10 | Slab and Beam Shuttering | 4183 | 4183 | Sqm | 2025-09-14 | 2025-10-18 | 2025-09-19 | 2025-10-24
9639 | T-16-2nd Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-10-06 | 2025-10-28 | Plumbing Pipe Line | 100 | 0 |  | 2025-09-14 |  | 2025-10-08
10271 | T-21-6th Floor Flat Area | Not Ready | Flooring & skirting | 2025-10-17 | 2025-12-02 | Flooring & skirting | 100 | 0 |  | 2025-09-14 |  | 2025-10-30
10314 | T-21-8th Floor Flat Area | Not Ready | Blockwork | 2025-10-09 | 2025-11-02 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-09-14 |  | 2025-10-05
10340 | T-21-9th Floor Flat Area | Not Ready | Blockwork | 2025-10-09 | 2025-11-02 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-09-14 |  | 2025-10-05
10353 | T-21-9th Floor Flat Area | Not Ready | Railing | 2025-10-09 | 2025-11-13 | Balcony Railing | 100 | 0 |  | 2025-09-14 |  | 2025-10-16
10379 | T-21-10th Floor Flat Area | Not Ready | Railing | 2025-10-09 | 2025-11-13 | Balcony Railing | 100 | 0 |  | 2025-09-14 |  | 2025-10-16
10597 | T-20-Terrace | Complete | Shear Walls/Corewalls Shuttering | 2025-10-10 | 2025-10-15 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-09-14 | 2025-10-06 | 2025-09-17 | 2025-10-18
11091 | T-19-8th Floor | Complete | Shuttering | 2025-09-28 | 2025-10-03 | Slab and Beam Shuttering | 3548 | 3548 | Sqm | 2025-09-14 | 2025-10-23 | 2025-09-17 | 2025-10-28
11225 | T-19-3rd Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-09-28 | 2025-10-21 | Plumbing Pipe Line | 100 | 0 |  | 2025-09-14 |  | 2025-10-06
11665 | T-18-GF Flat Area | Not Ready | Toilets False Celing | 2025-11-11 | 2025-11-27 | Toilets-False Celing | 100 | 0 |  | 2025-09-14 |  | 2025-10-01
11796 | T-18-5th Floor Flat Area | Not Ready | Blockwork | 2025-11-18 | 2025-12-09 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-09-14 |  | 2025-10-06
11835 | T-18-6th Floor Flat Area | Not Ready | Railing | 2025-11-18 | 2025-12-20 | Balcony Railing | 100 | 0 |  | 2025-09-14 |  | 2025-10-16
8482 | T-14-12th Floor | Complete |  | 2025-09-13 | 2025-09-26 | 11th Floor Roof | 100 | 100 |  | 2025-09-15 | 2025-12-22 | 2025-09-27 | 2026-01-14
8578 | T-14-2nd Floor Flat Area | Not Ready | Dado | 2025-08-17 | 2025-09-13 | Dado | 100 | 0 |  | 2025-09-15 |  | 2025-10-13
8626 | T-14-4th Floor Flat Area | Not Ready | Plastering | 2025-08-16 | 2025-09-06 | Plastering-Cement | 100 | 0 |  | 2025-09-15 |  | 2025-10-06
10765 | T-20-5th Floor Flat Area | Not Ready | Flooring & skirting | 2025-10-15 | 2025-11-29 | Flooring & skirting | 100 | 0 |  | 2025-09-15 |  | 2025-10-29
10858 |  | Not Ready |  | 2025-10-20 | 2026-07-23 | Ninth Floor | 100 | 0 |  | 2025-09-15 |  | 2026-06-18
10859 |  | Not Ready |  | 2025-10-20 | 2026-07-23 | Flat Area | 100 | 0 |  | 2025-09-15 |  | 2026-06-18
10884 |  | Not Ready |  | 2025-10-20 | 2026-08-08 | Tenth Floor | 100 | 0 |  | 2025-09-15 |  | 2026-07-04
10885 |  | Not Ready |  | 2025-10-20 | 2026-08-08 | Flat Area | 100 | 0 |  | 2025-09-15 |  | 2026-07-04
11108 | T-19-11th Floor | Not Ready |  | 2025-11-06 | 2025-11-19 | 10th Floor Roof | 100 | 0 |  | 2025-09-15 |  | 2025-09-27
11622 | T-18-10th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-11-19 | 2025-11-23 | AL - Shear Walls/Corewalls Steel | 20.5 | 20.5 | MT | 2025-09-15 | 2025-12-26 | 2025-09-17 | 2026-01-05
11772 | T-18-4th Floor Flat Area | Not Ready | Plastering | 2025-11-19 | 2025-12-10 | Plastering-Cement | 100 | 0 |  | 2025-09-15 |  | 2025-10-07
40608 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2024-03-05 | 2024-03-06 | FAPA Cabling | 100 | 0 |  | 2025-09-15 |  | 2025-09-16 |  | Tower A | Sub Structure | B3
40623 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2024-02-16 | 2024-02-17 | FAPA Cabling | 100 | 0 |  | 2025-09-15 |  | 2025-09-16 |  | Tower A | Sub Structure | B2
40650 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2024-03-13 | 2024-03-14 | FAPA Cabling | 100 | 0 |  | 2025-09-15 |  | 2025-09-16 |  | Tower A | Sub Structure | B1
40735 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2024-04-27 | 2024-04-29 | FAPA Cabling | 100 | 0 |  | 2025-09-15 |  | 2025-09-16 |  | Tower A | Super Structure
41062 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2024-06-21 | 2024-06-22 | FAPA Cabling | 100 | 0 |  | 2025-09-15 |  | 2025-09-16 |  | Tower A | Super Structure | L7
41078 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2024-07-04 | 2024-07-05 | FAPA Cabling | 100 | 0 |  | 2025-09-15 |  | 2025-09-16 |  | Tower A | Super Structure | L8
41094 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2024-07-29 | 2024-07-30 | FAPA Cabling | 100 | 0 |  | 2025-09-15 |  | 2025-09-16 |  | Tower A | Super Structure | L9
41110 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2024-09-02 | 2024-09-03 | FAPA Cabling | 100 | 0 |  | 2025-09-15 |  | 2025-09-16 |  | Tower A | Super Structure | L10
41126 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2024-09-09 | 2024-09-10 | FAPA Cabling | 100 | 0 |  | 2025-09-15 |  | 2025-09-16 |  | Tower A | Super Structure | L11
41142 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2024-10-15 | 2024-10-16 | FAPA Cabling | 100 | 0 |  | 2025-09-15 |  | 2025-09-16 |  | Tower A | Super Structure | L12
41158 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2024-10-19 | 2024-10-21 | FAPA Cabling | 100 | 0 |  | 2025-09-15 |  | 2025-09-16 |  | Tower A | Super Structure | L13
41174 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2024-11-26 | 2024-11-27 | FAPA Cabling | 100 | 0 |  | 2025-09-15 |  | 2025-09-16 |  | Tower A | Super Structure | L14
41190 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2025-01-01 | 2025-01-02 | FAPA Cabling | 100 | 0 |  | 2025-09-15 |  | 2025-09-16 |  | Tower A | Super Structure | L15
41206 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2025-01-09 | 2025-01-10 | FAPA Cabling | 100 | 0 |  | 2025-09-15 |  | 2025-09-16 |  | Tower A | Super Structure | L16
41222 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2025-01-14 | 2025-01-15 | FAPA Cabling | 100 | 0 |  | 2025-09-15 |  | 2025-09-16 |  | Tower A | Super Structure | L17
41238 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2025-01-21 | 2025-01-22 | FAPA Cabling | 100 | 0 |  | 2025-09-15 |  | 2025-09-16 |  | Tower A | Super Structure | L18
41254 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2025-01-28 | 2025-01-29 | FAPA Cabling | 100 | 0 |  | 2025-09-15 |  | 2025-09-16 |  | Tower A | Super Structure | L19
41270 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2025-02-04 | 2025-02-05 | FAPA Cabling | 100 | 0 |  | 2025-09-15 |  | 2025-09-16 |  | Tower A | Super Structure | L20
41286 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2025-02-13 | 2025-02-14 | FAPA Cabling | 100 | 0 |  | 2025-09-15 |  | 2025-09-16 |  | Tower A | Super Structure | L21
41302 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2025-02-20 | 2025-02-21 | FAPA Cabling | 100 | 0 |  | 2025-09-15 |  | 2025-09-16 |  | Tower A | Super Structure | L22
41318 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2025-02-27 | 2025-02-28 | FAPA Cabling | 100 | 0 |  | 2025-09-15 |  | 2025-09-16 |  | Tower A | Super Structure | L23
41334 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2025-03-05 | 2025-03-06 | FAPA Cabling | 100 | 0 |  | 2025-09-15 |  | 2025-09-16 |  | Tower A | Super Structure | L24
41350 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2025-03-11 | 2025-03-12 | FAPA Cabling | 100 | 0 |  | 2025-09-15 |  | 2025-09-16 |  | Tower A | Super Structure | L25
41366 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2025-03-20 | 2025-03-21 | FAPA Cabling | 100 | 0 |  | 2025-09-15 |  | 2025-09-16 |  | Tower A | Super Structure | L26
41382 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2025-03-29 | 2025-03-31 | FAPA Cabling | 100 | 0 |  | 2025-09-15 |  | 2025-09-16 |  | Tower A | Super Structure | L27
41398 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2025-08-08 | 2025-08-11 | FAPA Cabling | 100 | 0 |  | 2025-09-15 |  | 2025-09-16 |  | Tower A | Super Structure | L28
41414 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2025-08-14 | 2025-08-19 | FAPA Cabling | 100 | 0 |  | 2025-09-15 |  | 2025-09-16 |  | Tower A | Super Structure | L29
41430 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2025-08-25 | 2025-08-29 | FAPA Cabling | 100 | 0 |  | 2025-09-15 |  | 2025-09-16 |  | Tower A | Super Structure | L30
41446 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2025-09-04 | 2025-09-06 | FAPA Cabling | 100 | 0 |  | 2025-09-15 |  | 2025-09-16 |  | Tower A | Super Structure | L31
41462 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2025-09-10 | 2025-09-12 | FAPA Cabling | 100 | 0 |  | 2025-09-15 |  | 2025-09-16 |  | Tower A | Super Structure | L32
42261 |  | Started |  | 2024-09-23 | 2025-10-08 | Finishes after 1st Fix | 100 | 24 |  | 2025-09-15 | 2025-07-27 | 2025-10-29
42262 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2024-09-23 | 2024-10-17 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-09-15 |  | 2025-10-10 |  | Tower A | Super Structure | L10 | Finishes | Blockwork
42333 |  | Not Committed |  | 2024-10-25 | 2025-10-21 | Finishes after 1st Fix | 100 | 0 |  | 2025-09-15 |  | 2025-11-11
42334 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2024-10-25 | 2024-11-18 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-09-15 |  | 2025-10-09 |  | Tower A | Super Structure | L14 | Finishes | Blockwork
42358 |  | Not Committed |  | 2024-11-04 | 2025-10-27 | Finishes after 1st Fix | 100 | 0 |  | 2025-09-15 |  | 2025-11-17
42359 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2024-11-04 | 2024-11-26 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-09-15 |  | 2025-10-09 |  | Tower A | Super Structure | L15 | Finishes | Blockwork
47584 |  | Not Committed |  | 2024-09-21 | 2024-11-15 | Pour 12 (PB-A to PB-E) | 100 | 0 |  | 2025-09-15 |  | 2025-10-11
47585 |  | Not Ready |  | 2024-09-21 | 2024-09-24 | Dressing & PCC | 100 | 0 |  | 2025-09-15 |  | 2025-09-18
47585 |  | Not Ready |  | 2024-09-21 | 2024-09-24 | Dressing & PCC | 100 | 0 |  | 2025-09-15 |  | 2025-09-18 |  |  |  |  | RCC Super Structure | Foundation RCC Works
47585 |  | Not Ready |  | 2024-09-21 | 2024-09-24 | Dressing & PCC | 100 | 0 |  | 2025-09-15 |  | 2025-09-18 |  |  |  |  | RCC Sub Structure | Raft RCC Works
48402 |  | Not Committed |  | 2025-01-30 | 2025-03-05 | Pour RT-2 | 100 | 0 |  | 2025-09-15 |  | 2025-10-23
48403 | Retail - Sub structure - B2 to B1 - P2 | Not Ready |  | 2025-01-30 | 2025-02-15 | Columns/ Walls_NTA | 100 | 0 |  | 2025-09-15 |  | 2025-10-04 |  | Retail | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
48403 | Retail - Sub structure - B2 to B1 - P2 | Not Ready |  | 2025-01-30 | 2025-02-15 | Columns/ Walls_NTA | 100 | 0 |  | 2025-09-15 |  | 2025-10-04 |  | Retail | Sub Structure | B2
8467 | T-14-9th Floor | Complete | RCC | 2025-08-13 | 2025-08-14 | Slab& Beam RCC | 307 | 307 | CUM | 2025-09-16 | 2025-10-28 | 2025-09-17 | 2025-10-29
8554 | T-14-1st Floor Flat Area | Not Ready | Toilets False Celing | 2025-08-19 | 2025-09-20 | Toilets False Celing | 100 | 0 |  | 2025-09-16 |  | 2025-10-17
9525 | T-16-7th Floor | Complete | Slab& Beam Steel & Conduting | 2025-10-08 | 2025-10-11 | Slab& Beam Steel & Conduting | 14 | 14 | MT | 2025-09-16 | 2025-10-22 | 2025-09-18 | 2025-10-24
9643 | T-16-2nd Floor Flat Area | Not Ready | Plastering | 2025-10-08 | 2025-11-23 | Plastering-Gypsum | 100 | 0 |  | 2025-09-16 |  | 2025-10-29
9706 |  | Not Ready |  | 2025-11-15 | 2026-09-09 | Common Area | 100 | 0 |  | 2025-09-16 |  | 2026-07-13
10243 | T-21-5th Floor Flat Area | Not Ready | Toilet flooring | 2025-10-18 | 2025-11-22 | Toilet flooring | 100 | 0 |  | 2025-09-16 |  | 2025-10-17
10318 | T-21-8th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-10-11 | 2025-10-28 | Electrical DB Fixing | 100 | 0 |  | 2025-09-16 |  | 2025-10-02
10344 | T-21-9th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-10-11 | 2025-10-28 | Electrical DB Fixing | 100 | 0 |  | 2025-09-16 |  | 2025-10-02
10663 | T-20-1st Floor Flat Area | Not Ready | Window | 2025-10-22 | 2025-11-15 | Window | 100 | 0 |  | 2025-09-16 |  | 2025-10-10
11092 | T-19-8th Floor | Complete | Slab& Beam Steel & Conduting | 2025-09-30 | 2025-10-04 | Slab& Beam Steel & Conduting | 11.3 | 11.3 | MT | 2025-09-16 | 2025-10-25 | 2025-09-21 | 2025-10-31
11144 | T-19-GF Flat Area | Not Ready | Toilet flooring | 2025-10-08 | 2025-10-24 | Toilet flooring | 100 | 0 |  | 2025-09-16 |  | 2025-10-05
11160 | T-19-GF Common Area | Not Ready | Dado | 2025-10-06 | 2025-10-28 | Dado | 100 | 0 |  | 2025-09-16 |  | 2025-10-04
11229 | T-19-3rd Floor Flat Area | Not Ready | Plastering | 2025-09-30 | 2025-11-16 | Plastering-Gypsum | 100 | 0 |  | 2025-09-16 |  | 2025-10-30
11800 | T-18-5th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-11-20 | 2025-12-06 | Electrical DB Fixing | 100 | 0 |  | 2025-09-16 |  | 2025-10-01
40609 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2024-03-09 | 2024-03-16 | HVAC Ducting | 100 | 0 |  | 2025-09-16 |  | 2025-09-25 |  | Tower A | Sub Structure | B3 | MEP | HVAC Ducting
40610 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2024-03-09 | 2024-03-27 | Flooring & Dado | 100 | 0 |  | 2025-09-16 |  | 2025-10-06 |  | Tower A | Sub Structure | B3 | Finishes | Flooring & Dado
41478 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2025-09-16 | 2025-09-19 | FAPA Cabling | 100 | 0 |  | 2025-09-16 |  | 2025-09-18 |  | Tower A | Super Structure | L33
42530 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-02-04 | 2025-02-14 | Cement Plastering in wet areas | 100 | 0 |  | 2025-09-16 |  | 2025-09-29 |  | Tower A | Super Structure | L25
42584 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-02-28 | 2025-03-11 | Cement Plastering in wet areas | 100 | 0 |  | 2025-09-16 |  | 2025-09-29 |  | Tower A | Super Structure | L28
8641 | T-14-4th Floor Common Area | Not Ready | Plastering | 2025-08-18 | 2025-09-19 | Plastering-Gypsum | 100 | 0 |  | 2025-09-17 |  | 2025-10-18
8692 |  | Not Ready |  | 2025-09-16 | 2026-04-08 | Common Area | 100 | 0 |  | 2025-09-17 |  | 2026-04-09
10085 | T-21-Terrace | Not Ready | PARAPET | 2025-10-12 | 2025-12-02 | PARAPET | 100 | 0 |  | 2025-09-17 |  | 2025-11-06
10599 | T-20-Terrace | Complete | Shuttering | 2025-10-14 | 2025-10-18 | Slab and Beam Shuttering | 3583 | 3583 | Sqm | 2025-09-17 | 2025-10-31 | 2025-09-23 | 2025-11-08
10737 | T-20-4th Floor Flat Area | Not Ready | Toilet flooring | 2025-10-16 | 2025-11-20 | Toilet flooring | 100 | 0 |  | 2025-09-17 |  | 2025-10-21
10809 | T-20-7th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-10-14 | 2025-11-07 | Plumbing Pipe Line | 100 | 0 |  | 2025-09-17 |  | 2025-10-11
11178 | T-19-1st Floor Flat Area | Not Ready | Dado | 2025-10-08 | 2025-11-06 | Dado | 100 | 0 |  | 2025-09-17 |  | 2025-10-15
11292 |  | Not Ready |  | 2025-11-08 | 2026-07-16 | Common Area | 100 | 0 |  | 2025-09-17 |  | 2026-05-28
11624 | T-18-10th Floor | Complete | Conduiting | 2025-11-21 | 2025-11-24 | Conduiting works | 100 | 100 |  | 2025-09-17 | 2026-01-07 | 2025-09-18 | 2026-01-09
11681 | T-18-GF Common Area | Not Ready | Toilet flooring | 2025-11-14 | 2025-12-01 | Toilet flooring | 100 | 0 |  | 2025-09-17 |  | 2025-10-05
11787 | T-18-4th Floor Common Area | Not Ready | Plastering | 2025-11-21 | 2025-12-24 | Plastering-Gypsum | 100 | 0 |  | 2025-09-17 |  | 2025-10-21
8650 | T-14-5th Floor Flat Area | Not Ready | Blockwork | 2025-08-14 | 2025-09-05 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-09-18 |  | 2025-10-08
8689 | T-14-6th Floor Flat Area | Not Ready | Railing | 2025-08-14 | 2025-09-16 | Balcony Railing | 100 | 0 |  | 2025-09-18 |  | 2025-10-21
9020 | T-15-9th Floor | Complete | RCC | 2025-09-12 | 2025-09-13 | Slab& Beam RCC | 318 | 318 | CUM | 2025-09-18 | 2025-10-11 | 2025-09-18 | 2025-10-12
9100 | T-15-1st Floor Flat Area | Not Ready | Toilets False Celing | 2025-09-17 | 2025-10-21 | Toilets False Celing | 100 | 0 |  | 2025-09-18 |  | 2025-10-22
9172 | T-15-4th Floor Flat Area | Not Ready | Plastering | 2025-09-14 | 2025-10-07 | Plastering-Cement | 100 | 0 |  | 2025-09-18 |  | 2025-10-12
10602 |  | Not Ready |  | 2025-10-23 | 2025-12-20 | Above Terrace | 100 | 0 |  | 2025-09-18 |  | 2025-11-15
10759 | T-20-5th Floor Flat Area | Not Ready | Waterproofing | 2025-10-15 | 2025-12-05 | Waterproofing | 100 | 0 |  | 2025-09-18 |  | 2025-11-07
10824 |  | Not Ready |  | 2025-10-23 | 2026-05-24 | Common Area | 100 | 0 |  | 2025-09-18 |  | 2026-04-18
11623 | T-18-10th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-11-22 | 2025-11-26 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-09-18 | 2026-01-03 | 2025-09-24 | 2026-01-09
11702 | T-18-1st Floor Flat Area | Not Ready | Putty | 2025-11-20 | 2026-02-12 | Putty | 100 | 0 |  | 2025-09-18 |  | 2025-12-12
11820 |  | Not Ready |  | 2025-11-18 | 2026-07-10 | Sixth Floor | 100 | 0 |  | 2025-09-18 |  | 2026-05-12
11821 |  | Not Ready |  | 2025-11-18 | 2026-06-09 | Flat Area | 100 | 0 |  | 2025-09-18 |  | 2026-04-09
39711 | Tower A - Super Structure - Core Wall High Rise L67-68 | Complete | Core Wall RCC Works | 2025-09-06 | 2025-09-06 | Casting | 100 | 100 |  | 2025-09-18 | 2025-09-22 | 2025-09-19 | 2025-09-22 | Tower A | Super Structure | L67 | RCC Super Structure | Core Wall RCC Works
40776 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2024-05-18 | 2024-06-10 | PHE 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-09-18 |  | 2025-10-11 |  | Tower A | Super Structure
40777 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2024-05-18 | 2024-06-04 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-18 |  | 2025-10-06 |  | Tower A | Super Structure |  | MEP | Electrical 1st Fixes
45261 |  | Started |  | 2025-06-21 | 2025-07-09 | P4-P5 | 100 | 48 |  | 2025-09-18 | 2025-09-03 | 2025-10-08
45262 | Tower B - Super Structure - Core & Outer Slab P4-P5 | Started | RCC Works - Vertical | 2025-06-21 | 2025-07-04 | Outer Columns_TA | 100 | 52 | Units | 2025-09-18 | 2025-09-03 | 2025-10-03 |  | Tower B | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
45411 | Tower B - Super Structure - Finishes & MEP - P1 to P2 | Forced Ready | Partition Wall-Blockwork | 2025-05-17 | 2025-06-03 | Partition Walls | 100 | 0 |  | 2025-09-18 |  | 2025-10-06 |  | Tower B | Super Structure
45415 | Tower B - Super Structure - Finishes & MEP - P2 to P3 | Not Ready | Partition Wall-Blockwork | 2025-06-12 | 2025-06-28 | Partition Walls | 100 | 0 |  | 2025-09-18 |  | 2025-10-06 |  | Tower B | Super Structure
45417 |  | Not Committed |  | 2025-06-21 | 2025-07-31 | P3 to P4 | 100 | 0 |  | 2025-09-18 |  | 2025-10-25
45417 |  | Not Committed |  | 2025-06-21 | 2025-07-31 | P3 to P4 | 100 | 0 |  | 2025-09-18 |  | 2025-10-25
45417 |  | Not Committed |  | 2025-06-21 | 2025-07-31 | P3 to P4 | 100 | 0 |  | 2025-09-18 |  | 2025-10-25
45418 | Tower B - Super Structure - Finishes & MEP - P3 to P4 | Not Ready | Partition Wall-Blockwork | 2025-06-21 | 2025-06-26 | De-shuttering & Area clearance | 100 | 0 |  | 2025-09-18 |  | 2025-09-24 |  | Tower B | Super Structure
47582 |  | Not Ready |  | 2024-10-23 | 2024-11-09 | Raft & Footing Reinf_NTA | 100 | 0 |  | 2025-09-18 |  | 2025-10-06
47582 |  | Not Ready |  | 2024-10-23 | 2024-11-09 | Raft & Footing Reinf_NTA | 100 | 0 |  | 2025-09-18 |  | 2025-10-06 |  |  |  |  | RCC Super Structure | Foundation RCC Works
47582 |  | Not Ready |  | 2024-10-23 | 2024-11-09 | Raft & Footing Reinf_NTA | 100 | 0 |  | 2025-09-18 |  | 2025-10-06 |  |  |  |  | RCC Sub Structure | Raft RCC Works
47586 |  | Not Ready |  | 2024-10-23 | 2024-10-28 | Waterproofing-Raft Area | 100 | 0 |  | 2025-09-18 |  | 2025-09-23
8469 | T-14-10th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-08-16 | 2025-08-20 | AL - Shear Walls/Corewalls Steel | 22 | 22 | MT | 2025-09-19 | 2025-10-30 | 2025-09-22 | 2025-11-10
9124 | T-15-2nd Floor Flat Area | Not Ready | Dado | 2025-09-15 | 2025-10-14 | Dado | 100 | 0 |  | 2025-09-19 |  | 2025-10-17
9196 | T-15-5th Floor Flat Area | Not Ready | Blockwork | 2025-09-13 | 2025-10-06 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-09-19 |  | 2025-10-11
9235 | T-15-6th Floor Flat Area | Not Ready | Railing | 2025-09-13 | 2025-10-17 | Balcony Railing | 100 | 0 |  | 2025-09-19 |  | 2025-10-23
9526 | T-16-7th Floor | Complete | RCC | 2025-10-11 | 2025-10-13 | Slab& Beam RCC | 387 | 387 | CUM | 2025-09-19 | 2025-10-25 | 2025-09-22 | 2025-10-27
10083 | T-21-Terrace | Not Ready | LMR ROOM | 2025-10-14 | 2025-12-04 | LMR ROOM | 100 | 0 |  | 2025-09-19 |  | 2025-11-09
10086 | T-21-Terrace | Not Ready | STAIRCASE HR | 2025-10-14 | 2025-12-04 | STAIRCASE HR | 100 | 0 |  | 2025-09-19 |  | 2025-11-09
10600 | T-20-Terrace | Complete | Slab& Beam Steel & Conduting | 2025-10-16 | 2025-10-19 | Slab& Beam Steel & Conduting | 10.8 | 10.8 | MT | 2025-09-19 | 2025-11-08 | 2025-09-21 | 2025-11-11
10813 | T-20-7th Floor Flat Area | Not Ready | Plastering | 2025-10-16 | 2025-12-01 | Plastering-Gypsum | 100 | 0 |  | 2025-09-19 |  | 2025-11-02
11621 | T-18-10th Floor | Complete |  | 2025-11-19 | 2025-12-02 | 9th Floor Roof | 100 | 100 |  | 2025-09-19 | 2025-12-26 | 2025-09-30 | 2026-01-16
39712 | Tower A - Super Structure - Core Wall High Rise L67-68 | Complete | Core Wall RCC Works | 2025-09-08 | 2025-09-08 | ACS Form Release & jump to next level | 100 | 100 |  | 2025-09-19 | 2025-09-24 | 2025-09-20 | 2025-09-24 | Tower A | Super Structure | L67 | RCC Super Structure | Core Wall RCC Works
39995 |  | Started |  | 2025-09-09 | 2025-09-15 | L64-65 | 100 | 50 |  | 2025-09-19 | 2025-09-14 | 2025-09-26 |  |  |  |  | Finishes | Gypsum Plastering Works
39995 |  | Started |  | 2025-09-09 | 2025-09-15 | L64-65 | 100 | 50 |  | 2025-09-19 | 2025-09-14 | 2025-09-26
39996 | Tower A - Super Structure - Core & Outer Slab L64-65 | Complete | RCC Works - Vertical | 2025-09-09 | 2025-09-15 | Outer Columns_TA | 100 | 100 |  | 2025-09-19 | 2025-09-14 | 2025-09-25 | 2025-10-06 | Tower A | Super Structure | L64 | RCC Sub Structure | RCC Works - Vertical
40340 | Tower A - Super Structure - Finishes & MEP - L45 to L46 | Not Ready | Partition Wall-Blockwork | 2025-08-25 | 2025-09-01 | Staircase Area | 100 | 0 |  | 2025-09-19 |  | 2025-09-25 |  | Tower A | Super Structure | L45
40401 |  | Not Committed |  | 2025-09-09 | 2026-01-16 | L61-62 | 100 | 0 |  | 2025-09-19 |  | 2026-02-09
40401 |  | Not Committed |  | 2025-09-09 | 2026-01-16 | L61-62 | 100 | 0 |  | 2025-09-19 |  | 2026-02-09 |  |  |  |  | Finishes | Gypsum Plastering Works
40402 | Tower A - Super Structure - Finishes & MEP - L61 to L62 | Not Ready | Partition Wall-Blockwork | 2025-09-09 | 2025-09-26 | De-shuttering & Area clearance | 100 | 0 |  | 2025-09-19 |  | 2025-10-07 |  | Tower A | Super Structure | L61
40518 | Tower A - Super Structure - Finishes & MEP - L44 to L45 | Not Ready | Gypsum Plastering Works | 2025-09-04 | 2025-09-27 | L44-45 | 100 | 0 |  | 2025-09-19 |  | 2025-10-13 |  | Tower A | Super Structure | L44 | Finishes | Gypsum Plastering Works
40518 | Tower A - Super Structure - Finishes & MEP - L44 to L45 | Not Ready | Gypsum Plastering Works | 2025-09-04 | 2025-09-27 | L44-45 | 100 | 0 |  | 2025-09-19 |  | 2025-10-13 |  | Tower A | Super Structure | L44
41491 |  | Started |  | 2025-06-05 | 2026-04-22 | L34-35 | 100 | 44 |  | 2025-09-19 | 2025-09-19 | 2026-05-14 |  |  |  |  | Finishes | Gypsum Plastering Works
41491 |  | Started |  | 2025-06-05 | 2026-04-22 | L34-35 | 100 | 44 |  | 2025-09-19 | 2025-09-19 | 2026-05-14
41492 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2025-09-19 | 2025-09-22 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 65 |  | 2025-09-19 | 2025-09-19 | 2026-04-02 |  | Tower A | Super Structure | L34 | MEP | FPS 1st Fix - MEP & Finishes
41493 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-09-19 | 2025-09-23 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-19 |  | 2025-09-22 |  | Tower A | Super Structure | L34 | MEP | Electrical 1st Fixes
47594 |  | Complete |  | 2025-09-19 | 2025-09-26 | Section 3_lift 1 | 100 | 100 |  | 2025-09-19 | 2025-09-19 | 2025-09-26 | 2025-09-26
47594 |  | Complete |  | 2025-09-19 | 2025-09-26 | Section 3_lift 1 | 100 | 100 |  | 2025-09-19 | 2025-09-19 | 2025-09-26 | 2025-09-26 |  |  |  | RCC Super Structure | Retaining Wall RCC Works
8654 | T-14-5th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-08-17 | 2025-09-02 | Electrical DB Fixing | 100 | 0 |  | 2025-09-20 |  | 2025-10-06
9022 | T-15-10th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-09-14 | 2025-09-18 | AL - Shear Walls/Corewalls Steel | 24.5 | 24.5 | MT | 2025-09-20 | 2025-10-13 | 2025-09-25 | 2025-10-18
9187 | T-15-4th Floor Common Area | Not Ready | Plastering | 2025-09-16 | 2025-10-20 | Plastering-Gypsum | 100 | 0 |  | 2025-09-20 |  | 2025-10-24
10246 | T-21-5th Floor Flat Area | Not Ready | Putty | 2025-10-25 | 2026-01-19 | Putty | 100 | 0 |  | 2025-09-20 |  | 2025-12-14
10646 | T-20-GF Common Area | Not Ready | Door | 2025-10-25 | 2025-11-19 | Door | 100 | 0 |  | 2025-09-20 |  | 2025-10-11
10740 | T-20-4th Floor Flat Area | Not Ready | Putty | 2025-10-22 | 2026-01-14 | Putty | 100 | 0 |  | 2025-09-20 |  | 2025-12-14
11724 | T-18-2nd Floor Flat Area | Not Ready | Dado | 2025-11-20 | 2025-12-17 | Dado | 100 | 0 |  | 2025-09-20 |  | 2025-10-18
39713 |  | Complete |  | 2025-09-09 | 2025-09-16 | Core Wall L68-69 | 100 | 100 |  | 2025-09-20 | 2025-09-25 | 2025-09-29 | 2025-10-10
39714 | Tower A - Super Structure - Core Wall High Rise L68-69 | Complete | Core Wall RCC Works | 2025-09-09 | 2025-09-09 | Scaffolding & platform | 100 | 100 |  | 2025-09-20 | 2025-09-25 | 2025-09-22 | 2025-09-26 | Tower A | Super Structure | L68 | RCC Super Structure | Core Wall RCC Works
39997 | Tower A - Super Structure - Core & Outer Slab L64-65 | Started | RCC Works - Slab | 2025-09-10 | 2025-09-15 | Outer Slab_TA | 100 | 0 |  | 2025-09-20 | 2025-10-19 | 2025-09-26 |  | Tower A | Super Structure | L64 | RCC Sub Structure | RCC Works - Slab
40168 | Tower A - Super Structure - Finishes & MEP - P4 to P5 | Not Ready | Partition Wall-Blockwork | 2024-05-18 | 2024-05-29 | Staircase Area | 100 | 0 |  | 2025-09-20 |  | 2025-10-03 |  | Tower A | Super Structure
40171 | Tower A - Super Structure - Finishes & MEP - P5 to P6 | Not Ready | Partition Wall-Blockwork | 2024-05-18 | 2024-06-04 | Partition Walls | 100 | 0 |  | 2025-09-20 |  | 2025-10-09 |  | Tower A | Super Structure
40268 | Tower A - Super Structure - Finishes & MEP - L29 to L30 | Not Ready | Partition Wall-Blockwork | 2025-02-22 | 2025-02-27 | Staircase Area | 100 | 0 |  | 2025-09-20 |  | 2025-09-25 |  | Tower A | Super Structure | L29
40271 | Tower A - Super Structure - Finishes & MEP - L30 to L31 | Not Ready | Partition Wall-Blockwork | 2025-02-22 | 2025-03-01 | Partition Walls | 100 | 0 |  | 2025-09-20 |  | 2025-09-27 |  | Tower A | Super Structure | L30
40651 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2024-03-18 | 2024-03-26 | HVAC Ducting | 100 | 0 |  | 2025-09-20 |  | 2025-09-29 |  | Tower A | Sub Structure | B1 | MEP | HVAC Ducting
40652 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2024-03-18 | 2024-04-04 | Flooring & Dado | 100 | 0 |  | 2025-09-20 |  | 2025-10-09 |  | Tower A | Sub Structure | B1 | Finishes | Flooring & Dado
42264 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Apartment Area | Started | Flooring & Dado - MEP & Finishes | 2025-09-20 | 2025-10-08 | Flooring & Dado works | 100 | 46 | Units | 2025-09-20 | 2025-07-27 | 2025-10-29 |  | Tower A | Super Structure | L10 | Finishes | Flooring & Dado
42494 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-01-28 | 2025-02-07 | Cement Plastering in wet areas | 100 | 0 |  | 2025-09-20 |  | 2025-10-03 |  | Tower A | Super Structure | L23
42512 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-02-05 | 2025-02-10 | Cement Plastering in wet areas | 100 | 0 |  | 2025-09-20 |  | 2025-09-26 |  | Tower A | Super Structure | L24
42548 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-02-21 | 2025-03-04 | Cement Plastering in wet areas | 100 | 0 |  | 2025-09-20 |  | 2025-10-03 |  | Tower A | Super Structure | L26
42836 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-08-09 | 2025-08-22 | Cement Plastering in wet areas | 100 | 0 |  | 2025-09-20 |  | 2025-10-01 |  | Tower A | Super Structure | L42
42854 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-08-22 | 2025-09-04 | Cement Plastering in wet areas | 100 | 0 |  | 2025-09-20 |  | 2025-10-01 |  | Tower A | Super Structure | L43
47601 |  | Not Ready |  | 2024-11-02 | 2024-11-09 | Section 10_lift 1 | 100 | 0 |  | 2025-09-20 |  | 2025-09-27
47601 |  | Not Ready |  | 2024-11-02 | 2024-11-09 | Section 10_lift 1 | 100 | 0 |  | 2025-09-20 |  | 2025-09-27 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47611 |  | Not Ready |  | 2024-12-26 | 2025-01-02 | Section 8_lift 2 | 100 | 0 |  | 2025-09-20 |  | 2025-09-27
47611 |  | Not Ready |  | 2024-12-26 | 2025-01-02 | Section 8_lift 2 | 100 | 0 |  | 2025-09-20 |  | 2025-09-27 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47612 |  | Not Ready |  | 2024-11-02 | 2024-11-09 | Section 9_lift 2 | 100 | 0 |  | 2025-09-20 |  | 2025-09-27
47612 |  | Not Ready |  | 2024-11-02 | 2024-11-09 | Section 9_lift 2 | 100 | 0 |  | 2025-09-20 |  | 2025-09-27 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
48338 | Retail - Sub structure - B3 to B2 - P5 | Not Ready |  | 2025-02-03 | 2025-02-10 | Section 11_lift 2 | 100 | 0 |  | 2025-09-20 |  | 2025-09-27 |  | Retail | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
48338 | Retail - Sub structure - B3 to B2 - P5 | Not Ready |  | 2025-02-03 | 2025-02-10 | Section 11_lift 2 | 100 | 0 |  | 2025-09-20 |  | 2025-09-27 |  | Retail | Sub Structure | B3
48339 | Retail - Sub structure - B3 to B2 - P5 | Not Ready |  | 2025-02-11 | 2025-02-18 | Section 12_lift 2 | 100 | 0 |  | 2025-09-20 |  | 2025-09-27 |  | Retail | Sub Structure | B3
48371 | Retail - Sub structure - B3 to B2 - P3 | Not Ready |  | 2024-10-07 | 2024-10-24 | Slab_NTA | 100 | 0 |  | 2025-09-20 |  | 2025-10-08 |  | Retail | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
48371 | Retail - Sub structure - B3 to B2 - P3 | Not Ready |  | 2024-10-07 | 2024-10-24 | Slab_NTA | 100 | 0 |  | 2025-09-20 |  | 2025-10-08 |  | Retail | Sub Structure | B3
8471 | T-14-10th Floor | Complete | Conduiting | 2025-08-18 | 2025-08-21 | Conduiting works | 100 | 100 |  | 2025-09-21 | 2025-11-13 | 2025-09-26 | 2025-11-14
9200 | T-15-5th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-09-15 | 2025-10-01 | Electrical DB Fixing | 100 | 0 |  | 2025-09-21 |  | 2025-10-07
9640 | T-16-2nd Floor Flat Area | Not Ready | Plastering | 2025-10-14 | 2025-11-07 | Plastering-Cement | 100 | 0 |  | 2025-09-21 |  | 2025-10-11
10088 |  | Not Ready |  | 2025-10-16 | 2025-11-04 | Lowering Aluminium FW Material For PH-2 | 100 | 0 |  | 2025-09-21 |  | 2025-10-06
10315 | T-21-8th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-10-16 | 2025-11-10 | Plumbing Pipe Line | 100 | 0 |  | 2025-09-21 |  | 2025-10-12
10341 | T-21-9th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-10-16 | 2025-11-10 | Plumbing Pipe Line | 100 | 0 |  | 2025-09-21 |  | 2025-10-12
11145 | T-19-GF Flat Area | Not Ready | Toilets False Celing | 2025-10-13 | 2025-10-30 | Toilets-False Celing | 100 | 0 |  | 2025-09-21 |  | 2025-10-06
11226 | T-19-3rd Floor Flat Area | Not Ready | Plastering | 2025-10-07 | 2025-10-29 | Plastering-Cement | 100 | 0 |  | 2025-09-21 |  | 2025-10-12
11625 | T-18-10th Floor | Complete | Shuttering | 2025-11-25 | 2025-11-28 | Slab and Beam Shuttering | 3527 | 3527 | Sqm | 2025-09-21 | 2026-01-07 | 2025-09-23 | 2026-01-12
11700 | T-18-1st Floor Flat Area | Not Ready | Toilets False Celing | 2025-11-22 | 2025-12-25 | Toilets False Celing | 100 | 0 |  | 2025-09-21 |  | 2025-10-27
11753 | T-18-3rd Floor Flat Area | Not Ready | Flooring & skirting | 2025-11-26 | 2026-01-09 | Flooring & skirting | 100 | 0 |  | 2025-09-21 |  | 2025-11-07
11797 | T-18-5th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-11-25 | 2025-12-17 | Plumbing Pipe Line | 100 | 0 |  | 2025-09-21 |  | 2025-10-13
8470 | T-14-10th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-08-19 | 2025-08-23 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-09-22 | 2025-11-08 | 2025-09-27 | 2025-11-15
8579 | T-14-2nd Floor Flat Area | Not Ready | Toilet flooring | 2025-08-25 | 2025-09-26 | Toilet flooring | 100 | 0 |  | 2025-09-22 |  | 2025-10-23
8607 | T-14-3rd Floor Flat Area | Not Ready | Flooring & skirting | 2025-08-23 | 2025-10-07 | Flooring & skirting | 100 | 0 |  | 2025-09-22 |  | 2025-11-05
9024 | T-15-10th Floor | Complete | Conduiting | 2025-09-16 | 2025-09-19 | Conduiting works | 100 | 100 |  | 2025-09-22 | 2025-10-18 | 2025-09-24 | 2025-10-21
9246 |  | Not Ready |  | 2025-09-27 | 2026-05-30 | Seventh Floor | 100 | 0 |  | 2025-09-22 |  | 2026-05-26
9247 |  | Not Ready |  | 2025-09-27 | 2026-05-04 | Flat Area | 100 | 0 |  | 2025-09-22 |  | 2026-04-28
9597 | T-16-GF Common Area | Not Ready | Waterproofing | 2025-10-10 | 2025-11-04 | Waterproofing | 100 | 0 |  | 2025-09-22 |  | 2025-10-14
9599 | T-16-GF Common Area | Not Ready | Plastering | 2025-10-10 | 2025-11-14 | Plastering-Gypsum | 100 | 0 |  | 2025-09-22 |  | 2025-10-26
10087 | T-21-Terrace | Not Ready |  | 2025-10-17 | 2025-12-08 | MISC | 100 | 0 |  | 2025-09-22 |  | 2025-11-15
10601 | T-20-Terrace | Complete | RCC | 2025-10-19 | 2025-10-20 | Slab& Beam RCC | 321 | 321 | CUM | 2025-09-22 | 2025-11-12 | 2025-09-22 | 2025-11-13
10664 | T-20-1st Floor Flat Area | Not Ready | Door | 2025-10-29 | 2025-11-22 | Door | 100 | 0 |  | 2025-09-22 |  | 2025-10-15
11093 | T-19-8th Floor | Complete | RCC | 2025-10-04 | 2025-10-06 | Slab& Beam RCC | 340 | 340 | CUM | 2025-09-22 | 2025-11-01 | 2025-09-23 | 2025-11-02
11163 | T-19-GF Common Area | Not Ready | Flooring & skirting | 2025-10-11 | 2025-11-26 | Flooring & skirting | 100 | 0 |  | 2025-09-22 |  | 2025-11-04
11682 | T-18-GF Common Area | Not Ready | Toilets False Celing | 2025-11-20 | 2025-12-06 | Toilets False Celing | 100 | 0 |  | 2025-09-22 |  | 2025-10-10
39715 | Tower A - Super Structure - Core Wall High Rise L68-69 | Complete | Core Wall RCC Works | 2025-09-10 | 2025-09-12 | Reinf & Guide shoes fixing | 100 | 100 |  | 2025-09-22 | 2025-09-25 | 2025-09-25 | 2025-10-02 | Tower A | Super Structure | L68 | RCC Super Structure | Core Wall RCC Works
42369 |  | Not Committed |  | 2024-12-04 | 2025-11-01 | Finishes after 1st Fix | 100 | 0 |  | 2025-09-22 |  | 2025-11-22
42370 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2024-12-04 | 2024-12-27 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-09-22 |  | 2025-10-16 |  | Tower A | Super Structure | L16 | Finishes | Blockwork
42387 |  | Not Committed |  | 2024-11-14 | 2025-11-07 | Finishes after 1st Fix | 100 | 0 |  | 2025-09-22 |  | 2025-11-28
42388 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2024-11-14 | 2024-12-06 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-09-22 |  | 2025-10-16 |  | Tower A | Super Structure | L17 | Finishes | Blockwork
42405 |  | Not Committed |  | 2024-11-22 | 2025-11-13 | Finishes after 1st Fix | 100 | 0 |  | 2025-09-22 |  | 2025-11-12
42406 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2024-11-22 | 2024-12-14 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-09-22 |  | 2025-10-16 |  | Tower A | Super Structure | L18 | Finishes | Blockwork
42423 |  | Not Committed |  | 2025-01-15 | 2025-11-19 | Finishes after 1st Fix | 100 | 0 |  | 2025-09-22 |  | 2025-11-18
42424 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-01-15 | 2025-02-06 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-09-22 |  | 2025-10-16 |  | Tower A | Super Structure | L19 | Finishes | Blockwork
42476 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-01-25 | 2025-02-05 | Cement Plastering in wet areas | 100 | 0 |  | 2025-09-22 |  | 2025-10-03 |  | Tower A | Super Structure | L22
8521 | T-14-GF Flat Area | Not Ready | Putty | 2025-08-27 | 2025-09-17 | Putty | 100 | 0 |  | 2025-09-23 |  | 2025-10-15
9023 | T-15-10th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-09-17 | 2025-09-22 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-09-23 | 2025-10-16 | 2025-09-28 | 2025-10-20
9028 | T-15-11th Floor | Complete |  | 2025-09-28 | 2025-10-13 | 10th Floor Roof | 100 | 100 |  | 2025-09-23 | 2025-10-28 | 2025-10-07 | 2025-11-07
9655 | T-16-2nd Floor Common Area | Not Ready | Plastering | 2025-10-16 | 2025-11-20 | Plastering-Gypsum | 100 | 0 |  | 2025-09-23 |  | 2025-10-27
9664 | T-16-3rd Floor Flat Area | Not Ready | Blockwork | 2025-10-13 | 2025-11-06 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-09-23 |  | 2025-10-15
9703 | T-16-4th Floor Flat Area | Not Ready | Railing | 2025-10-13 | 2025-11-17 | Balcony Railing | 100 | 0 |  | 2025-09-23 |  | 2025-10-27
10084 | T-21-Terrace | Not Ready | OHT | 2025-10-18 | 2025-12-09 | OHT | 100 | 0 |  | 2025-09-23 |  | 2025-11-16
10198 | T-21-3rd Floor Flat Area | Not Ready | 1st Coat Painting | 2025-10-30 | 2026-01-23 | 1st Coat Painting | 100 | 0 |  | 2025-09-23 |  | 2025-12-16
10319 | T-21-8th Floor Flat Area | Not Ready | Plastering | 2025-10-18 | 2025-12-03 | Plastering-Gypsum | 100 | 0 |  | 2025-09-23 |  | 2025-11-08
10330 |  | Not Ready |  | 2025-10-27 | 2026-06-04 | Common Area | 100 | 0 |  | 2025-09-23 |  | 2026-05-02
10345 | T-21-9th Floor Flat Area | Not Ready | Plastering | 2025-10-18 | 2025-12-03 | Plastering-Gypsum | 100 | 0 |  | 2025-09-23 |  | 2025-11-08
10356 |  | Not Ready |  | 2025-10-27 | 2026-06-25 | Common Area | 100 | 0 |  | 2025-09-23 |  | 2026-05-25
10834 | T-20-8th Floor Flat Area | Not Ready | Blockwork | 2025-10-20 | 2025-11-13 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-09-23 |  | 2025-10-15
10860 | T-20-9th Floor Flat Area | Not Ready | Blockwork | 2025-10-20 | 2025-11-13 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-09-23 |  | 2025-10-15
10873 | T-20-9th Floor Flat Area | Not Ready | Railing | 2025-10-20 | 2025-11-24 | Balcony Railing | 100 | 0 |  | 2025-09-23 |  | 2025-10-26
10899 | T-20-10th Floor Flat Area | Not Ready | Railing | 2025-10-20 | 2025-11-24 | Balcony Railing | 100 | 0 |  | 2025-09-23 |  | 2025-10-26
11241 | T-19-3rd Floor Common Area | Not Ready | Plastering | 2025-10-09 | 2025-11-13 | Plastering-Gypsum | 100 | 0 |  | 2025-09-23 |  | 2025-10-26
11626 | T-18-10th Floor | Complete | Slab& Beam Steel & Conduting | 2025-11-27 | 2025-12-01 | Slab& Beam Steel & Conduting | 10.8 | 10.8 | MT | 2025-09-23 | 2026-01-10 | 2025-09-23 | 2026-01-14
11786 |  | Not Ready |  | 2025-11-21 | 2026-09-15 | Common Area | 100 | 0 |  | 2025-09-23 |  | 2026-07-16
11801 | T-18-5th Floor Flat Area | Not Ready | Plastering | 2025-11-27 | 2026-01-10 | Plastering-Gypsum | 100 | 0 |  | 2025-09-23 |  | 2025-11-09
39716 | Tower A - Super Structure - Core Wall High Rise L68-69 | Complete | Core Wall RCC Works | 2025-09-11 | 2025-09-13 | ACS Form Closing & Alignment | 100 | 100 |  | 2025-09-23 | 2025-10-03 | 2025-09-26 | 2025-10-07 | Tower A | Super Structure | L68 | RCC Super Structure | Core Wall RCC Works
41494 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2025-09-23 | 2025-09-25 | FAPA Cabling | 100 | 0 |  | 2025-09-23 |  | 2025-09-24 |  | Tower A | Super Structure | L34
8601 | T-14-3rd Floor Flat Area | Not Ready | Waterproofing | 2025-08-23 | 2025-10-13 | Waterproofing | 100 | 0 |  | 2025-09-24 |  | 2025-11-13
9528 | T-16-8th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-10-14 | 2025-10-18 | AL - Shear Walls/Corewalls Steel | 25 | 25 | MT | 2025-09-24 | 2025-10-28 | 2025-09-26 | 2025-11-04
10244 | T-21-5th Floor Flat Area | Not Ready | Toilets False Celing | 2025-10-28 | 2025-12-01 | Toilets False Celing | 100 | 0 |  | 2025-09-24 |  | 2025-10-28
10268 | T-21-6th Floor Flat Area | Not Ready | Dado | 2025-10-29 | 2025-11-27 | Dado | 100 | 0 |  | 2025-09-24 |  | 2025-10-22
10785 | T-20-6th Floor Flat Area | Not Ready | Waterproofing | 2025-10-23 | 2025-11-27 | Waterproofing | 100 | 0 |  | 2025-09-24 |  | 2025-10-27
10810 | T-20-7th Floor Flat Area | Not Ready | Plastering | 2025-10-21 | 2025-11-14 | Plastering-Cement | 100 | 0 |  | 2025-09-24 |  | 2025-10-16
11179 | T-19-1st Floor Flat Area | Not Ready | Toilet flooring | 2025-10-15 | 2025-11-19 | Toilet flooring | 100 | 0 |  | 2025-09-24 |  | 2025-10-27
11207 | T-19-2nd Floor Flat Area | Not Ready | Flooring & skirting | 2025-10-14 | 2025-11-29 | Flooring & skirting | 100 | 0 |  | 2025-09-24 |  | 2025-11-07
11250 | T-19-4th Floor Flat Area | Not Ready | Blockwork | 2025-10-06 | 2025-10-28 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-09-24 |  | 2025-10-14
11289 | T-19-5th Floor Flat Area | Not Ready | Railing | 2025-10-06 | 2025-11-10 | Balcony Railing | 100 | 0 |  | 2025-09-24 |  | 2025-10-27
11627 | T-18-10th Floor | Complete | RCC | 2025-12-01 | 2025-12-02 | Slab& Beam RCC | 330.8 | 330.8 | CUM | 2025-09-24 | 2026-01-15 | 2025-09-25 | 2026-01-16
40596 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | FAPA Cabling - MEP & Finishes | 2024-03-19 | 2024-03-30 | FAPA Cabling | 100 | 0 |  | 2025-09-24 |  | 2025-10-06 |  | Tower A | Sub Structure | B3
40639 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | FAPA Cabling - MEP & Finishes | 2024-03-01 | 2024-03-12 | FAPA Cabling | 100 | 0 |  | 2025-09-24 |  | 2025-10-06 |  | Tower A | Sub Structure | B2
40693 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | FAPA Cabling - MEP & Finishes | 2024-04-24 | 2024-05-06 | FAPA Cabling | 100 | 0 |  | 2025-09-24 |  | 2025-10-06 |  | Tower A | Super Structure | GF
40724 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | FAPA Cabling - MEP & Finishes | 2024-04-30 | 2024-05-11 | FAPA Cabling | 100 | 0 |  | 2025-09-24 |  | 2025-10-06 |  | Tower A | Super Structure
40751 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | FAPA Cabling - MEP & Finishes | 2024-05-13 | 2024-05-23 | FAPA Cabling | 100 | 0 |  | 2025-09-24 |  | 2025-10-06 |  | Tower A | Super Structure
40779 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | HVAC Ducting - MEP & Finishes | 2024-05-24 | 2024-06-10 | HVAC Ducting/ Fan Installations | 100 | 0 |  | 2025-09-24 |  | 2025-10-11 |  | Tower A | Super Structure |  | MEP | HVAC Ducting
40859 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | FAPA Cabling - MEP & Finishes | 2024-07-18 | 2024-07-30 | FAPA Cabling | 100 | 0 |  | 2025-09-24 |  | 2025-10-06 |  | Tower A | Super Structure
42566 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-03-01 | 2025-03-12 | Cement Plastering in wet areas | 100 | 0 |  | 2025-09-24 |  | 2025-10-07 |  | Tower A | Super Structure | L27
42638 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-05-06 | 2025-05-16 | Cement Plastering in wet areas | 100 | 0 |  | 2025-09-24 |  | 2025-10-07 |  | Tower A | Super Structure | L31
44243 | Tower A | Not Ready | High Side Procurement | 2025-10-21 | 2026-04-07 | DG Set | 100 | 0 |  | 2025-09-24 |  | 2026-03-11 |  | Tower A | --
45407 | Tower B - Super Structure - Finishes & MEP - GF to P1 | Not Ready | Partition Wall-Blockwork | 2025-05-09 | 2025-05-31 | Partition Walls | 100 | 0 |  | 2025-09-24 |  | 2025-10-17 |  | Tower B | Super Structure | GF
45419 | Tower B - Super Structure - Finishes & MEP - P3 to P4 | Not Ready | Partition Wall-Blockwork | 2025-06-27 | 2025-07-15 | Partition Walls | 100 | 0 |  | 2025-09-24 |  | 2025-10-13 |  | Tower B | Super Structure
47285 |  | Not Committed |  | 2027-04-05 | 2028-06-10 | L42-43 (Refuge) | 100 | 0 |  | 2025-09-24 |  | 2028-07-03
47292 |  | Not Committed |  | 2027-09-08 | 2027-11-02 | Finishes after 1st Fix | 100 | 0 |  | 2025-09-24 |  | 2027-09-18
47293 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2027-09-08 | 2027-09-20 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-09-24 |  | 2025-10-06 |  | Tower B | Super Structure | L42 | Finishes | Blockwork
47587 |  | Not Ready |  | 2024-10-29 | 2024-11-09 | Raft & Footing Reinf_NTA | 100 | 0 |  | 2025-09-24 |  | 2025-10-06
47587 |  | Not Ready |  | 2024-10-29 | 2024-11-09 | Raft & Footing Reinf_NTA | 100 | 0 |  | 2025-09-24 |  | 2025-10-06 |  |  |  |  | RCC Super Structure | Foundation RCC Works
47587 |  | Not Ready |  | 2024-10-29 | 2024-11-09 | Raft & Footing Reinf_NTA | 100 | 0 |  | 2025-09-24 |  | 2025-10-06 |  |  |  |  | RCC Sub Structure | Raft RCC Works
48154 | Retail - Foundation P5 | Not Ready |  | 2025-02-06 | 2025-02-11 | Fwk & Casting_NTA | 100 | 0 |  | 2025-09-24 |  | 2025-09-29 |  | Retail | Foundation |  | RCC Sub Structure | Raft RCC Works
48154 | Retail - Foundation P5 | Not Ready |  | 2025-02-06 | 2025-02-11 | Fwk & Casting_NTA | 100 | 0 |  | 2025-09-24 |  | 2025-09-29 |  | Retail | Foundation |  | RCC Super Structure | Foundation RCC Works
48154 | Retail - Foundation P5 | Not Ready |  | 2025-02-06 | 2025-02-11 | Fwk & Casting_NTA | 100 | 0 |  | 2025-09-24 |  | 2025-09-29 |  | Retail | Foundation
8472 | T-14-10th Floor | Complete | Shuttering | 2025-08-22 | 2025-08-26 | Slab and Beam Shuttering | 3605 | 3605 | Sqm | 2025-09-25 | 2025-11-10 | 2025-09-27 | 2025-11-17
8651 | T-14-5th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-08-22 | 2025-09-13 | Plumbing Pipe Line | 100 | 0 |  | 2025-09-25 |  | 2025-10-16
9153 | T-15-3rd Floor Flat Area | Not Ready | Flooring & skirting | 2025-09-22 | 2025-11-07 | Flooring & skirting | 100 | 0 |  | 2025-09-25 |  | 2025-11-09
9212 |  | Not Ready |  | 2025-09-30 | 2026-06-10 | Common Area | 100 | 0 |  | 2025-09-25 |  | 2026-06-05
9583 | T-16-GF Flat Area | Not Ready | Dado | 2025-10-18 | 2025-11-11 | Dado | 100 | 0 |  | 2025-09-25 |  | 2025-10-17
9668 | T-16-3rd Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-10-15 | 2025-11-03 | Electrical DB Fixing | 100 | 0 |  | 2025-09-25 |  | 2025-10-10
10738 | T-20-4th Floor Flat Area | Not Ready | Toilets False Celing | 2025-10-24 | 2025-11-28 | Toilets False Celing | 100 | 0 |  | 2025-09-25 |  | 2025-10-28
10762 | T-20-5th Floor Flat Area | Not Ready | Dado | 2025-10-22 | 2025-11-21 | Dado | 100 | 0 |  | 2025-09-25 |  | 2025-10-23
10838 | T-20-8th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-10-22 | 2025-11-10 | Electrical DB Fixing | 100 | 0 |  | 2025-09-25 |  | 2025-10-12
10864 | T-20-9th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-10-22 | 2025-11-10 | Electrical DB Fixing | 100 | 0 |  | 2025-09-25 |  | 2025-10-12
11095 | T-19-9th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-10-07 | 2025-10-11 | AL - Shear Walls/Corewalls Steel | 28.4 | 28.4 | MT | 2025-09-25 | 2025-11-03 | 2025-09-30 | 2025-11-08
40344 | Tower A - Super Structure - Finishes & MEP - L46 to L47 | Not Ready | Partition Wall-Blockwork | 2025-09-06 | 2025-09-11 | Staircase Area | 100 | 0 |  | 2025-09-25 |  | 2025-10-01 |  | Tower A | Super Structure | L46
41507 |  | Started |  | 2025-06-10 | 2026-04-24 | L35-36 | 100 | 44 |  | 2025-09-25 | 2025-09-25 | 2026-05-16 |  |  |  |  | Finishes | Gypsum Plastering Works
41507 |  | Started |  | 2025-06-10 | 2026-04-24 | L35-36 | 100 | 44 |  | 2025-09-25 | 2025-09-25 | 2026-05-16
41508 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2025-09-25 | 2025-09-27 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 65 |  | 2025-09-25 | 2025-09-25 | 2026-04-04 |  | Tower A | Super Structure | L35 | MEP | FPS 1st Fix - MEP & Finishes
41509 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-09-25 | 2025-09-29 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-09-25 |  | 2025-09-27 |  | Tower A | Super Structure | L35 | MEP | Electrical 1st Fixes
42884 |  | Not Committed |  | 2025-09-04 | 2026-08-25 | L45-46 | 100 | 0 |  | 2025-09-25 |  | 2026-08-05
42884 |  | Not Committed |  | 2025-09-04 | 2026-08-25 | L45-46 | 100 | 0 |  | 2025-09-25 |  | 2026-08-05 |  |  |  |  | Finishes | Gypsum Plastering Works
42885 |  | Not Committed |  | 2025-09-04 | 2025-10-04 | MEP 1st Fixes | 100 | 0 |  | 2025-09-25 |  | 2025-10-27
42886 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2025-09-04 | 2025-09-11 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-09-25 |  | 2025-10-04 |  | Tower A | Super Structure | L45 | MEP | FPS 1st Fix - MEP & Finishes
42887 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-09-04 | 2025-09-09 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2025-09-25 |  | 2025-10-01 |  | Tower A | Super Structure | L45 | MEP | Electrical 1st Fixes
42888 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2025-09-04 | 2025-09-11 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2025-09-25 |  | 2025-10-04 |  | Tower A | Super Structure | L45
42889 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2025-09-04 | 2025-09-22 | Wet Area Waterproofing | 100 | 0 |  | 2025-09-25 |  | 2025-10-14 |  | Tower A | Super Structure | L45
9025 | T-15-10th Floor | Complete | Shuttering | 2025-09-20 | 2025-09-25 | Slab and Beam Shuttering | 3715 | 3715 | Sqm | 2025-09-26 | 2025-10-21 | 2025-09-29 | 2025-10-25
9067 | T-15-GF Flat Area | Not Ready | Putty | 2025-09-26 | 2025-10-19 | Putty | 100 | 0 |  | 2025-09-26 |  | 2025-10-18
9125 | T-15-2nd Floor Flat Area | Not Ready | Toilet flooring | 2025-09-23 | 2025-10-27 | Toilet flooring | 100 | 0 |  | 2025-09-26 |  | 2025-10-29
9197 | T-15-5th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-09-20 | 2025-10-14 | Plumbing Pipe Line | 100 | 0 |  | 2025-09-26 |  | 2025-10-18
9530 | T-16-8th Floor | Complete | Conduiting | 2025-10-16 | 2025-10-20 | Conduiting works | 100 | 100 |  | 2025-09-26 | 2025-11-08 | 2025-10-01 | 2025-11-10
9766 |  | Not Ready |  | 2025-11-27 | 2026-07-27 | Seventh Floor | 100 | 0 |  | 2025-09-26 |  | 2026-05-30
9767 |  | Not Ready |  | 2025-11-27 | 2026-07-01 | Flat Area | 100 | 0 |  | 2025-09-26 |  | 2026-05-04
10291 | T-21-7th Floor Flat Area | Not Ready | Waterproofing | 2025-10-27 | 2025-11-30 | Waterproofing | 100 | 0 |  | 2025-09-26 |  | 2025-10-30
10605 | T-20-Terrace | Not Ready | PARAPET | 2025-10-23 | 2025-12-13 | PARAPET | 100 | 0 |  | 2025-09-26 |  | 2025-11-17
10825 | T-20-7th Floor Common Area | Not Ready |  | 2025-10-23 | 2025-11-27 | Plastering Gypsum | 100 | 0 |  | 2025-09-26 |  | 2025-10-29
11161 | T-19-GF Common Area | Not Ready | Toilet flooring | 2025-10-16 | 2025-11-04 | Toilet flooring | 100 | 0 |  | 2025-09-26 |  | 2025-10-12
11201 | T-19-2nd Floor Flat Area | Not Ready | Waterproofing | 2025-10-14 | 2025-12-04 | Waterproofing | 100 | 0 |  | 2025-09-26 |  | 2025-11-15
11254 | T-19-4th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-10-08 | 2025-10-24 | Electrical DB Fixing | 100 | 0 |  | 2025-09-26 |  | 2025-10-13
11747 | T-18-3rd Floor Flat Area | Not Ready | Waterproofing | 2025-11-26 | 2026-01-14 | Waterproofing | 100 | 0 |  | 2025-09-26 |  | 2025-11-16
11822 | T-18-6th Floor Flat Area | Not Ready | Blockwork | 2025-12-02 | 2025-12-24 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-09-26 |  | 2025-10-19
11861 | T-18-7th Floor Flat Area | Not Ready | Railing | 2025-12-02 | 2026-01-03 | Balcony Railing | 100 | 0 |  | 2025-09-26 |  | 2025-11-01
39717 | Tower A - Super Structure - Core Wall High Rise L68-69 | Complete | Core Wall RCC Works | 2025-09-15 | 2025-09-15 | Casting | 100 | 100 |  | 2025-09-26 | 2025-10-03 | 2025-09-27 | 2025-10-07 | Tower A | Super Structure | L68 | RCC Super Structure | Core Wall RCC Works
39998 |  | Complete |  | 2025-09-16 | 2025-10-04 | L65-66 | 100 | 100 |  | 2025-09-26 | 2025-10-12 | 2025-10-15 | 2025-10-30
39998 |  | Complete |  | 2025-09-16 | 2025-10-04 | L65-66 | 100 | 100 |  | 2025-09-26 | 2025-10-12 | 2025-10-15 | 2025-10-30 |  |  |  | Finishes | Gypsum Plastering Works
39999 | Tower A - Super Structure - Core & Outer Slab L65-66 | Complete | RCC Works - Vertical | 2025-09-16 | 2025-09-29 | Outer Columns_TA | 100 | 100 |  | 2025-09-26 | 2025-10-12 | 2025-10-10 | 2025-10-28 | Tower A | Super Structure | L65 | RCC Sub Structure | RCC Works - Vertical
40405 |  | Not Committed |  | 2025-09-16 | 2026-01-24 | L62-63 | 100 | 0 |  | 2025-09-26 |  | 2026-02-17
40405 |  | Not Committed |  | 2025-09-16 | 2026-01-24 | L62-63 | 100 | 0 |  | 2025-09-26 |  | 2026-02-17 |  |  |  |  | Finishes | Gypsum Plastering Works
40406 | Tower A - Super Structure - Finishes & MEP - L62 to L63 | Not Ready | Partition Wall-Blockwork | 2025-09-16 | 2025-10-04 | De-shuttering & Area clearance | 100 | 0 |  | 2025-09-26 |  | 2025-10-15 |  | Tower A | Super Structure | L62
40479 | Tower A - Super Structure - Finishes & MEP - P6 to L7 | Not Ready | Gypsum Plastering Works | 2024-06-28 | 2024-08-06 | P6 to L7 | 100 | 0 |  | 2025-09-26 |  | 2025-11-01 |  | Tower A | Super Structure |  | Finishes | Gypsum Plastering Works
40479 | Tower A - Super Structure - Finishes & MEP - P6 to L7 | Not Ready | Gypsum Plastering Works | 2024-06-28 | 2024-08-06 | P6 to L7 | 100 | 0 |  | 2025-09-26 |  | 2025-11-01 |  | Tower A | Super Structure
40626 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | False Ceiling - MEP & Finishes | 2024-03-04 | 2024-03-14 | False Ceiling | 100 | 0 |  | 2025-09-26 |  | 2025-10-09 |  | Tower A | Sub Structure | B2 | Finishes | False Ceiling
40921 |  | Not Committed |  | 2025-09-16 | 2025-12-20 | L55-65 | 100 | 0 |  | 2025-09-26 |  | 2026-01-01
40921 |  | Not Committed |  | 2025-09-16 | 2025-12-20 | L55-65 | 100 | 0 |  | 2025-09-26 |  | 2026-01-01
40922 | Tower A - Super Structure - Finishes & MEP - L55 to L65 | Not Ready |  | 2025-09-16 | 2025-10-10 | FHR Shaft Risers | 100 | 0 |  | 2025-09-26 |  | 2025-10-22 |  | Tower A | Super Structure | L55
40924 | Tower A - Super Structure - Finishes & MEP - L55 to L65 | Not Ready |  | 2025-09-16 | 2025-11-10 | Domestic Water & Flushing Riser in Plumbing Shaft | 100 | 0 |  | 2025-09-26 |  | 2025-11-20 |  | Tower A | Super Structure | L55
40926 | Tower A - Super Structure - Finishes & MEP - L55 to L65 | Not Ready |  | 2025-09-16 | 2025-10-23 | Shaft Cable Tray in Electrical Shaft | 100 | 0 |  | 2025-09-26 |  | 2025-11-03 |  | Tower A | Super Structure | L55
42513 |  | Not Committed |  | 2025-02-11 | 2025-12-12 | Finishes after 1st Fix | 100 | 0 |  | 2025-09-26 |  | 2025-11-28
42514 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-02-11 | 2025-03-05 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-09-26 |  | 2025-10-22 |  | Tower A | Super Structure | L24 | Finishes | Blockwork
42596 |  | Not Committed |  | 2025-02-28 | 2026-07-04 | L29-30 | 100 | 0 |  | 2025-09-26 |  | 2026-07-02
42596 |  | Not Committed |  | 2025-02-28 | 2026-07-04 | L29-30 | 100 | 0 |  | 2025-09-26 |  | 2026-07-02 |  |  |  |  | Finishes | Gypsum Plastering Works
42597 |  | Not Committed |  | 2025-02-28 | 2025-03-29 | MEP 1st Fixes | 100 | 0 |  | 2025-09-26 |  | 2025-10-27
42598 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2025-02-28 | 2025-03-07 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-09-26 |  | 2025-10-04 |  | Tower A | Super Structure | L29 | MEP | FPS 1st Fix - MEP & Finishes
42599 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-02-28 | 2025-03-05 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2025-09-26 |  | 2025-10-01 |  | Tower A | Super Structure | L29 | MEP | Electrical 1st Fixes
42600 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2025-02-28 | 2025-03-07 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2025-09-26 |  | 2025-10-04 |  | Tower A | Super Structure | L29
42601 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2025-02-28 | 2025-03-18 | Wet Area Waterproofing | 100 | 0 |  | 2025-09-26 |  | 2025-10-14 |  | Tower A | Super Structure | L29
42656 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-05-14 | 2025-05-24 | Cement Plastering in wet areas | 100 | 0 |  | 2025-09-26 |  | 2025-10-08 |  | Tower A | Super Structure | L32
44544 |  | Not Committed |  | 2024-04-27 | 2026-04-27 | Finishes (Lobby & Floor area) | 100 | 0 |  | 2025-09-26 |  | 2026-12-08
44545 |  | Not Committed |  | 2024-04-27 | 2024-09-18 | B3 to B2 | 100 | 0 |  | 2025-09-26 |  | 2026-01-30
44545 |  | Not Committed |  | 2024-04-27 | 2024-09-18 | B3 to B2 | 100 | 0 |  | 2025-09-26 |  | 2026-01-30
44545 |  | Not Committed |  | 2024-04-27 | 2024-09-18 | B3 to B2 | 100 | 0 |  | 2025-09-26 |  | 2026-01-30
44546 | NTA_Zone 2 - Sub Structure - B3 to B2 | Not Ready | Finishes (Lobby & Floor Area) | 2024-04-27 | 2024-06-20 | VDF Flooring | 100 | 0 |  | 2025-09-26 |  | 2025-11-19 |  | NTA_Zone 2 | Sub Structure | B3
44546 | NTA_Zone 2 - Sub Structure - B3 to B2 | Not Ready | Finishes (Lobby & Floor Area) | 2024-04-27 | 2024-06-20 | VDF Flooring | 100 | 0 |  | 2025-09-26 |  | 2025-11-19 |  | NTA_Zone 2 | Sub Structure | B3
48280 |  | Not Committed |  | 2025-04-15 | 2025-05-09 | Pour RT-5 | 100 | 0 |  | 2025-09-26 |  | 2025-10-22
48281 | Retail - Sub structure - B1 to GF - P5 | Not Ready |  | 2025-04-15 | 2025-04-22 | Section 10_lift 1 | 100 | 0 |  | 2025-09-26 |  | 2025-10-04 |  | Retail | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
48281 | Retail - Sub structure - B1 to GF - P5 | Not Ready |  | 2025-04-15 | 2025-04-22 | Section 10_lift 1 | 100 | 0 |  | 2025-09-26 |  | 2025-10-04 |  | Retail | Sub Structure | B1
48282 | Retail - Sub structure - B1 to GF - P5 | Not Ready |  | 2025-04-15 | 2025-04-22 | Section 11_lift 1 | 100 | 0 |  | 2025-09-26 |  | 2025-10-04 |  | Retail | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
48282 | Retail - Sub structure - B1 to GF - P5 | Not Ready |  | 2025-04-15 | 2025-04-22 | Section 11_lift 1 | 100 | 0 |  | 2025-09-26 |  | 2025-10-04 |  | Retail | Sub Structure | B1
8473 | T-14-10th Floor | Complete | Slab& Beam Steel & Conduting | 2025-08-25 | 2025-08-28 | Slab& Beam Steel & Conduting | 10 | 10 | MT | 2025-09-27 | 2025-11-16 | 2025-10-02 | 2025-11-18
8655 | T-14-5th Floor Flat Area | Not Ready | Plastering | 2025-08-25 | 2025-10-08 | Plastering-Gypsum | 100 | 0 |  | 2025-09-27 |  | 2025-11-12
8752 |  | Not Ready |  | 2025-09-26 | 2026-06-30 | Ninth Floor | 100 | 0 |  | 2025-09-27 |  | 2026-07-01
8753 |  | Not Ready |  | 2025-09-26 | 2026-06-30 | Flat Area | 100 | 0 |  | 2025-09-27 |  | 2026-07-01
9529 | T-16-8th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-10-17 | 2025-10-22 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-09-27 | 2025-11-03 | 2025-09-30 | 2025-11-10
9548 | T-16-11th Floor | Not Ready |  | 2025-11-28 | 2025-12-11 | 10th Floor Roof | 100 | 0 |  | 2025-09-27 |  | 2025-10-11
9621 | T-16-1st Floor Flat Area | Not Ready | Flooring & skirting | 2025-10-22 | 2025-12-06 | Flooring & skirting | 100 | 0 |  | 2025-09-27 |  | 2025-11-11
11097 | T-19-9th Floor | Complete | Conduiting | 2025-10-09 | 2025-10-12 | Conduiting works | 100 | 100 |  | 2025-09-27 | 2025-11-11 | 2025-09-30 | 2025-11-13
11352 |  | Not Ready |  | 2025-11-19 | 2026-07-27 | Eighth Floor | 100 | 0 |  | 2025-09-27 |  | 2026-06-08
11353 |  | Not Ready |  | 2025-11-19 | 2026-07-07 | Flat Area | 100 | 0 |  | 2025-09-27 |  | 2026-05-18
11629 | T-18-11th Floor | Not Ready | AL - Shear Walls/Corewalls Steel | 2025-12-03 | 2025-12-07 | AL - Shear Walls/Corewalls Steel | 20.5 | 0 | MT | 2025-09-27 |  | 2025-10-02
11725 | T-18-2nd Floor Flat Area | Not Ready | Toilet flooring | 2025-11-27 | 2025-12-30 | Toilet flooring | 100 | 0 |  | 2025-09-27 |  | 2025-10-31
39718 | Tower A - Super Structure - Core Wall High Rise L68-69 | Complete | Core Wall RCC Works | 2025-09-16 | 2025-09-16 | ACS Form Release & jump to next level | 100 | 100 |  | 2025-09-27 | 2025-10-09 | 2025-09-29 | 2025-10-10 | Tower A | Super Structure | L68 | RCC Super Structure | Core Wall RCC Works
45263 | Tower B - Super Structure - Core & Outer Slab P4-P5 | Started | RCC Works - Slab | 2025-07-01 | 2025-07-09 | Outer Slab_TA | 100 | 43 | Units | 2025-09-27 | 2025-09-19 | 2025-10-08 |  | Tower B | Super Structure |  | RCC Sub Structure | RCC Works - Slab
47595 |  | Complete |  | 2025-09-27 | 2025-10-06 | Section 4_lift 1 | 100 | 100 |  | 2025-09-27 | 2025-09-27 | 2025-10-06 | 2025-10-06
47595 |  | Complete |  | 2025-09-27 | 2025-10-06 | Section 4_lift 1 | 100 | 100 |  | 2025-09-27 | 2025-09-27 | 2025-10-06 | 2025-10-06 |  |  |  | RCC Super Structure | Retaining Wall RCC Works
48375 |  | Not Committed |  | 2025-02-10 | 2025-03-17 | Pour RT-5 | 100 | 0 |  | 2025-09-27 |  | 2025-11-03
48376 | Retail - Sub structure - B3 to B2 - P5 | Not Ready |  | 2025-02-10 | 2025-02-26 | Columns/ Walls_NTA | 100 | 0 |  | 2025-09-27 |  | 2025-10-15 |  | Retail | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
48376 | Retail - Sub structure - B3 to B2 - P5 | Not Ready |  | 2025-02-10 | 2025-02-26 | Columns/ Walls_NTA | 100 | 0 |  | 2025-09-27 |  | 2025-10-15 |  | Retail | Sub Structure | B3
9026 | T-15-10th Floor | Complete | Slab& Beam Steel & Conduting | 2025-09-23 | 2025-09-26 | Slab& Beam Steel & Conduting | 13 | 13 | MT | 2025-09-28 | 2025-10-23 | 2025-09-29 | 2025-10-25
9147 | T-15-3rd Floor Flat Area | Not Ready | Waterproofing | 2025-09-22 | 2025-11-13 | Waterproofing | 100 | 0 |  | 2025-09-28 |  | 2025-11-20
9201 | T-15-5th Floor Flat Area | Not Ready | Plastering | 2025-09-23 | 2025-11-08 | Plastering-Gypsum | 100 | 0 |  | 2025-09-28 |  | 2025-11-14
10108 | T-21-GF Flat Area | Not Ready | Window | 2025-09-25 | 2025-10-17 | Window | 100 | 0 |  | 2025-09-28 |  | 2025-10-19
10316 | T-21-8th Floor Flat Area | Not Ready | Plastering | 2025-10-24 | 2025-11-17 | Plastering-Cement | 100 | 0 |  | 2025-09-28 |  | 2025-10-22
10342 | T-21-9th Floor Flat Area | Not Ready | Plastering | 2025-10-24 | 2025-11-17 | Plastering-Cement | 100 | 0 |  | 2025-09-28 |  | 2025-10-22
10603 | T-20-Terrace | Not Ready | LMR ROOM | 2025-10-25 | 2025-12-16 | LMR ROOM | 100 | 0 |  | 2025-09-28 |  | 2025-11-17
10606 | T-20-Terrace | Not Ready | STAIRCASE HR | 2025-10-25 | 2025-12-16 | STAIRCASE HR | 100 | 0 |  | 2025-09-28 |  | 2025-11-17
11096 | T-19-9th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-10-10 | 2025-10-14 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-09-28 | 2025-11-07 | 2025-10-03 | 2025-11-12
11798 | T-18-5th Floor Flat Area | Not Ready | Plastering | 2025-12-03 | 2025-12-25 | Plastering-Cement | 100 | 0 |  | 2025-09-28 |  | 2025-10-18
11826 | T-18-6th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-12-04 | 2025-12-20 | Electrical DB Fixing | 100 | 0 |  | 2025-09-28 |  | 2025-10-15
8489 | T-14-Terrace | Not Ready |  | 2025-09-27 | 2025-10-11 | 12th Floor Roof | 100 | 0 |  | 2025-09-29 |  | 2025-10-13
9615 | T-16-1st Floor Flat Area | Not Ready | Waterproofing | 2025-10-22 | 2025-12-12 | Waterproofing | 100 | 0 |  | 2025-09-29 |  | 2025-11-17
10791 | T-20-6th Floor Flat Area | Not Ready | Flooring & skirting | 2025-10-29 | 2025-12-13 | Flooring & skirting | 100 | 0 |  | 2025-09-29 |  | 2025-11-15
11115 | T-19-Terrace | Not Ready |  | 2025-11-20 | 2025-12-03 | 11th Floor Roof | 100 | 0 |  | 2025-09-29 |  | 2025-10-13
11182 | T-19-1st Floor Flat Area | Not Ready | Putty | 2025-10-22 | 2026-01-14 | Putty | 100 | 0 |  | 2025-09-29 |  | 2025-12-25
11631 | T-18-11th Floor | Not Ready | Conduiting | 2025-12-05 | 2025-12-08 | Conduiting works | 100 | 0 |  | 2025-09-29 |  | 2025-09-29
39719 |  | Complete |  | 2025-09-18 | 2025-09-25 | Core Wall L69-70 | 100 | 100 |  | 2025-09-29 | 2025-10-09 | 2025-10-08 | 2025-10-23
39720 | Tower A - Super Structure - Core Wall High Rise L69-70 | Complete | Core Wall RCC Works | 2025-09-18 | 2025-09-18 | Scaffolding & platform | 100 | 100 |  | 2025-09-29 | 2025-10-09 | 2025-09-30 | 2025-10-11 | Tower A | Super Structure | L69 | RCC Super Structure | Core Wall RCC Works
40049 | Tower A - Super Structure - Finishes & MEP - L45 to L46 | Not Ready | CTU Elevators Crash Deck - High Side Services | 2025-02-20 | 2025-02-27 | Plumb check & door centre line by Lift agency for lobby blockwork | 100 | 0 |  | 2025-09-29 |  | 2025-10-07 |  | Tower A | Super Structure | L45
40049 | Tower A - Super Structure - Finishes & MEP - L45 to L46 | Not Ready | CTU Elevators Crash Deck - High Side Services | 2025-02-20 | 2025-02-27 | Plumb check & door centre line by Lift agency for lobby blockwork | 100 | 0 |  | 2025-09-29 |  | 2025-10-07 |  | Tower A | Super Structure | L45
40049 | Tower A - Super Structure - Finishes & MEP - L45 to L46 | Not Ready | CTU Elevators Crash Deck - High Side Services | 2025-02-20 | 2025-02-27 | Plumb check & door centre line by Lift agency for lobby blockwork | 100 | 0 |  | 2025-09-29 |  | 2025-10-07 |  | Tower A | Super Structure | L45
40050 | Tower A - Super Structure - Finishes & MEP - L45 to L46 | Not Ready | CTU Elevators Crash Deck - High Side Services | 2025-02-20 | 2025-03-17 | Shaft clearance & White Wash up to L40 | 100 | 0 |  | 2025-09-29 |  | 2025-10-24 |  | Tower A | Super Structure | L45
40272 | Tower A - Super Structure - Finishes & MEP - L30 to L31 | Not Ready | Partition Wall-Blockwork | 2025-03-03 | 2025-03-07 | Staircase Area | 100 | 0 |  | 2025-09-29 |  | 2025-10-04 |  | Tower A | Super Structure | L30
40611 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | False Ceiling - MEP & Finishes | 2024-03-21 | 2024-04-02 | False Ceiling | 100 | 0 |  | 2025-09-29 |  | 2025-10-11 |  | Tower A | Sub Structure | B3 | Finishes | False Ceiling
41510 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2025-09-29 | 2025-10-01 | FAPA Cabling | 100 | 0 |  | 2025-09-29 |  | 2025-09-30 |  | Tower A | Super Structure | L35
42531 |  | Not Committed |  | 2025-02-15 | 2025-12-18 | Finishes after 1st Fix | 100 | 0 |  | 2025-09-29 |  | 2025-12-04
42532 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-02-15 | 2025-03-10 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-09-29 |  | 2025-10-24 |  | Tower A | Super Structure | L25 | Finishes | Blockwork
42585 |  | Not Committed |  | 2025-03-12 | 2025-12-31 | Finishes after 1st Fix | 100 | 0 |  | 2025-09-29 |  | 2025-12-01
42586 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-03-12 | 2025-04-04 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-09-29 |  | 2025-10-24 |  | Tower A | Super Structure | L28 | Finishes | Blockwork
47613 |  | Not Ready |  | 2024-11-11 | 2024-11-18 | Section 10_lift 2 | 100 | 0 |  | 2025-09-29 |  | 2025-10-07
47613 |  | Not Ready |  | 2024-11-11 | 2024-11-18 | Section 10_lift 2 | 100 | 0 |  | 2025-09-29 |  | 2025-10-07 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47614 |  | Not Ready |  | 2025-01-03 | 2025-01-10 | Section 11_lift 2 | 100 | 0 |  | 2025-09-29 |  | 2025-10-07
47614 |  | Not Ready |  | 2025-01-03 | 2025-01-10 | Section 11_lift 2 | 100 | 0 |  | 2025-09-29 |  | 2025-10-07 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47959 | Tower B | Not Committed | Award of Packages | 2025-07-07 | 2025-12-19 | Finishing | 100 | 0 |  | 2025-09-29 |  | 2026-03-13 |  | Tower B | --
48340 | Retail - Sub structure - B3 to B2 - P5 | Not Ready |  | 2025-02-11 | 2025-02-18 | Section 13_lift 2 | 100 | 0 |  | 2025-09-29 |  | 2025-10-07 |  | Retail | Sub Structure | B3
48341 | Retail - Sub structure - B3 to B2 - P5 | Not Ready |  | 2025-02-19 | 2025-02-26 | Section 14_lift 2 | 100 | 0 |  | 2025-09-29 |  | 2025-10-07 |  | Retail | Sub Structure | B3
8580 | T-14-2nd Floor Flat Area | Not Ready | Toilets False Celing | 2025-09-02 | 2025-10-06 | Toilets False Celing | 100 | 0 |  | 2025-09-30 |  | 2025-11-03
9027 | T-15-10th Floor | Complete | RCC | 2025-09-26 | 2025-09-27 | Slab& Beam RCC | 318 | 318 | CUM | 2025-09-30 | 2025-10-25 | 2025-09-30 | 2025-10-27
9531 | T-16-8th Floor | Complete | Shuttering | 2025-10-21 | 2025-10-25 | Slab and Beam Shuttering | 4183 | 4183 | Sqm | 2025-09-30 | 2025-11-08 | 2025-10-05 | 2025-11-14
9665 | T-16-3rd Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-10-21 | 2025-11-13 | Plumbing Pipe Line | 100 | 0 |  | 2025-09-30 |  | 2025-10-21
9732 |  | Not Ready |  | 2025-11-30 | 2026-08-06 | Common Area | 100 | 0 |  | 2025-09-30 |  | 2026-06-10
10172 | T-21-2nd Floor Flat Area | Not Ready | 1st Coat Painting | 2025-11-14 | 2026-01-31 | 1st Coat Painting | 100 | 0 |  | 2025-09-30 |  | 2025-12-16
10331 | T-21-8th Floor Common Area | Not Ready | Plastering | 2025-10-27 | 2025-11-30 | Plastering-Gypsum | 100 | 0 |  | 2025-09-30 |  | 2025-11-03
10357 | T-21-9th Floor Common Area | Not Ready | Plastering | 2025-10-27 | 2025-11-30 | Plastering-Gypsum | 100 | 0 |  | 2025-09-30 |  | 2025-11-03
10608 |  | Not Ready |  | 2025-10-28 | 2025-11-15 | Lowering Aluminium FW Material For PH-2 | 100 | 0 |  | 2025-09-30 |  | 2025-10-19
10689 | T-20-2nd Floor Flat Area | Not Ready | Window | 2025-11-09 | 2025-12-01 | Window | 100 | 0 |  | 2025-09-30 |  | 2025-10-21
10835 | T-20-8th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-10-28 | 2025-11-21 | Plumbing Pipe Line | 100 | 0 |  | 2025-09-30 |  | 2025-10-23
10861 | T-20-9th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-10-28 | 2025-11-21 | Plumbing Pipe Line | 100 | 0 |  | 2025-09-30 |  | 2025-10-23
11630 | T-18-11th Floor | Not Ready | Shear Walls/Corewalls Shuttering | 2025-12-06 | 2025-12-10 | Shear Walls/Corewalls Shuttering | 100 | 0 |  | 2025-09-30 |  | 2025-10-03
11813 | T-18-5th Floor Common Area | Not Ready | Plastering | 2025-12-05 | 2026-01-07 | Plastering-Gypsum | 100 | 0 |  | 2025-09-30 |  | 2025-11-03
11846 |  | Not Ready |  | 2025-12-02 | 2026-08-01 | Seventh Floor | 100 | 0 |  | 2025-09-30 |  | 2026-06-02
11847 |  | Not Ready |  | 2025-12-02 | 2026-07-06 | Flat Area | 100 | 0 |  | 2025-09-30 |  | 2026-05-07
39721 | Tower A - Super Structure - Core Wall High Rise L69-70 | Complete | Core Wall RCC Works | 2025-09-19 | 2025-09-22 | Reinf & Guide shoes fixing | 100 | 100 |  | 2025-09-30 | 2025-10-10 | 2025-10-04 | 2025-10-18 | Tower A | Super Structure | L69 | RCC Super Structure | Core Wall RCC Works
40152 | Tower A - Super Structure - Finishes & MEP - GF to P1 | Not Ready | Partition Wall-Blockwork | 2024-03-07 | 2024-03-18 | Staircase Area | 100 | 0 |  | 2025-09-30 |  | 2025-10-11 |  | Tower A | Super Structure | GF
40155 | Tower A - Super Structure - Finishes & MEP - P1 to P2 | Not Ready | Partition Wall-Blockwork | 2024-03-07 | 2024-03-23 | Partition Walls | 100 | 0 |  | 2025-09-30 |  | 2025-10-17 |  | Tower A | Super Structure
40347 | Tower A - Super Structure - Finishes & MEP - L47 to L48 | Not Ready | Partition Wall-Blockwork | 2025-09-06 | 2025-09-13 | Partition Walls | 100 | 0 |  | 2025-09-30 |  | 2025-10-08 |  | Tower A | Super Structure | L47
40641 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | VDF/ Grade Slab - MEP & Finishes | 2024-03-13 | 2024-03-18 | VDF/ Grade Slab | 100 | 0 |  | 2025-09-30 |  | 2025-10-06 |  | Tower A | Sub Structure | B2
40668 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | VDF/ Grade Slab - MEP & Finishes | 2024-04-06 | 2024-04-11 | VDF/ Grade Slab | 100 | 0 |  | 2025-09-30 |  | 2025-10-06 |  | Tower A | Sub Structure | B1
40695 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | Flooring & Dado - MEP & Finishes | 2024-05-07 | 2024-06-04 | Flooring & Dado | 100 | 0 |  | 2025-09-30 |  | 2025-10-30 |  | Tower A | Super Structure | GF | Finishes | Flooring & Dado
40726 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | VDF/ Grade Slab - MEP & Finishes | 2024-05-13 | 2024-05-17 | VDF/ Grade Slab | 100 | 0 |  | 2025-09-30 |  | 2025-10-06 |  | Tower A | Super Structure
40753 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | VDF/ Grade Slab - MEP & Finishes | 2024-05-24 | 2024-05-29 | VDF/ Grade Slab | 100 | 0 |  | 2025-09-30 |  | 2025-10-06 |  | Tower A | Super Structure
40778 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | FAPA Cabling - MEP & Finishes | 2024-05-30 | 2024-06-10 | FAPA Cabling | 100 | 0 |  | 2025-09-30 |  | 2025-10-11 |  | Tower A | Super Structure
40861 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | VDF/ Grade Slab - MEP & Finishes | 2024-08-02 | 2024-08-08 | VDF/ Grade Slab | 100 | 0 |  | 2025-09-30 |  | 2025-10-06 |  | Tower A | Super Structure
42458 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-01-08 | 2025-01-18 | Cement Plastering in wet areas | 100 | 0 |  | 2025-09-30 |  | 2025-10-11 |  | Tower A | Super Structure | L21
42674 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-05-22 | 2025-06-02 | Cement Plastering in wet areas | 100 | 0 |  | 2025-09-30 |  | 2025-10-11 |  | Tower A | Super Structure | L33
42692 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-05-30 | 2025-06-11 | Cement Plastering in wet areas | 100 | 0 |  | 2025-09-30 |  | 2025-10-11 |  | Tower A | Super Structure | L34
42710 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-06-09 | 2025-06-19 | Cement Plastering in wet areas | 100 | 0 |  | 2025-09-30 |  | 2025-10-11 |  | Tower A | Super Structure | L35
42728 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-06-17 | 2025-06-27 | Cement Plastering in wet areas | 100 | 0 |  | 2025-09-30 |  | 2025-10-11 |  | Tower A | Super Structure | L36
42746 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-06-25 | 2025-07-05 | Cement Plastering in wet areas | 100 | 0 |  | 2025-09-30 |  | 2025-10-11 |  | Tower A | Super Structure | L37
42764 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-07-03 | 2025-07-15 | Cement Plastering in wet areas | 100 | 0 |  | 2025-09-30 |  | 2025-10-11 |  | Tower A | Super Structure | L38
42782 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-07-11 | 2025-07-24 | Cement Plastering in wet areas | 100 | 0 |  | 2025-09-30 |  | 2025-10-11 |  | Tower A | Super Structure | L39
42800 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-07-26 | 2025-08-08 | Cement Plastering in wet areas | 100 | 0 |  | 2025-09-30 |  | 2025-10-11 |  | Tower A | Super Structure | L40
42818 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-08-11 | 2025-08-23 | Cement Plastering in wet areas | 100 | 0 |  | 2025-09-30 |  | 2025-10-11 |  | Tower A | Super Structure | L41
42872 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-09-13 | 2025-09-25 | Cement Plastering in wet areas | 100 | 0 |  | 2025-09-30 |  | 2025-10-11 |  | Tower A | Super Structure | L44
48316 |  | Not Committed |  | 2025-03-22 | 2025-04-19 | Pour RT-4 | 100 | 0 |  | 2025-09-30 |  | 2025-10-30
48317 | Retail - Sub structure - B1 to GF - P4 | Not Ready |  | 2025-03-22 | 2025-04-08 | Columns/ Walls_NTA | 100 | 0 |  | 2025-09-30 |  | 2025-10-17 |  | Retail | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
48317 | Retail - Sub structure - B1 to GF - P4 | Not Ready |  | 2025-03-22 | 2025-04-08 | Columns/ Walls_NTA | 100 | 0 |  | 2025-09-30 |  | 2025-10-17 |  | Retail | Sub Structure | B1
48372 |  | Not Committed |  | 2024-10-07 | 2024-11-06 | Pour RT-4 | 100 | 0 |  | 2025-09-30 |  | 2025-10-30
48373 | Retail - Sub structure - B3 to B2 - P4 | Not Ready |  | 2024-10-07 | 2024-10-24 | Columns/ Walls_NTA | 100 | 0 |  | 2025-09-30 |  | 2025-10-17 |  | Retail | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
48373 | Retail - Sub structure - B3 to B2 - P4 | Not Ready |  | 2024-10-07 | 2024-10-24 | Columns/ Walls_NTA | 100 | 0 |  | 2025-09-30 |  | 2025-10-17 |  | Retail | Sub Structure | B3
48408 |  | Not Committed |  | 2025-02-25 | 2025-03-26 | Pour RT-4 | 100 | 0 |  | 2025-09-30 |  | 2025-10-30
48409 | Retail - Sub structure - B2 to B1 - P4 | Not Ready |  | 2025-02-25 | 2025-03-13 | Columns/ Walls_NTA | 100 | 0 |  | 2025-09-30 |  | 2025-10-17 |  | Retail | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
48409 | Retail - Sub structure - B2 to B1 - P4 | Not Ready |  | 2025-02-25 | 2025-03-13 | Columns/ Walls_NTA | 100 | 0 |  | 2025-09-30 |  | 2025-10-17 |  | Retail | Sub Structure | B2
8604 | T-14-3rd Floor Flat Area | Not Ready | Dado | 2025-08-31 | 2025-09-27 | Dado | 100 | 0 |  | 2025-10-01 |  | 2025-10-29
8718 |  | Not Ready |  | 2025-09-30 | 2026-04-30 | Common Area | 100 | 0 |  | 2025-10-01 |  | 2026-05-02
9222 | T-15-6th Floor Flat Area | Not Ready | Blockwork | 2025-09-27 | 2025-10-20 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-10-01 |  | 2025-10-24
9261 | T-15-7th Floor Flat Area | Not Ready | Railing | 2025-09-27 | 2025-11-02 | Balcony Railing | 100 | 0 |  | 2025-10-01 |  | 2025-11-02
10269 | T-21-6th Floor Flat Area | Not Ready | Toilet flooring | 2025-11-07 | 2025-12-10 | Toilet flooring | 100 | 0 |  | 2025-10-01 |  | 2025-11-04
10297 | T-21-7th Floor Flat Area | Not Ready | Flooring & skirting | 2025-11-03 | 2025-12-17 | Flooring & skirting | 100 | 0 |  | 2025-10-01 |  | 2025-11-18
10607 | T-20-Terrace | Not Ready |  | 2025-10-29 | 2025-12-19 | MISC | 100 | 0 |  | 2025-10-01 |  | 2025-11-24
11098 | T-19-9th Floor | Complete | Shuttering | 2025-10-13 | 2025-10-17 | Slab and Beam Shuttering | 3548 | 3548 | Sqm | 2025-10-01 | 2025-11-12 | 2025-10-04 | 2025-11-17
11162 | T-19-GF Common Area | Not Ready | Toilets False Celing | 2025-10-22 | 2025-11-10 | Toilets False Celing | 100 | 0 |  | 2025-10-01 |  | 2025-10-17
11251 | T-19-4th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-10-13 | 2025-11-06 | Plumbing Pipe Line | 100 | 0 |  | 2025-10-01 |  | 2025-10-22
11318 |  | Not Ready |  | 2025-11-22 | 2026-06-13 | Common Area | 100 | 0 |  | 2025-10-01 |  | 2026-04-24
11628 | T-18-11th Floor | Not Ready |  | 2025-12-03 | 2025-12-16 | 10th Floor Roof | 100 | 0 |  | 2025-10-01 |  | 2025-10-13
39722 | Tower A - Super Structure - Core Wall High Rise L69-70 | Complete | Core Wall RCC Works | 2025-09-20 | 2025-09-23 | ACS Form Closing & Alignment | 100 | 100 |  | 2025-10-01 | 2025-10-15 | 2025-10-06 | 2025-10-19 | Tower A | Super Structure | L69 | RCC Super Structure | Core Wall RCC Works
41523 |  | Started |  | 2025-06-13 | 2026-04-28 | L36-37 | 100 | 26 |  | 2025-10-01 | 2025-10-01 | 2026-05-20 |  |  |  |  | Finishes | Gypsum Plastering Works
41523 |  | Started |  | 2025-06-13 | 2026-04-28 | L36-37 | 100 | 26 |  | 2025-10-01 | 2025-10-01 | 2026-05-20
41524 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2025-10-01 | 2025-10-06 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 40 |  | 2025-10-01 | 2025-10-01 | 2026-04-08 |  | Tower A | Super Structure | L36 | MEP | FPS 1st Fix - MEP & Finishes
41525 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-10-01 | 2025-10-06 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-10-01 |  | 2025-10-04 |  | Tower A | Super Structure | L36 | MEP | Electrical 1st Fixes
42902 |  | Not Committed |  | 2025-09-12 | 2026-08-31 | L46-47 | 100 | 0 |  | 2025-10-01 |  | 2026-08-12
42902 |  | Not Committed |  | 2025-09-12 | 2026-08-31 | L46-47 | 100 | 0 |  | 2025-10-01 |  | 2026-08-12 |  |  |  |  | Finishes | Gypsum Plastering Works
42903 |  | Not Committed |  | 2025-09-12 | 2025-10-13 | MEP 1st Fixes | 100 | 0 |  | 2025-10-01 |  | 2025-11-01
42904 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2025-09-12 | 2025-09-20 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-10-01 |  | 2025-10-10 |  | Tower A | Super Structure | L46 | MEP | FPS 1st Fix - MEP & Finishes
42905 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-09-12 | 2025-09-18 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2025-10-01 |  | 2025-10-08 |  | Tower A | Super Structure | L46 | MEP | Electrical 1st Fixes
42906 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2025-09-12 | 2025-09-20 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2025-10-01 |  | 2025-10-10 |  | Tower A | Super Structure | L46
42907 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2025-09-12 | 2025-09-30 | Wet Area Waterproofing | 100 | 0 |  | 2025-10-01 |  | 2025-10-21 |  | Tower A | Super Structure | L46
8652 | T-14-5th Floor Flat Area | Not Ready | Plastering | 2025-08-30 | 2025-09-20 | Plastering-Cement | 100 | 0 |  | 2025-10-02 |  | 2025-10-23
9029 | T-15-11th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-09-28 | 2025-10-03 | AL - Shear Walls/Corewalls Steel | 24.5 | 24.5 | MT | 2025-10-02 | 2025-10-28 | 2025-10-05 | 2025-11-03
9532 | T-16-8th Floor | Complete | Slab& Beam Steel & Conduting | 2025-10-23 | 2025-10-26 | Slab& Beam Steel & Conduting | 14 | 14 | MT | 2025-10-02 | 2025-11-12 | 2025-10-05 | 2025-11-15
9669 | T-16-3rd Floor Flat Area | Not Ready | Plastering | 2025-10-23 | 2025-12-08 | Plastering-Gypsum | 100 | 0 |  | 2025-10-02 |  | 2025-11-15
10604 | T-20-Terrace | Not Ready | OHT | 2025-10-30 | 2025-12-20 | OHT | 100 | 0 |  | 2025-10-02 |  | 2025-11-24
10763 | T-20-5th Floor Flat Area | Not Ready | Toilet flooring | 2025-10-30 | 2025-12-04 | Toilet flooring | 100 | 0 |  | 2025-10-02 |  | 2025-11-05
10839 | T-20-8th Floor Flat Area | Not Ready | Plastering | 2025-10-30 | 2025-12-15 | Plastering-Gypsum | 100 | 0 |  | 2025-10-02 |  | 2025-11-18
10865 | T-20-9th Floor Flat Area | Not Ready | Plastering | 2025-10-30 | 2025-12-15 | Plastering-Gypsum | 100 | 0 |  | 2025-10-02 |  | 2025-11-18
11180 | T-19-1st Floor Flat Area | Not Ready | Toilets False Celing | 2025-10-24 | 2025-11-28 | Toilets False Celing | 100 | 0 |  | 2025-10-02 |  | 2025-11-02
39196 |  | Not Ready |  | 2025-03-11 | 2025-04-01 | Low Side Laying of 220KV HT Cable | 100 | 0 |  | 2025-10-02 |  | 2025-10-22
8474 | T-14-10th Floor | Complete | RCC | 2025-08-28 | 2025-08-29 | Slab& Beam RCC | 307 | 307 | CUM | 2025-10-03 | 2025-11-19 | 2025-10-03 | 2025-11-20
9198 | T-15-5th Floor Flat Area | Not Ready | Plastering | 2025-09-28 | 2025-10-21 | Plastering-Cement | 100 | 0 |  | 2025-10-03 |  | 2025-10-26
9226 | T-15-6th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-09-29 | 2025-10-17 | Electrical DB Fixing | 100 | 0 |  | 2025-10-03 |  | 2025-10-19
9586 | T-16-GF Flat Area | Not Ready | Flooring & skirting | 2025-10-22 | 2025-11-25 | Flooring & skirting | 100 | 0 |  | 2025-10-03 |  | 2025-11-05
10109 | T-21-GF Flat Area | Not Ready | Door | 2025-09-30 | 2025-10-23 | Door | 100 | 0 |  | 2025-10-03 |  | 2025-10-24
10648 | T-20-GF Common Area | Not Ready | 1st Coat Painting | 2025-11-08 | 2025-12-27 | 1st Coat Painting | 100 | 0 |  | 2025-10-03 |  | 2025-11-25
10718 | T-20-3rd Floor Flat Area | Not Ready | 1st Coat Painting | 2025-11-12 | 2026-02-04 | 1st Coat Painting | 100 | 0 |  | 2025-10-03 |  | 2025-12-26
10850 |  | Not Ready |  | 2025-11-09 | 2026-06-15 | Common Area | 100 | 0 |  | 2025-10-03 |  | 2026-05-11
10876 |  | Not Ready |  | 2025-11-09 | 2026-07-07 | Common Area | 100 | 0 |  | 2025-10-03 |  | 2026-06-02
11099 | T-19-9th Floor | Complete | Slab& Beam Steel & Conduting | 2025-10-15 | 2025-10-18 | Slab& Beam Steel & Conduting | 11.3 | 11.3 | MT | 2025-10-03 | 2025-11-15 | 2025-10-08 | 2025-11-20
11204 | T-19-2nd Floor Flat Area | Not Ready | Dado | 2025-10-22 | 2025-11-20 | Dado | 100 | 0 |  | 2025-10-03 |  | 2025-10-28
11255 | T-19-4th Floor Flat Area | Not Ready | Plastering | 2025-10-15 | 2025-11-30 | Plastering-Gypsum | 100 | 0 |  | 2025-10-03 |  | 2025-11-16
11632 | T-18-11th Floor | Not Ready | Shuttering | 2025-12-10 | 2025-12-12 | Slab and Beam Shuttering | 3527 | 0 | Sqm | 2025-10-03 |  | 2025-10-06
11750 | T-18-3rd Floor Flat Area | Not Ready | Dado | 2025-12-04 | 2025-12-31 | Dado | 100 | 0 |  | 2025-10-03 |  | 2025-10-31
11823 | T-18-6th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-12-10 | 2025-12-31 | Plumbing Pipe Line | 100 | 0 |  | 2025-10-03 |  | 2025-10-24
40653 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | False Ceiling - MEP & Finishes | 2024-03-30 | 2024-04-10 | False Ceiling | 100 | 0 |  | 2025-10-03 |  | 2025-10-15 |  | Tower A | Sub Structure | B1 | Finishes | False Ceiling
40785 |  | Not Committed |  | 2024-05-30 | 2024-10-21 | P4-5 Level | 100 | 0 |  | 2025-10-03 |  | 2026-01-31
40800 |  | Not Committed |  | 2024-05-30 | 2024-10-21 | Floor Area | 100 | 0 |  | 2025-10-03 |  | 2026-01-31
40801 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | Ceiling Painting/ PT Marking - MEP & Finishes | 2024-05-30 | 2024-06-04 | Ceiling Painting/ PT Marking | 100 | 0 |  | 2025-10-03 |  | 2025-10-09 |  | Tower A | Super Structure |  | Finishes | Ceiling Painting/ PT Marking
42495 |  | Not Committed |  | 2025-02-08 | 2025-12-06 | Finishes after 1st Fix | 100 | 0 |  | 2025-10-03 |  | 2025-11-22
42496 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-02-08 | 2025-03-03 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-10-03 |  | 2025-10-28 |  | Tower A | Super Structure | L23 | Finishes | Blockwork
42549 |  | Not Committed |  | 2025-03-05 | 2025-12-24 | Finishes after 1st Fix | 100 | 0 |  | 2025-10-03 |  | 2025-12-10
42550 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-03-05 | 2025-03-28 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-10-03 |  | 2025-10-28 |  | Tower A | Super Structure | L26 | Finishes | Blockwork
42837 |  | Not Committed |  | 2025-08-30 | 2026-03-13 | Finishes after 1st Fix | 100 | 0 |  | 2025-10-03 |  | 2026-02-11
42838 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-08-30 | 2025-09-23 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-10-03 |  | 2025-10-27 |  | Tower A | Super Structure | L42 | Finishes | Blockwork
42855 |  | Not Committed |  | 2025-09-08 | 2026-03-19 | Finishes after 1st Fix | 100 | 0 |  | 2025-10-03 |  | 2026-02-17
42856 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-09-08 | 2025-10-01 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-10-03 |  | 2025-10-27 |  | Tower A | Super Structure | L43 | Finishes | Blockwork
8667 | T-14-5th Floor Common Area | Not Ready | Plastering | 2025-09-01 | 2025-10-05 | Plastering-Gypsum | 100 | 0 |  | 2025-10-04 |  | 2025-11-05
8676 | T-14-6th Floor Flat Area | Not Ready | Blockwork | 2025-08-29 | 2025-09-19 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-10-04 |  | 2025-10-24
8715 | T-14-7th Floor Flat Area | Not Ready | Railing | 2025-08-29 | 2025-10-01 | Balcony Railing | 100 | 0 |  | 2025-10-04 |  | 2025-11-07
9031 | T-15-11th Floor | Complete | Conduiting | 2025-09-30 | 2025-10-04 | Conduiting works | 100 | 100 |  | 2025-10-04 | 2025-11-03 | 2025-10-08 | 2025-11-04
9126 | T-15-2nd Floor Flat Area | Not Ready |  | 2025-10-01 | 2025-11-06 | Toilets False Celing | 100 | 0 |  | 2025-10-04 |  | 2025-11-07
10272 | T-21-6th Floor Flat Area | Not Ready | Putty | 2025-11-11 | 2026-02-03 | Putty | 100 | 0 |  | 2025-10-04 |  | 2025-12-27
40000 | Tower A - Super Structure - Core & Outer Slab L65-66 | Complete | RCC Works - Slab | 2025-09-24 | 2025-10-04 | Outer Slab_TA | 100 | 100 |  | 2025-10-04 | 2025-10-20 | 2025-10-15 | 2025-10-30 | Tower A | Super Structure | L65 | RCC Sub Structure | RCC Works - Slab
40519 | Tower A - Super Structure - Finishes & MEP - L45 to L46 | Not Ready | Gypsum Plastering Works | 2025-09-12 | 2025-10-07 | L45-46 | 100 | 0 |  | 2025-10-04 |  | 2025-10-29 |  | Tower A | Super Structure | L45 | Finishes | Gypsum Plastering Works
40519 | Tower A - Super Structure - Finishes & MEP - L45 to L46 | Not Ready | Gypsum Plastering Works | 2025-09-12 | 2025-10-07 | L45-46 | 100 | 0 |  | 2025-10-04 |  | 2025-10-29 |  | Tower A | Super Structure | L45
42477 |  | Not Committed |  | 2025-02-06 | 2025-12-06 | Finishes after 1st Fix | 100 | 0 |  | 2025-10-04 |  | 2025-12-17
42478 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-02-06 | 2025-02-28 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-10-04 |  | 2025-10-28 |  | Tower A | Super Structure | L22 | Finishes | Blockwork
48404 | Retail - Sub structure - B2 to B1 - P2 | Not Ready |  | 2025-02-17 | 2025-03-05 | Slab_NTA | 100 | 0 |  | 2025-10-04 |  | 2025-10-23 |  | Retail | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
48404 | Retail - Sub structure - B2 to B1 - P2 | Not Ready |  | 2025-02-17 | 2025-03-05 | Slab_NTA | 100 | 0 |  | 2025-10-04 |  | 2025-10-23 |  | Retail | Sub Structure | B2
8476 | T-14-11th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-08-30 | 2025-09-03 | AL - Shear Walls/Corewalls Steel | 22 | 22 | MT | 2025-10-05 | 2025-11-21 | 2025-10-10 | 2025-11-29
8633 | T-14-4th Floor Flat Area | Not Ready | Flooring & skirting | 2025-09-06 | 2025-10-21 | Flooring & skirting | 100 | 0 |  | 2025-10-05 |  | 2025-11-20
9030 | T-15-11th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-10-01 | 2025-10-07 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-10-05 | 2025-11-01 | 2025-10-10 | 2025-11-04
9150 | T-15-3rd Floor Flat Area | Not Ready | Dado | 2025-09-29 | 2025-10-28 | Dado | 100 | 0 |  | 2025-10-05 |  | 2025-11-02
9213 | T-15-5th Floor Common Area | Not Ready | Plastering | 2025-09-30 | 2025-11-05 | Plastering-Gypsum | 100 | 0 |  | 2025-10-05 |  | 2025-11-08
9584 | T-16-GF Flat Area | Not Ready | Toilet flooring | 2025-10-29 | 2025-11-17 | Toilet flooring | 100 | 0 |  | 2025-10-05 |  | 2025-10-23
10124 | T-21-GF Common Area | Not Ready | Putty | 2025-09-30 | 2025-10-23 | Putty | 100 | 0 |  | 2025-10-05 |  | 2025-10-26
10766 | T-20-5th Floor Flat Area | Not Ready | Putty | 2025-11-08 | 2026-01-31 | Putty | 100 | 0 |  | 2025-10-05 |  | 2025-12-29
11633 | T-18-11th Floor | Not Ready | Slab& Beam Steel & Conduting | 2025-12-12 | 2025-12-15 | Slab& Beam Steel & Conduting | 10.8 | 0 | MT | 2025-10-05 |  | 2025-10-05
11726 | T-18-2nd Floor Flat Area | Not Ready |  | 2025-12-06 | 2026-01-08 | Toilets False Celing | 100 | 0 |  | 2025-10-05 |  | 2025-11-09
11779 | T-18-4th Floor Flat Area | Not Ready | Flooring & skirting | 2025-12-11 | 2026-01-24 | Flooring & skirting | 100 | 0 |  | 2025-10-05 |  | 2025-11-19
11827 | T-18-6th Floor Flat Area | Not Ready | Plastering | 2025-12-12 | 2026-01-27 | Plastering-Gypsum | 100 | 0 |  | 2025-10-05 |  | 2025-11-18
8582 | T-14-2nd Floor Flat Area | Not Ready | Putty | 2025-09-11 | 2025-12-05 | Putty | 100 | 0 |  | 2025-10-06 |  | 2025-12-29
8680 | T-14-6th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-08-31 | 2025-09-16 | Electrical DB Fixing | 100 | 0 |  | 2025-10-06 |  | 2025-10-23
9533 | T-16-8th Floor | Complete | RCC | 2025-10-26 | 2025-10-27 | Slab& Beam RCC | 387 | 387 | CUM | 2025-10-06 | 2025-11-17 | 2025-10-09 | 2025-11-18
9618 | T-16-1st Floor Flat Area | Not Ready | Dado | 2025-10-29 | 2025-11-27 | Dado | 100 | 0 |  | 2025-10-06 |  | 2025-11-02
11634 | T-18-11th Floor | Not Ready | RCC | 2025-12-15 | 2025-12-16 | Slab& Beam RCC | 330.8 | 0 | CUM | 2025-10-06 |  | 2025-10-06
39723 | Tower A - Super Structure - Core Wall High Rise L69-70 | Complete | Core Wall RCC Works | 2025-09-24 | 2025-09-24 | Casting | 100 | 100 |  | 2025-10-06 | 2025-10-19 | 2025-10-07 | 2025-10-20 | Tower A | Super Structure | L69 | RCC Super Structure | Core Wall RCC Works
40503 | Tower A - Super Structure - Finishes & MEP - L29 to L30 | Not Ready | Gypsum Plastering Works | 2025-03-08 | 2025-04-07 | L29-30 | 100 | 0 |  | 2025-10-06 |  | 2025-11-04 |  | Tower A | Super Structure | L29 | Finishes | Gypsum Plastering Works
40503 | Tower A - Super Structure - Finishes & MEP - L29 to L30 | Not Ready | Gypsum Plastering Works | 2025-03-08 | 2025-04-07 | L29-30 | 100 | 0 |  | 2025-10-06 |  | 2025-11-04 |  | Tower A | Super Structure | L29
41526 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2025-10-06 | 2025-10-08 | FAPA Cabling | 100 | 0 |  | 2025-10-06 |  | 2025-10-07 |  | Tower A | Super Structure | L36
42614 |  | Not Committed |  | 2025-03-08 | 2026-07-04 | L30-31 | 100 | 0 |  | 2025-10-06 |  | 2026-07-02
42614 |  | Not Committed |  | 2025-03-08 | 2026-07-04 | L30-31 | 100 | 0 |  | 2025-10-06 |  | 2026-07-02 |  |  |  |  | Finishes | Gypsum Plastering Works
42615 |  | Not Committed |  | 2025-03-08 | 2025-04-07 | MEP 1st Fixes | 100 | 0 |  | 2025-10-06 |  | 2025-11-04
42616 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2025-03-08 | 2025-03-17 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-10-06 |  | 2025-10-13 |  | Tower A | Super Structure | L30 | MEP | FPS 1st Fix - MEP & Finishes
42617 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-03-08 | 2025-03-13 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2025-10-06 |  | 2025-10-10 |  | Tower A | Super Structure | L30 | MEP | Electrical 1st Fixes
42618 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2025-03-08 | 2025-03-17 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2025-10-06 |  | 2025-10-13 |  | Tower A | Super Structure | L30
42619 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2025-03-08 | 2025-03-26 | Wet Area Waterproofing | 100 | 0 |  | 2025-10-06 |  | 2025-10-23 |  | Tower A | Super Structure | L30
47962 | Tower B | Not Committed | Award of Packages | 2025-08-11 | 2025-12-29 | ELV | 100 | 0 |  | 2025-10-06 |  | 2026-02-23 |  | Tower B | --
48283 | Retail - Sub structure - B1 to GF - P5 | Not Ready |  | 2025-04-23 | 2025-04-30 | Section 12_lift 1 | 100 | 0 |  | 2025-10-06 |  | 2025-10-13 |  | Retail | Sub Structure | B1
48284 | Retail - Sub structure - B1 to GF - P5 | Not Ready |  | 2025-04-23 | 2025-04-30 | Section 13_lift 1 | 100 | 0 |  | 2025-10-06 |  | 2025-10-13 |  | Retail | Sub Structure | B1
8478 | T-14-11th Floor | Complete | Conduiting | 2025-09-01 | 2025-09-04 | Conduiting works | 100 | 100 |  | 2025-10-07 | 2025-12-04 | 2025-10-10 | 2025-12-06
8627 | T-14-4th Floor Flat Area | Not Ready | Waterproofing | 2025-09-06 | 2025-10-27 | Waterproofing | 100 | 0 |  | 2025-10-07 |  | 2025-11-28
9272 |  | Not Ready |  | 2025-10-13 | 2026-06-22 | Eighth Floor | 100 | 0 |  | 2025-10-07 |  | 2026-06-16
9273 |  | Not Ready |  | 2025-10-13 | 2026-06-01 | Flat Area | 100 | 0 |  | 2025-10-07 |  | 2026-05-27
9600 | T-16-GF Common Area | Not Ready | Dado | 2025-10-27 | 2025-11-20 | Dado | 100 | 0 |  | 2025-10-07 |  | 2025-10-28
9666 | T-16-3rd Floor Flat Area | Not Ready | Plastering | 2025-10-28 | 2025-11-21 | Plastering-Cement | 100 | 0 |  | 2025-10-07 |  | 2025-10-25
10125 | T-21-GF Common Area | Not Ready | Window | 2025-10-03 | 2025-10-25 | Window | 100 | 0 |  | 2025-10-07 |  | 2025-10-28
10224 | T-21-4th Floor Flat Area | Not Ready | 1st Coat Painting | 2025-11-15 | 2026-02-07 | 1st Coat Painting | 100 | 0 |  | 2025-10-07 |  | 2025-12-29
10690 | T-20-2nd Floor Flat Area | Not Ready | Door | 2025-11-17 | 2025-12-08 | Door | 100 | 0 |  | 2025-10-07 |  | 2025-10-30
10836 | T-20-8th Floor Flat Area | Not Ready | Plastering | 2025-11-07 | 2025-11-28 | Plastering-Cement | 100 | 0 |  | 2025-10-07 |  | 2025-10-31
10862 | T-20-9th Floor Flat Area | Not Ready | Plastering | 2025-11-07 | 2025-11-28 | Plastering-Cement | 100 | 0 |  | 2025-10-07 |  | 2025-10-31
11812 |  | Not Ready |  | 2025-12-05 | 2026-08-12 | Common Area | 100 | 0 |  | 2025-10-07 |  | 2026-06-13
11848 | T-18-7th Floor Flat Area | Not Ready | Blockwork | 2025-12-16 | 2026-01-07 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-10-07 |  | 2025-11-02
11887 | T-18-8th Floor Flat Area | Not Ready | Railing | 2025-12-16 | 2026-01-19 | Balcony Railing | 100 | 0 |  | 2025-10-07 |  | 2025-11-11
39724 | Tower A - Super Structure - Core Wall High Rise L69-70 | Complete | Core Wall RCC Works | 2025-09-25 | 2025-09-25 | ACS Form Release & jump to next level | 100 | 100 |  | 2025-10-07 | 2025-10-23 | 2025-10-08 | 2025-10-23 | Tower A | Super Structure | L69 | RCC Super Structure | Core Wall RCC Works
40642 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2024-03-19 | 2024-03-27 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2025-10-07 |  | 2025-10-14 |  | Tower A | Sub Structure | B2 | MEP | FPS 2nd Fix - MEP & Finishes
40643 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-03-19 | 2024-03-27 | FAPA Device Fixing | 100 | 0 |  | 2025-10-07 |  | 2025-10-14 |  | Tower A | Sub Structure | B2
40643 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-03-19 | 2024-03-27 | FAPA Device Fixing | 100 | 0 |  | 2025-10-07 |  | 2025-10-14 |  | Tower A | Sub Structure | B2
40643 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-03-19 | 2024-03-27 | FAPA Device Fixing | 100 | 0 |  | 2025-10-07 |  | 2025-10-14 |  | Tower A | Sub Structure | B2
40643 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-03-19 | 2024-03-27 | FAPA Device Fixing | 100 | 0 |  | 2025-10-07 |  | 2025-10-14 |  | Tower A | Sub Structure | B2
40669 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2024-04-12 | 2024-04-29 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2025-10-07 |  | 2025-10-24 |  | Tower A | Sub Structure | B1 | MEP | FPS 2nd Fix - MEP & Finishes
40670 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-04-12 | 2024-04-29 | FAPA Device Fixing | 100 | 0 |  | 2025-10-07 |  | 2025-10-24 |  | Tower A | Sub Structure | B1
40670 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-04-12 | 2024-04-29 | FAPA Device Fixing | 100 | 0 |  | 2025-10-07 |  | 2025-10-24 |  | Tower A | Sub Structure | B1
40670 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-04-12 | 2024-04-29 | FAPA Device Fixing | 100 | 0 |  | 2025-10-07 |  | 2025-10-24 |  | Tower A | Sub Structure | B1
40670 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-04-12 | 2024-04-29 | FAPA Device Fixing | 100 | 0 |  | 2025-10-07 |  | 2025-10-24 |  | Tower A | Sub Structure | B1
40727 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2024-05-18 | 2024-05-25 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2025-10-07 |  | 2025-10-14 |  | Tower A | Super Structure |  | MEP | FPS 2nd Fix - MEP & Finishes
40728 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-05-18 | 2024-05-25 | FAPA Device Fixing | 100 | 0 |  | 2025-10-07 |  | 2025-10-14 |  | Tower A | Super Structure
40728 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-05-18 | 2024-05-25 | FAPA Device Fixing | 100 | 0 |  | 2025-10-07 |  | 2025-10-14 |  | Tower A | Super Structure
40728 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-05-18 | 2024-05-25 | FAPA Device Fixing | 100 | 0 |  | 2025-10-07 |  | 2025-10-14 |  | Tower A | Super Structure
40728 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-05-18 | 2024-05-25 | FAPA Device Fixing | 100 | 0 |  | 2025-10-07 |  | 2025-10-14 |  | Tower A | Super Structure
40754 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2024-05-30 | 2024-06-06 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2025-10-07 |  | 2025-10-14 |  | Tower A | Super Structure |  | MEP | FPS 2nd Fix - MEP & Finishes
40755 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-05-30 | 2024-06-06 | FAPA Device Fixing | 100 | 0 |  | 2025-10-07 |  | 2025-10-14 |  | Tower A | Super Structure
40755 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-05-30 | 2024-06-06 | FAPA Device Fixing | 100 | 0 |  | 2025-10-07 |  | 2025-10-14 |  | Tower A | Super Structure
40755 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-05-30 | 2024-06-06 | FAPA Device Fixing | 100 | 0 |  | 2025-10-07 |  | 2025-10-14 |  | Tower A | Super Structure
40755 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-05-30 | 2024-06-06 | FAPA Device Fixing | 100 | 0 |  | 2025-10-07 |  | 2025-10-14 |  | Tower A | Super Structure
40862 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2024-08-12 | 2024-08-21 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2025-10-07 |  | 2025-10-14 |  | Tower A | Super Structure |  | MEP | FPS 2nd Fix - MEP & Finishes
40863 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-08-12 | 2024-08-21 | FAPA Device Fixing | 100 | 0 |  | 2025-10-07 |  | 2025-10-14 |  | Tower A | Super Structure
40863 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-08-12 | 2024-08-21 | FAPA Device Fixing | 100 | 0 |  | 2025-10-07 |  | 2025-10-14 |  | Tower A | Super Structure
40863 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-08-12 | 2024-08-21 | FAPA Device Fixing | 100 | 0 |  | 2025-10-07 |  | 2025-10-14 |  | Tower A | Super Structure
40863 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-08-12 | 2024-08-21 | FAPA Device Fixing | 100 | 0 |  | 2025-10-07 |  | 2025-10-14 |  | Tower A | Super Structure
40869 | Tower A - Super Structure - Finishes & MEP - B3 to L7 | Not Ready |  | 2024-03-13 | 2024-05-06 | FHC & Accessories fixing | 100 | 0 |  | 2025-10-07 |  | 2025-11-28 |  | Tower A | Super Structure | B3
40871 | Tower A - Super Structure - Finishes & MEP - B3 to L7 | Not Ready |  | 2024-03-13 | 2024-05-06 | Soil & Waste Downtake piping in Plumbing Shaft | 100 | 0 |  | 2025-10-07 |  | 2025-11-28 |  | Tower A | Super Structure | B3
40875 | Tower A - Super Structure - Finishes & MEP - B3 to L7 | Not Ready |  | 2024-03-13 | 2024-05-06 | HVAC Shaft Ducting | 100 | 0 |  | 2025-10-07 |  | 2025-11-28 |  | Tower A | Super Structure | B3 | MEP | HVAC Grill Fixing
40878 | Tower A - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2024-09-13 | 2024-11-08 | FHC & Accessories fixing | 100 | 0 |  | 2025-10-07 |  | 2025-11-28 |  | Tower A | Super Structure | L15
40880 | Tower A - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2024-09-13 | 2024-11-08 | Soil & Waste Downtake piping in Plumbing Shaft | 100 | 0 |  | 2025-10-07 |  | 2025-11-28 |  | Tower A | Super Structure | L15
40884 | Tower A - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2024-09-13 | 2024-11-08 | HVAC Shaft Ducting | 100 | 0 |  | 2025-10-07 |  | 2025-11-28 |  | Tower A | Super Structure | L15 | MEP | HVAC Grill Fixing
40889 | Tower A - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2024-06-04 | 2024-07-30 | Soil & Waste Downtake piping in Plumbing Shaft | 100 | 0 |  | 2025-10-07 |  | 2025-11-28 |  | Tower A | Super Structure | L7
40896 | Tower A - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2024-11-30 | 2025-01-22 | FHC & Accessories fixing | 100 | 0 |  | 2025-10-07 |  | 2025-11-28 |  | Tower A | Super Structure | L25
40898 | Tower A - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2024-11-30 | 2025-01-22 | Soil & Waste Downtake piping in Plumbing Shaft | 100 | 0 |  | 2025-10-07 |  | 2025-11-28 |  | Tower A | Super Structure | L25
40902 | Tower A - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2024-11-30 | 2025-01-22 | HVAC Shaft Ducting | 100 | 0 |  | 2025-10-07 |  | 2025-11-28 |  | Tower A | Super Structure | L25 | MEP | HVAC Grill Fixing
40905 | Tower A - Super Structure - Finishes & MEP - L35 to L45 | Not Ready |  | 2025-02-27 | 2025-04-21 | FHC & Accessories fixing | 100 | 0 |  | 2025-10-07 |  | 2025-11-28 |  | Tower A | Super Structure | L35
40907 | Tower A - Super Structure - Finishes & MEP - L35 to L45 | Not Ready |  | 2025-02-27 | 2025-04-21 | Soil & Waste Downtake piping in Plumbing Shaft | 100 | 0 |  | 2025-10-07 |  | 2025-11-28 |  | Tower A | Super Structure | L35
40911 | Tower A - Super Structure - Finishes & MEP - L35 to L45 | Not Ready |  | 2025-02-27 | 2025-04-21 | HVAC Shaft Ducting | 100 | 0 |  | 2025-10-07 |  | 2025-11-28 |  | Tower A | Super Structure | L35 | MEP | HVAC Grill Fixing
40914 | Tower A - Super Structure - Finishes & MEP - L45 to L55 | Not Ready |  | 2025-06-25 | 2025-08-22 | FHC & Accessories fixing | 100 | 0 |  | 2025-10-07 |  | 2025-11-28 |  | Tower A | Super Structure | L45
40916 | Tower A - Super Structure - Finishes & MEP - L45 to L55 | Not Ready |  | 2025-06-25 | 2025-08-22 | Soil & Waste Downtake piping in Plumbing Shaft | 100 | 0 |  | 2025-10-07 |  | 2025-11-28 |  | Tower A | Super Structure | L45
40920 | Tower A - Super Structure - Finishes & MEP - L45 to L55 | Not Ready |  | 2025-06-25 | 2025-08-22 | HVAC Shaft Ducting | 100 | 0 |  | 2025-10-07 |  | 2025-11-28 |  | Tower A | Super Structure | L45 | MEP | HVAC Grill Fixing
42567 |  | Not Committed |  | 2025-03-13 | 2025-12-31 | Finishes after 1st Fix | 100 | 0 |  | 2025-10-07 |  | 2025-12-16
42568 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-03-13 | 2025-04-05 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-10-07 |  | 2025-10-31 |  | Tower A | Super Structure | L27 | Finishes | Blockwork
42639 |  | Not Committed |  | 2025-05-17 | 2026-01-17 | Finishes after 1st Fix | 100 | 0 |  | 2025-10-07 |  | 2025-12-30
42640 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-05-17 | 2025-06-10 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-10-07 |  | 2025-10-31 |  | Tower A | Super Structure | L31 | Finishes | Blockwork
44250 | Tower A | Not Ready | High Side Procurement | 2025-10-01 | 2026-03-18 | STP Equipments | 100 | 0 |  | 2025-10-07 |  | 2026-03-24 |  | Tower A | --
44523 |  | Not Committed |  | 2024-04-22 | 2024-05-21 | Pour 4 (Grid PA-4 to PA-8) | 100 | 0 |  | 2025-10-07 |  | 2025-11-05
44524 | NTA_Zone 2 - Super Structure - P4 to P5 - Pour 4 | Not Ready | RCC Works - Vertical | 2024-04-22 | 2024-05-09 | Columns/ Walls_NTA | 100 | 0 |  | 2025-10-07 |  | 2025-10-24 |  | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
44524 | NTA_Zone 2 - Super Structure - P4 to P5 - Pour 4 | Not Ready | RCC Works - Vertical | 2024-04-22 | 2024-05-09 | Columns/ Walls_NTA | 100 | 0 |  | 2025-10-07 |  | 2025-10-24 |  | NTA_Zone 2 | Super Structure
45403 | Tower B - Sub Structure - Finishes & MEP - B1 to GF | Not Ready | Partition Wall-Blockwork | 2025-02-21 | 2025-03-10 | Partition Walls | 100 | 0 |  | 2025-10-07 |  | 2025-10-24 |  | Tower B | Sub Structure | B1
45412 | Tower B - Super Structure - Finishes & MEP - P1 to P2 | Not Ready | Partition Wall-Blockwork | 2025-06-04 | 2025-06-16 | Staircase Area | 100 | 0 |  | 2025-10-07 |  | 2025-10-17 |  | Tower B | Super Structure
45416 | Tower B - Super Structure - Finishes & MEP - P2 to P3 | Not Ready | Partition Wall-Blockwork | 2025-06-30 | 2025-07-10 | Staircase Area | 100 | 0 |  | 2025-10-07 |  | 2025-10-17 |  | Tower B | Super Structure
47303 |  | Not Committed |  | 2027-04-22 | 2028-06-24 | L43-44 | 100 | 0 |  | 2025-10-07 |  | 2028-07-17
47303 |  | Not Committed |  | 2027-04-22 | 2028-06-24 | L43-44 | 100 | 0 |  | 2025-10-07 |  | 2028-07-17 |  |  |  |  | Finishes | Gypsum Plastering Works
47310 |  | Not Committed |  | 2027-09-21 | 2027-11-13 | Finishes after 1st Fix | 100 | 0 |  | 2025-10-07 |  | 2027-09-24
47311 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2027-09-21 | 2027-10-01 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-10-07 |  | 2025-10-17 |  | Tower B | Super Structure | L43 | Finishes | Blockwork
47583 |  | Not Ready |  | 2024-11-11 | 2024-11-18 | Fwk & Casting_NTA | 100 | 0 |  | 2025-10-07 |  | 2025-10-14
47583 |  | Not Ready |  | 2024-11-11 | 2024-11-18 | Fwk & Casting_NTA | 100 | 0 |  | 2025-10-07 |  | 2025-10-14 |  |  |  |  | RCC Super Structure | Foundation RCC Works
47583 |  | Not Ready |  | 2024-11-11 | 2024-11-18 | Fwk & Casting_NTA | 100 | 0 |  | 2025-10-07 |  | 2025-10-14 |  |  |  |  | RCC Sub Structure | Raft RCC Works
47588 |  | Not Ready |  | 2024-11-11 | 2024-11-15 | Fwk & Casting_NTA | 100 | 0 |  | 2025-10-07 |  | 2025-10-11
47588 |  | Not Ready |  | 2024-11-11 | 2024-11-15 | Fwk & Casting_NTA | 100 | 0 |  | 2025-10-07 |  | 2025-10-11 |  |  |  |  | RCC Super Structure | Foundation RCC Works
47588 |  | Not Ready |  | 2024-11-11 | 2024-11-15 | Fwk & Casting_NTA | 100 | 0 |  | 2025-10-07 |  | 2025-10-11 |  |  |  |  | RCC Sub Structure | Raft RCC Works
8477 | T-14-11th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-09-02 | 2025-09-06 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-10-08 | 2025-11-28 | 2025-10-13 | 2025-12-05
8522 | T-14-GF Flat Area | Not Ready | Window | 2025-09-12 | 2025-10-05 | Window | 100 | 0 |  | 2025-10-08 |  | 2025-10-29
8605 | T-14-3rd Floor Flat Area | Not Ready | Toilet flooring | 2025-09-08 | 2025-10-11 | Toilet flooring | 100 | 0 |  | 2025-10-08 |  | 2025-11-09
9032 | T-15-11th Floor | Complete | Shuttering | 2025-10-06 | 2025-10-10 | Slab and Beam Shuttering | 3715 | 3715 | Sqm | 2025-10-08 | 2025-11-01 | 2025-10-13 | 2025-11-05
9035 | T-15-Terrace | Complete |  | 2025-10-14 | 2025-10-27 | 11th Floor Roof | 100 | 100 |  | 2025-10-08 | 2025-11-08 | 2025-10-21 | 2025-12-02
9179 | T-15-4th Floor Flat Area | Not Ready | Flooring & skirting | 2025-10-07 | 2025-11-21 | Flooring & skirting | 100 | 0 |  | 2025-10-08 |  | 2025-11-24
9223 | T-15-6th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-10-06 | 2025-10-28 | Plumbing Pipe Line | 100 | 0 |  | 2025-10-08 |  | 2025-10-30
11252 | T-19-4th Floor Flat Area | Not Ready | Plastering | 2025-10-21 | 2025-11-14 | Plastering-Cement | 100 | 0 |  | 2025-10-08 |  | 2025-10-29
11636 | T-18-Terrace | Not Ready | AL - Shear Walls/Corewalls Steel | 2025-12-17 | 2025-12-22 | AL - Shear Walls/Corewalls Steel | 20.5 | 0 | MT | 2025-10-08 |  | 2025-10-13
11773 | T-18-4th Floor Flat Area | Not Ready | Waterproofing | 2025-12-11 | 2026-01-31 | Waterproofing | 100 | 0 |  | 2025-10-08 |  | 2025-11-30
39725 |  | Complete |  | 2025-09-26 | 2025-10-07 | Core Wall L70-71 | 100 | 100 |  | 2025-10-08 | 2025-10-21 | 2025-10-17 | 2025-11-29
39726 | Tower A - Super Structure - Core Wall High Rise L70-71 | Complete | Core Wall RCC Works | 2025-09-26 | 2025-09-26 | Scaffolding & platform | 100 | 100 |  | 2025-10-08 | 2025-10-27 | 2025-10-09 | 2025-10-27 | Tower A | Super Structure | L70 | RCC Super Structure | Core Wall RCC Works
41064 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-02-28 | 2025-03-03 | Lobby Blockwork | 100 | 0 |  | 2025-10-08 |  | 2025-10-10 |  | Tower A | Super Structure | L7 | Finishes | Blockwork
41539 |  | Started |  | 2025-06-17 | 2026-05-02 | L37-38 | 100 | 27 |  | 2025-10-08 | 2025-10-08 | 2026-05-23 |  |  |  |  | Finishes | Gypsum Plastering Works
41539 |  | Started |  | 2025-06-17 | 2026-05-02 | L37-38 | 100 | 27 |  | 2025-10-08 | 2025-10-08 | 2026-05-23
41540 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2025-10-08 | 2025-10-11 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 40 |  | 2025-10-08 | 2025-10-08 | 2026-04-11 |  | Tower A | Super Structure | L37 | MEP | FPS 1st Fix - MEP & Finishes
41541 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-10-08 | 2025-10-11 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-10-08 |  | 2025-10-10 |  | Tower A | Super Structure | L37 | MEP | Electrical 1st Fixes
45264 |  | Not Ready |  | 2025-07-10 | 2025-08-06 | P5-P6 | 100 | 0 |  | 2025-10-08 |  | 2025-10-28
45265 | Tower B - Super Structure - Core & Outer Slab P5-P6 | Not Ready | RCC Works - Vertical | 2025-07-10 | 2025-07-25 | Outer Columns_TA | 100 | 0 |  | 2025-10-08 |  | 2025-10-23 |  | Tower B | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
45421 |  | Not Committed |  | 2025-07-10 | 2025-09-03 | P4 to P5 | 100 | 0 |  | 2025-10-08 |  | 2025-11-13
45421 |  | Not Committed |  | 2025-07-10 | 2025-09-03 | P4 to P5 | 100 | 0 |  | 2025-10-08 |  | 2025-11-13
45421 |  | Not Committed |  | 2025-07-10 | 2025-09-03 | P4 to P5 | 100 | 0 |  | 2025-10-08 |  | 2025-11-13
45422 | Tower B - Super Structure - Finishes & MEP - P4 to P5 | Not Ready | Partition Wall-Blockwork | 2025-07-10 | 2025-07-16 | De-shuttering & Area clearance | 100 | 0 |  | 2025-10-08 |  | 2025-10-14 |  | Tower B | Super Structure
48342 | Retail - Sub structure - B3 to B2 - P5 | Not Ready |  | 2025-02-19 | 2025-02-26 | Section 15_lift 2 | 100 | 0 |  | 2025-10-08 |  | 2025-10-15 |  | Retail | Sub Structure | B3
9128 | T-15-2nd Floor Flat Area | Not Ready | Putty | 2025-10-11 | 2026-01-03 | Putty | 100 | 0 |  | 2025-10-09 |  | 2026-01-01
9681 | T-16-3rd Floor Common Area | Not Ready | Plastering | 2025-10-30 | 2025-12-04 | Plastering-Gypsum | 100 | 0 |  | 2025-10-09 |  | 2025-11-12
10111 | T-21-GF Flat Area | Not Ready | 1st Coat Painting | 2025-10-03 | 2025-11-24 | 1st Coat Painting | 100 | 0 |  | 2025-10-09 |  | 2025-11-27
10270 | T-21-6th Floor Flat Area | Not Ready | Toilets False Celing | 2025-11-16 | 2025-12-19 | Toilets False Celing | 100 | 0 |  | 2025-10-09 |  | 2025-11-13
10390 |  | Not Ready |  | 2025-11-13 | 2026-08-13 | Eleventh Floor | 100 | 0 |  | 2025-10-09 |  | 2026-07-13
10391 |  | Not Ready |  | 2025-11-13 | 2026-08-13 | Flat Area | 100 | 0 |  | 2025-10-09 |  | 2026-07-13
10788 | T-20-6th Floor Flat Area | Not Ready | Dado | 2025-11-11 | 2025-12-08 | Dado | 100 | 0 |  | 2025-10-09 |  | 2025-11-09
10811 | T-20-7th Floor Flat Area | Not Ready | Waterproofing | 2025-11-09 | 2025-12-11 | Waterproofing | 100 | 0 |  | 2025-10-09 |  | 2025-11-13
10851 | T-20-8th Floor Common Area | Not Ready | Plastering | 2025-11-09 | 2025-12-11 | Plastering-Gypsum | 100 | 0 |  | 2025-10-09 |  | 2025-11-13
10877 | T-20-9th Floor Common Area | Not Ready | Plastering | 2025-11-09 | 2025-12-11 | Plastering-Gypsum | 100 | 0 |  | 2025-10-09 |  | 2025-11-13
11100 | T-19-9th Floor | Complete | RCC | 2025-10-18 | 2025-10-20 | Slab& Beam RCC | 340 | 340 | CUM | 2025-10-09 | 2025-11-21 | 2025-10-09 | 2025-11-22
11852 | T-18-7th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-12-18 | 2026-01-03 | Electrical DB Fixing | 100 | 0 |  | 2025-10-09 |  | 2025-10-28
39727 | Tower A - Super Structure - Core Wall High Rise L70-71 | Complete | Core Wall RCC Works | 2025-09-27 | 2025-09-30 | Reinf & Guide shoes fixing | 100 | 100 |  | 2025-10-09 | 2025-10-21 | 2025-10-13 | 2025-10-29 | Tower A | Super Structure | L70 | RCC Super Structure | Core Wall RCC Works
40172 | Tower A - Super Structure - Finishes & MEP - P5 to P6 | Not Ready | Partition Wall-Blockwork | 2024-06-05 | 2024-06-15 | Staircase Area | 100 | 0 |  | 2025-10-09 |  | 2025-10-22 |  | Tower A | Super Structure
40348 | Tower A - Super Structure - Finishes & MEP - L47 to L48 | Not Ready | Partition Wall-Blockwork | 2025-09-15 | 2025-09-20 | Staircase Area | 100 | 0 |  | 2025-10-09 |  | 2025-10-14 |  | Tower A | Super Structure | L47
40351 | Tower A - Super Structure - Finishes & MEP - L48 to L49 | Not Ready | Partition Wall-Blockwork | 2025-09-15 | 2025-09-23 | Partition Walls | 100 | 0 |  | 2025-10-09 |  | 2025-10-16 |  | Tower A | Super Structure | L48
40627 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2024-03-15 | 2024-03-18 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2025-10-09 |  | 2025-10-13 |  | Tower A | Sub Structure | B2 | MEP | FPS 2nd Fix - MEP & Finishes
40628 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2024-03-15 | 2024-03-20 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2025-10-09 |  | 2025-10-15 |  | Tower A | Sub Structure | B2 | MEP | Electrical 2nd Fix - MEP & Finishes
40629 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-03-15 | 2024-03-22 | FAPA Device Fixing | 100 | 0 |  | 2025-10-09 |  | 2025-10-17 |  | Tower A | Sub Structure | B2
40629 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-03-15 | 2024-03-22 | FAPA Device Fixing | 100 | 0 |  | 2025-10-09 |  | 2025-10-17 |  | Tower A | Sub Structure | B2
40629 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-03-15 | 2024-03-22 | FAPA Device Fixing | 100 | 0 |  | 2025-10-09 |  | 2025-10-17 |  | Tower A | Sub Structure | B2
40629 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-03-15 | 2024-03-22 | FAPA Device Fixing | 100 | 0 |  | 2025-10-09 |  | 2025-10-17 |  | Tower A | Sub Structure | B2
40630 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2024-03-15 | 2024-03-18 | HVAC Grill Fixing | 100 | 0 |  | 2025-10-09 |  | 2025-10-13 |  | Tower A | Sub Structure | B2 | MEP | HVAC Grill Fixing
40802 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2024-06-05 | 2024-06-28 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-10-09 |  | 2025-11-03 |  | Tower A | Super Structure |  | MEP | FPS 1st Fix - MEP & Finishes
40803 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2024-06-05 | 2024-06-28 | PHE 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-10-09 |  | 2025-11-03 |  | Tower A | Super Structure
40804 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2024-06-05 | 2024-06-22 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-10-09 |  | 2025-10-28 |  | Tower A | Super Structure |  | MEP | Electrical 1st Fixes
42209 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2024-09-12 | 2024-09-20 | Door & Window Frame work | 100 | 0 |  | 2025-10-09 |  | 2025-10-17 |  | Tower A | Super Structure | L7 | Finishes | Door & Window Frame work
42227 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2024-09-21 | 2024-09-28 | Door & Window Frame work | 100 | 0 |  | 2025-10-09 |  | 2025-10-17 |  | Tower A | Super Structure | L8 | Finishes | Door & Window Frame work
42245 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2024-09-30 | 2024-10-08 | Door & Window Frame work | 100 | 0 |  | 2025-10-09 |  | 2025-10-17 |  | Tower A | Super Structure | L9 | Finishes | Door & Window Frame work
42281 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2024-10-18 | 2024-10-25 | Door & Window Frame work | 100 | 0 |  | 2025-10-09 |  | 2025-10-17 |  | Tower A | Super Structure | L11 | Finishes | Door & Window Frame work
42299 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2024-10-26 | 2024-11-04 | Door & Window Frame work | 100 | 0 |  | 2025-10-09 |  | 2025-10-17 |  | Tower A | Super Structure | L12 | Finishes | Door & Window Frame work
42317 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2024-11-05 | 2024-11-12 | Door & Window Frame work | 100 | 0 |  | 2025-10-09 |  | 2025-10-17 |  | Tower A | Super Structure | L13 | Finishes | Door & Window Frame work
42657 |  | Not Committed |  | 2025-05-26 | 2026-01-23 | Finishes after 1st Fix | 100 | 0 |  | 2025-10-09 |  | 2026-01-05
42658 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-05-26 | 2025-06-18 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-10-09 |  | 2025-11-01 |  | Tower A | Super Structure | L32 | Finishes | Blockwork
9033 | T-15-11th Floor | Complete | Slab& Beam Steel & Conduting | 2025-10-08 | 2025-10-11 | Slab& Beam Steel & Conduting | 13 | 13 | MT | 2025-10-10 | 2025-11-01 | 2025-10-13 | 2025-11-05
9053 | T-15-Basement Floor | Not Ready | 1st Coat Painting | 2025-09-23 | 2025-10-27 | 1st Coat Painting | 100 | 0 |  | 2025-10-10 |  | 2025-11-14
9227 | T-15-6th Floor Flat Area | Not Ready | Plastering | 2025-10-08 | 2025-11-22 | Plastering-Gypsum | 100 | 0 |  | 2025-10-10 |  | 2025-11-25
9238 |  | Not Ready |  | 2025-10-16 | 2026-05-08 | Common Area | 100 | 0 |  | 2025-10-10 |  | 2026-05-04
9585 | T-16-GF Flat Area | Not Ready | Toilets False Celing | 2025-11-06 | 2025-11-22 | Toilets-False Celing | 100 | 0 |  | 2025-10-10 |  | 2025-10-25
9690 | T-16-4th Floor Flat Area | Not Ready | Blockwork | 2025-10-27 | 2025-11-20 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-10-10 |  | 2025-10-31
9729 | T-16-5th Floor Flat Area | Not Ready | Railing | 2025-10-27 | 2025-12-01 | Balcony Railing | 100 | 0 |  | 2025-10-10 |  | 2025-11-10
10692 | T-20-2nd Floor Flat Area | Not Ready | 1st Coat Painting | 2025-11-25 | 2026-02-12 | 1st Coat Painting | 100 | 0 |  | 2025-10-10 |  | 2025-12-29
10764 | T-20-5th Floor Flat Area | Not Ready | Toilets False Celing | 2025-11-10 | 2025-12-12 | Toilets False Celing | 100 | 0 |  | 2025-10-10 |  | 2025-11-11
11205 | T-19-2nd Floor Flat Area | Not Ready | Toilet flooring | 2025-10-30 | 2025-12-03 | Toilet flooring | 100 | 0 |  | 2025-10-10 |  | 2025-11-13
11267 | T-19-4th Floor Common Area | Not Ready | Plastering | 2025-10-23 | 2025-11-27 | Plastering-Gypsum | 100 | 0 |  | 2025-10-10 |  | 2025-11-12
11276 | T-19-5th Floor Flat Area | Not Ready | Blockwork | 2025-10-20 | 2025-11-13 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-10-10 |  | 2025-10-30
11315 | T-19-6th Floor Flat Area | Not Ready | Railing | 2025-10-20 | 2025-11-24 | Balcony Railing | 100 | 0 |  | 2025-10-10 |  | 2025-11-13
11638 | T-18-Terrace | Not Ready | Conduiting | 2025-12-19 | 2025-12-23 | Conduiting works | 100 | 0 |  | 2025-10-10 |  | 2025-10-11
11667 | T-18-GF Flat Area | Not Ready | Putty | 2025-12-01 | 2025-12-23 | Putty | 100 | 0 |  | 2025-10-10 |  | 2025-11-03
11728 | T-18-2nd Floor Flat Area | Not Ready | Putty | 2025-12-15 | 2026-03-09 | Putty | 100 | 0 |  | 2025-10-10 |  | 2026-01-03
11751 | T-18-3rd Floor Flat Area | Not Ready | Toilet flooring | 2025-12-12 | 2026-01-13 | Toilet flooring | 100 | 0 |  | 2025-10-10 |  | 2025-11-14
11824 | T-18-6th Floor Flat Area | Not Ready | Plastering | 2025-12-17 | 2026-01-08 | Plastering-Cement | 100 | 0 |  | 2025-10-10 |  | 2025-11-01
39728 | Tower A - Super Structure - Core Wall High Rise L70-71 | Complete | Core Wall RCC Works | 2025-09-29 | 2025-10-01 | ACS Form Closing & Alignment | 100 | 100 |  | 2025-10-10 | 2025-10-28 | 2025-10-14 | 2025-11-29 | Tower A | Super Structure | L70 | RCC Super Structure | Core Wall RCC Works
40520 | Tower A - Super Structure - Finishes & MEP - L46 to L47 | Not Ready | Gypsum Plastering Works | 2025-09-22 | 2025-10-15 | L46-47 | 100 | 0 |  | 2025-10-10 |  | 2025-11-04 |  | Tower A | Super Structure | L46 | Finishes | Gypsum Plastering Works
40520 | Tower A - Super Structure - Finishes & MEP - L46 to L47 | Not Ready | Gypsum Plastering Works | 2025-09-22 | 2025-10-15 | L46-47 | 100 | 0 |  | 2025-10-10 |  | 2025-11-04 |  | Tower A | Super Structure | L46
42263 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2024-10-18 | 2024-10-25 | Door & Window Frame work | 100 | 0 |  | 2025-10-10 |  | 2025-10-18 |  | Tower A | Super Structure | L10 | Finishes | Door & Window Frame work
42335 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2024-11-19 | 2024-11-26 | Door & Window Frame work | 100 | 0 |  | 2025-10-10 |  | 2025-10-17 |  | Tower A | Super Structure | L14 | Finishes | Door & Window Frame work
42360 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2024-11-27 | 2024-12-04 | Door & Window Frame work | 100 | 0 |  | 2025-10-10 |  | 2025-10-17 |  | Tower A | Super Structure | L15 | Finishes | Door & Window Frame work
8479 | T-14-11th Floor | Complete | Shuttering | 2025-09-05 | 2025-09-09 | Slab and Beam Shuttering | 3605 | 3605 | Sqm | 2025-10-11 | 2025-12-05 | 2025-10-13 | 2025-12-11
8677 | T-14-6th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-09-05 | 2025-09-27 | Plumbing Pipe Line | 100 | 0 |  | 2025-10-11 |  | 2025-11-01
9068 | T-15-GF Flat Area | Not Ready | Window | 2025-10-14 | 2025-11-06 | Window | 100 | 0 |  | 2025-10-11 |  | 2025-11-02
9535 | T-16-9th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-10-28 | 2025-11-04 | AL - Shear Walls/Corewalls Steel | 25 | 25 | MT | 2025-10-11 | 2025-11-19 | 2025-10-13 | 2025-11-29
9647 | T-16-2nd Floor Flat Area | Not Ready | Flooring & skirting | 2025-11-07 | 2025-12-20 | Flooring & skirting | 100 | 0 |  | 2025-10-11 |  | 2025-11-23
9792 |  | Not Ready |  | 2025-12-11 | 2026-08-19 | Eighth Floor | 100 | 0 |  | 2025-10-11 |  | 2026-06-20
9793 |  | Not Ready |  | 2025-12-11 | 2026-07-28 | Flat Area | 100 | 0 |  | 2025-10-11 |  | 2026-05-31
10294 | T-21-7th Floor Flat Area | Not Ready | Dado | 2025-11-14 | 2025-12-11 | Dado | 100 | 0 |  | 2025-10-11 |  | 2025-11-08
11102 | T-19-10th Floor | Not Ready | AL - Shear Walls/Corewalls Steel | 2025-10-21 | 2025-10-25 | AL - Shear Walls/Corewalls Steel | 28.4 | 0 | MT | 2025-10-11 |  | 2025-10-17
11233 | T-19-3rd Floor Flat Area | Not Ready | Flooring & skirting | 2025-10-29 | 2025-12-13 | Flooring & skirting | 100 | 0 |  | 2025-10-11 |  | 2025-11-27
11637 | T-18-Terrace | Not Ready | Shear Walls/Corewalls Shuttering | 2025-12-20 | 2025-12-25 | Shear Walls/Corewalls Shuttering | 100 | 0 |  | 2025-10-11 |  | 2025-10-14
11754 | T-18-3rd Floor Flat Area | Not Ready | Putty | 2025-12-18 | 2026-03-12 | Putty | 100 | 0 |  | 2025-10-11 |  | 2026-01-03
40477 | Tower A - Super Structure - Finishes & MEP - P4 to P5 | Not Ready | Gypsum Plastering Works | 2024-06-07 | 2024-08-02 | P4 to P5_TA & NTA | 100 | 0 |  | 2025-10-11 |  | 2025-12-04 |  | Tower A | Super Structure |  | Finishes | Gypsum Plastering Works
40612 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2024-04-03 | 2024-04-05 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2025-10-11 |  | 2025-10-15 |  | Tower A | Sub Structure | B3 | MEP | FPS 2nd Fix - MEP & Finishes
40613 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2024-04-03 | 2024-04-08 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2025-10-11 |  | 2025-10-17 |  | Tower A | Sub Structure | B3 | MEP | Electrical 2nd Fix - MEP & Finishes
40614 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-04-03 | 2024-04-10 | FAPA Device Fixing | 100 | 0 |  | 2025-10-11 |  | 2025-10-21 |  | Tower A | Sub Structure | B3
40614 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-04-03 | 2024-04-10 | FAPA Device Fixing | 100 | 0 |  | 2025-10-11 |  | 2025-10-21 |  | Tower A | Sub Structure | B3
40614 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-04-03 | 2024-04-10 | FAPA Device Fixing | 100 | 0 |  | 2025-10-11 |  | 2025-10-21 |  | Tower A | Sub Structure | B3
40614 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-04-03 | 2024-04-10 | FAPA Device Fixing | 100 | 0 |  | 2025-10-11 |  | 2025-10-21 |  | Tower A | Sub Structure | B3
40615 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2024-04-03 | 2024-04-05 | HVAC Grill Fixing | 100 | 0 |  | 2025-10-11 |  | 2025-10-15 |  | Tower A | Sub Structure | B3 | MEP | HVAC Grill Fixing
41065 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-03-04 | 2025-03-08 | Lobby Plastering | 100 | 0 |  | 2025-10-11 |  | 2025-10-16 |  | Tower A | Super Structure | L7 | Finishes | Lobby Plastering
41080 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-03-04 | 2025-03-06 | Lobby Blockwork | 100 | 0 |  | 2025-10-11 |  | 2025-10-14 |  | Tower A | Super Structure | L8 | Finishes | Blockwork
41542 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2025-10-11 | 2025-10-14 | FAPA Cabling | 100 | 0 |  | 2025-10-11 |  | 2025-10-13 |  | Tower A | Super Structure | L37
44550 |  | Not Committed |  | 2024-07-12 | 2024-12-05 | B2 to B1 | 100 | 0 |  | 2025-10-11 |  | 2026-02-13
44550 |  | Not Committed |  | 2024-07-12 | 2024-12-05 | B2 to B1 | 100 | 0 |  | 2025-10-11 |  | 2026-02-13
44550 |  | Not Committed |  | 2024-07-12 | 2024-12-05 | B2 to B1 | 100 | 0 |  | 2025-10-11 |  | 2026-02-13
44551 | NTA_Zone 2 - Sub Structure - B2 to B1 | Not Ready | Finishes (Lobby & Floor Area) | 2024-07-12 | 2024-09-10 | VDF Flooring | 100 | 0 |  | 2025-10-11 |  | 2025-12-03 |  | NTA_Zone 2 | Sub Structure | B2
44551 | NTA_Zone 2 - Sub Structure - B2 to B1 | Not Ready | Finishes (Lobby & Floor Area) | 2024-07-12 | 2024-09-10 | VDF Flooring | 100 | 0 |  | 2025-10-11 |  | 2025-12-03 |  | NTA_Zone 2 | Sub Structure | B2
8560 | T-14-1st Floor Flat Area | Not Ready | 1st Coat Painting | 2025-09-19 | 2025-12-12 | 1st Coat Painting | 100 | 0 |  | 2025-10-12 |  | 2026-01-03
8608 | T-14-3rd Floor Flat Area | Not Ready | Putty | 2025-09-15 | 2025-12-08 | Putty | 100 | 0 |  | 2025-10-12 |  | 2026-01-05
9151 | T-15-3rd Floor Flat Area | Not Ready | Toilet flooring | 2025-10-08 | 2025-11-12 | Toilet flooring | 100 | 0 |  | 2025-10-12 |  | 2025-11-16
9603 | T-16-GF Common Area | Not Ready | Flooring & skirting | 2025-11-04 | 2025-12-17 | Flooring & skirting | 100 | 0 |  | 2025-10-12 |  | 2025-11-25
9641 | T-16-2nd Floor Flat Area | Not Ready | Waterproofing | 2025-11-07 | 2025-12-26 | Waterproofing | 100 | 0 |  | 2025-10-12 |  | 2025-11-30
9694 | T-16-4th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-10-29 | 2025-11-17 | Electrical DB Fixing | 100 | 0 |  | 2025-10-12 |  | 2025-10-30
10143 | T-21-1st Floor Flat Area | Not Ready | Window | 2025-10-11 | 2025-11-04 | Window | 100 | 0 |  | 2025-10-12 |  | 2025-11-03
11280 | T-19-5th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-10-22 | 2025-11-10 | Electrical DB Fixing | 100 | 0 |  | 2025-10-12 |  | 2025-10-30
11839 | T-18-6th Floor Common Area | Not Ready | Plastering | 2025-12-19 | 2026-01-22 | Plastering-Gypsum | 100 | 0 |  | 2025-10-12 |  | 2025-11-15
8480 | T-14-11th Floor | Complete | Slab& Beam Steel & Conduting | 2025-09-08 | 2025-09-11 | Slab& Beam Steel & Conduting | 10 | 10 | MT | 2025-10-13 | 2025-12-10 | 2025-10-18 | 2025-12-18
8523 | T-14-GF Flat Area | Not Ready | Door | 2025-09-18 | 2025-10-10 | Door | 100 | 0 |  | 2025-10-13 |  | 2025-11-03
8681 | T-14-6th Floor Flat Area | Not Ready | Plastering | 2025-09-08 | 2025-10-22 | Plastering-Gypsum | 100 | 0 |  | 2025-10-13 |  | 2025-11-26
8778 |  | Not Ready |  | 2025-10-11 | 2026-07-17 | Tenth Floor | 100 | 0 |  | 2025-10-13 |  | 2026-07-18
8779 |  | Not Ready |  | 2025-10-11 | 2026-07-17 | Flat Area | 100 | 0 |  | 2025-10-13 |  | 2026-07-18
9106 | T-15-1st Floor Flat Area | Not Ready | 1st Coat Painting | 2025-10-19 | 2026-01-11 | 1st Coat Painting | 100 | 0 |  | 2025-10-13 |  | 2026-01-05
9173 | T-15-4th Floor Flat Area | Not Ready | Waterproofing | 2025-10-07 | 2025-11-27 | Waterproofing | 100 | 0 |  | 2025-10-13 |  | 2025-12-03
9537 | T-16-9th Floor | Complete | Conduiting | 2025-10-30 | 2025-11-05 | Conduiting works | 100 | 100 |  | 2025-10-13 | 2025-12-02 | 2025-10-18 | 2025-12-05
9555 | T-16-Terrace | Not Ready |  | 2025-12-12 | 2025-12-25 | 11th Floor Roof | 100 | 0 |  | 2025-10-13 |  | 2025-10-25
9619 | T-16-1st Floor Flat Area | Not Ready | Toilet flooring | 2025-11-08 | 2025-12-11 | Toilet flooring | 100 | 0 |  | 2025-10-13 |  | 2025-11-16
10317 | T-21-8th Floor Flat Area | Not Ready | Waterproofing | 2025-11-12 | 2025-12-15 | Waterproofing | 100 | 0 |  | 2025-10-13 |  | 2025-11-17
10343 | T-21-9th Floor Flat Area | Not Ready | Waterproofing | 2025-11-12 | 2025-12-15 | Waterproofing | 100 | 0 |  | 2025-10-13 |  | 2025-11-17
10366 | T-21-10th Floor Flat Area | Not Ready | Blockwork | 2025-11-10 | 2025-12-01 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-10-13 |  | 2025-11-04
11104 | T-19-10th Floor | Not Ready | Conduiting | 2025-10-23 | 2025-10-27 | Conduiting works | 100 | 0 |  | 2025-10-13 |  | 2025-10-15
11227 | T-19-3rd Floor Flat Area | Not Ready | Waterproofing | 2025-10-29 | 2025-12-19 | Waterproofing | 100 | 0 |  | 2025-10-13 |  | 2025-12-02
11378 |  | Not Ready |  | 2025-12-04 | 2026-09-04 | Ninth Floor | 100 | 0 |  | 2025-10-13 |  | 2026-07-16
11379 |  | Not Ready |  | 2025-12-04 | 2026-09-04 | Flat Area | 100 | 0 |  | 2025-10-13 |  | 2026-07-16
11404 |  | Not Ready |  | 2025-12-04 | 2026-09-21 | Tenth Floor | 100 | 0 |  | 2025-10-13 |  | 2026-08-01
11405 |  | Not Ready |  | 2025-12-04 | 2026-09-21 | Flat Area | 100 | 0 |  | 2025-10-13 |  | 2026-08-01
11872 |  | Not Ready |  | 2025-12-16 | 2026-08-24 | Eighth Floor | 100 | 0 |  | 2025-10-13 |  | 2026-06-24
11873 |  | Not Ready |  | 2025-12-16 | 2026-08-02 | Flat Area | 100 | 0 |  | 2025-10-13 |  | 2026-06-03
40599 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | Surface Drain/ Manhole Works - MEP & Finishes | 2024-04-01 | 2024-04-17 | Surface Drain/ Manhole works | 100 | 0 |  | 2025-10-13 |  | 2025-10-30 |  | Tower A | Sub Structure | B3
40631 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2024-03-19 | 2024-03-21 | Staircase Fire Door Fixing | 100 | 0 |  | 2025-10-13 |  | 2025-10-16 |  | Tower A | Sub Structure | B2
40666 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | FAPA Cabling - MEP & Finishes | 2024-04-12 | 2024-05-06 | FAPA Cabling | 100 | 0 |  | 2025-10-13 |  | 2025-11-05 |  | Tower A | Sub Structure | B1
40675 |  | Not Committed |  | 2024-03-19 | 2024-05-09 | Lobby/ Common Area | 100 | 0 |  | 2025-10-13 |  | 2025-12-02
40676 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2024-03-19 | 2024-03-27 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-10-13 |  | 2025-10-21 |  | Tower A | Super Structure | GF | MEP | FPS 1st Fix - MEP & Finishes
40677 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2024-03-19 | 2024-03-21 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-10-13 |  | 2025-10-15 |  | Tower A | Super Structure | GF | MEP | Electrical 1st Fixes
40780 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | VDF/ Grade Slab - MEP & Finishes | 2024-06-11 | 2024-08-07 | VDF/ Grade Slab & Apt. finishes | 100 | 0 |  | 2025-10-13 |  | 2025-12-04 |  | Tower A | Super Structure
42459 |  | Not Committed |  | 2025-01-20 | 2025-12-01 | Finishes after 1st Fix | 100 | 0 |  | 2025-10-13 |  | 2025-12-11
42460 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-01-20 | 2025-02-11 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-10-13 |  | 2025-11-05 |  | Tower A | Super Structure | L21 | Finishes | Blockwork
42675 |  | Not Committed |  | 2025-06-03 | 2026-01-23 | Finishes after 1st Fix | 100 | 0 |  | 2025-10-13 |  | 2025-12-24
42676 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-06-03 | 2025-06-26 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-10-13 |  | 2025-11-05 |  | Tower A | Super Structure | L33 | Finishes | Blockwork
42693 |  | Not Committed |  | 2025-06-12 | 2026-01-30 | Finishes after 1st Fix | 100 | 0 |  | 2025-10-13 |  | 2025-12-31
42694 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-06-12 | 2025-07-04 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-10-13 |  | 2025-11-05 |  | Tower A | Super Structure | L34 | Finishes | Blockwork
42711 |  | Not Committed |  | 2025-06-20 | 2026-02-05 | Finishes after 1st Fix | 100 | 0 |  | 2025-10-13 |  | 2026-01-06
42712 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-06-20 | 2025-07-12 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-10-13 |  | 2025-11-05 |  | Tower A | Super Structure | L35 | Finishes | Blockwork
42729 |  | Not Committed |  | 2025-06-28 | 2026-02-11 | Finishes after 1st Fix | 100 | 0 |  | 2025-10-13 |  | 2026-01-12
42730 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-06-28 | 2025-07-23 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-10-13 |  | 2025-11-05 |  | Tower A | Super Structure | L36 | Finishes | Blockwork
42747 |  | Not Committed |  | 2025-07-07 | 2026-02-17 | Finishes after 1st Fix | 100 | 0 |  | 2025-10-13 |  | 2026-01-17
42748 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-07-07 | 2025-08-01 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-10-13 |  | 2025-11-05 |  | Tower A | Super Structure | L37 | Finishes | Blockwork
42765 |  | Not Committed |  | 2025-07-18 | 2026-02-17 | Finishes after 1st Fix | 100 | 0 |  | 2025-10-13 |  | 2026-01-17
42766 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-07-18 | 2025-08-13 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-10-13 |  | 2025-11-05 |  | Tower A | Super Structure | L38 | Finishes | Blockwork
42783 |  | Not Committed |  | 2025-08-02 | 2026-02-23 | Finishes after 1st Fix | 100 | 0 |  | 2025-10-13 |  | 2026-01-23
42784 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-08-02 | 2025-08-30 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-10-13 |  | 2025-11-05 |  | Tower A | Super Structure | L39 | Finishes | Blockwork
42801 |  | Not Committed |  | 2025-08-14 | 2026-02-28 | Finishes after 1st Fix | 100 | 0 |  | 2025-10-13 |  | 2026-01-30
42802 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-08-14 | 2025-09-10 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-10-13 |  | 2025-11-05 |  | Tower A | Super Structure | L40 | Finishes | Blockwork
42819 |  | Not Committed |  | 2025-09-01 | 2026-03-07 | Finishes after 1st Fix | 100 | 0 |  | 2025-10-13 |  | 2026-02-05
42820 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-09-01 | 2025-09-24 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-10-13 |  | 2025-11-05 |  | Tower A | Super Structure | L41 | Finishes | Blockwork
42821 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-09-01 | 2025-09-08 | Door & Window Frame work | 100 | 0 |  | 2025-10-13 |  | 2025-10-21 |  | Tower A | Super Structure | L41 | Finishes | Door & Window Frame work
42873 |  | Not Committed |  | 2025-09-26 | 2026-02-23 | Finishes after 1st Fix | 100 | 0 |  | 2025-10-13 |  | 2026-01-23
42874 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-09-26 | 2025-10-21 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-10-13 |  | 2025-11-05 |  | Tower A | Super Structure | L44 | Finishes | Blockwork
44525 | NTA_Zone 2 - Super Structure - P4 to P5 - Pour 4 | Not Ready | RCC Works - Slab | 2024-04-27 | 2024-05-21 | Slab_NTA | 100 | 0 |  | 2025-10-13 |  | 2025-11-05 |  | NTA_Zone 2 | Super Structure |  | RCC Sub Structure | RCC Works - Slab
44525 | NTA_Zone 2 - Super Structure - P4 to P5 - Pour 4 | Not Ready | RCC Works - Slab | 2024-04-27 | 2024-05-21 | Slab_NTA | 100 | 0 |  | 2025-10-13 |  | 2025-11-05 |  | NTA_Zone 2 | Super Structure
45420 | Tower B - Super Structure - Finishes & MEP - P3 to P4 | Not Ready | Partition Wall-Blockwork | 2025-07-18 | 2025-07-31 | Staircase Area | 100 | 0 |  | 2025-10-13 |  | 2025-10-25 |  | Tower B | Super Structure
47630 |  | Not Committed |  | 2024-11-16 | 2024-12-14 | Pour 12 (PB-A to PB-E) | 100 | 0 |  | 2025-10-13 |  | 2025-11-11
47631 |  | Not Ready |  | 2024-11-16 | 2024-12-03 | Columns/ Walls_NTA | 100 | 0 |  | 2025-10-13 |  | 2025-10-30
47631 |  | Not Ready |  | 2024-11-16 | 2024-12-03 | Columns/ Walls_NTA | 100 | 0 |  | 2025-10-13 |  | 2025-10-30 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
48318 | Retail - Sub structure - B1 to GF - P4 | Not Ready |  | 2025-04-03 | 2025-04-19 | Slab_NTA | 100 | 0 |  | 2025-10-13 |  | 2025-10-30 |  | Retail | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
48318 | Retail - Sub structure - B1 to GF - P4 | Not Ready |  | 2025-04-03 | 2025-04-19 | Slab_NTA | 100 | 0 |  | 2025-10-13 |  | 2025-10-30 |  | Retail | Sub Structure | B1
48374 | Retail - Sub structure - B3 to B2 - P4 | Not Ready |  | 2024-10-19 | 2024-11-06 | Slab_NTA | 100 | 0 |  | 2025-10-13 |  | 2025-10-30 |  | Retail | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
48374 | Retail - Sub structure - B3 to B2 - P4 | Not Ready |  | 2024-10-19 | 2024-11-06 | Slab_NTA | 100 | 0 |  | 2025-10-13 |  | 2025-10-30 |  | Retail | Sub Structure | B3
48410 | Retail - Sub structure - B2 to B1 - P4 | Not Ready |  | 2025-03-08 | 2025-03-26 | Slab_NTA | 100 | 0 |  | 2025-10-13 |  | 2025-10-30 |  | Retail | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
48410 | Retail - Sub structure - B2 to B1 - P4 | Not Ready |  | 2025-03-08 | 2025-03-26 | Slab_NTA | 100 | 0 |  | 2025-10-13 |  | 2025-10-30 |  | Retail | Sub Structure | B2
8630 | T-14-4th Floor Flat Area | Not Ready | Dado | 2025-09-15 | 2025-10-13 | Dado | 100 | 0 |  | 2025-10-14 |  | 2025-11-11
9034 | T-15-11th Floor | Complete | RCC | 2025-10-11 | 2025-10-13 | Slab& Beam RCC | 318 | 318 | CUM | 2025-10-14 | 2025-11-06 | 2025-10-15 | 2025-11-07
9536 | T-16-9th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-11-03 | 2025-11-07 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-10-14 | 2025-11-28 | 2025-10-17 | 2025-12-04
10715 | T-20-3rd Floor Flat Area | Not Ready | Window | 2025-11-24 | 2025-12-16 | Window | 100 | 0 |  | 2025-10-14 |  | 2025-11-05
10817 | T-20-7th Floor Flat Area | Not Ready | Flooring & skirting | 2025-11-14 | 2025-12-28 | Flooring & skirting | 100 | 0 |  | 2025-10-14 |  | 2025-11-27
11103 | T-19-10th Floor | Not Ready | Shear Walls/Corewalls Shuttering | 2025-10-24 | 2025-10-29 | Shear Walls/Corewalls Shuttering | 100 | 0 |  | 2025-10-14 |  | 2025-10-16
11635 | T-18-Terrace | Not Ready |  | 2025-12-17 | 2025-12-30 | 11th Floor Roof | 100 | 0 |  | 2025-10-14 |  | 2025-10-25
11639 | T-18-Terrace | Not Ready | Shuttering | 2025-12-24 | 2025-12-27 | Slab and Beam Shuttering | 3527 | 0 | Sqm | 2025-10-14 |  | 2025-10-19
11849 | T-18-7th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-12-24 | 2026-01-14 | Plumbing Pipe Line | 100 | 0 |  | 2025-10-14 |  | 2025-11-08
40504 | Tower A - Super Structure - Finishes & MEP - L30 to L31 | Not Ready | Gypsum Plastering Works | 2025-03-18 | 2025-04-09 | L30-31 | 100 | 0 |  | 2025-10-14 |  | 2025-11-06 |  | Tower A | Super Structure | L30 | Finishes | Gypsum Plastering Works
40504 | Tower A - Super Structure - Finishes & MEP - L30 to L31 | Not Ready | Gypsum Plastering Works | 2025-03-18 | 2025-04-09 | L30-31 | 100 | 0 |  | 2025-10-14 |  | 2025-11-06 |  | Tower A | Super Structure | L30
41555 |  | Started |  | 2025-06-20 | 2026-05-06 | L38-39 | 100 | 26 |  | 2025-10-14 | 2025-10-14 | 2026-05-28 |  |  |  |  | Finishes | Gypsum Plastering Works
41555 |  | Started |  | 2025-06-20 | 2026-05-06 | L38-39 | 100 | 26 |  | 2025-10-14 | 2025-10-14 | 2026-05-28
41556 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2025-10-14 | 2025-10-17 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 40 |  | 2025-10-14 | 2025-10-14 | 2026-04-15 |  | Tower A | Super Structure | L38 | MEP | FPS 1st Fix - MEP & Finishes
41557 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-10-14 | 2025-10-17 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-10-14 |  | 2025-10-16 |  | Tower A | Super Structure | L38 | MEP | Electrical 1st Fixes
42890 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-09-23 | 2025-10-04 | Cement Plastering in wet areas | 100 | 0 |  | 2025-10-14 |  | 2025-10-27 |  | Tower A | Super Structure | L45
44069 |  | Started |  | 2025-11-14 | 2025-12-24 | L28-33 | 100 | 20 |  | 2025-10-14 | 2025-09-04 | 2025-11-25
44070 | Tower A - Super Structure - Finishes & MEP - L28 to L33 | Started | Façade Works - MEP & Finishes | 2025-11-14 | 2025-12-01 | Al. Frame section (Mullion & Transom) Installation | 100 | 20 | Units | 2025-10-14 | 2025-09-04 | 2025-11-01 |  | Tower A | Super Structure | L28 | Façade | Façade Works
45423 | Tower B - Super Structure - Finishes & MEP - P4 to P5 | Not Ready | Partition Wall-Blockwork | 2025-07-19 | 2025-08-08 | Partition Walls | 100 | 0 |  | 2025-10-14 |  | 2025-11-01 |  | Tower B | Super Structure
48285 | Retail - Sub structure - B1 to GF - P5 | Not Ready |  | 2025-05-02 | 2025-05-09 | Section 14_lift 1 | 100 | 0 |  | 2025-10-14 |  | 2025-10-22 |  | Retail | Sub Structure | B1
48286 | Retail - Sub structure - B1 to GF - P5 | Not Ready |  | 2025-05-02 | 2025-05-09 | Section 15_lift 1 | 100 | 0 |  | 2025-10-14 |  | 2025-10-22 |  | Retail | Sub Structure | B1
9154 | T-15-3rd Floor Flat Area | Not Ready | Putty | 2025-10-15 | 2026-01-07 | Putty | 100 | 0 |  | 2025-10-15 |  | 2026-01-07
9224 | T-15-6th Floor Flat Area | Not Ready | Plastering | 2025-10-14 | 2025-11-06 | Plastering-Cement | 100 | 0 |  | 2025-10-15 |  | 2025-11-08
9758 |  | Not Ready |  | 2025-12-14 | 2026-07-05 | Common Area | 100 | 0 |  | 2025-10-15 |  | 2026-05-08
10370 | T-21-10th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-11-12 | 2025-11-28 | Electrical DB Fixing | 100 | 0 |  | 2025-10-15 |  | 2025-10-31
11776 | T-18-4th Floor Flat Area | Not Ready | Dado | 2025-12-18 | 2026-01-14 | Dado | 100 | 0 |  | 2025-10-15 |  | 2025-11-13
39729 | Tower A - Super Structure - Core Wall High Rise L70-71 | Complete | Core Wall RCC Works | 2025-10-06 | 2025-10-06 | Casting | 100 | 100 |  | 2025-10-15 | 2025-10-31 | 2025-10-16 | 2025-11-01 | Tower A | Super Structure | L70 | RCC Super Structure | Core Wall RCC Works
40001 |  | Complete |  | 2025-10-06 | 2025-10-11 | L66-67 | 100 | 100 |  | 2025-10-15 | 2025-11-01 | 2025-11-03 | 2025-11-14
40001 |  | Complete |  | 2025-10-06 | 2025-10-11 | L66-67 | 100 | 100 |  | 2025-10-15 | 2025-11-01 | 2025-11-03 | 2025-11-14 |  |  |  | Finishes | Gypsum Plastering Works
40002 | Tower A - Super Structure - Core & Outer Slab L66-67 | Complete | RCC Works - Vertical | 2025-10-06 | 2025-10-11 | Outer Columns_TA | 100 | 100 |  | 2025-10-15 | 2025-11-01 | 2025-10-28 | 2025-11-11 | Tower A | Super Structure | L66 | RCC Sub Structure | RCC Works - Vertical
40409 |  | Not Committed |  | 2025-10-06 | 2026-02-03 | L63-64 | 100 | 0 |  | 2025-10-15 |  | 2026-02-25
40409 |  | Not Committed |  | 2025-10-06 | 2026-02-03 | L63-64 | 100 | 0 |  | 2025-10-15 |  | 2026-02-25 |  |  |  |  | Finishes | Gypsum Plastering Works
40410 | Tower A - Super Structure - Finishes & MEP - L63 to L64 | Not Ready | Partition Wall-Blockwork | 2025-10-06 | 2025-10-23 | De-shuttering & Area clearance | 100 | 0 |  | 2025-10-15 |  | 2025-11-03 |  | Tower A | Super Structure | L63
40616 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2024-04-06 | 2024-04-09 | Staircase Fire Door Fixing | 100 | 0 |  | 2025-10-15 |  | 2025-10-18 |  | Tower A | Sub Structure | B3
40644 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2024-03-28 | 2024-04-05 | Final Painting | 100 | 0 |  | 2025-10-15 |  | 2025-10-24 |  | Tower A | Sub Structure | B2 | Finishes | Final Painting
40644 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2024-03-28 | 2024-04-05 | Final Painting | 100 | 0 |  | 2025-10-15 |  | 2025-10-24 |  | Tower A | Sub Structure | B2 | Finishes | Final Painting
40644 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2024-03-28 | 2024-04-05 | Final Painting | 100 | 0 |  | 2025-10-15 |  | 2025-10-24 |  | Tower A | Sub Structure | B2 | Finishes | Final Painting
40654 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2024-04-11 | 2024-04-13 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2025-10-15 |  | 2025-10-18 |  | Tower A | Sub Structure | B1 | MEP | FPS 2nd Fix - MEP & Finishes
40655 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2024-04-11 | 2024-04-16 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2025-10-15 |  | 2025-10-22 |  | Tower A | Sub Structure | B1 | MEP | Electrical 2nd Fix - MEP & Finishes
40656 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-04-11 | 2024-04-18 | FAPA Device Fixing | 100 | 0 |  | 2025-10-15 |  | 2025-10-24 |  | Tower A | Sub Structure | B1
40656 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-04-11 | 2024-04-18 | FAPA Device Fixing | 100 | 0 |  | 2025-10-15 |  | 2025-10-24 |  | Tower A | Sub Structure | B1
40656 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-04-11 | 2024-04-18 | FAPA Device Fixing | 100 | 0 |  | 2025-10-15 |  | 2025-10-24 |  | Tower A | Sub Structure | B1
40656 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-04-11 | 2024-04-18 | FAPA Device Fixing | 100 | 0 |  | 2025-10-15 |  | 2025-10-24 |  | Tower A | Sub Structure | B1
40657 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2024-04-11 | 2024-04-13 | HVAC Grill Fixing | 100 | 0 |  | 2025-10-15 |  | 2025-10-18 |  | Tower A | Sub Structure | B1 | MEP | HVAC Grill Fixing
40729 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2024-05-27 | 2024-06-04 | Final Painting | 100 | 0 |  | 2025-10-15 |  | 2025-10-24 |  | Tower A | Super Structure |  | Finishes | Final Painting
40729 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2024-05-27 | 2024-06-04 | Final Painting | 100 | 0 |  | 2025-10-15 |  | 2025-10-24 |  | Tower A | Super Structure |  | Finishes | Final Painting
40729 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2024-05-27 | 2024-06-04 | Final Painting | 100 | 0 |  | 2025-10-15 |  | 2025-10-24 |  | Tower A | Super Structure |  | Finishes | Final Painting
40756 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2024-06-07 | 2024-06-15 | Final Painting | 100 | 0 |  | 2025-10-15 |  | 2025-10-24 |  | Tower A | Super Structure |  | Finishes | Final Painting
40756 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2024-06-07 | 2024-06-15 | Final Painting | 100 | 0 |  | 2025-10-15 |  | 2025-10-24 |  | Tower A | Super Structure |  | Finishes | Final Painting
40756 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2024-06-07 | 2024-06-15 | Final Painting | 100 | 0 |  | 2025-10-15 |  | 2025-10-24 |  | Tower A | Super Structure |  | Finishes | Final Painting
40806 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | HVAC Ducting - MEP & Finishes | 2024-06-11 | 2024-06-28 | HVAC Ducting/ Fan Installations | 100 | 0 |  | 2025-10-15 |  | 2025-11-03 |  | Tower A | Super Structure |  | MEP | HVAC Ducting
40864 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2024-08-24 | 2024-09-03 | Final Painting | 100 | 0 |  | 2025-10-15 |  | 2025-10-24 |  | Tower A | Super Structure |  | Finishes | Final Painting
40864 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2024-08-24 | 2024-09-03 | Final Painting | 100 | 0 |  | 2025-10-15 |  | 2025-10-24 |  | Tower A | Super Structure |  | Finishes | Final Painting
40864 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2024-08-24 | 2024-09-03 | Final Painting | 100 | 0 |  | 2025-10-15 |  | 2025-10-24 |  | Tower A | Super Structure |  | Finishes | Final Painting
41081 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-03-07 | 2025-03-12 | Lobby Plastering | 100 | 0 |  | 2025-10-15 |  | 2025-10-21 |  | Tower A | Super Structure | L8 | Finishes | Lobby Plastering
41096 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-03-07 | 2025-03-10 | Lobby Blockwork | 100 | 0 |  | 2025-10-15 |  | 2025-10-17 |  | Tower A | Super Structure | L9 | Finishes | Blockwork
42602 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-03-19 | 2025-03-29 | Cement Plastering in wet areas | 100 | 0 |  | 2025-10-15 |  | 2025-10-27 |  | Tower A | Super Structure | L29
42920 |  | Not Committed |  | 2025-09-22 | 2026-08-31 | L47-48 | 100 | 0 |  | 2025-10-15 |  | 2026-08-12
42920 |  | Not Committed |  | 2025-09-22 | 2026-08-31 | L47-48 | 100 | 0 |  | 2025-10-15 |  | 2026-08-12 |  |  |  |  | Finishes | Gypsum Plastering Works
42921 |  | Not Committed |  | 2025-09-22 | 2025-10-22 | MEP 1st Fixes | 100 | 0 |  | 2025-10-15 |  | 2025-11-13
42922 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2025-09-22 | 2025-09-29 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-10-15 |  | 2025-10-23 |  | Tower A | Super Structure | L47 | MEP | FPS 1st Fix - MEP & Finishes
42923 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-09-22 | 2025-09-26 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2025-10-15 |  | 2025-10-21 |  | Tower A | Super Structure | L47 | MEP | Electrical 1st Fixes
42924 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2025-09-22 | 2025-09-29 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2025-10-15 |  | 2025-10-23 |  | Tower A | Super Structure | L47
42925 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2025-09-22 | 2025-10-09 | Wet Area Waterproofing | 100 | 0 |  | 2025-10-15 |  | 2025-11-01 |  | Tower A | Super Structure | L47
47627 |  | Not Committed |  | 2024-11-19 | 2024-12-30 | Pour 11 (PB-E to PB-K) | 100 | 0 |  | 2025-10-15 |  | 2025-11-25
47628 |  | Not Ready |  | 2024-11-19 | 2024-12-11 | Columns/ Walls_NTA | 100 | 0 |  | 2025-10-15 |  | 2025-11-07
47628 |  | Not Ready |  | 2024-11-19 | 2024-12-11 | Columns/ Walls_NTA | 100 | 0 |  | 2025-10-15 |  | 2025-11-07 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
8496 |  | Not Ready |  | 2025-10-15 | 2025-12-11 | Above Terrace | 100 | 0 |  | 2025-10-16 |  | 2025-12-13
8538 | T-14-GF Common Area | Not Ready | Putty | 2025-09-18 | 2025-10-27 | Putty | 100 | 0 |  | 2025-10-16 |  | 2025-11-22
8606 | T-14-3rd Floor Flat Area | Not Ready | Toilets False Celing | 2025-09-17 | 2025-10-20 | Toilets False Celing | 100 | 0 |  | 2025-10-16 |  | 2025-11-18
8744 |  | Not Ready |  | 2025-10-15 | 2026-05-23 | Common Area | 100 | 0 |  | 2025-10-16 |  | 2026-05-25
9069 | T-15-GF Flat Area | Not Ready | Door | 2025-10-19 | 2025-11-12 | Door | 100 | 0 |  | 2025-10-16 |  | 2025-11-09
9248 | T-15-7th Floor Flat Area | Not Ready | Blockwork | 2025-10-13 | 2025-11-05 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-10-16 |  | 2025-11-07
9287 | T-15-8th Floor Flat Area | Not Ready | Railing | 2025-10-13 | 2025-11-16 | Balcony Railing | 100 | 0 |  | 2025-10-16 |  | 2025-11-20
10789 | T-20-6th Floor Flat Area | Not Ready | Toilet flooring | 2025-11-19 | 2025-12-22 | Toilet flooring | 100 | 0 |  | 2025-10-16 |  | 2025-11-20
11122 |  | Not Ready |  | 2025-12-07 | 2026-02-03 | Above Terrace | 100 | 0 |  | 2025-10-16 |  | 2025-12-13
11344 |  | Not Ready |  | 2025-12-07 | 2026-07-06 | Common Area | 100 | 0 |  | 2025-10-16 |  | 2026-05-17
11640 | T-18-Terrace | Not Ready | Slab& Beam Steel & Conduting | 2025-12-26 | 2025-12-29 | Slab& Beam Steel & Conduting | 10.8 | 0 | MT | 2025-10-16 |  | 2025-10-17
11853 | T-18-7th Floor Flat Area | Not Ready | Plastering | 2025-12-26 | 2026-02-10 | Plastering-Gypsum | 100 | 0 |  | 2025-10-16 |  | 2025-11-29
39730 | Tower A - Super Structure - Core Wall High Rise L70-71 | Complete | Core Wall RCC Works | 2025-10-07 | 2025-10-07 | ACS Form Release & jump to next level | 100 | 100 |  | 2025-10-16 | 2025-11-02 | 2025-10-17 | 2025-11-03 | Tower A | Super Structure | L70 | RCC Super Structure | Core Wall RCC Works
40632 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2024-03-22 | 2024-03-28 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2025-10-16 |  | 2025-10-23 |  | Tower A | Sub Structure | B2 | MEP | Electrical
40678 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2024-03-22 | 2024-03-23 | FAPA Cabling | 100 | 0 |  | 2025-10-16 |  | 2025-10-17 |  | Tower A | Super Structure | GF
42371 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2024-12-28 | 2025-01-04 | Door & Window Frame work | 100 | 0 |  | 2025-10-16 |  | 2025-10-25 |  | Tower A | Super Structure | L16 | Finishes | Door & Window Frame work
42389 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2024-12-07 | 2024-12-14 | Door & Window Frame work | 100 | 0 |  | 2025-10-16 |  | 2025-10-25 |  | Tower A | Super Structure | L17 | Finishes | Door & Window Frame work
42407 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2024-12-16 | 2024-12-23 | Door & Window Frame work | 100 | 0 |  | 2025-10-16 |  | 2025-10-25 |  | Tower A | Super Structure | L18 | Finishes | Door & Window Frame work
42425 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-02-07 | 2025-02-14 | Door & Window Frame work | 100 | 0 |  | 2025-10-16 |  | 2025-10-25 |  | Tower A | Super Structure | L19 | Finishes | Door & Window Frame work
42441 |  | Not Committed |  | 2025-02-07 | 2025-11-25 | Finishes after 1st Fix | 100 | 0 |  | 2025-10-16 |  | 2025-12-05
42442 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-02-07 | 2025-03-01 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-10-16 |  | 2025-11-10 |  | Tower A | Super Structure | L20 | Finishes | Blockwork
48377 | Retail - Sub structure - B3 to B2 - P5 | Not Ready |  | 2025-02-27 | 2025-03-17 | Slab_NTA | 100 | 0 |  | 2025-10-16 |  | 2025-11-03 |  | Retail | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
48377 | Retail - Sub structure - B3 to B2 - P5 | Not Ready |  | 2025-02-27 | 2025-03-17 | Slab_NTA | 100 | 0 |  | 2025-10-16 |  | 2025-11-03 |  | Retail | Sub Structure | B3
9036 | T-15-Terrace | Complete | AL - Shear Walls/Corewalls Steel | 2025-10-14 | 2025-10-18 | AL - Shear Walls/Corewalls Steel | 24.5 | 24.5 | MT | 2025-10-17 | 2025-11-08 | 2025-10-22 | 2025-11-13
9239 | T-15-6th Floor Common Area | Not Ready | Plastering | 2025-10-16 | 2025-11-19 | Plastering-Gypsum | 100 | 0 |  | 2025-10-17 |  | 2025-11-21
9538 | T-16-9th Floor | Complete | Shuttering | 2025-11-06 | 2025-11-10 | Slab and Beam Shuttering | 4183 | 4183 | Sqm | 2025-10-17 | 2025-12-04 | 2025-10-22 | 2025-12-08
9601 | T-16-GF Common Area | Not Ready | Toilet flooring | 2025-11-09 | 2025-11-25 | Toilet flooring | 100 | 0 |  | 2025-10-17 |  | 2025-11-02
9622 | T-16-1st Floor Flat Area | Not Ready | Putty | 2025-11-14 | 2026-02-06 | Putty | 100 | 0 |  | 2025-10-17 |  | 2026-01-12
9691 | T-16-4th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-11-06 | 2025-11-27 | Plumbing Pipe Line | 100 | 0 |  | 2025-10-17 |  | 2025-11-07
10126 | T-21-GF Common Area | Not Ready | Door | 2025-10-14 | 2025-11-07 | Door | 100 | 0 |  | 2025-10-17 |  | 2025-11-08
10405 | T-21-11th Floor Flat Area | Not Ready | Railing | 2025-11-13 | 2025-12-16 | Balcony Railing | 100 | 0 |  | 2025-10-17 |  | 2025-11-21
11105 | T-19-10th Floor | Not Ready | Shuttering | 2025-10-28 | 2025-11-03 | Slab and Beam Shuttering | 3548 | 0 | Sqm | 2025-10-17 |  | 2025-10-22
11277 | T-19-5th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-10-28 | 2025-11-20 | Plumbing Pipe Line | 100 | 0 |  | 2025-10-17 |  | 2025-11-07
39731 |  | Complete |  | 2025-10-08 | 2025-10-15 | Core Wall L71-72 | 100 | 100 |  | 2025-10-17 | 2025-11-02 | 2025-11-05 | 2025-11-18
39732 | Tower A - Super Structure - Core Wall High Rise L71-72 | Complete | Core Wall RCC Works | 2025-10-08 | 2025-10-08 | Scaffolding & platform | 100 | 100 |  | 2025-10-17 | 2025-11-02 | 2025-10-18 | 2025-11-05 | Tower A | Super Structure | L71 | RCC Super Structure | Core Wall RCC Works
40352 | Tower A - Super Structure - Finishes & MEP - L48 to L49 | Not Ready | Partition Wall-Blockwork | 2025-09-24 | 2025-09-29 | Staircase Area | 100 | 0 |  | 2025-10-17 |  | 2025-10-23 |  | Tower A | Super Structure | L48
40355 | Tower A - Super Structure - Finishes & MEP - L49 to L50 | Not Ready | Partition Wall-Blockwork | 2025-09-24 | 2025-10-01 | Partition Walls | 100 | 0 |  | 2025-10-17 |  | 2025-10-25 |  | Tower A | Super Structure | L49
41558 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2025-10-17 | 2025-10-21 | FAPA Cabling | 100 | 0 |  | 2025-10-17 |  | 2025-10-18 |  | Tower A | Super Structure | L38
42282 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-09-26 | 2025-10-14 | Flooring & Dado works | 100 | 0 |  | 2025-10-17 |  | 2025-11-05 |  | Tower A | Super Structure | L11 | Finishes | Flooring & Dado
42318 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-09-26 | 2025-10-14 | Flooring & Dado works | 100 | 0 |  | 2025-10-17 |  | 2025-11-05 |  | Tower A | Super Structure | L13 | Finishes | Flooring & Dado
45266 | Tower B - Super Structure - Core & Outer Slab P5-P6 | Not Ready | RCC Works - Slab | 2025-07-26 | 2025-08-06 | Outer Slab_TA | 100 | 0 |  | 2025-10-17 |  | 2025-10-28 |  | Tower B | Super Structure |  | RCC Sub Structure | RCC Works - Slab
8525 | T-14-GF Flat Area | Not Ready | 1st Coat Painting | 2025-09-20 | 2025-11-11 | 1st Coat Painting | 100 | 0 |  | 2025-10-18 |  | 2025-12-10
8678 | T-14-6th Floor Flat Area | Not Ready | Plastering | 2025-09-13 | 2025-10-06 | Plastering-Cement | 100 | 0 |  | 2025-10-18 |  | 2025-11-09
9252 | T-15-7th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-10-15 | 2025-11-02 | Electrical DB Fixing | 100 | 0 |  | 2025-10-18 |  | 2025-11-02
10144 | T-21-1st Floor Flat Area | Not Ready | Door | 2025-10-17 | 2025-11-11 | Door | 100 | 0 |  | 2025-10-18 |  | 2025-11-09
10295 | T-21-7th Floor Flat Area | Not Ready | Toilet flooring | 2025-11-21 | 2025-12-24 | Toilet flooring | 100 | 0 |  | 2025-10-18 |  | 2025-11-21
10323 | T-21-8th Floor Flat Area | Not Ready | Flooring & skirting | 2025-11-17 | 2025-12-31 | Flooring & skirting | 100 | 0 |  | 2025-10-18 |  | 2025-12-04
10349 | T-21-9th Floor Flat Area | Not Ready | Flooring & skirting | 2025-11-17 | 2025-12-31 | Flooring & skirting | 100 | 0 |  | 2025-10-18 |  | 2025-12-04
10910 |  | Not Ready |  | 2025-11-24 | 2026-08-26 | Eleventh Floor | 100 | 0 |  | 2025-10-18 |  | 2026-07-21
10911 |  | Not Ready |  | 2025-11-24 | 2026-08-26 | Flat Area | 100 | 0 |  | 2025-10-18 |  | 2026-07-21
11147 | T-19-GF Flat Area | Not Ready | Putty | 2025-11-04 | 2025-11-26 | Putty | 100 | 0 |  | 2025-10-18 |  | 2025-11-08
11206 | T-19-2nd Floor Flat Area | Not Ready |  | 2025-11-10 | 2025-12-12 | Toilets False Celing | 100 | 0 |  | 2025-10-18 |  | 2025-11-19
11641 | T-18-Terrace | Not Ready | RCC | 2025-12-29 | 2025-12-30 | Slab& Beam RCC | 330.8 | 0 | CUM | 2025-10-18 |  | 2025-10-18
11706 | T-18-1st Floor Flat Area | Not Ready | 1st Coat Painting | 2025-12-23 | 2026-03-17 | 1st Coat Painting | 100 | 0 |  | 2025-10-18 |  | 2026-01-10
11752 | T-18-3rd Floor Flat Area | Not Ready |  | 2025-12-20 | 2026-01-23 | Toilets False Celing | 100 | 0 |  | 2025-10-18 |  | 2025-11-21
11805 | T-18-5th Floor Flat Area | Not Ready | Flooring & skirting | 2025-12-25 | 2026-02-09 | Flooring & skirting | 100 | 0 |  | 2025-10-18 |  | 2025-12-04
11838 |  | Not Ready |  | 2025-12-19 | 2026-07-10 | Common Area | 100 | 0 |  | 2025-10-18 |  | 2026-05-12
39733 | Tower A - Super Structure - Core Wall High Rise L71-72 | Complete | Core Wall RCC Works | 2025-10-09 | 2025-10-11 | Reinf & Guide shoes fixing | 100 | 100 |  | 2025-10-18 | 2025-11-03 | 2025-10-23 | 2025-11-09 | Tower A | Super Structure | L71 | RCC Super Structure | Core Wall RCC Works
40156 | Tower A - Super Structure - Finishes & MEP - P1 to P2 | Not Ready | Partition Wall-Blockwork | 2024-03-26 | 2024-04-05 | Staircase Area | 100 | 0 |  | 2025-10-18 |  | 2025-10-30 |  | Tower A | Super Structure
40159 | Tower A - Super Structure - Finishes & MEP - P2 to P3 | Not Ready | Partition Wall-Blockwork | 2024-03-26 | 2024-04-11 | Partition Walls | 100 | 0 |  | 2025-10-18 |  | 2025-11-05 |  | Tower A | Super Structure
40617 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2024-04-10 | 2024-04-15 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2025-10-18 |  | 2025-10-25 |  | Tower A | Sub Structure | B3 | MEP | Electrical
40658 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2024-04-15 | 2024-04-17 | Staircase Fire Door Fixing | 100 | 0 |  | 2025-10-18 |  | 2025-10-23 |  | Tower A | Sub Structure | B1
40873 | Tower A - Super Structure - Finishes & MEP - B3 to L7 | Not Ready |  | 2024-03-26 | 2024-04-29 | Shaft Cabling in Electrical & ELV Shaft | 100 | 0 |  | 2025-10-18 |  | 2025-11-22 |  | Tower A | Super Structure | B3
40882 | Tower A - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2024-09-26 | 2024-11-02 | Shaft Cabling in Electrical & ELV Shaft | 100 | 0 |  | 2025-10-18 |  | 2025-11-22 |  | Tower A | Super Structure | L15
40891 | Tower A - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2024-06-15 | 2024-07-24 | Shaft Cabling in Electrical & ELV Shaft | 100 | 0 |  | 2025-10-18 |  | 2025-11-22 |  | Tower A | Super Structure | L7
40900 | Tower A - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2024-12-12 | 2025-01-16 | Shaft Cabling in Electrical & ELV Shaft | 100 | 0 |  | 2025-10-18 |  | 2025-11-22 |  | Tower A | Super Structure | L25
40909 | Tower A - Super Structure - Finishes & MEP - L35 to L45 | Not Ready |  | 2025-03-11 | 2025-04-15 | Shaft Cabling in Electrical & ELV Shaft | 100 | 0 |  | 2025-10-18 |  | 2025-11-22 |  | Tower A | Super Structure | L35
40918 | Tower A - Super Structure - Finishes & MEP - L45 to L55 | Not Ready |  | 2025-07-07 | 2025-08-14 | Shaft Cabling in Electrical & ELV Shaft | 100 | 0 |  | 2025-10-18 |  | 2025-11-22 |  | Tower A | Super Structure | L45
41097 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-03-11 | 2025-03-17 | Lobby Plastering | 100 | 0 |  | 2025-10-18 |  | 2025-10-24 |  | Tower A | Super Structure | L9 | Finishes | Lobby Plastering
41112 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-03-11 | 2025-03-13 | Lobby Blockwork | 100 | 0 |  | 2025-10-18 |  | 2025-10-22 |  | Tower A | Super Structure | L10 | Finishes | Blockwork
44540 | NTA_Zone 2 - Super Structure - P1 to P2 | Not Ready | Partition Wall-Blockwork | 2024-06-03 | 2024-07-02 | P1 to P2 | 100 | 0 |  | 2025-10-18 |  | 2025-11-17 |  | NTA_Zone 2 | Super Structure
44540 | NTA_Zone 2 - Super Structure - P1 to P2 | Not Ready | Partition Wall-Blockwork | 2024-06-03 | 2024-07-02 | P1 to P2 | 100 | 0 |  | 2025-10-18 |  | 2025-11-17 |  | NTA_Zone 2 | Super Structure
44540 | NTA_Zone 2 - Super Structure - P1 to P2 | Not Ready | Partition Wall-Blockwork | 2024-06-03 | 2024-07-02 | P1 to P2 | 100 | 0 |  | 2025-10-18 |  | 2025-11-17 |  | NTA_Zone 2 | Super Structure
45394 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 | Not Ready | Partition Wall-Blockwork | 2024-12-05 | 2025-03-21 | Counter-weight Plum Concrete | 100 | 0 |  | 2025-10-18 |  | 2026-02-03 |  | Tower B | Sub Structure | B3
45408 | Tower B - Super Structure - Finishes & MEP - GF to P1 | Not Ready | Partition Wall-Blockwork | 2025-06-02 | 2025-06-19 | Staircase Area | 100 | 0 |  | 2025-10-18 |  | 2025-11-05 |  | Tower B | Super Structure | GF
47321 |  | Not Committed |  | 2027-05-11 | 2028-07-08 | L44-45 | 100 | 0 |  | 2025-10-18 |  | 2028-07-31
47321 |  | Not Committed |  | 2027-05-11 | 2028-07-08 | L44-45 | 100 | 0 |  | 2025-10-18 |  | 2028-07-31 |  |  |  |  | Finishes | Gypsum Plastering Works
47328 |  | Not Committed |  | 2027-10-04 | 2027-11-25 | Finishes after 1st Fix | 100 | 0 |  | 2025-10-18 |  | 2027-10-26
47329 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2027-10-04 | 2027-10-15 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-10-18 |  | 2025-10-30 |  | Tower B | Super Structure | L44 | Finishes | Blockwork
8481 | T-14-11th Floor | Complete | RCC | 2025-09-11 | 2025-09-12 | Slab& Beam RCC | 307 | 307 | CUM | 2025-10-19 | 2025-12-19 | 2025-10-19 | 2025-12-20
9038 | T-15-Terrace | Complete | Conduiting | 2025-10-16 | 2025-10-19 | Conduiting works | 100 | 100 |  | 2025-10-19 | 2025-11-17 | 2025-10-21 | 2025-11-18
9084 | T-15-GF Common Area | Not Ready | Putty | 2025-10-19 | 2025-11-12 | Putty | 100 | 0 |  | 2025-10-19 |  | 2025-11-12
9539 | T-16-9th Floor | Complete | Slab& Beam Steel & Conduting | 2025-11-08 | 2025-11-11 | Slab& Beam Steel & Conduting | 14 | 14 | MT | 2025-10-19 | 2025-12-08 | 2025-10-22 | 2025-12-12
9644 | T-16-2nd Floor Flat Area | Not Ready | Dado | 2025-11-14 | 2025-12-12 | Dado | 100 | 0 |  | 2025-10-19 |  | 2025-11-16
9695 | T-16-4th Floor Flat Area | Not Ready | Plastering | 2025-11-08 | 2025-12-22 | Plastering-Gypsum | 100 | 0 |  | 2025-10-19 |  | 2025-12-02
10792 | T-20-6th Floor Flat Area | Not Ready | Putty | 2025-11-22 | 2026-02-14 | Putty | 100 | 0 |  | 2025-10-19 |  | 2026-01-11
11106 | T-19-10th Floor | Not Ready | Slab& Beam Steel & Conduting | 2025-10-30 | 2025-11-04 | Slab& Beam Steel & Conduting | 11.3 | 0 | MT | 2025-10-19 |  | 2025-10-22
11281 | T-19-5th Floor Flat Area | Not Ready | Plastering | 2025-10-30 | 2025-12-15 | Plastering-Gypsum | 100 | 0 |  | 2025-10-19 |  | 2025-12-03
11799 | T-18-5th Floor Flat Area | Not Ready | Waterproofing | 2025-12-25 | 2026-02-14 | Waterproofing | 100 | 0 |  | 2025-10-19 |  | 2025-12-10
11874 | T-18-8th Floor Flat Area | Not Ready | Blockwork | 2025-12-30 | 2026-01-22 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-10-19 |  | 2025-11-12
11900 | T-18-9th Floor Flat Area | Not Ready | Blockwork | 2025-12-30 | 2026-01-22 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-10-19 |  | 2025-11-12
11913 | T-18-9th Floor Flat Area | Not Ready | Railing | 2025-12-30 | 2026-02-03 | Balcony Railing | 100 | 0 |  | 2025-10-19 |  | 2025-11-22
11939 | T-18-10th Floor Flat Area | Not Ready | Railing | 2025-12-30 | 2026-02-03 | Balcony Railing | 100 | 0 |  | 2025-10-19 |  | 2025-11-22
8693 | T-14-6th Floor Common Area | Not Ready | Plastering | 2025-09-16 | 2025-10-19 | Plastering-Gypsum | 100 | 0 |  | 2025-10-20 |  | 2025-11-22
8702 | T-14-7th Floor Flat Area | Not Ready | Blockwork | 2025-09-12 | 2025-10-05 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-10-20 |  | 2025-11-10
8741 | T-14-8th Floor Flat Area | Not Ready | Railing | 2025-09-12 | 2025-10-16 | Balcony Railing | 100 | 0 |  | 2025-10-20 |  | 2025-11-23
9037 | T-15-Terrace | Complete | Shear Walls/Corewalls Shuttering | 2025-10-17 | 2025-10-21 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-10-20 | 2025-11-12 | 2025-10-25 | 2025-11-17
9152 | T-15-3rd Floor Flat Area | Not Ready |  | 2025-10-17 | 2025-11-20 | Toilets False Celing | 100 | 0 |  | 2025-10-20 |  | 2025-11-21
9176 | T-15-4th Floor Flat Area | Not Ready | Dado | 2025-10-15 | 2025-11-13 | Dado | 100 | 0 |  | 2025-10-20 |  | 2025-11-18
10250 | T-21-5th Floor Flat Area | Not Ready | 1st Coat Painting | 2025-11-29 | 2026-02-21 | 1st Coat Painting | 100 | 0 |  | 2025-10-20 |  | 2026-01-12
10367 | T-21-10th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-11-17 | 2025-12-09 | Plumbing Pipe Line | 100 | 0 |  | 2025-10-20 |  | 2025-11-13
10744 | T-20-4th Floor Flat Area | Not Ready | 1st Coat Painting | 2025-11-26 | 2026-02-18 | 1st Coat Painting | 100 | 0 |  | 2025-10-20 |  | 2026-01-09
11230 | T-19-3rd Floor Flat Area | Not Ready | Dado | 2025-11-07 | 2025-12-04 | Dado | 100 | 0 |  | 2025-10-20 |  | 2025-11-17
8483 | T-14-12th Floor | Complete | AL - Shear Walls/Corewalls Steel | 2025-09-13 | 2025-09-17 | AL - Shear Walls/Corewalls Steel | 22 | 22 | MT | 2025-10-21 | 2025-12-22 | 2025-10-27 | 2025-12-28
8631 | T-14-4th Floor Flat Area | Not Ready | Toilet flooring | 2025-09-22 | 2025-10-25 | Toilet flooring | 100 | 0 |  | 2025-10-21 |  | 2025-11-24
9071 | T-15-GF Flat Area | Not Ready | 1st Coat Painting | 2025-10-21 | 2025-12-11 | 1st Coat Painting | 100 | 0 |  | 2025-10-21 |  | 2025-12-12
9620 | T-16-1st Floor Flat Area | Not Ready | Toilets False Celing | 2025-11-17 | 2025-12-19 | Toilets False Celing | 100 | 0 |  | 2025-10-21 |  | 2025-11-23
10298 | T-21-7th Floor Flat Area | Not Ready | Putty | 2025-11-25 | 2026-02-17 | Putty | 100 | 0 |  | 2025-10-21 |  | 2026-01-12
11850 | T-18-7th Floor Flat Area | Not Ready | Plastering | 2025-12-31 | 2026-01-23 | Plastering-Cement | 100 | 0 |  | 2025-10-21 |  | 2025-11-14
11878 | T-18-8th Floor Flat Area | Not Ready | Electrical DB Fixing | 2026-01-01 | 2026-01-19 | Electrical DB Fixing | 100 | 0 |  | 2025-10-21 |  | 2025-11-10
11904 | T-18-9th Floor Flat Area | Not Ready | Electrical DB Fixing | 2026-01-01 | 2026-01-19 | Electrical DB Fixing | 100 | 0 |  | 2025-10-21 |  | 2025-11-10
39734 | Tower A - Super Structure - Core Wall High Rise L71-72 | Complete | Core Wall RCC Works | 2025-10-10 | 2025-10-13 | ACS Form Closing & Alignment | 100 | 100 |  | 2025-10-21 | 2025-11-10 | 2025-10-24 | 2025-11-14 | Tower A | Super Structure | L71 | RCC Super Structure | Core Wall RCC Works
41571 |  | Started |  | 2025-06-24 | 2026-05-09 | L39-40 | 100 | 26 |  | 2025-10-21 | 2025-10-21 | 2026-06-01 |  |  |  |  | Finishes | Gypsum Plastering Works
41571 |  | Started |  | 2025-06-24 | 2026-05-09 | L39-40 | 100 | 26 |  | 2025-10-21 | 2025-10-21 | 2026-06-01
41572 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2025-10-21 | 2025-10-24 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 40 |  | 2025-10-21 | 2025-10-21 | 2026-04-18 |  | Tower A | Super Structure | L39 | MEP | FPS 1st Fix - MEP & Finishes
41573 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-10-21 | 2025-10-24 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-10-21 |  | 2025-10-23 |  | Tower A | Super Structure | L39 | MEP | Electrical 1st Fixes
42908 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-10-01 | 2025-10-13 | Cement Plastering in wet areas | 100 | 0 |  | 2025-10-21 |  | 2025-11-01 |  | Tower A | Super Structure | L46
8557 | T-14-1st Floor Flat Area | Not Ready | Window | 2025-09-27 | 2025-10-20 | Window | 100 | 0 |  | 2025-10-22 |  | 2025-11-15
8659 | T-14-5th Floor Flat Area | Not Ready | Flooring & skirting | 2025-09-21 | 2025-11-07 | Flooring & skirting | 100 | 0 |  | 2025-10-22 |  | 2025-12-09
8706 | T-14-7th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-09-15 | 2025-10-01 | Electrical DB Fixing | 100 | 0 |  | 2025-10-22 |  | 2025-11-10
9298 |  | Not Ready |  | 2025-10-27 | 2026-07-29 | Ninth Floor | 100 | 0 |  | 2025-10-22 |  | 2026-07-24
9299 |  | Not Ready |  | 2025-10-27 | 2026-07-29 | Flat Area | 100 | 0 |  | 2025-10-22 |  | 2026-07-24
9324 |  | Not Ready |  | 2025-10-27 | 2026-08-16 | Tenth Floor | 100 | 0 |  | 2025-10-22 |  | 2026-08-10
9325 |  | Not Ready |  | 2025-10-27 | 2026-08-16 | Flat Area | 100 | 0 |  | 2025-10-22 |  | 2026-08-10
9602 | T-16-GF Common Area | Not Ready | Toilets False Celing | 2025-11-14 | 2025-12-01 | Toilets False Celing | 100 | 0 |  | 2025-10-22 |  | 2025-11-07
10371 | T-21-10th Floor Flat Area | Not Ready | Plastering | 2025-11-19 | 2026-01-02 | Plastering-Gypsum | 100 | 0 |  | 2025-10-22 |  | 2025-12-05
10716 | T-20-3rd Floor Flat Area | Not Ready | Door | 2025-12-03 | 2025-12-25 | Door | 100 | 0 |  | 2025-10-22 |  | 2025-11-15
10837 | T-20-8th Floor Flat Area | Not Ready | Waterproofing | 2025-11-23 | 2025-12-26 | Waterproofing | 100 | 0 |  | 2025-10-22 |  | 2025-11-26
10863 | T-20-9th Floor Flat Area | Not Ready | Waterproofing | 2025-11-23 | 2025-12-26 | Waterproofing | 100 | 0 |  | 2025-10-22 |  | 2025-11-26
11645 | T-18-Terrace | Not Ready | PARAPET | 2026-01-02 | 2026-02-23 | PARAPET | 100 | 0 |  | 2025-10-22 |  | 2025-12-12
11777 | T-18-4th Floor Flat Area | Not Ready | Toilet flooring | 2025-12-26 | 2026-01-30 | Toilet flooring | 100 | 0 |  | 2025-10-22 |  | 2025-11-26
40003 | Tower A - Super Structure - Core & Outer Slab L66-67 | Complete | RCC Works - Slab | 2025-10-07 | 2025-10-11 | Outer Slab_TA | 100 | 100 |  | 2025-10-22 | 2025-11-09 | 2025-11-03 | 2025-11-14 | Tower A | Super Structure | L66 | RCC Sub Structure | RCC Works - Slab
40473 | Tower A - Super Structure - Finishes & MEP - GF to P1 | Not Ready | Gypsum Plastering Works | 2024-03-28 | 2024-06-06 | GF to P1_TA & NTA | 100 | 0 |  | 2025-10-22 |  | 2025-12-31 |  | Tower A | Super Structure | GF | Finishes | Gypsum Plastering Works
40679 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2024-03-28 | 2024-04-04 | HVAC Ducting | 100 | 0 |  | 2025-10-22 |  | 2025-10-29 |  | Tower A | Super Structure | GF | MEP | HVAC Ducting
40680 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2024-03-28 | 2024-04-13 | Flooring & Dado | 100 | 0 |  | 2025-10-22 |  | 2025-11-07 |  | Tower A | Super Structure | GF | Finishes | Flooring & Dado
40805 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | FAPA Cabling - MEP & Finishes | 2024-06-18 | 2024-06-28 | FAPA Cabling | 100 | 0 |  | 2025-10-22 |  | 2025-11-03 |  | Tower A | Super Structure
40812 |  | Not Committed |  | 2024-06-18 | 2024-11-08 | P5-6 Level | 100 | 0 |  | 2025-10-22 |  | 2026-02-18
40827 |  | Not Committed |  | 2024-06-18 | 2024-11-08 | Floor Area | 100 | 0 |  | 2025-10-22 |  | 2026-02-18
40828 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | Ceiling Painting/ PT Marking - MEP & Finishes | 2024-06-18 | 2024-06-22 | Ceiling Painting/ PT Marking | 100 | 0 |  | 2025-10-22 |  | 2025-10-28 |  | Tower A | Super Structure |  | Finishes | Ceiling Painting/ PT Marking
40923 | Tower A - Super Structure - Finishes & MEP - L55 to L65 | Not Ready |  | 2025-10-11 | 2025-12-03 | FHC & Accessories fixing | 100 | 0 |  | 2025-10-22 |  | 2025-12-13 |  | Tower A | Super Structure | L55
40925 | Tower A - Super Structure - Finishes & MEP - L55 to L65 | Not Ready |  | 2025-10-11 | 2025-12-03 | Soil & Waste Downtake piping in Plumbing Shaft | 100 | 0 |  | 2025-10-22 |  | 2025-12-13 |  | Tower A | Super Structure | L55
40929 | Tower A - Super Structure - Finishes & MEP - L55 to L65 | Not Ready |  | 2025-10-11 | 2025-12-03 | HVAC Shaft Ducting | 100 | 0 |  | 2025-10-22 |  | 2025-12-13 |  | Tower A | Super Structure | L55 | MEP | HVAC Grill Fixing
42515 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-03-06 | 2025-03-13 | Door & Window Frame work | 100 | 0 |  | 2025-10-22 |  | 2025-10-30 |  | Tower A | Super Structure | L24 | Finishes | Door & Window Frame work
8485 | T-14-12th Floor | Complete | Conduiting | 2025-09-16 | 2025-09-18 | Conduiting works | 100 | 100 |  | 2025-10-23 | 2026-01-02 | 2025-10-25 | 2026-01-04
9039 | T-15-Terrace | Complete | Shuttering | 2025-10-20 | 2025-10-24 | Slab and Beam Shuttering | 3715 | 3715 | Sqm | 2025-10-23 | 2025-11-19 | 2025-10-25 | 2025-11-25
9085 | T-15-GF Common Area | Not Ready | Window | 2025-10-21 | 2025-11-14 | Window | 100 | 0 |  | 2025-10-23 |  | 2025-11-14
9205 | T-15-5th Floor Flat Area | Not Ready | Flooring & skirting | 2025-10-21 | 2025-12-06 | Flooring & skirting | 100 | 0 |  | 2025-10-23 |  | 2025-12-06
9249 | T-15-7th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-10-20 | 2025-11-13 | Plumbing Pipe Line | 100 | 0 |  | 2025-10-23 |  | 2025-11-15
9540 | T-16-9th Floor | Complete | RCC | 2025-11-11 | 2025-11-12 | Slab& Beam RCC | 387 | 387 | CUM | 2025-10-23 | 2025-12-13 | 2025-10-26 | 2025-12-14
10886 | T-20-10th Floor Flat Area | Not Ready | Blockwork | 2025-11-21 | 2025-12-12 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-10-23 |  | 2025-11-17
11107 | T-19-10th Floor | Not Ready | RCC | 2025-11-04 | 2025-11-05 | Slab& Beam RCC | 340 | 0 | CUM | 2025-10-23 |  | 2025-10-23
11865 | T-18-7th Floor Common Area | Not Ready |  | 2026-01-02 | 2026-02-06 | Plastering Gypsum | 100 | 0 |  | 2025-10-23 |  | 2025-11-27
39197 |  | Not Ready |  | 2025-03-31 | 2025-04-18 | Low Side - Earthing Works | 100 | 0 |  | 2025-10-23 |  | 2025-11-12
39198 |  | Not Ready |  | 2025-03-31 | 2025-04-11 | High Side - Installation of Transformers | 100 | 0 |  | 2025-10-23 |  | 2025-11-05
40633 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2024-03-29 | 2024-04-03 | Final Painting | 100 | 0 |  | 2025-10-23 |  | 2025-10-29 |  | Tower A | Sub Structure | B2 | Finishes | Final Painting
40633 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2024-03-29 | 2024-04-03 | Final Painting | 100 | 0 |  | 2025-10-23 |  | 2025-10-29 |  | Tower A | Sub Structure | B2 | Finishes | Final Painting
40633 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2024-03-29 | 2024-04-03 | Final Painting | 100 | 0 |  | 2025-10-23 |  | 2025-10-29 |  | Tower A | Sub Structure | B2 | Finishes | Final Painting
40659 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2024-04-18 | 2024-04-23 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2025-10-23 |  | 2025-10-29 |  | Tower A | Sub Structure | B1 | MEP | Electrical
41113 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-03-15 | 2025-03-20 | Lobby Plastering | 100 | 0 |  | 2025-10-23 |  | 2025-10-28 |  | Tower A | Super Structure | L10 | Finishes | Lobby Plastering
41128 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-03-15 | 2025-03-18 | Lobby Blockwork | 100 | 0 |  | 2025-10-23 |  | 2025-10-25 |  | Tower A | Super Structure | L11 | Finishes | Blockwork
44245 | Tower A | Not Ready | High Side Procurement | 2025-10-01 | 2026-02-04 | HT Panels & Sub-Panels | 100 | 0 |  | 2025-10-23 |  | 2026-02-25 |  | Tower A | --
44246 | Tower A | Not Ready | High Side Procurement | 2025-10-01 | 2026-02-04 | LT Panels & Sub-Panels | 100 | 0 |  | 2025-10-23 |  | 2026-02-25 |  | Tower A | --
44247 | Tower A | Not Ready | High Side Procurement | 2025-10-01 | 2026-02-04 | Fire Alarm Panels | 100 | 0 |  | 2025-10-23 |  | 2026-02-25 |  | Tower A | --
8484 | T-14-12th Floor | Complete | Shear Walls/Corewalls Shuttering | 2025-09-17 | 2025-09-20 | Shear Walls/Corewalls Shuttering | 100 | 100 |  | 2025-10-24 | 2025-12-27 | 2025-10-26 | 2026-01-03
8653 | T-14-5th Floor Flat Area | Not Ready | Waterproofing | 2025-09-21 | 2025-11-12 | Waterproofing | 100 | 0 |  | 2025-10-24 |  | 2025-12-17
9692 | T-16-4th Floor Flat Area | Not Ready | Plastering | 2025-11-13 | 2025-12-05 | Plastering-Cement | 100 | 0 |  | 2025-10-24 |  | 2025-11-14
10382 |  | Not Ready |  | 2025-11-27 | 2026-07-12 | Common Area | 100 | 0 |  | 2025-10-24 |  | 2026-06-10
10790 | T-20-6th Floor Flat Area | Not Ready | Toilets False Celing | 2025-11-27 | 2025-12-30 | Toilets False Celing | 100 | 0 |  | 2025-10-24 |  | 2025-11-27
10814 | T-20-7th Floor Flat Area | Not Ready | Dado | 2025-11-25 | 2025-12-23 | Dado | 100 | 0 |  | 2025-10-24 |  | 2025-11-22
11208 | T-19-2nd Floor Flat Area | Not Ready | Putty | 2025-11-18 | 2026-02-10 | Putty | 100 | 0 |  | 2025-10-24 |  | 2026-01-16
11278 | T-19-5th Floor Flat Area | Not Ready | Plastering | 2025-11-06 | 2025-11-28 | Plastering-Cement | 100 | 0 |  | 2025-10-24 |  | 2025-11-15
11302 | T-19-6th Floor Flat Area | Not Ready | Blockwork | 2025-11-05 | 2025-11-27 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-10-24 |  | 2025-11-14
11341 | T-19-7th Floor Flat Area | Not Ready | Railing | 2025-11-05 | 2025-12-08 | Balcony Railing | 100 | 0 |  | 2025-10-24 |  | 2025-11-27
11643 | T-18-Terrace | Not Ready | LMR ROOM | 2026-01-05 | 2026-02-25 | LMR ROOM | 100 | 0 |  | 2025-10-24 |  | 2025-12-15
11646 | T-18-Terrace | Not Ready | STAIRCASE HR | 2026-01-05 | 2026-02-25 | STAIRCASE HR | 100 | 0 |  | 2025-10-24 |  | 2025-12-16
40521 | Tower A - Super Structure - Finishes & MEP - L47 to L48 | Not Ready | Gypsum Plastering Works | 2025-09-30 | 2025-10-24 | L47-48 | 100 | 0 |  | 2025-10-24 |  | 2025-11-15 |  | Tower A | Super Structure | L47 | Finishes | Gypsum Plastering Works
40521 | Tower A - Super Structure - Finishes & MEP - L47 to L48 | Not Ready | Gypsum Plastering Works | 2025-09-30 | 2025-10-24 | L47-48 | 100 | 0 |  | 2025-10-24 |  | 2025-11-15 |  | Tower A | Super Structure | L47
41574 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2025-10-24 | 2025-10-27 | FAPA Cabling | 100 | 0 |  | 2025-10-24 |  | 2025-10-25 |  | Tower A | Super Structure | L39
42300 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-10-03 | 2025-10-21 | Flooring & Dado works | 100 | 0 |  | 2025-10-24 |  | 2025-11-11 |  | Tower A | Super Structure | L12 | Finishes | Flooring & Dado
42336 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-10-03 | 2025-10-21 | Flooring & Dado works | 100 | 0 |  | 2025-10-24 |  | 2025-11-11 |  | Tower A | Super Structure | L14 | Finishes | Flooring & Dado
42533 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-03-11 | 2025-03-19 | Door & Window Frame work | 100 | 0 |  | 2025-10-24 |  | 2025-11-01 |  | Tower A | Super Structure | L25 | Finishes | Door & Window Frame work
42587 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-04-05 | 2025-04-12 | Door & Window Frame work | 100 | 0 |  | 2025-10-24 |  | 2025-11-01 |  | Tower A | Super Structure | L28 | Finishes | Door & Window Frame work
42620 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-03-27 | 2025-04-07 | Cement Plastering in wet areas | 100 | 0 |  | 2025-10-24 |  | 2025-11-04 |  | Tower A | Super Structure | L30
42938 |  | Not Committed |  | 2025-09-30 | 2026-08-31 | L48-49 | 100 | 0 |  | 2025-10-24 |  | 2026-08-12
42938 |  | Not Committed |  | 2025-09-30 | 2026-08-31 | L48-49 | 100 | 0 |  | 2025-10-24 |  | 2026-08-12 |  |  |  |  | Finishes | Gypsum Plastering Works
42939 |  | Not Committed |  | 2025-09-30 | 2025-10-30 | MEP 1st Fixes | 100 | 0 |  | 2025-10-24 |  | 2025-11-21
42940 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2025-09-30 | 2025-10-08 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-10-24 |  | 2025-10-31 |  | Tower A | Super Structure | L48 | MEP | FPS 1st Fix - MEP & Finishes
42941 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-09-30 | 2025-10-06 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2025-10-24 |  | 2025-10-29 |  | Tower A | Super Structure | L48 | MEP | Electrical 1st Fixes
42942 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2025-09-30 | 2025-10-08 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2025-10-24 |  | 2025-10-31 |  | Tower A | Super Structure | L48
42943 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2025-09-30 | 2025-10-17 | Wet Area Waterproofing | 100 | 0 |  | 2025-10-24 |  | 2025-11-10 |  | Tower A | Super Structure | L48
8634 | T-14-4th Floor Flat Area | Not Ready | Putty | 2025-09-29 | 2025-12-23 | Putty | 100 | 0 |  | 2025-10-25 |  | 2026-01-18
9040 | T-15-Terrace | Complete | Slab& Beam Steel & Conduting | 2025-10-22 | 2025-10-25 | Slab& Beam Steel & Conduting | 13 | 13 | MT | 2025-10-25 | 2025-11-26 | 2025-10-26 | 2025-11-30
9042 |  | Not Ready |  | 2025-10-30 | 2025-12-26 | Above Terrace | 100 | 0 |  | 2025-10-25 |  | 2025-12-22
9103 | T-15-1st Floor Flat Area | Not Ready | Window | 2025-10-29 | 2025-11-21 | Window | 100 | 0 |  | 2025-10-25 |  | 2025-11-18
9253 | T-15-7th Floor Flat Area | Not Ready | Plastering | 2025-10-22 | 2025-12-07 | Plastering-Gypsum | 100 | 0 |  | 2025-10-25 |  | 2025-12-08
9264 |  | Not Ready |  | 2025-10-30 | 2026-05-30 | Common Area | 100 | 0 |  | 2025-10-25 |  | 2026-05-26
10890 | T-20-10th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-11-23 | 2025-12-09 | Electrical DB Fixing | 100 | 0 |  | 2025-10-25 |  | 2025-11-11
11109 | T-19-11th Floor | Not Ready | AL - Shear Walls/Corewalls Steel | 2025-11-06 | 2025-11-11 | AL - Shear Walls/Corewalls Steel | 28.4 | 0 | MT | 2025-10-25 |  | 2025-10-31
11668 | T-18-GF Flat Area | Not Ready | Window | 2025-12-17 | 2026-01-08 | Window | 100 | 0 |  | 2025-10-25 |  | 2025-11-17
11780 | T-18-4th Floor Flat Area | Not Ready | Putty | 2026-01-01 | 2026-03-27 | Putty | 100 | 0 |  | 2025-10-25 |  | 2026-01-17
11825 | T-18-6th Floor Flat Area | Not Ready | Waterproofing | 2026-01-02 | 2026-02-06 | Waterproofing | 100 | 0 |  | 2025-10-25 |  | 2025-11-25
11898 |  | Not Ready |  | 2025-12-30 | 2026-10-01 | Ninth Floor | 100 | 0 |  | 2025-10-25 |  | 2026-08-01
11899 |  | Not Ready |  | 2025-12-30 | 2026-10-01 | Flat Area | 100 | 0 |  | 2025-10-25 |  | 2026-08-01
11924 |  | Not Ready |  | 2025-12-30 | 2026-10-19 | Tenth Floor | 100 | 0 |  | 2025-10-25 |  | 2026-08-19
11925 |  | Not Ready |  | 2025-12-30 | 2026-10-19 | Flat Area | 100 | 0 |  | 2025-10-25 |  | 2026-08-19
40051 | Tower A - Super Structure - Finishes & MEP - L45 to L46 | Not Ready | CTU Elevators Crash Deck - High Side Services | 2025-03-18 | 2025-04-18 | Bulk head light fix + Electrical works + Earthing | 100 | 0 |  | 2025-10-25 |  | 2025-11-26 |  | Tower A | Super Structure | L45
40051 | Tower A - Super Structure - Finishes & MEP - L45 to L46 | Not Ready | CTU Elevators Crash Deck - High Side Services | 2025-03-18 | 2025-04-18 | Bulk head light fix + Electrical works + Earthing | 100 | 0 |  | 2025-10-25 |  | 2025-11-26 |  | Tower A | Super Structure | L45
40051 | Tower A - Super Structure - Finishes & MEP - L45 to L46 | Not Ready | CTU Elevators Crash Deck - High Side Services | 2025-03-18 | 2025-04-18 | Bulk head light fix + Electrical works + Earthing | 100 | 0 |  | 2025-10-25 |  | 2025-11-26 |  | Tower A | Super Structure | L45
40618 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2024-04-16 | 2024-04-20 | Final Painting | 100 | 0 |  | 2025-10-25 |  | 2025-10-31 |  | Tower A | Sub Structure | B3 | Finishes | Final Painting
40618 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2024-04-16 | 2024-04-20 | Final Painting | 100 | 0 |  | 2025-10-25 |  | 2025-10-31 |  | Tower A | Sub Structure | B3 | Finishes | Final Painting
40618 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2024-04-16 | 2024-04-20 | Final Painting | 100 | 0 |  | 2025-10-25 |  | 2025-10-31 |  | Tower A | Sub Structure | B3 | Finishes | Final Painting
40645 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2024-04-06 | 2024-04-23 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2025-10-25 |  | 2025-11-11 |  | Tower A | Sub Structure | B2
40645 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2024-04-06 | 2024-04-23 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2025-10-25 |  | 2025-11-11 |  | Tower A | Sub Structure | B2
40645 | Tower A - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2024-04-06 | 2024-04-23 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2025-10-25 |  | 2025-11-11 |  | Tower A | Sub Structure | B2
40671 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2024-04-30 | 2024-05-23 | Final Painting | 100 | 0 |  | 2025-10-25 |  | 2025-11-17 |  | Tower A | Sub Structure | B1 | Finishes | Final Painting
40671 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2024-04-30 | 2024-05-23 | Final Painting | 100 | 0 |  | 2025-10-25 |  | 2025-11-17 |  | Tower A | Sub Structure | B1 | Finishes | Final Painting
40671 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2024-04-30 | 2024-05-23 | Final Painting | 100 | 0 |  | 2025-10-25 |  | 2025-11-17 |  | Tower A | Sub Structure | B1 | Finishes | Final Painting
40696 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | False Ceiling - MEP & Finishes | 2024-05-30 | 2024-06-28 | False Ceiling (Modular) | 100 | 0 |  | 2025-10-25 |  | 2025-11-22 |  | Tower A | Super Structure | GF | Finishes | False Ceiling
40730 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2024-06-05 | 2024-06-22 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2025-10-25 |  | 2025-11-11 |  | Tower A | Super Structure
40730 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2024-06-05 | 2024-06-22 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2025-10-25 |  | 2025-11-11 |  | Tower A | Super Structure
40730 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2024-06-05 | 2024-06-22 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2025-10-25 |  | 2025-11-11 |  | Tower A | Super Structure
40757 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2024-06-18 | 2024-07-04 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2025-10-25 |  | 2025-11-11 |  | Tower A | Super Structure
40757 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2024-06-18 | 2024-07-04 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2025-10-25 |  | 2025-11-11 |  | Tower A | Super Structure
40757 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2024-06-18 | 2024-07-04 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2025-10-25 |  | 2025-11-11 |  | Tower A | Super Structure
40865 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2024-09-07 | 2024-09-07 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2025-10-25 |  | 2025-10-25 |  | Tower A | Super Structure
40865 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2024-09-07 | 2024-09-07 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2025-10-25 |  | 2025-10-25 |  | Tower A | Super Structure
40865 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2024-09-07 | 2024-09-07 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2025-10-25 |  | 2025-10-25 |  | Tower A | Super Structure
42408 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-10-28 | 2025-11-13 | Flooring & Dado works | 100 | 0 |  | 2025-10-25 |  | 2025-11-12 |  | Tower A | Super Structure | L18 | Finishes | Flooring & Dado
45399 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 | Not Ready | Partition Wall-Blockwork | 2025-03-11 | 2025-03-28 | Partition Walls | 100 | 0 |  | 2025-10-25 |  | 2025-11-11 |  | Tower B | Sub Structure | B2
45404 | Tower B - Sub Structure - Finishes & MEP - B1 to GF | Not Ready | Partition Wall-Blockwork | 2025-03-11 | 2025-03-22 | Staircase Area | 100 | 0 |  | 2025-10-25 |  | 2025-11-05 |  | Tower B | Sub Structure | B1
47632 |  | Not Ready |  | 2024-11-28 | 2024-12-14 | Slab_NTA | 100 | 0 |  | 2025-10-25 |  | 2025-11-11
47632 |  | Not Ready |  | 2024-11-28 | 2024-12-14 | Slab_NTA | 100 | 0 |  | 2025-10-25 |  | 2025-11-11 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
9645 | T-16-2nd Floor Flat Area | Not Ready | Toilet flooring | 2025-11-22 | 2025-12-25 | Toilet flooring | 100 | 0 |  | 2025-10-26 |  | 2025-11-27
9667 | T-16-3rd Floor Flat Area | Not Ready | Waterproofing | 2025-11-21 | 2026-01-09 | Waterproofing | 100 | 0 |  | 2025-10-26 |  | 2025-12-16
9707 | T-16-4th Floor Common Area | Not Ready | Plastering | 2025-11-15 | 2025-12-18 | Plastering-Gypsum | 100 | 0 |  | 2025-10-26 |  | 2025-11-28
9818 |  | Not Ready |  | 2025-12-25 | 2026-09-26 | Ninth Floor | 100 | 0 |  | 2025-10-26 |  | 2026-07-29
9819 |  | Not Ready |  | 2025-12-25 | 2026-09-26 | Flat Area | 100 | 0 |  | 2025-10-26 |  | 2026-07-29
9844 |  | Not Ready |  | 2025-12-25 | 2026-10-13 | Tenth Floor | 100 | 0 |  | 2025-10-26 |  | 2026-08-14
9845 |  | Not Ready |  | 2025-12-25 | 2026-10-13 | Flat Area | 100 | 0 |  | 2025-10-26 |  | 2026-08-14
10169 | T-21-2nd Floor Flat Area | Not Ready | Window | 2025-10-27 | 2025-11-19 | Window | 100 | 0 |  | 2025-10-26 |  | 2025-11-18
10296 | T-21-7th Floor Flat Area | Not Ready | Toilets False Celing | 2025-12-01 | 2026-01-02 | Toilets False Celing | 100 | 0 |  | 2025-10-26 |  | 2025-11-30
11293 | T-19-5th Floor Common Area | Not Ready | Plastering | 2025-11-08 | 2025-12-11 | Plastering-Gypsum | 100 | 0 |  | 2025-10-26 |  | 2025-11-29
11306 | T-19-6th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-11-07 | 2025-11-24 | Electrical DB Fixing | 100 | 0 |  | 2025-10-26 |  | 2025-11-14
11648 |  | Not Ready |  | 2026-01-07 | 2026-01-24 | Lowering Aluminium FW Material For PH-2 | 100 | 0 |  | 2025-10-26 |  | 2025-11-11
11802 | T-18-5th Floor Flat Area | Not Ready | Dado | 2026-01-01 | 2026-01-31 | Dado | 100 | 0 |  | 2025-10-26 |  | 2025-11-22
11875 | T-18-8th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2026-01-07 | 2026-01-31 | Plumbing Pipe Line | 100 | 0 |  | 2025-10-26 |  | 2025-11-17
11901 | T-18-9th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2026-01-07 | 2026-01-31 | Plumbing Pipe Line | 100 | 0 |  | 2025-10-26 |  | 2025-11-17
8486 | T-14-12th Floor | Complete | Shuttering | 2025-09-20 | 2025-09-23 | Slab and Beam Shuttering | 3605 | 3605 | Sqm | 2025-10-27 | 2026-01-03 | 2025-10-31 | 2026-01-09
8703 | T-14-7th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-09-20 | 2025-10-13 | Plumbing Pipe Line | 100 | 0 |  | 2025-10-27 |  | 2025-11-20
9041 | T-15-Terrace | Complete | RCC | 2025-10-25 | 2025-10-27 | Slab& Beam RCC | 318 | 318 | CUM | 2025-10-27 | 2025-12-01 | 2025-10-27 | 2025-12-02
9177 | T-15-4th Floor Flat Area | Not Ready | Toilet flooring | 2025-10-22 | 2025-11-26 | Toilet flooring | 100 | 0 |  | 2025-10-27 |  | 2025-12-01
9199 | T-15-5th Floor Flat Area | Not Ready | Waterproofing | 2025-10-21 | 2025-12-11 | Waterproofing | 100 | 0 |  | 2025-10-27 |  | 2025-12-16
9673 | T-16-3rd Floor Flat Area | Not Ready | Flooring & skirting | 2025-11-21 | 2026-01-03 | Flooring & skirting | 100 | 0 |  | 2025-10-27 |  | 2025-12-12
9716 | T-16-5th Floor Flat Area | Not Ready | Blockwork | 2025-11-12 | 2025-12-04 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-10-27 |  | 2025-11-17
9755 | T-16-6th Floor Flat Area | Not Ready | Railing | 2025-11-12 | 2025-12-15 | Balcony Railing | 100 | 0 |  | 2025-10-27 |  | 2025-11-30
10093 | T-21-Basement Floor | Not Ready | 1st Coat Painting | 2025-09-05 | 2025-10-09 | 1st Coat Painting | 100 | 0 |  | 2025-10-27 |  | 2025-11-27
10368 | T-21-10th Floor Flat Area | Not Ready | Plastering | 2025-11-25 | 2025-12-17 | Plastering-Cement | 100 | 0 |  | 2025-10-27 |  | 2025-11-19
10843 | T-20-8th Floor Flat Area | Not Ready | Flooring & skirting | 2025-11-28 | 2026-01-11 | Flooring & skirting | 100 | 0 |  | 2025-10-27 |  | 2025-12-12
10869 | T-20-9th Floor Flat Area | Not Ready | Flooring & skirting | 2025-11-28 | 2026-01-11 | Flooring & skirting | 100 | 0 |  | 2025-10-27 |  | 2025-12-12
10925 | T-20-11th Floor Flat Area | Not Ready | Railing | 2025-11-24 | 2025-12-27 | Balcony Railing | 100 | 0 |  | 2025-10-27 |  | 2025-11-28
11111 | T-19-11th Floor | Not Ready | Conduiting | 2025-11-08 | 2025-11-12 | Conduiting works | 100 | 0 |  | 2025-10-27 |  | 2025-10-31
11231 | T-19-3rd Floor Flat Area | Not Ready | Toilet flooring | 2025-11-15 | 2025-12-18 | Toilet flooring | 100 | 0 |  | 2025-10-27 |  | 2025-11-30
11647 | T-18-Terrace | Not Ready |  | 2026-01-08 | 2026-02-28 | MISC | 100 | 0 |  | 2025-10-27 |  | 2025-12-15
40356 | Tower A - Super Structure - Finishes & MEP - L49 to L50 | Not Ready | Partition Wall-Blockwork | 2025-10-03 | 2025-10-08 | Staircase Area | 100 | 0 |  | 2025-10-27 |  | 2025-10-31 |  | Tower A | Super Structure | L49
40359 | Tower A - Super Structure - Finishes & MEP - L50 to L51 | Not Ready | Partition Wall-Blockwork | 2025-10-03 | 2025-10-10 | Partition Walls | 100 | 0 |  | 2025-10-27 |  | 2025-11-03 |  | Tower A | Super Structure | L50
41129 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-03-19 | 2025-03-24 | Lobby Plastering | 100 | 0 |  | 2025-10-27 |  | 2025-10-31 |  | Tower A | Super Structure | L11 | Finishes | Lobby Plastering
41144 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-03-19 | 2025-03-21 | Lobby Blockwork | 100 | 0 |  | 2025-10-27 |  | 2025-10-29 |  | Tower A | Super Structure | L12 | Finishes | Blockwork
41587 |  | Started |  | 2025-10-27 | 2026-05-13 | L40-41 | 100 | 26 |  | 2025-10-27 | 2025-10-27 | 2026-06-04 |  |  |  |  | Finishes | Gypsum Plastering Works
41587 |  | Started |  | 2025-10-27 | 2026-05-13 | L40-41 | 100 | 26 |  | 2025-10-27 | 2025-10-27 | 2026-06-04
41588 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2025-10-27 | 2025-10-30 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 40 |  | 2025-10-27 | 2025-10-27 | 2026-04-22 |  | Tower A | Super Structure | L40 | MEP | FPS 1st Fix - MEP & Finishes
41589 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-10-27 | 2025-10-30 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-10-27 |  | 2025-10-29 |  | Tower A | Super Structure | L40 | MEP | Electrical 1st Fixes
42891 |  | Not Committed |  | 2025-10-06 | 2026-02-28 | Finishes after 1st Fix | 100 | 0 |  | 2025-10-27 |  | 2026-01-30
42892 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-10-06 | 2025-10-29 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-10-27 |  | 2025-11-19 |  | Tower A | Super Structure | L45 | Finishes | Blockwork
8558 | T-14-1st Floor Flat Area | Not Ready | Door | 2025-10-05 | 2025-10-27 | Door | 100 | 0 |  | 2025-10-28 |  | 2025-11-19
9180 | T-15-4th Floor Flat Area | Not Ready | Putty | 2025-10-29 | 2026-01-22 | Putty | 100 | 0 |  | 2025-10-28 |  | 2026-01-20
9274 | T-15-8th Floor Flat Area | Not Ready | Blockwork | 2025-10-27 | 2025-11-19 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-10-28 |  | 2025-11-20
9300 | T-15-9th Floor Flat Area | Not Ready | Blockwork | 2025-10-27 | 2025-11-19 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-10-28 |  | 2025-11-20
9313 | T-15-9th Floor Flat Area | Not Ready | Railing | 2025-10-27 | 2025-12-01 | Balcony Railing | 100 | 0 |  | 2025-10-28 |  | 2025-11-29
9339 | T-15-10th Floor Flat Area | Not Ready | Railing | 2025-10-27 | 2025-12-01 | Balcony Railing | 100 | 0 |  | 2025-10-28 |  | 2025-11-29
9542 | T-16-10th Floor | Not Ready | AL - Shear Walls/Corewalls Steel | 2025-11-13 | 2025-11-18 | AL - Shear Walls/Corewalls Steel | 25 | 0 | MT | 2025-10-28 |  | 2025-11-02
10320 | T-21-8th Floor Flat Area | Not Ready | Dado | 2025-11-28 | 2025-12-25 | Dado | 100 | 0 |  | 2025-10-28 |  | 2025-11-24
10346 | T-21-9th Floor Flat Area | Not Ready | Dado | 2025-11-28 | 2025-12-25 | Dado | 100 | 0 |  | 2025-10-28 |  | 2025-11-24
10741 | T-20-4th Floor Flat Area | Not Ready | Window | 2025-12-10 | 2025-12-31 | Window | 100 | 0 |  | 2025-10-28 |  | 2025-11-18
11110 | T-19-11th Floor | Not Ready | Shear Walls/Corewalls Shuttering | 2025-11-10 | 2025-11-14 | Shear Walls/Corewalls Shuttering | 100 | 0 |  | 2025-10-28 |  | 2025-10-30
11133 | T-19-Basement Floor | Not Ready | 1st Coat Painting | 2025-10-28 | 2025-12-01 | 1st Coat Painting | 100 | 0 |  | 2025-10-28 |  | 2025-12-01
11259 | T-19-4th Floor Flat Area | Not Ready | Flooring & skirting | 2025-11-14 | 2025-12-27 | Flooring & skirting | 100 | 0 |  | 2025-10-28 |  | 2025-12-15
11642 |  | Not Ready |  | 2026-01-02 | 2026-03-01 | Above Terrace | 100 | 0 |  | 2025-10-28 |  | 2025-12-25
11644 | T-18-Terrace | Not Ready | OHT | 2026-01-09 | 2026-03-01 | OHT | 100 | 0 |  | 2025-10-28 |  | 2025-12-16
11653 | T-18-Basement Floor | Not Ready | 1st Coat Painting | 2025-11-27 | 2025-12-30 | 1st Coat Painting | 100 | 0 |  | 2025-10-28 |  | 2025-11-30
11879 | T-18-8th Floor Flat Area | Not Ready | Plastering | 2026-01-09 | 2026-02-24 | Plastering-Gypsum | 100 | 0 |  | 2025-10-28 |  | 2025-12-10
11905 | T-18-9th Floor Flat Area | Not Ready | Plastering | 2026-01-09 | 2026-02-24 | Plastering-Gypsum | 100 | 0 |  | 2025-10-28 |  | 2025-12-10
39237 |  | Not Ready |  | 2025-08-11 | 2025-09-19 | High Side Installation - Installation of Chilled Water Pumps and Chillers (GF) | 100 | 0 |  | 2025-10-28 |  | 2025-12-08
40829 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2024-06-24 | 2024-07-18 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-10-28 |  | 2025-11-20 |  | Tower A | Super Structure |  | MEP | FPS 1st Fix - MEP & Finishes
40830 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2024-06-24 | 2024-07-18 | PHE 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-10-28 |  | 2025-11-20 |  | Tower A | Super Structure
40831 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2024-06-24 | 2024-07-11 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-10-28 |  | 2025-11-14 |  | Tower A | Super Structure |  | MEP | Electrical 1st Fixes
42497 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-03-04 | 2025-03-11 | Door & Window Frame work | 100 | 0 |  | 2025-10-28 |  | 2025-11-05 |  | Tower A | Super Structure | L23 | Finishes | Door & Window Frame work
42551 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-03-29 | 2025-04-05 | Door & Window Frame work | 100 | 0 |  | 2025-10-28 |  | 2025-11-05 |  | Tower A | Super Structure | L26 | Finishes | Door & Window Frame work
42603 |  | Not Committed |  | 2025-03-31 | 2026-01-06 | Finishes after 1st Fix | 100 | 0 |  | 2025-10-28 |  | 2025-12-15
42604 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-03-31 | 2025-04-22 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-10-28 |  | 2025-11-19 |  | Tower A | Super Structure | L29 | Finishes | Blockwork
42835 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2025-09-24 | 2025-10-11 | Wet Area Waterproofing | 100 | 0 |  | 2025-10-28 |  | 2025-11-13 |  | Tower A | Super Structure | L42
42839 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-09-24 | 2025-10-01 | Door & Window Frame work | 100 | 0 |  | 2025-10-28 |  | 2025-11-04 |  | Tower A | Super Structure | L42 | Finishes | Door & Window Frame work
42857 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-10-03 | 2025-10-10 | Door & Window Frame work | 100 | 0 |  | 2025-10-28 |  | 2025-11-04 |  | Tower A | Super Structure | L43 | Finishes | Door & Window Frame work
45267 |  | Not Ready |  | 2025-08-12 | 2025-09-29 | P6-L7 | 100 | 0 |  | 2025-10-28 |  | 2025-12-05
45268 | Tower B - Super Structure - Core & Outer Slab P6-L7 | Not Ready | Modular Formwork Setup | 2025-08-12 | 2025-09-08 | 1st Typical Modular Formwork Set-up | 100 | 0 |  | 2025-10-28 |  | 2025-11-20 |  | Tower B | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
45268 | Tower B - Super Structure - Core & Outer Slab P6-L7 | Not Ready | Modular Formwork Setup | 2025-08-12 | 2025-09-08 | 1st Typical Modular Formwork Set-up | 100 | 0 |  | 2025-10-28 |  | 2025-11-20 |  | Tower B | Super Structure
45425 |  | Not Committed |  | 2025-08-12 | 2025-09-25 | P5 to P6 | 100 | 0 |  | 2025-10-28 |  | 2025-12-02
45426 | Tower B - Super Structure - Finishes & MEP - P5 to P6 | Not Ready | Partition Wall-Blockwork | 2025-08-12 | 2025-08-19 | De-shuttering & Area clearance | 100 | 0 |  | 2025-10-28 |  | 2025-11-03 |  | Tower B | Super Structure
8487 | T-14-12th Floor | Complete | Slab& Beam Steel & Conduting | 2025-09-22 | 2025-09-25 | Slab& Beam Steel & Conduting | 10 | 10 | MT | 2025-10-29 | 2026-01-08 | 2025-11-01 | 2026-01-12
8632 | T-14-4th Floor Flat Area | Not Ready | Toilets False Celing | 2025-10-01 | 2025-11-06 | Toilets False Celing | 100 | 0 |  | 2025-10-29 |  | 2025-12-03
8707 | T-14-7th Floor Flat Area | Not Ready | Plastering | 2025-09-22 | 2025-11-08 | Plastering-Gypsum | 100 | 0 |  | 2025-10-29 |  | 2025-12-13
9562 |  | Not Ready |  | 2025-12-28 | 2026-02-24 | Above Terrace | 100 | 0 |  | 2025-10-29 |  | 2025-12-26
9720 | T-16-5th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-11-14 | 2025-12-01 | Electrical DB Fixing | 100 | 0 |  | 2025-10-29 |  | 2025-11-16
9784 |  | Not Ready |  | 2025-12-28 | 2026-07-27 | Common Area | 100 | 0 |  | 2025-10-29 |  | 2026-05-30
10128 | T-21-GF Common Area | Not Ready | 1st Coat Painting | 2025-10-25 | 2025-12-16 | 1st Coat Painting | 100 | 0 |  | 2025-10-29 |  | 2025-12-22
10383 | T-21-11th Floor Common Area | Not Ready | Plastering | 2025-11-27 | 2025-12-30 | Plastering-Gypsum | 100 | 0 |  | 2025-10-29 |  | 2025-12-02
11186 | T-19-1st Floor Flat Area | Not Ready | 1st Coat Painting | 2025-11-26 | 2026-02-18 | 1st Coat Painting | 100 | 0 |  | 2025-10-29 |  | 2026-01-20
40660 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2024-04-24 | 2024-04-29 | Final Painting | 100 | 0 |  | 2025-10-29 |  | 2025-11-04 |  | Tower A | Sub Structure | B1 | Finishes | Final Painting
40660 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2024-04-24 | 2024-04-29 | Final Painting | 100 | 0 |  | 2025-10-29 |  | 2025-11-04 |  | Tower A | Sub Structure | B1 | Finishes | Final Painting
40660 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2024-04-24 | 2024-04-29 | Final Painting | 100 | 0 |  | 2025-10-29 |  | 2025-11-04 |  | Tower A | Sub Structure | B1 | Finishes | Final Painting
42479 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-03-01 | 2025-03-08 | Door & Window Frame work | 100 | 0 |  | 2025-10-29 |  | 2025-11-05 |  | Tower A | Super Structure | L22 | Finishes | Door & Window Frame work
8770 |  | Not Ready |  | 2025-10-29 | 2026-06-14 | Common Area | 100 | 0 |  | 2025-10-30 |  | 2026-06-15
9225 | T-15-6th Floor Flat Area | Not Ready | Waterproofing | 2025-10-30 | 2025-12-04 | Waterproofing | 100 | 0 |  | 2025-10-30 |  | 2025-12-03
9250 | T-15-7th Floor Flat Area | Not Ready | Plastering | 2025-10-28 | 2025-11-20 | Plastering-Cement | 100 | 0 |  | 2025-10-30 |  | 2025-11-21
9278 | T-15-8th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-10-29 | 2025-11-16 | Electrical DB Fixing | 100 | 0 |  | 2025-10-30 |  | 2025-11-15
9304 | T-15-9th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-10-29 | 2025-11-16 | Electrical DB Fixing | 100 | 0 |  | 2025-10-30 |  | 2025-11-15
9544 | T-16-10th Floor | Not Ready | Conduiting | 2025-11-15 | 2025-11-19 | Conduiting works | 100 | 0 |  | 2025-10-30 |  | 2025-11-04
10887 | T-20-10th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-11-28 | 2025-12-20 | Plumbing Pipe Line | 100 | 0 |  | 2025-10-30 |  | 2025-11-21
11253 | T-19-4th Floor Flat Area | Not Ready | Waterproofing | 2025-11-14 | 2026-01-02 | Waterproofing | 100 | 0 |  | 2025-10-30 |  | 2025-12-23
11370 |  | Not Ready |  | 2025-12-21 | 2026-07-27 | Common Area | 100 | 0 |  | 2025-10-30 |  | 2026-06-08
11396 |  | Not Ready |  | 2025-12-21 | 2026-08-19 | Common Area | 100 | 0 |  | 2025-10-30 |  | 2026-06-30
11669 | T-18-GF Flat Area | Not Ready | Door | 2025-12-23 | 2026-01-13 | Door | 100 | 0 |  | 2025-10-30 |  | 2025-11-21
11778 | T-18-4th Floor Flat Area | Not Ready | Toilets False Celing | 2026-01-03 | 2026-02-07 | Toilets False Celing | 100 | 0 |  | 2025-10-30 |  | 2025-12-01
11831 | T-18-6th Floor Flat Area | Not Ready | Flooring & skirting | 2026-01-08 | 2026-02-23 | Flooring & skirting | 100 | 0 |  | 2025-10-30 |  | 2025-12-12
11864 |  | Not Ready |  | 2026-01-02 | 2026-08-01 | Common Area | 100 | 0 |  | 2025-10-30 |  | 2026-06-02
40478 | Tower A - Super Structure - Finishes & MEP - P5 to P6 | Not Ready | Gypsum Plastering Works | 2024-06-26 | 2024-08-23 | P5 to P6_TA & NTA | 100 | 0 |  | 2025-10-30 |  | 2025-12-22 |  | Tower A | Super Structure |  | Finishes | Gypsum Plastering Works
41145 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-03-22 | 2025-03-27 | Lobby Plastering | 100 | 0 |  | 2025-10-30 |  | 2025-11-04 |  | Tower A | Super Structure | L12 | Finishes | Lobby Plastering
41160 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-03-22 | 2025-03-25 | Lobby Blockwork | 100 | 0 |  | 2025-10-30 |  | 2025-11-01 |  | Tower A | Super Structure | L13 | Finishes | Blockwork
41590 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2025-10-30 | 2025-11-01 | FAPA Cabling | 100 | 0 |  | 2025-10-30 |  | 2025-10-31 |  | Tower A | Super Structure | L40
42361 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-10-09 | 2025-10-27 | Flooring & Dado works | 100 | 0 |  | 2025-10-30 |  | 2025-11-17 |  | Tower A | Super Structure | L15 | Finishes | Flooring & Dado
44530 | NTA_Zone 2 - Super Structure - GF to P1 | Not Ready | MEP 1st Fix Works | 2024-11-01 | 2025-01-10 | GF to P1 | 100 | 0 |  | 2025-10-30 |  | 2025-11-15 |  | NTA_Zone 2 | Super Structure | GF
44530 | NTA_Zone 2 - Super Structure - GF to P1 | Not Ready | MEP 1st Fix Works | 2024-11-01 | 2025-01-10 | GF to P1 | 100 | 0 |  | 2025-10-30 |  | 2025-11-15 |  | NTA_Zone 2 | Super Structure | GF
44530 | NTA_Zone 2 - Super Structure - GF to P1 | Not Ready | MEP 1st Fix Works | 2024-11-01 | 2025-01-10 | GF to P1 | 100 | 0 |  | 2025-10-30 |  | 2025-11-15 |  | NTA_Zone 2 | Super Structure | GF
44555 |  | Not Committed |  | 2024-11-01 | 2025-03-04 | B1 to GF | 100 | 0 |  | 2025-10-30 |  | 2026-03-04
44555 |  | Not Committed |  | 2024-11-01 | 2025-03-04 | B1 to GF | 100 | 0 |  | 2025-10-30 |  | 2026-03-04
44555 |  | Not Committed |  | 2024-11-01 | 2025-03-04 | B1 to GF | 100 | 0 |  | 2025-10-30 |  | 2026-03-04
44556 | NTA_Zone 2 - Sub Structure - B1 to GF | Not Ready | Finishes (Lobby & Floor Area) | 2024-11-01 | 2024-12-23 | VDF Flooring | 100 | 0 |  | 2025-10-30 |  | 2025-12-20 |  | NTA_Zone 2 | Sub Structure | B1
44556 | NTA_Zone 2 - Sub Structure - B1 to GF | Not Ready | Finishes (Lobby & Floor Area) | 2024-11-01 | 2024-12-23 | VDF Flooring | 100 | 0 |  | 2025-10-30 |  | 2025-12-20 |  | NTA_Zone 2 | Sub Structure | B1
8656 | T-14-5th Floor Flat Area | Not Ready | Dado | 2025-09-29 | 2025-10-27 | Dado | 100 | 0 |  | 2025-10-31 |  | 2025-11-28
9045 | T-15-Terrace | Not Ready | PARAPET | 2025-10-30 | 2025-12-20 | PARAPET | 100 | 0 |  | 2025-10-31 |  | 2025-12-19
9104 | T-15-1st Floor Flat Area | Not Ready | Door | 2025-11-06 | 2025-11-28 | Door | 100 | 0 |  | 2025-10-31 |  | 2025-11-22
9543 | T-16-10th Floor | Not Ready | Shear Walls/Corewalls Shuttering | 2025-11-17 | 2025-11-21 | Shear Walls/Corewalls Shuttering | 100 | 0 |  | 2025-10-31 |  | 2025-11-02
10280 | T-21-6th Floor Common Area | Not Ready | Flooring & skirting | 2025-12-03 | 2025-12-24 | Flooring & skirting | 100 | 0 |  | 2025-10-31 |  | 2025-11-23
10815 | T-20-7th Floor Flat Area | Not Ready | Toilet flooring | 2025-12-03 | 2026-01-05 | Toilet flooring | 100 | 0 |  | 2025-10-31 |  | 2025-12-05
11112 | T-19-11th Floor | Not Ready | Shuttering | 2025-11-13 | 2025-11-17 | Slab and Beam Shuttering | 3548 | 0 | Sqm | 2025-10-31 |  | 2025-11-05
11234 | T-19-3rd Floor Flat Area | Not Ready | Putty | 2025-11-21 | 2026-02-13 | Putty | 100 | 0 |  | 2025-10-31 |  | 2026-01-24
11303 | T-19-6th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-11-13 | 2025-12-04 | Plumbing Pipe Line | 100 | 0 |  | 2025-10-31 |  | 2025-11-22
11684 | T-18-GF Common Area | Not Ready | Putty | 2025-12-23 | 2026-01-13 | Putty | 100 | 0 |  | 2025-10-31 |  | 2025-11-22
40600 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | VDF/ Grade Slab - MEP & Finishes | 2024-04-18 | 2024-04-23 | VDF/ Grade Slab | 100 | 0 |  | 2025-10-31 |  | 2025-11-05 |  | Tower A | Sub Structure | B3
40705 |  | Not Committed |  | 2024-04-06 | 2024-05-27 | Lobby/ Common Area | 100 | 0 |  | 2025-10-31 |  | 2025-12-19
40706 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2024-04-06 | 2024-04-13 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-10-31 |  | 2025-11-07 |  | Tower A | Super Structure |  | MEP | FPS 1st Fix - MEP & Finishes
40707 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2024-04-06 | 2024-04-09 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-10-31 |  | 2025-11-03 |  | Tower A | Super Structure |  | MEP | Electrical 1st Fixes
42426 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-11-03 | 2025-11-19 | Flooring & Dado works | 100 | 0 |  | 2025-10-31 |  | 2025-11-18 |  | Tower A | Super Structure | L19 | Finishes | Flooring & Dado
42569 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-04-07 | 2025-04-14 | Door & Window Frame work | 100 | 0 |  | 2025-10-31 |  | 2025-11-08 |  | Tower A | Super Structure | L27 | Finishes | Door & Window Frame work
42641 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-06-11 | 2025-06-18 | Door & Window Frame work | 100 | 0 |  | 2025-10-31 |  | 2025-11-08 |  | Tower A | Super Structure | L31 | Finishes | Door & Window Frame work
48214 | Retail & Clubhouse - Sub structure - B2 to B1 | Not Ready |  | 2025-04-15 | 2025-05-26 | B2 to B1 | 100 | 0 |  | 2025-10-31 |  | 2025-12-10 |  | Club House | Sub Structure | B2
48214 | Retail & Clubhouse - Sub structure - B2 to B1 | Not Ready |  | 2025-04-15 | 2025-05-26 | B2 to B1 | 100 | 0 |  | 2025-10-31 |  | 2025-12-10 |  | Club House | Sub Structure | B2
48214 | Retail & Clubhouse - Sub structure - B2 to B1 | Not Ready |  | 2025-04-15 | 2025-05-26 | B2 to B1 | 100 | 0 |  | 2025-10-31 |  | 2025-12-10 |  | Club House | Sub Structure | B2
48266 |  | Not Ready |  | 2025-06-17 | 2025-06-17 | Plinth Checking (30 calendar days) | 100 | 0 |  | 2025-10-31 |  | 2025-10-31
48266 |  | Not Ready |  | 2025-06-17 | 2025-06-17 | Plinth Checking (30 calendar days) | 100 | 0 |  | 2025-10-31 |  | 2025-10-31
9265 | T-15-7th Floor Common Area | Not Ready |  | 2025-10-30 | 2025-12-04 | Plastering Gypsum | 100 | 0 |  | 2025-11-01 |  | 2025-12-05
10891 | T-20-10th Floor Flat Area | Not Ready | Plastering | 2025-12-01 | 2026-01-13 | Plastering-Gypsum | 100 | 0 |  | 2025-11-01 |  | 2025-12-17
40522 | Tower A - Super Structure - Finishes & MEP - L48 to L49 | Not Ready | Gypsum Plastering Works | 2025-10-09 | 2025-11-01 | L48-49 | 100 | 0 |  | 2025-11-01 |  | 2025-11-24 |  | Tower A | Super Structure | L48 | Finishes | Gypsum Plastering Works
40522 | Tower A - Super Structure - Finishes & MEP - L48 to L49 | Not Ready | Gypsum Plastering Works | 2025-10-09 | 2025-11-01 | L48-49 | 100 | 0 |  | 2025-11-01 |  | 2025-11-24 |  | Tower A | Super Structure | L48
41603 |  | Started |  | 2025-11-01 | 2026-05-16 | L41-42 | 100 | 26 |  | 2025-11-01 | 2025-11-01 | 2026-06-08 |  |  |  |  | Finishes | Gypsum Plastering Works
41603 |  | Started |  | 2025-11-01 | 2026-05-16 | L41-42 | 100 | 26 |  | 2025-11-01 | 2025-11-01 | 2026-06-08
41604 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2025-11-01 | 2025-11-05 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 40 |  | 2025-11-01 | 2025-11-01 | 2026-04-25 |  | Tower A | Super Structure | L41 | MEP | FPS 1st Fix - MEP & Finishes
41605 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-11-01 | 2025-11-05 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-11-01 |  | 2025-11-04 |  | Tower A | Super Structure | L41 | MEP | Electrical 1st Fixes
42909 |  | Not Committed |  | 2025-10-14 | 2026-03-07 | Finishes after 1st Fix | 100 | 0 |  | 2025-11-01 |  | 2026-02-05
42910 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-10-14 | 2025-11-06 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-11-01 |  | 2025-11-25 |  | Tower A | Super Structure | L46 | Finishes | Blockwork
42956 |  | Not Committed |  | 2025-10-09 | 2026-09-05 | L49-50 (Refuge) | 100 | 0 |  | 2025-11-01 |  | 2026-08-20
42957 |  | Not Committed |  | 2025-10-09 | 2025-11-07 | MEP 1st Fixes | 100 | 0 |  | 2025-11-01 |  | 2025-11-29
42958 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2025-10-09 | 2025-10-16 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-11-01 |  | 2025-11-08 |  | Tower A | Super Structure | L49 | MEP | FPS 1st Fix - MEP & Finishes
42959 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-10-09 | 2025-10-14 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2025-11-01 |  | 2025-11-06 |  | Tower A | Super Structure | L49 | MEP | Electrical 1st Fixes
42960 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2025-10-09 | 2025-10-16 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2025-11-01 |  | 2025-11-08 |  | Tower A | Super Structure | L49
42961 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2025-10-09 | 2025-10-27 | Wet Area Waterproofing | 100 | 0 |  | 2025-11-01 |  | 2025-11-18 |  | Tower A | Super Structure | L49
44071 | Tower A - Super Structure - Finishes & MEP - L28 to L33 | Started | Façade Works - MEP & Finishes | 2025-12-02 | 2025-12-12 | DGU Assembly Installation | 100 | 20 | Units | 2025-11-01 | 2025-09-05 | 2025-11-13 |  | Tower A | Super Structure | L28 | Façade | Façade Works
44072 | Tower A - Super Structure - Finishes & MEP - L28 to L33 | Started | Façade Works - MEP & Finishes | 2025-12-02 | 2025-12-24 | Installation of highly reflective metal sheet | 100 | 20 | Units | 2025-11-01 | 2025-09-08 | 2025-11-25 |  | Tower A | Super Structure | L28 | Façade | Façade Works
44073 | Tower A - Super Structure - Finishes & MEP - L28 to L33 | Started | Façade Works - MEP & Finishes | 2025-12-02 | 2025-12-12 | Fixing of Backlit Laminated Glass assembly & ACP Panels | 100 | 20 | Units | 2025-11-01 | 2025-09-09 | 2025-11-13 |  | Tower A | Super Structure | L28 | Façade | Façade Works
44074 | Tower A - Super Structure - Finishes & MEP - L28 to L33 | Started | Façade Works - MEP & Finishes | 2025-12-02 | 2025-12-12 | Fixing of Louvers | 100 | 20 | Units | 2025-11-01 | 2025-09-09 | 2025-11-13 |  | Tower A | Super Structure | L28 | Façade | Façade Works
44074 | Tower A - Super Structure - Finishes & MEP - L28 to L33 | Started | Façade Works - MEP & Finishes | 2025-12-02 | 2025-12-12 | Fixing of Louvers | 100 | 20 | Units | 2025-11-01 | 2025-09-09 | 2025-11-13 |  | Tower A | Super Structure | L28
45424 | Tower B - Super Structure - Finishes & MEP - P4 to P5 | Not Ready | Partition Wall-Blockwork | 2025-08-21 | 2025-09-03 | Staircase Area | 100 | 0 |  | 2025-11-01 |  | 2025-11-13 |  | Tower B | Super Structure
48155 |  | Not Committed |  | 2025-06-18 | 2025-11-26 | Super-Structure_Retail | 100 | 0 |  | 2025-11-01 |  | 2026-03-19
48156 |  | Not Committed |  | 2025-06-18 | 2025-10-08 | GF to R1 (6.61m) | 100 | 0 |  | 2025-11-01 |  | 2026-01-29
48157 |  | Not Committed |  | 2025-06-18 | 2025-08-20 | Pour RT-1 | 100 | 0 |  | 2025-11-01 |  | 2025-12-23
48158 | Retail - Super structure - GF to R1 - P1 | Not Ready |  | 2025-06-18 | 2025-07-24 | Columns_RT | 100 | 0 |  | 2025-11-01 |  | 2025-12-05 |  | Retail | Super Structure | GF | RCC Sub Structure | RCC Works - Vertical
48158 | Retail - Super structure - GF to R1 - P1 | Not Ready |  | 2025-06-18 | 2025-07-24 | Columns_RT | 100 | 0 |  | 2025-11-01 |  | 2025-12-05 |  | Retail | Super Structure | GF
48159 | Retail - Super structure - GF to R1 - P1 | Not Ready |  | 2025-06-18 | 2025-07-17 | Staircase_RT | 100 | 0 |  | 2025-11-01 |  | 2025-11-29 |  | Retail | Super Structure | GF | RCC Sub Structure | RCC Works - Slab
48159 | Retail - Super structure - GF to R1 - P1 | Not Ready |  | 2025-06-18 | 2025-07-17 | Staircase_RT | 100 | 0 |  | 2025-11-01 |  | 2025-11-29 |  | Retail | Super Structure | GF
48164 |  | Not Committed |  | 2025-06-18 | 2025-08-20 | Pour RT-3 | 100 | 0 |  | 2025-11-01 |  | 2025-12-23
48165 | Retail - Super structure - GF to R1 - P3 | Not Ready |  | 2025-06-18 | 2025-07-24 | Columns_RT | 100 | 0 |  | 2025-11-01 |  | 2025-12-05 |  | Retail | Super Structure | GF | RCC Sub Structure | RCC Works - Vertical
48165 | Retail - Super structure - GF to R1 - P3 | Not Ready |  | 2025-06-18 | 2025-07-24 | Columns_RT | 100 | 0 |  | 2025-11-01 |  | 2025-12-05 |  | Retail | Super Structure | GF
48166 | Retail - Super structure - GF to R1 - P3 | Not Ready |  | 2025-06-18 | 2025-07-17 | Staircase_RT | 100 | 0 |  | 2025-11-01 |  | 2025-11-29 |  | Retail | Super Structure | GF | RCC Sub Structure | RCC Works - Slab
48166 | Retail - Super structure - GF to R1 - P3 | Not Ready |  | 2025-06-18 | 2025-07-17 | Staircase_RT | 100 | 0 |  | 2025-11-01 |  | 2025-11-29 |  | Retail | Super Structure | GF
48172 |  | Not Committed |  | 2025-06-18 | 2025-08-07 | Pour RT-5 | 100 | 0 |  | 2025-11-01 |  | 2025-12-17
48173 | Retail - Super structure - GF to R1 - P5 | Not Ready |  | 2025-06-18 | 2025-07-17 | Columns_RT | 100 | 0 |  | 2025-11-01 |  | 2025-11-29 |  | Retail | Super Structure | GF | RCC Sub Structure | RCC Works - Vertical
48173 | Retail - Super structure - GF to R1 - P5 | Not Ready |  | 2025-06-18 | 2025-07-17 | Columns_RT | 100 | 0 |  | 2025-11-01 |  | 2025-11-29 |  | Retail | Super Structure | GF
48174 | Retail - Super structure - GF to R1 - P5 | Not Ready |  | 2025-06-18 | 2025-07-17 | Staircase_RT | 100 | 0 |  | 2025-11-01 |  | 2025-11-29 |  | Retail | Super Structure | GF | RCC Sub Structure | RCC Works - Slab
48174 | Retail - Super structure - GF to R1 - P5 | Not Ready |  | 2025-06-18 | 2025-07-17 | Staircase_RT | 100 | 0 |  | 2025-11-01 |  | 2025-11-29 |  | Retail | Super Structure | GF
8488 | T-14-12th Floor | Complete | RCC | 2025-09-25 | 2025-09-26 | Slab& Beam RCC | 307 | 307 | CUM | 2025-11-02 | 2026-01-13 | 2025-11-02 | 2026-01-14
8539 | T-14-GF Common Area | Not Ready | Window | 2025-10-07 | 2025-10-29 | Window | 100 | 0 |  | 2025-11-02 |  | 2025-11-24
8679 | T-14-6th Floor Flat Area | Not Ready | Waterproofing | 2025-09-30 | 2025-11-05 | Toilet & Balcony sunken Waterproofing | 100 | 0 |  | 2025-11-02 |  | 2025-12-08
9043 | T-15-Terrace | Not Ready | LMR ROOM | 2025-11-03 | 2025-12-22 | LMR ROOM | 100 | 0 |  | 2025-11-02 |  | 2025-12-23
9046 | T-15-Terrace | Not Ready | STAIRCASE HR | 2025-11-03 | 2025-12-22 | STAIRCASE HR | 100 | 0 |  | 2025-11-02 |  | 2025-12-23
9086 | T-15-GF Common Area | Not Ready | Door | 2025-11-03 | 2025-11-25 | Door | 100 | 0 |  | 2025-11-02 |  | 2025-11-26
9670 | T-16-3rd Floor Flat Area | Not Ready | Dado | 2025-11-29 | 2025-12-26 | Dado | 100 | 0 |  | 2025-11-02 |  | 2025-11-30
10170 | T-21-2nd Floor Flat Area | Not Ready | Door | 2025-11-05 | 2025-11-27 | Door | 100 | 0 |  | 2025-11-02 |  | 2025-11-24
11113 | T-19-11th Floor | Not Ready | Slab& Beam Steel & Conduting | 2025-11-15 | 2025-11-18 | Slab& Beam Steel & Conduting | 11.3 | 0 | MT | 2025-11-02 |  | 2025-11-05
11148 | T-19-GF Flat Area | Not Ready | Window | 2025-11-20 | 2025-12-12 | Window | 100 | 0 |  | 2025-11-02 |  | 2025-11-25
11307 | T-19-6th Floor Flat Area | Not Ready | Plastering | 2025-11-15 | 2025-12-29 | Plastering-Gypsum | 100 | 0 |  | 2025-11-02 |  | 2025-12-17
11803 | T-18-5th Floor Flat Area | Not Ready | Toilet flooring | 2026-01-09 | 2026-02-13 | Toilet flooring | 100 | 0 |  | 2025-11-02 |  | 2025-12-05
11876 | T-18-8th Floor Flat Area | Not Ready | Plastering | 2026-01-14 | 2026-02-07 | Plastering-Cement | 100 | 0 |  | 2025-11-02 |  | 2025-11-24
11902 | T-18-9th Floor Flat Area | Not Ready | Plastering | 2026-01-14 | 2026-02-07 | Plastering-Cement | 100 | 0 |  | 2025-11-02 |  | 2025-11-24
8507 | T-14-Basement Floor | Not Ready | 1st Coat Painting | 2025-09-27 | 2025-11-03 | 1st Coat Painting | 100 | 0 |  | 2025-11-03 |  | 2025-12-09
8704 | T-14-7th Floor Flat Area | Not Ready | Plastering | 2025-09-27 | 2025-10-20 | Plastering-Cement | 100 | 0 |  | 2025-11-03 |  | 2025-11-25
8728 | T-14-8th Floor Flat Area | Not Ready | Blockwork | 2025-09-26 | 2025-10-19 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-11-03 |  | 2025-11-24
8767 | T-14-9th Floor Flat Area | Not Ready | Railing | 2025-09-26 | 2025-10-30 | Balcony Railing | 100 | 0 |  | 2025-11-03 |  | 2025-12-08
9202 | T-15-5th Floor Flat Area | Not Ready | Dado | 2025-10-29 | 2025-11-27 | Dado | 100 | 0 |  | 2025-11-03 |  | 2025-12-01
9545 | T-16-10th Floor | Not Ready | Shuttering | 2025-11-20 | 2025-11-24 | Slab and Beam Shuttering | 4183 | 0 | Sqm | 2025-11-03 |  | 2025-11-07
9646 | T-16-2nd Floor Flat Area | Not Ready |  | 2025-12-01 | 2026-01-02 | Toilets False Celing | 100 | 0 |  | 2025-11-03 |  | 2025-12-09
9717 | T-16-5th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-11-20 | 2025-12-12 | Plumbing Pipe Line | 100 | 0 |  | 2025-11-03 |  | 2025-11-24
10276 | T-21-6th Floor Flat Area | Not Ready | 1st Coat Painting | 2025-12-13 | 2026-03-07 | 1st Coat Painting | 100 | 0 |  | 2025-11-03 |  | 2026-01-26
10818 | T-20-7th Floor Flat Area | Not Ready | Putty | 2025-12-06 | 2026-02-28 | Putty | 100 | 0 |  | 2025-11-03 |  | 2026-01-27
39735 | Tower A - Super Structure - Core Wall High Rise L71-72 | Complete | Core Wall RCC Works | 2025-10-14 | 2025-10-14 | Casting | 100 | 100 |  | 2025-11-03 | 2025-11-15 | 2025-11-04 | 2025-11-16 | Tower A | Super Structure | L71 | RCC Super Structure | Core Wall RCC Works
40004 |  | Complete |  | 2025-10-13 | 2025-10-18 | L67-68 | 100 | 100 |  | 2025-11-03 | 2025-11-15 | 2025-11-14 | 2025-11-23
40004 |  | Complete |  | 2025-10-13 | 2025-10-18 | L67-68 | 100 | 100 |  | 2025-11-03 | 2025-11-15 | 2025-11-14 | 2025-11-23 |  |  |  | Finishes | Gypsum Plastering Works
40005 | Tower A - Super Structure - Core & Outer Slab L67-68 | Complete | RCC Works - Vertical | 2025-10-13 | 2025-10-18 | Outer Columns_TA | 100 | 100 |  | 2025-11-03 | 2025-11-15 | 2025-11-12 | 2025-11-21 | Tower A | Super Structure | L67 | RCC Sub Structure | RCC Works - Vertical
40413 |  | Not Committed |  | 2025-10-13 | 2026-02-11 | L64-65 | 100 | 0 |  | 2025-11-03 |  | 2026-03-06
40413 |  | Not Committed |  | 2025-10-13 | 2026-02-11 | L64-65 | 100 | 0 |  | 2025-11-03 |  | 2026-03-06 |  |  |  |  | Finishes | Gypsum Plastering Works
40414 | Tower A - Super Structure - Finishes & MEP - L64 to L65 | Not Ready | Partition Wall-Blockwork | 2025-10-13 | 2025-10-30 | De-shuttering & Area clearance | 100 | 0 |  | 2025-11-03 |  | 2025-11-20 |  | Tower A | Super Structure | L64
40681 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | False Ceiling - MEP & Finishes | 2024-04-09 | 2024-04-19 | False Ceiling | 100 | 0 |  | 2025-11-03 |  | 2025-11-13 |  | Tower A | Super Structure | GF | Finishes | False Ceiling
40807 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | VDF/ Grade Slab - MEP & Finishes | 2024-06-29 | 2024-08-28 | VDF/ Grade Slab & Apt. finishes | 100 | 0 |  | 2025-11-03 |  | 2025-12-26 |  | Tower A | Super Structure
40833 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | HVAC Ducting - MEP & Finishes | 2024-06-29 | 2024-07-18 | HVAC Ducting/ Fan Installations | 100 | 0 |  | 2025-11-03 |  | 2025-11-20 |  | Tower A | Super Structure |  | MEP | HVAC Ducting
40927 | Tower A - Super Structure - Finishes & MEP - L55 to L65 | Not Ready |  | 2025-10-24 | 2025-11-27 | Shaft Cabling in Electrical & ELV Shaft | 100 | 0 |  | 2025-11-03 |  | 2025-12-08 |  | Tower A | Super Structure | L55
41161 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-03-26 | 2025-03-31 | Lobby Plastering | 100 | 0 |  | 2025-11-03 |  | 2025-11-07 |  | Tower A | Super Structure | L13 | Finishes | Lobby Plastering
41176 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-03-26 | 2025-03-28 | Lobby Blockwork | 100 | 0 |  | 2025-11-03 |  | 2025-11-05 |  | Tower A | Super Structure | L14 | Finishes | Blockwork
42659 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-06-19 | 2025-06-26 | Door & Window Frame work | 100 | 0 |  | 2025-11-03 |  | 2025-11-10 |  | Tower A | Super Structure | L32 | Finishes | Door & Window Frame work
42926 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-10-10 | 2025-10-22 | Cement Plastering in wet areas | 100 | 0 |  | 2025-11-03 |  | 2025-11-13 |  | Tower A | Super Structure | L47
45427 | Tower B - Super Structure - Finishes & MEP - P5 to P6 | Not Ready | Partition Wall-Blockwork | 2025-08-22 | 2025-09-10 | Partition Walls | 100 | 0 |  | 2025-11-03 |  | 2025-11-20 |  | Tower B | Super Structure
47629 |  | Not Ready |  | 2024-12-06 | 2024-12-30 | Slab_NTA | 100 | 0 |  | 2025-11-03 |  | 2025-11-25
47629 |  | Not Ready |  | 2024-12-06 | 2024-12-30 | Slab_NTA | 100 | 0 |  | 2025-11-03 |  | 2025-11-25 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
8490 | T-14-Terrace | Not Ready | AL - Shear Walls/Corewalls Steel | 2025-09-27 | 2025-10-03 | AL - Shear Walls/Corewalls Steel | 22 | 0 | MT | 2025-11-04 |  | 2025-11-10
9048 |  | Not Ready |  | 2025-11-05 | 2025-11-21 | Lowering Aluminium FW Material For PH-2 | 100 | 0 |  | 2025-11-04 |  | 2025-11-23
9178 | T-15-4th Floor Flat Area | Not Ready | Toilets False Celing | 2025-11-02 | 2025-12-05 | Toilets False Celing | 100 | 0 |  | 2025-11-04 |  | 2025-12-08
9231 | T-15-6th Floor Flat Area | Not Ready | Flooring & skirting | 2025-11-06 | 2025-12-20 | Flooring & skirting | 100 | 0 |  | 2025-11-04 |  | 2025-12-20
9275 | T-15-8th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-11-05 | 2025-11-27 | Plumbing Pipe Line | 100 | 0 |  | 2025-11-04 |  | 2025-11-27
9301 | T-15-9th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-11-05 | 2025-11-27 | Plumbing Pipe Line | 100 | 0 |  | 2025-11-04 |  | 2025-11-27
10321 | T-21-8th Floor Flat Area | Not Ready | Toilet flooring | 2025-12-06 | 2026-01-07 | Toilet flooring | 100 | 0 |  | 2025-11-04 |  | 2025-12-05
10347 | T-21-9th Floor Flat Area | Not Ready | Toilet flooring | 2025-12-06 | 2026-01-07 | Toilet flooring | 100 | 0 |  | 2025-11-04 |  | 2025-12-05
10770 | T-20-5th Floor Flat Area | Not Ready | 1st Coat Painting | 2025-12-11 | 2026-03-04 | 1st Coat Painting | 100 | 0 |  | 2025-11-04 |  | 2026-01-27
10902 |  | Not Ready |  | 2025-12-09 | 2026-07-23 | Common Area | 100 | 0 |  | 2025-11-04 |  | 2026-06-18
11232 | T-19-3rd Floor Flat Area | Not Ready |  | 2025-11-24 | 2025-12-26 | Toilets False Celing | 100 | 0 |  | 2025-11-04 |  | 2025-12-09
11685 | T-18-GF Common Area | Not Ready | Window | 2025-12-25 | 2026-01-16 | Window | 100 | 0 |  | 2025-11-04 |  | 2025-11-24
11891 | T-18-8th Floor Common Area | Not Ready | Plastering | 2026-01-17 | 2026-02-20 | Plastering-Gypsum | 100 | 0 |  | 2025-11-04 |  | 2025-12-05
11917 | T-18-9th Floor Common Area | Not Ready | Plastering | 2026-01-17 | 2026-02-20 | Plastering-Gypsum | 100 | 0 |  | 2025-11-04 |  | 2025-12-05
39736 | Tower A - Super Structure - Core Wall High Rise L71-72 | Complete | Core Wall RCC Works | 2025-10-15 | 2025-10-15 | ACS Form Release & jump to next level | 100 | 100 |  | 2025-11-04 | 2025-11-17 | 2025-11-05 | 2025-11-18 | Tower A | Super Structure | L71 | RCC Super Structure | Core Wall RCC Works
40360 | Tower A - Super Structure - Finishes & MEP - L50 to L51 | Not Ready | Partition Wall-Blockwork | 2025-10-11 | 2025-10-16 | Staircase Area | 100 | 0 |  | 2025-11-04 |  | 2025-11-08 |  | Tower A | Super Structure | L50
40363 | Tower A - Super Structure - Finishes & MEP - L51 to L52 | Not Ready | Partition Wall-Blockwork | 2025-10-11 | 2025-10-18 | Partition Walls | 100 | 0 |  | 2025-11-04 |  | 2025-11-11 |  | Tower A | Super Structure | L51
40708 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2024-04-10 | 2024-04-11 | FAPA Cabling | 100 | 0 |  | 2025-11-04 |  | 2025-11-05 |  | Tower A | Super Structure
8583 | T-14-2nd Floor Flat Area | Not Ready | Window | 2025-10-14 | 2025-11-07 | Window | 100 | 0 |  | 2025-11-05 |  | 2025-11-30
8719 | T-14-7th Floor Common Area | Not Ready |  | 2025-09-30 | 2025-11-05 | Plastering Gypsum | 100 | 0 |  | 2025-11-05 |  | 2025-12-11
8732 | T-14-8th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-09-29 | 2025-10-16 | Electrical DB Fixing | 100 | 0 |  | 2025-11-05 |  | 2025-11-24
9047 | T-15-Terrace | Not Ready |  | 2025-11-06 | 2025-12-25 | MISC | 100 | 0 |  | 2025-11-05 |  | 2025-12-25
9546 | T-16-10th Floor | Not Ready | Slab& Beam Steel & Conduting | 2025-11-22 | 2025-11-25 | Slab& Beam Steel & Conduting | 14 | 0 | MT | 2025-11-05 |  | 2025-11-08
9721 | T-16-5th Floor Flat Area | Not Ready | Plastering | 2025-11-22 | 2026-01-05 | Plastering-Gypsum | 100 | 0 |  | 2025-11-05 |  | 2025-12-21
11164 | T-19-GF Common Area | Not Ready | Putty | 2025-11-26 | 2025-12-18 | Putty | 100 | 0 |  | 2025-11-05 |  | 2025-11-26
11851 | T-18-7th Floor Flat Area | Not Ready | Waterproofing | 2026-01-17 | 2026-02-20 | Waterproofing | 100 | 0 |  | 2025-11-05 |  | 2025-12-06
39737 |  | Started |  | 2025-10-16 | 2025-10-24 | Core Wall L72-73 | 100 | 86 |  | 2025-11-05 | 2025-11-17 | 2025-11-17
39738 | Tower A - Super Structure - Core Wall High Rise L72-73 | Complete | Core Wall RCC Works | 2025-10-16 | 2025-10-16 | Scaffolding & platform | 100 | 100 |  | 2025-11-05 | 2025-11-17 | 2025-11-06 | 2025-11-20 | Tower A | Super Structure | L72 | RCC Super Structure | Core Wall RCC Works
40107 |  | Not Committed |  | 2025-11-07 | 2026-07-09 | Sub-Station (GF-P1-P2 in Zone 2) | 100 | 0 |  | 2025-11-05 |  | 2026-07-07
40108 | Tower A - Super Structure - Finishes & MEP - Sub Station | Not Ready | Sub Station - High Side Services | 2025-11-07 | 2025-12-11 | Masonry Works (Trench, Partitions etc) | 100 | 0 |  | 2025-11-05 |  | 2025-12-09 |  | Tower A | Super Structure
41606 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2025-11-05 | 2025-11-07 | FAPA Cabling | 100 | 0 |  | 2025-11-05 |  | 2025-11-06 |  | Tower A | Super Structure | L41
42372 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-10-15 | 2025-11-01 | Flooring & Dado works | 100 | 0 |  | 2025-11-05 |  | 2025-11-22 |  | Tower A | Super Structure | L16 | Finishes | Flooring & Dado
42498 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-11-20 | 2025-12-06 | Flooring & Dado works | 100 | 0 |  | 2025-11-05 |  | 2025-11-22 |  | Tower A | Super Structure | L23 | Finishes | Flooring & Dado
42621 |  | Not Committed |  | 2025-04-08 | 2026-01-12 | Finishes after 1st Fix | 100 | 0 |  | 2025-11-05 |  | 2025-12-23
42622 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-04-08 | 2025-04-30 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-11-05 |  | 2025-11-27 |  | Tower A | Super Structure | L30 | Finishes | Blockwork
8492 | T-14-Terrace | Not Ready | Conduiting | 2025-09-30 | 2025-10-04 | Conduiting works | 100 | 0 |  | 2025-11-06 |  | 2025-11-10
9044 | T-15-Terrace | Not Ready | OHT | 2025-11-07 | 2025-12-26 | OHT | 100 | 0 |  | 2025-11-06 |  | 2025-12-25
9279 | T-15-8th Floor Flat Area | Not Ready | Plastering | 2025-11-07 | 2025-12-21 | Plastering-Gypsum | 100 | 0 |  | 2025-11-06 |  | 2025-12-21
9305 | T-15-9th Floor Flat Area | Not Ready | Plastering | 2025-11-07 | 2025-12-21 | Plastering-Gypsum | 100 | 0 |  | 2025-11-06 |  | 2025-12-21
9587 | T-16-GF Flat Area | Not Ready | Putty | 2025-11-26 | 2025-12-17 | Putty | 100 | 0 |  | 2025-11-06 |  | 2025-11-28
10742 | T-20-4th Floor Flat Area | Not Ready | Door | 2025-12-19 | 2026-01-10 | Door | 100 | 0 |  | 2025-11-06 |  | 2025-11-27
10840 | T-20-8th Floor Flat Area | Not Ready | Dado | 2025-12-10 | 2026-01-06 | Dado | 100 | 0 |  | 2025-11-06 |  | 2025-12-03
10866 | T-20-9th Floor Flat Area | Not Ready | Dado | 2025-12-10 | 2026-01-06 | Dado | 100 | 0 |  | 2025-11-06 |  | 2025-12-03
10888 | T-20-10th Floor Flat Area | Not Ready | Plastering | 2025-12-06 | 2025-12-28 | Plastering-Cement | 100 | 0 |  | 2025-11-06 |  | 2025-11-28
11114 | T-19-11th Floor | Not Ready | RCC | 2025-11-18 | 2025-11-19 | Slab& Beam RCC | 340 | 0 | CUM | 2025-11-06 |  | 2025-11-06
11256 | T-19-4th Floor Flat Area | Not Ready | Dado | 2025-11-21 | 2025-12-19 | Dado | 100 | 0 |  | 2025-11-06 |  | 2025-12-04
11671 | T-18-GF Flat Area | Not Ready | 1st Coat Painting | 2025-12-25 | 2026-02-14 | 1st Coat Painting | 100 | 0 |  | 2025-11-06 |  | 2025-12-24
39199 |  | Not Ready |  | 2025-04-10 | 2025-04-24 | High Side - Installation of RMU and HT Panels | 100 | 0 |  | 2025-11-06 |  | 2025-11-19
39739 | Tower A - Super Structure - Core Wall High Rise L72-73 | Complete | Core Wall RCC Works | 2025-10-17 | 2025-10-21 | Reinf & Guide shoes fixing | 100 | 100 |  | 2025-11-06 | 2025-11-18 | 2025-11-10 | 2025-11-24 | Tower A | Super Structure | L72 | RCC Super Structure | Core Wall RCC Works
40006 | Tower A - Super Structure - Core & Outer Slab L67-68 | Complete | RCC Works - Slab | 2025-10-14 | 2025-10-18 | Outer Slab_TA | 100 | 100 |  | 2025-11-06 | 2025-11-19 | 2025-11-14 | 2025-11-23 | Tower A | Super Structure | L67 | RCC Sub Structure | RCC Works - Slab
40160 | Tower A - Super Structure - Finishes & MEP - P2 to P3 | Not Ready | Partition Wall-Blockwork | 2024-04-12 | 2024-04-23 | Staircase Area | 100 | 0 |  | 2025-11-06 |  | 2025-11-17 |  | Tower A | Super Structure
40601 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2024-04-24 | 2024-05-02 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2025-11-06 |  | 2025-11-13 |  | Tower A | Sub Structure | B3 | MEP | FPS 2nd Fix - MEP & Finishes
40602 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-04-24 | 2024-05-02 | FAPA Device Fixing | 100 | 0 |  | 2025-11-06 |  | 2025-11-13 |  | Tower A | Sub Structure | B3
40602 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-04-24 | 2024-05-02 | FAPA Device Fixing | 100 | 0 |  | 2025-11-06 |  | 2025-11-13 |  | Tower A | Sub Structure | B3
40602 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-04-24 | 2024-05-02 | FAPA Device Fixing | 100 | 0 |  | 2025-11-06 |  | 2025-11-13 |  | Tower A | Sub Structure | B3
40602 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-04-24 | 2024-05-02 | FAPA Device Fixing | 100 | 0 |  | 2025-11-06 |  | 2025-11-13 |  | Tower A | Sub Structure | B3
41177 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-03-29 | 2025-04-03 | Lobby Plastering | 100 | 0 |  | 2025-11-06 |  | 2025-11-11 |  | Tower A | Super Structure | L14 | Finishes | Lobby Plastering
41192 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-03-29 | 2025-04-01 | Lobby Blockwork | 100 | 0 |  | 2025-11-06 |  | 2025-11-08 |  | Tower A | Super Structure | L15 | Finishes | Blockwork
42461 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-02-12 | 2025-02-19 | Door & Window Frame work | 100 | 0 |  | 2025-11-06 |  | 2025-11-13 |  | Tower A | Super Structure | L21 | Finishes | Door & Window Frame work
42677 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-06-27 | 2025-07-04 | Door & Window Frame work | 100 | 0 |  | 2025-11-06 |  | 2025-11-13 |  | Tower A | Super Structure | L33 | Finishes | Door & Window Frame work
42695 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-07-05 | 2025-07-12 | Door & Window Frame work | 100 | 0 |  | 2025-11-06 |  | 2025-11-13 |  | Tower A | Super Structure | L34 | Finishes | Door & Window Frame work
42713 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-07-17 | 2025-07-25 | Door & Window Frame work | 100 | 0 |  | 2025-11-06 |  | 2025-11-13 |  | Tower A | Super Structure | L35 | Finishes | Door & Window Frame work
42731 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-08-01 | 2025-08-09 | Door & Window Frame work | 100 | 0 |  | 2025-11-06 |  | 2025-11-13 |  | Tower A | Super Structure | L36 | Finishes | Door & Window Frame work
42749 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-08-13 | 2025-08-22 | Door & Window Frame work | 100 | 0 |  | 2025-11-06 |  | 2025-11-13 |  | Tower A | Super Structure | L37 | Finishes | Door & Window Frame work
42767 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-08-30 | 2025-09-06 | Door & Window Frame work | 100 | 0 |  | 2025-11-06 |  | 2025-11-13 |  | Tower A | Super Structure | L38 | Finishes | Door & Window Frame work
42785 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-09-08 | 2025-09-15 | Door & Window Frame work | 100 | 0 |  | 2025-11-06 |  | 2025-11-13 |  | Tower A | Super Structure | L39 | Finishes | Door & Window Frame work
42803 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-09-16 | 2025-09-24 | Door & Window Frame work | 100 | 0 |  | 2025-11-06 |  | 2025-11-13 |  | Tower A | Super Structure | L40 | Finishes | Door & Window Frame work
42875 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-10-22 | 2025-10-29 | Door & Window Frame work | 100 | 0 |  | 2025-11-06 |  | 2025-11-13 |  | Tower A | Super Structure | L44 | Finishes | Door & Window Frame work
8491 | T-14-Terrace | Not Ready | Shear Walls/Corewalls Shuttering | 2025-10-01 | 2025-10-06 | Shear Walls/Corewalls Shuttering | 100 | 0 |  | 2025-11-07 |  | 2025-11-09
8657 | T-14-5th Floor Flat Area | Not Ready | Toilet flooring | 2025-10-07 | 2025-11-11 | Toilet flooring | 100 | 0 |  | 2025-11-07 |  | 2025-12-12
8685 | T-14-6th Floor Flat Area | Not Ready | Flooring & skirting | 2025-10-06 | 2025-11-21 | Flooring & skirting | 100 | 0 |  | 2025-11-07 |  | 2025-12-24
10324 | T-21-8th Floor Flat Area | Not Ready | Putty | 2025-12-09 | 2026-03-03 | Putty | 100 | 0 |  | 2025-11-07 |  | 2026-01-30
10350 | T-21-9th Floor Flat Area | Not Ready | Putty | 2025-12-09 | 2026-03-03 | Putty | 100 | 0 |  | 2025-11-07 |  | 2026-01-30
11149 | T-19-GF Flat Area | Not Ready | Door | 2025-11-26 | 2025-12-18 | Door | 100 | 0 |  | 2025-11-07 |  | 2025-11-28
11165 | T-19-GF Common Area | Not Ready | Window | 2025-11-28 | 2025-12-20 | Window | 100 | 0 |  | 2025-11-07 |  | 2025-11-28
11304 | T-19-6th Floor Flat Area | Not Ready | Plastering | 2025-11-20 | 2025-12-12 | Plastering-Cement | 100 | 0 |  | 2025-11-07 |  | 2025-11-30
11328 | T-19-7th Floor Flat Area | Not Ready | Blockwork | 2025-11-19 | 2025-12-11 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-11-07 |  | 2025-11-29
11367 | T-19-8th Floor Flat Area | Not Ready | Railing | 2025-11-19 | 2025-12-22 | Balcony Railing | 100 | 0 |  | 2025-11-07 |  | 2025-12-12
11806 | T-18-5th Floor Flat Area | Not Ready | Putty | 2026-01-16 | 2026-04-10 | Putty | 100 | 0 |  | 2025-11-07 |  | 2026-01-30
39740 | Tower A - Super Structure - Core Wall High Rise L72-73 | Complete | Core Wall RCC Works | 2025-10-18 | 2025-10-22 | ACS Form Closing & Alignment | 100 | 100 |  | 2025-11-07 | 2025-11-25 | 2025-11-11 | 2025-11-27 | Tower A | Super Structure | L72 | RCC Super Structure | Core Wall RCC Works
41619 |  | Started |  | 2025-11-07 | 2026-05-20 | L42-43 | 100 | 26 |  | 2025-11-07 | 2025-11-07 | 2026-06-11 |  |  |  |  | Finishes | Gypsum Plastering Works
41619 |  | Started |  | 2025-11-07 | 2026-05-20 | L42-43 | 100 | 26 |  | 2025-11-07 | 2025-11-07 | 2026-06-11
41620 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2025-11-07 | 2025-11-11 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 40 |  | 2025-11-07 | 2025-11-07 | 2026-04-29 |  | Tower A | Super Structure | L42 | MEP | FPS 1st Fix - MEP & Finishes
41621 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-11-07 | 2025-11-11 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-11-07 |  | 2025-11-10 |  | Tower A | Super Structure | L42 | MEP | Electrical 1st Fixes
44076 |  | Started |  | 2025-12-08 | 2026-01-17 | L33-38 | 100 | 10 |  | 2025-11-07 | 2025-09-09 | 2025-12-18
44077 | Tower A - Super Structure - Finishes & MEP - L33 to L38 | Started | Façade Works - MEP & Finishes | 2025-12-08 | 2025-12-24 | Al. Frame section (Mullion & Transom) Installation | 100 | 10 | Units | 2025-11-07 | 2025-09-09 | 2025-11-25 |  | Tower A | Super Structure | L33 | Façade | Façade Works
9129 | T-15-2nd Floor Flat Area | Not Ready | Window | 2025-11-15 | 2025-12-07 | Window | 100 | 0 |  | 2025-11-08 |  | 2025-11-30
10816 | T-20-7th Floor Flat Area | Not Ready | Toilets False Celing | 2025-12-12 | 2026-01-13 | Toilets False Celing | 100 | 0 |  | 2025-11-08 |  | 2025-12-09
10903 | T-20-11th Floor Common Area | Not Ready | Plastering | 2025-12-09 | 2026-01-10 | Plastering-Gypsum | 100 | 0 |  | 2025-11-08 |  | 2025-12-09
11116 | T-19-Terrace | Not Ready | AL - Shear Walls/Corewalls Steel | 2025-11-20 | 2025-11-25 | AL - Shear Walls/Corewalls Steel | 28.4 | 0 | MT | 2025-11-08 |  | 2025-11-14
11703 | T-18-1st Floor Flat Area | Not Ready | Window | 2026-01-01 | 2026-01-24 | Window | 100 | 0 |  | 2025-11-08 |  | 2025-11-29
40474 | Tower A - Super Structure - Finishes & MEP - P1 to P2 | Not Ready | Gypsum Plastering Works | 2024-04-15 | 2024-06-06 | P1 to P2_TA & NTA | 100 | 0 |  | 2025-11-08 |  | 2025-12-31 |  | Tower A | Super Structure |  | Finishes | Gypsum Plastering Works
40709 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2024-04-15 | 2024-04-22 | HVAC Ducting | 100 | 0 |  | 2025-11-08 |  | 2025-11-15 |  | Tower A | Super Structure |  | MEP | HVAC Ducting
40710 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2024-04-15 | 2024-05-02 | Flooring & Dado | 100 | 0 |  | 2025-11-08 |  | 2025-11-25 |  | Tower A | Super Structure |  | Finishes | Flooring & Dado
40832 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | FAPA Cabling - MEP & Finishes | 2024-07-05 | 2024-07-18 | FAPA Cabling | 100 | 0 |  | 2025-11-08 |  | 2025-11-20 |  | Tower A | Super Structure
9547 | T-16-10th Floor | Not Ready | RCC | 2025-11-26 | 2025-11-26 | Slab& Beam RCC | 387 | 0 | CUM | 2025-11-09 |  | 2025-11-12
9671 | T-16-3rd Floor Flat Area | Not Ready | Toilet flooring | 2025-12-06 | 2026-01-08 | Toilet flooring | 100 | 0 |  | 2025-11-09 |  | 2025-12-14
10195 | T-21-3rd Floor Flat Area | Not Ready | Window | 2025-11-13 | 2025-12-04 | Window | 100 | 0 |  | 2025-11-09 |  | 2025-12-04
11319 | T-19-6th Floor Common Area | Not Ready | Plastering | 2025-11-22 | 2025-12-25 | Plastering-Gypsum | 100 | 0 |  | 2025-11-09 |  | 2025-12-15
11332 | T-19-7th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-11-21 | 2025-12-08 | Electrical DB Fixing | 100 | 0 |  | 2025-11-09 |  | 2025-11-28
11828 | T-18-6th Floor Flat Area | Not Ready | Dado | 2026-01-20 | 2026-02-17 | Dado | 100 | 0 |  | 2025-11-09 |  | 2025-12-06
8493 | T-14-Terrace | Not Ready | Shuttering | 2025-10-05 | 2025-10-08 | Slab and Beam Shuttering | 3605 | 0 | Sqm | 2025-11-10 |  | 2025-11-15
8729 | T-14-8th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-10-05 | 2025-10-27 | Plumbing Pipe Line | 100 | 0 |  | 2025-11-10 |  | 2025-12-02
9203 | T-15-5th Floor Flat Area | Not Ready | Toilet flooring | 2025-11-07 | 2025-12-10 | Toilet flooring | 100 | 0 |  | 2025-11-10 |  | 2025-12-14
9290 |  | Not Ready |  | 2025-11-15 | 2026-06-22 | Common Area | 100 | 0 |  | 2025-11-10 |  | 2026-06-16
9316 |  | Not Ready |  | 2025-11-15 | 2026-07-13 | Common Area | 100 | 0 |  | 2025-11-10 |  | 2026-07-08
9648 | T-16-2nd Floor Flat Area | Not Ready | Putty | 2025-12-10 | 2026-03-04 | Putty | 100 | 0 |  | 2025-11-10 |  | 2026-02-02
9718 | T-16-5th Floor Flat Area | Not Ready | Plastering | 2025-11-28 | 2025-12-19 | Plastering-Cement | 100 | 0 |  | 2025-11-10 |  | 2025-12-01
10767 | T-20-5th Floor Flat Area | Not Ready | Window | 2025-12-24 | 2026-01-14 | Window | 100 | 0 |  | 2025-11-10 |  | 2025-12-04
11118 | T-19-Terrace | Not Ready | Conduiting | 2025-11-22 | 2025-11-26 | Conduiting works | 100 | 0 |  | 2025-11-10 |  | 2025-11-14
11758 | T-18-3rd Floor Flat Area | Not Ready | 1st Coat Painting | 2026-01-21 | 2026-04-15 | 1st Coat Painting | 100 | 0 |  | 2025-11-10 |  | 2026-02-02
11804 | T-18-5th Floor Flat Area | Not Ready | Toilets False Celing | 2026-01-19 | 2026-02-21 | Toilets False Celing | 100 | 0 |  | 2025-11-10 |  | 2025-12-11
11857 | T-18-7th Floor Flat Area | Not Ready | Flooring & skirting | 2026-01-23 | 2026-03-09 | Flooring & skirting | 100 | 0 |  | 2025-11-10 |  | 2025-12-22
40523 | Tower A - Super Structure - Finishes & MEP - L49 to L50 | Not Ready | Gypsum Plastering Works | 2025-10-17 | 2025-11-10 | L49-50 | 100 | 0 |  | 2025-11-10 |  | 2025-12-02 |  | Tower A | Super Structure | L49 | Finishes | Gypsum Plastering Works
40523 | Tower A - Super Structure - Finishes & MEP - L49 to L50 | Not Ready | Gypsum Plastering Works | 2025-10-17 | 2025-11-10 | L49-50 | 100 | 0 |  | 2025-11-10 |  | 2025-12-02 |  | Tower A | Super Structure | L49
41193 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-04-02 | 2025-04-07 | Lobby Plastering | 100 | 0 |  | 2025-11-10 |  | 2025-11-14 |  | Tower A | Super Structure | L15 | Finishes | Lobby Plastering
41208 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-04-02 | 2025-04-04 | Lobby Blockwork | 100 | 0 |  | 2025-11-10 |  | 2025-11-12 |  | Tower A | Super Structure | L16 | Finishes | Blockwork
42443 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-03-03 | 2025-03-10 | Door & Window Frame work | 100 | 0 |  | 2025-11-10 |  | 2025-11-18 |  | Tower A | Super Structure | L20 | Finishes | Door & Window Frame work
42974 |  | Not Committed |  | 2025-10-17 | 2026-08-29 | L50-51 (MEP Transfer) | 100 | 0 |  | 2025-11-10 |  | 2026-08-11
42975 |  | Not Committed |  | 2025-10-17 | 2025-10-31 | MEP 1st Fixes | 100 | 0 |  | 2025-11-10 |  | 2025-11-22
42976 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2025-10-17 | 2025-10-25 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-11-10 |  | 2025-11-17 |  | Tower A | Super Structure | L50 | MEP | FPS 1st Fix - MEP & Finishes
42977 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-10-17 | 2025-10-23 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2025-11-10 |  | 2025-11-14 |  | Tower A | Super Structure | L50 | MEP | Electrical 1st Fixes
42978 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2025-10-17 | 2025-10-25 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2025-11-10 |  | 2025-11-17 |  | Tower A | Super Structure | L50
42979 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2025-10-17 | 2025-10-17 | Wet Area Waterproofing | 100 | 0 |  | 2025-11-10 |  | 2025-11-10 |  | Tower A | Super Structure | L50
8612 | T-14-3rd Floor Flat Area | Not Ready | 1st Coat Painting | 2025-10-18 | 2026-01-10 | 1st Coat Painting | 100 | 0 |  | 2025-11-11 |  | 2026-01-31
8660 | T-14-5th Floor Flat Area | Not Ready | Putty | 2025-10-14 | 2026-01-06 | Putty | 100 | 0 |  | 2025-11-11 |  | 2026-02-03
9276 | T-15-8th Floor Flat Area | Not Ready | Plastering | 2025-11-13 | 2025-12-05 | Plastering-Cement | 100 | 0 |  | 2025-11-11 |  | 2025-12-01
9302 | T-15-9th Floor Flat Area | Not Ready | Plastering | 2025-11-13 | 2025-12-05 | Plastering-Cement | 100 | 0 |  | 2025-11-11 |  | 2025-12-01
10369 | T-21-10th Floor Flat Area | Not Ready | Waterproofing | 2025-12-11 | 2026-01-13 | Waterproofing | 100 | 0 |  | 2025-11-11 |  | 2025-12-15
11117 | T-19-Terrace | Not Ready | Shear Walls/Corewalls Shuttering | 2025-11-24 | 2025-11-28 | Shear Walls/Corewalls Shuttering | 100 | 0 |  | 2025-11-11 |  | 2025-11-15
11151 | T-19-GF Flat Area | Not Ready | 1st Coat Painting | 2025-11-28 | 2026-01-17 | 1st Coat Painting | 100 | 0 |  | 2025-11-11 |  | 2026-01-03
41622 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2025-11-11 | 2025-11-13 | FAPA Cabling | 100 | 0 |  | 2025-11-11 |  | 2025-11-12 |  | Tower A | Super Structure | L42
42390 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-10-22 | 2025-11-07 | Flooring & Dado works | 100 | 0 |  | 2025-11-11 |  | 2025-11-28 |  | Tower A | Super Structure | L17 | Finishes | Flooring & Dado
42516 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-11-26 | 2025-12-12 | Flooring & Dado works | 100 | 0 |  | 2025-11-11 |  | 2025-11-28 |  | Tower A | Super Structure | L24 | Finishes | Flooring & Dado
42944 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-10-18 | 2025-10-30 | Cement Plastering in wet areas | 100 | 0 |  | 2025-11-11 |  | 2025-11-21 |  | Tower A | Super Structure | L48
8494 | T-14-Terrace | Not Ready | Slab& Beam Steel & Conduting | 2025-10-07 | 2025-10-10 | Slab& Beam Steel & Conduting | 10 | 0 | MT | 2025-11-12 |  | 2025-11-14
8540 | T-14-GF Common Area | Not Ready | Door | 2025-10-18 | 2025-11-11 | Door | 100 | 0 |  | 2025-11-12 |  | 2025-12-05
8584 | T-14-2nd Floor Flat Area | Not Ready | Door | 2025-10-21 | 2025-11-14 | Door | 100 | 0 |  | 2025-11-12 |  | 2025-12-04
8733 | T-14-8th Floor Flat Area | Not Ready | Plastering | 2025-10-07 | 2025-11-22 | Plastering-Gypsum | 100 | 0 |  | 2025-11-12 |  | 2025-12-26
9206 | T-15-5th Floor Flat Area | Not Ready | Putty | 2025-11-14 | 2026-02-06 | Putty | 100 | 0 |  | 2025-11-12 |  | 2026-02-03
9733 | T-16-5th Floor Common Area | Not Ready | Plastering | 2025-11-30 | 2026-01-01 | Plastering-Gypsum | 100 | 0 |  | 2025-11-12 |  | 2025-12-18
10322 | T-21-8th Floor Flat Area | Not Ready | Toilets False Celing | 2025-12-15 | 2026-01-17 | Toilets False Celing | 100 | 0 |  | 2025-11-12 |  | 2025-12-15
10348 | T-21-9th Floor Flat Area | Not Ready | Toilets False Celing | 2025-12-15 | 2026-01-17 | Toilets False Celing | 100 | 0 |  | 2025-11-12 |  | 2025-12-15
10392 | T-21-11th Floor Flat Area | Not Ready | Blockwork | 2025-12-09 | 2025-12-31 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-11-12 |  | 2025-12-03
40364 | Tower A - Super Structure - Finishes & MEP - L51 to L52 | Not Ready | Partition Wall-Blockwork | 2025-10-21 | 2025-10-25 | Staircase Area | 100 | 0 |  | 2025-11-12 |  | 2025-11-17 |  | Tower A | Super Structure | L51
40367 | Tower A - Super Structure - Finishes & MEP - L52 to L53 | Not Ready | Partition Wall-Blockwork | 2025-10-21 | 2025-10-28 | Partition Walls | 100 | 0 |  | 2025-11-12 |  | 2025-11-19 |  | Tower A | Super Structure | L52
41063 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2025-10-23 | 2025-10-30 | HVAC Ducting | 100 | 0 |  | 2025-11-12 |  | 2025-11-20 |  | Tower A | Super Structure | L7 | MEP | HVAC Ducting
45400 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 | Not Ready | Partition Wall-Blockwork | 2025-03-29 | 2025-04-09 | Staircase Area | 100 | 0 |  | 2025-11-12 |  | 2025-11-22 |  | Tower B | Sub Structure | B2
47661 |  | Not Committed |  | 2024-12-16 | 2025-01-14 | Pour 12 (PB-A to PB-E) | 100 | 0 |  | 2025-11-12 |  | 2025-12-10
47662 |  | Not Ready |  | 2024-12-16 | 2025-01-02 | Columns/ Walls_NTA | 100 | 0 |  | 2025-11-12 |  | 2025-11-28
47662 |  | Not Ready |  | 2024-12-16 | 2025-01-02 | Columns/ Walls_NTA | 100 | 0 |  | 2025-11-12 |  | 2025-11-28 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
9291 | T-15-8th Floor Common Area | Not Ready | Plastering | 2025-11-15 | 2025-12-18 | Plastering-Gypsum | 100 | 0 |  | 2025-11-13 |  | 2025-12-17
9317 | T-15-9th Floor Common Area | Not Ready | Plastering | 2025-11-15 | 2025-12-18 | Plastering-Gypsum | 100 | 0 |  | 2025-11-13 |  | 2025-12-17
9573 | T-16-Basement Floor | Not Ready | 1st Coat Painting | 2025-11-20 | 2025-12-23 | 1st Coat Painting | 100 | 0 |  | 2025-11-13 |  | 2025-12-15
9699 | T-16-4th Floor Flat Area | Not Ready | Flooring & skirting | 2025-12-05 | 2026-01-19 | Flooring & skirting | 100 | 0 |  | 2025-11-13 |  | 2025-12-29
9742 | T-16-6th Floor Flat Area | Not Ready | Blockwork | 2025-11-27 | 2025-12-18 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-11-13 |  | 2025-12-04
9781 | T-16-7th Floor Flat Area | Not Ready | Railing | 2025-11-27 | 2025-12-29 | Balcony Railing | 100 | 0 |  | 2025-11-13 |  | 2025-12-17
10841 | T-20-8th Floor Flat Area | Not Ready | Toilet flooring | 2025-12-17 | 2026-01-20 | Toilet flooring | 100 | 0 |  | 2025-11-13 |  | 2025-12-14
10867 | T-20-9th Floor Flat Area | Not Ready | Toilet flooring | 2025-12-17 | 2026-01-20 | Toilet flooring | 100 | 0 |  | 2025-11-13 |  | 2025-12-14
11257 | T-19-4th Floor Flat Area | Not Ready | Toilet flooring | 2025-11-29 | 2026-01-01 | Toilet flooring | 100 | 0 |  | 2025-11-13 |  | 2025-12-17
11285 | T-19-5th Floor Flat Area | Not Ready | Flooring & skirting | 2025-11-28 | 2026-01-10 | Flooring & skirting | 100 | 0 |  | 2025-11-13 |  | 2025-12-27
11890 |  | Not Ready |  | 2026-01-17 | 2026-08-24 | Common Area | 100 | 0 |  | 2025-11-13 |  | 2026-06-24
11916 |  | Not Ready |  | 2026-01-17 | 2026-09-15 | Common Area | 100 | 0 |  | 2025-11-13 |  | 2026-07-16
41209 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-04-05 | 2025-04-10 | Lobby Plastering | 100 | 0 |  | 2025-11-13 |  | 2025-11-18 |  | Tower A | Super Structure | L16 | Finishes | Lobby Plastering
41224 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-04-05 | 2025-04-08 | Lobby Blockwork | 100 | 0 |  | 2025-11-13 |  | 2025-11-15 |  | Tower A | Super Structure | L17 | Finishes | Blockwork
41635 |  | Started |  | 2025-11-13 | 2026-05-23 | L43-44 | 100 | 25 |  | 2025-11-13 | 2025-11-13 | 2026-06-15 |  |  |  |  | Finishes | Gypsum Plastering Works
41635 |  | Started |  | 2025-11-13 | 2026-05-23 | L43-44 | 100 | 25 |  | 2025-11-13 | 2025-11-13 | 2026-06-15
41636 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Started | FPS 1st Fix - MEP & Finishes | 2025-11-13 | 2025-11-17 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 40 |  | 2025-11-13 | 2025-11-13 | 2026-05-04 |  | Tower A | Super Structure | L43 | MEP | FPS 1st Fix - MEP & Finishes
41637 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-11-13 | 2025-11-17 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-11-13 |  | 2025-11-15 |  | Tower A | Super Structure | L43 | MEP | Electrical 1st Fixes
42588 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-12-13 | 2025-12-31 | Flooring & Dado works | 100 | 0 |  | 2025-11-13 |  | 2025-12-01 |  | Tower A | Super Structure | L28 | Finishes | Flooring & Dado
44075 | Tower A - Super Structure - Finishes & MEP - L28 to L33 | Started | Façade Works - MEP & Finishes | 2025-12-13 | 2025-12-24 | Accessories & Alignment | 100 | 20 | Units | 2025-11-13 | 2025-09-09 | 2025-11-25 |  | Tower A | Super Structure | L28 | Façade | Façade Works
44075 | Tower A - Super Structure - Finishes & MEP - L28 to L33 | Started | Façade Works - MEP & Finishes | 2025-12-13 | 2025-12-24 | Accessories & Alignment | 100 | 20 | Units | 2025-11-13 | 2025-09-09 | 2025-11-25 |  | Tower A | Super Structure | L28
9158 | T-15-3rd Floor Flat Area | Not Ready | 1st Coat Painting | 2025-11-19 | 2026-02-10 | 1st Coat Painting | 100 | 0 |  | 2025-11-14 |  | 2026-02-06
9228 | T-15-6th Floor Flat Area | Not Ready | Dado | 2025-11-18 | 2025-12-15 | Dado | 100 | 0 |  | 2025-11-14 |  | 2025-12-12
9251 | T-15-7th Floor Flat Area | Not Ready | Waterproofing | 2025-11-15 | 2025-12-18 | Waterproofing | 100 | 0 |  | 2025-11-14 |  | 2025-12-18
9549 | T-16-11th Floor | Not Ready | AL - Shear Walls/Corewalls Steel | 2025-11-28 | 2025-12-02 | AL - Shear Walls/Corewalls Steel | 25 | 0 | MT | 2025-11-14 |  | 2025-11-20
9810 |  | Not Ready |  | 2026-01-12 | 2026-08-19 | Common Area | 100 | 0 |  | 2025-11-14 |  | 2026-06-20
9836 |  | Not Ready |  | 2026-01-12 | 2026-09-09 | Common Area | 100 | 0 |  | 2025-11-14 |  | 2026-07-13
10396 | T-21-11th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-12-11 | 2025-12-27 | Electrical DB Fixing | 100 | 0 |  | 2025-11-14 |  | 2025-12-01
11119 | T-19-Terrace | Not Ready | Shuttering | 2025-11-27 | 2025-12-01 | Slab and Beam Shuttering | 3548 | 0 | Sqm | 2025-11-14 |  | 2025-11-19
11329 | T-19-7th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-11-27 | 2025-12-19 | Plumbing Pipe Line | 100 | 0 |  | 2025-11-14 |  | 2025-12-05
11686 | T-18-GF Common Area | Not Ready | Door | 2026-01-05 | 2026-01-29 | Door | 100 | 0 |  | 2025-11-14 |  | 2025-12-06
11704 | T-18-1st Floor Flat Area | Not Ready | Door | 2026-01-08 | 2026-02-01 | Door | 100 | 0 |  | 2025-11-14 |  | 2025-12-04
39741 | Tower A - Super Structure - Core Wall High Rise L72-73 | Complete | Core Wall RCC Works | 2025-10-23 | 2025-10-23 | Casting | 100 | 100 |  | 2025-11-14 | 2025-11-28 | 2025-11-15 | 2025-11-28 | Tower A | Super Structure | L72 | RCC Super Structure | Core Wall RCC Works
40007 |  | Not Ready |  | 2025-10-21 | 2025-10-27 | L68-69 | 100 | 0 |  | 2025-11-14 |  | 2025-11-26
40007 |  | Not Ready |  | 2025-10-21 | 2025-10-27 | L68-69 | 100 | 0 |  | 2025-11-14 |  | 2025-11-26 |  |  |  |  | Finishes | Gypsum Plastering Works
40008 | Tower A - Super Structure - Core & Outer Slab L68-69 | Not Ready | RCC Works - Vertical | 2025-10-21 | 2025-10-27 | Outer Columns_TA | 100 | 0 |  | 2025-11-14 |  | 2025-11-24 |  | Tower A | Super Structure | L68 | RCC Sub Structure | RCC Works - Vertical
40417 |  | Not Committed |  | 2025-10-21 | 2026-02-19 | L65-66 | 100 | 0 |  | 2025-11-14 |  | 2026-03-14
40417 |  | Not Committed |  | 2025-10-21 | 2026-02-19 | L65-66 | 100 | 0 |  | 2025-11-14 |  | 2026-03-14 |  |  |  |  | Finishes | Gypsum Plastering Works
40418 | Tower A - Super Structure - Finishes & MEP - L65 to L66 | Not Ready | Partition Wall-Blockwork | 2025-10-21 | 2025-11-06 | De-shuttering & Area clearance | 100 | 0 |  | 2025-11-14 |  | 2025-12-02 |  | Tower A | Super Structure | L65
40603 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2024-05-03 | 2024-05-11 | Final Painting | 100 | 0 |  | 2025-11-14 |  | 2025-11-22 |  | Tower A | Sub Structure | B3 | Finishes | Final Painting
40603 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2024-05-03 | 2024-05-11 | Final Painting | 100 | 0 |  | 2025-11-14 |  | 2025-11-22 |  | Tower A | Sub Structure | B3 | Finishes | Final Painting
40603 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2024-05-03 | 2024-05-11 | Final Painting | 100 | 0 |  | 2025-11-14 |  | 2025-11-22 |  | Tower A | Sub Structure | B3 | Finishes | Final Painting
40682 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2024-04-20 | 2024-04-23 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2025-11-14 |  | 2025-11-17 |  | Tower A | Super Structure | GF | MEP | FPS 2nd Fix - MEP & Finishes
40683 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2024-04-20 | 2024-04-25 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2025-11-14 |  | 2025-11-19 |  | Tower A | Super Structure | GF | MEP | Electrical 2nd Fix - MEP & Finishes
40684 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-04-20 | 2024-04-27 | FAPA Device Fixing | 100 | 0 |  | 2025-11-14 |  | 2025-11-21 |  | Tower A | Super Structure | GF
40684 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-04-20 | 2024-04-27 | FAPA Device Fixing | 100 | 0 |  | 2025-11-14 |  | 2025-11-21 |  | Tower A | Super Structure | GF
40684 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-04-20 | 2024-04-27 | FAPA Device Fixing | 100 | 0 |  | 2025-11-14 |  | 2025-11-21 |  | Tower A | Super Structure | GF
40684 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-04-20 | 2024-04-27 | FAPA Device Fixing | 100 | 0 |  | 2025-11-14 |  | 2025-11-21 |  | Tower A | Super Structure | GF
40685 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2024-04-20 | 2024-04-23 | HVAC Grill Fixing | 100 | 0 |  | 2025-11-14 |  | 2025-11-17 |  | Tower A | Super Structure | GF | MEP | HVAC Grill Fixing
42927 |  | Not Committed |  | 2025-10-23 | 2026-03-13 | Finishes after 1st Fix | 100 | 0 |  | 2025-11-14 |  | 2026-02-11
42928 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-10-23 | 2025-11-14 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-11-14 |  | 2025-12-06 |  | Tower A | Super Structure | L47 | Finishes | Blockwork
8495 | T-14-Terrace | Not Ready | RCC | 2025-10-10 | 2025-10-11 | Slab& Beam RCC | 307 | 0 | CUM | 2025-11-15 |  | 2025-11-15
8658 | T-14-5th Floor Flat Area | Not Ready | Toilets False Celing | 2025-10-16 | 2025-11-20 | Toilets False Celing | 100 | 0 |  | 2025-11-15 |  | 2025-12-20
9088 | T-15-GF Common Area | Not Ready | 1st Coat Painting | 2025-11-14 | 2026-01-02 | 1st Coat Painting | 100 | 0 |  | 2025-11-15 |  | 2026-01-02
9130 | T-15-2nd Floor Flat Area | Not Ready | Door | 2025-11-23 | 2025-12-15 | Door | 100 | 0 |  | 2025-11-15 |  | 2025-12-07
9693 | T-16-4th Floor Flat Area | Not Ready | Waterproofing | 2025-12-05 | 2026-01-24 | Waterproofing | 100 | 0 |  | 2025-11-15 |  | 2026-01-05
9746 | T-16-6th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-11-29 | 2025-12-15 | Electrical DB Fixing | 100 | 0 |  | 2025-11-15 |  | 2025-12-04
10306 | T-21-7th Floor Common Area | Not Ready | Flooring & skirting | 2025-12-19 | 2026-01-09 | Flooring & skirting | 100 | 0 |  | 2025-11-15 |  | 2025-12-07
39742 | Tower A - Super Structure - Core Wall High Rise L72-73 | Not Ready | Core Wall RCC Works | 2025-10-24 | 2025-10-24 | ACS Form Release & jump to next level | 100 | 0 |  | 2025-11-15 |  | 2025-11-17 |  | Tower A | Super Structure | L72 | RCC Super Structure | Core Wall RCC Works
8754 | T-14-9th Floor Flat Area | Not Ready | Blockwork | 2025-10-11 | 2025-11-05 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-11-16 |  | 2025-12-12
8793 | T-14-10th Floor Flat Area | Not Ready | Railing | 2025-10-11 | 2025-11-15 | Balcony Railing | 100 | 0 |  | 2025-11-16 |  | 2025-12-21
9551 | T-16-11th Floor | Not Ready | Conduiting | 2025-11-30 | 2025-12-03 | Conduiting works | 100 | 0 |  | 2025-11-16 |  | 2025-11-21
9626 | T-16-1st Floor Flat Area | Not Ready | 1st Coat Painting | 2025-12-17 | 2026-03-11 | 1st Coat Painting | 100 | 0 |  | 2025-11-16 |  | 2026-02-07
9674 | T-16-3rd Floor Flat Area | Not Ready | Putty | 2025-12-13 | 2026-03-07 | Putty | 100 | 0 |  | 2025-11-16 |  | 2026-02-08
10375 | T-21-10th Floor Flat Area | Not Ready | Flooring & skirting | 2025-12-17 | 2026-01-31 | Flooring & skirting | 100 | 0 |  | 2025-11-16 |  | 2025-12-28
10800 | T-20-6th Floor Common Area | Not Ready | Flooring & skirting | 2025-12-14 | 2026-01-05 | Flooring & skirting | 100 | 0 |  | 2025-11-16 |  | 2025-12-07
10844 | T-20-8th Floor Flat Area | Not Ready | Putty | 2025-12-20 | 2026-03-14 | Putty | 100 | 0 |  | 2025-11-16 |  | 2026-02-07
10870 | T-20-9th Floor Flat Area | Not Ready | Putty | 2025-12-20 | 2026-03-14 | Putty | 100 | 0 |  | 2025-11-16 |  | 2026-02-07
11120 | T-19-Terrace | Not Ready | Slab& Beam Steel & Conduting | 2025-11-29 | 2025-12-02 | Slab& Beam Steel & Conduting | 11.3 | 0 | MT | 2025-11-16 |  | 2025-11-19
11183 | T-19-1st Floor Flat Area | Not Ready | Window | 2025-12-06 | 2025-12-27 | Window | 100 | 0 |  | 2025-11-16 |  | 2025-12-09
11279 | T-19-5th Floor Flat Area | Not Ready | Waterproofing | 2025-11-28 | 2026-01-17 | Waterproofing | 100 | 0 |  | 2025-11-16 |  | 2026-01-08
11333 | T-19-7th Floor Flat Area | Not Ready | Plastering | 2025-11-29 | 2026-01-12 | Plastering-Gypsum | 100 | 0 |  | 2025-11-16 |  | 2026-01-01
11829 | T-18-6th Floor Flat Area | Not Ready | Toilet flooring | 2026-01-29 | 2026-03-02 | Toilet flooring | 100 | 0 |  | 2025-11-16 |  | 2025-12-18
8682 | T-14-6th Floor Flat Area | Not Ready | Dado | 2025-10-17 | 2025-11-15 | Dado | 100 | 0 |  | 2025-11-17 |  | 2025-12-15
8730 | T-14-8th Floor Flat Area | Not Ready | Plastering | 2025-10-13 | 2025-11-06 | Plastering-Cement | 100 | 0 |  | 2025-11-17 |  | 2025-12-11
8804 |  | Not Ready |  | 2025-11-15 | 2026-08-02 | Eleventh Floor | 100 | 0 |  | 2025-11-17 |  | 2026-08-03
8805 |  | Not Ready |  | 2025-11-15 | 2026-08-02 | Flat Area | 100 | 0 |  | 2025-11-17 |  | 2026-08-03
9550 | T-16-11th Floor | Not Ready | Shear Walls/Corewalls Shuttering | 2025-12-01 | 2025-12-05 | Shear Walls/Corewalls Shuttering | 100 | 0 |  | 2025-11-17 |  | 2025-11-20
9672 | T-16-3rd Floor Flat Area | Not Ready |  | 2025-12-15 | 2026-01-18 | Toilets False Celing | 100 | 0 |  | 2025-11-17 |  | 2025-12-22
10196 | T-21-3rd Floor Flat Area | Not Ready | Door | 2025-11-21 | 2025-12-13 | Door | 100 | 0 |  | 2025-11-17 |  | 2025-12-09
11166 | T-19-GF Common Area | Not Ready | Door | 2025-12-09 | 2025-12-31 | Door | 100 | 0 |  | 2025-11-17 |  | 2025-12-11
11260 | T-19-4th Floor Flat Area | Not Ready | Putty | 2025-12-06 | 2026-02-27 | Putty | 100 | 0 |  | 2025-11-17 |  | 2026-02-09
11430 |  | Not Ready |  | 2026-01-05 | 2026-10-08 | Eleventh Floor | 100 | 0 |  | 2025-11-17 |  | 2026-08-19
11431 |  | Not Ready |  | 2026-01-05 | 2026-10-08 | Flat Area | 100 | 0 |  | 2025-11-17 |  | 2026-08-19
11877 | T-18-8th Floor Flat Area | Not Ready | Waterproofing | 2026-02-02 | 2026-03-06 | Waterproofing | 100 | 0 |  | 2025-11-17 |  | 2025-12-19
11903 | T-18-9th Floor Flat Area | Not Ready | Waterproofing | 2026-02-02 | 2026-03-06 | Waterproofing | 100 | 0 |  | 2025-11-17 |  | 2025-12-19
39743 |  | Not Ready |  | 2025-10-25 | 2025-11-01 | Core Wall L73-74 | 100 | 0 |  | 2025-11-17 |  | 2025-11-28
39744 | Tower A - Super Structure - Core Wall High Rise L73-74 | Not Ready | Core Wall RCC Works | 2025-10-25 | 2025-10-25 | Scaffolding & platform | 100 | 0 |  | 2025-11-17 |  | 2025-11-18 |  | Tower A | Super Structure | L73 | RCC Super Structure | Core Wall RCC Works
41225 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-04-09 | 2025-04-14 | Lobby Plastering | 100 | 0 |  | 2025-11-17 |  | 2025-11-21 |  | Tower A | Super Structure | L17 | Finishes | Lobby Plastering
41240 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-04-09 | 2025-04-11 | Lobby Blockwork | 100 | 0 |  | 2025-11-17 |  | 2025-11-19 |  | Tower A | Super Structure | L18 | Finishes | Blockwork
41638 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2025-11-17 | 2025-11-19 | FAPA Cabling | 100 | 0 |  | 2025-11-17 |  | 2025-11-18 |  | Tower A | Super Structure | L43
42534 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-12-02 | 2025-12-18 | Flooring & Dado works | 100 | 0 |  | 2025-11-17 |  | 2025-12-04 |  | Tower A | Super Structure | L25 | Finishes | Flooring & Dado
8705 | T-14-7th Floor Flat Area | Not Ready | Waterproofing | 2025-10-15 | 2025-11-19 | Waterproofing | 100 | 0 |  | 2025-11-18 |  | 2025-12-23
8758 | T-14-9th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-10-14 | 2025-10-30 | Electrical DB Fixing | 100 | 0 |  | 2025-11-18 |  | 2025-12-05
9204 | T-15-5th Floor Flat Area | Not Ready | Toilets False Celing | 2025-11-17 | 2025-12-19 | Toilets False Celing | 100 | 0 |  | 2025-11-18 |  | 2025-12-21
10796 | T-20-6th Floor Flat Area | Not Ready | 1st Coat Painting | 2025-12-25 | 2026-03-19 | 1st Coat Painting | 100 | 0 |  | 2025-11-18 |  | 2026-02-10
12037 |  | Quality checked |  |  |  | RCC | 100 | 100 | Units | 2025-11-18 | 2025-11-19 | 2025-11-23 | 2025-11-20
12037 |  | Quality checked |  |  |  | RCC | 100 | 100 | Units | 2025-11-18 | 2025-11-19 | 2025-11-23 | 2025-11-20
39745 | Tower A - Super Structure - Core Wall High Rise L73-74 | Not Ready | Core Wall RCC Works | 2025-10-27 | 2025-10-29 | Reinf & Guide shoes fixing | 100 | 0 |  | 2025-11-18 |  | 2025-11-21 |  | Tower A | Super Structure | L73 | RCC Super Structure | Core Wall RCC Works
40009 | Tower A - Super Structure - Core & Outer Slab L68-69 | Not Ready | RCC Works - Slab | 2025-10-22 | 2025-10-27 | Outer Slab_TA | 100 | 0 |  | 2025-11-18 |  | 2025-11-26 |  | Tower A | Super Structure | L68 | RCC Sub Structure | RCC Works - Slab
40524 | Tower A - Super Structure - Finishes & MEP - L50 to L51 | Not Ready | Gypsum Plastering Works | 2025-10-27 | 2025-11-12 | L50-51 | 100 | 0 |  | 2025-11-18 |  | 2025-12-04 |  | Tower A | Super Structure | L50 | Finishes | Gypsum Plastering Works
40524 | Tower A - Super Structure - Finishes & MEP - L50 to L51 | Not Ready | Gypsum Plastering Works | 2025-10-27 | 2025-11-12 | L50-51 | 100 | 0 |  | 2025-11-18 |  | 2025-12-04 |  | Tower A | Super Structure | L50
40672 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2024-05-24 | 2024-06-10 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2025-11-18 |  | 2025-12-04 |  | Tower A | Sub Structure | B1
40672 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2024-05-24 | 2024-06-10 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2025-11-18 |  | 2025-12-04 |  | Tower A | Sub Structure | B1
40672 | Tower A - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2024-05-24 | 2024-06-10 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2025-11-18 |  | 2025-12-04 |  | Tower A | Sub Structure | B1
40686 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2024-04-24 | 2024-04-26 | Staircase Fire Door Fixing | 100 | 0 |  | 2025-11-18 |  | 2025-11-20 |  | Tower A | Super Structure | GF
41079 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2025-10-29 | 2025-11-05 | HVAC Ducting | 100 | 0 |  | 2025-11-18 |  | 2025-11-26 |  | Tower A | Super Structure | L8 | MEP | HVAC Ducting
42444 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-11-08 | 2025-11-25 | Flooring & Dado works | 100 | 0 |  | 2025-11-18 |  | 2025-12-05 |  | Tower A | Super Structure | L20 | Finishes | Flooring & Dado
42980 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-10-27 | 2025-10-31 | Cement Plastering in wet areas | 100 | 0 |  | 2025-11-18 |  | 2025-11-22 |  | Tower A | Super Structure | L50
42992 |  | Not Committed |  | 2025-10-27 | 2026-09-05 | L51-52 | 100 | 0 |  | 2025-11-18 |  | 2026-08-20
42992 |  | Not Committed |  | 2025-10-27 | 2026-09-05 | L51-52 | 100 | 0 |  | 2025-11-18 |  | 2026-08-20 |  |  |  |  | Finishes | Gypsum Plastering Works
42993 |  | Not Committed |  | 2025-10-27 | 2025-11-24 | MEP 1st Fixes | 100 | 0 |  | 2025-11-18 |  | 2025-12-16
42994 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2025-10-27 | 2025-11-03 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-11-18 |  | 2025-11-25 |  | Tower A | Super Structure | L51 | MEP | FPS 1st Fix - MEP & Finishes
42995 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-10-27 | 2025-10-31 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2025-11-18 |  | 2025-11-22 |  | Tower A | Super Structure | L51 | MEP | Electrical 1st Fixes
42996 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2025-10-27 | 2025-11-03 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2025-11-18 |  | 2025-11-25 |  | Tower A | Super Structure | L51
42997 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2025-10-27 | 2025-11-12 | Wet Area Waterproofing | 100 | 0 |  | 2025-11-18 |  | 2025-12-04 |  | Tower A | Super Structure | L51
44531 | NTA_Zone 2 - Super Structure - P1 to P2 | Not Ready | MEP 1st Fix Works | 2025-01-11 | 2025-01-28 | P1 to P2 | 100 | 0 |  | 2025-11-18 |  | 2025-12-04 |  | NTA_Zone 2 | Super Structure
44531 | NTA_Zone 2 - Super Structure - P1 to P2 | Not Ready | MEP 1st Fix Works | 2025-01-11 | 2025-01-28 | P1 to P2 | 100 | 0 |  | 2025-11-18 |  | 2025-12-04 |  | NTA_Zone 2 | Super Structure
44531 | NTA_Zone 2 - Super Structure - P1 to P2 | Not Ready | MEP 1st Fix Works | 2025-01-11 | 2025-01-28 | P1 to P2 | 100 | 0 |  | 2025-11-18 |  | 2025-12-04 |  | NTA_Zone 2 | Super Structure
44541 | NTA_Zone 2 - Super Structure - P2 to P3 | Not Ready | Partition Wall-Blockwork | 2024-07-03 | 2024-08-10 | P2 to P3 | 100 | 0 |  | 2025-11-18 |  | 2025-12-22 |  | NTA_Zone 2 | Super Structure
44541 | NTA_Zone 2 - Super Structure - P2 to P3 | Not Ready | Partition Wall-Blockwork | 2024-07-03 | 2024-08-10 | P2 to P3 | 100 | 0 |  | 2025-11-18 |  | 2025-12-22 |  | NTA_Zone 2 | Super Structure
44541 | NTA_Zone 2 - Super Structure - P2 to P3 | Not Ready | Partition Wall-Blockwork | 2024-07-03 | 2024-08-10 | P2 to P3 | 100 | 0 |  | 2025-11-18 |  | 2025-12-22 |  | NTA_Zone 2 | Super Structure
47623 |  | Complete |  | 2025-11-18 | 2025-12-10 | Slab_NTA | 100 | 100 |  | 2025-11-18 | 2025-11-18 | 2025-12-10 | 2025-12-10
47623 |  | Complete |  | 2025-11-18 | 2025-12-10 | Slab_NTA | 100 | 100 |  | 2025-11-18 | 2025-11-18 | 2025-12-10 | 2025-12-10 |  |  |  | RCC Sub Structure | RCC Works - Slab
8499 | T-14-Terrace | Not Ready | PARAPET | 2025-10-15 | 2025-12-05 | PARAPET | 100 | 0 |  | 2025-11-19 |  | 2026-01-08
8609 | T-14-3rd Floor Flat Area | Not Ready | Window | 2025-10-29 | 2025-11-22 | Window | 100 | 0 |  | 2025-11-19 |  | 2025-12-11
8745 | T-14-8th Floor Common Area | Not Ready | Plastering | 2025-10-15 | 2025-11-19 | Plastering-Gypsum | 100 | 0 |  | 2025-11-19 |  | 2025-12-24
9257 | T-15-7th Floor Flat Area | Not Ready | Flooring & skirting | 2025-11-21 | 2026-01-03 | Flooring & skirting | 100 | 0 |  | 2025-11-19 |  | 2025-12-31
10393 | T-21-11th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-12-17 | 2026-01-07 | Plumbing Pipe Line | 100 | 0 |  | 2025-11-19 |  | 2025-12-10
11832 | T-18-6th Floor Flat Area | Not Ready | Putty | 2026-02-01 | 2026-04-25 | Putty | 100 | 0 |  | 2025-11-19 |  | 2026-02-11
39746 | Tower A - Super Structure - Core Wall High Rise L73-74 | Not Ready | Core Wall RCC Works | 2025-10-28 | 2025-10-30 | ACS Form Closing & Alignment | 100 | 0 |  | 2025-11-19 |  | 2025-11-22 |  | Tower A | Super Structure | L73 | RCC Super Structure | Core Wall RCC Works
42893 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-10-30 | 2025-11-06 | Door & Window Frame work | 100 | 0 |  | 2025-11-19 |  | 2025-11-27 |  | Tower A | Super Structure | L45 | Finishes | Door & Window Frame work
42962 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-10-28 | 2025-11-07 | Cement Plastering in wet areas | 100 | 0 |  | 2025-11-19 |  | 2025-11-29 |  | Tower A | Super Structure | L49
8586 | T-14-2nd Floor Flat Area | Not Ready | 1st Coat Painting | 2025-11-03 | 2026-01-19 | 1st Coat Painting | 100 | 0 |  | 2025-11-20 |  | 2026-02-05
9552 | T-16-11th Floor | Not Ready | Shuttering | 2025-12-04 | 2025-12-09 | Slab and Beam Shuttering | 4183 | 0 | Sqm | 2025-11-20 |  | 2025-11-25
9743 | T-16-6th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-12-04 | 2025-12-26 | Plumbing Pipe Line | 100 | 0 |  | 2025-11-20 |  | 2025-12-11
10302 | T-21-7th Floor Flat Area | Not Ready | 1st Coat Painting | 2025-12-27 | 2026-03-21 | 1st Coat Painting | 100 | 0 |  | 2025-11-20 |  | 2026-02-12
11121 | T-19-Terrace | Not Ready | RCC | 2025-12-03 | 2025-12-03 | Slab& Beam RCC | 340 | 0 | CUM | 2025-11-20 |  | 2025-11-20
11854 | T-18-7th Floor Flat Area | Not Ready | Dado | 2026-02-04 | 2026-03-03 | Dado | 100 | 0 |  | 2025-11-20 |  | 2025-12-17
11926 | T-18-10th Floor Flat Area | Not Ready | Blockwork | 2026-01-31 | 2026-02-21 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-11-20 |  | 2025-12-11
39244 |  | Not Ready |  | 2025-05-26 | 2025-07-07 | Plum Concrete | 100 | 0 |  | 2025-11-20 |  | 2026-01-01
40368 | Tower A - Super Structure - Finishes & MEP - L52 to L53 | Not Ready | Partition Wall-Blockwork | 2025-10-29 | 2025-11-03 | Staircase Area | 100 | 0 |  | 2025-11-20 |  | 2025-11-25 |  | Tower A | Super Structure | L52
40371 | Tower A - Super Structure - Finishes & MEP - L53 to L54 | Not Ready | Partition Wall-Blockwork | 2025-10-29 | 2025-11-05 | Partition Walls | 100 | 0 |  | 2025-11-20 |  | 2025-11-27 |  | Tower A | Super Structure | L53
40711 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | False Ceiling - MEP & Finishes | 2024-04-26 | 2024-05-08 | False Ceiling | 100 | 0 |  | 2025-11-20 |  | 2025-12-01 |  | Tower A | Super Structure |  | Finishes | False Ceiling
40834 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | VDF/ Grade Slab - MEP & Finishes | 2024-07-27 | 2024-09-24 | VDF/ Grade Slab & Apt. finishes | 100 | 0 |  | 2025-11-20 |  | 2026-01-13 |  | Tower A | Super Structure
41066 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-10-31 | 2025-11-11 | Flooring & Dado | 100 | 0 |  | 2025-11-20 |  | 2025-12-02 |  | Tower A | Super Structure | L7 | Finishes | Flooring & Dado
41241 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-04-12 | 2025-04-17 | Lobby Plastering | 100 | 0 |  | 2025-11-20 |  | 2025-11-25 |  | Tower A | Super Structure | L18 | Finishes | Lobby Plastering
41256 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-04-12 | 2025-04-15 | Lobby Blockwork | 100 | 0 |  | 2025-11-20 |  | 2025-11-22 |  | Tower A | Super Structure | L19 | Finishes | Blockwork
42605 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-04-23 | 2025-04-30 | Door & Window Frame work | 100 | 0 |  | 2025-11-20 |  | 2025-11-27 |  | Tower A | Super Structure | L29 | Finishes | Door & Window Frame work
44547 | NTA_Zone 2 - Sub Structure - B3 to B2 | Not Ready | Finishes (Lobby & Floor Area) | 2024-06-21 | 2024-07-16 | MEP Rooms - Plaster & IPS | 100 | 0 |  | 2025-11-20 |  | 2025-12-12 |  | NTA_Zone 2 | Sub Structure | B3
44547 | NTA_Zone 2 - Sub Structure - B3 to B2 | Not Ready | Finishes (Lobby & Floor Area) | 2024-06-21 | 2024-07-16 | MEP Rooms - Plaster & IPS | 100 | 0 |  | 2025-11-20 |  | 2025-12-12 |  | NTA_Zone 2 | Sub Structure | B3
44548 | NTA_Zone 2 - Sub Structure - B3 to B2 | Not Ready | Finishes (Lobby & Floor Area) | 2024-06-21 | 2024-07-29 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2025-11-20 |  | 2025-12-24 |  | NTA_Zone 2 | Sub Structure | B3
44548 | NTA_Zone 2 - Sub Structure - B3 to B2 | Not Ready | Finishes (Lobby & Floor Area) | 2024-06-21 | 2024-07-29 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2025-11-20 |  | 2025-12-24 |  | NTA_Zone 2 | Sub Structure | B3
45269 | Tower B - Super Structure - Core & Outer Slab P6-L7 | Not Ready | RCC Works - Vertical | 2025-09-13 | 2025-09-25 | Outer Columns_TA | 100 | 0 |  | 2025-11-20 |  | 2025-12-02 |  | Tower B | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
45428 | Tower B - Super Structure - Finishes & MEP - P5 to P6 | Not Ready | Partition Wall-Blockwork | 2025-09-13 | 2025-09-25 | Staircase Area | 100 | 0 |  | 2025-11-20 |  | 2025-12-02 |  | Tower B | Super Structure
8497 | T-14-Terrace | Not Ready | LMR ROOM | 2025-10-17 | 2025-12-07 | LMR ROOM | 100 | 0 |  | 2025-11-21 |  | 2026-01-12
8500 | T-14-Terrace | Not Ready | STAIRCASE HR | 2025-10-17 | 2025-12-07 | STAIRCASE HR | 100 | 0 |  | 2025-11-21 |  | 2026-01-12
9229 | T-15-6th Floor Flat Area | Not Ready | Toilet flooring | 2025-11-25 | 2025-12-27 | Toilet flooring | 100 | 0 |  | 2025-11-21 |  | 2025-12-22
9588 | T-16-GF Flat Area | Not Ready | Window | 2025-12-12 | 2026-01-02 | Window | 100 | 0 |  | 2025-11-21 |  | 2025-12-17
10397 | T-21-11th Floor Flat Area | Not Ready | Plastering | 2025-12-19 | 2026-02-03 | Plastering-Gypsum | 100 | 0 |  | 2025-11-21 |  | 2026-01-03
10768 | T-20-5th Floor Flat Area | Not Ready | Door | 2026-01-05 | 2026-01-29 | Door | 100 | 0 |  | 2025-11-21 |  | 2025-12-13
10842 | T-20-8th Floor Flat Area | Not Ready | Toilets False Celing | 2025-12-26 | 2026-01-30 | Toilets False Celing | 100 | 0 |  | 2025-11-21 |  | 2025-12-24
10868 | T-20-9th Floor Flat Area | Not Ready | Toilets False Celing | 2025-12-26 | 2026-01-30 | Toilets False Celing | 100 | 0 |  | 2025-11-21 |  | 2025-12-24
10889 | T-20-10th Floor Flat Area | Not Ready | Waterproofing | 2025-12-23 | 2026-01-27 | Waterproofing | 100 | 0 |  | 2025-11-21 |  | 2025-12-24
11258 | T-19-4th Floor Flat Area | Not Ready | Toilets False Celing | 2025-12-08 | 2026-01-09 | Toilets False Celing | 100 | 0 |  | 2025-11-21 |  | 2025-12-26
11330 | T-19-7th Floor Flat Area | Not Ready | Plastering | 2025-12-05 | 2025-12-26 | Plastering-Cement | 100 | 0 |  | 2025-11-21 |  | 2025-12-17
11354 | T-19-8th Floor Flat Area | Not Ready | Blockwork | 2025-12-04 | 2025-12-25 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-11-21 |  | 2025-12-17
11380 | T-19-9th Floor Flat Area | Not Ready | Blockwork | 2025-12-04 | 2025-12-25 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-11-21 |  | 2025-12-17
11393 | T-19-9th Floor Flat Area | Not Ready | Railing | 2025-12-04 | 2026-01-05 | Balcony Railing | 100 | 0 |  | 2025-11-21 |  | 2025-12-26
11419 | T-19-10th Floor Flat Area | Not Ready | Railing | 2025-12-04 | 2026-01-05 | Balcony Railing | 100 | 0 |  | 2025-11-21 |  | 2025-12-26
40687 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2024-04-27 | 2024-05-03 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2025-11-21 |  | 2025-11-26 |  | Tower A | Super Structure | GF | MEP | Electrical
9155 | T-15-3rd Floor Flat Area | Not Ready | Window | 2025-12-01 | 2025-12-22 | Window | 100 | 0 |  | 2025-11-22 |  | 2025-12-14
9553 | T-16-11th Floor | Not Ready | Slab& Beam Steel & Conduting | 2025-12-06 | 2025-12-10 | Slab& Beam Steel & Conduting | 14 | 0 | MT | 2025-11-22 |  | 2025-11-25
9696 | T-16-4th Floor Flat Area | Not Ready | Dado | 2025-12-13 | 2026-01-09 | Dado | 100 | 0 |  | 2025-11-22 |  | 2025-12-21
9747 | T-16-6th Floor Flat Area | Not Ready | Plastering | 2025-12-06 | 2026-01-20 | Plastering-Gypsum | 100 | 0 |  | 2025-11-22 |  | 2026-01-06
11184 | T-19-1st Floor Flat Area | Not Ready | Door | 2025-12-12 | 2026-01-03 | Door | 100 | 0 |  | 2025-11-22 |  | 2025-12-15
11305 | T-19-6th Floor Flat Area | Not Ready | Waterproofing | 2025-12-07 | 2026-01-08 | Waterproofing | 100 | 0 |  | 2025-11-22 |  | 2025-12-27
11729 | T-18-2nd Floor Flat Area | Not Ready | Window | 2026-01-17 | 2026-02-10 | Window | 100 | 0 |  | 2025-11-22 |  | 2025-12-16
11883 | T-18-8th Floor Flat Area | Not Ready | Flooring & skirting | 2026-02-07 | 2026-03-23 | Flooring & skirting | 100 | 0 |  | 2025-11-22 |  | 2026-01-07
11909 | T-18-9th Floor Flat Area | Not Ready | Flooring & skirting | 2026-02-07 | 2026-03-23 | Flooring & skirting | 100 | 0 |  | 2025-11-22 |  | 2026-01-07
11930 | T-18-10th Floor Flat Area | Not Ready | Electrical DB Fixing | 2026-02-02 | 2026-02-18 | Electrical DB Fixing | 100 | 0 |  | 2025-11-22 |  | 2025-12-06
42552 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-12-08 | 2025-12-24 | Flooring & Dado works | 100 | 0 |  | 2025-11-22 |  | 2025-12-10 |  | Tower A | Super Structure | L26 | Finishes | Flooring & Dado
42945 |  | Not Committed |  | 2025-10-31 | 2026-03-19 | Finishes after 1st Fix | 100 | 0 |  | 2025-11-22 |  | 2026-02-17
42946 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-10-31 | 2025-11-22 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-11-22 |  | 2025-12-15 |  | Tower A | Super Structure | L48 | Finishes | Blockwork
8502 |  | Not Ready |  | 2025-10-19 | 2025-11-07 | Lowering Aluminium FW Material For PH-2 | 100 | 0 |  | 2025-11-23 |  | 2025-12-10
8711 | T-14-7th Floor Flat Area | Not Ready | Flooring & skirting | 2025-10-20 | 2025-12-05 | Flooring & skirting | 100 | 0 |  | 2025-11-23 |  | 2026-01-06
8755 | T-14-9th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-10-19 | 2025-11-12 | Plumbing Pipe Line | 100 | 0 |  | 2025-11-23 |  | 2025-12-16
9132 | T-15-2nd Floor Flat Area | Not Ready | 1st Coat Painting | 2025-12-02 | 2026-02-18 | 1st Coat Painting | 100 | 0 |  | 2025-11-23 |  | 2026-02-10
10221 | T-21-4th Floor Flat Area | Not Ready | Window | 2025-11-28 | 2025-12-20 | Window | 100 | 0 |  | 2025-11-23 |  | 2025-12-15
10793 | T-20-6th Floor Flat Area | Not Ready | Window | 2026-01-07 | 2026-01-31 | Window | 100 | 0 |  | 2025-11-23 |  | 2025-12-15
11282 | T-19-5th Floor Flat Area | Not Ready | Dado | 2025-12-06 | 2026-01-02 | Dado | 100 | 0 |  | 2025-11-23 |  | 2025-12-22
11345 | T-19-7th Floor Common Area | Not Ready |  | 2025-12-07 | 2026-01-08 | Plastering Gypsum | 100 | 0 |  | 2025-11-23 |  | 2025-12-28
11358 | T-19-8th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-12-06 | 2025-12-22 | Electrical DB Fixing | 100 | 0 |  | 2025-11-23 |  | 2025-12-12
11384 | T-19-9th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-12-06 | 2025-12-22 | Electrical DB Fixing | 100 | 0 |  | 2025-11-23 |  | 2025-12-12
11965 | T-18-11th Floor Flat Area | Not Ready | Railing | 2026-02-03 | 2026-03-07 | Balcony Railing & Coridor Railing | 100 | 0 |  | 2025-11-23 |  | 2025-12-25
8501 | T-14-Terrace | Not Ready |  | 2025-10-20 | 2025-12-10 | MISC | 100 | 0 |  | 2025-11-24 |  | 2026-01-14
8638 | T-14-4th Floor Flat Area | Not Ready | 1st Coat Painting | 2025-11-04 | 2026-01-27 | 1st Coat Painting | 100 | 0 |  | 2025-11-24 |  | 2026-02-16
8683 | T-14-6th Floor Flat Area | Not Ready | Toilet flooring | 2025-10-24 | 2025-11-28 | Toilet flooring | 100 | 0 |  | 2025-11-24 |  | 2025-12-28
9232 | T-15-6th Floor Flat Area | Not Ready | Putty | 2025-11-28 | 2026-02-20 | Putty | 100 | 0 |  | 2025-11-24 |  | 2026-02-15
10254 | T-21-5th Floor Common Area | Not Ready | Flooring & skirting | 2025-12-24 | 2026-01-16 | Flooring & skirting | 100 | 0 |  | 2025-11-24 |  | 2025-12-12
10281 | T-21-6th Floor Common Area | Not Ready | Putty | 2025-12-24 | 2026-02-03 | Putty | 100 | 0 |  | 2025-11-24 |  | 2025-12-30
10408 |  | Not Ready |  | 2025-12-26 | 2026-08-08 | Common Area | 100 | 0 |  | 2025-11-24 |  | 2026-07-07
11125 | T-19-Terrace | Not Ready | PARAPET | 2025-12-07 | 2026-01-27 | PARAPET | 100 | 0 |  | 2025-11-24 |  | 2026-01-13
11732 | T-18-2nd Floor Flat Area | Not Ready | 1st Coat Painting | 2026-02-04 | 2026-04-23 | 1st Coat Painting | 100 | 0 |  | 2025-11-24 |  | 2026-02-09
11784 | T-18-4th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-02-05 | 2026-04-29 | 1st Coat Painting | 100 | 0 |  | 2025-11-24 |  | 2026-02-16
11830 | T-18-6th Floor Flat Area | Not Ready | Toilets False Celing | 2026-02-06 | 2026-03-11 | Toilets False Celing | 100 | 0 |  | 2025-11-24 |  | 2025-12-25
40604 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2024-05-13 | 2024-05-29 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2025-11-24 |  | 2025-12-10 |  | Tower A | Sub Structure | B3
40604 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2024-05-13 | 2024-05-29 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2025-11-24 |  | 2025-12-10 |  | Tower A | Sub Structure | B3
40604 | Tower A - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2024-05-13 | 2024-05-29 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2025-11-24 |  | 2025-12-10 |  | Tower A | Sub Structure | B3
40697 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2024-06-29 | 2024-07-06 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2025-11-24 |  | 2025-12-01 |  | Tower A | Super Structure | GF | MEP | FPS 2nd Fix - MEP & Finishes
40874 | Tower A - Super Structure - Finishes & MEP - B3 to L7 | Not Ready |  | 2024-04-30 | 2024-06-04 | Electrical Rising Mains | 100 | 0 |  | 2025-11-24 |  | 2025-12-29 |  | Tower A | Super Structure | B3
40883 | Tower A - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2024-11-04 | 2024-12-07 | Electrical Rising Mains | 100 | 0 |  | 2025-11-24 |  | 2025-12-29 |  | Tower A | Super Structure | L15
40892 | Tower A - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2024-08-01 | 2024-09-10 | Electrical Rising Mains | 100 | 0 |  | 2025-11-24 |  | 2025-12-29 |  | Tower A | Super Structure | L7
40901 | Tower A - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2025-01-17 | 2025-02-08 | Electrical Rising Mains | 100 | 0 |  | 2025-11-24 |  | 2025-12-16 |  | Tower A | Super Structure | L25
40910 | Tower A - Super Structure - Finishes & MEP - L35 to L45 | Not Ready |  | 2025-04-16 | 2025-05-09 | Electrical Rising Mains | 100 | 0 |  | 2025-11-24 |  | 2025-12-16 |  | Tower A | Super Structure | L35
40919 | Tower A - Super Structure - Finishes & MEP - L45 to L55 | Not Ready |  | 2025-09-03 | 2025-09-26 | Electrical Rising Mains | 100 | 0 |  | 2025-11-24 |  | 2025-12-16 |  | Tower A | Super Structure | L45
41095 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2025-11-04 | 2025-11-11 | HVAC Ducting | 100 | 0 |  | 2025-11-24 |  | 2025-12-02 |  | Tower A | Super Structure | L9 | MEP | HVAC Ducting
41257 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-04-16 | 2025-04-21 | Lobby Plastering | 100 | 0 |  | 2025-11-24 |  | 2025-11-28 |  | Tower A | Super Structure | L19 | Finishes | Lobby Plastering
41272 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-04-16 | 2025-04-18 | Lobby Blockwork | 100 | 0 |  | 2025-11-24 |  | 2025-11-26 |  | Tower A | Super Structure | L20 | Finishes | Blockwork
42462 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-11-14 | 2025-12-01 | Flooring & Dado works | 100 | 0 |  | 2025-11-24 |  | 2025-12-11 |  | Tower A | Super Structure | L21 | Finishes | Flooring & Dado
42981 |  | Not Committed |  | 2025-11-01 | 2026-03-31 | Finishes after 1st Fix | 100 | 0 |  | 2025-11-24 |  | 2026-02-28
42982 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-11-01 | 2025-11-24 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-11-24 |  | 2025-12-16 |  | Tower A | Super Structure | L50 | Finishes | Blockwork
47663 |  | Not Ready |  | 2024-12-28 | 2025-01-14 | Slab_NTA | 100 | 0 |  | 2025-11-24 |  | 2025-12-10
47663 |  | Not Ready |  | 2024-12-28 | 2025-01-14 | Slab_NTA | 100 | 0 |  | 2025-11-24 |  | 2025-12-10 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
8498 | T-14-Terrace | Not Ready | OHT | 2025-10-21 | 2025-12-11 | OHT | 100 | 0 |  | 2025-11-25 |  | 2026-01-14
8542 | T-14-GF Common Area | Not Ready | 1st Coat Painting | 2025-10-29 | 2025-12-19 | 1st Coat Painting | 100 | 0 |  | 2025-11-25 |  | 2026-01-14
8759 | T-14-9th Floor Flat Area | Not Ready | Plastering | 2025-10-21 | 2025-12-06 | Plastering-Gypsum | 100 | 0 |  | 2025-11-25 |  | 2026-01-10
9350 |  | Not Ready |  | 2025-12-01 | 2026-09-01 | Eleventh Floor | 100 | 0 |  | 2025-11-25 |  | 2026-08-27
9351 |  | Not Ready |  | 2025-12-01 | 2026-09-01 | Flat Area | 100 | 0 |  | 2025-11-25 |  | 2026-08-27
10912 | T-20-11th Floor Flat Area | Not Ready | Blockwork | 2025-12-20 | 2026-01-11 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-11-25 |  | 2025-12-16
11688 | T-18-GF Common Area | Not Ready | 1st Coat Painting | 2026-01-16 | 2026-03-07 | 1st Coat Painting | 100 | 0 |  | 2025-11-25 |  | 2026-01-13
40736 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2024-05-03 | 2024-05-10 | HVAC Ducting | 100 | 0 |  | 2025-11-25 |  | 2025-12-03 |  | Tower A | Super Structure |  | MEP | HVAC Ducting
40737 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2024-05-03 | 2024-05-20 | Flooring & Dado | 100 | 0 |  | 2025-11-25 |  | 2025-12-12 |  | Tower A | Super Structure |  | Finishes | Flooring & Dado
40759 |  | Not Committed |  | 2024-05-13 | 2024-07-02 | Lobby/ Common Area | 100 | 0 |  | 2025-11-25 |  | 2026-01-15
40760 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2024-05-13 | 2024-05-20 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-11-25 |  | 2025-12-03 |  | Tower A | Super Structure |  | MEP | FPS 1st Fix - MEP & Finishes
40761 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2024-05-13 | 2024-05-15 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-11-25 |  | 2025-11-28 |  | Tower A | Super Structure |  | MEP | Electrical 1st Fixes
42911 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-11-07 | 2025-11-14 | Door & Window Frame work | 100 | 0 |  | 2025-11-25 |  | 2025-12-03 |  | Tower A | Super Structure | L46 | Finishes | Door & Window Frame work
44078 | Tower A - Super Structure - Finishes & MEP - L33 to L38 | Started | Façade Works - MEP & Finishes | 2025-12-26 | 2026-01-06 | DGU Assembly Installation | 100 | 10 | Units | 2025-11-25 | 2025-09-10 | 2025-12-06 |  | Tower A | Super Structure | L33 | Façade | Façade Works
44079 | Tower A - Super Structure - Finishes & MEP - L33 to L38 | Started | Façade Works - MEP & Finishes | 2025-12-26 | 2026-01-17 | Installation of highly reflective metal sheet | 100 | 10 | Units | 2025-11-25 | 2025-09-10 | 2025-12-18 |  | Tower A | Super Structure | L33 | Façade | Façade Works
44080 | Tower A - Super Structure - Finishes & MEP - L33 to L38 | Started | Façade Works - MEP & Finishes | 2025-12-26 | 2026-01-06 | Fixing of Backlit Laminated Glass assembly & ACP Panels | 100 | 10 | Units | 2025-11-25 | 2025-09-11 | 2025-12-06 |  | Tower A | Super Structure | L33 | Façade | Façade Works
44081 | Tower A - Super Structure - Finishes & MEP - L33 to L38 | Started | Façade Works - MEP & Finishes | 2025-12-26 | 2026-01-06 | Fixing of Louvers | 100 | 10 | Units | 2025-11-25 | 2025-09-12 | 2025-12-06 |  | Tower A | Super Structure | L33 | Façade | Façade Works
44081 | Tower A - Super Structure - Finishes & MEP - L33 to L38 | Started | Façade Works - MEP & Finishes | 2025-12-26 | 2026-01-06 | Fixing of Louvers | 100 | 10 | Units | 2025-11-25 | 2025-09-12 | 2025-12-06 |  | Tower A | Super Structure | L33
48175 | Retail - Super structure - GF to R1 - P5 | Not Ready |  | 2025-07-11 | 2025-08-07 | Slab_RT | 100 | 0 |  | 2025-11-25 |  | 2025-12-17 |  | Retail | Super Structure | GF | RCC Sub Structure | RCC Works - Slab
48175 | Retail - Super structure - GF to R1 - P5 | Not Ready |  | 2025-07-11 | 2025-08-07 | Slab_RT | 100 | 0 |  | 2025-11-25 |  | 2025-12-17 |  | Retail | Super Structure | GF
9277 | T-15-8th Floor Flat Area | Not Ready | Waterproofing | 2025-11-29 | 2026-01-01 | Waterproofing | 100 | 0 |  | 2025-11-26 |  | 2025-12-30
9303 | T-15-9th Floor Flat Area | Not Ready | Waterproofing | 2025-11-29 | 2026-01-01 | Waterproofing | 100 | 0 |  | 2025-11-26 |  | 2025-12-30
9554 | T-16-11th Floor | Not Ready | RCC | 2025-12-10 | 2025-12-11 | Slab& Beam RCC | 387 | 0 | CUM | 2025-11-26 |  | 2025-11-26
9589 | T-16-GF Flat Area | Not Ready | Door | 2025-12-17 | 2026-01-08 | Door | 100 | 0 |  | 2025-11-26 |  | 2025-12-18
9604 | T-16-GF Common Area | Not Ready | Putty | 2025-12-17 | 2026-01-08 | Putty | 100 | 0 |  | 2025-11-26 |  | 2025-12-20
10372 | T-21-10th Floor Flat Area | Not Ready | Dado | 2025-12-27 | 2026-01-25 | Dado | 100 | 0 |  | 2025-11-26 |  | 2025-12-24
10394 | T-21-11th Floor Flat Area | Not Ready | Plastering | 2025-12-24 | 2026-01-16 | Plastering-Cement | 100 | 0 |  | 2025-11-26 |  | 2025-12-16
10895 | T-20-10th Floor Flat Area | Not Ready | Flooring & skirting | 2025-12-28 | 2026-02-12 | Flooring & skirting | 100 | 0 |  | 2025-11-26 |  | 2026-01-08
11123 | T-19-Terrace | Not Ready | LMR ROOM | 2025-12-09 | 2026-01-29 | LMR ROOM | 100 | 0 |  | 2025-11-26 |  | 2026-01-15
11126 | T-19-Terrace | Not Ready | STAIRCASE HR | 2025-12-09 | 2026-01-29 | STAIRCASE HR | 100 | 0 |  | 2025-11-26 |  | 2026-01-15
39747 | Tower A - Super Structure - Core Wall High Rise L73-74 | Not Ready | Core Wall RCC Works | 2025-10-31 | 2025-10-31 | Casting | 100 | 0 |  | 2025-11-26 |  | 2025-11-27 |  | Tower A | Super Structure | L73 | RCC Super Structure | Core Wall RCC Works
40010 |  | Not Ready |  | 2025-10-28 | 2025-11-03 | L69-70 | 100 | 0 |  | 2025-11-26 |  | 2025-12-03
40010 |  | Not Ready |  | 2025-10-28 | 2025-11-03 | L69-70 | 100 | 0 |  | 2025-11-26 |  | 2025-12-03 |  |  |  |  | Finishes | Gypsum Plastering Works
40011 | Tower A - Super Structure - Core & Outer Slab L69-70 | Not Ready | RCC Works - Vertical | 2025-10-28 | 2025-11-03 | Outer Columns_TA | 100 | 0 |  | 2025-11-26 |  | 2025-12-03 |  | Tower A | Super Structure | L69 | RCC Sub Structure | RCC Works - Vertical
40421 |  | Not Committed |  | 2025-10-28 | 2026-02-27 | L66-67 | 100 | 0 |  | 2025-11-26 |  | 2026-03-23
40421 |  | Not Committed |  | 2025-10-28 | 2026-02-27 | L66-67 | 100 | 0 |  | 2025-11-26 |  | 2026-03-23 |  |  |  |  | Finishes | Gypsum Plastering Works
40422 | Tower A - Super Structure - Finishes & MEP - L66 to L67 | Not Ready | Partition Wall-Blockwork | 2025-10-28 | 2025-11-13 | De-shuttering & Area clearance | 100 | 0 |  | 2025-11-26 |  | 2025-12-13 |  | Tower A | Super Structure | L66
40475 | Tower A - Super Structure - Finishes & MEP - P2 to P3 | Not Ready | Gypsum Plastering Works | 2024-05-03 | 2024-06-25 | P2 to P3_TA & NTA | 100 | 0 |  | 2025-11-26 |  | 2026-01-17 |  | Tower A | Super Structure |  | Finishes | Gypsum Plastering Works
40525 | Tower A - Super Structure - Finishes & MEP - L51 to L52 | Not Ready | Gypsum Plastering Works | 2025-11-04 | 2025-11-20 | L51-52 | 100 | 0 |  | 2025-11-26 |  | 2025-12-12 |  | Tower A | Super Structure | L51 | Finishes | Gypsum Plastering Works
40525 | Tower A - Super Structure - Finishes & MEP - L51 to L52 | Not Ready | Gypsum Plastering Works | 2025-11-04 | 2025-11-20 | L51-52 | 100 | 0 |  | 2025-11-26 |  | 2025-12-12 |  | Tower A | Super Structure | L51
41067 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2025-11-06 | 2025-11-13 | False Ceiling | 100 | 0 |  | 2025-11-26 |  | 2025-12-04 |  | Tower A | Super Structure | L7 | Finishes | False Ceiling
41082 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-11-06 | 2025-11-17 | Flooring & Dado | 100 | 0 |  | 2025-11-26 |  | 2025-12-08 |  | Tower A | Super Structure | L8 | Finishes | Flooring & Dado
43010 |  | Not Committed |  | 2025-11-04 | 2026-09-12 | L52-53 | 100 | 0 |  | 2025-11-26 |  | 2026-08-26
43010 |  | Not Committed |  | 2025-11-04 | 2026-09-12 | L52-53 | 100 | 0 |  | 2025-11-26 |  | 2026-08-26 |  |  |  |  | Finishes | Gypsum Plastering Works
43011 |  | Not Committed |  | 2025-11-04 | 2025-12-02 | MEP 1st Fixes | 100 | 0 |  | 2025-11-26 |  | 2025-12-24
43012 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2025-11-04 | 2025-11-11 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-11-26 |  | 2025-12-03 |  | Tower A | Super Structure | L52 | MEP | FPS 1st Fix - MEP & Finishes
43013 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-11-04 | 2025-11-08 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2025-11-26 |  | 2025-12-01 |  | Tower A | Super Structure | L52 | MEP | Electrical 1st Fixes
43014 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2025-11-04 | 2025-11-11 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2025-11-26 |  | 2025-12-03 |  | Tower A | Super Structure | L52
43015 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2025-11-04 | 2025-11-20 | Wet Area Waterproofing | 100 | 0 |  | 2025-11-26 |  | 2025-12-12 |  | Tower A | Super Structure | L52
8610 | T-14-3rd Floor Flat Area | Not Ready | Door | 2025-11-09 | 2025-12-01 | Door | 100 | 0 |  | 2025-11-27 |  | 2025-12-19
8686 | T-14-6th Floor Flat Area | Not Ready | Putty | 2025-10-28 | 2026-01-21 | Putty | 100 | 0 |  | 2025-11-27 |  | 2026-02-20
9184 | T-15-4th Floor Flat Area | Not Ready | 1st Coat Painting | 2025-12-03 | 2026-02-25 | 1st Coat Painting | 100 | 0 |  | 2025-11-27 |  | 2026-02-19
9744 | T-16-6th Floor Flat Area | Not Ready | Plastering | 2025-12-12 | 2026-01-02 | Plastering-Cement | 100 | 0 |  | 2025-11-27 |  | 2025-12-21
9768 | T-16-7th Floor Flat Area | Not Ready | Blockwork | 2025-12-11 | 2026-01-01 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-11-27 |  | 2025-12-20
9807 | T-16-8th Floor Flat Area | Not Ready | Railing | 2025-12-11 | 2026-01-13 | Balcony Railing | 100 | 0 |  | 2025-11-27 |  | 2025-12-29
10916 | T-20-11th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-12-23 | 2026-01-08 | Electrical DB Fixing | 100 | 0 |  | 2025-11-27 |  | 2025-12-13
11311 | T-19-6th Floor Flat Area | Not Ready | Flooring & skirting | 2025-12-12 | 2026-01-27 | Flooring & skirting | 100 | 0 |  | 2025-11-27 |  | 2026-01-10
11855 | T-18-7th Floor Flat Area | Not Ready | Toilet flooring | 2026-02-12 | 2026-03-17 | Toilet flooring | 100 | 0 |  | 2025-11-27 |  | 2025-12-30
11927 | T-18-10th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2026-02-07 | 2026-03-01 | Plumbing Pipe Line | 100 | 0 |  | 2025-11-27 |  | 2025-12-19
39748 | Tower A - Super Structure - Core Wall High Rise L73-74 | Not Ready | Core Wall RCC Works | 2025-11-01 | 2025-11-01 | ACS Form Release & jump to next level | 100 | 0 |  | 2025-11-27 |  | 2025-11-28 |  | Tower A | Super Structure | L73 | RCC Super Structure | Core Wall RCC Works
40012 | Tower A - Super Structure - Core & Outer Slab L69-70 | Not Ready | RCC Works - Slab | 2025-10-29 | 2025-11-03 | Outer Slab_TA | 100 | 0 |  | 2025-11-27 |  | 2025-12-03 |  | Tower A | Super Structure | L69 | RCC Sub Structure | RCC Works - Slab
40052 | Tower A - Super Structure - Finishes & MEP - L45 to L46 | Not Ready | CTU Elevators Crash Deck - High Side Services | 2025-04-19 | 2025-05-06 | Scaffolding (for 15m) & Jump platform installation | 100 | 0 |  | 2025-11-27 |  | 2025-12-12 |  | Tower A | Super Structure | L45
40688 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2024-05-04 | 2024-05-09 | Final Painting | 100 | 0 |  | 2025-11-27 |  | 2025-12-02 |  | Tower A | Super Structure | GF | Finishes | Final Painting
40688 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2024-05-04 | 2024-05-09 | Final Painting | 100 | 0 |  | 2025-11-27 |  | 2025-12-02 |  | Tower A | Super Structure | GF | Finishes | Final Painting
40688 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2024-05-04 | 2024-05-09 | Final Painting | 100 | 0 |  | 2025-11-27 |  | 2025-12-02 |  | Tower A | Super Structure | GF | Finishes | Final Painting
41273 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-04-19 | 2025-04-24 | Lobby Plastering | 100 | 0 |  | 2025-11-27 |  | 2025-12-02 |  | Tower A | Super Structure | L20 | Finishes | Lobby Plastering
41288 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-04-19 | 2025-04-22 | Lobby Blockwork | 100 | 0 |  | 2025-11-27 |  | 2025-11-29 |  | Tower A | Super Structure | L21 | Finishes | Blockwork
45270 | Tower B - Super Structure - Core & Outer Slab P6-L7 | Not Ready | RCC Works - Slab | 2025-09-22 | 2025-09-29 | Outer Slab_TA | 100 | 0 |  | 2025-11-27 |  | 2025-12-05 |  | Tower B | Super Structure |  | RCC Sub Structure | RCC Works - Slab
9326 | T-15-10th Floor Flat Area | Not Ready | Blockwork | 2025-11-27 | 2025-12-19 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-11-28 |  | 2025-12-16
9556 | T-16-Terrace | Not Ready | AL - Shear Walls/Corewalls Steel | 2025-12-12 | 2025-12-16 | AL - Shear Walls/Corewalls Steel | 25 | 0 | MT | 2025-11-28 |  | 2025-12-04
10277 | T-21-6th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-01-09 | 2026-03-18 | 2nd Coat Painting | 100 | 0 |  | 2025-11-28 |  | 2026-02-04
10409 | T-21-11th Floor Common Area | Not Ready | Plastering | 2025-12-26 | 2026-01-30 | Plastering-Gypsum | 100 | 0 |  | 2025-11-28 |  | 2026-01-01
11128 |  | Not Ready |  | 2025-12-11 | 2025-12-27 | Lowering Aluminium FW Material For PH-2 | 100 | 0 |  | 2025-11-28 |  | 2025-12-17
11355 | T-19-8th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-12-11 | 2026-01-02 | Plumbing Pipe Line | 100 | 0 |  | 2025-11-28 |  | 2025-12-23
11381 | T-19-9th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-12-11 | 2026-01-02 | Plumbing Pipe Line | 100 | 0 |  | 2025-11-28 |  | 2025-12-23
39749 |  | Not Ready |  | 2025-11-03 | 2025-11-10 | Core Wall L74-75 (Penthouse) | 100 | 0 |  | 2025-11-28 |  | 2025-12-06
39750 | Tower A - Super Structure - Core Wall High Rise L74-75 | Not Ready | Core Wall RCC Works | 2025-11-03 | 2025-11-03 | Scaffolding & platform | 100 | 0 |  | 2025-11-28 |  | 2025-11-29 |  | Tower A | Super Structure | L74 | RCC Super Structure | Core Wall RCC Works
40372 | Tower A - Super Structure - Finishes & MEP - L53 to L54 | Not Ready | Partition Wall-Blockwork | 2025-11-06 | 2025-11-11 | Staircase Area | 100 | 0 |  | 2025-11-28 |  | 2025-12-03 |  | Tower A | Super Structure | L53
40375 | Tower A - Super Structure - Finishes & MEP - L54 to L55 | Not Ready | Partition Wall-Blockwork | 2025-11-06 | 2025-11-13 | Partition Walls | 100 | 0 |  | 2025-11-28 |  | 2025-12-05 |  | Tower A | Super Structure | L54
40762 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2024-05-16 | 2024-05-17 | FAPA Cabling | 100 | 0 |  | 2025-11-28 |  | 2025-12-01 |  | Tower A | Super Structure
42570 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-12-13 | 2025-12-31 | Flooring & Dado works | 100 | 0 |  | 2025-11-28 |  | 2025-12-16 |  | Tower A | Super Structure | L27 | Finishes | Flooring & Dado
42606 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-12-19 | 2026-01-06 | Flooring & Dado works | 100 | 0 |  | 2025-11-28 |  | 2025-12-15 |  | Tower A | Super Structure | L29 | Finishes | Flooring & Dado
42623 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-05-02 | 2025-05-09 | Door & Window Frame work | 100 | 0 |  | 2025-11-28 |  | 2025-12-05 |  | Tower A | Super Structure | L30 | Finishes | Door & Window Frame work
9230 | T-15-6th Floor Flat Area | Not Ready | Toilets False Celing | 2025-12-04 | 2026-01-06 | Toilets False Celing | 100 | 0 |  | 2025-11-29 |  | 2026-01-01
9254 | T-15-7th Floor Flat Area | Not Ready | Dado | 2025-12-02 | 2025-12-29 | Dado | 100 | 0 |  | 2025-11-29 |  | 2025-12-27
9605 | T-16-GF Common Area | Not Ready | Window | 2025-12-19 | 2026-01-10 | Window | 100 | 0 |  | 2025-11-29 |  | 2025-12-22
9697 | T-16-4th Floor Flat Area | Not Ready | Toilet flooring | 2025-12-20 | 2026-01-23 | Toilet flooring | 100 | 0 |  | 2025-11-29 |  | 2025-12-31
9759 | T-16-6th Floor Common Area | Not Ready | Plastering | 2025-12-14 | 2026-01-17 | Plastering-Gypsum | 100 | 0 |  | 2025-11-29 |  | 2026-01-03
9772 | T-16-7th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-12-13 | 2025-12-29 | Electrical DB Fixing | 100 | 0 |  | 2025-11-29 |  | 2025-12-15
9870 |  | Not Ready |  | 2026-01-29 | 2026-10-29 | Eleventh Floor | 100 | 0 |  | 2025-11-29 |  | 2026-09-01
9871 |  | Not Ready |  | 2026-01-29 | 2026-10-29 | Flat Area | 100 | 0 |  | 2025-11-29 |  | 2026-09-01
11127 | T-19-Terrace | Not Ready |  | 2025-12-12 | 2026-02-02 | MISC | 100 | 0 |  | 2025-11-29 |  | 2026-01-19
11168 | T-19-GF Common Area | Not Ready | 1st Coat Painting | 2025-12-20 | 2026-02-09 | 1st Coat Painting | 100 | 0 |  | 2025-11-29 |  | 2026-01-19
11730 | T-18-2nd Floor Flat Area | Not Ready | Door | 2026-01-27 | 2026-02-17 | Door | 100 | 0 |  | 2025-11-29 |  | 2025-12-20
11931 | T-18-10th Floor Flat Area | Not Ready | Plastering | 2026-02-10 | 2026-03-26 | Plastering-Gypsum | 100 | 0 |  | 2025-11-29 |  | 2026-01-11
11950 |  | Not Ready |  | 2026-02-03 | 2026-11-05 | Eleventh Floor | 100 | 0 |  | 2025-11-29 |  | 2026-09-04
11951 |  | Not Ready |  | 2026-02-03 | 2026-11-05 | Flat Area | 100 | 0 |  | 2025-11-29 |  | 2026-09-04
39751 | Tower A - Super Structure - Core Wall High Rise L74-75 | Not Ready | Core Wall RCC Works | 2025-11-04 | 2025-11-06 | Reinf & Guide shoes fixing | 100 | 0 |  | 2025-11-29 |  | 2025-12-03 |  | Tower A | Super Structure | L74 | RCC Super Structure | Core Wall RCC Works
40698 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2024-07-05 | 2024-07-13 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2025-11-29 |  | 2025-12-06 |  | Tower A | Super Structure | GF | MEP | Electrical 2nd Fix - MEP & Finishes
41111 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2025-11-10 | 2025-11-17 | HVAC Ducting | 100 | 0 |  | 2025-11-29 |  | 2025-12-08 |  | Tower A | Super Structure | L10 | MEP | HVAC Ducting
42480 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-11-20 | 2025-12-06 | Flooring & Dado works | 100 | 0 |  | 2025-11-29 |  | 2025-12-17 |  | Tower A | Super Structure | L22 | Finishes | Flooring & Dado
8756 | T-14-9th Floor Flat Area | Not Ready | Plastering | 2025-10-27 | 2025-11-20 | Plastering-Cement | 100 | 0 |  | 2025-11-30 |  | 2025-12-26
9156 | T-15-3rd Floor Flat Area | Not Ready | Door | 2025-12-09 | 2025-12-31 | Door | 100 | 0 |  | 2025-11-30 |  | 2025-12-22
9330 | T-15-10th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-11-29 | 2025-12-16 | Electrical DB Fixing | 100 | 0 |  | 2025-11-30 |  | 2025-12-19
9365 | T-15-11th Floor Flat Area | Not Ready | Railing | 2025-12-01 | 2026-01-02 | Balcony Railing | 100 | 0 |  | 2025-11-30 |  | 2025-12-31
9558 | T-16-Terrace | Not Ready | Conduiting | 2025-12-14 | 2025-12-17 | Conduiting works | 100 | 0 |  | 2025-11-30 |  | 2025-12-04
9725 | T-16-5th Floor Flat Area | Not Ready | Flooring & skirting | 2025-12-19 | 2026-02-03 | Flooring & skirting | 100 | 0 |  | 2025-11-30 |  | 2026-01-14
10332 | T-21-8th Floor Common Area | Not Ready | Flooring & skirting | 2026-01-04 | 2026-01-28 | Flooring & skirting | 100 | 0 |  | 2025-11-30 |  | 2025-12-22
11124 | T-19-Terrace | Not Ready | OHT | 2025-12-13 | 2026-02-03 | OHT | 100 | 0 |  | 2025-11-30 |  | 2026-01-19
11209 | T-19-2nd Floor Flat Area | Not Ready | Window | 2025-12-21 | 2026-01-12 | Window | 100 | 0 |  | 2025-11-30 |  | 2025-12-25
11238 | T-19-3rd Floor Flat Area | Not Ready | 1st Coat Painting | 2025-12-24 | 2026-03-18 | 1st Coat Painting | 100 | 0 |  | 2025-11-30 |  | 2026-02-22
11283 | T-19-5th Floor Flat Area | Not Ready | Toilet flooring | 2025-12-13 | 2026-01-16 | Toilet flooring | 100 | 0 |  | 2025-11-30 |  | 2026-01-04
11359 | T-19-8th Floor Flat Area | Not Ready | Plastering | 2025-12-13 | 2026-01-28 | Plastering-Gypsum | 100 | 0 |  | 2025-11-30 |  | 2026-01-13
11385 | T-19-9th Floor Flat Area | Not Ready | Plastering | 2025-12-13 | 2026-01-28 | Plastering-Gypsum | 100 | 0 |  | 2025-11-30 |  | 2026-01-13
11858 | T-18-7th Floor Flat Area | Not Ready | Putty | 2026-02-15 | 2026-05-10 | Putty | 100 | 0 |  | 2025-11-30 |  | 2026-02-21
8796 |  | Not Ready |  | 2025-11-29 | 2026-06-30 | Common Area | 100 | 0 |  | 2025-12-01 |  | 2026-07-01
9283 | T-15-8th Floor Flat Area | Not Ready | Flooring & skirting | 2025-12-05 | 2026-01-19 | Flooring & skirting | 100 | 0 |  | 2025-12-01 |  | 2026-01-12
9309 | T-15-9th Floor Flat Area | Not Ready | Flooring & skirting | 2025-12-05 | 2026-01-19 | Flooring & skirting | 100 | 0 |  | 2025-12-01 |  | 2026-01-12
9557 | T-16-Terrace | Not Ready | Shear Walls/Corewalls Shuttering | 2025-12-15 | 2025-12-19 | Shear Walls/Corewalls Shuttering | 100 | 0 |  | 2025-12-01 |  | 2025-12-05
9591 | T-16-GF Flat Area | Not Ready | 1st Coat Painting | 2025-12-19 | 2026-02-09 | 1st Coat Painting | 100 | 0 |  | 2025-12-01 |  | 2026-01-21
10826 | T-20-7th Floor Common Area | Not Ready | Flooring & skirting | 2025-12-30 | 2026-01-22 | Flooring & skirting | 100 | 0 |  | 2025-12-01 |  | 2025-12-23
11422 |  | Not Ready |  | 2026-01-21 | 2026-09-04 | Common Area | 100 | 0 |  | 2025-12-01 |  | 2026-07-16
29812 | Tower B | Not Committed |  | 2025-12-01 | 2029-03-31 | Tower B Milestones | 100 | 0 |  | 2025-12-01 |  | 2029-03-31 |  | Tower B | --
39752 | Tower A - Super Structure - Core Wall High Rise L74-75 | Not Ready | Core Wall RCC Works | 2025-11-05 | 2025-11-07 | ACS Form Closing & Alignment | 100 | 0 |  | 2025-12-01 |  | 2025-12-04 |  | Tower A | Super Structure | L74 | RCC Super Structure | Core Wall RCC Works
41289 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-04-23 | 2025-04-28 | Lobby Plastering | 100 | 0 |  | 2025-12-01 |  | 2025-12-05 |  | Tower A | Super Structure | L21 | Finishes | Lobby Plastering
41304 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-04-23 | 2025-04-25 | Lobby Blockwork | 100 | 0 |  | 2025-12-01 |  | 2025-12-03 |  | Tower A | Super Structure | L22 | Finishes | Blockwork
42963 |  | Not Committed |  | 2025-11-08 | 2026-03-25 | Finishes after 1st Fix | 100 | 0 |  | 2025-12-01 |  | 2026-02-23
42964 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-11-08 | 2025-12-01 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-12-01 |  | 2025-12-23 |  | Tower A | Super Structure | L49 | Finishes | Blockwork
44083 |  | Started |  | 2026-01-01 | 2026-02-11 | L38-43 | 100 | 5 |  | 2025-12-01 | 2025-09-13 | 2026-01-12
44084 | Tower A - Super Structure - Finishes & MEP - L38 to L43 | Started | Façade Works - MEP & Finishes | 2026-01-01 | 2026-01-17 | Al. Frame section (Mullion & Transom) Installation | 100 | 5 | Units | 2025-12-01 | 2025-09-13 | 2025-12-18 |  | Tower A | Super Structure | L38 | Façade | Façade Works
48160 | Retail - Super structure - GF to R1 - P1 | Not Ready |  | 2025-07-24 | 2025-08-20 | Slab_RT | 100 | 0 |  | 2025-12-01 |  | 2025-12-23 |  | Retail | Super Structure | GF | RCC Sub Structure | RCC Works - Slab
48160 | Retail - Super structure - GF to R1 - P1 | Not Ready |  | 2025-07-24 | 2025-08-20 | Slab_RT | 100 | 0 |  | 2025-12-01 |  | 2025-12-23 |  | Retail | Super Structure | GF
48167 | Retail - Super structure - GF to R1 - P3 | Not Ready |  | 2025-07-24 | 2025-08-20 | Slab_RT | 100 | 0 |  | 2025-12-01 |  | 2025-12-23 |  | Retail | Super Structure | GF | RCC Sub Structure | RCC Works - Slab
48167 | Retail - Super structure - GF to R1 - P3 | Not Ready |  | 2025-07-24 | 2025-08-20 | Slab_RT | 100 | 0 |  | 2025-12-01 |  | 2025-12-23 |  | Retail | Super Structure | GF
48176 |  | Not Committed |  | 2025-07-24 | 2025-09-25 | Pour RT-6 | 100 | 0 |  | 2025-12-01 |  | 2026-01-16
48177 | Retail - Super structure - GF to R1 - P6 | Not Ready |  | 2025-07-24 | 2025-08-28 | Columns_RT | 100 | 0 |  | 2025-12-01 |  | 2025-12-30 |  | Retail | Super Structure | GF | RCC Sub Structure | RCC Works - Vertical
48177 | Retail - Super structure - GF to R1 - P6 | Not Ready |  | 2025-07-24 | 2025-08-28 | Columns_RT | 100 | 0 |  | 2025-12-01 |  | 2025-12-30 |  | Retail | Super Structure | GF
48178 | Retail - Super structure - GF to R1 - P6 | Not Ready |  | 2025-07-24 | 2025-08-28 | Staircase_RT | 100 | 0 |  | 2025-12-01 |  | 2025-12-30 |  | Retail | Super Structure | GF | RCC Sub Structure | RCC Works - Slab
48178 | Retail - Super structure - GF to R1 - P6 | Not Ready |  | 2025-07-24 | 2025-08-28 | Staircase_RT | 100 | 0 |  | 2025-12-01 |  | 2025-12-30 |  | Retail | Super Structure | GF
8684 | T-14-6th Floor Flat Area | Not Ready | Toilets False Celing | 2025-11-05 | 2025-12-07 | Toilets False Celing | 100 | 0 |  | 2025-12-02 |  | 2026-01-04
8731 | T-14-8th Floor Flat Area | Not Ready | Waterproofing | 2025-10-29 | 2025-12-03 | Waterproofing | 100 | 0 |  | 2025-12-02 |  | 2026-01-06
8771 | T-14-9th Floor Common Area | Not Ready | Plastering | 2025-10-29 | 2025-12-03 | Plastering-Gypsum | 100 | 0 |  | 2025-12-02 |  | 2026-01-06
9719 | T-16-5th Floor Flat Area | Not Ready | Waterproofing | 2025-12-19 | 2026-02-09 | Waterproofing | 100 | 0 |  | 2025-12-02 |  | 2026-01-22
10222 | T-21-4th Floor Flat Area | Not Ready | Door | 2025-12-08 | 2025-12-30 | Door | 100 | 0 |  | 2025-12-02 |  | 2025-12-23
10913 | T-20-11th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-12-28 | 2026-01-20 | Plumbing Pipe Line | 100 | 0 |  | 2025-12-02 |  | 2025-12-23
11880 | T-18-8th Floor Flat Area | Not Ready | Dado | 2026-02-18 | 2026-03-18 | Dado | 100 | 0 |  | 2025-12-02 |  | 2025-12-29
11906 | T-18-9th Floor Flat Area | Not Ready | Dado | 2026-02-18 | 2026-03-18 | Dado | 100 | 0 |  | 2025-12-02 |  | 2025-12-29
40712 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2024-05-09 | 2024-05-11 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2025-12-02 |  | 2025-12-04 |  | Tower A | Super Structure |  | MEP | FPS 2nd Fix - MEP & Finishes
40713 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2024-05-09 | 2024-05-14 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2025-12-02 |  | 2025-12-06 |  | Tower A | Super Structure |  | MEP | Electrical 2nd Fix - MEP & Finishes
40714 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-05-09 | 2024-05-16 | FAPA Device Fixing | 100 | 0 |  | 2025-12-02 |  | 2025-12-09 |  | Tower A | Super Structure
40714 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-05-09 | 2024-05-16 | FAPA Device Fixing | 100 | 0 |  | 2025-12-02 |  | 2025-12-09 |  | Tower A | Super Structure
40714 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-05-09 | 2024-05-16 | FAPA Device Fixing | 100 | 0 |  | 2025-12-02 |  | 2025-12-09 |  | Tower A | Super Structure
40714 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-05-09 | 2024-05-16 | FAPA Device Fixing | 100 | 0 |  | 2025-12-02 |  | 2025-12-09 |  | Tower A | Super Structure
40715 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2024-05-09 | 2024-05-11 | HVAC Grill Fixing | 100 | 0 |  | 2025-12-02 |  | 2025-12-04 |  | Tower A | Super Structure |  | MEP | HVAC Grill Fixing
41083 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2025-11-12 | 2025-11-19 | False Ceiling | 100 | 0 |  | 2025-12-02 |  | 2025-12-10 |  | Tower A | Super Structure | L8 | Finishes | False Ceiling
41098 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-11-12 | 2025-11-22 | Flooring & Dado | 100 | 0 |  | 2025-12-02 |  | 2025-12-13 |  | Tower A | Super Structure | L9 | Finishes | Flooring & Dado
8635 | T-14-4th Floor Flat Area | Not Ready | Window | 2025-11-15 | 2025-12-07 | Window | 100 | 0 |  | 2025-12-03 |  | 2025-12-25
8708 | T-14-7th Floor Flat Area | Not Ready | Dado | 2025-11-03 | 2025-11-29 | Dado | 100 | 0 |  | 2025-12-03 |  | 2025-12-30
9700 | T-16-4th Floor Flat Area | Not Ready | Putty | 2025-12-27 | 2026-03-21 | Putty | 100 | 0 |  | 2025-12-03 |  | 2026-02-26
10373 | T-21-10th Floor Flat Area | Not Ready | Toilet flooring | 2026-01-04 | 2026-02-08 | Toilet flooring | 100 | 0 |  | 2025-12-03 |  | 2026-01-05
10794 | T-20-6th Floor Flat Area | Not Ready | Door | 2026-01-19 | 2026-02-11 | Door | 100 | 0 |  | 2025-12-03 |  | 2025-12-24
10822 | T-20-7th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-01-08 | 2026-04-03 | 1st Coat Painting | 100 | 0 |  | 2025-12-03 |  | 2026-02-25
10928 |  | Not Ready |  | 2026-01-07 | 2026-08-20 | Common Area | 100 | 0 |  | 2025-12-03 |  | 2026-07-16
11286 | T-19-5th Floor Flat Area | Not Ready | Putty | 2025-12-20 | 2026-03-14 | Putty | 100 | 0 |  | 2025-12-03 |  | 2026-02-26
40013 |  | Not Ready |  | 2025-11-04 | 2025-11-10 | L70-71 | 100 | 0 |  | 2025-12-03 |  | 2025-12-10
40013 |  | Not Ready |  | 2025-11-04 | 2025-11-10 | L70-71 | 100 | 0 |  | 2025-12-03 |  | 2025-12-10 |  |  |  |  | Finishes | Gypsum Plastering Works
40014 | Tower A - Super Structure - Core & Outer Slab L70-71 | Not Ready | RCC Works - Vertical | 2025-11-04 | 2025-11-10 | Outer Columns_TA | 100 | 0 |  | 2025-12-03 |  | 2025-12-10 |  | Tower A | Super Structure | L70 | RCC Sub Structure | RCC Works - Vertical
40069 |  | Not Committed |  | 2025-11-04 | 2026-01-27 | CTU Elevators Crash Deck at L70 | 100 | 0 |  | 2025-12-03 |  | 2026-02-26
40070 | Tower A - Super Structure - Finishes & MEP - L70 to L71 | Not Ready | CTU Elevators Crash Deck - High Side Services | 2025-11-04 | 2025-11-14 | Crash deck install at L70 (after L70 slab casting) + Crash Deck shift at L70 for other lifts | 100 | 0 |  | 2025-12-03 |  | 2025-12-15 |  | Tower A | Super Structure | L70
40425 |  | Not Committed |  | 2025-11-04 | 2026-03-09 | L67-68 | 100 | 0 |  | 2025-12-03 |  | 2026-03-31
40425 |  | Not Committed |  | 2025-11-04 | 2026-03-09 | L67-68 | 100 | 0 |  | 2025-12-03 |  | 2026-03-31 |  |  |  |  | Finishes | Gypsum Plastering Works
40426 | Tower A - Super Structure - Finishes & MEP - L67 to L68 | Not Ready | Partition Wall-Blockwork | 2025-11-04 | 2025-11-20 | De-shuttering & Area clearance | 100 | 0 |  | 2025-12-03 |  | 2025-12-20 |  | Tower A | Super Structure | L67
40763 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2024-05-21 | 2024-05-28 | HVAC Ducting | 100 | 0 |  | 2025-12-03 |  | 2025-12-11 |  | Tower A | Super Structure |  | MEP | HVAC Ducting
40764 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2024-05-21 | 2024-06-06 | Flooring & Dado | 100 | 0 |  | 2025-12-03 |  | 2025-12-20 |  | Tower A | Super Structure |  | Finishes | Flooring & Dado
40786 |  | Not Committed |  | 2024-05-30 | 2024-07-30 | Lobby/ Common Area | 100 | 0 |  | 2025-12-03 |  | 2026-01-23
40787 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2024-05-30 | 2024-06-06 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-12-03 |  | 2025-12-11 |  | Tower A | Super Structure |  | MEP | FPS 1st Fix - MEP & Finishes
40788 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2024-05-30 | 2024-06-01 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-12-03 |  | 2025-12-06 |  | Tower A | Super Structure |  | MEP | Electrical 1st Fixes
9559 | T-16-Terrace | Not Ready | Shuttering | 2025-12-18 | 2025-12-23 | Slab and Beam Shuttering | 4183 | 0 | Sqm | 2025-12-04 |  | 2025-12-09
9769 | T-16-7th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-12-18 | 2026-01-09 | Plumbing Pipe Line | 100 | 0 |  | 2025-12-04 |  | 2025-12-27
10917 | T-20-11th Floor Flat Area | Not Ready | Plastering | 2025-12-30 | 2026-02-14 | Plastering-Gypsum | 100 | 0 |  | 2025-12-04 |  | 2026-01-19
11928 | T-18-10th Floor Flat Area | Not Ready | Plastering | 2026-02-15 | 2026-03-09 | Plastering-Cement | 100 | 0 |  | 2025-12-04 |  | 2025-12-25
39241 |  | Not Ready |  | 2025-01-22 | 2025-03-05 | Shut Down for Hooking Up with Centurion Electrical Shaft with T & C | 100 | 0 |  | 2025-12-04 |  | 2026-01-14
39753 | Tower A - Super Structure - Core Wall High Rise L74-75 | Not Ready | Core Wall RCC Works | 2025-11-08 | 2025-11-08 | Casting | 100 | 0 |  | 2025-12-04 |  | 2025-12-05 |  | Tower A | Super Structure | L74 | RCC Super Structure | Core Wall RCC Works
40015 | Tower A - Super Structure - Core & Outer Slab L70-71 | Not Ready | RCC Works - Slab | 2025-11-05 | 2025-11-10 | Outer Slab_TA | 100 | 0 |  | 2025-12-04 |  | 2025-12-10 |  | Tower A | Super Structure | L70 | RCC Sub Structure | RCC Works - Slab
40526 | Tower A - Super Structure - Finishes & MEP - L52 to L53 | Not Ready | Gypsum Plastering Works | 2025-11-12 | 2025-11-28 | L52-53 | 100 | 0 |  | 2025-12-04 |  | 2025-12-20 |  | Tower A | Super Structure | L52 | Finishes | Gypsum Plastering Works
40526 | Tower A - Super Structure - Finishes & MEP - L52 to L53 | Not Ready | Gypsum Plastering Works | 2025-11-12 | 2025-11-28 | L52-53 | 100 | 0 |  | 2025-12-04 |  | 2025-12-20 |  | Tower A | Super Structure | L52
41068 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2025-11-14 | 2025-11-17 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2025-12-04 |  | 2025-12-08 |  | Tower A | Super Structure | L7 | MEP | FPS 2nd Fix - MEP & Finishes
41069 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2025-11-14 | 2025-11-19 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2025-12-04 |  | 2025-12-10 |  | Tower A | Super Structure | L7 | MEP | Electrical 2nd Fix - MEP & Finishes
41070 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-11-14 | 2025-11-21 | FAPA Device Fixing | 100 | 0 |  | 2025-12-04 |  | 2025-12-12 |  | Tower A | Super Structure | L7
41070 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-11-14 | 2025-11-21 | FAPA Device Fixing | 100 | 0 |  | 2025-12-04 |  | 2025-12-12 |  | Tower A | Super Structure | L7
41070 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-11-14 | 2025-11-21 | FAPA Device Fixing | 100 | 0 |  | 2025-12-04 |  | 2025-12-12 |  | Tower A | Super Structure | L7
41070 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-11-14 | 2025-11-21 | FAPA Device Fixing | 100 | 0 |  | 2025-12-04 |  | 2025-12-12 |  | Tower A | Super Structure | L7
41071 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2025-11-14 | 2025-11-17 | HVAC Grill Fixing | 100 | 0 |  | 2025-12-04 |  | 2025-12-08 |  | Tower A | Super Structure | L7 | MEP | HVAC Grill Fixing
41305 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-04-26 | 2025-05-02 | Lobby Plastering | 100 | 0 |  | 2025-12-04 |  | 2025-12-09 |  | Tower A | Super Structure | L22 | Finishes | Lobby Plastering
41320 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-04-26 | 2025-04-29 | Lobby Blockwork | 100 | 0 |  | 2025-12-04 |  | 2025-12-06 |  | Tower A | Super Structure | L23 | Finishes | Blockwork
43028 |  | Not Committed |  | 2025-11-12 | 2026-09-12 | L53-54 | 100 | 0 |  | 2025-12-04 |  | 2026-08-26
43028 |  | Not Committed |  | 2025-11-12 | 2026-09-12 | L53-54 | 100 | 0 |  | 2025-12-04 |  | 2026-08-26 |  |  |  |  | Finishes | Gypsum Plastering Works
43029 |  | Not Committed |  | 2025-11-12 | 2025-12-10 | MEP 1st Fixes | 100 | 0 |  | 2025-12-04 |  | 2026-01-02
43030 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2025-11-12 | 2025-11-19 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-12-04 |  | 2025-12-11 |  | Tower A | Super Structure | L53 | MEP | FPS 1st Fix - MEP & Finishes
43031 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-11-12 | 2025-11-17 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2025-12-04 |  | 2025-12-09 |  | Tower A | Super Structure | L53 | MEP | Electrical 1st Fixes
43032 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2025-11-12 | 2025-11-19 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2025-12-04 |  | 2025-12-11 |  | Tower A | Super Structure | L53
43033 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2025-11-12 | 2025-11-28 | Wet Area Waterproofing | 100 | 0 |  | 2025-12-04 |  | 2025-12-20 |  | Tower A | Super Structure | L53
44552 | NTA_Zone 2 - Sub Structure - B2 to B1 | Not Ready | Finishes (Lobby & Floor Area) | 2024-09-24 | 2024-10-18 | MEP Rooms - Plaster & IPS | 100 | 0 |  | 2025-12-04 |  | 2025-12-27 |  | NTA_Zone 2 | Sub Structure | B2
44552 | NTA_Zone 2 - Sub Structure - B2 to B1 | Not Ready | Finishes (Lobby & Floor Area) | 2024-09-24 | 2024-10-18 | MEP Rooms - Plaster & IPS | 100 | 0 |  | 2025-12-04 |  | 2025-12-27 |  | NTA_Zone 2 | Sub Structure | B2
44553 | NTA_Zone 2 - Sub Structure - B2 to B1 | Not Ready | Finishes (Lobby & Floor Area) | 2024-09-24 | 2024-10-30 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2025-12-04 |  | 2026-01-08 |  | NTA_Zone 2 | Sub Structure | B2
44553 | NTA_Zone 2 - Sub Structure - B2 to B1 | Not Ready | Finishes (Lobby & Floor Area) | 2024-09-24 | 2024-10-30 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2025-12-04 |  | 2026-01-08 |  | NTA_Zone 2 | Sub Structure | B2
9327 | T-15-10th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-12-05 | 2025-12-26 | Plumbing Pipe Line | 100 | 0 |  | 2025-12-05 |  | 2025-12-26
9623 | T-16-1st Floor Flat Area | Not Ready | Window | 2025-12-27 | 2026-01-19 | Window | 100 | 0 |  | 2025-12-05 |  | 2025-12-29
10819 | T-20-7th Floor Flat Area | Not Ready | Window | 2026-01-21 | 2026-02-13 | Window | 100 | 0 |  | 2025-12-05 |  | 2025-12-29
11356 | T-19-8th Floor Flat Area | Not Ready | Plastering | 2025-12-19 | 2026-01-09 | Plastering-Cement | 100 | 0 |  | 2025-12-05 |  | 2025-12-29
11382 | T-19-9th Floor Flat Area | Not Ready | Plastering | 2025-12-19 | 2026-01-09 | Plastering-Cement | 100 | 0 |  | 2025-12-05 |  | 2025-12-29
11856 | T-18-7th Floor Flat Area | Not Ready | Toilets False Celing | 2026-02-20 | 2026-03-26 | Toilets False Celing | 100 | 0 |  | 2025-12-05 |  | 2026-01-08
39754 | Tower A - Super Structure - Core Wall High Rise L74-75 | Not Ready | Core Wall RCC Works | 2025-11-10 | 2025-11-10 | ACS Form Release & jump to next level | 100 | 0 |  | 2025-12-05 |  | 2025-12-06 |  | Tower A | Super Structure | L74 | RCC Super Structure | Core Wall RCC Works
40699 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-07-18 | 2024-07-26 | FAPA Device Fixing | 100 | 0 |  | 2025-12-05 |  | 2025-12-12 |  | Tower A | Super Structure | GF
40699 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-07-18 | 2024-07-26 | FAPA Device Fixing | 100 | 0 |  | 2025-12-05 |  | 2025-12-12 |  | Tower A | Super Structure | GF
40699 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-07-18 | 2024-07-26 | FAPA Device Fixing | 100 | 0 |  | 2025-12-05 |  | 2025-12-12 |  | Tower A | Super Structure | GF
40699 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-07-18 | 2024-07-26 | FAPA Device Fixing | 100 | 0 |  | 2025-12-05 |  | 2025-12-12 |  | Tower A | Super Structure | GF
40716 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2024-05-13 | 2024-05-15 | Staircase Fire Door Fixing | 100 | 0 |  | 2025-12-05 |  | 2025-12-08 |  | Tower A | Super Structure
40781 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2024-08-22 | 2024-08-30 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2025-12-05 |  | 2025-12-12 |  | Tower A | Super Structure |  | MEP | FPS 2nd Fix - MEP & Finishes
40782 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-08-22 | 2024-08-30 | FAPA Device Fixing | 100 | 0 |  | 2025-12-05 |  | 2025-12-12 |  | Tower A | Super Structure
40782 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-08-22 | 2024-08-30 | FAPA Device Fixing | 100 | 0 |  | 2025-12-05 |  | 2025-12-12 |  | Tower A | Super Structure
40782 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-08-22 | 2024-08-30 | FAPA Device Fixing | 100 | 0 |  | 2025-12-05 |  | 2025-12-12 |  | Tower A | Super Structure
40782 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-08-22 | 2024-08-30 | FAPA Device Fixing | 100 | 0 |  | 2025-12-05 |  | 2025-12-12 |  | Tower A | Super Structure
41127 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2025-11-15 | 2025-11-22 | HVAC Ducting | 100 | 0 |  | 2025-12-05 |  | 2025-12-13 |  | Tower A | Super Structure | L11 | MEP | HVAC Ducting
42998 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-11-13 | 2025-11-24 | Cement Plastering in wet areas | 100 | 0 |  | 2025-12-05 |  | 2025-12-16 |  | Tower A | Super Structure | L51
44565 |  | Not Committed |  | 2025-01-29 | 2025-04-26 | P1 to P2 | 100 | 0 |  | 2025-12-05 |  | 2026-03-05
44565 |  | Not Committed |  | 2025-01-29 | 2025-04-26 | P1 to P2 | 100 | 0 |  | 2025-12-05 |  | 2026-03-05
44565 |  | Not Committed |  | 2025-01-29 | 2025-04-26 | P1 to P2 | 100 | 0 |  | 2025-12-05 |  | 2026-03-05
44566 | NTA_Zone 2 - Super Structure - P1 to P2 | Not Ready | Finishes (Lobby & Floor Area) | 2025-01-29 | 2025-02-14 | IPS Flooring in STP, Sub-Stn & DG Area | 100 | 0 |  | 2025-12-05 |  | 2025-12-22 |  | NTA_Zone 2 | Super Structure
45271 |  | Not Ready |  | 2025-09-30 | 2025-10-15 | L7-8 | 100 | 0 |  | 2025-12-05 |  | 2025-12-20
45271 |  | Not Ready |  | 2025-09-30 | 2025-10-15 | L7-8 | 100 | 0 |  | 2025-12-05 |  | 2025-12-20 |  |  |  |  | Finishes | Gypsum Plastering Works
45272 | Tower B - Super Structure - Core & Outer Slab L7-8 | Not Ready | RCC Works - Vertical | 2025-09-30 | 2025-10-11 | Outer Columns_TA | 100 | 0 |  | 2025-12-05 |  | 2025-12-17 |  | Tower B | Super Structure | L7 | RCC Sub Structure | RCC Works - Vertical
45721 |  | Not Ready |  | 2025-09-30 | 2027-06-07 | Shaft MEP Works | 100 | 0 |  | 2025-12-05 |  | 2027-09-01
45722 |  | Not Committed |  | 2025-09-30 | 2026-01-15 | B2-GF-L7 | 100 | 0 |  | 2025-12-05 |  | 2026-03-24
45723 | Tower B - Super Structure - Finishes & MEP - B3 to L7 | Not Ready |  | 2025-09-30 | 2025-10-24 | FHR Shaft Risers | 100 | 0 |  | 2025-12-05 |  | 2025-12-30 |  | Tower B | Super Structure | B3
45725 | Tower B - Super Structure - Finishes & MEP - B3 to L7 | Not Ready |  | 2025-09-30 | 2025-11-22 | Domestic Water & Flushing Riser in Plumbing Shaft | 100 | 0 |  | 2025-12-05 |  | 2026-01-29 |  | Tower B | Super Structure | B3
45727 | Tower B - Super Structure - Finishes & MEP - B3 to L7 | Not Ready |  | 2025-09-30 | 2025-11-05 | Shaft Cable Tray in Electrical Shaft | 100 | 0 |  | 2025-12-05 |  | 2026-01-10 |  | Tower B | Super Structure | B3
9181 | T-15-4th Floor Flat Area | Not Ready | Window | 2025-12-16 | 2026-01-07 | Window | 100 | 0 |  | 2025-12-06 |  | 2025-12-27
9255 | T-15-7th Floor Flat Area | Not Ready | Toilet flooring | 2025-12-09 | 2026-01-11 | Toilet flooring | 100 | 0 |  | 2025-12-06 |  | 2026-01-08
9560 | T-16-Terrace | Not Ready | Slab& Beam Steel & Conduting | 2025-12-20 | 2025-12-24 | Slab& Beam Steel & Conduting | 14 | 0 | MT | 2025-12-06 |  | 2025-12-10
9773 | T-16-7th Floor Flat Area | Not Ready | Plastering | 2025-12-20 | 2026-02-04 | Plastering-Gypsum | 100 | 0 |  | 2025-12-06 |  | 2026-01-21
10247 | T-21-5th Floor Flat Area | Not Ready | Window | 2025-12-12 | 2026-01-03 | Window | 100 | 0 |  | 2025-12-06 |  | 2025-12-28
10376 | T-21-10th Floor Flat Area | Not Ready | Putty | 2026-01-07 | 2026-04-02 | Putty | 100 | 0 |  | 2025-12-06 |  | 2026-02-27
10892 | T-20-10th Floor Flat Area | Not Ready | Dado | 2026-01-08 | 2026-02-06 | Dado | 100 | 0 |  | 2025-12-06 |  | 2026-01-02
11331 | T-19-7th Floor Flat Area | Not Ready | Waterproofing | 2025-12-21 | 2026-01-24 | Waterproofing | 100 | 0 |  | 2025-12-06 |  | 2026-01-10
11755 | T-18-3rd Floor Flat Area | Not Ready | Window | 2026-02-03 | 2026-02-25 | Window | 100 | 0 |  | 2025-12-06 |  | 2025-12-28
11943 | T-18-11th Floor Common Area | Not Ready | Plastering | 2026-02-17 | 2026-03-22 | Plastering-Gypsum | 100 | 0 |  | 2025-12-06 |  | 2026-01-09
39755 |  | Not Ready |  | 2025-11-11 | 2025-11-18 | Core Wall L75-76 (Penthouse) | 100 | 0 |  | 2025-12-06 |  | 2025-12-15
39756 | Tower A - Super Structure - Core Wall High Rise L75-76 | Not Ready | Core Wall RCC Works | 2025-11-11 | 2025-11-11 | Scaffolding & platform | 100 | 0 |  | 2025-12-06 |  | 2025-12-08 |  | Tower A | Super Structure | L75 | RCC Super Structure | Core Wall RCC Works
40376 | Tower A - Super Structure - Finishes & MEP - L54 to L55 | Not Ready | Partition Wall-Blockwork | 2025-11-14 | 2025-11-19 | Staircase Area | 100 | 0 |  | 2025-12-06 |  | 2025-12-11 |  | Tower A | Super Structure | L54
40379 | Tower A - Super Structure - Finishes & MEP - L55 to L56 | Not Ready | Partition Wall-Blockwork | 2025-11-14 | 2025-11-21 | Partition Walls | 100 | 0 |  | 2025-12-06 |  | 2025-12-13 |  | Tower A | Super Structure | L55
40738 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | False Ceiling - MEP & Finishes | 2024-05-15 | 2024-05-25 | False Ceiling | 100 | 0 |  | 2025-12-06 |  | 2025-12-18 |  | Tower A | Super Structure |  | Finishes | False Ceiling
40789 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2024-06-03 | 2024-06-04 | FAPA Cabling | 100 | 0 |  | 2025-12-06 |  | 2025-12-09 |  | Tower A | Super Structure
42624 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-12-26 | 2026-01-12 | Flooring & Dado works | 100 | 0 |  | 2025-12-06 |  | 2025-12-23 |  | Tower A | Super Structure | L30 | Finishes | Flooring & Dado
42678 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-01-07 | 2026-01-23 | Flooring & Dado works | 100 | 0 |  | 2025-12-06 |  | 2025-12-24 |  | Tower A | Super Structure | L33 | Finishes | Flooring & Dado
44082 | Tower A - Super Structure - Finishes & MEP - L33 to L38 | Started | Façade Works - MEP & Finishes | 2026-01-07 | 2026-01-17 | Accessories & Alignment | 100 | 10 | Units | 2025-12-06 | 2025-09-13 | 2025-12-18 |  | Tower A | Super Structure | L33 | Façade | Façade Works
44082 | Tower A - Super Structure - Finishes & MEP - L33 to L38 | Started | Façade Works - MEP & Finishes | 2026-01-07 | 2026-01-17 | Accessories & Alignment | 100 | 10 | Units | 2025-12-06 | 2025-09-13 | 2025-12-18 |  | Tower A | Super Structure | L33
48161 |  | Not Committed |  | 2025-08-02 | 2025-10-08 | Pour RT-2 | 100 | 0 |  | 2025-12-06 |  | 2026-01-29
48162 | Retail - Super structure - GF to R1 - P2 | Not Ready |  | 2025-08-02 | 2025-09-11 | Columns_RT | 100 | 0 |  | 2025-12-06 |  | 2026-01-10 |  | Retail | Super Structure | GF | RCC Sub Structure | RCC Works - Vertical
48162 | Retail - Super structure - GF to R1 - P2 | Not Ready |  | 2025-08-02 | 2025-09-11 | Columns_RT | 100 | 0 |  | 2025-12-06 |  | 2026-01-10 |  | Retail | Super Structure | GF
48168 |  | Not Committed |  | 2025-08-02 | 2025-10-08 | Pour RT-4 | 100 | 0 |  | 2025-12-06 |  | 2026-01-29
48169 | Retail - Super structure - GF to R1 - P4 | Not Ready |  | 2025-08-02 | 2025-09-11 | Columns_RT | 100 | 0 |  | 2025-12-06 |  | 2026-01-10 |  | Retail | Super Structure | GF | RCC Sub Structure | RCC Works - Vertical
48169 | Retail - Super structure - GF to R1 - P4 | Not Ready |  | 2025-08-02 | 2025-09-11 | Columns_RT | 100 | 0 |  | 2025-12-06 |  | 2026-01-10 |  | Retail | Super Structure | GF
48170 | Retail - Super structure - GF to R1 - P4 | Not Ready |  | 2025-08-02 | 2025-09-05 | Staircase_RT | 100 | 0 |  | 2025-12-06 |  | 2026-01-05 |  | Retail | Super Structure | GF | RCC Sub Structure | RCC Works - Slab
48170 | Retail - Super structure - GF to R1 - P4 | Not Ready |  | 2025-08-02 | 2025-09-05 | Staircase_RT | 100 | 0 |  | 2025-12-06 |  | 2026-01-05 |  | Retail | Super Structure | GF
8737 | T-14-8th Floor Flat Area | Not Ready | Flooring & skirting | 2025-11-06 | 2025-12-19 | Flooring & skirting | 100 | 0 |  | 2025-12-07 |  | 2026-01-18
9331 | T-15-10th Floor Flat Area | Not Ready | Plastering | 2025-12-07 | 2026-01-21 | Plastering-Gypsum | 100 | 0 |  | 2025-12-07 |  | 2026-01-21
9698 | T-16-4th Floor Flat Area | Not Ready | Toilets False Celing | 2025-12-29 | 2026-02-02 | Toilets False Celing | 100 | 0 |  | 2025-12-07 |  | 2026-01-11
10328 | T-21-8th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-01-10 | 2026-04-06 | 1st Coat Painting | 100 | 0 |  | 2025-12-07 |  | 2026-03-01
10354 | T-21-9th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-01-10 | 2026-04-06 | 1st Coat Painting | 100 | 0 |  | 2025-12-07 |  | 2026-03-01
11210 | T-19-2nd Floor Flat Area | Not Ready | Door | 2025-12-29 | 2026-01-21 | Door | 100 | 0 |  | 2025-12-07 |  | 2025-12-28
11308 | T-19-6th Floor Flat Area | Not Ready | Dado | 2025-12-23 | 2026-01-21 | Dado | 100 | 0 |  | 2025-12-07 |  | 2026-01-01
11371 | T-19-8th Floor Common Area | Not Ready | Plastering | 2025-12-21 | 2026-01-24 | Plastering-Gypsum | 100 | 0 |  | 2025-12-07 |  | 2026-01-11
11397 | T-19-9th Floor Common Area | Not Ready | Plastering | 2025-12-21 | 2026-01-24 | Plastering-Gypsum | 100 | 0 |  | 2025-12-07 |  | 2026-01-11
11810 | T-18-5th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-02-19 | 2026-05-14 | 1st Coat Painting | 100 | 0 |  | 2025-12-07 |  | 2026-03-01
10307 | T-21-7th Floor Common Area | Not Ready | Putty | 2026-01-09 | 2026-02-19 | Putty | 100 | 0 |  | 2025-12-08 |  | 2026-01-17
10774 | T-20-5th Floor Common Area | Not Ready | Flooring & skirting | 2026-01-05 | 2026-01-29 | Flooring & skirting | 100 | 0 |  | 2025-12-08 |  | 2026-01-01
10801 | T-20-6th Floor Common Area | Not Ready | Putty | 2026-01-05 | 2026-02-14 | Putty | 100 | 0 |  | 2025-12-08 |  | 2026-01-17
11212 | T-19-2nd Floor Flat Area | Not Ready | 1st Coat Painting | 2026-01-06 | 2026-03-27 | 1st Coat Painting | 100 | 0 |  | 2025-12-08 |  | 2026-02-24
11284 | T-19-5th Floor Flat Area | Not Ready | Toilets False Celing | 2025-12-22 | 2026-01-25 | Toilets False Celing | 100 | 0 |  | 2025-12-08 |  | 2026-01-09
39757 | Tower A - Super Structure - Core Wall High Rise L75-76 | Not Ready | Core Wall RCC Works | 2025-11-12 | 2025-11-14 | Reinf & Guide shoes fixing | 100 | 0 |  | 2025-12-08 |  | 2025-12-11 |  | Tower A | Super Structure | L75 | RCC Super Structure | Core Wall RCC Works
40928 | Tower A - Super Structure - Finishes & MEP - L55 to L65 | Not Ready |  | 2025-11-28 | 2025-12-20 | Electrical Rising Mains | 100 | 0 |  | 2025-12-08 |  | 2026-01-01 |  | Tower A | Super Structure | L55
41072 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2025-11-18 | 2025-11-20 | Staircase Fire Door Fixing | 100 | 0 |  | 2025-12-08 |  | 2025-12-11 |  | Tower A | Super Structure | L7
41099 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2025-11-18 | 2025-11-25 | False Ceiling | 100 | 0 |  | 2025-12-08 |  | 2025-12-16 |  | Tower A | Super Structure | L9 | Finishes | False Ceiling
41114 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-11-18 | 2025-11-28 | Flooring & Dado | 100 | 0 |  | 2025-12-08 |  | 2025-12-19 |  | Tower A | Super Structure | L10 | Finishes | Flooring & Dado
41321 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-04-30 | 2025-05-06 | Lobby Plastering | 100 | 0 |  | 2025-12-08 |  | 2025-12-12 |  | Tower A | Super Structure | L23 | Finishes | Lobby Plastering
41336 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-04-30 | 2025-05-03 | Lobby Blockwork | 100 | 0 |  | 2025-12-08 |  | 2025-12-10 |  | Tower A | Super Structure | L24 | Finishes | Blockwork
42929 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-11-15 | 2025-11-22 | Door & Window Frame work | 100 | 0 |  | 2025-12-08 |  | 2025-12-15 |  | Tower A | Super Structure | L47 | Finishes | Door & Window Frame work
9258 | T-15-7th Floor Flat Area | Not Ready | Putty | 2025-12-12 | 2026-03-06 | Putty | 100 | 0 |  | 2025-12-09 |  | 2026-03-03
9606 | T-16-GF Common Area | Not Ready | Door | 2025-12-30 | 2026-01-22 | Door | 100 | 0 |  | 2025-12-09 |  | 2025-12-30
9722 | T-16-5th Floor Flat Area | Not Ready | Dado | 2025-12-27 | 2026-01-24 | Dado | 100 | 0 |  | 2025-12-09 |  | 2026-01-07
10914 | T-20-11th Floor Flat Area | Not Ready | Plastering | 2026-01-05 | 2026-01-29 | Plastering-Cement | 100 | 0 |  | 2025-12-09 |  | 2025-12-31
11881 | T-18-8th Floor Flat Area | Not Ready | Toilet flooring | 2026-02-26 | 2026-04-01 | Toilet flooring | 100 | 0 |  | 2025-12-09 |  | 2026-01-10
11907 | T-18-9th Floor Flat Area | Not Ready | Toilet flooring | 2026-02-26 | 2026-04-01 | Toilet flooring | 100 | 0 |  | 2025-12-09 |  | 2026-01-10
39238 |  | Not Ready |  | 2025-09-24 | 2025-11-05 | HVAC Electrical Works (B02) | 100 | 0 |  | 2025-12-09 |  | 2026-01-19
39758 | Tower A - Super Structure - Core Wall High Rise L75-76 | Not Ready | Core Wall RCC Works | 2025-11-13 | 2025-11-15 | ACS Form Closing & Alignment | 100 | 0 |  | 2025-12-09 |  | 2025-12-12 |  | Tower A | Super Structure | L75 | RCC Super Structure | Core Wall RCC Works
40717 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2024-05-16 | 2024-05-21 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2025-12-09 |  | 2025-12-13 |  | Tower A | Super Structure |  | MEP | Electrical
8709 | T-14-7th Floor Flat Area | Not Ready | Toilet flooring | 2025-11-10 | 2025-12-12 | Toilet flooring | 100 | 0 |  | 2025-12-10 |  | 2026-01-12
9342 |  | Not Ready |  | 2025-12-15 | 2026-07-29 | Common Area | 100 | 0 |  | 2025-12-10 |  | 2026-07-24
40016 |  | Not Ready |  | 2025-11-11 | 2025-11-17 | L71-72 | 100 | 0 |  | 2025-12-10 |  | 2025-12-17
40016 |  | Not Ready |  | 2025-11-11 | 2025-11-17 | L71-72 | 100 | 0 |  | 2025-12-10 |  | 2025-12-17 |  |  |  |  | Finishes | Gypsum Plastering Works
40017 | Tower A - Super Structure - Core & Outer Slab L71-72 | Not Ready | RCC Works - Vertical | 2025-11-11 | 2025-11-17 | Outer Columns_TA | 100 | 0 |  | 2025-12-10 |  | 2025-12-17 |  | Tower A | Super Structure | L71 | RCC Sub Structure | RCC Works - Vertical
40109 | Tower A - Super Structure - Finishes & MEP - Sub Station | Not Ready | Sub Station - High Side Services | 2025-12-12 | 2025-12-30 | IPS Flooring & Trench Finishing | 100 | 0 |  | 2025-12-10 |  | 2025-12-27 |  | Tower A | Super Structure
40429 |  | Not Committed |  | 2025-11-11 | 2026-03-17 | L68-69 | 100 | 0 |  | 2025-12-10 |  | 2026-04-08
40429 |  | Not Committed |  | 2025-11-11 | 2026-03-17 | L68-69 | 100 | 0 |  | 2025-12-10 |  | 2026-04-08 |  |  |  |  | Finishes | Gypsum Plastering Works
40430 | Tower A - Super Structure - Finishes & MEP - L68 to L69 | Not Ready | Partition Wall-Blockwork | 2025-11-11 | 2025-11-27 | De-shuttering & Area clearance | 100 | 0 |  | 2025-12-10 |  | 2025-12-29 |  | Tower A | Super Structure | L68
41084 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2025-11-20 | 2025-11-22 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2025-12-10 |  | 2025-12-13 |  | Tower A | Super Structure | L8 | MEP | FPS 2nd Fix - MEP & Finishes
41085 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2025-11-20 | 2025-11-25 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2025-12-10 |  | 2025-12-16 |  | Tower A | Super Structure | L8 | MEP | Electrical 2nd Fix - MEP & Finishes
41086 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-11-20 | 2025-11-27 | FAPA Device Fixing | 100 | 0 |  | 2025-12-10 |  | 2025-12-18 |  | Tower A | Super Structure | L8
41086 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-11-20 | 2025-11-27 | FAPA Device Fixing | 100 | 0 |  | 2025-12-10 |  | 2025-12-18 |  | Tower A | Super Structure | L8
41086 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-11-20 | 2025-11-27 | FAPA Device Fixing | 100 | 0 |  | 2025-12-10 |  | 2025-12-18 |  | Tower A | Super Structure | L8
41086 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-11-20 | 2025-11-27 | FAPA Device Fixing | 100 | 0 |  | 2025-12-10 |  | 2025-12-18 |  | Tower A | Super Structure | L8
41087 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2025-11-20 | 2025-11-22 | HVAC Grill Fixing | 100 | 0 |  | 2025-12-10 |  | 2025-12-13 |  | Tower A | Super Structure | L8 | MEP | HVAC Grill Fixing
8664 | T-14-5th Floor Flat Area | Not Ready | 1st Coat Painting | 2025-11-18 | 2026-02-10 | 1st Coat Painting | 100 | 0 |  | 2025-12-11 |  | 2026-03-05
9280 | T-15-8th Floor Flat Area | Not Ready | Dado | 2025-12-16 | 2026-01-12 | Dado | 100 | 0 |  | 2025-12-11 |  | 2026-01-07
9306 | T-15-9th Floor Flat Area | Not Ready | Dado | 2025-12-16 | 2026-01-12 | Dado | 100 | 0 |  | 2025-12-11 |  | 2026-01-07
9561 | T-16-Terrace | Not Ready | RCC | 2025-12-24 | 2025-12-25 | Slab& Beam RCC | 387 | 0 | CUM | 2025-12-11 |  | 2025-12-11
9624 | T-16-1st Floor Flat Area | Not Ready | Door | 2026-01-02 | 2026-01-27 | Door | 100 | 0 |  | 2025-12-11 |  | 2026-01-01
9770 | T-16-7th Floor Flat Area | Not Ready | Plastering | 2025-12-26 | 2026-01-18 | Plastering-Cement | 100 | 0 |  | 2025-12-11 |  | 2026-01-06
10374 | T-21-10th Floor Flat Area | Not Ready | Toilets False Celing | 2026-01-13 | 2026-02-17 | Toilets False Celing | 100 | 0 |  | 2025-12-11 |  | 2026-01-10
10395 | T-21-11th Floor Flat Area | Not Ready | Waterproofing | 2026-01-09 | 2026-02-13 | Waterproofing | 100 | 0 |  | 2025-12-11 |  | 2026-01-11
10929 | T-20-11th Floor Common Area | Not Ready | Plastering | 2026-01-07 | 2026-02-11 | Plastering-Gypsum | 100 | 0 |  | 2025-12-11 |  | 2026-01-11
11337 | T-19-7th Floor Flat Area | Not Ready | Flooring & skirting | 2025-12-26 | 2026-02-10 | Flooring & skirting | 100 | 0 |  | 2025-12-11 |  | 2026-01-22
40018 | Tower A - Super Structure - Core & Outer Slab L71-72 | Not Ready | RCC Works - Slab | 2025-11-12 | 2025-11-17 | Outer Slab_TA | 100 | 0 |  | 2025-12-11 |  | 2025-12-17 |  | Tower A | Super Structure | L71 | RCC Sub Structure | RCC Works - Slab
40790 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2024-06-07 | 2024-06-14 | HVAC Ducting | 100 | 0 |  | 2025-12-11 |  | 2025-12-19 |  | Tower A | Super Structure |  | MEP | HVAC Ducting
40791 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2024-06-07 | 2024-06-25 | Flooring & Dado | 100 | 0 |  | 2025-12-11 |  | 2025-12-30 |  | Tower A | Super Structure |  | Finishes | Flooring & Dado
40813 |  | Not Committed |  | 2024-06-18 | 2024-08-22 | Lobby/ Common Area | 100 | 0 |  | 2025-12-11 |  | 2026-02-02
40814 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2024-06-18 | 2024-06-25 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-12-11 |  | 2025-12-19 |  | Tower A | Super Structure |  | MEP | FPS 1st Fix - MEP & Finishes
40815 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2024-06-18 | 2024-06-20 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-12-11 |  | 2025-12-15 |  | Tower A | Super Structure |  | MEP | Electrical 1st Fixes
41073 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2025-11-21 | 2025-11-26 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2025-12-11 |  | 2025-12-17 |  | Tower A | Super Structure | L7 | MEP | Electrical
41143 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2025-11-21 | 2025-11-28 | HVAC Ducting | 100 | 0 |  | 2025-12-11 |  | 2025-12-19 |  | Tower A | Super Structure | L12 | MEP | HVAC Ducting
41337 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-05-05 | 2025-05-09 | Lobby Plastering | 100 | 0 |  | 2025-12-11 |  | 2025-12-16 |  | Tower A | Super Structure | L24 | Finishes | Lobby Plastering
41352 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-05-05 | 2025-05-07 | Lobby Blockwork | 100 | 0 |  | 2025-12-11 |  | 2025-12-13 |  | Tower A | Super Structure | L25 | Finishes | Blockwork
47641 |  | Not Ready |  | 2025-12-11 | 2025-12-18 | Section 7_lift 1 | 100 | 0 |  | 2025-12-11 |  | 2025-12-18
47641 |  | Not Ready |  | 2025-12-11 | 2025-12-18 | Section 7_lift 1 | 100 | 0 |  | 2025-12-11 |  | 2025-12-18 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
48216 |  | Not Committed |  | 2025-05-27 | 2026-09-10 | MEP 1st Fixes (all trades) | 100 | 0 |  | 2025-12-11 |  | 2027-03-04
48217 |  | Not Committed |  | 2025-05-27 | 2026-02-20 | Basement | 100 | 0 |  | 2025-12-11 |  | 2026-08-04
48219 | Retail & Clubhouse - Sub structure - B2 to B1 | Not Ready |  | 2025-05-27 | 2025-09-01 | B2 to B1 (Fire, Domestic, Flush, Maintenance water, Rain water Tanks, Chiller pump room, Ventilation Fan Rooms) | 100 | 0 |  | 2025-12-11 |  | 2026-03-11 |  | Club House | Sub Structure | B2
48220 | Retail & Clubhouse - Sub structure - B1 to GF | Not Ready |  | 2025-08-11 | 2025-11-13 | B1 to GF (FTTH, Data, Tel., Plant, Fan Rooms) | 100 | 0 |  | 2025-12-11 |  | 2026-03-11 |  | Club House | Sub Structure | B1
8636 | T-14-4th Floor Flat Area | Not Ready | Door | 2025-11-25 | 2025-12-17 | Door | 100 | 0 |  | 2025-12-12 |  | 2026-01-03
9210 | T-15-5th Floor Flat Area | Not Ready | 1st Coat Painting | 2025-12-17 | 2026-03-11 | 1st Coat Painting | 100 | 0 |  | 2025-12-12 |  | 2026-03-06
9328 | T-15-10th Floor Flat Area | Not Ready | Plastering | 2025-12-12 | 2026-01-03 | Plastering-Cement | 100 | 0 |  | 2025-12-12 |  | 2026-01-02
9745 | T-16-6th Floor Flat Area | Not Ready | Waterproofing | 2025-12-28 | 2026-02-01 | Waterproofing | 100 | 0 |  | 2025-12-12 |  | 2026-01-16
9794 | T-16-8th Floor Flat Area | Not Ready | Blockwork | 2025-12-25 | 2026-01-17 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-12-12 |  | 2026-01-04
9820 | T-16-9th Floor Flat Area | Not Ready | Blockwork | 2025-12-25 | 2026-01-17 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-12-12 |  | 2026-01-04
9833 | T-16-9th Floor Flat Area | Not Ready | Railing | 2025-12-25 | 2026-01-29 | Balcony Railing | 100 | 0 |  | 2025-12-12 |  | 2026-01-15
9859 | T-16-10th Floor Flat Area | Not Ready | Railing | 2025-12-25 | 2026-01-29 | Balcony Railing | 100 | 0 |  | 2025-12-12 |  | 2026-01-15
11884 | T-18-8th Floor Flat Area | Not Ready | Putty | 2026-03-02 | 2026-05-24 | Putty | 100 | 0 |  | 2025-12-12 |  | 2026-03-06
11910 | T-18-9th Floor Flat Area | Not Ready | Putty | 2026-03-02 | 2026-05-24 | Putty | 100 | 0 |  | 2025-12-12 |  | 2026-03-06
39759 | Tower A - Super Structure - Core Wall High Rise L75-76 | Not Ready | Core Wall RCC Works | 2025-11-17 | 2025-11-17 | Casting | 100 | 0 |  | 2025-12-12 |  | 2025-12-13 |  | Tower A | Super Structure | L75 | RCC Super Structure | Core Wall RCC Works
40527 | Tower A - Super Structure - Finishes & MEP - L53 to L54 | Not Ready | Gypsum Plastering Works | 2025-11-20 | 2025-12-06 | L53-54 | 100 | 0 |  | 2025-12-12 |  | 2025-12-30 |  | Tower A | Super Structure | L53 | Finishes | Gypsum Plastering Works
40527 | Tower A - Super Structure - Finishes & MEP - L53 to L54 | Not Ready | Gypsum Plastering Works | 2025-11-20 | 2025-12-06 | L53-54 | 100 | 0 |  | 2025-12-12 |  | 2025-12-30 |  | Tower A | Super Structure | L53
42642 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-01-01 | 2026-01-17 | Flooring & Dado works | 100 | 0 |  | 2025-12-12 |  | 2025-12-30 |  | Tower A | Super Structure | L31 | Finishes | Flooring & Dado
42696 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-01-13 | 2026-01-30 | Flooring & Dado works | 100 | 0 |  | 2025-12-12 |  | 2025-12-31 |  | Tower A | Super Structure | L34 | Finishes | Flooring & Dado
43046 |  | Not Committed |  | 2025-11-20 | 2026-09-12 | L54-55 | 100 | 0 |  | 2025-12-12 |  | 2026-08-26
43046 |  | Not Committed |  | 2025-11-20 | 2026-09-12 | L54-55 | 100 | 0 |  | 2025-12-12 |  | 2026-08-26 |  |  |  |  | Finishes | Gypsum Plastering Works
43047 |  | Not Committed |  | 2025-11-20 | 2025-12-18 | MEP 1st Fixes | 100 | 0 |  | 2025-12-12 |  | 2026-01-10
43048 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2025-11-20 | 2025-11-27 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-12-12 |  | 2025-12-19 |  | Tower A | Super Structure | L54 | MEP | FPS 1st Fix - MEP & Finishes
43049 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-11-20 | 2025-11-25 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2025-12-12 |  | 2025-12-17 |  | Tower A | Super Structure | L54 | MEP | Electrical 1st Fixes
43050 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2025-11-20 | 2025-11-27 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2025-12-12 |  | 2025-12-19 |  | Tower A | Super Structure | L54
43051 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2025-11-20 | 2025-12-06 | Wet Area Waterproofing | 100 | 0 |  | 2025-12-12 |  | 2025-12-30 |  | Tower A | Super Structure | L54
45273 | Tower B - Super Structure - Core & Outer Slab L7-8 | Not Ready | RCC Works - Slab | 2025-10-08 | 2025-10-15 | Outer Slab_TA | 100 | 0 |  | 2025-12-12 |  | 2025-12-20 |  | Tower B | Super Structure | L7 | RCC Sub Structure | RCC Works - Slab
48058 |  | Not Committed |  | 2025-08-12 | 2025-11-13 | Spanish Steps from Plaza | 100 | 0 |  | 2025-12-12 |  | 2026-03-06
48059 | Retail & Clubhouse - Super structure - GF to R1 | Not Ready |  | 2025-08-12 | 2025-09-20 | GF to R1 | 100 | 0 |  | 2025-12-12 |  | 2026-01-16 |  | Club House | Sub Structure | GF
8712 | T-14-7th Floor Flat Area | Not Ready | Putty | 2025-11-13 | 2026-02-05 | Putty | 100 | 0 |  | 2025-12-13 |  | 2026-03-07
9785 | T-16-7th Floor Common Area | Not Ready |  | 2025-12-28 | 2026-02-01 | Plastering Gypsum | 100 | 0 |  | 2025-12-13 |  | 2026-01-17
10228 | T-21-4th Floor Common Area | Not Ready | Flooring & skirting | 2026-01-16 | 2026-02-08 | Flooring & skirting | 100 | 0 |  | 2025-12-13 |  | 2026-01-03
10255 | T-21-5th Floor Common Area | Not Ready | Putty | 2026-01-16 | 2026-02-24 | Putty | 100 | 0 |  | 2025-12-13 |  | 2026-01-20
10797 | T-20-6th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-01-22 | 2026-03-31 | 2nd Coat Painting | 100 | 0 |  | 2025-12-13 |  | 2026-02-19
10893 | T-20-10th Floor Flat Area | Not Ready | Toilet flooring | 2026-01-16 | 2026-02-19 | Toilet flooring | 100 | 0 |  | 2025-12-13 |  | 2026-01-12
11840 | T-18-6th Floor Common Area | Not Ready | Flooring & skirting | 2026-02-23 | 2026-03-17 | Flooring & skirting | 100 | 0 |  | 2025-12-13 |  | 2026-01-04
11942 |  | Not Ready |  | 2026-02-17 | 2026-10-01 | Common Area | 100 | 0 |  | 2025-12-13 |  | 2026-08-01
39760 | Tower A - Super Structure - Core Wall High Rise L75-76 | Not Ready | Core Wall RCC Works | 2025-11-18 | 2025-11-18 | ACS Form Release & jump to next level | 100 | 0 |  | 2025-12-13 |  | 2025-12-15 |  | Tower A | Super Structure | L75 | RCC Super Structure | Core Wall RCC Works
40053 | Tower A - Super Structure - Finishes & MEP - L45 to L46 | Not Ready | CTU Elevators Crash Deck - High Side Services | 2025-05-07 | 2025-06-09 | Guide Rail Installation by rising platform (only car guide rails) | 100 | 0 |  | 2025-12-13 |  | 2026-01-15 |  | Tower A | Super Structure | L45
40053 | Tower A - Super Structure - Finishes & MEP - L45 to L46 | Not Ready | CTU Elevators Crash Deck - High Side Services | 2025-05-07 | 2025-06-09 | Guide Rail Installation by rising platform (only car guide rails) | 100 | 0 |  | 2025-12-13 |  | 2026-01-15 |  | Tower A | Super Structure | L45
40053 | Tower A - Super Structure - Finishes & MEP - L45 to L46 | Not Ready | CTU Elevators Crash Deck - High Side Services | 2025-05-07 | 2025-06-09 | Guide Rail Installation by rising platform (only car guide rails) | 100 | 0 |  | 2025-12-13 |  | 2026-01-15 |  | Tower A | Super Structure | L45
40700 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2024-07-30 | 2024-08-07 | HVAC Grill Fixing | 100 | 0 |  | 2025-12-13 |  | 2025-12-20 |  | Tower A | Super Structure | GF | MEP | HVAC Grill Fixing
40783 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2024-09-03 | 2024-09-12 | Final Painting | 100 | 0 |  | 2025-12-13 |  | 2025-12-22 |  | Tower A | Super Structure |  | Finishes | Final Painting
40783 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2024-09-03 | 2024-09-12 | Final Painting | 100 | 0 |  | 2025-12-13 |  | 2025-12-22 |  | Tower A | Super Structure |  | Finishes | Final Painting
40783 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2024-09-03 | 2024-09-12 | Final Painting | 100 | 0 |  | 2025-12-13 |  | 2025-12-22 |  | Tower A | Super Structure |  | Finishes | Final Painting
41088 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2025-11-24 | 2025-11-26 | Staircase Fire Door Fixing | 100 | 0 |  | 2025-12-13 |  | 2025-12-17 |  | Tower A | Super Structure | L8
41115 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2025-11-24 | 2025-12-01 | False Ceiling | 100 | 0 |  | 2025-12-13 |  | 2025-12-22 |  | Tower A | Super Structure | L10 | Finishes | False Ceiling
41130 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-11-24 | 2025-12-04 | Flooring & Dado | 100 | 0 |  | 2025-12-13 |  | 2025-12-26 |  | Tower A | Super Structure | L11 | Finishes | Flooring & Dado
43016 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-11-21 | 2025-12-02 | Cement Plastering in wet areas | 100 | 0 |  | 2025-12-13 |  | 2025-12-24 |  | Tower A | Super Structure | L52
9256 | T-15-7th Floor Flat Area | Not Ready | Toilets False Celing | 2025-12-18 | 2026-01-21 | Toilets False Celing | 100 | 0 |  | 2025-12-14 |  | 2026-01-13
9343 | T-15-11th Floor Common Area | Not Ready | Plastering | 2025-12-15 | 2026-01-17 | Plastering-Gypsum | 100 | 0 |  | 2025-12-14 |  | 2026-01-13
9798 | T-16-8th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-12-27 | 2026-01-13 | Electrical DB Fixing | 100 | 0 |  | 2025-12-14 |  | 2026-01-02
9824 | T-16-9th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-12-27 | 2026-01-13 | Electrical DB Fixing | 100 | 0 |  | 2025-12-14 |  | 2026-01-02
9862 |  | Not Ready |  | 2026-02-12 | 2026-09-26 | Common Area | 100 | 0 |  | 2025-12-14 |  | 2026-07-29
11235 | T-19-3rd Floor Flat Area | Not Ready | Window | 2026-01-05 | 2026-01-29 | Window | 100 | 0 |  | 2025-12-14 |  | 2026-01-05
11309 | T-19-6th Floor Flat Area | Not Ready | Toilet flooring | 2025-12-31 | 2026-02-04 | Toilet flooring | 100 | 0 |  | 2025-12-14 |  | 2026-01-16
11756 | T-18-3rd Floor Flat Area | Not Ready | Door | 2026-02-12 | 2026-03-05 | Door | 100 | 0 |  | 2025-12-14 |  | 2026-01-05
8757 | T-14-9th Floor Flat Area | Not Ready | Waterproofing | 2025-11-14 | 2025-12-17 | Waterproofing | 100 | 0 |  | 2025-12-15 |  | 2026-01-17
9182 | T-15-4th Floor Flat Area | Not Ready | Door | 2025-12-25 | 2026-01-17 | Door | 100 | 0 |  | 2025-12-15 |  | 2026-01-02
9565 | T-16-Terrace | Not Ready | PARAPET | 2025-12-28 | 2026-02-17 | PARAPET | 100 | 0 |  | 2025-12-15 |  | 2026-02-04
10358 | T-21-9th Floor Common Area | Not Ready | Flooring & skirting | 2026-01-22 | 2026-02-13 | Flooring & skirting | 100 | 0 |  | 2025-12-15 |  | 2026-01-05
10820 | T-20-7th Floor Flat Area | Not Ready | Door | 2026-02-02 | 2026-02-24 | Door | 100 | 0 |  | 2025-12-15 |  | 2026-01-05
39761 |  | Not Ready |  | 2025-11-19 | 2025-11-26 | Core Wall L76-77 | 100 | 0 |  | 2025-12-15 |  | 2025-12-23
39762 | Tower A - Super Structure - Core Wall High Rise L76-77 | Not Ready | Core Wall RCC Works | 2025-11-19 | 2025-11-19 | Scaffolding & platform | 100 | 0 |  | 2025-12-15 |  | 2025-12-16 |  | Tower A | Super Structure | L76 | RCC Super Structure | Core Wall RCC Works
40071 | Tower A - Super Structure - Finishes & MEP - L70 to L71 | Not Ready | CTU Elevators Crash Deck - High Side Services | 2025-11-15 | 2025-11-22 | Plumb check & door centre line by Lift agency for lobby blockwork | 100 | 0 |  | 2025-12-15 |  | 2025-12-23 |  | Tower A | Super Structure | L70
40071 | Tower A - Super Structure - Finishes & MEP - L70 to L71 | Not Ready | CTU Elevators Crash Deck - High Side Services | 2025-11-15 | 2025-11-22 | Plumb check & door centre line by Lift agency for lobby blockwork | 100 | 0 |  | 2025-12-15 |  | 2025-12-23 |  | Tower A | Super Structure | L70
40071 | Tower A - Super Structure - Finishes & MEP - L70 to L71 | Not Ready | CTU Elevators Crash Deck - High Side Services | 2025-11-15 | 2025-11-22 | Plumb check & door centre line by Lift agency for lobby blockwork | 100 | 0 |  | 2025-12-15 |  | 2025-12-23 |  | Tower A | Super Structure | L70
40072 | Tower A - Super Structure - Finishes & MEP - L70 to L71 | Not Ready | CTU Elevators Crash Deck - High Side Services | 2025-11-15 | 2025-11-22 | Shaft clearance & White Wash up to L65 | 100 | 0 |  | 2025-12-15 |  | 2025-12-23 |  | Tower A | Super Structure | L70
40380 | Tower A - Super Structure - Finishes & MEP - L55 to L56 | Not Ready | Partition Wall-Blockwork | 2025-11-22 | 2025-11-27 | Staircase Area | 100 | 0 |  | 2025-12-15 |  | 2025-12-19 |  | Tower A | Super Structure | L55
40383 | Tower A - Super Structure - Finishes & MEP - L56 to L57 | Not Ready | Partition Wall-Blockwork | 2025-11-22 | 2025-11-29 | Partition Walls | 100 | 0 |  | 2025-12-15 |  | 2025-12-22 |  | Tower A | Super Structure | L56
40718 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2024-05-22 | 2024-05-27 | Final Painting | 100 | 0 |  | 2025-12-15 |  | 2025-12-19 |  | Tower A | Super Structure |  | Finishes | Final Painting
40718 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2024-05-22 | 2024-05-27 | Final Painting | 100 | 0 |  | 2025-12-15 |  | 2025-12-19 |  | Tower A | Super Structure |  | Finishes | Final Painting
40718 | Tower A - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2024-05-22 | 2024-05-27 | Final Painting | 100 | 0 |  | 2025-12-15 |  | 2025-12-19 |  | Tower A | Super Structure |  | Finishes | Final Painting
40765 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | False Ceiling - MEP & Finishes | 2024-06-01 | 2024-06-12 | False Ceiling | 100 | 0 |  | 2025-12-15 |  | 2025-12-27 |  | Tower A | Super Structure |  | Finishes | False Ceiling
40816 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2024-06-21 | 2024-06-22 | FAPA Cabling | 100 | 0 |  | 2025-12-15 |  | 2025-12-17 |  | Tower A | Super Structure
41353 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-05-08 | 2025-05-13 | Lobby Plastering | 100 | 0 |  | 2025-12-15 |  | 2025-12-19 |  | Tower A | Super Structure | L25 | Finishes | Lobby Plastering
41368 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-05-08 | 2025-05-10 | Lobby Blockwork | 100 | 0 |  | 2025-12-15 |  | 2025-12-17 |  | Tower A | Super Structure | L26 | Finishes | Blockwork
8661 | T-14-5th Floor Flat Area | Not Ready | Window | 2025-11-29 | 2025-12-22 | Window | 100 | 0 |  | 2025-12-16 |  | 2026-01-09
9678 | T-16-3rd Floor Flat Area | Not Ready | 1st Coat Painting | 2026-01-16 | 2026-04-10 | 1st Coat Painting | 100 | 0 |  | 2025-12-16 |  | 2026-03-10
9723 | T-16-5th Floor Flat Area | Not Ready | Toilet flooring | 2026-01-03 | 2026-02-07 | Toilet flooring | 100 | 0 |  | 2025-12-16 |  | 2026-01-16
10401 | T-21-11th Floor Flat Area | Not Ready | Flooring & skirting | 2026-01-16 | 2026-03-02 | Flooring & skirting | 100 | 0 |  | 2025-12-16 |  | 2026-01-30
10848 | T-20-8th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-01-23 | 2026-04-17 | 1st Coat Painting | 100 | 0 |  | 2025-12-16 |  | 2026-03-10
10852 | T-20-8th Floor Common Area | Not Ready | Flooring & skirting | 2026-01-16 | 2026-02-09 | Flooring & skirting | 100 | 0 |  | 2025-12-16 |  | 2026-01-06
10874 | T-20-9th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-01-23 | 2026-04-17 | 1st Coat Painting | 100 | 0 |  | 2025-12-16 |  | 2026-03-10
10896 | T-20-10th Floor Flat Area | Not Ready | Putty | 2026-01-20 | 2026-04-14 | Putty | 100 | 0 |  | 2025-12-16 |  | 2026-03-10
39239 |  | Not Ready |  | 2025-09-30 | 2025-11-11 | End Terminations @ Chiller Rooms and Cooling Tower (B02 and GF) | 100 | 0 |  | 2025-12-16 |  | 2026-01-26
39763 | Tower A - Super Structure - Core Wall High Rise L76-77 | Not Ready | Core Wall RCC Works | 2025-11-20 | 2025-11-22 | Reinf & Guide shoes fixing | 100 | 0 |  | 2025-12-16 |  | 2025-12-19 |  | Tower A | Super Structure | L76 | RCC Super Structure | Core Wall RCC Works
41100 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2025-11-26 | 2025-11-28 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2025-12-16 |  | 2025-12-19 |  | Tower A | Super Structure | L9 | MEP | FPS 2nd Fix - MEP & Finishes
41101 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2025-11-26 | 2025-12-01 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2025-12-16 |  | 2025-12-22 |  | Tower A | Super Structure | L9 | MEP | Electrical 2nd Fix - MEP & Finishes
41102 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-11-26 | 2025-12-03 | FAPA Device Fixing | 100 | 0 |  | 2025-12-16 |  | 2025-12-24 |  | Tower A | Super Structure | L9
41102 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-11-26 | 2025-12-03 | FAPA Device Fixing | 100 | 0 |  | 2025-12-16 |  | 2025-12-24 |  | Tower A | Super Structure | L9
41102 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-11-26 | 2025-12-03 | FAPA Device Fixing | 100 | 0 |  | 2025-12-16 |  | 2025-12-24 |  | Tower A | Super Structure | L9
41102 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-11-26 | 2025-12-03 | FAPA Device Fixing | 100 | 0 |  | 2025-12-16 |  | 2025-12-24 |  | Tower A | Super Structure | L9
41103 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2025-11-26 | 2025-11-28 | HVAC Grill Fixing | 100 | 0 |  | 2025-12-16 |  | 2025-12-19 |  | Tower A | Super Structure | L9 | MEP | HVAC Grill Fixing
42947 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-11-24 | 2025-12-01 | Door & Window Frame work | 100 | 0 |  | 2025-12-16 |  | 2025-12-23 |  | Tower A | Super Structure | L48 | Finishes | Door & Window Frame work
8734 | T-14-8th Floor Flat Area | Not Ready | Dado | 2025-11-17 | 2025-12-13 | Dado | 100 | 0 |  | 2025-12-17 |  | 2026-01-11
9563 | T-16-Terrace | Not Ready | LMR ROOM | 2025-12-30 | 2026-02-19 | LMR ROOM | 100 | 0 |  | 2025-12-17 |  | 2026-02-04
9566 | T-16-Terrace | Not Ready | STAIRCASE HR | 2025-12-30 | 2026-02-19 | STAIRCASE HR | 100 | 0 |  | 2025-12-17 |  | 2026-02-04
9751 | T-16-6th Floor Flat Area | Not Ready | Flooring & skirting | 2026-01-02 | 2026-02-17 | Flooring & skirting | 100 | 0 |  | 2025-12-17 |  | 2026-01-29
10248 | T-21-5th Floor Flat Area | Not Ready | Door | 2025-12-24 | 2026-01-16 | Door | 100 | 0 |  | 2025-12-17 |  | 2026-01-06
10845 | T-20-8th Floor Flat Area | Not Ready | Window | 2026-02-04 | 2026-02-26 | Window | 100 | 0 |  | 2025-12-17 |  | 2026-01-09
11264 | T-19-4th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-01-07 | 2026-04-02 | 1st Coat Painting | 100 | 0 |  | 2025-12-17 |  | 2026-03-11
11312 | T-19-6th Floor Flat Area | Not Ready | Putty | 2026-01-03 | 2026-03-29 | Putty | 100 | 0 |  | 2025-12-17 |  | 2026-03-11
11882 | T-18-8th Floor Flat Area | Not Ready | Toilets False Celing | 2026-03-07 | 2026-04-09 | Toilets False Celing | 100 | 0 |  | 2025-12-17 |  | 2026-01-20
11908 | T-18-9th Floor Flat Area | Not Ready | Toilets False Celing | 2026-03-07 | 2026-04-09 | Toilets False Celing | 100 | 0 |  | 2025-12-17 |  | 2026-01-20
39764 | Tower A - Super Structure - Core Wall High Rise L76-77 | Not Ready | Core Wall RCC Works | 2025-11-21 | 2025-11-24 | ACS Form Closing & Alignment | 100 | 0 |  | 2025-12-17 |  | 2025-12-20 |  | Tower A | Super Structure | L76 | RCC Super Structure | Core Wall RCC Works
40019 |  | Not Ready |  | 2025-11-18 | 2025-11-24 | L72-73 | 100 | 0 |  | 2025-12-17 |  | 2025-12-24
40019 |  | Not Ready |  | 2025-11-18 | 2025-11-24 | L72-73 | 100 | 0 |  | 2025-12-17 |  | 2025-12-24 |  |  |  |  | Finishes | Gypsum Plastering Works
40020 | Tower A - Super Structure - Core & Outer Slab L72-73 | Not Ready | RCC Works - Vertical | 2025-11-18 | 2025-11-24 | Outer Columns_TA | 100 | 0 |  | 2025-12-17 |  | 2025-12-24 |  | Tower A | Super Structure | L72 | RCC Sub Structure | RCC Works - Vertical
40433 |  | Not Committed |  | 2025-11-18 | 2026-03-19 | L69-70 | 100 | 0 |  | 2025-12-17 |  | 2026-04-10
40433 |  | Not Committed |  | 2025-11-18 | 2026-03-19 | L69-70 | 100 | 0 |  | 2025-12-17 |  | 2026-04-10 |  |  |  |  | Finishes | Gypsum Plastering Works
40434 | Tower A - Super Structure - Finishes & MEP - L69 to L70 | Not Ready | Partition Wall-Blockwork | 2025-11-18 | 2025-12-04 | De-shuttering & Area clearance | 100 | 0 |  | 2025-12-17 |  | 2026-01-05 |  | Tower A | Super Structure | L69
41074 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2025-11-27 | 2025-12-02 | Final Painting | 100 | 0 |  | 2025-12-17 |  | 2025-12-23 |  | Tower A | Super Structure | L7 | Finishes | Final Painting
41074 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2025-11-27 | 2025-12-02 | Final Painting | 100 | 0 |  | 2025-12-17 |  | 2025-12-23 |  | Tower A | Super Structure | L7 | Finishes | Final Painting
41074 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2025-11-27 | 2025-12-02 | Final Painting | 100 | 0 |  | 2025-12-17 |  | 2025-12-23 |  | Tower A | Super Structure | L7 | Finishes | Final Painting
41089 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2025-11-27 | 2025-12-02 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2025-12-17 |  | 2025-12-23 |  | Tower A | Super Structure | L8 | MEP | Electrical
41159 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2025-11-27 | 2025-12-04 | HVAC Ducting | 100 | 0 |  | 2025-12-17 |  | 2025-12-26 |  | Tower A | Super Structure | L13 | MEP | HVAC Ducting
42983 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-11-25 | 2025-12-02 | Door & Window Frame work | 100 | 0 |  | 2025-12-17 |  | 2025-12-24 |  | Tower A | Super Structure | L50 | Finishes | Door & Window Frame work
42999 |  | Not Committed |  | 2025-11-25 | 2026-04-06 | Finishes after 1st Fix | 100 | 0 |  | 2025-12-17 |  | 2026-03-07
43000 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-11-25 | 2025-12-17 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-12-17 |  | 2026-01-09 |  | Tower A | Super Structure | L51 | Finishes | Blockwork
8710 | T-14-7th Floor Flat Area | Not Ready | Toilets False Celing | 2025-11-19 | 2025-12-22 | Toilets False Celing | 100 | 0 |  | 2025-12-18 |  | 2026-01-18
9281 | T-15-8th Floor Flat Area | Not Ready | Toilet flooring | 2025-12-23 | 2026-01-27 | Toilet flooring | 100 | 0 |  | 2025-12-18 |  | 2026-01-21
9307 | T-15-9th Floor Flat Area | Not Ready | Toilet flooring | 2025-12-23 | 2026-01-27 | Toilet flooring | 100 | 0 |  | 2025-12-18 |  | 2026-01-21
40021 | Tower A - Super Structure - Core & Outer Slab L72-73 | Not Ready | RCC Works - Slab | 2025-11-19 | 2025-11-24 | Outer Slab_TA | 100 | 0 |  | 2025-12-18 |  | 2025-12-24 |  | Tower A | Super Structure | L72 | RCC Sub Structure | RCC Works - Slab
40739 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2024-05-27 | 2024-05-29 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2025-12-18 |  | 2025-12-22 |  | Tower A | Super Structure |  | MEP | FPS 2nd Fix - MEP & Finishes
40740 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2024-05-27 | 2024-05-31 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2025-12-18 |  | 2025-12-24 |  | Tower A | Super Structure |  | MEP | Electrical 2nd Fix - MEP & Finishes
40741 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-05-27 | 2024-06-03 | FAPA Device Fixing | 100 | 0 |  | 2025-12-18 |  | 2025-12-27 |  | Tower A | Super Structure
40741 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-05-27 | 2024-06-03 | FAPA Device Fixing | 100 | 0 |  | 2025-12-18 |  | 2025-12-27 |  | Tower A | Super Structure
40741 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-05-27 | 2024-06-03 | FAPA Device Fixing | 100 | 0 |  | 2025-12-18 |  | 2025-12-27 |  | Tower A | Super Structure
40741 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-05-27 | 2024-06-03 | FAPA Device Fixing | 100 | 0 |  | 2025-12-18 |  | 2025-12-27 |  | Tower A | Super Structure
40742 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2024-05-27 | 2024-05-29 | HVAC Grill Fixing | 100 | 0 |  | 2025-12-18 |  | 2025-12-22 |  | Tower A | Super Structure |  | MEP | HVAC Grill Fixing
41369 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-05-12 | 2025-05-16 | Lobby Plastering | 100 | 0 |  | 2025-12-18 |  | 2025-12-23 |  | Tower A | Super Structure | L26 | Finishes | Lobby Plastering
41384 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-05-12 | 2025-05-14 | Lobby Blockwork | 100 | 0 |  | 2025-12-18 |  | 2025-12-20 |  | Tower A | Super Structure | L27 | Finishes | Blockwork
42660 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-01-07 | 2026-01-23 | Flooring & Dado works | 100 | 0 |  | 2025-12-18 |  | 2026-01-05 |  | Tower A | Super Structure | L32 | Finishes | Flooring & Dado
42714 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-01-19 | 2026-02-05 | Flooring & Dado works | 100 | 0 |  | 2025-12-18 |  | 2026-01-06 |  | Tower A | Super Structure | L35 | Finishes | Flooring & Dado
44085 | Tower A - Super Structure - Finishes & MEP - L38 to L43 | Started | Façade Works - MEP & Finishes | 2026-01-19 | 2026-01-30 | DGU Assembly Installation | 100 | 5 | Units | 2025-12-18 | 2025-09-13 | 2025-12-31 |  | Tower A | Super Structure | L38 | Façade | Façade Works
44086 | Tower A - Super Structure - Finishes & MEP - L38 to L43 | Started | Façade Works - MEP & Finishes | 2026-01-19 | 2026-02-11 | Installation of highly reflective metal sheet | 100 | 5 | Units | 2025-12-18 | 2025-09-14 | 2026-01-12 |  | Tower A | Super Structure | L38 | Façade | Façade Works
44087 | Tower A - Super Structure - Finishes & MEP - L38 to L43 | Started | Façade Works - MEP & Finishes | 2026-01-19 | 2026-01-30 | Fixing of Backlit Laminated Glass assembly & ACP Panels | 100 | 5 | Units | 2025-12-18 | 2025-09-15 | 2025-12-31 |  | Tower A | Super Structure | L38 | Façade | Façade Works
44088 | Tower A - Super Structure - Finishes & MEP - L38 to L43 | Started | Façade Works - MEP & Finishes | 2026-01-19 | 2026-01-30 | Fixing of Louvers | 100 | 5 | Units | 2025-12-18 | 2025-09-18 | 2025-12-31 |  | Tower A | Super Structure | L38 | Façade | Façade Works
44088 | Tower A - Super Structure - Finishes & MEP - L38 to L43 | Started | Façade Works - MEP & Finishes | 2026-01-19 | 2026-01-30 | Fixing of Louvers | 100 | 5 | Units | 2025-12-18 | 2025-09-18 | 2025-12-31 |  | Tower A | Super Structure | L38
48180 |  | Not Committed |  | 2025-08-22 | 2025-11-26 | R1 to CH00 (7.32m) | 100 | 0 |  | 2025-12-18 |  | 2026-03-19
48196 |  | Not Committed |  | 2025-08-22 | 2025-10-08 | Pour RT-5 | 100 | 0 |  | 2025-12-18 |  | 2026-01-29
48197 | Retail - Super structure - R1 to CH00 - P5 | Not Ready |  | 2025-08-22 | 2025-09-23 | Columns_RT | 100 | 0 |  | 2025-12-18 |  | 2026-01-16 |  | Retail | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
48197 | Retail - Super structure - R1 to CH00 - P5 | Not Ready |  | 2025-08-22 | 2025-09-23 | Columns_RT | 100 | 0 |  | 2025-12-18 |  | 2026-01-16 |  | Retail | Super Structure
48198 | Retail - Super structure - R1 to CH00 - P5 | Not Ready |  | 2025-08-22 | 2025-09-23 | Staircase_RT | 100 | 0 |  | 2025-12-18 |  | 2026-01-16 |  | Retail | Super Structure |  | RCC Sub Structure | RCC Works - Slab
48198 | Retail - Super structure - R1 to CH00 - P5 | Not Ready |  | 2025-08-22 | 2025-09-23 | Staircase_RT | 100 | 0 |  | 2025-12-18 |  | 2026-01-16 |  | Retail | Super Structure
8830 |  | Not Ready |  | 2025-12-18 | 2026-08-19 | Twelfth Floor | 100 | 0 |  | 2025-12-19 |  | 2026-08-21
8831 |  | Not Ready |  | 2025-12-18 | 2026-08-19 | Flat Area | 100 | 0 |  | 2025-12-19 |  | 2026-08-21
9207 | T-15-5th Floor Flat Area | Not Ready | Window | 2025-12-30 | 2026-01-22 | Window | 100 | 0 |  | 2025-12-19 |  | 2026-01-12
9568 |  | Not Ready |  | 2026-01-01 | 2026-01-19 | Lowering Aluminium FW Material For PH-2 | 100 | 0 |  | 2025-12-19 |  | 2026-01-06
9649 | T-16-2nd Floor Flat Area | Not Ready | Window | 2026-01-12 | 2026-02-04 | Window | 100 | 0 |  | 2025-12-19 |  | 2026-01-09
9795 | T-16-8th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2026-01-01 | 2026-01-24 | Plumbing Pipe Line | 100 | 0 |  | 2025-12-19 |  | 2026-01-09
9821 | T-16-9th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2026-01-01 | 2026-01-24 | Plumbing Pipe Line | 100 | 0 |  | 2025-12-19 |  | 2026-01-09
10273 | T-21-6th Floor Flat Area | Not Ready | Window | 2025-12-26 | 2026-01-19 | Window | 100 | 0 |  | 2025-12-19 |  | 2026-01-12
11836 | T-18-6th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-03-06 | 2026-05-28 | 1st Coat Painting | 100 | 0 |  | 2025-12-19 |  | 2026-03-12
11929 | T-18-10th Floor Flat Area | Not Ready | Waterproofing | 2026-03-04 | 2026-04-06 | Waterproofing | 100 | 0 |  | 2025-12-19 |  | 2026-01-22
11952 | T-18-11th Floor Flat Area | Not Ready | Blockwork | 2026-03-02 | 2026-03-23 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-12-19 |  | 2026-01-10
40559 | Tower A - Super Structure - Finishes & MEP | Not Ready | MEP Shaft Masonry | 2025-12-10 | 2026-01-08 | L55-L65 | 100 | 0 |  | 2025-12-19 |  | 2026-01-19 |  | Tower A | Super Structure
40817 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2024-06-26 | 2024-07-03 | HVAC Ducting | 100 | 0 |  | 2025-12-19 |  | 2025-12-29 |  | Tower A | Super Structure |  | MEP | HVAC Ducting
40818 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2024-06-26 | 2024-07-13 | Flooring & Dado | 100 | 0 |  | 2025-12-19 |  | 2026-01-07 |  | Tower A | Super Structure |  | Finishes | Flooring & Dado
40840 |  | Not Committed |  | 2024-06-26 | 2024-09-05 | Lobby/ Common Area | 100 | 0 |  | 2025-12-19 |  | 2026-02-10
40841 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2024-06-26 | 2024-07-03 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-12-19 |  | 2025-12-29 |  | Tower A | Super Structure |  | MEP | FPS 1st Fix - MEP & Finishes
40842 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2024-06-26 | 2024-06-28 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2025-12-19 |  | 2025-12-23 |  | Tower A | Super Structure |  | MEP | Electrical 1st Fixes
41104 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2025-11-29 | 2025-12-02 | Staircase Fire Door Fixing | 100 | 0 |  | 2025-12-19 |  | 2025-12-23 |  | Tower A | Super Structure | L9
41131 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2025-11-29 | 2025-12-06 | False Ceiling | 100 | 0 |  | 2025-12-19 |  | 2025-12-29 |  | Tower A | Super Structure | L11 | Finishes | False Ceiling
41146 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-11-29 | 2025-12-10 | Flooring & Dado | 100 | 0 |  | 2025-12-19 |  | 2026-01-01 |  | Tower A | Super Structure | L12 | Finishes | Flooring & Dado
47642 |  | Not Ready |  | 2025-12-19 | 2025-12-27 | Section 8_lift 1 | 100 | 0 |  | 2025-12-19 |  | 2025-12-27
47642 |  | Not Ready |  | 2025-12-19 | 2025-12-27 | Section 8_lift 1 | 100 | 0 |  | 2025-12-19 |  | 2025-12-27 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
8763 | T-14-9th Floor Flat Area | Not Ready | Flooring & skirting | 2025-11-20 | 2026-01-02 | Flooring & skirting | 100 | 0 |  | 2025-12-20 |  | 2026-01-31
8780 | T-14-10th Floor Flat Area | Not Ready | Blockwork | 2025-11-12 | 2025-12-04 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-12-20 |  | 2026-01-11
9567 | T-16-Terrace | Not Ready |  | 2026-01-02 | 2026-02-23 | MISC | 100 | 0 |  | 2025-12-20 |  | 2026-02-07
9726 | T-16-5th Floor Flat Area | Not Ready | Putty | 2026-01-10 | 2026-04-06 | Putty | 100 | 0 |  | 2025-12-20 |  | 2026-03-14
11357 | T-19-8th Floor Flat Area | Not Ready | Waterproofing | 2026-01-04 | 2026-02-08 | Waterproofing | 100 | 0 |  | 2025-12-20 |  | 2026-01-20
11383 | T-19-9th Floor Flat Area | Not Ready | Waterproofing | 2026-01-04 | 2026-02-08 | Waterproofing | 100 | 0 |  | 2025-12-20 |  | 2026-01-20
11781 | T-18-4th Floor Flat Area | Not Ready | Window | 2026-02-18 | 2026-03-12 | Window | 100 | 0 |  | 2025-12-20 |  | 2026-01-11
39765 | Tower A - Super Structure - Core Wall High Rise L76-77 | Not Ready | Core Wall RCC Works | 2025-11-25 | 2025-11-25 | Casting | 100 | 0 |  | 2025-12-20 |  | 2025-12-22 |  | Tower A | Super Structure | L76 | RCC Super Structure | Core Wall RCC Works
40528 | Tower A - Super Structure - Finishes & MEP - L54 to L55 | Not Ready | Gypsum Plastering Works | 2025-11-28 | 2025-12-15 | L54-55 | 100 | 0 |  | 2025-12-20 |  | 2026-01-07 |  | Tower A | Super Structure | L54 | Finishes | Gypsum Plastering Works
40528 | Tower A - Super Structure - Finishes & MEP - L54 to L55 | Not Ready | Gypsum Plastering Works | 2025-11-28 | 2025-12-15 | L54-55 | 100 | 0 |  | 2025-12-20 |  | 2026-01-07 |  | Tower A | Super Structure | L54
43064 |  | Not Committed |  | 2025-11-28 | 2026-09-21 | L55-56 | 100 | 0 |  | 2025-12-20 |  | 2026-09-01
43064 |  | Not Committed |  | 2025-11-28 | 2026-09-21 | L55-56 | 100 | 0 |  | 2025-12-20 |  | 2026-09-01 |  |  |  |  | Finishes | Gypsum Plastering Works
43065 |  | Not Committed |  | 2025-11-28 | 2025-12-27 | MEP 1st Fixes | 100 | 0 |  | 2025-12-20 |  | 2026-01-19
43066 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2025-11-28 | 2025-12-05 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-12-20 |  | 2025-12-29 |  | Tower A | Super Structure | L55 | MEP | FPS 1st Fix - MEP & Finishes
43067 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-11-28 | 2025-12-03 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2025-12-20 |  | 2025-12-26 |  | Tower A | Super Structure | L55 | MEP | Electrical 1st Fixes
43068 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2025-11-28 | 2025-12-05 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2025-12-20 |  | 2025-12-29 |  | Tower A | Super Structure | L55
43069 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2025-11-28 | 2025-12-15 | Wet Area Waterproofing | 100 | 0 |  | 2025-12-20 |  | 2026-01-07 |  | Tower A | Super Structure | L55
45274 |  | Not Ready |  | 2025-10-16 | 2025-10-31 | L8-9 | 100 | 0 |  | 2025-12-20 |  | 2026-01-06
45274 |  | Not Ready |  | 2025-10-16 | 2025-10-31 | L8-9 | 100 | 0 |  | 2025-12-20 |  | 2026-01-06 |  |  |  |  | Finishes | Gypsum Plastering Works
45275 | Tower B - Super Structure - Core & Outer Slab L8-9 | Not Ready | RCC Works - Vertical | 2025-10-16 | 2025-10-28 | Outer Columns_TA | 100 | 0 |  | 2025-12-20 |  | 2026-01-02 |  | Tower B | Super Structure | L8 | RCC Sub Structure | RCC Works - Vertical
9240 | T-15-6th Floor Common Area | Not Ready | Flooring & skirting | 2025-12-20 | 2026-01-11 | Flooring & skirting | 100 | 0 |  | 2025-12-21 |  | 2026-01-12
9284 | T-15-8th Floor Flat Area | Not Ready | Putty | 2025-12-26 | 2026-03-20 | Putty | 100 | 0 |  | 2025-12-21 |  | 2026-03-15
9310 | T-15-9th Floor Flat Area | Not Ready | Putty | 2025-12-26 | 2026-03-20 | Putty | 100 | 0 |  | 2025-12-21 |  | 2026-03-15
9564 | T-16-Terrace | Not Ready | OHT | 2026-01-03 | 2026-02-24 | OHT | 100 | 0 |  | 2025-12-21 |  | 2026-02-08
9799 | T-16-8th Floor Flat Area | Not Ready | Plastering | 2026-01-03 | 2026-02-18 | Plastering-Gypsum | 100 | 0 |  | 2025-12-21 |  | 2026-02-01
9825 | T-16-9th Floor Flat Area | Not Ready | Plastering | 2026-01-03 | 2026-02-18 | Plastering-Gypsum | 100 | 0 |  | 2025-12-21 |  | 2026-02-01
10894 | T-20-10th Floor Flat Area | Not Ready | Toilets False Celing | 2026-01-27 | 2026-02-28 | Toilets False Celing | 100 | 0 |  | 2025-12-21 |  | 2026-01-24
11334 | T-19-7th Floor Flat Area | Not Ready | Dado | 2026-01-06 | 2026-02-05 | Dado | 100 | 0 |  | 2025-12-21 |  | 2026-01-17
11956 | T-18-11th Floor Flat Area | Not Ready | Electrical DB Fixing | 2026-03-04 | 2026-03-20 | Electrical DB Fixing | 100 | 0 |  | 2025-12-21 |  | 2026-01-05
8784 | T-14-10th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-11-14 | 2025-12-01 | Electrical DB Fixing | 100 | 0 |  | 2025-12-22 |  | 2026-01-06
8819 | T-14-11th Floor Flat Area | Not Ready | Railing | 2025-11-15 | 2025-12-18 | Balcony Railing | 100 | 0 |  | 2025-12-22 |  | 2026-01-23
11236 | T-19-3rd Floor Flat Area | Not Ready | Door | 2026-01-14 | 2026-02-07 | Door | 100 | 0 |  | 2025-12-22 |  | 2026-01-12
11310 | T-19-6th Floor Flat Area | Not Ready | Toilets False Celing | 2026-01-08 | 2026-02-12 | Toilets False Celing | 100 | 0 |  | 2025-12-22 |  | 2026-01-22
39766 | Tower A - Super Structure - Core Wall High Rise L76-77 | Not Ready | Core Wall RCC Works | 2025-11-26 | 2025-11-26 | ACS Form Release & jump to next level | 100 | 0 |  | 2025-12-22 |  | 2025-12-23 |  | Tower A | Super Structure | L76 | RCC Super Structure | Core Wall RCC Works
40743 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2024-05-30 | 2024-06-01 | Staircase Fire Door Fixing | 100 | 0 |  | 2025-12-22 |  | 2025-12-26 |  | Tower A | Super Structure
41116 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2025-12-02 | 2025-12-04 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2025-12-22 |  | 2025-12-26 |  | Tower A | Super Structure | L10 | MEP | FPS 2nd Fix - MEP & Finishes
41117 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2025-12-02 | 2025-12-06 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2025-12-22 |  | 2025-12-29 |  | Tower A | Super Structure | L10 | MEP | Electrical 2nd Fix - MEP & Finishes
41118 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-12-02 | 2025-12-09 | FAPA Device Fixing | 100 | 0 |  | 2025-12-22 |  | 2025-12-31 |  | Tower A | Super Structure | L10
41118 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-12-02 | 2025-12-09 | FAPA Device Fixing | 100 | 0 |  | 2025-12-22 |  | 2025-12-31 |  | Tower A | Super Structure | L10
41118 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-12-02 | 2025-12-09 | FAPA Device Fixing | 100 | 0 |  | 2025-12-22 |  | 2025-12-31 |  | Tower A | Super Structure | L10
41118 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-12-02 | 2025-12-09 | FAPA Device Fixing | 100 | 0 |  | 2025-12-22 |  | 2025-12-31 |  | Tower A | Super Structure | L10
41119 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2025-12-02 | 2025-12-04 | HVAC Grill Fixing | 100 | 0 |  | 2025-12-22 |  | 2025-12-26 |  | Tower A | Super Structure | L10 | MEP | HVAC Grill Fixing
41385 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-05-15 | 2025-05-20 | Lobby Plastering | 100 | 0 |  | 2025-12-22 |  | 2025-12-27 |  | Tower A | Super Structure | L27 | Finishes | Lobby Plastering
41400 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-05-15 | 2025-05-17 | Lobby Blockwork | 100 | 0 |  | 2025-12-22 |  | 2025-12-24 |  | Tower A | Super Structure | L28 | Finishes | Blockwork
43034 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-11-29 | 2025-12-10 | Cement Plastering in wet areas | 100 | 0 |  | 2025-12-22 |  | 2026-01-02 |  | Tower A | Super Structure | L53
44557 | NTA_Zone 2 - Sub Structure - B1 to GF | Not Ready | Finishes (Lobby & Floor Area) | 2024-12-24 | 2025-01-16 | MEP Rooms - Plaster & IPS | 100 | 0 |  | 2025-12-22 |  | 2026-01-14 |  | NTA_Zone 2 | Sub Structure | B1
44557 | NTA_Zone 2 - Sub Structure - B1 to GF | Not Ready | Finishes (Lobby & Floor Area) | 2024-12-24 | 2025-01-16 | MEP Rooms - Plaster & IPS | 100 | 0 |  | 2025-12-22 |  | 2026-01-14 |  | NTA_Zone 2 | Sub Structure | B1
44558 | NTA_Zone 2 - Sub Structure - B1 to GF | Not Ready | Finishes (Lobby & Floor Area) | 2024-12-24 | 2025-01-28 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2025-12-22 |  | 2026-01-27 |  | NTA_Zone 2 | Sub Structure | B1
44558 | NTA_Zone 2 - Sub Structure - B1 to GF | Not Ready | Finishes (Lobby & Floor Area) | 2024-12-24 | 2025-01-28 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2025-12-22 |  | 2026-01-27 |  | NTA_Zone 2 | Sub Structure | B1
9608 | T-16-GF Common Area | Not Ready | 1st Coat Painting | 2026-01-10 | 2026-03-03 | 1st Coat Painting | 100 | 0 |  | 2025-12-23 |  | 2026-02-10
10251 | T-21-5th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-02-08 | 2026-04-16 | 2nd Coat Painting | 100 | 0 |  | 2025-12-23 |  | 2026-03-02
10303 | T-21-7th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-02-08 | 2026-04-16 | 2nd Coat Painting | 100 | 0 |  | 2025-12-23 |  | 2026-03-02
10333 | T-21-8th Floor Common Area | Not Ready | Putty | 2026-01-28 | 2026-03-07 | Putty | 100 | 0 |  | 2025-12-23 |  | 2026-02-01
39767 |  | Not Ready |  | 2025-11-27 | 2025-12-04 | Core Wall L77-78 | 100 | 0 |  | 2025-12-23 |  | 2026-01-01
39768 | Tower A - Super Structure - Core Wall High Rise L77-78 | Not Ready | Core Wall RCC Works | 2025-11-27 | 2025-11-27 | Scaffolding & platform | 100 | 0 |  | 2025-12-23 |  | 2025-12-24 |  | Tower A | Super Structure | L77 | RCC Super Structure | Core Wall RCC Works
40073 | Tower A - Super Structure - Finishes & MEP - L70 to L71 | Not Ready | CTU Elevators Crash Deck - High Side Services | 2025-11-24 | 2025-12-04 | Bulk head light fix + Electrical works + Earthing | 100 | 0 |  | 2025-12-23 |  | 2026-01-05 |  | Tower A | Super Structure | L70
40073 | Tower A - Super Structure - Finishes & MEP - L70 to L71 | Not Ready | CTU Elevators Crash Deck - High Side Services | 2025-11-24 | 2025-12-04 | Bulk head light fix + Electrical works + Earthing | 100 | 0 |  | 2025-12-23 |  | 2026-01-05 |  | Tower A | Super Structure | L70
40073 | Tower A - Super Structure - Finishes & MEP - L70 to L71 | Not Ready | CTU Elevators Crash Deck - High Side Services | 2025-11-24 | 2025-12-04 | Bulk head light fix + Electrical works + Earthing | 100 | 0 |  | 2025-12-23 |  | 2026-01-05 |  | Tower A | Super Structure | L70
40384 | Tower A - Super Structure - Finishes & MEP - L56 to L57 | Not Ready | Partition Wall-Blockwork | 2025-12-01 | 2025-12-05 | Staircase Area | 100 | 0 |  | 2025-12-23 |  | 2025-12-29 |  | Tower A | Super Structure | L56
40387 | Tower A - Super Structure - Finishes & MEP - L57 to L58 | Not Ready | Partition Wall-Blockwork | 2025-12-01 | 2025-12-08 | Partition Walls | 100 | 0 |  | 2025-12-23 |  | 2025-12-31 |  | Tower A | Super Structure | L57
40784 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2024-09-13 | 2024-10-01 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2025-12-23 |  | 2026-01-09 |  | Tower A | Super Structure
40784 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2024-09-13 | 2024-10-01 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2025-12-23 |  | 2026-01-09 |  | Tower A | Super Structure
40784 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2024-09-13 | 2024-10-01 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2025-12-23 |  | 2026-01-09 |  | Tower A | Super Structure
40792 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | False Ceiling - MEP & Finishes | 2024-06-20 | 2024-07-01 | False Ceiling | 100 | 0 |  | 2025-12-23 |  | 2026-01-05 |  | Tower A | Super Structure |  | Finishes | False Ceiling
40843 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2024-06-29 | 2024-07-01 | FAPA Cabling | 100 | 0 |  | 2025-12-23 |  | 2025-12-26 |  | Tower A | Super Structure
41090 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2025-12-03 | 2025-12-08 | Final Painting | 100 | 0 |  | 2025-12-23 |  | 2025-12-30 |  | Tower A | Super Structure | L8 | Finishes | Final Painting
41090 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2025-12-03 | 2025-12-08 | Final Painting | 100 | 0 |  | 2025-12-23 |  | 2025-12-30 |  | Tower A | Super Structure | L8 | Finishes | Final Painting
41090 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2025-12-03 | 2025-12-08 | Final Painting | 100 | 0 |  | 2025-12-23 |  | 2025-12-30 |  | Tower A | Super Structure | L8 | Finishes | Final Painting
41105 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2025-12-03 | 2025-12-08 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2025-12-23 |  | 2025-12-30 |  | Tower A | Super Structure | L9 | MEP | Electrical
41175 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2025-12-03 | 2025-12-10 | HVAC Ducting | 100 | 0 |  | 2025-12-23 |  | 2026-01-01 |  | Tower A | Super Structure | L14 | MEP | HVAC Ducting
41592 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-11-24 | 2025-11-26 | Lobby Blockwork | 100 | 0 |  | 2025-12-23 |  | 2025-12-27 |  | Tower A | Super Structure | L40 | Finishes | Blockwork
44532 | NTA_Zone 2 - Super Structure - P2 to P3 | Not Ready | MEP 1st Fix Works | 2025-01-29 | 2025-04-09 | P2 to P3 | 100 | 0 |  | 2025-12-23 |  | 2026-01-09 |  | NTA_Zone 2 | Super Structure
44532 | NTA_Zone 2 - Super Structure - P2 to P3 | Not Ready | MEP 1st Fix Works | 2025-01-29 | 2025-04-09 | P2 to P3 | 100 | 0 |  | 2025-12-23 |  | 2026-01-09 |  | NTA_Zone 2 | Super Structure
44532 | NTA_Zone 2 - Super Structure - P2 to P3 | Not Ready | MEP 1st Fix Works | 2025-01-29 | 2025-04-09 | P2 to P3 | 100 | 0 |  | 2025-12-23 |  | 2026-01-09 |  | NTA_Zone 2 | Super Structure
44542 | NTA_Zone 2 - Super Structure - P3 to P4 | Not Ready | Partition Wall-Blockwork | 2024-08-29 | 2024-10-05 | P3 to P4 | 100 | 0 |  | 2025-12-23 |  | 2026-01-28 |  | NTA_Zone 2 | Super Structure
44542 | NTA_Zone 2 - Super Structure - P3 to P4 | Not Ready | Partition Wall-Blockwork | 2024-08-29 | 2024-10-05 | P3 to P4 | 100 | 0 |  | 2025-12-23 |  | 2026-01-28 |  | NTA_Zone 2 | Super Structure
44542 | NTA_Zone 2 - Super Structure - P3 to P4 | Not Ready | Partition Wall-Blockwork | 2024-08-29 | 2024-10-05 | P3 to P4 | 100 | 0 |  | 2025-12-23 |  | 2026-01-28 |  | NTA_Zone 2 | Super Structure
44567 | NTA_Zone 2 - Super Structure - P1 to P2 | Not Ready | Finishes (Lobby & Floor Area) | 2025-02-15 | 2025-03-22 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2025-12-23 |  | 2026-01-28 |  | NTA_Zone 2 | Super Structure
44567 | NTA_Zone 2 - Super Structure - P1 to P2 | Not Ready | Finishes (Lobby & Floor Area) | 2025-02-15 | 2025-03-22 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2025-12-23 |  | 2026-01-28 |  | NTA_Zone 2 | Super Structure
8735 | T-14-8th Floor Flat Area | Not Ready | Toilet flooring | 2025-11-24 | 2025-12-27 | Toilet flooring | 100 | 0 |  | 2025-12-24 |  | 2026-01-26
9236 | T-15-6th Floor Flat Area | Not Ready | 1st Coat Painting | 2025-12-31 | 2026-03-26 | 1st Coat Painting | 100 | 0 |  | 2025-12-24 |  | 2026-03-18
9352 | T-15-11th Floor Flat Area | Not Ready | Blockwork | 2025-12-26 | 2026-01-19 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-12-24 |  | 2026-01-14
9724 | T-16-5th Floor Flat Area | Not Ready | Toilets False Celing | 2026-01-13 | 2026-02-16 | Toilets False Celing | 100 | 0 |  | 2025-12-24 |  | 2026-01-26
10827 | T-20-7th Floor Common Area | Not Ready | Putty | 2026-01-22 | 2026-03-02 | Putty | 100 | 0 |  | 2025-12-24 |  | 2026-02-01
10915 | T-20-11th Floor Flat Area | Not Ready | Waterproofing | 2026-01-22 | 2026-02-25 | Waterproofing | 100 | 0 |  | 2025-12-24 |  | 2026-01-27
11935 | T-18-10th Floor Flat Area | Not Ready | Flooring & skirting | 2026-03-09 | 2026-04-23 | Flooring & skirting | 100 | 0 |  | 2025-12-24 |  | 2026-02-06
39769 | Tower A - Super Structure - Core Wall High Rise L77-78 | Not Ready | Core Wall RCC Works | 2025-11-28 | 2025-12-01 | Reinf & Guide shoes fixing | 100 | 0 |  | 2025-12-24 |  | 2025-12-29 |  | Tower A | Super Structure | L77 | RCC Super Structure | Core Wall RCC Works
40022 |  | Not Ready |  | 2025-11-25 | 2025-12-02 | L73-74 | 100 | 0 |  | 2025-12-24 |  | 2026-01-06
40022 |  | Not Ready |  | 2025-11-25 | 2025-12-02 | L73-74 | 100 | 0 |  | 2025-12-24 |  | 2026-01-06 |  |  |  |  | Finishes | Gypsum Plastering Works
40023 | Tower A - Super Structure - Core & Outer Slab L73-74 | Not Ready | RCC Works - Vertical | 2025-11-25 | 2025-12-01 | Outer Columns_TA | 100 | 0 |  | 2025-12-24 |  | 2026-01-03 |  | Tower A | Super Structure | L73 | RCC Sub Structure | RCC Works - Vertical
40437 |  | Not Committed |  | 2025-11-25 | 2026-03-21 | L70-71 | 100 | 0 |  | 2025-12-24 |  | 2026-04-13
40437 |  | Not Committed |  | 2025-11-25 | 2026-03-21 | L70-71 | 100 | 0 |  | 2025-12-24 |  | 2026-04-13 |  |  |  |  | Finishes | Gypsum Plastering Works
40438 | Tower A - Super Structure - Finishes & MEP - L70 to L71 | Not Ready | Partition Wall-Blockwork | 2025-11-25 | 2025-12-11 | De-shuttering & Area clearance | 100 | 0 |  | 2025-12-24 |  | 2026-01-12 |  | Tower A | Super Structure | L70
42732 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-01-24 | 2026-02-11 | Flooring & Dado works | 100 | 0 |  | 2025-12-24 |  | 2026-01-12 |  | Tower A | Super Structure | L36 | Finishes | Flooring & Dado
42965 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-12-02 | 2025-12-09 | Door & Window Frame work | 100 | 0 |  | 2025-12-24 |  | 2026-01-01 |  | Tower A | Super Structure | L49 | Finishes | Door & Window Frame work
44090 |  | Started |  | 2026-01-24 | 2026-03-07 | L43-48 | 100 | 2 |  | 2025-12-24 | 2025-09-19 | 2026-02-05
44091 | Tower A - Super Structure - Finishes & MEP - L43 to L48 | Started | Façade Works - MEP & Finishes | 2026-01-24 | 2026-02-11 | Al. Frame section (Mullion & Transom) Installation | 100 | 1 | Units | 2025-12-24 | 2025-09-19 | 2026-01-12 |  | Tower A | Super Structure | L43 | Façade | Façade Works
48179 | Retail - Super structure - GF to R1 - P6 | Not Ready |  | 2025-09-02 | 2025-09-25 | Slab_RT | 100 | 0 |  | 2025-12-24 |  | 2026-01-16 |  | Retail | Super Structure | GF | RCC Sub Structure | RCC Works - Slab
48179 | Retail - Super structure - GF to R1 - P6 | Not Ready |  | 2025-09-02 | 2025-09-25 | Slab_RT | 100 | 0 |  | 2025-12-24 |  | 2026-01-16 |  | Retail | Super Structure | GF
48181 |  | Not Committed |  | 2025-09-02 | 2025-10-14 | Pour RT-1 | 100 | 0 |  | 2025-12-24 |  | 2026-02-04
48182 | Retail - Super structure - R1 to CH00 - P1 | Not Ready |  | 2025-09-02 | 2025-10-01 | Columns_RT | 100 | 0 |  | 2025-12-24 |  | 2026-01-22 |  | Retail | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
48182 | Retail - Super structure - R1 to CH00 - P1 | Not Ready |  | 2025-09-02 | 2025-10-01 | Columns_RT | 100 | 0 |  | 2025-12-24 |  | 2026-01-22 |  | Retail | Super Structure
48183 | Retail - Super structure - R1 to CH00 - P1 | Not Ready |  | 2025-09-02 | 2025-10-01 | Staircase_RT | 100 | 0 |  | 2025-12-24 |  | 2026-01-22 |  | Retail | Super Structure |  | RCC Sub Structure | RCC Works - Slab
48183 | Retail - Super structure - R1 to CH00 - P1 | Not Ready |  | 2025-09-02 | 2025-10-01 | Staircase_RT | 100 | 0 |  | 2025-12-24 |  | 2026-01-22 |  | Retail | Super Structure
48188 |  | Not Committed |  | 2025-09-02 | 2025-10-14 | Pour RT-3 | 100 | 0 |  | 2025-12-24 |  | 2026-02-04
48189 | Retail - Super structure - R1 to CH00 - P3 | Not Ready |  | 2025-09-02 | 2025-10-01 | Columns_RT | 100 | 0 |  | 2025-12-24 |  | 2026-01-22 |  | Retail | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
48189 | Retail - Super structure - R1 to CH00 - P3 | Not Ready |  | 2025-09-02 | 2025-10-01 | Columns_RT | 100 | 0 |  | 2025-12-24 |  | 2026-01-22 |  | Retail | Super Structure
48190 | Retail - Super structure - R1 to CH00 - P3 | Not Ready |  | 2025-09-02 | 2025-10-01 | Staircase_RT | 100 | 0 |  | 2025-12-24 |  | 2026-01-22 |  | Retail | Super Structure |  | RCC Sub Structure | RCC Works - Slab
48190 | Retail - Super structure - R1 to CH00 - P3 | Not Ready |  | 2025-09-02 | 2025-10-01 | Staircase_RT | 100 | 0 |  | 2025-12-24 |  | 2026-01-22 |  | Retail | Super Structure
8694 | T-14-6th Floor Common Area | Not Ready | Flooring & skirting | 2025-11-21 | 2025-12-12 | Flooring & skirting | 100 | 0 |  | 2025-12-25 |  | 2026-01-14
9652 | T-16-2nd Floor Flat Area | Not Ready | 1st Coat Painting | 2026-01-30 | 2026-04-17 | 1st Coat Painting | 100 | 0 |  | 2025-12-25 |  | 2026-03-13
11363 | T-19-8th Floor Flat Area | Not Ready | Flooring & skirting | 2026-01-09 | 2026-02-24 | Flooring & skirting | 100 | 0 |  | 2025-12-25 |  | 2026-02-05
11389 | T-19-9th Floor Flat Area | Not Ready | Flooring & skirting | 2026-01-09 | 2026-02-24 | Flooring & skirting | 100 | 0 |  | 2025-12-25 |  | 2026-02-05
11406 | T-19-10th Floor Flat Area | Not Ready | Blockwork | 2026-01-02 | 2026-01-25 | Blockwork-Ledge Wall | 100 | 0 |  | 2025-12-25 |  | 2026-01-16
47956 | Tower B | Not Committed | Award of Packages | 2025-11-17 | 2026-04-03 | HVAC (Lift & Stairwell Pressurisation) | 100 | 0 |  | 2025-12-25 |  | 2026-05-14 |  | Tower B | --
9282 | T-15-8th Floor Flat Area | Not Ready | Toilets False Celing | 2026-01-01 | 2026-02-05 | Toilets False Celing | 100 | 0 |  | 2025-12-26 |  | 2026-01-29
9308 | T-15-9th Floor Flat Area | Not Ready | Toilets False Celing | 2026-01-01 | 2026-02-05 | Toilets False Celing | 100 | 0 |  | 2025-12-26 |  | 2026-01-29
9356 | T-15-11th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-12-29 | 2026-01-14 | Electrical DB Fixing | 100 | 0 |  | 2025-12-26 |  | 2026-01-13
9650 | T-16-2nd Floor Flat Area | Not Ready | Door | 2026-01-20 | 2026-02-12 | Door | 100 | 0 |  | 2025-12-26 |  | 2026-01-15
9771 | T-16-7th Floor Flat Area | Not Ready | Waterproofing | 2026-01-12 | 2026-02-15 | Waterproofing | 100 | 0 |  | 2025-12-26 |  | 2026-01-28
9796 | T-16-8th Floor Flat Area | Not Ready | Plastering | 2026-01-09 | 2026-02-02 | Plastering-Cement | 100 | 0 |  | 2025-12-26 |  | 2026-01-17
9822 | T-16-9th Floor Flat Area | Not Ready | Plastering | 2026-01-09 | 2026-02-02 | Plastering-Cement | 100 | 0 |  | 2025-12-26 |  | 2026-01-17
10398 | T-21-11th Floor Flat Area | Not Ready | Dado | 2026-01-28 | 2026-02-24 | Dado | 100 | 0 |  | 2025-12-26 |  | 2026-01-23
11953 | T-18-11th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2026-03-09 | 2026-04-01 | Plumbing Pipe Line | 100 | 0 |  | 2025-12-26 |  | 2026-01-16
39770 | Tower A - Super Structure - Core Wall High Rise L77-78 | Not Ready | Core Wall RCC Works | 2025-11-29 | 2025-12-02 | ACS Form Closing & Alignment | 100 | 0 |  | 2025-12-26 |  | 2025-12-30 |  | Tower A | Super Structure | L77 | RCC Super Structure | Core Wall RCC Works
40744 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2024-06-03 | 2024-06-07 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2025-12-26 |  | 2026-01-01 |  | Tower A | Super Structure |  | MEP | Electrical
40808 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2024-09-13 | 2024-09-21 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2025-12-26 |  | 2026-01-03 |  | Tower A | Super Structure |  | MEP | FPS 2nd Fix - MEP & Finishes
40809 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-09-13 | 2024-09-21 | FAPA Device Fixing | 100 | 0 |  | 2025-12-26 |  | 2026-01-03 |  | Tower A | Super Structure
40809 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-09-13 | 2024-09-21 | FAPA Device Fixing | 100 | 0 |  | 2025-12-26 |  | 2026-01-03 |  | Tower A | Super Structure
40809 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-09-13 | 2024-09-21 | FAPA Device Fixing | 100 | 0 |  | 2025-12-26 |  | 2026-01-03 |  | Tower A | Super Structure
40809 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-09-13 | 2024-09-21 | FAPA Device Fixing | 100 | 0 |  | 2025-12-26 |  | 2026-01-03 |  | Tower A | Super Structure
41120 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2025-12-05 | 2025-12-08 | Staircase Fire Door Fixing | 100 | 0 |  | 2025-12-26 |  | 2025-12-30 |  | Tower A | Super Structure | L10
41147 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2025-12-05 | 2025-12-12 | False Ceiling | 100 | 0 |  | 2025-12-26 |  | 2026-01-03 |  | Tower A | Super Structure | L12 | Finishes | False Ceiling
41162 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-12-05 | 2025-12-16 | Flooring & Dado | 100 | 0 |  | 2025-12-26 |  | 2026-01-07 |  | Tower A | Super Structure | L13 | Finishes | Flooring & Dado
41401 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-05-19 | 2025-05-23 | Lobby Plastering | 100 | 0 |  | 2025-12-26 |  | 2025-12-31 |  | Tower A | Super Structure | L28 | Finishes | Lobby Plastering
41416 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-05-19 | 2025-05-21 | Lobby Blockwork | 100 | 0 |  | 2025-12-26 |  | 2025-12-29 |  | Tower A | Super Structure | L29 | Finishes | Blockwork
43017 |  | Not Committed |  | 2025-12-03 | 2026-04-11 | Finishes after 1st Fix | 100 | 0 |  | 2025-12-26 |  | 2026-03-13
43018 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-12-03 | 2025-12-26 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2025-12-26 |  | 2026-01-17 |  | Tower A | Super Structure | L52 | Finishes | Blockwork
44549 | NTA_Zone 2 - Sub Structure - B3 to B2 | Not Ready | Finishes (Lobby & Floor Area) | 2024-08-09 | 2024-09-18 | Staircase Finishes | 100 | 0 |  | 2025-12-26 |  | 2026-01-30 |  | NTA_Zone 2 | Sub Structure | B3
44549 | NTA_Zone 2 - Sub Structure - B3 to B2 | Not Ready | Finishes (Lobby & Floor Area) | 2024-08-09 | 2024-09-18 | Staircase Finishes | 100 | 0 |  | 2025-12-26 |  | 2026-01-30 |  | NTA_Zone 2 | Sub Structure | B3
8662 | T-14-5th Floor Flat Area | Not Ready | Door | 2025-12-12 | 2026-01-02 | Door | 100 | 0 |  | 2025-12-27 |  | 2026-01-14
8690 | T-14-6th Floor Flat Area | Not Ready | 1st Coat Painting | 2025-12-02 | 2026-02-24 | 1st Coat Painting | 100 | 0 |  | 2025-12-27 |  | 2026-03-21
8738 | T-14-8th Floor Flat Area | Not Ready | Putty | 2025-11-27 | 2026-02-19 | Putty | 100 | 0 |  | 2025-12-27 |  | 2026-03-21
8781 | T-14-10th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-11-20 | 2025-12-11 | Plumbing Pipe Line | 100 | 0 |  | 2025-12-27 |  | 2026-01-17
9329 | T-15-10th Floor Flat Area | Not Ready | Waterproofing | 2025-12-29 | 2026-02-02 | Waterproofing | 100 | 0 |  | 2025-12-27 |  | 2026-01-31
9748 | T-16-6th Floor Flat Area | Not Ready | Dado | 2026-01-14 | 2026-02-12 | Dado | 100 | 0 |  | 2025-12-27 |  | 2026-01-21
10846 | T-20-8th Floor Flat Area | Not Ready | Door | 2026-02-15 | 2026-03-09 | Door | 100 | 0 |  | 2025-12-27 |  | 2026-01-18
11410 | T-19-10th Floor Flat Area | Not Ready | Electrical DB Fixing | 2026-01-04 | 2026-01-22 | Electrical DB Fixing | 100 | 0 |  | 2025-12-27 |  | 2026-01-11
11445 | T-19-11th Floor Flat Area | Not Ready | Railing | 2026-01-05 | 2026-02-09 | Balcony Railing | 100 | 0 |  | 2025-12-27 |  | 2026-01-30
40766 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2024-06-13 | 2024-06-15 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2025-12-27 |  | 2025-12-31 |  | Tower A | Super Structure |  | MEP | FPS 2nd Fix - MEP & Finishes
40767 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2024-06-13 | 2024-06-19 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2025-12-27 |  | 2026-01-02 |  | Tower A | Super Structure |  | MEP | Electrical 2nd Fix - MEP & Finishes
40768 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-06-13 | 2024-06-21 | FAPA Device Fixing | 100 | 0 |  | 2025-12-27 |  | 2026-01-05 |  | Tower A | Super Structure
40768 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-06-13 | 2024-06-21 | FAPA Device Fixing | 100 | 0 |  | 2025-12-27 |  | 2026-01-05 |  | Tower A | Super Structure
40768 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-06-13 | 2024-06-21 | FAPA Device Fixing | 100 | 0 |  | 2025-12-27 |  | 2026-01-05 |  | Tower A | Super Structure
40768 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-06-13 | 2024-06-21 | FAPA Device Fixing | 100 | 0 |  | 2025-12-27 |  | 2026-01-05 |  | Tower A | Super Structure
40769 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2024-06-13 | 2024-06-15 | HVAC Grill Fixing | 100 | 0 |  | 2025-12-27 |  | 2025-12-31 |  | Tower A | Super Structure |  | MEP | HVAC Grill Fixing
41593 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-11-27 | 2025-12-02 | Lobby Plastering | 100 | 0 |  | 2025-12-27 |  | 2026-01-02 |  | Tower A | Super Structure | L40 | Finishes | Lobby Plastering
41608 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-11-27 | 2025-11-29 | Lobby Blockwork | 100 | 0 |  | 2025-12-27 |  | 2025-12-31 |  | Tower A | Super Structure | L41 | Finishes | Blockwork
9811 | T-16-8th Floor Common Area | Not Ready | Plastering | 2026-01-12 | 2026-02-15 | Plastering-Gypsum | 100 | 0 |  | 2025-12-28 |  | 2026-01-30
9837 | T-16-9th Floor Common Area | Not Ready | Plastering | 2026-01-12 | 2026-02-15 | Plastering-Gypsum | 100 | 0 |  | 2025-12-28 |  | 2026-01-30
11261 | T-19-4th Floor Flat Area | Not Ready | Window | 2026-01-22 | 2026-02-13 | Window | 100 | 0 |  | 2025-12-28 |  | 2026-01-19
11335 | T-19-7th Floor Flat Area | Not Ready | Toilet flooring | 2026-01-14 | 2026-02-18 | Toilet flooring | 100 | 0 |  | 2025-12-28 |  | 2026-01-27
11866 | T-18-7th Floor Common Area | Not Ready | Flooring & skirting | 2026-03-11 | 2026-04-03 | Flooring & skirting | 100 | 0 |  | 2025-12-28 |  | 2026-01-19
11957 | T-18-11th Floor Flat Area | Not Ready | Plastering | 2026-03-11 | 2026-04-25 | Plastering-Gypsum | 100 | 0 |  | 2025-12-28 |  | 2026-02-11
8687 | T-14-6th Floor Flat Area | Not Ready | Window | 2025-12-14 | 2026-01-05 | Window | 100 | 0 |  | 2025-12-29 |  | 2026-01-20
8785 | T-14-10th Floor Flat Area | Not Ready | Plastering | 2025-11-22 | 2026-01-05 | Plastering-Gypsum | 100 | 0 |  | 2025-12-29 |  | 2026-02-12
10274 | T-21-6th Floor Flat Area | Not Ready | Door | 2026-01-06 | 2026-01-30 | Door | 100 | 0 |  | 2025-12-29 |  | 2026-01-19
10871 | T-20-9th Floor Flat Area | Not Ready | Window | 2026-02-17 | 2026-03-11 | Window | 100 | 0 |  | 2025-12-29 |  | 2026-01-23
10921 | T-20-11th Floor Flat Area | Not Ready | Flooring & skirting | 2026-01-29 | 2026-03-13 | Flooring & skirting | 100 | 0 |  | 2025-12-29 |  | 2026-02-14
11782 | T-18-4th Floor Flat Area | Not Ready | Door | 2026-02-28 | 2026-03-22 | Door | 100 | 0 |  | 2025-12-29 |  | 2026-01-20
40024 | Tower A - Super Structure - Core & Outer Slab L73-74 | Not Ready | RCC Works - Slab | 2025-11-27 | 2025-12-02 | Outer Slab_TA | 100 | 0 |  | 2025-12-29 |  | 2026-01-06 |  | Tower A | Super Structure | L73 | RCC Sub Structure | RCC Works - Slab
40110 | Tower A - Super Structure - Finishes & MEP - Sub Station | Not Ready | Sub Station - High Side Services | 2025-12-31 | 2026-01-16 | Platform fixing for Transformer Placing | 100 | 0 |  | 2025-12-29 |  | 2026-01-14 |  | Tower A | Super Structure
40844 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2024-07-04 | 2024-07-12 | HVAC Ducting | 100 | 0 |  | 2025-12-29 |  | 2026-01-06 |  | Tower A | Super Structure |  | MEP | HVAC Ducting
40845 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2024-07-04 | 2024-07-24 | Flooring & Dado | 100 | 0 |  | 2025-12-29 |  | 2026-01-15 |  | Tower A | Super Structure |  | Finishes | Flooring & Dado
41132 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2025-12-08 | 2025-12-10 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2025-12-29 |  | 2026-01-01 |  | Tower A | Super Structure | L11 | MEP | FPS 2nd Fix - MEP & Finishes
41133 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2025-12-08 | 2025-12-12 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2025-12-29 |  | 2026-01-03 |  | Tower A | Super Structure | L11 | MEP | Electrical 2nd Fix - MEP & Finishes
41134 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-12-08 | 2025-12-15 | FAPA Device Fixing | 100 | 0 |  | 2025-12-29 |  | 2026-01-06 |  | Tower A | Super Structure | L11
41134 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-12-08 | 2025-12-15 | FAPA Device Fixing | 100 | 0 |  | 2025-12-29 |  | 2026-01-06 |  | Tower A | Super Structure | L11
41134 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-12-08 | 2025-12-15 | FAPA Device Fixing | 100 | 0 |  | 2025-12-29 |  | 2026-01-06 |  | Tower A | Super Structure | L11
41134 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-12-08 | 2025-12-15 | FAPA Device Fixing | 100 | 0 |  | 2025-12-29 |  | 2026-01-06 |  | Tower A | Super Structure | L11
41135 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2025-12-08 | 2025-12-10 | HVAC Grill Fixing | 100 | 0 |  | 2025-12-29 |  | 2026-01-01 |  | Tower A | Super Structure | L11 | MEP | HVAC Grill Fixing
45276 | Tower B - Super Structure - Core & Outer Slab L8-9 | Not Ready | RCC Works - Slab | 2025-10-24 | 2025-10-31 | Outer Slab_TA | 100 | 0 |  | 2025-12-29 |  | 2026-01-06 |  | Tower B | Super Structure | L8 | RCC Sub Structure | RCC Works - Slab
47645 |  | Not Ready |  | 2025-12-29 | 2026-01-05 | Section 11_lift 1 | 100 | 0 |  | 2025-12-29 |  | 2026-01-05
47645 |  | Not Ready |  | 2025-12-29 | 2026-01-05 | Section 11_lift 1 | 100 | 0 |  | 2025-12-29 |  | 2026-01-05 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
8760 | T-14-9th Floor Flat Area | Not Ready | Dado | 2025-12-01 | 2025-12-28 | Dado | 100 | 0 |  | 2025-12-30 |  | 2026-01-26
8822 |  | Not Ready |  | 2025-12-29 | 2026-07-28 | Common Area | 100 | 0 |  | 2025-12-30 |  | 2026-07-29
9208 | T-15-5th Floor Flat Area | Not Ready | Door | 2026-01-11 | 2026-02-04 | Door | 100 | 0 |  | 2025-12-30 |  | 2026-01-23
10384 | T-21-11th Floor Common Area | Not Ready | Flooring & skirting | 2026-02-08 | 2026-03-02 | Flooring & skirting | 100 | 0 |  | 2025-12-30 |  | 2026-01-25
11862 | T-18-7th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-03-20 | 2026-06-12 | 1st Coat Painting | 100 | 0 |  | 2025-12-30 |  | 2026-03-24
39771 | Tower A - Super Structure - Core Wall High Rise L77-78 | Not Ready | Core Wall RCC Works | 2025-12-03 | 2025-12-03 | Casting | 100 | 0 |  | 2025-12-30 |  | 2025-12-31 |  | Tower A | Super Structure | L77 | RCC Super Structure | Core Wall RCC Works
40529 | Tower A - Super Structure - Finishes & MEP - L55 to L56 | Not Ready | Gypsum Plastering Works | 2025-12-06 | 2025-12-23 | L55-56 | 100 | 0 |  | 2025-12-30 |  | 2026-01-15 |  | Tower A | Super Structure | L55 | Finishes | Gypsum Plastering Works
40529 | Tower A - Super Structure - Finishes & MEP - L55 to L56 | Not Ready | Gypsum Plastering Works | 2025-12-06 | 2025-12-23 | L55-56 | 100 | 0 |  | 2025-12-30 |  | 2026-01-15 |  | Tower A | Super Structure | L55
41106 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2025-12-09 | 2025-12-13 | Final Painting | 100 | 0 |  | 2025-12-30 |  | 2026-01-05 |  | Tower A | Super Structure | L9 | Finishes | Final Painting
41106 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2025-12-09 | 2025-12-13 | Final Painting | 100 | 0 |  | 2025-12-30 |  | 2026-01-05 |  | Tower A | Super Structure | L9 | Finishes | Final Painting
41106 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2025-12-09 | 2025-12-13 | Final Painting | 100 | 0 |  | 2025-12-30 |  | 2026-01-05 |  | Tower A | Super Structure | L9 | Finishes | Final Painting
41121 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2025-12-09 | 2025-12-13 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2025-12-30 |  | 2026-01-05 |  | Tower A | Super Structure | L10 | MEP | Electrical
41191 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2025-12-09 | 2025-12-16 | HVAC Ducting | 100 | 0 |  | 2025-12-30 |  | 2026-01-07 |  | Tower A | Super Structure | L15 | MEP | HVAC Ducting
41417 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-05-22 | 2025-05-27 | Lobby Plastering | 100 | 0 |  | 2025-12-30 |  | 2026-01-03 |  | Tower A | Super Structure | L29 | Finishes | Lobby Plastering
41432 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-05-22 | 2025-05-24 | Lobby Blockwork | 100 | 0 |  | 2025-12-30 |  | 2026-01-01 |  | Tower A | Super Structure | L30 | Finishes | Blockwork
43082 |  | Not Committed |  | 2025-12-06 | 2026-09-21 | L56-57 | 100 | 0 |  | 2025-12-30 |  | 2026-09-01
43082 |  | Not Committed |  | 2025-12-06 | 2026-09-21 | L56-57 | 100 | 0 |  | 2025-12-30 |  | 2026-09-01 |  |  |  |  | Finishes | Gypsum Plastering Works
43083 |  | Not Committed |  | 2025-12-06 | 2026-01-05 | MEP 1st Fixes | 100 | 0 |  | 2025-12-30 |  | 2026-01-28
43084 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2025-12-06 | 2025-12-13 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2025-12-30 |  | 2026-01-06 |  | Tower A | Super Structure | L56 | MEP | FPS 1st Fix - MEP & Finishes
43085 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-12-06 | 2025-12-11 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2025-12-30 |  | 2026-01-03 |  | Tower A | Super Structure | L56 | MEP | Electrical 1st Fixes
43086 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2025-12-06 | 2025-12-13 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2025-12-30 |  | 2026-01-06 |  | Tower A | Super Structure | L56
43087 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2025-12-06 | 2025-12-23 | Wet Area Waterproofing | 100 | 0 |  | 2025-12-30 |  | 2026-01-15 |  | Tower A | Super Structure | L56
45724 | Tower B - Super Structure - Finishes & MEP - B3 to L7 | Not Ready |  | 2025-10-25 | 2025-12-16 | FHC & Accessories fixing | 100 | 0 |  | 2025-12-30 |  | 2026-02-21 |  | Tower B | Super Structure | B3
45726 | Tower B - Super Structure - Finishes & MEP - B3 to L7 | Not Ready |  | 2025-10-25 | 2025-12-16 | Soil & Waste Downtake piping in Plumbing Shaft | 100 | 0 |  | 2025-12-30 |  | 2026-02-21 |  | Tower B | Super Structure | B3
45730 | Tower B - Super Structure - Finishes & MEP - B3 to L7 | Not Ready |  | 2025-10-25 | 2025-12-16 | HVAC Shaft Ducting | 100 | 0 |  | 2025-12-30 |  | 2026-02-21 |  | Tower B | Super Structure | B3 | MEP | HVAC Grill Fixing
9353 | T-15-11th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2026-01-03 | 2026-01-27 | Plumbing Pipe Line | 100 | 0 |  | 2025-12-31 |  | 2026-01-25
9777 | T-16-7th Floor Flat Area | Not Ready | Flooring & skirting | 2026-01-18 | 2026-03-04 | Flooring & skirting | 100 | 0 |  | 2025-12-31 |  | 2026-02-14
10282 | T-21-6th Floor Common Area | Not Ready | Door-Shaft | 2026-02-03 | 2026-02-16 | Door-Shaft | 100 | 0 |  | 2025-12-31 |  | 2026-01-13
10299 | T-21-7th Floor Flat Area | Not Ready | Window | 2026-01-08 | 2026-02-02 | Window | 100 | 0 |  | 2025-12-31 |  | 2026-01-21
10878 | T-20-9th Floor Common Area | Not Ready | Flooring & skirting | 2026-02-03 | 2026-02-25 | Flooring & skirting | 100 | 0 |  | 2025-12-31 |  | 2026-01-22
11338 | T-19-7th Floor Flat Area | Not Ready | Putty | 2026-01-19 | 2026-04-13 | Putty | 100 | 0 |  | 2025-12-31 |  | 2026-03-24
11448 |  | Not Ready |  | 2026-02-20 | 2026-10-03 | Common Area | 100 | 0 |  | 2025-12-31 |  | 2026-08-12
39772 | Tower A - Super Structure - Core Wall High Rise L77-78 | Not Ready | Core Wall RCC Works | 2025-12-04 | 2025-12-04 | ACS Form Release & jump to next level | 100 | 0 |  | 2025-12-31 |  | 2026-01-01 |  | Tower A | Super Structure | L77 | RCC Super Structure | Core Wall RCC Works
40770 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2024-06-18 | 2024-06-20 | Staircase Fire Door Fixing | 100 | 0 |  | 2025-12-31 |  | 2026-01-03 |  | Tower A | Super Structure
41609 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-12-01 | 2025-12-05 | Lobby Plastering | 100 | 0 |  | 2025-12-31 |  | 2026-01-06 |  | Tower A | Super Structure | L41 | Finishes | Lobby Plastering
41624 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-12-01 | 2025-12-03 | Lobby Blockwork | 100 | 0 |  | 2025-12-31 |  | 2026-01-03 |  | Tower A | Super Structure | L42 | Finishes | Blockwork
42750 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-01-31 | 2026-02-17 | Flooring & Dado works | 100 | 0 |  | 2025-12-31 |  | 2026-01-17 |  | Tower A | Super Structure | L37 | Finishes | Flooring & Dado
42768 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-01-31 | 2026-02-17 | Flooring & Dado works | 100 | 0 |  | 2025-12-31 |  | 2026-01-17 |  | Tower A | Super Structure | L38 | Finishes | Flooring & Dado
43052 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-12-08 | 2025-12-18 | Cement Plastering in wet areas | 100 | 0 |  | 2025-12-31 |  | 2026-01-10 |  | Tower A | Super Structure | L54
44089 | Tower A - Super Structure - Finishes & MEP - L38 to L43 | Started | Façade Works - MEP & Finishes | 2026-01-31 | 2026-02-11 | Accessories & Alignment | 100 | 5 | Units | 2025-12-31 | 2025-09-19 | 2026-01-12 |  | Tower A | Super Structure | L38 | Façade | Façade Works
44089 | Tower A - Super Structure - Finishes & MEP - L38 to L43 | Started | Façade Works - MEP & Finishes | 2026-01-31 | 2026-02-11 | Accessories & Alignment | 100 | 5 | Units | 2025-12-31 | 2025-09-19 | 2026-01-12 |  | Tower A | Super Structure | L38
8736 | T-14-8th Floor Flat Area | Not Ready | Toilets False Celing | 2025-12-03 | 2026-01-05 | Toilets False Celing | 100 | 0 |  | 2026-01-01 |  | 2026-02-01
9233 | T-15-6th Floor Flat Area | Not Ready | Window | 2026-01-13 | 2026-02-06 | Window | 100 | 0 |  | 2026-01-01 |  | 2026-01-23
9335 | T-15-10th Floor Flat Area | Not Ready | Flooring & skirting | 2026-01-03 | 2026-02-18 | Flooring & skirting | 100 | 0 |  | 2026-01-01 |  | 2026-02-18
11407 | T-19-10th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2026-01-09 | 2026-02-03 | Plumbing Pipe Line | 100 | 0 |  | 2026-01-01 |  | 2026-01-22
12038 |  | Complete |  |  |  | Test | 100 | 100 | Units | 2026-01-01 | 2026-01-05 | 2026-01-31 | 2026-01-29
12039 |  | Complete |  |  |  | Test 2 | 100 | 100 | Units | 2026-01-01 | 2026-01-05 | 2026-01-17 | 2026-01-21
39773 |  | Not Ready |  | 2025-12-05 | 2025-12-12 | Core Wall L78-79 | 100 | 0 |  | 2026-01-01 |  | 2026-01-09
39774 | Tower A - Super Structure - Core Wall High Rise L78-79 | Not Ready | Core Wall RCC Works | 2025-12-05 | 2025-12-05 | Scaffolding & platform | 100 | 0 |  | 2026-01-01 |  | 2026-01-02 |  | Tower A | Super Structure | L78 | RCC Super Structure | Core Wall RCC Works
40388 | Tower A - Super Structure - Finishes & MEP - L57 to L58 | Not Ready | Partition Wall-Blockwork | 2025-12-09 | 2025-12-13 | Staircase Area | 100 | 0 |  | 2026-01-01 |  | 2026-01-06 |  | Tower A | Super Structure | L57
40391 | Tower A - Super Structure - Finishes & MEP - L58 to L59 | Not Ready | Partition Wall-Blockwork | 2025-12-09 | 2025-12-16 | Partition Walls | 100 | 0 |  | 2026-01-01 |  | 2026-01-08 |  | Tower A | Super Structure | L58
40745 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2024-06-08 | 2024-06-13 | Final Painting | 100 | 0 |  | 2026-01-01 |  | 2026-01-07 |  | Tower A | Super Structure |  | Finishes | Final Painting
40745 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2024-06-08 | 2024-06-13 | Final Painting | 100 | 0 |  | 2026-01-01 |  | 2026-01-07 |  | Tower A | Super Structure |  | Finishes | Final Painting
40745 | Tower A - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2024-06-08 | 2024-06-13 | Final Painting | 100 | 0 |  | 2026-01-01 |  | 2026-01-07 |  | Tower A | Super Structure |  | Finishes | Final Painting
40819 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | False Ceiling - MEP & Finishes | 2024-07-11 | 2024-07-24 | False Ceiling | 100 | 0 |  | 2026-01-01 |  | 2026-01-13 |  | Tower A | Super Structure |  | Finishes | False Ceiling
41136 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2025-12-11 | 2025-12-13 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-01-01 |  | 2026-01-05 |  | Tower A | Super Structure | L11
41163 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2025-12-11 | 2025-12-18 | False Ceiling | 100 | 0 |  | 2026-01-01 |  | 2026-01-09 |  | Tower A | Super Structure | L13 | Finishes | False Ceiling
41178 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-12-11 | 2025-12-22 | Flooring & Dado | 100 | 0 |  | 2026-01-01 |  | 2026-01-13 |  | Tower A | Super Structure | L14 | Finishes | Flooring & Dado
9357 | T-15-11th Floor Flat Area | Not Ready | Plastering | 2026-01-06 | 2026-02-20 | Plastering-Gypsum | 100 | 0 |  | 2026-01-02 |  | 2026-02-15
9675 | T-16-3rd Floor Flat Area | Not Ready | Window | 2026-01-29 | 2026-02-19 | Window | 100 | 0 |  | 2026-01-02 |  | 2026-01-23
9704 | T-16-4th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-01-31 | 2026-04-24 | 1st Coat Painting | 100 | 0 |  | 2026-01-02 |  | 2026-03-27
10399 | T-21-11th Floor Flat Area | Not Ready | Toilet flooring | 2026-02-05 | 2026-03-10 | Toilet flooring | 100 | 0 |  | 2026-01-02 |  | 2026-02-06
10748 | T-20-4th Floor Common Area | Not Ready | Flooring & skirting | 2026-01-29 | 2026-02-19 | Flooring & skirting | 100 | 0 |  | 2026-01-02 |  | 2026-01-23
10775 | T-20-5th Floor Common Area | Not Ready | Putty | 2026-01-29 | 2026-03-07 | Putty | 100 | 0 |  | 2026-01-02 |  | 2026-02-09
11290 | T-19-5th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-01-23 | 2026-04-17 | 1st Coat Painting | 100 | 0 |  | 2026-01-02 |  | 2026-03-27
11807 | T-18-5th Floor Flat Area | Not Ready | Window | 2026-03-05 | 2026-03-27 | Window | 100 | 0 |  | 2026-01-02 |  | 2026-01-23
11954 | T-18-11th Floor Flat Area | Not Ready | Plastering | 2026-03-17 | 2026-04-08 | Plastering-Cement | 100 | 0 |  | 2026-01-02 |  | 2026-01-24
39775 | Tower A - Super Structure - Core Wall High Rise L78-79 | Not Ready | Core Wall RCC Works | 2025-12-06 | 2025-12-09 | Reinf & Guide shoes fixing | 100 | 0 |  | 2026-01-02 |  | 2026-01-06 |  | Tower A | Super Structure | L78 | RCC Super Structure | Core Wall RCC Works
41433 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-05-26 | 2025-05-30 | Lobby Plastering | 100 | 0 |  | 2026-01-02 |  | 2026-01-07 |  | Tower A | Super Structure | L30 | Finishes | Lobby Plastering
41448 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-05-26 | 2025-05-28 | Lobby Blockwork | 100 | 0 |  | 2026-01-02 |  | 2026-01-05 |  | Tower A | Super Structure | L31 | Finishes | Blockwork
8782 | T-14-10th Floor Flat Area | Not Ready | Plastering | 2025-11-27 | 2025-12-19 | Plastering-Cement | 100 | 0 |  | 2026-01-03 |  | 2026-01-24
9749 | T-16-6th Floor Flat Area | Not Ready | Toilet flooring | 2026-01-22 | 2026-02-25 | Toilet flooring | 100 | 0 |  | 2026-01-03 |  | 2026-02-06
11411 | T-19-10th Floor Flat Area | Not Ready | Plastering | 2026-01-12 | 2026-02-26 | Plastering-Gypsum | 100 | 0 |  | 2026-01-03 |  | 2026-02-15
11932 | T-18-10th Floor Flat Area | Not Ready | Dado | 2026-03-20 | 2026-04-17 | Dado | 100 | 0 |  | 2026-01-03 |  | 2026-02-01
39247 | Retail - Foundation | Not Ready | Raft RCC Works | 2025-07-03 | 2025-07-07 | Liner Wall | 100 | 0 |  | 2026-01-03 |  | 2026-01-07 |  | Retail | Foundation | -- | RCC Sub Structure | Raft RCC Works
39247 | Retail - Foundation | Not Ready | Raft RCC Works | 2025-07-03 | 2025-07-07 | Liner Wall | 100 | 0 |  | 2026-01-03 |  | 2026-01-07 |  | Retail | Foundation | -- | RCC Super Structure | Foundation RCC Works
39247 | Retail - Foundation | Not Ready | Raft RCC Works | 2025-07-03 | 2025-07-07 | Liner Wall | 100 | 0 |  | 2026-01-03 |  | 2026-01-07 |  | Retail | Foundation | --
39776 | Tower A - Super Structure - Core Wall High Rise L78-79 | Not Ready | Core Wall RCC Works | 2025-12-08 | 2025-12-10 | ACS Form Closing & Alignment | 100 | 0 |  | 2026-01-03 |  | 2026-01-07 |  | Tower A | Super Structure | L78 | RCC Super Structure | Core Wall RCC Works
40771 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2024-06-21 | 2024-06-26 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-01-03 |  | 2026-01-09 |  | Tower A | Super Structure |  | MEP | Electrical
40810 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2024-09-23 | 2024-10-01 | Final Painting | 100 | 0 |  | 2026-01-03 |  | 2026-01-13 |  | Tower A | Super Structure |  | Finishes | Final Painting
40810 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2024-09-23 | 2024-10-01 | Final Painting | 100 | 0 |  | 2026-01-03 |  | 2026-01-13 |  | Tower A | Super Structure |  | Finishes | Final Painting
40810 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2024-09-23 | 2024-10-01 | Final Painting | 100 | 0 |  | 2026-01-03 |  | 2026-01-13 |  | Tower A | Super Structure |  | Finishes | Final Painting
41148 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2025-12-13 | 2025-12-16 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-01-03 |  | 2026-01-07 |  | Tower A | Super Structure | L12 | MEP | FPS 2nd Fix - MEP & Finishes
41149 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2025-12-13 | 2025-12-18 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-01-03 |  | 2026-01-09 |  | Tower A | Super Structure | L12 | MEP | Electrical 2nd Fix - MEP & Finishes
41150 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-12-13 | 2025-12-20 | FAPA Device Fixing | 100 | 0 |  | 2026-01-03 |  | 2026-01-12 |  | Tower A | Super Structure | L12
41150 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-12-13 | 2025-12-20 | FAPA Device Fixing | 100 | 0 |  | 2026-01-03 |  | 2026-01-12 |  | Tower A | Super Structure | L12
41150 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-12-13 | 2025-12-20 | FAPA Device Fixing | 100 | 0 |  | 2026-01-03 |  | 2026-01-12 |  | Tower A | Super Structure | L12
41150 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-12-13 | 2025-12-20 | FAPA Device Fixing | 100 | 0 |  | 2026-01-03 |  | 2026-01-12 |  | Tower A | Super Structure | L12
41151 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2025-12-13 | 2025-12-16 | HVAC Grill Fixing | 100 | 0 |  | 2026-01-03 |  | 2026-01-07 |  | Tower A | Super Structure | L12 | MEP | HVAC Grill Fixing
41625 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-12-04 | 2025-12-09 | Lobby Plastering | 100 | 0 |  | 2026-01-03 |  | 2026-01-09 |  | Tower A | Super Structure | L42 | Finishes | Lobby Plastering
41640 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-12-04 | 2025-12-06 | Lobby Blockwork | 100 | 0 |  | 2026-01-03 |  | 2026-01-07 |  | Tower A | Super Structure | L43 | Finishes | Blockwork
43035 |  | Not Committed |  | 2025-12-11 | 2026-04-17 | Finishes after 1st Fix | 100 | 0 |  | 2026-01-03 |  | 2026-03-19
43036 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-12-11 | 2026-01-03 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-01-03 |  | 2026-01-27 |  | Tower A | Super Structure | L53 | Finishes | Blockwork
10202 | T-21-3rd Floor Common Area | Not Ready | Flooring & skirting | 2026-02-08 | 2026-03-02 | Flooring & skirting | 100 | 0 |  | 2026-01-04 |  | 2026-01-28
10229 | T-21-4th Floor Common Area | Not Ready | Putty | 2026-02-08 | 2026-03-18 | Putty | 100 | 0 |  | 2026-01-04 |  | 2026-02-14
11360 | T-19-8th Floor Flat Area | Not Ready | Dado | 2026-01-22 | 2026-02-19 | Dado | 100 | 0 |  | 2026-01-04 |  | 2026-01-31
11386 | T-19-9th Floor Flat Area | Not Ready | Dado | 2026-01-22 | 2026-02-19 | Dado | 100 | 0 |  | 2026-01-04 |  | 2026-01-31
11969 | T-18-11th Floor Common Area | Not Ready | Plastering | 2026-03-19 | 2026-04-22 | Plastering-Gypsum | 100 | 0 |  | 2026-01-04 |  | 2026-02-08
8797 | T-14-11th Floor Common Area | Not Ready | Plastering | 2025-11-29 | 2026-01-01 | Plastering-Gypsum | 100 | 0 |  | 2026-01-05 |  | 2026-02-08
9266 | T-15-7th Floor Common Area | Not Ready | Flooring & skirting | 2026-01-06 | 2026-01-29 | Flooring & skirting | 100 | 0 |  | 2026-01-05 |  | 2026-01-28
10380 | T-21-10th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-02-11 | 2026-05-06 | 1st Coat Painting | 100 | 0 |  | 2026-01-05 |  | 2026-03-31
10402 | T-21-11th Floor Flat Area | Not Ready | Putty | 2026-02-08 | 2026-05-03 | Putty | 100 | 0 |  | 2026-01-05 |  | 2026-03-31
11336 | T-19-7th Floor Flat Area | Not Ready | Toilets False Celing | 2026-01-24 | 2026-02-26 | Toilets False Celing | 100 | 0 |  | 2026-01-05 |  | 2026-02-07
11814 | T-18-5th Floor Common Area | Not Ready | Flooring & skirting | 2026-03-17 | 2026-04-08 | Flooring & skirting | 100 | 0 |  | 2026-01-05 |  | 2026-01-28
11841 | T-18-6th Floor Common Area | Not Ready | Putty | 2026-03-17 | 2026-04-25 | Putty | 100 | 0 |  | 2026-01-05 |  | 2026-02-12
40074 | Tower A - Super Structure - Finishes & MEP - L70 to L71 | Not Ready | CTU Elevators Crash Deck - High Side Services | 2025-12-05 | 2025-12-12 | Jump platform installation | 100 | 0 |  | 2026-01-05 |  | 2026-01-13 |  | Tower A | Super Structure | L70
40074 | Tower A - Super Structure - Finishes & MEP - L70 to L71 | Not Ready | CTU Elevators Crash Deck - High Side Services | 2025-12-05 | 2025-12-12 | Jump platform installation | 100 | 0 |  | 2026-01-05 |  | 2026-01-13 |  | Tower A | Super Structure | L70
40074 | Tower A - Super Structure - Finishes & MEP - L70 to L71 | Not Ready | CTU Elevators Crash Deck - High Side Services | 2025-12-05 | 2025-12-12 | Jump platform installation | 100 | 0 |  | 2026-01-05 |  | 2026-01-13 |  | Tower A | Super Structure | L70
40793 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2024-07-02 | 2024-07-04 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-01-05 |  | 2026-01-08 |  | Tower A | Super Structure |  | MEP | FPS 2nd Fix - MEP & Finishes
40794 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2024-07-02 | 2024-07-06 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-01-05 |  | 2026-01-10 |  | Tower A | Super Structure |  | MEP | Electrical 2nd Fix - MEP & Finishes
40795 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-07-02 | 2024-07-10 | FAPA Device Fixing | 100 | 0 |  | 2026-01-05 |  | 2026-01-13 |  | Tower A | Super Structure
40795 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-07-02 | 2024-07-10 | FAPA Device Fixing | 100 | 0 |  | 2026-01-05 |  | 2026-01-13 |  | Tower A | Super Structure
40795 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-07-02 | 2024-07-10 | FAPA Device Fixing | 100 | 0 |  | 2026-01-05 |  | 2026-01-13 |  | Tower A | Super Structure
40795 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-07-02 | 2024-07-10 | FAPA Device Fixing | 100 | 0 |  | 2026-01-05 |  | 2026-01-13 |  | Tower A | Super Structure
40796 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2024-07-02 | 2024-07-04 | HVAC Grill Fixing | 100 | 0 |  | 2026-01-05 |  | 2026-01-08 |  | Tower A | Super Structure |  | MEP | HVAC Grill Fixing
41122 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2025-12-15 | 2025-12-19 | Final Painting | 100 | 0 |  | 2026-01-05 |  | 2026-01-10 |  | Tower A | Super Structure | L10 | Finishes | Final Painting
41122 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2025-12-15 | 2025-12-19 | Final Painting | 100 | 0 |  | 2026-01-05 |  | 2026-01-10 |  | Tower A | Super Structure | L10 | Finishes | Final Painting
41122 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2025-12-15 | 2025-12-19 | Final Painting | 100 | 0 |  | 2026-01-05 |  | 2026-01-10 |  | Tower A | Super Structure | L10 | Finishes | Final Painting
41137 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2025-12-15 | 2025-12-19 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-01-05 |  | 2026-01-10 |  | Tower A | Super Structure | L11 | MEP | Electrical
41207 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2025-12-15 | 2025-12-22 | HVAC Ducting | 100 | 0 |  | 2026-01-05 |  | 2026-01-13 |  | Tower A | Super Structure | L16 | MEP | HVAC Ducting
8761 | T-14-9th Floor Flat Area | Not Ready | Toilet flooring | 2025-12-09 | 2026-01-10 | Toilet flooring | 100 | 0 |  | 2026-01-06 |  | 2026-02-05
9752 | T-16-6th Floor Flat Area | Not Ready | Putty | 2026-01-27 | 2026-04-20 | Putty | 100 | 0 |  | 2026-01-06 |  | 2026-03-31
10359 | T-21-9th Floor Common Area | Not Ready | Putty | 2026-02-13 | 2026-03-24 | Putty | 100 | 0 |  | 2026-01-06 |  | 2026-02-15
11262 | T-19-4th Floor Flat Area | Not Ready | Door | 2026-02-02 | 2026-02-23 | Door | 100 | 0 |  | 2026-01-06 |  | 2026-01-27
40025 |  | Not Ready |  | 2025-12-03 | 2025-12-10 | L74-75 | 100 | 0 |  | 2026-01-06 |  | 2026-01-17
40025 |  | Not Ready |  | 2025-12-03 | 2025-12-10 | L74-75 | 100 | 0 |  | 2026-01-06 |  | 2026-01-17 |  |  |  |  | Finishes | Gypsum Plastering Works
40026 | Tower A - Super Structure - Core & Outer Slab L74-75 | Not Ready | RCC Works - Vertical | 2025-12-03 | 2025-12-09 | Outer Columns_TA | 100 | 0 |  | 2026-01-06 |  | 2026-01-15 |  | Tower A | Super Structure | L74 | RCC Sub Structure | RCC Works - Vertical
40441 |  | Not Committed |  | 2025-12-03 | 2026-03-24 | L71-72 | 100 | 0 |  | 2026-01-06 |  | 2026-04-15
40441 |  | Not Committed |  | 2025-12-03 | 2026-03-24 | L71-72 | 100 | 0 |  | 2026-01-06 |  | 2026-04-15 |  |  |  |  | Finishes | Gypsum Plastering Works
40442 | Tower A - Super Structure - Finishes & MEP - L71 to L72 | Not Ready | Partition Wall-Blockwork | 2025-12-03 | 2025-12-19 | De-shuttering & Area clearance | 100 | 0 |  | 2026-01-06 |  | 2026-01-23 |  | Tower A | Super Structure | L71
41449 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-05-29 | 2025-06-03 | Lobby Plastering | 100 | 0 |  | 2026-01-06 |  | 2026-01-10 |  | Tower A | Super Structure | L31 | Finishes | Lobby Plastering
41464 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-05-29 | 2025-05-31 | Lobby Blockwork | 100 | 0 |  | 2026-01-06 |  | 2026-01-08 |  | Tower A | Super Structure | L32 | Finishes | Blockwork
42786 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-02-06 | 2026-02-23 | Flooring & Dado works | 100 | 0 |  | 2026-01-06 |  | 2026-01-23 |  | Tower A | Super Structure | L39 | Finishes | Flooring & Dado
42876 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-02-06 | 2026-02-23 | Flooring & Dado works | 100 | 0 |  | 2026-01-06 |  | 2026-01-23 |  | Tower A | Super Structure | L44 | Finishes | Flooring & Dado
45277 |  | Not Ready |  | 2025-11-01 | 2025-11-15 | L9-10 | 100 | 0 |  | 2026-01-06 |  | 2026-01-21
45277 |  | Not Ready |  | 2025-11-01 | 2025-11-15 | L9-10 | 100 | 0 |  | 2026-01-06 |  | 2026-01-21 |  |  |  |  | Finishes | Gypsum Plastering Works
45278 | Tower B - Super Structure - Core & Outer Slab L9-10 | Not Ready | RCC Works - Vertical | 2025-11-01 | 2025-11-12 | Outer Columns_TA | 100 | 0 |  | 2026-01-06 |  | 2026-01-17 |  | Tower B | Super Structure | L9 | RCC Sub Structure | RCC Works - Vertical
45429 |  | Not Committed |  | 2025-11-01 | 2025-12-02 | P6 to L7 | 100 | 0 |  | 2026-01-06 |  | 2026-02-07
45429 |  | Not Committed |  | 2025-11-01 | 2025-12-02 | P6 to L7 | 100 | 0 |  | 2026-01-06 |  | 2026-02-07 |  |  |  |  | Finishes | Gypsum Plastering Works
45430 | Tower B - Super Structure - Finishes & MEP - P6 to L7 | Not Ready | Partition Wall-Blockwork | 2025-11-01 | 2025-11-18 | De-shuttering & Area clearance | 100 | 0 |  | 2026-01-06 |  | 2026-01-23 |  | Tower B | Super Structure
48163 | Retail - Super structure - GF to R1 - P2 | Not Ready |  | 2025-09-13 | 2025-10-08 | Slab_RT | 100 | 0 |  | 2026-01-06 |  | 2026-01-29 |  | Retail | Super Structure | GF | RCC Sub Structure | RCC Works - Slab
48163 | Retail - Super structure - GF to R1 - P2 | Not Ready |  | 2025-09-13 | 2025-10-08 | Slab_RT | 100 | 0 |  | 2026-01-06 |  | 2026-01-29 |  | Retail | Super Structure | GF
48171 | Retail - Super structure - GF to R1 - P4 | Not Ready |  | 2025-09-13 | 2025-10-08 | Slab_RT | 100 | 0 |  | 2026-01-06 |  | 2026-01-29 |  | Retail | Super Structure | GF | RCC Sub Structure | RCC Works - Slab
48171 | Retail - Super structure - GF to R1 - P4 | Not Ready |  | 2025-09-13 | 2025-10-08 | Slab_RT | 100 | 0 |  | 2026-01-06 |  | 2026-01-29 |  | Retail | Super Structure | GF
9354 | T-15-11th Floor Flat Area | Not Ready | Plastering | 2026-01-11 | 2026-02-04 | Plastering-Cement | 100 | 0 |  | 2026-01-07 |  | 2026-01-31
10771 | T-20-5th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-02-19 | 2026-04-27 | 2nd Coat Painting | 100 | 0 |  | 2026-01-07 |  | 2026-03-15
10823 | T-20-7th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-02-19 | 2026-04-27 | 2nd Coat Painting | 100 | 0 |  | 2026-01-07 |  | 2026-03-15
10853 | T-20-8th Floor Common Area | Not Ready | Putty | 2026-02-09 | 2026-03-19 | Putty | 100 | 0 |  | 2026-01-07 |  | 2026-02-17
39248 | Retail - Foundation | Not Ready | Raft RCC Works | 2025-07-07 | 2025-07-12 | Waterproofing Horizontal | 100 | 0 |  | 2026-01-07 |  | 2026-01-13 |  | Retail | Foundation | -- | RCC Sub Structure | Raft RCC Works
39248 | Retail - Foundation | Not Ready | Raft RCC Works | 2025-07-07 | 2025-07-12 | Waterproofing Horizontal | 100 | 0 |  | 2026-01-07 |  | 2026-01-13 |  | Retail | Foundation | -- | RCC Super Structure | Foundation RCC Works
39248 | Retail - Foundation | Not Ready | Raft RCC Works | 2025-07-07 | 2025-07-12 | Waterproofing Horizontal | 100 | 0 |  | 2026-01-07 |  | 2026-01-13 |  | Retail | Foundation | --
39777 | Tower A - Super Structure - Core Wall High Rise L78-79 | Not Ready | Core Wall RCC Works | 2025-12-11 | 2025-12-11 | Casting | 100 | 0 |  | 2026-01-07 |  | 2026-01-08 |  | Tower A | Super Structure | L78 | RCC Super Structure | Core Wall RCC Works
40530 | Tower A - Super Structure - Finishes & MEP - L56 to L57 | Not Ready | Gypsum Plastering Works | 2025-12-15 | 2026-01-01 | L56-57 | 100 | 0 |  | 2026-01-07 |  | 2026-01-23 |  | Tower A | Super Structure | L56 | Finishes | Gypsum Plastering Works
40530 | Tower A - Super Structure - Finishes & MEP - L56 to L57 | Not Ready | Gypsum Plastering Works | 2025-12-15 | 2026-01-01 | L56-57 | 100 | 0 |  | 2026-01-07 |  | 2026-01-23 |  | Tower A | Super Structure | L56
41152 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2025-12-17 | 2025-12-19 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-01-07 |  | 2026-01-10 |  | Tower A | Super Structure | L12
41179 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2025-12-17 | 2025-12-24 | False Ceiling | 100 | 0 |  | 2026-01-07 |  | 2026-01-15 |  | Tower A | Super Structure | L14 | Finishes | False Ceiling
41194 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-12-17 | 2025-12-29 | Flooring & Dado | 100 | 0 |  | 2026-01-07 |  | 2026-01-19 |  | Tower A | Super Structure | L15 | Finishes | Flooring & Dado
41641 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-12-08 | 2025-12-12 | Lobby Plastering | 100 | 0 |  | 2026-01-07 |  | 2026-01-13 |  | Tower A | Super Structure | L43 | Finishes | Lobby Plastering
41651 |  | Not Committed |  | 2025-12-08 | 2026-05-30 | L44-45 | 100 | 0 |  | 2026-01-07 |  | 2026-06-20
41651 |  | Not Committed |  | 2025-12-08 | 2026-05-30 | L44-45 | 100 | 0 |  | 2026-01-07 |  | 2026-06-20 |  |  |  |  | Finishes | Gypsum Plastering Works
41656 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-12-08 | 2025-12-10 | Lobby Blockwork | 100 | 0 |  | 2026-01-07 |  | 2026-01-10 |  | Tower A | Super Structure | L44 | Finishes | Blockwork
43100 |  | Not Committed |  | 2025-12-15 | 2026-09-21 | L57-58 (Refuge) | 100 | 0 |  | 2026-01-07 |  | 2026-09-01
43101 |  | Not Committed |  | 2025-12-15 | 2026-01-13 | MEP 1st Fixes | 100 | 0 |  | 2026-01-07 |  | 2026-02-05
43102 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2025-12-15 | 2025-12-22 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-01-07 |  | 2026-01-14 |  | Tower A | Super Structure | L57 | MEP | FPS 1st Fix - MEP & Finishes
43103 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-12-15 | 2025-12-19 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-01-07 |  | 2026-01-12 |  | Tower A | Super Structure | L57 | MEP | Electrical 1st Fixes
43104 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2025-12-15 | 2025-12-22 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-01-07 |  | 2026-01-14 |  | Tower A | Super Structure | L57
43105 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2025-12-15 | 2026-01-01 | Wet Area Waterproofing | 100 | 0 |  | 2026-01-07 |  | 2026-01-23 |  | Tower A | Super Structure | L57
8688 | T-14-6th Floor Flat Area | Not Ready | Door | 2025-12-25 | 2026-01-16 | Door | 100 | 0 |  | 2026-01-08 |  | 2026-01-29
9262 | T-15-7th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-01-14 | 2026-04-09 | 1st Coat Painting | 100 | 0 |  | 2026-01-08 |  | 2026-04-02
9368 |  | Not Ready |  | 2026-01-13 | 2026-08-27 | Common Area | 100 | 0 |  | 2026-01-08 |  | 2026-08-22
10872 | T-20-9th Floor Flat Area | Not Ready | Door | 2026-02-28 | 2026-03-22 | Door | 100 | 0 |  | 2026-01-08 |  | 2026-01-29
10897 | T-20-10th Floor Flat Area | Not Ready | Window | 2026-02-28 | 2026-03-22 | Window | 100 | 0 |  | 2026-01-08 |  | 2026-01-29
10918 | T-20-11th Floor Flat Area | Not Ready | Dado | 2026-02-09 | 2026-03-07 | Dado | 100 | 0 |  | 2026-01-08 |  | 2026-02-05
11408 | T-19-10th Floor Flat Area | Not Ready | Plastering | 2026-01-19 | 2026-02-10 | Plastering-Cement | 100 | 0 |  | 2026-01-08 |  | 2026-01-28
39778 | Tower A - Super Structure - Core Wall High Rise L78-79 | Not Ready | Core Wall RCC Works | 2025-12-12 | 2025-12-12 | ACS Form Release & jump to next level | 100 | 0 |  | 2026-01-08 |  | 2026-01-09 |  | Tower A | Super Structure | L78 | RCC Super Structure | Core Wall RCC Works
40797 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2024-07-05 | 2024-07-09 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-01-08 |  | 2026-01-12 |  | Tower A | Super Structure
43070 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-12-16 | 2025-12-27 | Cement Plastering in wet areas | 100 | 0 |  | 2026-01-08 |  | 2026-01-19 |  | Tower A | Super Structure | L55
8720 | T-14-7th Floor Common Area | Not Ready | Flooring & skirting | 2025-12-08 | 2025-12-29 | Flooring & skirting | 100 | 0 |  | 2026-01-09 |  | 2026-01-30
8764 | T-14-9th Floor Flat Area | Not Ready | Putty | 2025-12-12 | 2026-03-05 | Putty | 100 | 0 |  | 2026-01-09 |  | 2026-04-02
9369 | T-15-11th Floor Common Area | Not Ready | Plastering | 2026-01-13 | 2026-02-17 | Plastering-Gypsum | 100 | 0 |  | 2026-01-09 |  | 2026-02-13
39779 |  | Not Ready |  | 2025-12-13 | 2025-12-20 | Core Wall L79-80 | 100 | 0 |  | 2026-01-09 |  | 2026-01-20
39780 | Tower A - Super Structure - Core Wall High Rise L79-80 | Not Ready | Core Wall RCC Works | 2025-12-13 | 2025-12-13 | Scaffolding & platform | 100 | 0 |  | 2026-01-09 |  | 2026-01-10 |  | Tower A | Super Structure | L79 | RCC Super Structure | Core Wall RCC Works
40027 | Tower A - Super Structure - Core & Outer Slab L74-75 | Not Ready | RCC Works - Slab | 2025-12-05 | 2025-12-10 | Outer Slab_TA | 100 | 0 |  | 2026-01-09 |  | 2026-01-17 |  | Tower A | Super Structure | L74 | RCC Sub Structure | RCC Works - Slab
40392 | Tower A - Super Structure - Finishes & MEP - L58 to L59 | Not Ready | Partition Wall-Blockwork | 2025-12-17 | 2025-12-22 | Staircase Area | 100 | 0 |  | 2026-01-09 |  | 2026-01-14 |  | Tower A | Super Structure | L58
40395 | Tower A - Super Structure - Finishes & MEP - L59 to L60 | Not Ready | Partition Wall-Blockwork | 2025-12-17 | 2025-12-24 | Partition Walls | 100 | 0 |  | 2026-01-09 |  | 2026-01-16 |  | Tower A | Super Structure | L59
40772 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2024-06-27 | 2024-07-02 | Final Painting | 100 | 0 |  | 2026-01-09 |  | 2026-01-15 |  | Tower A | Super Structure |  | Finishes | Final Painting
40772 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2024-06-27 | 2024-07-02 | Final Painting | 100 | 0 |  | 2026-01-09 |  | 2026-01-15 |  | Tower A | Super Structure |  | Finishes | Final Painting
40772 | Tower A - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2024-06-27 | 2024-07-02 | Final Painting | 100 | 0 |  | 2026-01-09 |  | 2026-01-15 |  | Tower A | Super Structure |  | Finishes | Final Painting
40846 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | False Ceiling - MEP & Finishes | 2024-07-26 | 2024-08-07 | False Ceiling | 100 | 0 |  | 2026-01-09 |  | 2026-01-21 |  | Tower A | Super Structure |  | Finishes | False Ceiling
41164 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2025-12-19 | 2025-12-22 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-01-09 |  | 2026-01-13 |  | Tower A | Super Structure | L13 | MEP | FPS 2nd Fix - MEP & Finishes
41165 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2025-12-19 | 2025-12-24 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-01-09 |  | 2026-01-15 |  | Tower A | Super Structure | L13 | MEP | Electrical 2nd Fix - MEP & Finishes
41166 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-12-19 | 2025-12-27 | FAPA Device Fixing | 100 | 0 |  | 2026-01-09 |  | 2026-01-17 |  | Tower A | Super Structure | L13
41166 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-12-19 | 2025-12-27 | FAPA Device Fixing | 100 | 0 |  | 2026-01-09 |  | 2026-01-17 |  | Tower A | Super Structure | L13
41166 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-12-19 | 2025-12-27 | FAPA Device Fixing | 100 | 0 |  | 2026-01-09 |  | 2026-01-17 |  | Tower A | Super Structure | L13
41166 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-12-19 | 2025-12-27 | FAPA Device Fixing | 100 | 0 |  | 2026-01-09 |  | 2026-01-17 |  | Tower A | Super Structure | L13
41167 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2025-12-19 | 2025-12-22 | HVAC Grill Fixing | 100 | 0 |  | 2026-01-09 |  | 2026-01-13 |  | Tower A | Super Structure | L13 | MEP | HVAC Grill Fixing
41465 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-06-02 | 2025-06-06 | Lobby Plastering | 100 | 0 |  | 2026-01-09 |  | 2026-01-14 |  | Tower A | Super Structure | L32 | Finishes | Lobby Plastering
41480 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-06-02 | 2025-06-04 | Lobby Blockwork | 100 | 0 |  | 2026-01-09 |  | 2026-01-12 |  | Tower A | Super Structure | L33 | Finishes | Blockwork
44554 | NTA_Zone 2 - Sub Structure - B2 to B1 | Not Ready | Finishes (Lobby & Floor Area) | 2024-11-01 | 2024-12-05 | Staircase Finishes | 100 | 0 |  | 2026-01-09 |  | 2026-02-13 |  | NTA_Zone 2 | Sub Structure | B2
44554 | NTA_Zone 2 - Sub Structure - B2 to B1 | Not Ready | Finishes (Lobby & Floor Area) | 2024-11-01 | 2024-12-05 | Staircase Finishes | 100 | 0 |  | 2026-01-09 |  | 2026-02-13 |  | NTA_Zone 2 | Sub Structure | B2
8713 | T-14-7th Floor Flat Area | Not Ready | Window | 2025-12-27 | 2026-01-19 | Window | 100 | 0 |  | 2026-01-10 |  | 2026-02-03
9676 | T-16-3rd Floor Flat Area | Not Ready | Door | 2026-02-06 | 2026-02-28 | Door | 100 | 0 |  | 2026-01-10 |  | 2026-01-31
9774 | T-16-7th Floor Flat Area | Not Ready | Dado | 2026-01-30 | 2026-02-26 | Dado | 100 | 0 |  | 2026-01-10 |  | 2026-02-06
9797 | T-16-8th Floor Flat Area | Not Ready | Waterproofing | 2026-01-28 | 2026-03-02 | Waterproofing | 100 | 0 |  | 2026-01-10 |  | 2026-02-10
9823 | T-16-9th Floor Flat Area | Not Ready | Waterproofing | 2026-01-28 | 2026-03-02 | Waterproofing | 100 | 0 |  | 2026-01-10 |  | 2026-02-10
10300 | T-21-7th Floor Flat Area | Not Ready | Door | 2026-01-21 | 2026-02-12 | Door | 100 | 0 |  | 2026-01-10 |  | 2026-02-01
10400 | T-21-11th Floor Flat Area | Not Ready | Toilets False Celing | 2026-02-13 | 2026-03-18 | Toilets False Celing | 100 | 0 |  | 2026-01-10 |  | 2026-02-13
11287 | T-19-5th Floor Flat Area | Not Ready | Window | 2026-02-06 | 2026-02-27 | Window | 100 | 0 |  | 2026-01-10 |  | 2026-02-01
11423 | T-19-11th Floor Common Area | Not Ready | Plastering | 2026-01-21 | 2026-02-23 | Plastering-Gypsum | 100 | 0 |  | 2026-01-10 |  | 2026-02-13
11933 | T-18-10th Floor Flat Area | Not Ready | Toilet flooring | 2026-03-28 | 2026-04-30 | Toilet flooring | 100 | 0 |  | 2026-01-10 |  | 2026-02-13
39781 | Tower A - Super Structure - Core Wall High Rise L79-80 | Not Ready | Core Wall RCC Works | 2025-12-15 | 2025-12-17 | Reinf & Guide shoes fixing | 100 | 0 |  | 2026-01-10 |  | 2026-01-14 |  | Tower A | Super Structure | L79 | RCC Super Structure | Core Wall RCC Works
41138 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2025-12-20 | 2025-12-26 | Final Painting | 100 | 0 |  | 2026-01-10 |  | 2026-01-16 |  | Tower A | Super Structure | L11 | Finishes | Final Painting
41138 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2025-12-20 | 2025-12-26 | Final Painting | 100 | 0 |  | 2026-01-10 |  | 2026-01-16 |  | Tower A | Super Structure | L11 | Finishes | Final Painting
41138 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2025-12-20 | 2025-12-26 | Final Painting | 100 | 0 |  | 2026-01-10 |  | 2026-01-16 |  | Tower A | Super Structure | L11 | Finishes | Final Painting
41153 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2025-12-20 | 2025-12-26 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-01-10 |  | 2026-01-16 |  | Tower A | Super Structure | L12 | MEP | Electrical
41223 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2025-12-20 | 2025-12-29 | HVAC Ducting | 100 | 0 |  | 2026-01-10 |  | 2026-01-19 |  | Tower A | Super Structure | L17 | MEP | HVAC Ducting
41657 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-12-11 | 2025-12-16 | Lobby Plastering | 100 | 0 |  | 2026-01-10 |  | 2026-01-16 |  | Tower A | Super Structure | L44 | Finishes | Lobby Plastering
41667 |  | Not Committed |  | 2025-12-11 | 2026-06-05 | L45-46 | 100 | 0 |  | 2026-01-10 |  | 2026-06-26
41667 |  | Not Committed |  | 2025-12-11 | 2026-06-05 | L45-46 | 100 | 0 |  | 2026-01-10 |  | 2026-06-26 |  |  |  |  | Finishes | Gypsum Plastering Works
41672 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-12-11 | 2025-12-13 | Lobby Blockwork | 100 | 0 |  | 2026-01-10 |  | 2026-01-14 |  | Tower A | Super Structure | L45 | Finishes | Blockwork
43001 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-12-18 | 2025-12-26 | Door & Window Frame work | 100 | 0 |  | 2026-01-10 |  | 2026-01-17 |  | Tower A | Super Structure | L51 | Finishes | Door & Window Frame work
44569 |  | Not Committed |  | 2025-04-10 | 2025-08-19 | P2 to P3 | 100 | 0 |  | 2026-01-10 |  | 2026-05-15
44569 |  | Not Committed |  | 2025-04-10 | 2025-08-19 | P2 to P3 | 100 | 0 |  | 2026-01-10 |  | 2026-05-15
44569 |  | Not Committed |  | 2025-04-10 | 2025-08-19 | P2 to P3 | 100 | 0 |  | 2026-01-10 |  | 2026-05-15
44570 | NTA_Zone 2 - Super Structure - P2 to P3 | Not Ready | Finishes (Lobby & Floor Area) | 2025-04-10 | 2025-06-02 | VDF Flooring | 100 | 0 |  | 2026-01-10 |  | 2026-03-05 |  | NTA_Zone 2 | Super Structure
44570 | NTA_Zone 2 - Super Structure - P2 to P3 | Not Ready | Finishes (Lobby & Floor Area) | 2025-04-10 | 2025-06-02 | VDF Flooring | 100 | 0 |  | 2026-01-10 |  | 2026-03-05 |  | NTA_Zone 2 | Super Structure
45728 | Tower B - Super Structure - Finishes & MEP - B3 to L7 | Not Ready |  | 2025-11-06 | 2025-12-10 | Shaft Cabling in Electrical & ELV Shaft | 100 | 0 |  | 2026-01-10 |  | 2026-02-16 |  | Tower B | Super Structure | B3
9234 | T-15-6th Floor Flat Area | Not Ready | Door | 2026-01-25 | 2026-02-17 | Door | 100 | 0 |  | 2026-01-11 |  | 2026-02-03
9332 | T-15-10th Floor Flat Area | Not Ready | Dado | 2026-01-14 | 2026-02-12 | Dado | 100 | 0 |  | 2026-01-11 |  | 2026-02-08
9750 | T-16-6th Floor Flat Area | Not Ready | Toilets False Celing | 2026-02-01 | 2026-03-06 | Toilets False Celing | 100 | 0 |  | 2026-01-11 |  | 2026-02-11
11320 | T-19-6th Floor Common Area | Not Ready | Flooring & skirting | 2026-01-27 | 2026-02-18 | Flooring & skirting | 100 | 0 |  | 2026-01-11 |  | 2026-01-31
11361 | T-19-8th Floor Flat Area | Not Ready | Toilet flooring | 2026-01-30 | 2026-03-04 | Toilet flooring | 100 | 0 |  | 2026-01-11 |  | 2026-02-13
11387 | T-19-9th Floor Flat Area | Not Ready | Toilet flooring | 2026-01-30 | 2026-03-04 | Toilet flooring | 100 | 0 |  | 2026-01-11 |  | 2026-02-13
11888 | T-18-8th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-04-04 | 2026-06-26 | 1st Coat Painting | 100 | 0 |  | 2026-01-11 |  | 2026-04-04
11914 | T-18-9th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-04-04 | 2026-06-26 | 1st Coat Painting | 100 | 0 |  | 2026-01-11 |  | 2026-04-04
8716 | T-14-7th Floor Flat Area | Not Ready | 1st Coat Painting | 2025-12-16 | 2026-03-10 | 1st Coat Painting | 100 | 0 |  | 2026-01-12 |  | 2026-04-06
9846 | T-16-10th Floor Flat Area | Not Ready | Blockwork | 2026-01-24 | 2026-02-16 | Blockwork-Ledge Wall | 100 | 0 |  | 2026-01-12 |  | 2026-02-03
10325 | T-21-8th Floor Flat Area | Not Ready | Window | 2026-01-23 | 2026-02-14 | Window | 100 | 0 |  | 2026-01-12 |  | 2026-02-01
11892 | T-18-8th Floor Common Area | Not Ready | Flooring & skirting | 2026-03-28 | 2026-04-20 | Flooring & skirting | 100 | 0 |  | 2026-01-12 |  | 2026-02-03
11968 |  | Not Ready |  | 2026-03-19 | 2026-10-29 | Common Area | 100 | 0 |  | 2026-01-12 |  | 2026-08-29
39782 | Tower A - Super Structure - Core Wall High Rise L79-80 | Not Ready | Core Wall RCC Works | 2025-12-16 | 2025-12-18 | ACS Form Closing & Alignment | 100 | 0 |  | 2026-01-12 |  | 2026-01-15 |  | Tower A | Super Structure | L79 | RCC Super Structure | Core Wall RCC Works
40798 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2024-07-12 | 2024-07-18 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-01-12 |  | 2026-01-17 |  | Tower A | Super Structure |  | MEP | Electrical
42804 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-02-12 | 2026-02-28 | Flooring & Dado works | 100 | 0 |  | 2026-01-12 |  | 2026-01-30 |  | Tower A | Super Structure | L40 | Finishes | Flooring & Dado
42894 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-02-12 | 2026-02-28 | Flooring & Dado works | 100 | 0 |  | 2026-01-12 |  | 2026-01-30 |  | Tower A | Super Structure | L45 | Finishes | Flooring & Dado
43053 |  | Not Committed |  | 2025-12-19 | 2026-04-23 | Finishes after 1st Fix | 100 | 0 |  | 2026-01-12 |  | 2026-03-25
43054 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-12-19 | 2026-01-12 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-01-12 |  | 2026-02-04 |  | Tower A | Super Structure | L54 | Finishes | Blockwork
44092 | Tower A - Super Structure - Finishes & MEP - L43 to L48 | Started | Façade Works - MEP & Finishes | 2026-02-12 | 2026-02-23 | DGU Assembly Installation | 100 | 1 | Units | 2026-01-12 | 2025-09-19 | 2026-01-23 |  | Tower A | Super Structure | L43 | Façade | Façade Works
44093 | Tower A - Super Structure - Finishes & MEP - L43 to L48 | Started | Façade Works - MEP & Finishes | 2026-02-12 | 2026-03-07 | Installation of highly reflective metal sheet | 100 | 6 | Units | 2026-01-12 | 2025-09-19 | 2026-02-05 |  | Tower A | Super Structure | L43 | Façade | Façade Works
44094 | Tower A - Super Structure - Finishes & MEP - L43 to L48 | Started | Façade Works - MEP & Finishes | 2026-02-12 | 2026-02-23 | Fixing of Backlit Laminated Glass assembly & ACP Panels | 100 | 1 | Units | 2026-01-12 | 2025-09-19 | 2026-01-23 |  | Tower A | Super Structure | L43 | Façade | Façade Works
44095 | Tower A - Super Structure - Finishes & MEP - L43 to L48 | Not Ready | Façade Works - MEP & Finishes | 2026-02-12 | 2026-02-23 | Fixing of Louvers | 100 | 0 |  | 2026-01-12 |  | 2026-01-23 |  | Tower A | Super Structure | L43 | Façade | Façade Works
44095 | Tower A - Super Structure - Finishes & MEP - L43 to L48 | Not Ready | Façade Works - MEP & Finishes | 2026-02-12 | 2026-02-23 | Fixing of Louvers | 100 | 0 |  | 2026-01-12 |  | 2026-01-23 |  | Tower A | Super Structure | L43
48199 | Retail - Super structure - R1 to CH00 - P5 | Not Ready |  | 2025-09-20 | 2025-10-08 | Slab_RT | 100 | 0 |  | 2026-01-12 |  | 2026-01-29 |  | Retail | Super Structure |  | RCC Sub Structure | RCC Works - Slab
48199 | Retail - Super structure - R1 to CH00 - P5 | Not Ready |  | 2025-09-20 | 2025-10-08 | Slab_RT | 100 | 0 |  | 2026-01-12 |  | 2026-01-29 |  | Retail | Super Structure
9214 | T-15-5th Floor Common Area | Not Ready | Flooring & skirting | 2026-01-11 | 2026-02-04 | Flooring & skirting | 100 | 0 |  | 2026-01-13 |  | 2026-02-08
9241 | T-15-6th Floor Common Area | Not Ready | Putty | 2026-01-11 | 2026-02-20 | Putty | 100 | 0 |  | 2026-01-13 |  | 2026-02-22
9259 | T-15-7th Floor Flat Area | Not Ready | Window | 2026-01-28 | 2026-02-19 | Window | 100 | 0 |  | 2026-01-13 |  | 2026-02-06
9888 |  | Not Ready |  | 2026-03-13 | 2026-10-24 | Common Area | 100 | 0 |  | 2026-01-13 |  | 2026-08-26
11808 | T-18-5th Floor Flat Area | Not Ready | Door | 2026-03-17 | 2026-04-08 | Door | 100 | 0 |  | 2026-01-13 |  | 2026-02-04
11837 | T-18-6th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-04-03 | 2026-06-09 | 2nd Coat Painting | 100 | 0 |  | 2026-01-13 |  | 2026-03-20
11936 | T-18-10th Floor Flat Area | Not Ready | Putty | 2026-04-01 | 2026-06-23 | Putty | 100 | 0 |  | 2026-01-13 |  | 2026-04-06
39249 | Retail - Foundation | Not Ready | Raft RCC Works | 2025-07-12 | 2025-07-16 | Waterproofing vertical - toe ht. | 100 | 0 |  | 2026-01-13 |  | 2026-01-15 |  | Retail | Foundation | -- | RCC Sub Structure | Raft RCC Works
39249 | Retail - Foundation | Not Ready | Raft RCC Works | 2025-07-12 | 2025-07-16 | Waterproofing vertical - toe ht. | 100 | 0 |  | 2026-01-13 |  | 2026-01-15 |  | Retail | Foundation | -- | RCC Super Structure | Foundation RCC Works
39249 | Retail - Foundation | Not Ready | Raft RCC Works | 2025-07-12 | 2025-07-16 | Waterproofing vertical - toe ht. | 100 | 0 |  | 2026-01-13 |  | 2026-01-15 |  | Retail | Foundation | --
40811 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2024-10-03 | 2024-10-21 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-01-13 |  | 2026-01-31 |  | Tower A | Super Structure
40811 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2024-10-03 | 2024-10-21 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-01-13 |  | 2026-01-31 |  | Tower A | Super Structure
40811 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2024-10-03 | 2024-10-21 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-01-13 |  | 2026-01-31 |  | Tower A | Super Structure
40820 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2024-07-30 | 2024-08-01 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-01-13 |  | 2026-01-16 |  | Tower A | Super Structure |  | MEP | FPS 2nd Fix - MEP & Finishes
40821 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2024-07-30 | 2024-08-03 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-01-13 |  | 2026-01-19 |  | Tower A | Super Structure |  | MEP | Electrical 2nd Fix - MEP & Finishes
40822 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-07-30 | 2024-08-07 | FAPA Device Fixing | 100 | 0 |  | 2026-01-13 |  | 2026-01-21 |  | Tower A | Super Structure
40822 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-07-30 | 2024-08-07 | FAPA Device Fixing | 100 | 0 |  | 2026-01-13 |  | 2026-01-21 |  | Tower A | Super Structure
40822 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-07-30 | 2024-08-07 | FAPA Device Fixing | 100 | 0 |  | 2026-01-13 |  | 2026-01-21 |  | Tower A | Super Structure
40822 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-07-30 | 2024-08-07 | FAPA Device Fixing | 100 | 0 |  | 2026-01-13 |  | 2026-01-21 |  | Tower A | Super Structure
40823 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2024-07-30 | 2024-08-01 | HVAC Grill Fixing | 100 | 0 |  | 2026-01-13 |  | 2026-01-16 |  | Tower A | Super Structure |  | MEP | HVAC Grill Fixing
40835 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2024-10-03 | 2024-10-10 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-01-13 |  | 2026-01-21 |  | Tower A | Super Structure |  | MEP | FPS 2nd Fix - MEP & Finishes
40836 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-10-03 | 2024-10-10 | FAPA Device Fixing | 100 | 0 |  | 2026-01-13 |  | 2026-01-21 |  | Tower A | Super Structure
40836 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-10-03 | 2024-10-10 | FAPA Device Fixing | 100 | 0 |  | 2026-01-13 |  | 2026-01-21 |  | Tower A | Super Structure
40836 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-10-03 | 2024-10-10 | FAPA Device Fixing | 100 | 0 |  | 2026-01-13 |  | 2026-01-21 |  | Tower A | Super Structure
40836 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-10-03 | 2024-10-10 | FAPA Device Fixing | 100 | 0 |  | 2026-01-13 |  | 2026-01-21 |  | Tower A | Super Structure
41168 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2025-12-23 | 2025-12-26 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-01-13 |  | 2026-01-16 |  | Tower A | Super Structure | L13
41195 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2025-12-23 | 2025-12-31 | False Ceiling | 100 | 0 |  | 2026-01-13 |  | 2026-01-21 |  | Tower A | Super Structure | L15 | Finishes | False Ceiling
41210 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-12-23 | 2026-01-03 | Flooring & Dado | 100 | 0 |  | 2026-01-13 |  | 2026-01-24 |  | Tower A | Super Structure | L16 | Finishes | Flooring & Dado
41481 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-06-05 | 2025-06-11 | Lobby Plastering | 100 | 0 |  | 2026-01-13 |  | 2026-01-17 |  | Tower A | Super Structure | L33 | Finishes | Lobby Plastering
41496 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-06-05 | 2025-06-09 | Lobby Blockwork | 100 | 0 |  | 2026-01-13 |  | 2026-01-15 |  | Tower A | Super Structure | L34 | Finishes | Blockwork
45279 | Tower B - Super Structure - Core & Outer Slab L9-10 | Not Ready | RCC Works - Slab | 2025-11-08 | 2025-11-15 | Outer Slab_TA | 100 | 0 |  | 2026-01-13 |  | 2026-01-21 |  | Tower B | Super Structure | L9 | RCC Sub Structure | RCC Works - Slab
8762 | T-14-9th Floor Flat Area | Not Ready | Toilets False Celing | 2025-12-17 | 2026-01-20 | Toilets False Celing | 100 | 0 |  | 2026-01-14 |  | 2026-02-17
9850 | T-16-10th Floor Flat Area | Not Ready | Electrical DB Fixing | 2026-01-28 | 2026-02-13 | Electrical DB Fixing | 100 | 0 |  | 2026-01-14 |  | 2026-01-31
10283 | T-21-6th Floor Common Area | Not Ready | Window-Open Area | 2026-02-16 | 2026-02-23 | Window-Open Area | 100 | 0 |  | 2026-01-14 |  | 2026-01-22
10410 | T-21-11th Floor Common Area | Not Ready | Flooring & skirting | 2026-02-25 | 2026-03-18 | Flooring & skirting | 100 | 0 |  | 2026-01-14 |  | 2026-02-05
11364 | T-19-8th Floor Flat Area | Not Ready | Putty | 2026-02-03 | 2026-04-27 | Putty | 100 | 0 |  | 2026-01-14 |  | 2026-04-07
11390 | T-19-9th Floor Flat Area | Not Ready | Putty | 2026-02-03 | 2026-04-27 | Putty | 100 | 0 |  | 2026-01-14 |  | 2026-04-07
41673 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-12-15 | 2025-12-19 | Lobby Plastering | 100 | 0 |  | 2026-01-14 |  | 2026-01-20 |  | Tower A | Super Structure | L45 | Finishes | Lobby Plastering
41683 |  | Not Committed |  | 2025-12-15 | 2026-06-11 | L46-47 | 100 | 0 |  | 2026-01-14 |  | 2026-07-02
41683 |  | Not Committed |  | 2025-12-15 | 2026-06-11 | L46-47 | 100 | 0 |  | 2026-01-14 |  | 2026-07-02 |  |  |  |  | Finishes | Gypsum Plastering Works
41688 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-12-15 | 2025-12-17 | Lobby Blockwork | 100 | 0 |  | 2026-01-14 |  | 2026-01-17 |  | Tower A | Super Structure | L46 | Finishes | Blockwork
8668 | T-14-5th Floor Common Area | Not Ready | Flooring & skirting | 2025-12-13 | 2026-01-03 | Flooring & skirting | 100 | 0 |  | 2026-01-15 |  | 2026-02-05
8695 | T-14-6th Floor Common Area | Not Ready | Putty | 2025-12-13 | 2026-01-21 | Putty | 100 | 0 |  | 2026-01-15 |  | 2026-02-22
9803 | T-16-8th Floor Flat Area | Not Ready | Flooring & skirting | 2026-02-02 | 2026-03-18 | Flooring & skirting | 100 | 0 |  | 2026-01-15 |  | 2026-02-27
9829 | T-16-9th Floor Flat Area | Not Ready | Flooring & skirting | 2026-02-02 | 2026-03-18 | Flooring & skirting | 100 | 0 |  | 2026-01-15 |  | 2026-02-27
10900 | T-20-10th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-02-23 | 2026-05-18 | 1st Coat Painting | 100 | 0 |  | 2026-01-15 |  | 2026-04-08
10904 | T-20-11th Floor Common Area | Not Ready | Flooring & skirting | 2026-02-19 | 2026-03-13 | Flooring & skirting | 100 | 0 |  | 2026-01-15 |  | 2026-02-09
10919 | T-20-11th Floor Flat Area | Not Ready | Toilet flooring | 2026-02-16 | 2026-03-21 | Toilet flooring | 100 | 0 |  | 2026-01-15 |  | 2026-02-16
11833 | T-18-6th Floor Flat Area | Not Ready | Window | 2026-03-19 | 2026-04-10 | Window | 100 | 0 |  | 2026-01-15 |  | 2026-02-04
39242 |  | Not Ready |  | 2025-02-26 | 2025-04-09 | Disengaging / Handing Over / Taking Over | 100 | 0 |  | 2026-01-15 |  | 2026-02-25
39250 | Retail - Foundation | Not Ready | Raft RCC Works | 2025-07-18 | 2025-07-25 | RW toe foundation | 100 | 0 |  | 2026-01-15 |  | 2026-01-21 |  | Retail | Foundation | -- | RCC Sub Structure | Raft RCC Works
39250 | Retail - Foundation | Not Ready | Raft RCC Works | 2025-07-18 | 2025-07-25 | RW toe foundation | 100 | 0 |  | 2026-01-15 |  | 2026-01-21 |  | Retail | Foundation | -- | RCC Super Structure | Foundation RCC Works
39250 | Retail - Foundation | Not Ready | Raft RCC Works | 2025-07-18 | 2025-07-25 | RW toe foundation | 100 | 0 |  | 2026-01-15 |  | 2026-01-21 |  | Retail | Foundation | --
40111 | Tower A - Super Structure - Finishes & MEP - Sub Station | Not Ready | Sub Station - High Side Services | 2026-01-17 | 2026-01-29 | Transformer Shifting & Placing | 100 | 0 |  | 2026-01-15 |  | 2026-01-27 |  | Tower A | Super Structure
40120 |  | Not Committed |  | 2026-01-17 | 2026-06-27 | DG Sets (GF-P1-P2 in Zone 2) | 100 | 0 |  | 2026-01-15 |  | 2026-06-25
40121 | Tower A - Super Structure - Finishes & MEP - DG Sets | Not Ready |  | 2026-01-17 | 2026-03-12 | DG Foundation | 100 | 0 |  | 2026-01-15 |  | 2026-03-10 |  | Tower A | Super Structure
40531 | Tower A - Super Structure - Finishes & MEP - L57 to L58 | Not Ready | Gypsum Plastering Works | 2025-12-23 | 2026-01-09 | L57-58 | 100 | 0 |  | 2026-01-15 |  | 2026-02-02 |  | Tower A | Super Structure | L57 | Finishes | Gypsum Plastering Works
40531 | Tower A - Super Structure - Finishes & MEP - L57 to L58 | Not Ready | Gypsum Plastering Works | 2025-12-23 | 2026-01-09 | L57-58 | 100 | 0 |  | 2026-01-15 |  | 2026-02-02 |  | Tower A | Super Structure | L57
41180 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2025-12-26 | 2025-12-29 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-01-15 |  | 2026-01-19 |  | Tower A | Super Structure | L14 | MEP | FPS 2nd Fix - MEP & Finishes
41181 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2025-12-26 | 2025-12-31 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-01-15 |  | 2026-01-21 |  | Tower A | Super Structure | L14 | MEP | Electrical 2nd Fix - MEP & Finishes
41182 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-12-26 | 2026-01-02 | FAPA Device Fixing | 100 | 0 |  | 2026-01-15 |  | 2026-01-23 |  | Tower A | Super Structure | L14
41182 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-12-26 | 2026-01-02 | FAPA Device Fixing | 100 | 0 |  | 2026-01-15 |  | 2026-01-23 |  | Tower A | Super Structure | L14
41182 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-12-26 | 2026-01-02 | FAPA Device Fixing | 100 | 0 |  | 2026-01-15 |  | 2026-01-23 |  | Tower A | Super Structure | L14
41182 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2025-12-26 | 2026-01-02 | FAPA Device Fixing | 100 | 0 |  | 2026-01-15 |  | 2026-01-23 |  | Tower A | Super Structure | L14
41183 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2025-12-26 | 2025-12-29 | HVAC Grill Fixing | 100 | 0 |  | 2026-01-15 |  | 2026-01-19 |  | Tower A | Super Structure | L14 | MEP | HVAC Grill Fixing
43118 |  | Not Committed |  | 2025-12-23 | 2026-09-28 | L58-59 | 100 | 0 |  | 2026-01-15 |  | 2026-09-07
43118 |  | Not Committed |  | 2025-12-23 | 2026-09-28 | L58-59 | 100 | 0 |  | 2026-01-15 |  | 2026-09-07 |  |  |  |  | Finishes | Gypsum Plastering Works
43119 |  | Not Committed |  | 2025-12-23 | 2026-01-21 | MEP 1st Fixes | 100 | 0 |  | 2026-01-15 |  | 2026-02-13
43120 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2025-12-23 | 2025-12-31 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-01-15 |  | 2026-01-22 |  | Tower A | Super Structure | L58 | MEP | FPS 1st Fix - MEP & Finishes
43121 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-12-23 | 2025-12-29 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-01-15 |  | 2026-01-20 |  | Tower A | Super Structure | L58 | MEP | Electrical 1st Fixes
43122 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2025-12-23 | 2025-12-31 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-01-15 |  | 2026-01-22 |  | Tower A | Super Structure | L58
43123 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2025-12-23 | 2026-01-09 | Wet Area Waterproofing | 100 | 0 |  | 2026-01-15 |  | 2026-02-02 |  | Tower A | Super Structure | L58
43952 |  | Not Committed |  | 2026-02-16 | 2026-10-22 | Staircase Finishes | 100 | 0 |  | 2026-01-15 |  | 2026-09-01
43952 |  | Not Committed |  | 2026-02-16 | 2026-10-22 | Staircase Finishes | 100 | 0 |  | 2026-01-15 |  | 2026-09-01
43953 |  | Not Committed |  | 2026-02-16 | 2026-04-03 | GF-B3 | 100 | 0 |  | 2026-01-15 |  | 2026-03-05
43954 | Tower A - Super Structure - Finishes & MEP - B3 to GF | Not Ready | Staircase Finishes - MEP & Finishes | 2026-02-16 | 2026-03-05 | Staircase Wall & Ceiling finishes | 100 | 0 |  | 2026-01-15 |  | 2026-02-03 |  | Tower A | Super Structure | B3
43955 | Tower A - Super Structure - Finishes & MEP - B3 to GF | Not Ready | Staircase Finishes - MEP & Finishes | 2026-02-16 | 2026-03-23 | Staircase Flooring | 100 | 0 |  | 2026-01-15 |  | 2026-02-20 |  | Tower A | Super Structure | B3 | Finishes | Staircase Flooring
9701 | T-16-4th Floor Flat Area | Not Ready | Window | 2026-02-13 | 2026-03-07 | Window | 100 | 0 |  | 2026-01-16 |  | 2026-02-07
9885 | T-16-11th Floor Flat Area | Not Ready | Railing | 2026-01-29 | 2026-03-03 | Balcony Railing | 100 | 0 |  | 2026-01-16 |  | 2026-02-18
11316 | T-19-6th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-02-07 | 2026-05-02 | 1st Coat Painting | 100 | 0 |  | 2026-01-16 |  | 2026-04-10
40054 | Tower A - Super Structure - Finishes & MEP - L45 to L46 | Not Ready | CTU Elevators Crash Deck - High Side Services | 2025-06-10 | 2025-06-25 | Guide Rail Installation for CWT (up to L40) | 100 | 0 |  | 2026-01-16 |  | 2026-02-02 |  | Tower A | Super Structure | L45
40130 | Tower A - Super Structure - Finishes & MEP - MEP Service Floors | Not Ready |  | 2025-12-12 | 2026-05-05 | Lift Well Pressurization Fans Installations | 100 | 0 |  | 2026-01-16 |  | 2026-06-09 |  | Tower A | Super Structure
40824 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2024-08-02 | 2024-08-06 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-01-16 |  | 2026-01-20 |  | Tower A | Super Structure
41154 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2025-12-27 | 2026-01-01 | Final Painting | 100 | 0 |  | 2026-01-16 |  | 2026-01-22 |  | Tower A | Super Structure | L12 | Finishes | Final Painting
41154 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2025-12-27 | 2026-01-01 | Final Painting | 100 | 0 |  | 2026-01-16 |  | 2026-01-22 |  | Tower A | Super Structure | L12 | Finishes | Final Painting
41154 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2025-12-27 | 2026-01-01 | Final Painting | 100 | 0 |  | 2026-01-16 |  | 2026-01-22 |  | Tower A | Super Structure | L12 | Finishes | Final Painting
41169 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2025-12-27 | 2026-01-01 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-01-16 |  | 2026-01-22 |  | Tower A | Super Structure | L13 | MEP | Electrical
41497 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-06-10 | 2025-06-14 | Lobby Plastering | 100 | 0 |  | 2026-01-16 |  | 2026-01-21 |  | Tower A | Super Structure | L34 | Finishes | Lobby Plastering
41512 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-06-10 | 2025-06-12 | Lobby Blockwork | 100 | 0 |  | 2026-01-16 |  | 2026-01-19 |  | Tower A | Super Structure | L35 | Finishes | Blockwork
43088 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2025-12-24 | 2026-01-05 | Cement Plastering in wet areas | 100 | 0 |  | 2026-01-16 |  | 2026-01-28 |  | Tower A | Super Structure | L56
9775 | T-16-7th Floor Flat Area | Not Ready | Toilet flooring | 2026-02-06 | 2026-03-11 | Toilet flooring | 100 | 0 |  | 2026-01-17 |  | 2026-02-17
10225 | T-21-4th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-03-07 | 2026-05-14 | 2nd Coat Painting | 100 | 0 |  | 2026-01-17 |  | 2026-03-26
10329 | T-21-8th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-03-07 | 2026-05-14 | 2nd Coat Painting | 100 | 0 |  | 2026-01-17 |  | 2026-03-26
11955 | T-18-11th Floor Flat Area | Not Ready | Waterproofing | 2026-04-03 | 2026-05-07 | Waterproofing | 100 | 0 |  | 2026-01-17 |  | 2026-02-17
39783 | Tower A - Super Structure - Core Wall High Rise L79-80 | Not Ready | Core Wall RCC Works | 2025-12-19 | 2025-12-19 | Casting | 100 | 0 |  | 2026-01-17 |  | 2026-01-19 |  | Tower A | Super Structure | L79 | RCC Super Structure | Core Wall RCC Works
40028 |  | Not Ready |  | 2025-12-11 | 2025-12-18 | L75-76 | 100 | 0 |  | 2026-01-17 |  | 2026-01-30
40028 |  | Not Ready |  | 2025-12-11 | 2025-12-18 | L75-76 | 100 | 0 |  | 2026-01-17 |  | 2026-01-30 |  |  |  |  | Finishes | Gypsum Plastering Works
40029 | Tower A - Super Structure - Core & Outer Slab L75-76 | Not Ready | RCC Works - Vertical | 2025-12-11 | 2025-12-17 | Outer Columns_TA | 100 | 0 |  | 2026-01-17 |  | 2026-01-28 |  | Tower A | Super Structure | L75 | RCC Sub Structure | RCC Works - Vertical
40396 | Tower A - Super Structure - Finishes & MEP - L59 to L60 | Not Ready | Partition Wall-Blockwork | 2025-12-26 | 2025-12-31 | Staircase Area | 100 | 0 |  | 2026-01-17 |  | 2026-01-22 |  | Tower A | Super Structure | L59
40399 | Tower A - Super Structure - Finishes & MEP - L60 to L61 | Not Ready | Partition Wall-Blockwork | 2025-12-26 | 2026-01-02 | Partition Walls | 100 | 0 |  | 2026-01-17 |  | 2026-01-24 |  | Tower A | Super Structure | L60
40445 |  | Not Committed |  | 2025-12-11 | 2026-03-26 | L72-73 | 100 | 0 |  | 2026-01-17 |  | 2026-04-17
40445 |  | Not Committed |  | 2025-12-11 | 2026-03-26 | L72-73 | 100 | 0 |  | 2026-01-17 |  | 2026-04-17 |  |  |  |  | Finishes | Gypsum Plastering Works
40446 | Tower A - Super Structure - Finishes & MEP - L72 to L73 | Not Ready | Partition Wall-Blockwork | 2025-12-11 | 2025-12-29 | De-shuttering & Area clearance | 100 | 0 |  | 2026-01-17 |  | 2026-02-05 |  | Tower A | Super Structure | L72
40799 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2024-07-25 | 2024-07-30 | Final Painting | 100 | 0 |  | 2026-01-17 |  | 2026-01-23 |  | Tower A | Super Structure |  | Finishes | Final Painting
40799 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2024-07-25 | 2024-07-30 | Final Painting | 100 | 0 |  | 2026-01-17 |  | 2026-01-23 |  | Tower A | Super Structure |  | Finishes | Final Painting
40799 | Tower A - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2024-07-25 | 2024-07-30 | Final Painting | 100 | 0 |  | 2026-01-17 |  | 2026-01-23 |  | Tower A | Super Structure |  | Finishes | Final Painting
41239 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2025-12-29 | 2026-01-05 | HVAC Ducting | 100 | 0 |  | 2026-01-17 |  | 2026-01-27 |  | Tower A | Super Structure | L18 | MEP | HVAC Ducting
41689 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-12-18 | 2025-12-23 | Lobby Plastering | 100 | 0 |  | 2026-01-17 |  | 2026-01-23 |  | Tower A | Super Structure | L46 | Finishes | Lobby Plastering
41699 |  | Not Committed |  | 2025-12-18 | 2026-06-17 | L47-48 | 100 | 0 |  | 2026-01-17 |  | 2026-07-08
41699 |  | Not Committed |  | 2025-12-18 | 2026-06-17 | L47-48 | 100 | 0 |  | 2026-01-17 |  | 2026-07-08 |  |  |  |  | Finishes | Gypsum Plastering Works
41704 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-12-18 | 2025-12-20 | Lobby Blockwork | 100 | 0 |  | 2026-01-17 |  | 2026-01-21 |  | Tower A | Super Structure | L47 | Finishes | Blockwork
42822 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-02-18 | 2026-03-07 | Flooring & Dado works | 100 | 0 |  | 2026-01-17 |  | 2026-02-05 |  | Tower A | Super Structure | L41 | Finishes | Flooring & Dado
42912 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-02-18 | 2026-03-07 | Flooring & Dado works | 100 | 0 |  | 2026-01-17 |  | 2026-02-05 |  | Tower A | Super Structure | L46 | Finishes | Flooring & Dado
44097 |  | Not Ready |  | 2026-02-18 | 2026-03-31 | L48-53 | 100 | 0 |  | 2026-01-17 |  | 2026-02-28
44098 | Tower A - Super Structure - Finishes & MEP - L48 to L53 | Not Ready | Façade Works - MEP & Finishes | 2026-02-18 | 2026-03-07 | Al. Frame section (Mullion & Transom) Installation | 100 | 0 |  | 2026-01-17 |  | 2026-02-05 |  | Tower A | Super Structure | L48 | Façade | Façade Works
48184 | Retail - Super structure - R1 to CH00 - P1 | Not Ready |  | 2025-09-26 | 2025-10-14 | Slab_RT | 100 | 0 |  | 2026-01-17 |  | 2026-02-04 |  | Retail | Super Structure |  | RCC Sub Structure | RCC Works - Slab
48184 | Retail - Super structure - R1 to CH00 - P1 | Not Ready |  | 2025-09-26 | 2025-10-14 | Slab_RT | 100 | 0 |  | 2026-01-17 |  | 2026-02-04 |  | Retail | Super Structure
48191 | Retail - Super structure - R1 to CH00 - P3 | Not Ready |  | 2025-09-26 | 2025-10-14 | Slab_RT | 100 | 0 |  | 2026-01-17 |  | 2026-02-04 |  | Retail | Super Structure |  | RCC Sub Structure | RCC Works - Slab
48191 | Retail - Super structure - R1 to CH00 - P3 | Not Ready |  | 2025-09-26 | 2025-10-14 | Slab_RT | 100 | 0 |  | 2026-01-17 |  | 2026-02-04 |  | Retail | Super Structure
48200 |  | Not Committed |  | 2025-09-26 | 2025-11-13 | Pour RT-6 | 100 | 0 |  | 2026-01-17 |  | 2026-03-06
48201 | Retail - Super structure - R1 to CH00 - P6 | Not Ready |  | 2025-09-26 | 2025-10-27 | Columns_RT | 100 | 0 |  | 2026-01-17 |  | 2026-02-16 |  | Retail | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
48201 | Retail - Super structure - R1 to CH00 - P6 | Not Ready |  | 2025-09-26 | 2025-10-27 | Columns_RT | 100 | 0 |  | 2026-01-17 |  | 2026-02-16 |  | Retail | Super Structure
48202 | Retail - Super structure - R1 to CH00 - P6 | Not Ready |  | 2025-09-26 | 2025-10-21 | Staircase_RT | 100 | 0 |  | 2026-01-17 |  | 2026-02-10 |  | Retail | Super Structure |  | RCC Sub Structure | RCC Works - Slab
48202 | Retail - Super structure - R1 to CH00 - P6 | Not Ready |  | 2025-09-26 | 2025-10-21 | Staircase_RT | 100 | 0 |  | 2026-01-17 |  | 2026-02-10 |  | Retail | Super Structure
8783 | T-14-10th Floor Flat Area | Not Ready | Waterproofing | 2025-12-14 | 2026-01-16 | Waterproofing | 100 | 0 |  | 2026-01-18 |  | 2026-02-21
9237 | T-15-6th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-01-29 | 2026-04-06 | 2nd Coat Painting | 100 | 0 |  | 2026-01-18 |  | 2026-03-27
9333 | T-15-10th Floor Flat Area | Not Ready | Toilet flooring | 2026-01-23 | 2026-02-26 | Toilet flooring | 100 | 0 |  | 2026-01-18 |  | 2026-02-21
10308 | T-21-7th Floor Common Area | Not Ready | Door-Shaft | 2026-02-19 | 2026-03-04 | Door-Shaft | 100 | 0 |  | 2026-01-18 |  | 2026-01-31
10802 | T-20-6th Floor Common Area | Not Ready | Door-Shaft | 2026-02-14 | 2026-02-27 | Door-Shaft | 100 | 0 |  | 2026-01-18 |  | 2026-02-01
10898 | T-20-10th Floor Flat Area | Not Ready | Door | 2026-03-11 | 2026-04-03 | Door | 100 | 0 |  | 2026-01-18 |  | 2026-02-09
10922 | T-20-11th Floor Flat Area | Not Ready | Putty | 2026-02-19 | 2026-05-14 | Putty | 100 | 0 |  | 2026-01-18 |  | 2026-04-12
10923 | T-20-11th Floor Flat Area | Not Ready | Window | 2026-03-11 | 2026-04-03 | Window | 100 | 0 |  | 2026-01-18 |  | 2026-02-09
11934 | T-18-10th Floor Flat Area | Not Ready | Toilets False Celing | 2026-04-06 | 2026-05-10 | Toilets False Celing | 100 | 0 |  | 2026-01-18 |  | 2026-02-20
8806 | T-14-11th Floor Flat Area | Not Ready | Blockwork | 2025-12-12 | 2026-01-02 | Blockwork-Ledge Wall | 100 | 0 |  | 2026-01-19 |  | 2026-02-08
9730 | T-16-5th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-02-14 | 2026-05-09 | 1st Coat Painting | 100 | 0 |  | 2026-01-19 |  | 2026-04-13
9847 | T-16-10th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2026-02-02 | 2026-02-24 | Plumbing Pipe Line | 100 | 0 |  | 2026-01-19 |  | 2026-02-12
10199 | T-21-3rd Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-03-10 | 2026-05-16 | 2nd Coat Painting | 100 | 0 |  | 2026-01-19 |  | 2026-03-25
11362 | T-19-8th Floor Flat Area | Not Ready | Toilets False Celing | 2026-02-08 | 2026-03-13 | Toilets False Celing | 100 | 0 |  | 2026-01-19 |  | 2026-02-22
11388 | T-19-9th Floor Flat Area | Not Ready | Toilets False Celing | 2026-02-08 | 2026-03-13 | Toilets False Celing | 100 | 0 |  | 2026-01-19 |  | 2026-02-22
39784 | Tower A - Super Structure - Core Wall High Rise L79-80 | Not Ready | Core Wall RCC Works | 2025-12-20 | 2025-12-20 | ACS Form Release & jump to next level | 100 | 0 |  | 2026-01-19 |  | 2026-01-20 |  | Tower A | Super Structure | L79 | RCC Super Structure | Core Wall RCC Works
40031 |  | Not Ready |  | 2025-12-20 | 2026-02-27 | Above Terrace Structure | 100 | 0 |  | 2026-01-19 |  | 2026-03-30
40032 | Tower A - Super Structure - Core & Outer Slab Above Terrace | Not Ready | RCC Works - Slab | 2025-12-20 | 2026-01-24 | Lift Machine Room Top Slab (L80) | 100 | 0 |  | 2026-01-19 |  | 2026-02-18 |  | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Slab
40034 | Tower A - Super Structure - Core & Outer Slab Above Terrace | Not Ready | RCC Works - Slab | 2025-12-20 | 2026-01-13 | Mumty Slab | 100 | 0 |  | 2026-01-19 |  | 2026-02-18 |  | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Slab
41184 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2025-12-30 | 2026-01-01 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-01-19 |  | 2026-01-22 |  | Tower A | Super Structure | L14
41211 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2025-12-30 | 2026-01-06 | False Ceiling | 100 | 0 |  | 2026-01-19 |  | 2026-01-28 |  | Tower A | Super Structure | L16 | Finishes | False Ceiling
41226 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2025-12-30 | 2026-01-09 | Flooring & Dado | 100 | 0 |  | 2026-01-19 |  | 2026-01-31 |  | Tower A | Super Structure | L17 | Finishes | Flooring & Dado
43019 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2025-12-27 | 2026-01-03 | Door & Window Frame work | 100 | 0 |  | 2026-01-19 |  | 2026-01-27 |  | Tower A | Super Structure | L52 | Finishes | Door & Window Frame work
8714 | T-14-7th Floor Flat Area | Not Ready | Door | 2026-01-07 | 2026-01-31 | Door | 100 | 0 |  | 2026-01-20 |  | 2026-02-13
9288 | T-15-8th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-01-30 | 2026-04-23 | 1st Coat Painting | 100 | 0 |  | 2026-01-20 |  | 2026-04-13
9292 | T-15-8th Floor Common Area | Not Ready | Flooring & skirting | 2026-01-23 | 2026-02-14 | Flooring & skirting | 100 | 0 |  | 2026-01-20 |  | 2026-02-11
9314 | T-15-9th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-01-30 | 2026-04-23 | 1st Coat Painting | 100 | 0 |  | 2026-01-20 |  | 2026-04-13
9778 | T-16-7th Floor Flat Area | Not Ready | Putty | 2026-02-10 | 2026-05-05 | Putty | 100 | 0 |  | 2026-01-20 |  | 2026-04-14
11867 | T-18-7th Floor Common Area | Not Ready | Putty | 2026-04-03 | 2026-05-12 | Putty | 100 | 0 |  | 2026-01-20 |  | 2026-02-26
39700 | Tower A - Super Structure - Core Wall High Rise | Not Ready | Core Wall RCC Works | 2025-12-22 | 2026-01-08 | Core Wall Formwork Removal | 100 | 0 |  | 2026-01-20 |  | 2026-02-07 |  | Tower A | Super Structure |  | RCC Super Structure | Core Wall RCC Works
40825 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2024-08-09 | 2024-08-14 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-01-20 |  | 2026-01-27 |  | Tower A | Super Structure |  | MEP | Electrical
41513 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-06-13 | 2025-06-18 | Lobby Plastering | 100 | 0 |  | 2026-01-20 |  | 2026-01-24 |  | Tower A | Super Structure | L35 | Finishes | Lobby Plastering
41528 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-06-13 | 2025-06-16 | Lobby Blockwork | 100 | 0 |  | 2026-01-20 |  | 2026-01-22 |  | Tower A | Super Structure | L36 | Finishes | Blockwork
43071 |  | Not Committed |  | 2025-12-29 | 2026-04-29 | Finishes after 1st Fix | 100 | 0 |  | 2026-01-20 |  | 2026-03-31
43072 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2025-12-29 | 2026-01-20 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-01-20 |  | 2026-02-12 |  | Tower A | Super Structure | L55 | Finishes | Blockwork
8691 | T-14-6th Floor Flat Area | Not Ready | 2nd Coat Painting | 2025-12-29 | 2026-03-06 | 2nd Coat Painting | 100 | 0 |  | 2026-01-21 |  | 2026-03-30
8810 | T-14-11th Floor Flat Area | Not Ready | Electrical DB Fixing | 2025-12-14 | 2025-12-30 | Electrical DB Fixing | 100 | 0 |  | 2026-01-21 |  | 2026-02-06
9336 | T-15-10th Floor Flat Area | Not Ready | Putty | 2026-01-27 | 2026-04-20 | Putty | 100 | 0 |  | 2026-01-21 |  | 2026-04-15
9851 | T-16-10th Floor Flat Area | Not Ready | Plastering | 2026-02-04 | 2026-03-20 | Plastering-Gypsum | 100 | 0 |  | 2026-01-21 |  | 2026-03-05
10256 | T-21-5th Floor Common Area | Not Ready | Door-Shaft | 2026-02-25 | 2026-03-10 | Door-Shaft | 100 | 0 |  | 2026-01-21 |  | 2026-02-04
11288 | T-19-5th Floor Flat Area | Not Ready | Door | 2026-02-18 | 2026-03-12 | Door | 100 | 0 |  | 2026-01-21 |  | 2026-02-12
39251 | Retail - Foundation | Not Ready | Raft RCC Works | 2025-07-31 | 2025-08-13 | Raft & Footing Reinf_NTA | 100 | 0 |  | 2026-01-21 |  | 2026-02-03 |  | Retail | Foundation | -- | RCC Sub Structure | Raft RCC Works
39251 | Retail - Foundation | Not Ready | Raft RCC Works | 2025-07-31 | 2025-08-13 | Raft & Footing Reinf_NTA | 100 | 0 |  | 2026-01-21 |  | 2026-02-03 |  | Retail | Foundation | -- | RCC Super Structure | Foundation RCC Works
39251 | Retail - Foundation | Not Ready | Raft RCC Works | 2025-07-31 | 2025-08-13 | Raft & Footing Reinf_NTA | 100 | 0 |  | 2026-01-21 |  | 2026-02-03 |  | Retail | Foundation | --
40030 | Tower A - Super Structure - Core & Outer Slab L75-76 | Not Ready | RCC Works - Slab | 2025-12-13 | 2025-12-18 | Outer Slab_TA | 100 | 0 |  | 2026-01-21 |  | 2026-01-30 |  | Tower A | Super Structure | L75 | RCC Sub Structure | RCC Works - Slab
40837 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2024-10-11 | 2024-10-21 | Final Painting | 100 | 0 |  | 2026-01-21 |  | 2026-01-31 |  | Tower A | Super Structure |  | Finishes | Final Painting
40837 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2024-10-11 | 2024-10-21 | Final Painting | 100 | 0 |  | 2026-01-21 |  | 2026-01-31 |  | Tower A | Super Structure |  | Finishes | Final Painting
40837 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2024-10-11 | 2024-10-21 | Final Painting | 100 | 0 |  | 2026-01-21 |  | 2026-01-31 |  | Tower A | Super Structure |  | Finishes | Final Painting
40847 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2024-08-10 | 2024-08-13 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-01-21 |  | 2026-01-24 |  | Tower A | Super Structure |  | MEP | FPS 2nd Fix - MEP & Finishes
40848 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2024-08-10 | 2024-08-16 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-01-21 |  | 2026-01-28 |  | Tower A | Super Structure |  | MEP | Electrical 2nd Fix - MEP & Finishes
40849 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-08-10 | 2024-08-20 | FAPA Device Fixing | 100 | 0 |  | 2026-01-21 |  | 2026-01-30 |  | Tower A | Super Structure
40849 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-08-10 | 2024-08-20 | FAPA Device Fixing | 100 | 0 |  | 2026-01-21 |  | 2026-01-30 |  | Tower A | Super Structure
40849 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-08-10 | 2024-08-20 | FAPA Device Fixing | 100 | 0 |  | 2026-01-21 |  | 2026-01-30 |  | Tower A | Super Structure
40849 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2024-08-10 | 2024-08-20 | FAPA Device Fixing | 100 | 0 |  | 2026-01-21 |  | 2026-01-30 |  | Tower A | Super Structure
40850 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2024-08-10 | 2024-08-13 | HVAC Grill Fixing | 100 | 0 |  | 2026-01-21 |  | 2026-01-24 |  | Tower A | Super Structure |  | MEP | HVAC Grill Fixing
41196 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-01-01 | 2026-01-03 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-01-21 |  | 2026-01-24 |  | Tower A | Super Structure | L15 | MEP | FPS 2nd Fix - MEP & Finishes
41197 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-01-01 | 2026-01-06 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-01-21 |  | 2026-01-28 |  | Tower A | Super Structure | L15 | MEP | Electrical 2nd Fix - MEP & Finishes
41198 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-01-01 | 2026-01-08 | FAPA Device Fixing | 100 | 0 |  | 2026-01-21 |  | 2026-01-30 |  | Tower A | Super Structure | L15
41198 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-01-01 | 2026-01-08 | FAPA Device Fixing | 100 | 0 |  | 2026-01-21 |  | 2026-01-30 |  | Tower A | Super Structure | L15
41198 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-01-01 | 2026-01-08 | FAPA Device Fixing | 100 | 0 |  | 2026-01-21 |  | 2026-01-30 |  | Tower A | Super Structure | L15
41198 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-01-01 | 2026-01-08 | FAPA Device Fixing | 100 | 0 |  | 2026-01-21 |  | 2026-01-30 |  | Tower A | Super Structure | L15
41199 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-01-01 | 2026-01-03 | HVAC Grill Fixing | 100 | 0 |  | 2026-01-21 |  | 2026-01-24 |  | Tower A | Super Structure | L15 | MEP | HVAC Grill Fixing
41705 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-12-22 | 2025-12-27 | Lobby Plastering | 100 | 0 |  | 2026-01-21 |  | 2026-01-28 |  | Tower A | Super Structure | L47 | Finishes | Lobby Plastering
41715 |  | Not Committed |  | 2025-12-22 | 2026-06-23 | L48-49 | 100 | 0 |  | 2026-01-21 |  | 2026-07-15
41715 |  | Not Committed |  | 2025-12-22 | 2026-06-23 | L48-49 | 100 | 0 |  | 2026-01-21 |  | 2026-07-15 |  |  |  |  | Finishes | Gypsum Plastering Works
41720 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-12-22 | 2025-12-24 | Lobby Blockwork | 100 | 0 |  | 2026-01-21 |  | 2026-01-24 |  | Tower A | Super Structure | L48 | Finishes | Blockwork
43956 | Tower A - Super Structure - Finishes & MEP - B3 to GF | Not Ready | Staircase Finishes - MEP & Finishes | 2026-02-21 | 2026-03-23 | Staircase Window | 100 | 0 |  | 2026-01-21 |  | 2026-02-20 |  | Tower A | Super Structure | B3
43960 |  | Not Committed |  | 2026-02-21 | 2026-06-15 | GF-L7 | 100 | 0 |  | 2026-01-21 |  | 2026-05-15
43961 | Tower A - Super Structure - Finishes & MEP - GF to L7 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-02-21 | 2026-03-28 | Staircase Wall & Ceiling finishes | 100 | 0 |  | 2026-01-21 |  | 2026-02-26 |  | Tower A | Super Structure | GF
45280 |  | Not Ready |  | 2025-11-17 | 2025-12-01 | L10-11 | 100 | 0 |  | 2026-01-21 |  | 2026-02-06
45280 |  | Not Ready |  | 2025-11-17 | 2025-12-01 | L10-11 | 100 | 0 |  | 2026-01-21 |  | 2026-02-06 |  |  |  |  | Finishes | Gypsum Plastering Works
45281 | Tower B - Super Structure - Core & Outer Slab L10-11 | Not Ready | RCC Works - Vertical | 2025-11-17 | 2025-11-27 | Outer Columns_TA | 100 | 0 |  | 2026-01-21 |  | 2026-02-03 |  | Tower B | Super Structure | L10 | RCC Sub Structure | RCC Works - Vertical
45433 |  | Not Committed |  | 2025-11-17 | 2025-12-17 | L7-8 | 100 | 0 |  | 2026-01-21 |  | 2026-02-23
45433 |  | Not Committed |  | 2025-11-17 | 2025-12-17 | L7-8 | 100 | 0 |  | 2026-01-21 |  | 2026-02-23 |  |  |  |  | Finishes | Gypsum Plastering Works
45434 | Tower B - Super Structure - Finishes & MEP - L7 to L8 | Not Ready | Partition Wall-Blockwork | 2025-11-17 | 2025-12-03 | De-shuttering & Area clearance | 100 | 0 |  | 2026-01-21 |  | 2026-02-09 |  | Tower B | Super Structure | L7
8739 | T-14-8th Floor Flat Area | Not Ready | Window | 2026-01-09 | 2026-02-02 | Window | 100 | 0 |  | 2026-01-22 |  | 2026-02-13
9355 | T-15-11th Floor Flat Area | Not Ready | Waterproofing | 2026-01-29 | 2026-03-03 | Waterproofing | 100 | 0 |  | 2026-01-22 |  | 2026-02-25
10326 | T-21-8th Floor Flat Area | Not Ready | Door | 2026-02-04 | 2026-02-25 | Door | 100 | 0 |  | 2026-01-22 |  | 2026-02-16
11961 | T-18-11th Floor Flat Area | Not Ready | Flooring & skirting | 2026-04-08 | 2026-05-23 | Flooring & skirting | 100 | 0 |  | 2026-01-22 |  | 2026-03-07
41170 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-01-02 | 2026-01-07 | Final Painting | 100 | 0 |  | 2026-01-22 |  | 2026-01-29 |  | Tower A | Super Structure | L13 | Finishes | Final Painting
41170 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-01-02 | 2026-01-07 | Final Painting | 100 | 0 |  | 2026-01-22 |  | 2026-01-29 |  | Tower A | Super Structure | L13 | Finishes | Final Painting
41170 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-01-02 | 2026-01-07 | Final Painting | 100 | 0 |  | 2026-01-22 |  | 2026-01-29 |  | Tower A | Super Structure | L13 | Finishes | Final Painting
41185 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-01-02 | 2026-01-07 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-01-22 |  | 2026-01-29 |  | Tower A | Super Structure | L14 | MEP | Electrical
8789 | T-14-10th Floor Flat Area | Not Ready | Flooring & skirting | 2025-12-19 | 2026-02-03 | Flooring & skirting | 100 | 0 |  | 2026-01-23 |  | 2026-03-10
9260 | T-15-7th Floor Flat Area | Not Ready | Door | 2026-02-09 | 2026-03-02 | Door | 100 | 0 |  | 2026-01-23 |  | 2026-02-16
10284 | T-21-6th Floor Common Area | Forced Ready | 1st Coat Painting | 2026-02-24 | 2026-03-17 | 1st Coat Painting | 100 | 0 |  | 2026-01-23 |  | 2026-02-17
10879 | T-20-9th Floor Common Area | Not Ready | Putty | 2026-02-25 | 2026-04-05 | Putty | 100 | 0 |  | 2026-01-23 |  | 2026-03-02
10920 | T-20-11th Floor Flat Area | Not Ready | Toilets False Celing | 2026-02-25 | 2026-03-31 | Toilets False Celing | 100 | 0 |  | 2026-01-23 |  | 2026-02-26
11313 | T-19-6th Floor Flat Area | Not Ready | Window | 2026-02-20 | 2026-03-14 | Window | 100 | 0 |  | 2026-01-23 |  | 2026-02-14
11409 | T-19-10th Floor Flat Area | Not Ready | Waterproofing | 2026-02-05 | 2026-03-10 | Waterproofing | 100 | 0 |  | 2026-01-23 |  | 2026-02-26
40532 | Tower A - Super Structure - Finishes & MEP - L58 to L59 | Not Ready | Gypsum Plastering Works | 2026-01-01 | 2026-01-17 | L58-59 | 100 | 0 |  | 2026-01-23 |  | 2026-02-10 |  | Tower A | Super Structure | L58 | Finishes | Gypsum Plastering Works
40532 | Tower A - Super Structure - Finishes & MEP - L58 to L59 | Not Ready | Gypsum Plastering Works | 2026-01-01 | 2026-01-17 | L58-59 | 100 | 0 |  | 2026-01-23 |  | 2026-02-10 |  | Tower A | Super Structure | L58
41529 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-06-17 | 2025-06-21 | Lobby Plastering | 100 | 0 |  | 2026-01-23 |  | 2026-01-29 |  | Tower A | Super Structure | L36 | Finishes | Lobby Plastering
41544 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-06-17 | 2025-06-19 | Lobby Blockwork | 100 | 0 |  | 2026-01-23 |  | 2026-01-27 |  | Tower A | Super Structure | L37 | Finishes | Blockwork
42840 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-02-24 | 2026-03-13 | Flooring & Dado works | 100 | 0 |  | 2026-01-23 |  | 2026-02-11 |  | Tower A | Super Structure | L42 | Finishes | Flooring & Dado
42930 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-02-24 | 2026-03-13 | Flooring & Dado works | 100 | 0 |  | 2026-01-23 |  | 2026-02-11 |  | Tower A | Super Structure | L47 | Finishes | Flooring & Dado
43136 |  | Not Committed |  | 2026-01-01 | 2026-09-28 | L59-60 | 100 | 0 |  | 2026-01-23 |  | 2026-09-07
43136 |  | Not Committed |  | 2026-01-01 | 2026-09-28 | L59-60 | 100 | 0 |  | 2026-01-23 |  | 2026-09-07 |  |  |  |  | Finishes | Gypsum Plastering Works
43137 |  | Not Committed |  | 2026-01-01 | 2026-01-30 | MEP 1st Fixes | 100 | 0 |  | 2026-01-23 |  | 2026-02-21
43138 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-01-01 | 2026-01-08 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-01-23 |  | 2026-01-31 |  | Tower A | Super Structure | L59 | MEP | FPS 1st Fix - MEP & Finishes
43139 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-01-01 | 2026-01-06 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-01-23 |  | 2026-01-29 |  | Tower A | Super Structure | L59 | MEP | Electrical 1st Fixes
43140 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-01-01 | 2026-01-08 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-01-23 |  | 2026-01-31 |  | Tower A | Super Structure | L59
43141 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-01-01 | 2026-01-17 | Wet Area Waterproofing | 100 | 0 |  | 2026-01-23 |  | 2026-02-10 |  | Tower A | Super Structure | L59
44096 | Tower A - Super Structure - Finishes & MEP - L43 to L48 | Not Ready | Façade Works - MEP & Finishes | 2026-02-24 | 2026-03-07 | Accessories & Alignment | 100 | 0 |  | 2026-01-23 |  | 2026-02-05 |  | Tower A | Super Structure | L43 | Façade | Façade Works
44096 | Tower A - Super Structure - Finishes & MEP - L43 to L48 | Not Ready | Façade Works - MEP & Finishes | 2026-02-24 | 2026-03-07 | Accessories & Alignment | 100 | 0 |  | 2026-01-23 |  | 2026-02-05 |  | Tower A | Super Structure | L43
44248 | Tower A | Not Ready | High Side Procurement | 2026-01-12 | 2026-05-18 | FPS Pumps | 100 | 0 |  | 2026-01-23 |  | 2026-05-29 |  | Tower A | --
44249 | Tower A | Not Ready | High Side Procurement | 2026-01-12 | 2026-05-18 | PHE Pumps | 100 | 0 |  | 2026-01-23 |  | 2026-05-29 |  | Tower A | --
45431 | Tower B - Super Structure - Finishes & MEP - P6 to L7 | Not Ready | Partition Wall-Blockwork | 2025-11-19 | 2025-11-26 | Partition Walls | 100 | 0 |  | 2026-01-23 |  | 2026-02-02 |  | Tower B | Super Structure
8746 | T-14-8th Floor Common Area | Not Ready | Flooring & skirting | 2025-12-24 | 2026-01-14 | Flooring & skirting | 100 | 0 |  | 2026-01-24 |  | 2026-02-15
8845 | T-14-12th Floor Flat Area | Not Ready | Railing | 2025-12-18 | 2026-01-21 | Balcony Railing | 100 | 0 |  | 2026-01-24 |  | 2026-02-25
10351 | T-21-9th Floor Flat Area | Not Ready | Window | 2026-02-06 | 2026-02-27 | Window | 100 | 0 |  | 2026-01-24 |  | 2026-02-16
10722 | T-20-3rd Floor Common Area | Not Ready | Flooring & skirting | 2026-02-19 | 2026-03-13 | Flooring & skirting | 100 | 0 |  | 2026-01-24 |  | 2026-02-16
10749 | T-20-4th Floor Common Area | Not Ready | Putty | 2026-02-19 | 2026-03-31 | Putty | 100 | 0 |  | 2026-01-24 |  | 2026-03-05
11432 | T-19-11th Floor Flat Area | Not Ready | Blockwork | 2026-02-03 | 2026-02-24 | Blockwork-Ledge Wall | 100 | 0 |  | 2026-01-24 |  | 2026-02-13
40851 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2024-08-14 | 2024-08-17 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-01-24 |  | 2026-01-29 |  | Tower A | Super Structure
41200 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-01-05 | 2026-01-07 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-01-24 |  | 2026-01-29 |  | Tower A | Super Structure | L15
41227 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-01-05 | 2026-01-12 | False Ceiling | 100 | 0 |  | 2026-01-24 |  | 2026-02-03 |  | Tower A | Super Structure | L17 | Finishes | False Ceiling
41255 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-01-05 | 2026-01-12 | HVAC Ducting | 100 | 0 |  | 2026-01-24 |  | 2026-02-03 |  | Tower A | Super Structure | L19 | MEP | HVAC Ducting
41721 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-12-26 | 2025-12-31 | Lobby Plastering | 100 | 0 |  | 2026-01-24 |  | 2026-01-31 |  | Tower A | Super Structure | L48 | Finishes | Lobby Plastering
41731 |  | Not Committed |  | 2025-12-26 | 2026-06-29 | L49-50 | 100 | 0 |  | 2026-01-24 |  | 2026-07-22
41731 |  | Not Committed |  | 2025-12-26 | 2026-06-29 | L49-50 | 100 | 0 |  | 2026-01-24 |  | 2026-07-22 |  |  |  |  | Finishes | Gypsum Plastering Works
41736 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-12-26 | 2025-12-29 | Lobby Blockwork | 100 | 0 |  | 2026-01-24 |  | 2026-01-29 |  | Tower A | Super Structure | L49 | Finishes | Blockwork
43106 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-01-02 | 2026-01-13 | Cement Plastering in wet areas | 100 | 0 |  | 2026-01-24 |  | 2026-02-05 |  | Tower A | Super Structure | L57
9285 | T-15-8th Floor Flat Area | Not Ready | Window | 2026-02-11 | 2026-03-04 | Window | 100 | 0 |  | 2026-01-25 |  | 2026-02-16
9702 | T-16-4th Floor Flat Area | Not Ready | Door | 2026-02-23 | 2026-03-17 | Door | 100 | 0 |  | 2026-01-25 |  | 2026-02-16
9776 | T-16-7th Floor Flat Area | Not Ready | Toilets False Celing | 2026-02-16 | 2026-03-20 | Toilets False Celing | 100 | 0 |  | 2026-01-25 |  | 2026-02-28
9800 | T-16-8th Floor Flat Area | Not Ready | Dado | 2026-02-13 | 2026-03-12 | Dado | 100 | 0 |  | 2026-01-25 |  | 2026-02-21
9826 | T-16-9th Floor Flat Area | Not Ready | Dado | 2026-02-13 | 2026-03-12 | Dado | 100 | 0 |  | 2026-01-25 |  | 2026-02-21
11834 | T-18-6th Floor Flat Area | Not Ready | Door | 2026-03-31 | 2026-04-22 | Door | 100 | 0 |  | 2026-01-25 |  | 2026-02-16
8742 | T-14-8th Floor Flat Area | Not Ready | 1st Coat Painting | 2025-12-30 | 2026-03-24 | 1st Coat Painting | 100 | 0 |  | 2026-01-26 |  | 2026-04-21
8807 | T-14-11th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2025-12-19 | 2026-01-10 | Plumbing Pipe Line | 100 | 0 |  | 2026-01-26 |  | 2026-02-15
9334 | T-15-10th Floor Flat Area | Not Ready | Toilets False Celing | 2026-02-02 | 2026-03-06 | Toilets False Celing | 100 | 0 |  | 2026-01-26 |  | 2026-02-28
9848 | T-16-10th Floor Flat Area | Not Ready | Plastering | 2026-02-10 | 2026-03-04 | Plastering-Cement | 100 | 0 |  | 2026-01-26 |  | 2026-02-16
10385 | T-21-11th Floor Common Area | Not Ready | Putty | 2026-03-02 | 2026-04-10 | Putty | 100 | 0 |  | 2026-01-26 |  | 2026-03-03
11346 | T-19-7th Floor Common Area | Not Ready | Flooring & skirting | 2026-02-12 | 2026-03-06 | Flooring & skirting | 100 | 0 |  | 2026-01-26 |  | 2026-02-17
11436 | T-19-11th Floor Flat Area | Not Ready | Electrical DB Fixing | 2026-02-05 | 2026-02-21 | Electrical DB Fixing | 100 | 0 |  | 2026-01-26 |  | 2026-02-13
9361 | T-15-11th Floor Flat Area | Not Ready | Flooring & skirting | 2026-02-04 | 2026-03-19 | Flooring & skirting | 100 | 0 |  | 2026-01-27 |  | 2026-03-10
11859 | T-18-7th Floor Flat Area | Not Ready | Window | 2026-04-02 | 2026-04-24 | Window | 100 | 0 |  | 2026-01-27 |  | 2026-02-17
11918 | T-18-9th Floor Common Area | Not Ready | Flooring & skirting | 2026-04-14 | 2026-05-07 | Flooring & skirting | 100 | 0 |  | 2026-01-27 |  | 2026-02-18
40400 | Tower A - Super Structure - Finishes & MEP - L60 to L61 | Not Ready | Partition Wall-Blockwork | 2026-01-03 | 2026-01-08 | Staircase Area | 100 | 0 |  | 2026-01-27 |  | 2026-01-31 |  | Tower A | Super Structure | L60
40403 | Tower A - Super Structure - Finishes & MEP - L61 to L62 | Not Ready | Partition Wall-Blockwork | 2026-01-03 | 2026-01-10 | Partition Walls | 100 | 0 |  | 2026-01-27 |  | 2026-02-03 |  | Tower A | Super Structure | L61
40826 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2024-08-16 | 2024-08-22 | Final Painting | 100 | 0 |  | 2026-01-27 |  | 2026-02-02 |  | Tower A | Super Structure |  | Finishes | Final Painting
40826 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2024-08-16 | 2024-08-22 | Final Painting | 100 | 0 |  | 2026-01-27 |  | 2026-02-02 |  | Tower A | Super Structure |  | Finishes | Final Painting
40826 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2024-08-16 | 2024-08-22 | Final Painting | 100 | 0 |  | 2026-01-27 |  | 2026-02-02 |  | Tower A | Super Structure |  | Finishes | Final Painting
41242 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-01-06 | 2026-01-16 | Flooring & Dado | 100 | 0 |  | 2026-01-27 |  | 2026-02-07 |  | Tower A | Super Structure | L18 | Finishes | Flooring & Dado
8811 | T-14-11th Floor Flat Area | Not Ready | Plastering | 2025-12-22 | 2026-02-05 | Plastering-Gypsum | 100 | 0 |  | 2026-01-28 |  | 2026-03-16
9863 | T-16-11th Floor Common Area | Not Ready | Plastering | 2026-02-12 | 2026-03-17 | Plastering-Gypsum | 100 | 0 |  | 2026-01-28 |  | 2026-03-03
10924 | T-20-11th Floor Flat Area | Not Ready | Door | 2026-03-22 | 2026-04-14 | Door | 100 | 0 |  | 2026-01-28 |  | 2026-02-18
11415 | T-19-10th Floor Flat Area | Not Ready | Flooring & skirting | 2026-02-10 | 2026-03-27 | Flooring & skirting | 100 | 0 |  | 2026-01-28 |  | 2026-03-13
40112 | Tower A - Super Structure - Finishes & MEP - Sub Station | Not Ready | Sub Station - High Side Services | 2026-01-30 | 2026-02-27 | Panel Installation | 100 | 0 |  | 2026-01-28 |  | 2026-02-25 |  | Tower A | Super Structure
40112 | Tower A - Super Structure - Finishes & MEP - Sub Station | Not Ready | Sub Station - High Side Services | 2026-01-30 | 2026-02-27 | Panel Installation | 100 | 0 |  | 2026-01-28 |  | 2026-02-25 |  | Tower A | Super Structure
41212 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-01-07 | 2026-01-09 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-01-28 |  | 2026-01-31 |  | Tower A | Super Structure | L16 | MEP | FPS 2nd Fix - MEP & Finishes
41213 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-01-07 | 2026-01-12 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-01-28 |  | 2026-02-03 |  | Tower A | Super Structure | L16 | MEP | Electrical 2nd Fix - MEP & Finishes
41214 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-01-07 | 2026-01-14 | FAPA Device Fixing | 100 | 0 |  | 2026-01-28 |  | 2026-02-05 |  | Tower A | Super Structure | L16
41214 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-01-07 | 2026-01-14 | FAPA Device Fixing | 100 | 0 |  | 2026-01-28 |  | 2026-02-05 |  | Tower A | Super Structure | L16
41214 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-01-07 | 2026-01-14 | FAPA Device Fixing | 100 | 0 |  | 2026-01-28 |  | 2026-02-05 |  | Tower A | Super Structure | L16
41214 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-01-07 | 2026-01-14 | FAPA Device Fixing | 100 | 0 |  | 2026-01-28 |  | 2026-02-05 |  | Tower A | Super Structure | L16
41215 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-01-07 | 2026-01-09 | HVAC Grill Fixing | 100 | 0 |  | 2026-01-28 |  | 2026-01-31 |  | Tower A | Super Structure | L16 | MEP | HVAC Grill Fixing
41545 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-06-20 | 2025-06-25 | Lobby Plastering | 100 | 0 |  | 2026-01-28 |  | 2026-02-02 |  | Tower A | Super Structure | L37 | Finishes | Lobby Plastering
41560 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-06-20 | 2025-06-23 | Lobby Blockwork | 100 | 0 |  | 2026-01-28 |  | 2026-01-30 |  | Tower A | Super Structure | L38 | Finishes | Blockwork
43037 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-01-05 | 2026-01-12 | Door & Window Frame work | 100 | 0 |  | 2026-01-28 |  | 2026-02-04 |  | Tower A | Super Structure | L53 | Finishes | Door & Window Frame work
44559 | NTA_Zone 2 - Sub Structure - B1 to GF | Not Ready | Finishes (Lobby & Floor Area) | 2025-01-29 | 2025-03-04 | Staircase Finishes | 100 | 0 |  | 2026-01-28 |  | 2026-03-04 |  | NTA_Zone 2 | Sub Structure | B1
44559 | NTA_Zone 2 - Sub Structure - B1 to GF | Not Ready | Finishes (Lobby & Floor Area) | 2025-01-29 | 2025-03-04 | Staircase Finishes | 100 | 0 |  | 2026-01-28 |  | 2026-03-04 |  | NTA_Zone 2 | Sub Structure | B1
9267 | T-15-7th Floor Common Area | Not Ready | Putty | 2026-01-29 | 2026-03-09 | Putty | 100 | 0 |  | 2026-01-29 |  | 2026-03-08
9727 | T-16-5th Floor Flat Area | Not Ready | Window | 2026-02-27 | 2026-03-21 | Window | 100 | 0 |  | 2026-01-29 |  | 2026-02-21
10176 | T-21-2nd Floor Common Area | Not Ready | Flooring & skirting | 2026-03-02 | 2026-03-24 | Flooring & skirting | 100 | 0 |  | 2026-01-29 |  | 2026-02-19
10203 | T-21-3rd Floor Common Area | Not Ready | Putty | 2026-03-02 | 2026-04-10 | Putty | 100 | 0 |  | 2026-01-29 |  | 2026-03-06
11788 | T-18-4th Floor Common Area | Not Ready | Flooring & skirting | 2026-04-08 | 2026-04-30 | Flooring & skirting | 100 | 0 |  | 2026-01-29 |  | 2026-02-19
11815 | T-18-5th Floor Common Area | Not Ready | Putty | 2026-04-08 | 2026-05-18 | Putty | 100 | 0 |  | 2026-01-29 |  | 2026-03-09
40075 | Tower A - Super Structure - Finishes & MEP - L70 to L71 | Not Ready | CTU Elevators Crash Deck - High Side Services | 2025-12-30 | 2026-01-09 | Guide Rail Installation by rising platform (only car guide rails) | 100 | 0 |  | 2026-01-29 |  | 2026-02-10 |  | Tower A | Super Structure | L70
40075 | Tower A - Super Structure - Finishes & MEP - L70 to L71 | Not Ready | CTU Elevators Crash Deck - High Side Services | 2025-12-30 | 2026-01-09 | Guide Rail Installation by rising platform (only car guide rails) | 100 | 0 |  | 2026-01-29 |  | 2026-02-10 |  | Tower A | Super Structure | L70
40075 | Tower A - Super Structure - Finishes & MEP - L70 to L71 | Not Ready | CTU Elevators Crash Deck - High Side Services | 2025-12-30 | 2026-01-09 | Guide Rail Installation by rising platform (only car guide rails) | 100 | 0 |  | 2026-01-29 |  | 2026-02-10 |  | Tower A | Super Structure | L70
40852 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2024-08-22 | 2024-08-28 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-01-29 |  | 2026-02-04 |  | Tower A | Super Structure |  | MEP | Electrical
41186 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-01-08 | 2026-01-13 | Final Painting | 100 | 0 |  | 2026-01-29 |  | 2026-02-04 |  | Tower A | Super Structure | L14 | Finishes | Final Painting
41186 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-01-08 | 2026-01-13 | Final Painting | 100 | 0 |  | 2026-01-29 |  | 2026-02-04 |  | Tower A | Super Structure | L14 | Finishes | Final Painting
41186 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-01-08 | 2026-01-13 | Final Painting | 100 | 0 |  | 2026-01-29 |  | 2026-02-04 |  | Tower A | Super Structure | L14 | Finishes | Final Painting
41201 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-01-08 | 2026-01-13 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-01-29 |  | 2026-02-04 |  | Tower A | Super Structure | L15 | MEP | Electrical
41737 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-12-30 | 2026-01-03 | Lobby Plastering | 100 | 0 |  | 2026-01-29 |  | 2026-02-04 |  | Tower A | Super Structure | L49 | Finishes | Lobby Plastering
41747 |  | Not Committed |  | 2025-12-30 | 2026-06-29 | L50-51 | 100 | 0 |  | 2026-01-29 |  | 2026-07-22
41747 |  | Not Committed |  | 2025-12-30 | 2026-06-29 | L50-51 | 100 | 0 |  | 2026-01-29 |  | 2026-07-22 |  |  |  |  | Finishes | Gypsum Plastering Works
41752 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-12-30 | 2026-01-01 | Lobby Blockwork | 100 | 0 |  | 2026-01-29 |  | 2026-02-02 |  | Tower A | Super Structure | L50 | Finishes | Blockwork
43089 |  | Not Committed |  | 2026-01-06 | 2026-05-06 | Finishes after 1st Fix | 100 | 0 |  | 2026-01-29 |  | 2026-04-06
43090 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-01-06 | 2026-01-29 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-01-29 |  | 2026-02-20 |  | Tower A | Super Structure | L56 | Finishes | Blockwork
44533 | NTA_Zone 2 - Super Structure - P3 to P4 | Not Ready | MEP 1st Fix Works | 2025-04-10 | 2025-06-02 | P3 to P4 | 100 | 0 |  | 2026-01-29 |  | 2026-02-14 |  | NTA_Zone 2 | Super Structure
44533 | NTA_Zone 2 - Super Structure - P3 to P4 | Not Ready | MEP 1st Fix Works | 2025-04-10 | 2025-06-02 | P3 to P4 | 100 | 0 |  | 2026-01-29 |  | 2026-02-14 |  | NTA_Zone 2 | Super Structure
44533 | NTA_Zone 2 - Super Structure - P3 to P4 | Not Ready | MEP 1st Fix Works | 2025-04-10 | 2025-06-02 | P3 to P4 | 100 | 0 |  | 2026-01-29 |  | 2026-02-14 |  | NTA_Zone 2 | Super Structure
44543 | NTA_Zone 2 - Super Structure - P4 to P5 | Not Ready | Partition Wall-Blockwork | 2024-10-07 | 2024-11-12 | P4 to P5 | 100 | 0 |  | 2026-01-29 |  | 2026-03-05 |  | NTA_Zone 2 | Super Structure
44543 | NTA_Zone 2 - Super Structure - P4 to P5 | Not Ready | Partition Wall-Blockwork | 2024-10-07 | 2024-11-12 | P4 to P5 | 100 | 0 |  | 2026-01-29 |  | 2026-03-05 |  | NTA_Zone 2 | Super Structure
44543 | NTA_Zone 2 - Super Structure - P4 to P5 | Not Ready | Partition Wall-Blockwork | 2024-10-07 | 2024-11-12 | P4 to P5 | 100 | 0 |  | 2026-01-29 |  | 2026-03-05 |  | NTA_Zone 2 | Super Structure
44568 | NTA_Zone 2 - Super Structure - P1 to P2 | Not Ready | Finishes (Lobby & Floor Area) | 2025-03-24 | 2025-04-26 | Staircase Finishes | 100 | 0 |  | 2026-01-29 |  | 2026-03-05 |  | NTA_Zone 2 | Super Structure
44568 | NTA_Zone 2 - Super Structure - P1 to P2 | Not Ready | Finishes (Lobby & Floor Area) | 2025-03-24 | 2025-04-26 | Staircase Finishes | 100 | 0 |  | 2026-01-29 |  | 2026-03-05 |  | NTA_Zone 2 | Super Structure
45282 | Tower B - Super Structure - Core & Outer Slab L10-11 | Not Ready | RCC Works - Slab | 2025-11-24 | 2025-12-01 | Outer Slab_TA | 100 | 0 |  | 2026-01-29 |  | 2026-02-06 |  | Tower B | Super Structure | L10 | RCC Sub Structure | RCC Works - Slab
9760 | T-16-6th Floor Common Area | Not Ready | Flooring & skirting | 2026-02-18 | 2026-03-11 | Flooring & skirting | 100 | 0 |  | 2026-01-30 |  | 2026-02-20
10930 | T-20-11th Floor Common Area | Not Ready | Flooring & skirting | 2026-03-08 | 2026-03-31 | Flooring & skirting | 100 | 0 |  | 2026-01-30 |  | 2026-02-20
11342 | T-19-7th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-02-21 | 2026-05-16 | 1st Coat Painting | 100 | 0 |  | 2026-01-30 |  | 2026-04-24
40036 |  | Not Ready |  | 2025-12-19 | 2025-12-27 | L76-77 | 100 | 0 |  | 2026-01-30 |  | 2026-02-11
40036 |  | Not Ready |  | 2025-12-19 | 2025-12-27 | L76-77 | 100 | 0 |  | 2026-01-30 |  | 2026-02-11 |  |  |  |  | Finishes | Gypsum Plastering Works
40037 | Tower A - Super Structure - Core & Outer Slab L76-76 | Not Ready | RCC Works - Vertical | 2025-12-19 | 2025-12-26 | Outer Columns_TA | 100 | 0 |  | 2026-01-30 |  | 2026-02-09 |  | Tower A | Super Structure | L76 | RCC Sub Structure | RCC Works - Vertical
40449 |  | Not Committed |  | 2025-12-19 | 2026-03-28 | L73-74 | 100 | 0 |  | 2026-01-30 |  | 2026-04-20
40449 |  | Not Committed |  | 2025-12-19 | 2026-03-28 | L73-74 | 100 | 0 |  | 2026-01-30 |  | 2026-04-20 |  |  |  |  | Finishes | Gypsum Plastering Works
40450 | Tower A - Super Structure - Finishes & MEP - L73 to L74 | Not Ready | Partition Wall-Blockwork | 2025-12-19 | 2026-01-06 | De-shuttering & Area clearance | 100 | 0 |  | 2026-01-30 |  | 2026-02-17 |  | Tower A | Super Structure | L73
42858 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-03-02 | 2026-03-19 | Flooring & Dado works | 100 | 0 |  | 2026-01-30 |  | 2026-02-17 |  | Tower A | Super Structure | L43 | Finishes | Flooring & Dado
42948 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-03-02 | 2026-03-19 | Flooring & Dado works | 100 | 0 |  | 2026-01-30 |  | 2026-02-17 |  | Tower A | Super Structure | L48 | Finishes | Flooring & Dado
48060 | Retail & Clubhouse - Super structure - R1 to CH00 | Not Ready |  | 2025-10-09 | 2025-11-13 | R1 to CH00 | 100 | 0 |  | 2026-01-30 |  | 2026-03-06 |  | Club House | Super Structure | R1
48185 |  | Not Committed |  | 2025-10-09 | 2025-11-19 | Pour RT-2 | 100 | 0 |  | 2026-01-30 |  | 2026-03-12
48186 | Retail - Super structure - R1 to CH00 - P2 | Not Ready |  | 2025-10-09 | 2025-11-07 | Columns_RT | 100 | 0 |  | 2026-01-30 |  | 2026-02-27 |  | Retail | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
48186 | Retail - Super structure - R1 to CH00 - P2 | Not Ready |  | 2025-10-09 | 2025-11-07 | Columns_RT | 100 | 0 |  | 2026-01-30 |  | 2026-02-27 |  | Retail | Super Structure
48192 |  | Not Committed |  | 2025-10-09 | 2025-11-26 | Pour RT-4 | 100 | 0 |  | 2026-01-30 |  | 2026-03-19
48193 | Retail - Super structure - R1 to CH00 - P4 | Not Ready |  | 2025-10-09 | 2025-11-07 | Columns_RT | 100 | 0 |  | 2026-01-30 |  | 2026-02-27 |  | Retail | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
48193 | Retail - Super structure - R1 to CH00 - P4 | Not Ready |  | 2025-10-09 | 2025-11-07 | Columns_RT | 100 | 0 |  | 2026-01-30 |  | 2026-02-27 |  | Retail | Super Structure
48194 | Retail - Super structure - R1 to CH00 - P4 | Not Ready |  | 2025-10-09 | 2025-11-07 | Staircase_RT | 100 | 0 |  | 2026-01-30 |  | 2026-02-27 |  | Retail | Super Structure |  | RCC Sub Structure | RCC Works - Slab
48194 | Retail - Super structure - R1 to CH00 - P4 | Not Ready |  | 2025-10-09 | 2025-11-07 | Staircase_RT | 100 | 0 |  | 2026-01-30 |  | 2026-02-27 |  | Retail | Super Structure
8721 | T-14-7th Floor Common Area | Not Ready | Putty | 2025-12-29 | 2026-02-07 | Putty | 100 | 0 |  | 2026-01-31 |  | 2026-03-13
8848 |  | Not Ready |  | 2026-01-30 | 2026-08-19 | Common Area | 100 | 0 |  | 2026-01-31 |  | 2026-08-21
11433 | T-19-11th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2026-02-10 | 2026-03-04 | Plumbing Pipe Line | 100 | 0 |  | 2026-01-31 |  | 2026-02-21
40838 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2024-10-22 | 2024-11-08 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-01-31 |  | 2026-02-18 |  | Tower A | Super Structure
40838 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2024-10-22 | 2024-11-08 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-01-31 |  | 2026-02-18 |  | Tower A | Super Structure
40838 | Tower A - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2024-10-22 | 2024-11-08 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-01-31 |  | 2026-02-18 |  | Tower A | Super Structure
41216 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-01-10 | 2026-01-13 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-01-31 |  | 2026-02-04 |  | Tower A | Super Structure | L16
41561 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-06-24 | 2025-06-28 | Lobby Plastering | 100 | 0 |  | 2026-01-31 |  | 2026-02-05 |  | Tower A | Super Structure | L38 | Finishes | Lobby Plastering
41576 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2025-06-24 | 2025-06-26 | Lobby Blockwork | 100 | 0 |  | 2026-01-31 |  | 2026-02-03 |  | Tower A | Super Structure | L39 | Finishes | Blockwork
8740 | T-14-8th Floor Flat Area | Not Ready | Door | 2026-01-21 | 2026-02-13 | Door | 100 | 0 |  | 2026-02-01 |  | 2026-02-23
9801 | T-16-8th Floor Flat Area | Not Ready | Toilet flooring | 2026-02-21 | 2026-03-26 | Toilet flooring | 100 | 0 |  | 2026-02-01 |  | 2026-03-08
9827 | T-16-9th Floor Flat Area | Not Ready | Toilet flooring | 2026-02-21 | 2026-03-26 | Toilet flooring | 100 | 0 |  | 2026-02-01 |  | 2026-03-08
10309 | T-21-7th Floor Common Area | Not Ready | Window-Open Area | 2026-03-04 | 2026-03-12 | Window-Open Area | 100 | 0 |  | 2026-02-01 |  | 2026-02-07
10745 | T-20-4th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-03-19 | 2026-05-25 | 2nd Coat Painting | 100 | 0 |  | 2026-02-01 |  | 2026-04-09
10849 | T-20-8th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-03-19 | 2026-05-25 | 2nd Coat Painting | 100 | 0 |  | 2026-02-01 |  | 2026-04-09
11294 | T-19-5th Floor Common Area | Not Ready | Flooring & skirting | 2026-02-18 | 2026-03-12 | Flooring & skirting | 100 | 0 |  | 2026-02-01 |  | 2026-02-23
11321 | T-19-6th Floor Common Area | Not Ready | Putty | 2026-02-18 | 2026-03-29 | Putty | 100 | 0 |  | 2026-02-01 |  | 2026-03-14
11958 | T-18-11th Floor Flat Area | Not Ready | Dado | 2026-04-20 | 2026-05-18 | Dado | 100 | 0 |  | 2026-02-01 |  | 2026-02-26
8786 | T-14-10th Floor Flat Area | Not Ready | Dado | 2025-12-30 | 2026-01-29 | Dado | 100 | 0 |  | 2026-02-02 |  | 2026-03-06
8808 | T-14-11th Floor Flat Area | Not Ready | Plastering | 2025-12-27 | 2026-01-19 | Plastering-Cement | 100 | 0 |  | 2026-02-02 |  | 2026-02-24
10334 | T-21-8th Floor Common Area | Not Ready | Door-Shaft | 2026-03-07 | 2026-03-20 | Door-Shaft | 100 | 0 |  | 2026-02-02 |  | 2026-02-15
10803 | T-20-6th Floor Common Area | Not Ready | Window-Open Area | 2026-02-27 | 2026-03-06 | Window-Open Area | 100 | 0 |  | 2026-02-02 |  | 2026-02-12
10828 | T-20-7th Floor Common Area | Not Ready | Door-Shaft | 2026-03-03 | 2026-03-16 | Door-Shaft | 100 | 0 |  | 2026-02-02 |  | 2026-02-13
11314 | T-19-6th Floor Flat Area | Not Ready | Door | 2026-03-03 | 2026-03-26 | Door | 100 | 0 |  | 2026-02-02 |  | 2026-02-24
11437 | T-19-11th Floor Flat Area | Not Ready | Plastering | 2026-02-12 | 2026-03-29 | Plastering-Gypsum | 100 | 0 |  | 2026-02-02 |  | 2026-03-19
40533 | Tower A - Super Structure - Finishes & MEP - L59 to L60 | Not Ready | Gypsum Plastering Works | 2026-01-09 | 2026-01-27 | L59-60 | 100 | 0 |  | 2026-02-02 |  | 2026-02-18 |  | Tower A | Super Structure | L59 | Finishes | Gypsum Plastering Works
40533 | Tower A - Super Structure - Finishes & MEP - L59 to L60 | Not Ready | Gypsum Plastering Works | 2026-01-09 | 2026-01-27 | L59-60 | 100 | 0 |  | 2026-02-02 |  | 2026-02-18 |  | Tower A | Super Structure | L59
41243 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-01-12 | 2026-01-19 | False Ceiling | 100 | 0 |  | 2026-02-02 |  | 2026-02-10 |  | Tower A | Super Structure | L18 | Finishes | False Ceiling
41271 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-01-12 | 2026-01-19 | HVAC Ducting | 100 | 0 |  | 2026-02-02 |  | 2026-02-10 |  | Tower A | Super Structure | L20 | MEP | HVAC Ducting
41753 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2026-01-02 | 2026-01-07 | Lobby Plastering | 100 | 0 |  | 2026-02-02 |  | 2026-02-07 |  | Tower A | Super Structure | L50 | Finishes | Lobby Plastering
41763 |  | Not Committed |  | 2026-01-02 | 2026-07-04 | L51-52 | 100 | 0 |  | 2026-02-02 |  | 2026-07-29
41763 |  | Not Committed |  | 2026-01-02 | 2026-07-04 | L51-52 | 100 | 0 |  | 2026-02-02 |  | 2026-07-29 |  |  |  |  | Finishes | Gypsum Plastering Works
41768 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2026-01-02 | 2026-01-05 | Lobby Blockwork | 100 | 0 |  | 2026-02-02 |  | 2026-02-05 |  | Tower A | Super Structure | L51 | Finishes | Blockwork
43154 |  | Not Committed |  | 2026-01-09 | 2026-09-28 | L60-61 | 100 | 0 |  | 2026-02-02 |  | 2026-09-07
43154 |  | Not Committed |  | 2026-01-09 | 2026-09-28 | L60-61 | 100 | 0 |  | 2026-02-02 |  | 2026-09-07 |  |  |  |  | Finishes | Gypsum Plastering Works
43155 |  | Not Committed |  | 2026-01-09 | 2026-02-07 | MEP 1st Fixes | 100 | 0 |  | 2026-02-02 |  | 2026-03-02
43156 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-01-09 | 2026-01-16 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-02-02 |  | 2026-02-09 |  | Tower A | Super Structure | L60 | MEP | FPS 1st Fix - MEP & Finishes
43157 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-01-09 | 2026-01-14 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-02-02 |  | 2026-02-06 |  | Tower A | Super Structure | L60 | MEP | Electrical 1st Fixes
43158 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-01-09 | 2026-01-16 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-02-02 |  | 2026-02-09 |  | Tower A | Super Structure | L60
43159 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-01-09 | 2026-01-27 | Wet Area Waterproofing | 100 | 0 |  | 2026-02-02 |  | 2026-02-18 |  | Tower A | Super Structure | L60
45432 | Tower B - Super Structure - Finishes & MEP - P6 to L7 | Not Ready | Partition Wall-Blockwork | 2025-11-27 | 2025-12-02 | Staircase Area | 100 | 0 |  | 2026-02-02 |  | 2026-02-07 |  | Tower B | Super Structure
8765 | T-14-9th Floor Flat Area | Not Ready | Window | 2026-01-23 | 2026-02-15 | Window | 100 | 0 |  | 2026-02-03 |  | 2026-02-24
10352 | T-21-9th Floor Flat Area | Not Ready | Door | 2026-02-17 | 2026-03-11 | Door | 100 | 0 |  | 2026-02-03 |  | 2026-02-26
10377 | T-21-10th Floor Flat Area | Not Ready | Window | 2026-02-17 | 2026-03-11 | Window | 100 | 0 |  | 2026-02-03 |  | 2026-02-26
10719 | T-20-3rd Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-03-21 | 2026-05-27 | 2nd Coat Painting | 100 | 0 |  | 2026-02-03 |  | 2026-04-09
39252 | Retail - Foundation | Not Ready | Raft RCC Works | 2025-08-16 | 2025-08-23 | Fwk & Casting_NTA | 100 | 0 |  | 2026-02-03 |  | 2026-02-09 |  | Retail | Foundation | -- | RCC Sub Structure | Raft RCC Works
39252 | Retail - Foundation | Not Ready | Raft RCC Works | 2025-08-16 | 2025-08-23 | Fwk & Casting_NTA | 100 | 0 |  | 2026-02-03 |  | 2026-02-09 |  | Retail | Foundation | -- | RCC Super Structure | Foundation RCC Works
39252 | Retail - Foundation | Not Ready | Raft RCC Works | 2025-08-16 | 2025-08-23 | Fwk & Casting_NTA | 100 | 0 |  | 2026-02-03 |  | 2026-02-09 |  | Retail | Foundation | --
40038 | Tower A - Super Structure - Core & Outer Slab L76-76 | Not Ready | RCC Works - Slab | 2025-12-22 | 2025-12-27 | Outer Slab_TA | 100 | 0 |  | 2026-02-03 |  | 2026-02-11 |  | Tower A | Super Structure | L76 | RCC Sub Structure | RCC Works - Slab
41228 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-01-13 | 2026-01-15 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-02-03 |  | 2026-02-06 |  | Tower A | Super Structure | L17 | MEP | FPS 2nd Fix - MEP & Finishes
41229 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-01-13 | 2026-01-17 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-02-03 |  | 2026-02-09 |  | Tower A | Super Structure | L17 | MEP | Electrical 2nd Fix - MEP & Finishes
41230 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-01-13 | 2026-01-20 | FAPA Device Fixing | 100 | 0 |  | 2026-02-03 |  | 2026-02-11 |  | Tower A | Super Structure | L17
41230 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-01-13 | 2026-01-20 | FAPA Device Fixing | 100 | 0 |  | 2026-02-03 |  | 2026-02-11 |  | Tower A | Super Structure | L17
41230 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-01-13 | 2026-01-20 | FAPA Device Fixing | 100 | 0 |  | 2026-02-03 |  | 2026-02-11 |  | Tower A | Super Structure | L17
41230 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-01-13 | 2026-01-20 | FAPA Device Fixing | 100 | 0 |  | 2026-02-03 |  | 2026-02-11 |  | Tower A | Super Structure | L17
41231 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-01-13 | 2026-01-15 | HVAC Grill Fixing | 100 | 0 |  | 2026-02-03 |  | 2026-02-06 |  | Tower A | Super Structure | L17 | MEP | HVAC Grill Fixing
41258 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-01-13 | 2026-01-23 | Flooring & Dado | 100 | 0 |  | 2026-02-03 |  | 2026-02-14 |  | Tower A | Super Structure | L19 | Finishes | Flooring & Dado
43124 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-01-10 | 2026-01-21 | Cement Plastering in wet areas | 100 | 0 |  | 2026-02-03 |  | 2026-02-13 |  | Tower A | Super Structure | L58
43958 | Tower A - Super Structure - Finishes & MEP - B3 to GF | Not Ready | Staircase Finishes - MEP & Finishes | 2026-03-06 | 2026-03-11 | Staircase cabling | 100 | 0 |  | 2026-02-03 |  | 2026-02-09 |  | Tower A | Super Structure | B3
8823 | T-14-11th Floor Common Area | Not Ready | Plastering | 2025-12-29 | 2026-02-02 | Plastering-Gypsum | 100 | 0 |  | 2026-02-04 |  | 2026-03-11
9286 | T-15-8th Floor Flat Area | Not Ready | Door | 2026-02-21 | 2026-03-15 | Door | 100 | 0 |  | 2026-02-04 |  | 2026-02-26
9318 | T-15-9th Floor Common Area | Not Ready | Flooring & skirting | 2026-02-10 | 2026-03-03 | Flooring & skirting | 100 | 0 |  | 2026-02-04 |  | 2026-02-26
9804 | T-16-8th Floor Flat Area | Not Ready | Putty | 2026-02-24 | 2026-05-19 | Putty | 100 | 0 |  | 2026-02-04 |  | 2026-04-29
9830 | T-16-9th Floor Flat Area | Not Ready | Putty | 2026-02-24 | 2026-05-19 | Putty | 100 | 0 |  | 2026-02-04 |  | 2026-04-29
10406 | T-21-11th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-03-13 | 2026-06-05 | 1st Coat Painting | 100 | 0 |  | 2026-02-04 |  | 2026-04-29
11339 | T-19-7th Floor Flat Area | Not Ready | Window | 2026-03-05 | 2026-03-28 | Window | 100 | 0 |  | 2026-02-04 |  | 2026-02-27
11893 | T-18-8th Floor Common Area | Not Ready | Putty | 2026-04-20 | 2026-05-28 | Putty | 100 | 0 |  | 2026-02-04 |  | 2026-03-13
40404 | Tower A - Super Structure - Finishes & MEP - L61 to L62 | Not Ready | Partition Wall-Blockwork | 2026-01-12 | 2026-01-16 | Staircase Area | 100 | 0 |  | 2026-02-04 |  | 2026-02-09 |  | Tower A | Super Structure | L61
40407 | Tower A - Super Structure - Finishes & MEP - L62 to L63 | Not Ready | Partition Wall-Blockwork | 2026-01-12 | 2026-01-19 | Partition Walls | 100 | 0 |  | 2026-02-04 |  | 2026-02-11 |  | Tower A | Super Structure | L62
40853 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2024-08-31 | 2024-09-05 | Final Painting | 100 | 0 |  | 2026-02-04 |  | 2026-02-10 |  | Tower A | Super Structure |  | Finishes | Final Painting
40853 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2024-08-31 | 2024-09-05 | Final Painting | 100 | 0 |  | 2026-02-04 |  | 2026-02-10 |  | Tower A | Super Structure |  | Finishes | Final Painting
40853 | Tower A - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2024-08-31 | 2024-09-05 | Final Painting | 100 | 0 |  | 2026-02-04 |  | 2026-02-10 |  | Tower A | Super Structure |  | Finishes | Final Painting
41202 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-01-14 | 2026-01-19 | Final Painting | 100 | 0 |  | 2026-02-04 |  | 2026-02-10 |  | Tower A | Super Structure | L15 | Finishes | Final Painting
41202 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-01-14 | 2026-01-19 | Final Painting | 100 | 0 |  | 2026-02-04 |  | 2026-02-10 |  | Tower A | Super Structure | L15 | Finishes | Final Painting
41202 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-01-14 | 2026-01-19 | Final Painting | 100 | 0 |  | 2026-02-04 |  | 2026-02-10 |  | Tower A | Super Structure | L15 | Finishes | Final Painting
41217 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-01-14 | 2026-01-19 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-02-04 |  | 2026-02-10 |  | Tower A | Super Structure | L16 | MEP | Electrical
41577 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2025-06-27 | 2025-07-02 | Lobby Plastering | 100 | 0 |  | 2026-02-04 |  | 2026-02-09 |  | Tower A | Super Structure | L39 | Finishes | Lobby Plastering
45395 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 | Not Ready | Partition Wall-Blockwork | 2025-03-29 | 2025-04-15 | Partition Walls | 100 | 0 |  | 2026-02-04 |  | 2026-02-20 |  | Tower B | Sub Structure | B3
9756 | T-16-6th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-02-28 | 2026-05-23 | 1st Coat Painting | 100 | 0 |  | 2026-02-05 |  | 2026-04-30
10257 | T-21-5th Floor Common Area | Not Ready | Window-Open Area | 2026-03-10 | 2026-03-17 | Window-Open Area | 100 | 0 |  | 2026-02-05 |  | 2026-02-13
41769 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2026-01-06 | 2026-01-10 | Lobby Plastering | 100 | 0 |  | 2026-02-05 |  | 2026-02-11 |  | Tower A | Super Structure | L51 | Finishes | Lobby Plastering
41779 |  | Not Committed |  | 2026-01-06 | 2026-07-10 | L52-53 | 100 | 0 |  | 2026-02-05 |  | 2026-08-05
41779 |  | Not Committed |  | 2026-01-06 | 2026-07-10 | L52-53 | 100 | 0 |  | 2026-02-05 |  | 2026-08-05 |  |  |  |  | Finishes | Gypsum Plastering Works
41784 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2026-01-06 | 2026-01-08 | Lobby Blockwork | 100 | 0 |  | 2026-02-05 |  | 2026-02-09 |  | Tower A | Super Structure | L52 | Finishes | Blockwork
42966 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-03-09 | 2026-03-25 | Flooring & Dado works | 100 | 0 |  | 2026-02-05 |  | 2026-02-23 |  | Tower A | Super Structure | L49 | Finishes | Flooring & Dado
43055 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-01-13 | 2026-01-20 | Door & Window Frame work | 100 | 0 |  | 2026-02-05 |  | 2026-02-12 |  | Tower A | Super Structure | L54 | Finishes | Door & Window Frame work
44099 | Tower A - Super Structure - Finishes & MEP - L48 to L53 | Not Ready | Façade Works - MEP & Finishes | 2026-03-09 | 2026-03-19 | DGU Assembly Installation | 100 | 0 |  | 2026-02-05 |  | 2026-02-17 |  | Tower A | Super Structure | L48 | Façade | Façade Works
44100 | Tower A - Super Structure - Finishes & MEP - L48 to L53 | Not Ready | Façade Works - MEP & Finishes | 2026-03-09 | 2026-03-31 | Installation of highly reflective metal sheet | 100 | 0 |  | 2026-02-05 |  | 2026-02-28 |  | Tower A | Super Structure | L48 | Façade | Façade Works
44101 | Tower A - Super Structure - Finishes & MEP - L48 to L53 | Not Ready | Façade Works - MEP & Finishes | 2026-03-09 | 2026-03-19 | Fixing of Backlit Laminated Glass assembly & ACP Panels | 100 | 0 |  | 2026-02-05 |  | 2026-02-17 |  | Tower A | Super Structure | L48 | Façade | Façade Works
44102 | Tower A - Super Structure - Finishes & MEP - L48 to L53 | Not Ready | Façade Works - MEP & Finishes | 2026-03-09 | 2026-03-19 | Fixing of Louvers | 100 | 0 |  | 2026-02-05 |  | 2026-02-17 |  | Tower A | Super Structure | L48 | Façade | Façade Works
44102 | Tower A - Super Structure - Finishes & MEP - L48 to L53 | Not Ready | Façade Works - MEP & Finishes | 2026-03-09 | 2026-03-19 | Fixing of Louvers | 100 | 0 |  | 2026-02-05 |  | 2026-02-17 |  | Tower A | Super Structure | L48
8642 | T-14-4th Floor Common Area | Not Ready | Flooring & skirting | 2026-01-03 | 2026-01-28 | Flooring & skirting | 100 | 0 |  | 2026-02-06 |  | 2026-03-04
8669 | T-14-5th Floor Common Area | Not Ready | Putty | 2026-01-03 | 2026-02-13 | Putty | 100 | 0 |  | 2026-02-06 |  | 2026-03-19
9311 | T-15-9th Floor Flat Area | Not Ready | Window | 2026-02-24 | 2026-03-17 | Window | 100 | 0 |  | 2026-02-06 |  | 2026-02-28
9358 | T-15-11th Floor Flat Area | Not Ready | Dado | 2026-02-15 | 2026-03-14 | Dado | 100 | 0 |  | 2026-02-06 |  | 2026-03-05
10411 | T-21-11th Floor Common Area | Not Ready | Putty | 2026-03-18 | 2026-04-27 | Putty | 100 | 0 |  | 2026-02-06 |  | 2026-03-16
11860 | T-18-7th Floor Flat Area | Not Ready | Door | 2026-04-13 | 2026-05-06 | Door | 100 | 0 |  | 2026-02-06 |  | 2026-02-28
41232 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-01-16 | 2026-01-19 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-02-06 |  | 2026-02-10 |  | Tower A | Super Structure | L17
43107 |  | Not Committed |  | 2026-01-14 | 2026-05-12 | Finishes after 1st Fix | 100 | 0 |  | 2026-02-06 |  | 2026-04-11
43108 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-01-14 | 2026-02-06 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-02-06 |  | 2026-02-28 |  | Tower A | Super Structure | L57 | Finishes | Blockwork
45283 |  | Not Ready |  | 2025-12-02 | 2025-12-16 | L11-12 | 100 | 0 |  | 2026-02-06 |  | 2026-02-21
45283 |  | Not Ready |  | 2025-12-02 | 2025-12-16 | L11-12 | 100 | 0 |  | 2026-02-06 |  | 2026-02-21 |  |  |  |  | Finishes | Gypsum Plastering Works
45284 | Tower B - Super Structure - Core & Outer Slab L11-12 | Not Ready | RCC Works - Vertical | 2025-12-02 | 2025-12-12 | Outer Columns_TA | 100 | 0 |  | 2026-02-06 |  | 2026-02-18 |  | Tower B | Super Structure | L11 | RCC Sub Structure | RCC Works - Vertical
45437 |  | Not Committed |  | 2025-12-02 | 2026-01-02 | L8-9 | 100 | 0 |  | 2026-02-06 |  | 2026-03-11
45437 |  | Not Committed |  | 2025-12-02 | 2026-01-02 | L8-9 | 100 | 0 |  | 2026-02-06 |  | 2026-03-11 |  |  |  |  | Finishes | Gypsum Plastering Works
45438 | Tower B - Super Structure - Finishes & MEP - L8 to L9 | Not Ready | Partition Wall-Blockwork | 2025-12-02 | 2025-12-18 | De-shuttering & Area clearance | 100 | 0 |  | 2026-02-06 |  | 2026-02-24 |  | Tower B | Super Structure | L8
11412 | T-19-10th Floor Flat Area | Not Ready | Dado | 2026-02-21 | 2026-03-20 | Dado | 100 | 0 |  | 2026-02-07 |  | 2026-03-08
11434 | T-19-11th Floor Flat Area | Not Ready | Plastering | 2026-02-18 | 2026-03-12 | Plastering-Cement | 100 | 0 |  | 2026-02-07 |  | 2026-03-01
11811 | T-18-5th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-04-30 | 2026-07-06 | 2nd Coat Painting | 100 | 0 |  | 2026-02-07 |  | 2026-04-14
11863 | T-18-7th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-04-30 | 2026-07-06 | 2nd Coat Painting | 100 | 0 |  | 2026-02-07 |  | 2026-04-14
8768 | T-14-9th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-01-13 | 2026-04-08 | 1st Coat Painting | 100 | 0 |  | 2026-02-08 |  | 2026-05-02
8772 | T-14-9th Floor Common Area | Not Ready | Flooring & skirting | 2026-01-09 | 2026-02-02 | Flooring & skirting | 100 | 0 |  | 2026-02-08 |  | 2026-03-02
10310 | T-21-7th Floor Common Area | Not Ready | 1st Coat Painting | 2026-03-12 | 2026-04-03 | 1st Coat Painting | 100 | 0 |  | 2026-02-08 |  | 2026-03-01
11885 | T-18-8th Floor Flat Area | Not Ready | Window | 2026-04-15 | 2026-05-08 | Window | 100 | 0 |  | 2026-02-08 |  | 2026-03-02
11959 | T-18-11th Floor Flat Area | Not Ready | Toilet flooring | 2026-04-27 | 2026-05-30 | Toilet flooring | 100 | 0 |  | 2026-02-08 |  | 2026-03-13
8787 | T-14-10th Floor Flat Area | Not Ready | Toilet flooring | 2026-01-07 | 2026-02-11 | Toilet flooring | 100 | 0 |  | 2026-02-09 |  | 2026-03-16
9188 | T-15-4th Floor Common Area | Not Ready | Flooring & skirting | 2026-02-04 | 2026-02-26 | Flooring & skirting | 100 | 0 |  | 2026-02-09 |  | 2026-03-02
9215 | T-15-5th Floor Common Area | Not Ready | Putty | 2026-02-04 | 2026-03-14 | Putty | 100 | 0 |  | 2026-02-09 |  | 2026-03-17
9728 | T-16-5th Floor Flat Area | Not Ready | Door | 2026-03-11 | 2026-04-03 | Door | 100 | 0 |  | 2026-02-09 |  | 2026-03-03
9802 | T-16-8th Floor Flat Area | Not Ready | Toilets False Celing | 2026-03-02 | 2026-04-04 | Toilets False Celing | 100 | 0 |  | 2026-02-09 |  | 2026-03-16
9828 | T-16-9th Floor Flat Area | Not Ready | Toilets False Celing | 2026-03-02 | 2026-04-04 | Toilets False Celing | 100 | 0 |  | 2026-02-09 |  | 2026-03-16
10439 |  | Not Ready |  | 2026-03-13 | 2026-08-14 | Staircase-1 | 100 | 0 |  | 2026-02-09 |  | 2026-07-14
11449 | T-19-11th Floor Common Area | Not Ready | Plastering | 2026-02-20 | 2026-03-26 | Plastering-Gypsum | 100 | 0 |  | 2026-02-09 |  | 2026-03-15
39253 |  | Not Committed |  | 2025-08-30 | 2026-02-20 | Sub-Structure_Retail | 100 | 0 |  | 2026-02-09 |  | 2026-08-17
39254 |  | Not Committed |  | 2025-08-30 | 2025-10-30 | B3 to B2 | 100 | 0 |  | 2026-02-09 |  | 2026-04-08
39254 |  | Not Committed |  | 2025-08-30 | 2025-10-30 | B3 to B2 | 100 | 0 |  | 2026-02-09 |  | 2026-04-08
39254 |  | Not Committed |  | 2025-08-30 | 2025-10-30 | B3 to B2 | 100 | 0 |  | 2026-02-09 |  | 2026-04-08
39255 | Retail - Sub structure - B3 to B2 | Not Ready | Retaining Wall RCC Works | 2025-08-30 | 2025-09-08 | Retaining Wall_lift 1 | 100 | 0 |  | 2026-02-09 |  | 2026-02-17 |  | Retail | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
39255 | Retail - Sub structure - B3 to B2 | Not Ready | Retaining Wall RCC Works | 2025-08-30 | 2025-09-08 | Retaining Wall_lift 1 | 100 | 0 |  | 2026-02-09 |  | 2026-02-17 |  | Retail | Sub Structure | B3
41259 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-01-19 | 2026-01-27 | False Ceiling | 100 | 0 |  | 2026-02-09 |  | 2026-02-17 |  | Tower A | Super Structure | L19 | Finishes | False Ceiling
41287 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-01-19 | 2026-01-27 | HVAC Ducting | 100 | 0 |  | 2026-02-09 |  | 2026-02-17 |  | Tower A | Super Structure | L21 | MEP | HVAC Ducting
41785 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2026-01-09 | 2026-01-14 | Lobby Plastering | 100 | 0 |  | 2026-02-09 |  | 2026-02-14 |  | Tower A | Super Structure | L52 | Finishes | Lobby Plastering
41795 |  | Not Committed |  | 2026-01-09 | 2026-07-17 | L53-54 | 100 | 0 |  | 2026-02-09 |  | 2026-08-12
41795 |  | Not Committed |  | 2026-01-09 | 2026-07-17 | L53-54 | 100 | 0 |  | 2026-02-09 |  | 2026-08-12 |  |  |  |  | Finishes | Gypsum Plastering Works
41800 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2026-01-09 | 2026-01-12 | Lobby Blockwork | 100 | 0 |  | 2026-02-09 |  | 2026-02-12 |  | Tower A | Super Structure | L53 | Finishes | Blockwork
43962 | Tower A - Super Structure - Finishes & MEP - GF to L7 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-03-12 | 2026-05-04 | Staircase Flooring | 100 | 0 |  | 2026-02-09 |  | 2026-04-03 |  | Tower A | Super Structure | GF | Finishes | Staircase Flooring
45435 | Tower B - Super Structure - Finishes & MEP - L7 to L8 | Not Ready | Partition Wall-Blockwork | 2025-12-04 | 2025-12-11 | Partition Walls | 100 | 0 |  | 2026-02-09 |  | 2026-02-17 |  | Tower B | Super Structure | L7
9849 | T-16-10th Floor Flat Area | Not Ready | Waterproofing | 2026-02-26 | 2026-04-01 | Waterproofing | 100 | 0 |  | 2026-02-10 |  | 2026-03-16
10440 | T-21-Staircase 1 | Not Ready |  | 2026-03-13 | 2026-03-24 | TF-12F | 100 | 0 |  | 2026-02-10 |  | 2026-02-20
10776 | T-20-5th Floor Common Area | Not Ready | Door-Shaft | 2026-03-08 | 2026-03-21 | Door-Shaft | 100 | 0 |  | 2026-02-10 |  | 2026-02-21
10905 | T-20-11th Floor Common Area | Not Ready | Putty | 2026-03-13 | 2026-04-22 | Putty | 100 | 0 |  | 2026-02-10 |  | 2026-03-19
11317 | T-19-6th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-03-06 | 2026-05-13 | 2nd Coat Painting | 100 | 0 |  | 2026-02-10 |  | 2026-04-16
11372 | T-19-8th Floor Common Area | Not Ready | Flooring & skirting | 2026-03-01 | 2026-03-23 | Flooring & skirting | 100 | 0 |  | 2026-02-10 |  | 2026-03-04
40076 | Tower A - Super Structure - Finishes & MEP - L70 to L71 | Not Ready | CTU Elevators Crash Deck - High Side Services | 2026-01-10 | 2026-01-27 | Guide Rail Installation for CWT (up to L65) | 100 | 0 |  | 2026-02-10 |  | 2026-02-26 |  | Tower A | Super Structure | L70
40534 | Tower A - Super Structure - Finishes & MEP - L60 to L61 | Not Ready | Gypsum Plastering Works | 2026-01-17 | 2026-02-04 | L60-61 | 100 | 0 |  | 2026-02-10 |  | 2026-02-26 |  | Tower A | Super Structure | L60 | Finishes | Gypsum Plastering Works
40534 | Tower A - Super Structure - Finishes & MEP - L60 to L61 | Not Ready | Gypsum Plastering Works | 2026-01-17 | 2026-02-04 | L60-61 | 100 | 0 |  | 2026-02-10 |  | 2026-02-26 |  | Tower A | Super Structure | L60
41218 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-01-20 | 2026-01-24 | Final Painting | 100 | 0 |  | 2026-02-10 |  | 2026-02-16 |  | Tower A | Super Structure | L16 | Finishes | Final Painting
41218 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-01-20 | 2026-01-24 | Final Painting | 100 | 0 |  | 2026-02-10 |  | 2026-02-16 |  | Tower A | Super Structure | L16 | Finishes | Final Painting
41218 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-01-20 | 2026-01-24 | Final Painting | 100 | 0 |  | 2026-02-10 |  | 2026-02-16 |  | Tower A | Super Structure | L16 | Finishes | Final Painting
41233 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-01-20 | 2026-01-24 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-02-10 |  | 2026-02-16 |  | Tower A | Super Structure | L17 | MEP | Electrical
41244 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-01-20 | 2026-01-22 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-02-10 |  | 2026-02-13 |  | Tower A | Super Structure | L18 | MEP | FPS 2nd Fix - MEP & Finishes
41245 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-01-20 | 2026-01-24 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-02-10 |  | 2026-02-16 |  | Tower A | Super Structure | L18 | MEP | Electrical 2nd Fix - MEP & Finishes
41246 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-01-20 | 2026-01-28 | FAPA Device Fixing | 100 | 0 |  | 2026-02-10 |  | 2026-02-18 |  | Tower A | Super Structure | L18
41246 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-01-20 | 2026-01-28 | FAPA Device Fixing | 100 | 0 |  | 2026-02-10 |  | 2026-02-18 |  | Tower A | Super Structure | L18
41246 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-01-20 | 2026-01-28 | FAPA Device Fixing | 100 | 0 |  | 2026-02-10 |  | 2026-02-18 |  | Tower A | Super Structure | L18
41246 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-01-20 | 2026-01-28 | FAPA Device Fixing | 100 | 0 |  | 2026-02-10 |  | 2026-02-18 |  | Tower A | Super Structure | L18
41247 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-01-20 | 2026-01-22 | HVAC Grill Fixing | 100 | 0 |  | 2026-02-10 |  | 2026-02-13 |  | Tower A | Super Structure | L18 | MEP | HVAC Grill Fixing
41274 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-01-20 | 2026-01-31 | Flooring & Dado | 100 | 0 |  | 2026-02-10 |  | 2026-02-21 |  | Tower A | Super Structure | L20 | Finishes | Flooring & Dado
43172 |  | Not Committed |  | 2026-01-17 | 2026-10-06 | L61-62 | 100 | 0 |  | 2026-02-10 |  | 2026-09-14
43172 |  | Not Committed |  | 2026-01-17 | 2026-10-06 | L61-62 | 100 | 0 |  | 2026-02-10 |  | 2026-09-14 |  |  |  |  | Finishes | Gypsum Plastering Works
43173 |  | Not Committed |  | 2026-01-17 | 2026-02-16 | MEP 1st Fixes | 100 | 0 |  | 2026-02-10 |  | 2026-03-11
43174 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-01-17 | 2026-01-24 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-02-10 |  | 2026-02-17 |  | Tower A | Super Structure | L61 | MEP | FPS 1st Fix - MEP & Finishes
43175 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-01-17 | 2026-01-22 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-02-10 |  | 2026-02-14 |  | Tower A | Super Structure | L61 | MEP | Electrical 1st Fixes
43176 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-01-17 | 2026-01-24 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-02-10 |  | 2026-02-17 |  | Tower A | Super Structure | L61
43177 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-01-17 | 2026-02-04 | Wet Area Waterproofing | 100 | 0 |  | 2026-02-10 |  | 2026-02-26 |  | Tower A | Super Structure | L61
9753 | T-16-6th Floor Flat Area | Not Ready | Window | 2026-03-13 | 2026-04-06 | Window | 100 | 0 |  | 2026-02-11 |  | 2026-03-08
9872 | T-16-11th Floor Flat Area | Not Ready | Blockwork | 2026-02-24 | 2026-03-18 | Blockwork-Ledge Wall | 100 | 0 |  | 2026-02-11 |  | 2026-03-04
11944 | T-18-11th Floor Common Area | Not Ready | Flooring & skirting | 2026-04-30 | 2026-05-23 | Flooring & skirting | 100 | 0 |  | 2026-02-11 |  | 2026-03-03
11962 | T-18-11th Floor Flat Area | Not Ready | Putty | 2026-04-30 | 2026-07-22 | Putty | 100 | 0 |  | 2026-02-11 |  | 2026-05-06
40039 |  | Not Ready |  | 2025-12-29 | 2026-01-22 | L77-78 | 100 | 0 |  | 2026-02-11 |  | 2026-02-27
40039 |  | Not Ready |  | 2025-12-29 | 2026-01-22 | L77-78 | 100 | 0 |  | 2026-02-11 |  | 2026-02-27 |  |  |  |  | Finishes | Gypsum Plastering Works
40040 | Tower A - Super Structure - Core & Outer Slab L77-78 | Not Ready | RCC Works - Vertical | 2025-12-29 | 2026-01-13 | Outer Columns_TA | 100 | 0 |  | 2026-02-11 |  | 2026-02-23 |  | Tower A | Super Structure | L77 | RCC Sub Structure | RCC Works - Vertical
40453 |  | Not Committed |  | 2025-12-29 | 2026-03-31 | L74-75 | 100 | 0 |  | 2026-02-11 |  | 2026-04-22
40453 |  | Not Committed |  | 2025-12-29 | 2026-03-31 | L74-75 | 100 | 0 |  | 2026-02-11 |  | 2026-04-22 |  |  |  |  | Finishes | Gypsum Plastering Works
40454 | Tower A - Super Structure - Finishes & MEP - L74 to L75 | Not Ready | Partition Wall-Blockwork | 2025-12-29 | 2026-01-14 | De-shuttering & Area clearance | 100 | 0 |  | 2026-02-11 |  | 2026-02-28 |  | Tower A | Super Structure | L74
42984 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-03-14 | 2026-03-31 | Flooring & Dado works | 100 | 0 |  | 2026-02-11 |  | 2026-02-28 |  | Tower A | Super Structure | L50 | Finishes | Flooring & Dado
43142 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-01-19 | 2026-01-30 | Cement Plastering in wet areas | 100 | 0 |  | 2026-02-11 |  | 2026-02-21 |  | Tower A | Super Structure | L59
43957 | Tower A - Super Structure - Finishes & MEP - B3 to GF | Not Ready | Staircase Finishes - MEP & Finishes | 2026-03-14 | 2026-04-03 | Staircase Railing | 100 | 0 |  | 2026-02-11 |  | 2026-03-05 |  | Tower A | Super Structure | B3
44104 |  | Not Ready |  | 2026-03-14 | 2026-04-17 | L53-58 | 100 | 0 |  | 2026-02-11 |  | 2026-03-19
44105 | Tower A - Super Structure - Finishes & MEP - L53 to L58 | Not Ready | Façade Works - MEP & Finishes | 2026-03-14 | 2026-03-25 | Al. Frame section (Mullion & Transom) Installation | 100 | 0 |  | 2026-02-11 |  | 2026-02-23 |  | Tower A | Super Structure | L53 | Façade | Façade Works
48203 | Retail - Super structure - R1 to CH00 - P6 | Not Ready |  | 2025-10-22 | 2025-11-13 | Slab_RT | 100 | 0 |  | 2026-02-11 |  | 2026-03-06 |  | Retail | Super Structure |  | RCC Sub Structure | RCC Works - Slab
48203 | Retail - Super structure - R1 to CH00 - P6 | Not Ready |  | 2025-10-22 | 2025-11-13 | Slab_RT | 100 | 0 |  | 2026-02-11 |  | 2026-03-06 |  | Retail | Super Structure
8790 | T-14-10th Floor Flat Area | Not Ready | Putty | 2026-01-10 | 2026-04-05 | Putty | 100 | 0 |  | 2026-02-12 |  | 2026-05-07
9211 | T-15-5th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-02-26 | 2026-05-04 | 2nd Coat Painting | 100 | 0 |  | 2026-02-12 |  | 2026-04-20
9263 | T-15-7th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-02-26 | 2026-05-04 | 2nd Coat Painting | 100 | 0 |  | 2026-02-12 |  | 2026-04-20
9293 | T-15-8th Floor Common Area | Not Ready | Putty | 2026-02-15 | 2026-03-26 | Putty | 100 | 0 |  | 2026-02-12 |  | 2026-03-24
10285 | T-21-6th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-03-17 | 2026-04-20 | 2nd Coat Painting | 100 | 0 |  | 2026-02-12 |  | 2026-03-17
11940 | T-18-10th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-05-05 | 2026-07-25 | 1st Coat Painting | 100 | 0 |  | 2026-02-12 |  | 2026-05-07
40408 | Tower A - Super Structure - Finishes & MEP - L62 to L63 | Not Ready | Partition Wall-Blockwork | 2026-01-20 | 2026-01-24 | Staircase Area | 100 | 0 |  | 2026-02-12 |  | 2026-02-17 |  | Tower A | Super Structure | L62
40411 | Tower A - Super Structure - Finishes & MEP - L63 to L64 | Not Ready | Partition Wall-Blockwork | 2026-01-20 | 2026-01-28 | Partition Walls | 100 | 0 |  | 2026-02-12 |  | 2026-02-19 |  | Tower A | Super Structure | L63
41801 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2026-01-13 | 2026-01-17 | Lobby Plastering | 100 | 0 |  | 2026-02-12 |  | 2026-02-18 |  | Tower A | Super Structure | L53 | Finishes | Lobby Plastering
41811 |  | Not Committed |  | 2026-01-13 | 2026-07-30 | L54-55 | 100 | 0 |  | 2026-02-12 |  | 2026-08-20
41811 |  | Not Committed |  | 2026-01-13 | 2026-07-30 | L54-55 | 100 | 0 |  | 2026-02-12 |  | 2026-08-20 |  |  |  |  | Finishes | Gypsum Plastering Works
41816 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2026-01-13 | 2026-01-15 | Lobby Blockwork | 100 | 0 |  | 2026-02-12 |  | 2026-02-16 |  | Tower A | Super Structure | L54 | Finishes | Blockwork
8766 | T-14-9th Floor Flat Area | Not Ready | Door | 2026-02-04 | 2026-02-26 | Door | 100 | 0 |  | 2026-02-13 |  | 2026-03-07
8791 | T-14-10th Floor Flat Area | Not Ready | Window | 2026-02-04 | 2026-02-26 | Window | 100 | 0 |  | 2026-02-13 |  | 2026-03-07
9359 | T-15-11th Floor Flat Area | Not Ready | Toilet flooring | 2026-02-23 | 2026-03-28 | Toilet flooring | 100 | 0 |  | 2026-02-13 |  | 2026-03-18
9876 | T-16-11th Floor Flat Area | Not Ready | Electrical DB Fixing | 2026-02-26 | 2026-03-14 | Electrical DB Fixing | 100 | 0 |  | 2026-02-13 |  | 2026-02-28
10173 | T-21-2nd Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-04-07 | 2026-06-29 | 2nd Coat Painting | 100 | 0 |  | 2026-02-13 |  | 2026-05-08
10378 | T-21-10th Floor Flat Area | Not Ready | Door | 2026-02-28 | 2026-03-21 | Door | 100 | 0 |  | 2026-02-13 |  | 2026-03-06
10403 | T-21-11th Floor Flat Area | Not Ready | Window | 2026-02-28 | 2026-03-21 | Window | 100 | 0 |  | 2026-02-13 |  | 2026-03-06
10804 | T-20-6th Floor Common Area | Not Ready | 1st Coat Painting | 2026-03-07 | 2026-03-30 | 1st Coat Painting | 100 | 0 |  | 2026-02-13 |  | 2026-03-05
11368 | T-19-8th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-03-07 | 2026-05-30 | 1st Coat Painting | 100 | 0 |  | 2026-02-13 |  | 2026-05-08
11394 | T-19-9th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-03-07 | 2026-05-30 | 1st Coat Painting | 100 | 0 |  | 2026-02-13 |  | 2026-05-08
11842 | T-18-6th Floor Common Area | Not Ready | Door-Shaft | 2026-04-25 | 2026-05-09 | Door-Shaft | 100 | 0 |  | 2026-02-13 |  | 2026-02-26
41248 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-01-23 | 2026-01-27 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-02-13 |  | 2026-02-17 |  | Tower A | Super Structure | L18
43073 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-01-21 | 2026-01-29 | Door & Window Frame work | 100 | 0 |  | 2026-02-13 |  | 2026-02-20 |  | Tower A | Super Structure | L55 | Finishes | Door & Window Frame work
45285 | Tower B - Super Structure - Core & Outer Slab L11-12 | Not Ready | RCC Works - Slab | 2025-12-09 | 2025-12-16 | Outer Slab_TA | 100 | 0 |  | 2026-02-13 |  | 2026-02-21 |  | Tower B | Super Structure | L11 | RCC Sub Structure | RCC Works - Slab
9786 | T-16-7th Floor Common Area | Not Ready | Flooring & skirting | 2026-03-06 | 2026-03-28 | Flooring & skirting | 100 | 0 |  | 2026-02-14 |  | 2026-03-12
10258 | T-21-5th Floor Common Area | Not Ready | 1st Coat Painting | 2026-03-17 | 2026-04-09 | 1st Coat Painting | 100 | 0 |  | 2026-02-14 |  | 2026-03-07
10829 | T-20-7th Floor Common Area | Not Ready | Window-Open Area | 2026-03-16 | 2026-03-23 | Window-Open Area | 100 | 0 |  | 2026-02-14 |  | 2026-02-21
11340 | T-19-7th Floor Flat Area | Not Ready | Door | 2026-03-16 | 2026-04-08 | Door | 100 | 0 |  | 2026-02-14 |  | 2026-03-08
11413 | T-19-10th Floor Flat Area | Not Ready | Toilet flooring | 2026-03-01 | 2026-04-03 | Toilet flooring | 100 | 0 |  | 2026-02-14 |  | 2026-03-21
43125 |  | Not Committed |  | 2026-01-22 | 2026-05-18 | Finishes after 1st Fix | 100 | 0 |  | 2026-02-14 |  | 2026-04-17
43126 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-01-22 | 2026-02-14 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-02-14 |  | 2026-03-10 |  | Tower A | Super Structure | L58 | Finishes | Blockwork
43967 |  | Not Committed |  | 2026-03-18 | 2026-05-28 | L7-15 | 100 | 0 |  | 2026-02-14 |  | 2026-04-27
43967 |  | Not Committed |  | 2026-03-18 | 2026-05-28 | L7-15 | 100 | 0 |  | 2026-02-14 |  | 2026-04-27
43968 | Tower A - Super Structure - Finishes & MEP - L7 to L15 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-03-18 | 2026-04-21 | Staircase Wall & Ceiling finishes | 100 | 0 |  | 2026-02-14 |  | 2026-03-23 |  | Tower A | Super Structure | L7
8665 | T-14-5th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-01-28 | 2026-04-04 | 2nd Coat Painting | 100 | 0 |  | 2026-02-15 |  | 2026-04-20
8717 | T-14-7th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-01-28 | 2026-04-04 | 2nd Coat Painting | 100 | 0 |  | 2026-02-15 |  | 2026-04-20
9855 | T-16-10th Floor Flat Area | Not Ready | Flooring & skirting | 2026-03-04 | 2026-04-17 | Flooring & skirting | 100 | 0 |  | 2026-02-15 |  | 2026-03-31
10230 | T-21-4th Floor Common Area | Not Ready | Door-Shaft | 2026-03-18 | 2026-04-01 | Door-Shaft | 100 | 0 |  | 2026-02-15 |  | 2026-02-28
8747 | T-14-8th Floor Common Area | Not Ready | Putty | 2026-01-14 | 2026-02-24 | Putty | 100 | 0 |  | 2026-02-16 |  | 2026-03-27
8832 | T-14-12th Floor Flat Area | Not Ready | Blockwork | 2026-01-10 | 2026-02-03 | Blockwork-Ledge Wall | 100 | 0 |  | 2026-02-16 |  | 2026-03-11
9312 | T-15-9th Floor Flat Area | Not Ready | Door | 2026-03-06 | 2026-03-30 | Door | 100 | 0 |  | 2026-02-16 |  | 2026-03-09
9337 | T-15-10th Floor Flat Area | Not Ready | Window | 2026-03-06 | 2026-03-30 | Window | 100 | 0 |  | 2026-02-16 |  | 2026-03-09
9362 | T-15-11th Floor Flat Area | Not Ready | Putty | 2026-02-26 | 2026-05-21 | Putty | 100 | 0 |  | 2026-02-16 |  | 2026-05-11
10335 | T-21-8th Floor Common Area | Not Ready | Window-Open Area | 2026-03-20 | 2026-03-29 | Window-Open Area | 100 | 0 |  | 2026-02-16 |  | 2026-02-24
10360 | T-21-9th Floor Common Area | Not Ready | Door-Shaft | 2026-03-24 | 2026-04-07 | Door-Shaft | 100 | 0 |  | 2026-02-16 |  | 2026-03-02
11365 | T-19-8th Floor Flat Area | Not Ready | Window | 2026-03-18 | 2026-04-10 | Window | 100 | 0 |  | 2026-02-16 |  | 2026-03-10
11960 | T-18-11th Floor Flat Area | Not Ready | Toilets False Celing | 2026-05-07 | 2026-06-09 | Toilets False Celing | 100 | 0 |  | 2026-02-16 |  | 2026-03-20
41234 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-01-27 | 2026-01-31 | Final Painting | 100 | 0 |  | 2026-02-16 |  | 2026-02-21 |  | Tower A | Super Structure | L17 | Finishes | Final Painting
41234 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-01-27 | 2026-01-31 | Final Painting | 100 | 0 |  | 2026-02-16 |  | 2026-02-21 |  | Tower A | Super Structure | L17 | Finishes | Final Painting
41234 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-01-27 | 2026-01-31 | Final Painting | 100 | 0 |  | 2026-02-16 |  | 2026-02-21 |  | Tower A | Super Structure | L17 | Finishes | Final Painting
41275 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-01-27 | 2026-02-03 | False Ceiling | 100 | 0 |  | 2026-02-16 |  | 2026-02-24 |  | Tower A | Super Structure | L20 | Finishes | False Ceiling
41303 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-01-27 | 2026-02-03 | HVAC Ducting | 100 | 0 |  | 2026-02-16 |  | 2026-02-24 |  | Tower A | Super Structure | L22 | MEP | HVAC Ducting
41817 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2026-01-16 | 2026-01-21 | Lobby Plastering | 100 | 0 |  | 2026-02-16 |  | 2026-02-21 |  | Tower A | Super Structure | L54 | Finishes | Lobby Plastering
41827 |  | Not Committed |  | 2026-01-16 | 2026-08-08 | L55-56 | 100 | 0 |  | 2026-02-16 |  | 2026-08-26
41827 |  | Not Committed |  | 2026-01-16 | 2026-08-08 | L55-56 | 100 | 0 |  | 2026-02-16 |  | 2026-08-26 |  |  |  |  | Finishes | Gypsum Plastering Works
41832 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2026-01-16 | 2026-01-19 | Lobby Blockwork | 100 | 0 |  | 2026-02-16 |  | 2026-02-19 |  | Tower A | Super Structure | L55 | Finishes | Blockwork
44573 |  | Not Committed |  | 2025-06-03 | 2025-10-30 | P3 to P4 | 100 | 0 |  | 2026-02-16 |  | 2026-06-20
44573 |  | Not Committed |  | 2025-06-03 | 2025-10-30 | P3 to P4 | 100 | 0 |  | 2026-02-16 |  | 2026-06-20
44573 |  | Not Committed |  | 2025-06-03 | 2025-10-30 | P3 to P4 | 100 | 0 |  | 2026-02-16 |  | 2026-06-20
44574 | NTA_Zone 2 - Super Structure - P3 to P4 | Not Ready | Finishes (Lobby & Floor Area) | 2025-06-03 | 2025-07-29 | VDF Flooring | 100 | 0 |  | 2026-02-16 |  | 2026-04-09 |  | NTA_Zone 2 | Super Structure
44574 | NTA_Zone 2 - Super Structure - P3 to P4 | Not Ready | Finishes (Lobby & Floor Area) | 2025-06-03 | 2025-07-29 | VDF Flooring | 100 | 0 |  | 2026-02-16 |  | 2026-04-09 |  | NTA_Zone 2 | Super Structure
45729 | Tower B - Super Structure - Finishes & MEP - B3 to L7 | Not Ready |  | 2025-12-11 | 2026-01-15 | Electrical Rising Mains | 100 | 0 |  | 2026-02-16 |  | 2026-03-24 |  | Tower B | Super Structure | B3
8809 | T-14-11th Floor Flat Area | Not Ready | Waterproofing | 2026-01-12 | 2026-02-16 | Waterproofing | 100 | 0 |  | 2026-02-17 |  | 2026-03-23
10696 | T-20-2nd Floor Common Area | Not Ready | Flooring & skirting | 2026-03-13 | 2026-04-05 | Flooring & skirting | 100 | 0 |  | 2026-02-17 |  | 2026-03-10
10723 | T-20-3rd Floor Common Area | Not Ready | Putty | 2026-03-13 | 2026-04-22 | Putty | 100 | 0 |  | 2026-02-17 |  | 2026-03-26
10926 | T-20-11th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-03-24 | 2026-06-16 | 1st Coat Painting | 100 | 0 |  | 2026-02-17 |  | 2026-05-12
10959 |  | Not Ready |  | 2026-03-24 | 2026-08-27 | Staircase-1 | 100 | 0 |  | 2026-02-17 |  | 2026-07-22
11416 | T-19-10th Floor Flat Area | Not Ready | Putty | 2026-03-04 | 2026-05-27 | Putty | 100 | 0 |  | 2026-02-17 |  | 2026-05-13
39256 | Retail - Sub structure - B3 to B2 - P4 | Not Ready | Retaining Wall RCC Works | 2025-09-08 | 2025-09-16 | Retaining Wall_lift 2 | 100 | 0 |  | 2026-02-17 |  | 2026-02-25 |  | Retail | Sub Structure | B3 | RCC Super Structure | Retaining Wall RCC Works
39256 | Retail - Sub structure - B3 to B2 - P4 | Not Ready | Retaining Wall RCC Works | 2025-09-08 | 2025-09-16 | Retaining Wall_lift 2 | 100 | 0 |  | 2026-02-17 |  | 2026-02-25 |  | Retail | Sub Structure | B3
40041 | Tower A - Super Structure - Core & Outer Slab L77-78 | Not Ready | RCC Works - Slab | 2026-01-09 | 2026-01-22 | Outer Slab_TA | 100 | 0 |  | 2026-02-17 |  | 2026-02-27 |  | Tower A | Super Structure | L77 | RCC Sub Structure | RCC Works - Slab
41249 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-01-28 | 2026-02-02 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-02-17 |  | 2026-02-23 |  | Tower A | Super Structure | L18 | MEP | Electrical
41260 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-01-28 | 2026-01-30 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-02-17 |  | 2026-02-20 |  | Tower A | Super Structure | L19 | MEP | FPS 2nd Fix - MEP & Finishes
41261 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-01-28 | 2026-02-02 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-02-17 |  | 2026-02-23 |  | Tower A | Super Structure | L19 | MEP | Electrical 2nd Fix - MEP & Finishes
41262 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-01-28 | 2026-02-04 | FAPA Device Fixing | 100 | 0 |  | 2026-02-17 |  | 2026-02-25 |  | Tower A | Super Structure | L19
41262 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-01-28 | 2026-02-04 | FAPA Device Fixing | 100 | 0 |  | 2026-02-17 |  | 2026-02-25 |  | Tower A | Super Structure | L19
41262 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-01-28 | 2026-02-04 | FAPA Device Fixing | 100 | 0 |  | 2026-02-17 |  | 2026-02-25 |  | Tower A | Super Structure | L19
41262 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-01-28 | 2026-02-04 | FAPA Device Fixing | 100 | 0 |  | 2026-02-17 |  | 2026-02-25 |  | Tower A | Super Structure | L19
41263 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-01-28 | 2026-01-30 | HVAC Grill Fixing | 100 | 0 |  | 2026-02-17 |  | 2026-02-20 |  | Tower A | Super Structure | L19 | MEP | HVAC Grill Fixing
41290 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-01-28 | 2026-02-07 | Flooring & Dado | 100 | 0 |  | 2026-02-17 |  | 2026-02-28 |  | Tower A | Super Structure | L21 | Finishes | Flooring & Dado
43002 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-03-20 | 2026-04-06 | Flooring & Dado works | 100 | 0 |  | 2026-02-17 |  | 2026-03-07 |  | Tower A | Super Structure | L51 | Finishes | Flooring & Dado
44103 | Tower A - Super Structure - Finishes & MEP - L48 to L53 | Not Ready | Façade Works - MEP & Finishes | 2026-03-20 | 2026-03-31 | Accessories & Alignment | 100 | 0 |  | 2026-02-17 |  | 2026-02-28 |  | Tower A | Super Structure | L48 | Façade | Façade Works
44103 | Tower A - Super Structure - Finishes & MEP - L48 to L53 | Not Ready | Façade Works - MEP & Finishes | 2026-03-20 | 2026-03-31 | Accessories & Alignment | 100 | 0 |  | 2026-02-17 |  | 2026-02-28 |  | Tower A | Super Structure | L48
45436 | Tower B - Super Structure - Finishes & MEP - L7 to L8 | Not Ready | Partition Wall-Blockwork | 2025-12-12 | 2025-12-17 | Staircase Area | 100 | 0 |  | 2026-02-17 |  | 2026-02-23 |  | Tower B | Super Structure | L7
8798 | T-14-11th Floor Common Area | Not Ready | Flooring & skirting | 2026-01-21 | 2026-02-13 | Flooring & skirting | 100 | 0 |  | 2026-02-18 |  | 2026-03-12
8836 | T-14-12th Floor Flat Area | Not Ready | Electrical DB Fixing | 2026-01-12 | 2026-01-31 | Electrical DB Fixing | 100 | 0 |  | 2026-02-18 |  | 2026-03-08
9873 | T-16-11th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2026-03-04 | 2026-03-26 | Plumbing Pipe Line | 100 | 0 |  | 2026-02-18 |  | 2026-03-15
10854 | T-20-8th Floor Common Area | Not Ready | Door-Shaft | 2026-03-19 | 2026-04-02 | Door-Shaft | 100 | 0 |  | 2026-02-18 |  | 2026-03-03
11347 | T-19-7th Floor Common Area | Not Ready | Putty | 2026-03-06 | 2026-04-15 | Putty | 100 | 0 |  | 2026-02-18 |  | 2026-03-28
11886 | T-18-8th Floor Flat Area | Not Ready | Door | 2026-04-26 | 2026-05-19 | Door | 100 | 0 |  | 2026-02-18 |  | 2026-03-13
40055 |  | Not Committed |  | 2026-01-27 | 2026-05-19 | CTU Elevators | 100 | 0 |  | 2026-02-18 |  | 2026-06-12
40056 | Tower A - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2026-01-27 | 2026-02-03 | Plumb check & door centre line by Lift agency for lobby blockwork | 100 | 0 |  | 2026-02-18 |  | 2026-02-26 |  | Tower A | Super Structure
40056 | Tower A - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2026-01-27 | 2026-02-03 | Plumb check & door centre line by Lift agency for lobby blockwork | 100 | 0 |  | 2026-02-18 |  | 2026-02-26 |  | Tower A | Super Structure
40056 | Tower A - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2026-01-27 | 2026-02-03 | Plumb check & door centre line by Lift agency for lobby blockwork | 100 | 0 |  | 2026-02-18 |  | 2026-02-26 |  | Tower A | Super Structure
40057 | Tower A - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2026-01-27 | 2026-02-11 | Shaft clearance & White Wash up to LMR | 100 | 0 |  | 2026-02-18 |  | 2026-03-07 |  | Tower A | Super Structure
40057 | Tower A - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2026-01-27 | 2026-02-11 | Shaft clearance & White Wash up to LMR | 100 | 0 |  | 2026-02-18 |  | 2026-03-07 |  | Tower A | Super Structure
40062 | Tower A - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2026-01-27 | 2026-04-07 | LMR Works | 100 | 0 |  | 2026-02-18 |  | 2026-04-30 |  | Tower A | Super Structure
40062 | Tower A - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2026-01-27 | 2026-04-07 | LMR Works | 100 | 0 |  | 2026-02-18 |  | 2026-04-30 |  | Tower A | Super Structure
40077 |  | Not Committed |  | 2026-01-27 | 2026-07-02 | Other Elevators | 100 | 0 |  | 2026-02-18 |  | 2026-07-29
40078 | Tower A - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2026-01-27 | 2026-03-14 | Crash deck removal & De-commission of temporary LMR | 100 | 0 |  | 2026-02-18 |  | 2026-04-07 |  | Tower A | Super Structure
40461 |  | Not Committed |  | 2026-01-14 | 2026-03-12 | Above Terrace Masonry | 100 | 0 |  | 2026-02-18 |  | 2026-04-10
40465 | Tower A - Super Structure - Finishes & MEP - Above Terrace | Not Ready | Partition Wall-Blockwork | 2026-01-14 | 2026-02-18 | Staircase Area | 100 | 0 |  | 2026-02-18 |  | 2026-03-26 |  | Tower A | Super Structure
43190 |  | Not Committed |  | 2026-01-27 | 2026-10-06 | L62-63 | 100 | 0 |  | 2026-02-18 |  | 2026-09-14
43190 |  | Not Committed |  | 2026-01-27 | 2026-10-06 | L62-63 | 100 | 0 |  | 2026-02-18 |  | 2026-09-14 |  |  |  |  | Finishes | Gypsum Plastering Works
43191 |  | Not Committed |  | 2026-01-27 | 2026-02-24 | MEP 1st Fixes | 100 | 0 |  | 2026-02-18 |  | 2026-03-19
43192 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-01-27 | 2026-02-03 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-02-18 |  | 2026-02-25 |  | Tower A | Super Structure | L62 | MEP | FPS 1st Fix - MEP & Finishes
43193 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-01-27 | 2026-01-31 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-02-18 |  | 2026-02-23 |  | Tower A | Super Structure | L62 | MEP | Electrical 1st Fixes
43194 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-01-27 | 2026-02-03 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-02-18 |  | 2026-02-25 |  | Tower A | Super Structure | L62
43195 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-01-27 | 2026-02-12 | Wet Area Waterproofing | 100 | 0 |  | 2026-02-18 |  | 2026-03-07 |  | Tower A | Super Structure | L62
9344 | T-15-11th Floor Common Area | Not Ready | Flooring & skirting | 2026-02-26 | 2026-03-19 | Flooring & skirting | 100 | 0 |  | 2026-02-19 |  | 2026-03-12
9782 | T-16-7th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-03-14 | 2026-06-06 | 1st Coat Painting | 100 | 0 |  | 2026-02-19 |  | 2026-05-14
10424 |  | Not Ready |  | 2026-03-24 | 2026-11-13 | Lift lobby | 100 | 0 |  | 2026-02-19 |  | 2026-10-11
10454 |  | Not Ready |  | 2026-03-24 | 2026-08-27 | Staircase-2 | 100 | 0 |  | 2026-02-19 |  | 2026-07-24
11919 | T-18-9th Floor Common Area | Not Ready | Putty | 2026-05-07 | 2026-06-14 | Putty | 100 | 0 |  | 2026-02-19 |  | 2026-03-28
41833 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2026-01-20 | 2026-01-24 | Lobby Plastering | 100 | 0 |  | 2026-02-19 |  | 2026-02-25 |  | Tower A | Super Structure | L55 | Finishes | Lobby Plastering
41843 |  | Not Committed |  | 2026-01-20 | 2026-08-22 | L56-57 | 100 | 0 |  | 2026-02-19 |  | 2026-09-01
41843 |  | Not Committed |  | 2026-01-20 | 2026-08-22 | L56-57 | 100 | 0 |  | 2026-02-19 |  | 2026-09-01 |  |  |  |  | Finishes | Gypsum Plastering Works
41848 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2026-01-20 | 2026-01-22 | Lobby Blockwork | 100 | 0 |  | 2026-02-19 |  | 2026-02-23 |  | Tower A | Super Structure | L56 | Finishes | Blockwork
43160 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-01-28 | 2026-02-07 | Cement Plastering in wet areas | 100 | 0 |  | 2026-02-19 |  | 2026-03-02 |  | Tower A | Super Structure | L60
9340 | T-15-10th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-03-01 | 2026-05-24 | 1st Coat Painting | 100 | 0 |  | 2026-02-20 |  | 2026-05-15
9877 | T-16-11th Floor Flat Area | Not Ready | Plastering | 2026-03-06 | 2026-04-20 | Plastering-Gypsum | 100 | 0 |  | 2026-02-20 |  | 2026-04-06
10150 | T-21-1st Floor Common Area | Not Ready | Flooring & skirting | 2026-03-24 | 2026-04-16 | Flooring & skirting | 100 | 0 |  | 2026-02-20 |  | 2026-03-14
10177 | T-21-2nd Floor Common Area | Not Ready | Putty | 2026-03-24 | 2026-05-03 | Putty | 100 | 0 |  | 2026-02-20 |  | 2026-03-30
10425 | T-21-Lift Lobby | Not Ready |  | 2026-03-24 | 2026-04-10 | 12F | 100 | 0 |  | 2026-02-20 |  | 2026-03-07
11762 | T-18-3rd Floor Common Area | Not Ready | Flooring & skirting | 2026-04-30 | 2026-05-23 | Flooring & skirting | 100 | 0 |  | 2026-02-20 |  | 2026-03-12
11789 | T-18-4th Floor Common Area | Not Ready | Putty | 2026-04-30 | 2026-06-09 | Putty | 100 | 0 |  | 2026-02-20 |  | 2026-04-01
11911 | T-18-9th Floor Flat Area | Not Ready | Window | 2026-04-28 | 2026-05-21 | Window | 100 | 0 |  | 2026-02-20 |  | 2026-03-17
40412 | Tower A - Super Structure - Finishes & MEP - L63 to L64 | Not Ready | Partition Wall-Blockwork | 2026-01-29 | 2026-02-03 | Staircase Area | 100 | 0 |  | 2026-02-20 |  | 2026-02-25 |  | Tower A | Super Structure | L63
40415 | Tower A - Super Structure - Finishes & MEP - L64 to L65 | Not Ready | Partition Wall-Blockwork | 2026-01-29 | 2026-02-05 | Partition Walls | 100 | 0 |  | 2026-02-20 |  | 2026-02-27 |  | Tower A | Super Structure | L64
41264 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-01-31 | 2026-02-03 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-02-20 |  | 2026-02-24 |  | Tower A | Super Structure | L19
43959 | Tower A - Super Structure - Finishes & MEP - B3 to GF | Not Ready | Staircase Finishes - MEP & Finishes | 2026-03-24 | 2026-04-03 | Staircase Light Fixtures & Devices fixing | 100 | 0 |  | 2026-02-20 |  | 2026-03-05 |  | Tower A | Super Structure | B3
43969 | Tower A - Super Structure - Finishes & MEP - L7 to L15 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-03-24 | 2026-05-15 | Staircase Flooring | 100 | 0 |  | 2026-02-20 |  | 2026-04-15 |  | Tower A | Super Structure | L7 | Finishes | Staircase Flooring
9360 | T-15-11th Floor Flat Area | Not Ready | Toilets False Celing | 2026-03-03 | 2026-04-06 | Toilets False Celing | 100 | 0 |  | 2026-02-21 |  | 2026-03-27
9734 | T-16-5th Floor Common Area | Not Ready | Flooring & skirting | 2026-03-11 | 2026-04-03 | Flooring & skirting | 100 | 0 |  | 2026-02-21 |  | 2026-03-15
9754 | T-16-6th Floor Flat Area | Not Ready | Door | 2026-03-24 | 2026-04-16 | Door | 100 | 0 |  | 2026-02-21 |  | 2026-03-14
9761 | T-16-6th Floor Common Area | Not Ready | Putty | 2026-03-11 | 2026-04-20 | Putty | 100 | 0 |  | 2026-02-21 |  | 2026-04-02
10441 | T-21-Staircase 1 | Not Ready |  | 2026-03-24 | 2026-04-04 | 12F-11F | 100 | 0 |  | 2026-02-21 |  | 2026-03-05
10455 | T-21-Staircase 2 | Not Ready |  | 2026-03-24 | 2026-04-04 | TF-12F | 100 | 0 |  | 2026-02-21 |  | 2026-03-05
10931 | T-20-11th Floor Common Area | Not Ready | Putty | 2026-03-31 | 2026-05-09 | Putty | 100 | 0 |  | 2026-02-21 |  | 2026-04-03
40131 | Tower A - Super Structure - Finishes & MEP - MEP Service Floors | Not Ready |  | 2026-01-17 | 2026-06-10 | Outdoor Units Installations | 100 | 0 |  | 2026-02-21 |  | 2026-07-15 |  | Tower A | Super Structure
40132 | Tower A - Super Structure - Finishes & MEP - MEP Service Floors | Not Ready |  | 2026-01-17 | 2026-07-16 | Refrigeration & Condensation Piping Works | 100 | 0 |  | 2026-02-21 |  | 2026-08-26 |  | Tower A | Super Structure
40535 | Tower A - Super Structure - Finishes & MEP - L61 to L62 | Not Ready | Gypsum Plastering Works | 2026-01-30 | 2026-02-16 | L61-62 | 100 | 0 |  | 2026-02-21 |  | 2026-03-11 |  | Tower A | Super Structure | L61 | Finishes | Gypsum Plastering Works
40535 | Tower A - Super Structure - Finishes & MEP - L61 to L62 | Not Ready | Gypsum Plastering Works | 2026-01-30 | 2026-02-16 | L61-62 | 100 | 0 |  | 2026-02-21 |  | 2026-03-11 |  | Tower A | Super Structure | L61
43091 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-01-30 | 2026-02-06 | Door & Window Frame work | 100 | 0 |  | 2026-02-21 |  | 2026-02-28 |  | Tower A | Super Structure | L56 | Finishes | Door & Window Frame work
45286 |  | Not Ready |  | 2025-12-17 | 2026-01-01 | L12-13 | 100 | 0 |  | 2026-02-21 |  | 2026-03-10
45286 |  | Not Ready |  | 2025-12-17 | 2026-01-01 | L12-13 | 100 | 0 |  | 2026-02-21 |  | 2026-03-10 |  |  |  |  | Finishes | Gypsum Plastering Works
45287 | Tower B - Super Structure - Core & Outer Slab L12-13 | Not Ready | RCC Works - Vertical | 2025-12-17 | 2025-12-29 | Outer Columns_TA | 100 | 0 |  | 2026-02-21 |  | 2026-03-06 |  | Tower B | Super Structure | L12 | RCC Sub Structure | RCC Works - Vertical
45396 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 | Not Ready | Partition Wall-Blockwork | 2025-04-16 | 2025-04-26 | Staircase Area | 100 | 0 |  | 2026-02-21 |  | 2026-03-05 |  | Tower B | Sub Structure | B3
45441 |  | Not Committed |  | 2025-12-17 | 2026-01-17 | L9-10 | 100 | 0 |  | 2026-02-21 |  | 2026-03-26
45441 |  | Not Committed |  | 2025-12-17 | 2026-01-17 | L9-10 | 100 | 0 |  | 2026-02-21 |  | 2026-03-26 |  |  |  |  | Finishes | Gypsum Plastering Works
45442 | Tower B - Super Structure - Finishes & MEP - L9 to L10 | Not Ready | Partition Wall-Blockwork | 2025-12-17 | 2026-01-03 | De-shuttering & Area clearance | 100 | 0 |  | 2026-02-21 |  | 2026-03-12 |  | Tower B | Super Structure | L9
8815 | T-14-11th Floor Flat Area | Not Ready | Flooring & skirting | 2026-01-19 | 2026-03-04 | Flooring & skirting | 100 | 0 |  | 2026-02-22 |  | 2026-04-10
10777 | T-20-5th Floor Common Area | Not Ready | Window-Open Area | 2026-03-21 | 2026-03-30 | Window-Open Area | 100 | 0 |  | 2026-02-22 |  | 2026-02-26
10830 | T-20-7th Floor Common Area | Not Ready | 1st Coat Painting | 2026-03-23 | 2026-04-15 | 1st Coat Painting | 100 | 0 |  | 2026-02-22 |  | 2026-03-16
11414 | T-19-10th Floor Flat Area | Not Ready | Toilets False Celing | 2026-03-10 | 2026-04-13 | Toilets False Celing | 100 | 0 |  | 2026-02-22 |  | 2026-03-28
11435 | T-19-11th Floor Flat Area | Not Ready | Waterproofing | 2026-03-06 | 2026-04-09 | Waterproofing | 100 | 0 |  | 2026-02-22 |  | 2026-03-29
8696 | T-14-6th Floor Common Area | Not Ready | Door-Shaft | 2026-01-21 | 2026-02-04 | Door-Shaft | 100 | 0 |  | 2026-02-23 |  | 2026-03-09
8792 | T-14-10th Floor Flat Area | Not Ready | Door | 2026-02-15 | 2026-03-09 | Door | 100 | 0 |  | 2026-02-23 |  | 2026-03-17
8817 | T-14-11th Floor Flat Area | Not Ready | Window | 2026-02-15 | 2026-03-09 | Window | 100 | 0 |  | 2026-02-23 |  | 2026-03-17
8833 | T-14-12th Floor Flat Area | Not Ready | Plumbing Pipe Line | 2026-01-19 | 2026-02-11 | Plumbing Pipe Line | 100 | 0 |  | 2026-02-23 |  | 2026-03-20
9242 | T-15-6th Floor Common Area | Not Ready | Door-Shaft | 2026-02-20 | 2026-03-05 | Door-Shaft | 100 | 0 |  | 2026-02-23 |  | 2026-03-08
9779 | T-16-7th Floor Flat Area | Not Ready | Window | 2026-03-27 | 2026-04-18 | Window | 100 | 0 |  | 2026-02-23 |  | 2026-03-16
10404 | T-21-11th Floor Flat Area | Not Ready | Door | 2026-03-11 | 2026-04-02 | Door | 100 | 0 |  | 2026-02-23 |  | 2026-03-16
41250 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-02-03 | 2026-02-07 | Final Painting | 100 | 0 |  | 2026-02-23 |  | 2026-02-28 |  | Tower A | Super Structure | L18 | Finishes | Final Painting
41250 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-02-03 | 2026-02-07 | Final Painting | 100 | 0 |  | 2026-02-23 |  | 2026-02-28 |  | Tower A | Super Structure | L18 | Finishes | Final Painting
41250 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-02-03 | 2026-02-07 | Final Painting | 100 | 0 |  | 2026-02-23 |  | 2026-02-28 |  | Tower A | Super Structure | L18 | Finishes | Final Painting
41291 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-02-03 | 2026-02-10 | False Ceiling | 100 | 0 |  | 2026-02-23 |  | 2026-03-04 |  | Tower A | Super Structure | L21 | Finishes | False Ceiling
41319 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-02-03 | 2026-02-10 | HVAC Ducting | 100 | 0 |  | 2026-02-23 |  | 2026-03-04 |  | Tower A | Super Structure | L23 | MEP | HVAC Ducting
41849 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2026-01-23 | 2026-01-29 | Lobby Plastering | 100 | 0 |  | 2026-02-23 |  | 2026-02-28 |  | Tower A | Super Structure | L56 | Finishes | Lobby Plastering
41859 |  | Not Committed |  | 2026-01-23 | 2026-08-31 | L57-58 | 100 | 0 |  | 2026-02-23 |  | 2026-09-07
41859 |  | Not Committed |  | 2026-01-23 | 2026-08-31 | L57-58 | 100 | 0 |  | 2026-02-23 |  | 2026-09-07 |  |  |  |  | Finishes | Gypsum Plastering Works
41864 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2026-01-23 | 2026-01-27 | Lobby Blockwork | 100 | 0 |  | 2026-02-23 |  | 2026-02-26 |  | Tower A | Super Structure | L57 | Finishes | Blockwork
43020 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-03-26 | 2026-04-11 | Flooring & Dado works | 100 | 0 |  | 2026-02-23 |  | 2026-03-13 |  | Tower A | Super Structure | L52 | Finishes | Flooring & Dado
43143 |  | Not Committed |  | 2026-01-31 | 2026-05-12 | Finishes after 1st Fix | 100 | 0 |  | 2026-02-23 |  | 2026-04-13
43144 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-01-31 | 2026-02-23 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-02-23 |  | 2026-03-18 |  | Tower A | Super Structure | L59 | Finishes | Blockwork
44106 | Tower A - Super Structure - Finishes & MEP - L53 to L58 | Not Ready | Façade Works - MEP & Finishes | 2026-03-26 | 2026-04-06 | DGU Assembly Installation | 100 | 0 |  | 2026-02-23 |  | 2026-03-07 |  | Tower A | Super Structure | L53 | Façade | Façade Works
44107 | Tower A - Super Structure - Finishes & MEP - L53 to L58 | Not Ready | Façade Works - MEP & Finishes | 2026-03-26 | 2026-04-17 | Installation of highly reflective metal sheet | 100 | 0 |  | 2026-02-23 |  | 2026-03-19 |  | Tower A | Super Structure | L53 | Façade | Façade Works
44108 | Tower A - Super Structure - Finishes & MEP - L53 to L58 | Not Ready | Façade Works - MEP & Finishes | 2026-03-26 | 2026-04-06 | Fixing of Backlit Laminated Glass assembly & ACP Panels | 100 | 0 |  | 2026-02-23 |  | 2026-03-07 |  | Tower A | Super Structure | L53 | Façade | Façade Works
44109 | Tower A - Super Structure - Finishes & MEP - L53 to L58 | Not Ready | Façade Works - MEP & Finishes | 2026-03-26 | 2026-04-06 | Fixing of Louvers | 100 | 0 |  | 2026-02-23 |  | 2026-03-07 |  | Tower A | Super Structure | L53 | Façade | Façade Works
44109 | Tower A - Super Structure - Finishes & MEP - L53 to L58 | Not Ready | Façade Works - MEP & Finishes | 2026-03-26 | 2026-04-06 | Fixing of Louvers | 100 | 0 |  | 2026-02-23 |  | 2026-03-07 |  | Tower A | Super Structure | L53
46655 |  | Not Committed |  | 2025-12-18 | 2027-01-23 | L7-8 | 100 | 0 |  | 2026-02-23 |  | 2027-04-02
46655 |  | Not Committed |  | 2025-12-18 | 2027-01-23 | L7-8 | 100 | 0 |  | 2026-02-23 |  | 2027-04-02 |  |  |  |  | Finishes | Gypsum Plastering Works
46656 |  | Not Committed |  | 2025-12-18 | 2026-01-24 | MEP 1st Fixes | 100 | 0 |  | 2026-02-23 |  | 2026-04-02
46657 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2025-12-18 | 2025-12-26 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-02-23 |  | 2026-03-04 |  | Tower B | Super Structure | L7 | MEP | FPS 1st Fix - MEP & Finishes
46658 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2025-12-18 | 2025-12-23 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-02-23 |  | 2026-02-28 |  | Tower B | Super Structure | L7 | MEP | Electrical 1st Fixes
46659 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2025-12-18 | 2025-12-26 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-02-23 |  | 2026-03-04 |  | Tower B | Super Structure | L7
48187 | Retail - Super structure - R1 to CH00 - P2 | Not Ready |  | 2025-11-03 | 2025-11-19 | Slab_RT | 100 | 0 |  | 2026-02-23 |  | 2026-03-12 |  | Retail | Super Structure |  | RCC Sub Structure | RCC Works - Slab
48187 | Retail - Super structure - R1 to CH00 - P2 | Not Ready |  | 2025-11-03 | 2025-11-19 | Slab_RT | 100 | 0 |  | 2026-02-23 |  | 2026-03-12 |  | Retail | Super Structure
48195 | Retail - Super structure - R1 to CH00 - P4 | Not Ready |  | 2025-11-03 | 2025-11-26 | Slab_RT | 100 | 0 |  | 2026-02-23 |  | 2026-03-19 |  | Retail | Super Structure |  | RCC Sub Structure | RCC Works - Slab
48195 | Retail - Super structure - R1 to CH00 - P4 | Not Ready |  | 2025-11-03 | 2025-11-26 | Slab_RT | 100 | 0 |  | 2026-02-23 |  | 2026-03-19 |  | Retail | Super Structure
11268 | T-19-4th Floor Common Area | Not Ready | Flooring & skirting | 2026-03-12 | 2026-04-03 | Flooring & skirting | 100 | 0 |  | 2026-02-24 |  | 2026-03-19
11295 | T-19-5th Floor Common Area | Not Ready | Putty | 2026-03-12 | 2026-04-20 | Putty | 100 | 0 |  | 2026-02-24 |  | 2026-04-03
41265 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-02-04 | 2026-02-09 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-02-24 |  | 2026-03-02 |  | Tower A | Super Structure | L19 | MEP | Electrical
41276 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-02-04 | 2026-02-06 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-02-24 |  | 2026-02-27 |  | Tower A | Super Structure | L20 | MEP | FPS 2nd Fix - MEP & Finishes
41277 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-02-04 | 2026-02-09 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-02-24 |  | 2026-03-02 |  | Tower A | Super Structure | L20 | MEP | Electrical 2nd Fix - MEP & Finishes
41278 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-02-04 | 2026-02-11 | FAPA Device Fixing | 100 | 0 |  | 2026-02-24 |  | 2026-03-05 |  | Tower A | Super Structure | L20
41278 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-02-04 | 2026-02-11 | FAPA Device Fixing | 100 | 0 |  | 2026-02-24 |  | 2026-03-05 |  | Tower A | Super Structure | L20
41278 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-02-04 | 2026-02-11 | FAPA Device Fixing | 100 | 0 |  | 2026-02-24 |  | 2026-03-05 |  | Tower A | Super Structure | L20
41278 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-02-04 | 2026-02-11 | FAPA Device Fixing | 100 | 0 |  | 2026-02-24 |  | 2026-03-05 |  | Tower A | Super Structure | L20
41279 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-02-04 | 2026-02-06 | HVAC Grill Fixing | 100 | 0 |  | 2026-02-24 |  | 2026-02-27 |  | Tower A | Super Structure | L20 | MEP | HVAC Grill Fixing
41306 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-02-04 | 2026-02-14 | Flooring & Dado | 100 | 0 |  | 2026-02-24 |  | 2026-03-09 |  | Tower A | Super Structure | L22 | Finishes | Flooring & Dado
45439 | Tower B - Super Structure - Finishes & MEP - L8 to L9 | Not Ready | Partition Wall-Blockwork | 2025-12-19 | 2025-12-27 | Partition Walls | 100 | 0 |  | 2026-02-24 |  | 2026-03-05 |  | Tower B | Super Structure | L8
8837 | T-14-12th Floor Flat Area | Not Ready | Plastering | 2026-01-21 | 2026-03-06 | Plastering-Gypsum | 100 | 0 |  | 2026-02-25 |  | 2026-04-09
9852 | T-16-10th Floor Flat Area | Not Ready | Dado | 2026-03-14 | 2026-04-12 | Dado | 100 | 0 |  | 2026-02-25 |  | 2026-03-26
9874 | T-16-11th Floor Flat Area | Not Ready | Plastering | 2026-03-11 | 2026-04-03 | Plastering-Cement | 100 | 0 |  | 2026-02-25 |  | 2026-03-19
10336 | T-21-8th Floor Common Area | Not Ready | 1st Coat Painting | 2026-03-29 | 2026-04-20 | 1st Coat Painting | 100 | 0 |  | 2026-02-25 |  | 2026-03-19
10469 |  | Not Ready |  | 2026-03-30 | 2026-09-23 | External Finishes | 100 | 0 |  | 2026-02-25 |  | 2026-08-22
10470 |  | Not Ready |  | 2026-03-30 | 2026-09-23 | External Painting | 100 | 0 |  | 2026-02-25 |  | 2026-08-22
10471 | T-21- Elevation A | Not Ready |  | 2026-03-30 | 2026-06-21 | Elevation-A | 100 | 0 |  | 2026-02-25 |  | 2026-05-20
10960 | T-20-Staircase 1 | Not Ready |  | 2026-03-24 | 2026-04-05 | TF-12F | 100 | 0 |  | 2026-02-25 |  | 2026-03-09
11398 | T-19-9th Floor Common Area | Not Ready | Flooring & skirting | 2026-03-17 | 2026-04-09 | Flooring & skirting | 100 | 0 |  | 2026-02-25 |  | 2026-03-19
39257 | Retail - Sub structure - B3 to B2 | Not Ready | RCC Works - Vertical | 2025-09-16 | 2025-10-17 | Columns/ Walls_NTA | 100 | 0 |  | 2026-02-25 |  | 2026-03-27 |  | Retail | Sub Structure | B3 | RCC Sub Structure | RCC Works - Vertical
39257 | Retail - Sub structure - B3 to B2 | Not Ready | RCC Works - Vertical | 2025-09-16 | 2025-10-17 | Columns/ Walls_NTA | 100 | 0 |  | 2026-02-25 |  | 2026-03-27 |  | Retail | Sub Structure | B3
9338 | T-15-10th Floor Flat Area | Not Ready | Door | 2026-03-17 | 2026-04-09 | Door | 100 | 0 |  | 2026-02-26 |  | 2026-03-20
9363 | T-15-11th Floor Flat Area | Not Ready | Window | 2026-03-17 | 2026-04-09 | Window | 100 | 0 |  | 2026-02-26 |  | 2026-03-20
11366 | T-19-8th Floor Flat Area | Not Ready | Door | 2026-03-30 | 2026-04-21 | Door | 100 | 0 |  | 2026-02-26 |  | 2026-03-19
11970 | T-18-11th Floor Common Area | Not Ready | Flooring & skirting | 2026-05-18 | 2026-06-09 | Flooring & skirting | 100 | 0 |  | 2026-02-26 |  | 2026-03-23
39209 |  | Not Ready |  | 2025-04-14 | 2025-05-30 | Installation of Electrical High Side Equipments (B01) | 100 | 0 |  | 2026-02-26 |  | 2026-04-15
39223 |  | Not Ready |  | 2025-08-18 | 2025-09-26 | Installation of Electrical High Side Equipments (B01) | 100 | 0 |  | 2026-02-26 |  | 2026-04-08
40113 | Tower A - Super Structure - Finishes & MEP - Sub Station | Not Ready | Sub Station - High Side Services | 2026-02-28 | 2026-03-12 | Cable support bracket work at Trench | 100 | 0 |  | 2026-02-26 |  | 2026-03-10 |  | Tower A | Super Structure
41865 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2026-01-28 | 2026-02-02 | Lobby Plastering | 100 | 0 |  | 2026-02-26 |  | 2026-03-05 |  | Tower A | Super Structure | L57 | Finishes | Lobby Plastering
41875 |  | Not Committed |  | 2026-01-28 | 2026-09-05 | L58-59 | 100 | 0 |  | 2026-02-26 |  | 2026-09-14
41875 |  | Not Committed |  | 2026-01-28 | 2026-09-05 | L58-59 | 100 | 0 |  | 2026-02-26 |  | 2026-09-14 |  |  |  |  | Finishes | Gypsum Plastering Works
41880 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2026-01-28 | 2026-01-30 | Lobby Blockwork | 100 | 0 |  | 2026-02-26 |  | 2026-03-02 |  | Tower A | Super Structure | L58 | Finishes | Blockwork
42067 |  | Not Committed |  | 2026-02-04 | 2026-11-23 | L70-71 | 100 | 0 |  | 2026-02-26 |  | 2026-11-30
42067 |  | Not Committed |  | 2026-02-04 | 2026-11-23 | L70-71 | 100 | 0 |  | 2026-02-26 |  | 2026-11-30 |  |  |  |  | Finishes | Gypsum Plastering Works
42072 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2026-02-04 | 2026-02-06 | Lobby Blockwork | 100 | 0 |  | 2026-02-26 |  | 2026-03-02 |  | Tower A | Super Structure | L70 | Finishes | Blockwork
43208 |  | Not Committed |  | 2026-02-04 | 2026-09-26 | L63-64 (MEP Transfer) | 100 | 0 |  | 2026-02-26 |  | 2026-09-05
43209 |  | Not Committed |  | 2026-02-04 | 2026-02-17 | MEP 1st Fixes | 100 | 0 |  | 2026-02-26 |  | 2026-03-12
43210 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-02-04 | 2026-02-11 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-02-26 |  | 2026-03-06 |  | Tower A | Super Structure | L63 | MEP | FPS 1st Fix - MEP & Finishes
43211 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-02-04 | 2026-02-09 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-02-26 |  | 2026-03-04 |  | Tower A | Super Structure | L63 | MEP | Electrical 1st Fixes
43212 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-02-04 | 2026-02-11 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-02-26 |  | 2026-03-06 |  | Tower A | Super Structure | L63
43213 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-02-04 | 2026-02-04 | Wet Area Waterproofing | 100 | 0 |  | 2026-02-26 |  | 2026-02-26 |  | Tower A | Super Structure | L63
43963 | Tower A - Super Structure - Finishes & MEP - GF to L7 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-03-30 | 2026-04-27 | Staircase Window | 100 | 0 |  | 2026-02-26 |  | 2026-03-28 |  | Tower A | Super Structure | GF
43965 | Tower A - Super Structure - Finishes & MEP - GF to L7 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-03-30 | 2026-04-09 | Staircase cabling | 100 | 0 |  | 2026-02-26 |  | 2026-03-11 |  | Tower A | Super Structure | GF
9319 | T-15-9th Floor Common Area | Not Ready | Putty | 2026-03-03 | 2026-04-11 | Putty | 100 | 0 |  | 2026-02-27 |  | 2026-04-07
9889 | T-16-11th Floor Common Area | Not Ready | Plastering | 2026-03-13 | 2026-04-16 | Plastering-Gypsum | 100 | 0 |  | 2026-02-27 |  | 2026-04-02
10778 | T-20-5th Floor Common Area | Not Ready | 1st Coat Painting | 2026-03-30 | 2026-04-21 | 1st Coat Painting | 100 | 0 |  | 2026-02-27 |  | 2026-03-20
11441 | T-19-11th Floor Flat Area | Not Ready | Flooring & skirting | 2026-03-12 | 2026-04-25 | Flooring & skirting | 100 | 0 |  | 2026-02-27 |  | 2026-04-13
11843 | T-18-6th Floor Common Area | Not Ready | Window-Open Area | 2026-05-09 | 2026-05-16 | Window-Open Area | 100 | 0 |  | 2026-02-27 |  | 2026-03-06
11868 | T-18-7th Floor Common Area | Not Ready | Door-Shaft | 2026-05-12 | 2026-05-25 | Door-Shaft | 100 | 0 |  | 2026-02-27 |  | 2026-03-12
39123 |  | Not Committed |  | 2026-01-23 |  | TA_Completion of Top Slab | 100 | 0 |  | 2026-02-27
40033 | Tower A - Super Structure - Core & Outer Slab Above Terrace | Not Ready | RCC Works - Slab | 2026-01-23 | 2026-02-27 | Over Head Tanks | 100 | 0 |  | 2026-02-27 |  | 2026-03-30 |  | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Slab
40033 | Tower A - Super Structure - Core & Outer Slab Above Terrace | Not Ready | RCC Works - Slab | 2026-01-23 | 2026-02-27 | Over Head Tanks | 100 | 0 |  | 2026-02-27 |  | 2026-03-30 |  | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
40035 | Tower A - Super Structure - Core & Outer Slab Above Terrace | Not Ready | RCC Works - Vertical | 2026-01-23 | 2026-02-27 | Miscellaneous - Parapet, Architectural, MEP Utility | 100 | 0 |  | 2026-02-27 |  | 2026-03-30 |  | Tower A | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
40457 |  | Not Committed |  | 2026-01-23 | 2026-04-02 | L75-76 | 100 | 0 |  | 2026-02-27 |  | 2026-04-24
40457 |  | Not Committed |  | 2026-01-23 | 2026-04-02 | L75-76 | 100 | 0 |  | 2026-02-27 |  | 2026-04-24 |  |  |  |  | Finishes | Gypsum Plastering Works
40458 | Tower A - Super Structure - Finishes & MEP - L75 to L76 | Not Ready | Partition Wall-Blockwork | 2026-01-23 | 2026-02-10 | De-shuttering & Area clearance | 100 | 0 |  | 2026-02-27 |  | 2026-03-18 |  | Tower A | Super Structure | L75
40930 |  | Not Committed |  | 2026-01-23 | 2026-04-28 | L65-Terrace | 100 | 0 |  | 2026-02-27 |  | 2026-06-04
40930 |  | Not Committed |  | 2026-01-23 | 2026-04-28 | L65-Terrace | 100 | 0 |  | 2026-02-27 |  | 2026-06-04
40931 | Tower A - Super Structure - Finishes & MEP - L65 to Terrace | Not Ready |  | 2026-01-23 | 2026-02-16 | FHR Shaft Risers | 100 | 0 |  | 2026-02-27 |  | 2026-03-24 |  | Tower A | Super Structure | L65
40933 | Tower A - Super Structure - Finishes & MEP - L65 to Terrace | Not Ready |  | 2026-01-23 | 2026-03-18 | Domestic Water & Flushing Riser in Plumbing Shaft | 100 | 0 |  | 2026-02-27 |  | 2026-04-22 |  | Tower A | Super Structure | L65
40935 | Tower A - Super Structure - Finishes & MEP - L65 to Terrace | Not Ready |  | 2026-01-23 | 2026-02-27 | Shaft Cable Tray in Electrical Shaft | 100 | 0 |  | 2026-02-27 |  | 2026-04-04 |  | Tower A | Super Structure | L65
41280 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-02-07 | 2026-02-10 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-02-27 |  | 2026-03-04 |  | Tower A | Super Structure | L20
43178 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-02-05 | 2026-02-16 | Cement Plastering in wet areas | 100 | 0 |  | 2026-02-27 |  | 2026-03-11 |  | Tower A | Super Structure | L61
8824 | T-14-11th Floor Common Area | Not Ready | Flooring & skirting | 2026-02-02 | 2026-02-24 | Flooring & skirting | 100 | 0 |  | 2026-02-28 |  | 2026-03-22
10693 | T-20-2nd Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-04-18 | 2026-07-10 | 2nd Coat Painting | 100 | 0 |  | 2026-02-28 |  | 2026-05-23
10944 |  | Not Ready |  | 2026-04-05 | 2026-11-25 | Lift lobby | 100 | 0 |  | 2026-02-28 |  | 2026-10-20
10974 |  | Not Ready |  | 2026-04-05 | 2026-09-07 | Staircase-2 | 100 | 0 |  | 2026-02-28 |  | 2026-08-02
11391 | T-19-9th Floor Flat Area | Not Ready | Window | 2026-04-01 | 2026-04-23 | Window | 100 | 0 |  | 2026-02-28 |  | 2026-03-24
40416 | Tower A - Super Structure - Finishes & MEP - L64 to L65 | Not Ready | Partition Wall-Blockwork | 2026-02-06 | 2026-02-11 | Staircase Area | 100 | 0 |  | 2026-02-28 |  | 2026-03-06 |  | Tower A | Super Structure | L64
40419 | Tower A - Super Structure - Finishes & MEP - L65 to L66 | Not Ready | Partition Wall-Blockwork | 2026-02-06 | 2026-02-13 | Partition Walls | 100 | 0 |  | 2026-02-28 |  | 2026-03-09 |  | Tower A | Super Structure | L65
43038 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-04-01 | 2026-04-17 | Flooring & Dado works | 100 | 0 |  | 2026-02-28 |  | 2026-03-19 |  | Tower A | Super Structure | L53 | Finishes | Flooring & Dado
44111 |  | Not Ready |  | 2026-04-01 | 2026-05-06 | L58-63 | 100 | 0 |  | 2026-02-28 |  | 2026-04-06
44112 | Tower A - Super Structure - Finishes & MEP - L58 to L63 | Not Ready | Façade Works - MEP & Finishes | 2026-04-01 | 2026-04-11 | Al. Frame section (Mullion & Transom) Installation | 100 | 0 |  | 2026-02-28 |  | 2026-03-13 |  | Tower A | Super Structure | L58 | Façade | Façade Works
45288 | Tower B - Super Structure - Core & Outer Slab L12-13 | Not Ready | RCC Works - Slab | 2025-12-24 | 2026-01-01 | Outer Slab_TA | 100 | 0 |  | 2026-02-28 |  | 2026-03-10 |  | Tower B | Super Structure | L12 | RCC Sub Structure | RCC Works - Slab
9812 | T-16-8th Floor Common Area | Not Ready | Flooring & skirting | 2026-03-22 | 2026-04-14 | Flooring & skirting | 100 | 0 |  | 2026-03-01 |  | 2026-03-23
10231 | T-21-4th Floor Common Area | Not Ready | Window-Open Area | 2026-04-01 | 2026-04-09 | Window-Open Area | 100 | 0 |  | 2026-03-01 |  | 2026-03-08
8834 | T-14-12th Floor Flat Area | Not Ready | Plastering | 2026-01-28 | 2026-02-18 | Plastering-Cement | 100 | 0 |  | 2026-03-02 |  | 2026-03-23
9757 | T-16-6th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-03-28 | 2026-06-03 | 2nd Coat Painting | 100 | 0 |  | 2026-03-02 |  | 2026-05-05
11912 | T-18-9th Floor Flat Area | Not Ready | Door | 2026-05-10 | 2026-06-01 | Door | 100 | 0 |  | 2026-03-02 |  | 2026-03-26
11937 | T-18-10th Floor Flat Area | Not Ready | Window | 2026-05-10 | 2026-06-01 | Window | 100 | 0 |  | 2026-03-02 |  | 2026-03-26
40536 | Tower A - Super Structure - Finishes & MEP - L62 to L63 | Not Ready | Gypsum Plastering Works | 2026-02-07 | 2026-02-24 | L62-63 | 100 | 0 |  | 2026-03-02 |  | 2026-03-19 |  | Tower A | Super Structure | L62 | Finishes | Gypsum Plastering Works
40536 | Tower A - Super Structure - Finishes & MEP - L62 to L63 | Not Ready | Gypsum Plastering Works | 2026-02-07 | 2026-02-24 | L62-63 | 100 | 0 |  | 2026-03-02 |  | 2026-03-19 |  | Tower A | Super Structure | L62
41266 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-02-10 | 2026-02-14 | Final Painting | 100 | 0 |  | 2026-03-02 |  | 2026-03-09 |  | Tower A | Super Structure | L19 | Finishes | Final Painting
41266 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-02-10 | 2026-02-14 | Final Painting | 100 | 0 |  | 2026-03-02 |  | 2026-03-09 |  | Tower A | Super Structure | L19 | Finishes | Final Painting
41266 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-02-10 | 2026-02-14 | Final Painting | 100 | 0 |  | 2026-03-02 |  | 2026-03-09 |  | Tower A | Super Structure | L19 | Finishes | Final Painting
41307 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-02-10 | 2026-02-17 | False Ceiling | 100 | 0 |  | 2026-03-02 |  | 2026-03-11 |  | Tower A | Super Structure | L22 | Finishes | False Ceiling
41335 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-02-10 | 2026-02-17 | HVAC Ducting | 100 | 0 |  | 2026-03-02 |  | 2026-03-11 |  | Tower A | Super Structure | L24 | MEP | HVAC Ducting
41881 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2026-01-31 | 2026-02-05 | Lobby Plastering | 100 | 0 |  | 2026-03-02 |  | 2026-03-09 |  | Tower A | Super Structure | L58 | Finishes | Lobby Plastering
41891 |  | Not Committed |  | 2026-01-31 | 2026-09-12 | L59-60 | 100 | 0 |  | 2026-03-02 |  | 2026-09-23
41891 |  | Not Committed |  | 2026-01-31 | 2026-09-12 | L59-60 | 100 | 0 |  | 2026-03-02 |  | 2026-09-23 |  |  |  |  | Finishes | Gypsum Plastering Works
41896 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2026-01-31 | 2026-02-03 | Lobby Blockwork | 100 | 0 |  | 2026-03-02 |  | 2026-03-06 |  | Tower A | Super Structure | L59 | Finishes | Blockwork
42073 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2026-02-07 | 2026-02-12 | Lobby Plastering | 100 | 0 |  | 2026-03-02 |  | 2026-03-09 |  | Tower A | Super Structure | L70 | Finishes | Lobby Plastering
42083 |  | Not Committed |  | 2026-02-07 | 2026-11-28 | L71-72 | 100 | 0 |  | 2026-03-02 |  | 2026-12-05
42083 |  | Not Committed |  | 2026-02-07 | 2026-11-28 | L71-72 | 100 | 0 |  | 2026-03-02 |  | 2026-12-05 |  |  |  |  | Finishes | Gypsum Plastering Works
42088 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2026-02-07 | 2026-02-10 | Lobby Blockwork | 100 | 0 |  | 2026-03-02 |  | 2026-03-06 |  | Tower A | Super Structure | L71 | Finishes | Blockwork
43109 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-02-07 | 2026-02-14 | Door & Window Frame work | 100 | 0 |  | 2026-03-02 |  | 2026-03-10 |  | Tower A | Super Structure | L57 | Finishes | Door & Window Frame work
8773 | T-14-9th Floor Common Area | Not Ready | Putty | 2026-02-02 | 2026-03-12 | Putty | 100 | 0 |  | 2026-03-03 |  | 2026-04-12
9162 | T-15-3rd Floor Common Area | Not Ready | Flooring & skirting | 2026-02-26 | 2026-03-19 | Flooring & skirting | 100 | 0 |  | 2026-03-03 |  | 2026-03-24
9189 | T-15-4th Floor Common Area | Not Ready | Putty | 2026-02-26 | 2026-04-06 | Putty | 100 | 0 |  | 2026-03-03 |  | 2026-04-12
10361 | T-21-9th Floor Common Area | Not Ready | Window-Open Area | 2026-04-07 | 2026-04-15 | Window-Open Area | 100 | 0 |  | 2026-03-03 |  | 2026-03-10
10880 | T-20-9th Floor Common Area | Not Ready | Door-Shaft | 2026-04-05 | 2026-04-18 | Door-Shaft | 100 | 0 |  | 2026-03-03 |  | 2026-03-16
8812 | T-14-11th Floor Flat Area | Not Ready | Dado | 2026-01-31 | 2026-02-27 | Dado | 100 | 0 |  | 2026-03-04 |  | 2026-03-31
8849 | T-14-12th Floor Common Area | Not Ready | Plastering | 2026-01-30 | 2026-03-03 | Plastering-Gypsum | 100 | 0 |  | 2026-03-04 |  | 2026-04-06
9853 | T-16-10th Floor Flat Area | Not Ready | Toilet flooring | 2026-03-22 | 2026-04-25 | Toilet flooring | 100 | 0 |  | 2026-03-04 |  | 2026-04-07
10311 | T-21-7th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-04-09 | 2026-05-13 | 2nd Coat Painting | 100 | 0 |  | 2026-03-04 |  | 2026-04-06
10386 | T-21-11th Floor Common Area | Not Ready | Door-Shaft | 2026-04-10 | 2026-04-23 | Door-Shaft | 100 | 0 |  | 2026-03-04 |  | 2026-03-17
10855 | T-20-8th Floor Common Area | Not Ready | Window-Open Area | 2026-04-02 | 2026-04-09 | Window-Open Area | 100 | 0 |  | 2026-03-04 |  | 2026-03-14
11785 | T-18-4th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-05-29 | 2026-08-02 | 2nd Coat Painting | 100 | 0 |  | 2026-03-04 |  | 2026-05-08
11889 | T-18-8th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-05-29 | 2026-08-02 | 2nd Coat Painting | 100 | 0 |  | 2026-03-04 |  | 2026-05-08
11945 | T-18-11th Floor Common Area | Not Ready | Putty | 2026-05-23 | 2026-06-30 | Putty | 100 | 0 |  | 2026-03-04 |  | 2026-04-13
41281 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-02-11 | 2026-02-16 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-03-04 |  | 2026-03-10 |  | Tower A | Super Structure | L20 | MEP | Electrical
41292 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-02-11 | 2026-02-13 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-03-04 |  | 2026-03-07 |  | Tower A | Super Structure | L21 | MEP | FPS 2nd Fix - MEP & Finishes
41293 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-02-11 | 2026-02-16 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-03-04 |  | 2026-03-10 |  | Tower A | Super Structure | L21 | MEP | Electrical 2nd Fix - MEP & Finishes
41294 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-02-11 | 2026-02-18 | FAPA Device Fixing | 100 | 0 |  | 2026-03-04 |  | 2026-03-12 |  | Tower A | Super Structure | L21
41294 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-02-11 | 2026-02-18 | FAPA Device Fixing | 100 | 0 |  | 2026-03-04 |  | 2026-03-12 |  | Tower A | Super Structure | L21
41294 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-02-11 | 2026-02-18 | FAPA Device Fixing | 100 | 0 |  | 2026-03-04 |  | 2026-03-12 |  | Tower A | Super Structure | L21
41294 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-02-11 | 2026-02-18 | FAPA Device Fixing | 100 | 0 |  | 2026-03-04 |  | 2026-03-12 |  | Tower A | Super Structure | L21
41295 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-02-11 | 2026-02-13 | HVAC Grill Fixing | 100 | 0 |  | 2026-03-04 |  | 2026-03-07 |  | Tower A | Super Structure | L21 | MEP | HVAC Grill Fixing
41322 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-02-11 | 2026-02-21 | Flooring & Dado | 100 | 0 |  | 2026-03-04 |  | 2026-03-16 |  | Tower A | Super Structure | L23 | Finishes | Flooring & Dado
43161 |  | Not Committed |  | 2026-02-09 | 2026-05-18 | Finishes after 1st Fix | 100 | 0 |  | 2026-03-04 |  | 2026-04-21
43162 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-02-09 | 2026-03-04 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-03-04 |  | 2026-03-26 |  | Tower A | Super Structure | L60 | Finishes | Blockwork
45851 |  | Not Ready |  | 2025-12-27 | 2027-11-01 | Podium MEP & Finishes | 100 | 0 |  | 2026-03-04 |  | 2027-12-22
46017 |  | Not Committed |  | 2025-12-27 | 2026-12-07 | P6-7 Level (Refuge) | 100 | 0 |  | 2026-03-04 |  | 2027-02-16
46032 |  | Not Committed |  | 2025-12-27 | 2026-02-19 | Floor Area | 100 | 0 |  | 2026-03-04 |  | 2026-04-27
46033 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | Ceiling Painting/ PT Marking - MEP & Finishes | 2025-12-27 | 2026-01-01 | Ceiling Painting/ PT Marking | 100 | 0 |  | 2026-03-04 |  | 2026-03-10 |  | Tower B | Super Structure |  | Finishes | Ceiling Painting/ PT Marking
46660 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2025-12-27 | 2026-01-13 | Wet Area Waterproofing | 100 | 0 |  | 2026-03-04 |  | 2026-03-21 |  | Tower B | Super Structure | L7
8616 | T-14-3rd Floor Common Area | Not Ready | Flooring & skirting | 2026-01-28 | 2026-02-18 | Flooring & skirting | 100 | 0 |  | 2026-03-05 |  | 2026-03-26
8643 | T-14-4th Floor Common Area | Not Ready | Putty | 2026-01-28 | 2026-03-06 | Putty | 100 | 0 |  | 2026-03-05 |  | 2026-04-10
8818 | T-14-11th Floor Flat Area | Not Ready | Door | 2026-02-26 | 2026-03-20 | Door | 100 | 0 |  | 2026-03-05 |  | 2026-03-26
8843 | T-14-12th Floor Flat Area | Not Ready | Window | 2026-02-26 | 2026-03-20 | Window | 100 | 0 |  | 2026-03-05 |  | 2026-03-26
9780 | T-16-7th Floor Flat Area | Not Ready | Door | 2026-04-08 | 2026-04-29 | Door | 100 | 0 |  | 2026-03-05 |  | 2026-03-26
10805 | T-20-6th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-03-30 | 2026-05-02 | 2nd Coat Painting | 100 | 0 |  | 2026-03-05 |  | 2026-04-08
11373 | T-19-8th Floor Common Area | Not Ready | Putty | 2026-03-23 | 2026-05-02 | Putty | 100 | 0 |  | 2026-03-05 |  | 2026-04-11
45440 | Tower B - Super Structure - Finishes & MEP - L8 to L9 | Not Ready | Partition Wall-Blockwork | 2025-12-29 | 2026-01-02 | Staircase Area | 100 | 0 |  | 2026-03-05 |  | 2026-03-11 |  | Tower B | Super Structure | L8
9370 | T-15-11th Floor Common Area | Not Ready | Flooring & skirting | 2026-03-14 | 2026-04-06 | Flooring & skirting | 100 | 0 |  | 2026-03-06 |  | 2026-03-29
9808 | T-16-8th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-03-30 | 2026-06-20 | 1st Coat Painting | 100 | 0 |  | 2026-03-06 |  | 2026-05-28
9834 | T-16-9th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-03-30 | 2026-06-20 | 1st Coat Painting | 100 | 0 |  | 2026-03-06 |  | 2026-05-28
10442 | T-21-Staircase 1 | Not Ready |  | 2026-04-04 | 2026-04-16 | 11F-10F | 100 | 0 |  | 2026-03-06 |  | 2026-03-18
10456 | T-21-Staircase 2 | Not Ready |  | 2026-04-04 | 2026-04-16 | 12F-11F | 100 | 0 |  | 2026-03-06 |  | 2026-03-18
10750 | T-20-4th Floor Common Area | Not Ready | Door-Shaft | 2026-03-31 | 2026-04-13 | Door-Shaft | 100 | 0 |  | 2026-03-06 |  | 2026-03-19
10989 |  | Not Ready |  | 2026-04-10 | 2026-10-06 | External Finishes | 100 | 0 |  | 2026-03-06 |  | 2026-08-31
10990 |  | Not Ready |  | 2026-04-10 | 2026-10-06 | External Painting | 100 | 0 |  | 2026-03-06 |  | 2026-08-31
11759 | T-18-3rd Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-05-31 | 2026-08-04 | 2nd Coat Painting | 100 | 0 |  | 2026-03-06 |  | 2026-05-13
41897 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2026-02-04 | 2026-02-09 | Lobby Plastering | 100 | 0 |  | 2026-03-06 |  | 2026-03-12 |  | Tower A | Super Structure | L59 | Finishes | Lobby Plastering
41907 |  | Not Committed |  | 2026-02-04 | 2026-09-21 | L60-61 | 100 | 0 |  | 2026-03-06 |  | 2026-09-30
41907 |  | Not Committed |  | 2026-02-04 | 2026-09-21 | L60-61 | 100 | 0 |  | 2026-03-06 |  | 2026-09-30 |  |  |  |  | Finishes | Gypsum Plastering Works
41912 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2026-02-04 | 2026-02-06 | Lobby Blockwork | 100 | 0 |  | 2026-03-06 |  | 2026-03-10 |  | Tower A | Super Structure | L60 | Finishes | Blockwork
42089 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2026-02-11 | 2026-02-16 | Lobby Plastering | 100 | 0 |  | 2026-03-06 |  | 2026-03-12 |  | Tower A | Super Structure | L71 | Finishes | Lobby Plastering
42099 |  | Not Committed |  | 2026-02-11 | 2026-12-04 | L72-73 | 100 | 0 |  | 2026-03-06 |  | 2026-12-11
42099 |  | Not Committed |  | 2026-02-11 | 2026-12-04 | L72-73 | 100 | 0 |  | 2026-03-06 |  | 2026-12-11 |  |  |  |  | Finishes | Gypsum Plastering Works
42104 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2026-02-11 | 2026-02-13 | Lobby Blockwork | 100 | 0 |  | 2026-03-06 |  | 2026-03-10 |  | Tower A | Super Structure | L72 | Finishes | Blockwork
44534 | NTA_Zone 2 - Super Structure - P4 to P5 | Not Ready | MEP 1st Fix Works | 2025-06-03 | 2025-07-29 | P4 to P5 | 100 | 0 |  | 2026-03-06 |  | 2026-03-23 |  | NTA_Zone 2 | Super Structure
44534 | NTA_Zone 2 - Super Structure - P4 to P5 | Not Ready | MEP 1st Fix Works | 2025-06-03 | 2025-07-29 | P4 to P5 | 100 | 0 |  | 2026-03-06 |  | 2026-03-23 |  | NTA_Zone 2 | Super Structure
44534 | NTA_Zone 2 - Super Structure - P4 to P5 | Not Ready | MEP 1st Fix Works | 2025-06-03 | 2025-07-29 | P4 to P5 | 100 | 0 |  | 2026-03-06 |  | 2026-03-23 |  | NTA_Zone 2 | Super Structure
44571 | NTA_Zone 2 - Super Structure - P2 to P3 | Not Ready | Finishes (Lobby & Floor Area) | 2025-06-03 | 2025-07-08 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2026-03-06 |  | 2026-04-09 |  | NTA_Zone 2 | Super Structure
44571 | NTA_Zone 2 - Super Structure - P2 to P3 | Not Ready | Finishes (Lobby & Floor Area) | 2025-06-03 | 2025-07-08 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2026-03-06 |  | 2026-04-09 |  | NTA_Zone 2 | Super Structure
9805 | T-16-8th Floor Flat Area | Not Ready | Window | 2026-04-10 | 2026-05-02 | Window | 100 | 0 |  | 2026-03-07 |  | 2026-03-29
9856 | T-16-10th Floor Flat Area | Not Ready | Putty | 2026-03-26 | 2026-06-17 | Putty | 100 | 0 |  | 2026-03-07 |  | 2026-05-29
10204 | T-21-3rd Floor Common Area | Not Ready | Door-Shaft | 2026-04-10 | 2026-04-23 | Door-Shaft | 100 | 0 |  | 2026-03-07 |  | 2026-03-20
10420 | T-21-Lift | Not Ready | PARAPET | 2026-04-16 | 2026-06-21 | Parapets | 100 | 0 |  | 2026-03-07 |  | 2026-05-12
10472 | T-21- Elevation-B | Not Ready |  | 2026-04-10 | 2026-07-02 | Elevation-B | 100 | 0 |  | 2026-03-07 |  | 2026-05-27
10945 | T-20-Lift Lobby | Not Ready |  | 2026-04-05 | 2026-04-22 | 12F | 100 | 0 |  | 2026-03-07 |  | 2026-03-22
11291 | T-19-5th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-04-03 | 2026-06-09 | 2nd Coat Painting | 100 | 0 |  | 2026-03-07 |  | 2026-05-11
11343 | T-19-7th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-04-03 | 2026-06-09 | 2nd Coat Painting | 100 | 0 |  | 2026-03-07 |  | 2026-05-11
11844 | T-18-6th Floor Common Area | Not Ready | 1st Coat Painting | 2026-05-16 | 2026-06-08 | 1st Coat Painting | 100 | 0 |  | 2026-03-07 |  | 2026-03-30
40058 | Tower A - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2026-02-12 | 2026-02-23 | Bulk head light fix + Electrical works + Earthing | 100 | 0 |  | 2026-03-07 |  | 2026-03-19 |  | Tower A | Super Structure
40058 | Tower A - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2026-02-12 | 2026-02-23 | Bulk head light fix + Electrical works + Earthing | 100 | 0 |  | 2026-03-07 |  | 2026-03-19 |  | Tower A | Super Structure
40058 | Tower A - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2026-02-12 | 2026-02-23 | Bulk head light fix + Electrical works + Earthing | 100 | 0 |  | 2026-03-07 |  | 2026-03-19 |  | Tower A | Super Structure
41296 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-02-14 | 2026-02-17 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-03-07 |  | 2026-03-11 |  | Tower A | Super Structure | L21
43056 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-04-07 | 2026-04-23 | Flooring & Dado works | 100 | 0 |  | 2026-03-07 |  | 2026-03-25 |  | Tower A | Super Structure | L54 | Finishes | Flooring & Dado
43214 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-02-12 | 2026-02-17 | Cement Plastering in wet areas | 100 | 0 |  | 2026-03-07 |  | 2026-03-12 |  | Tower A | Super Structure | L63
43226 |  | Not Committed |  | 2026-02-12 | 2026-10-31 | L64-65 (Club House) | 100 | 0 |  | 2026-03-07 |  | 2026-10-14
43227 |  | Not Committed |  | 2026-02-12 | 2026-03-31 | MEP 1st Fixes | 100 | 0 |  | 2026-03-07 |  | 2026-04-22
43228 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-02-12 | 2026-02-28 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-03-07 |  | 2026-03-24 |  | Tower A | Super Structure | L64 | MEP | FPS 1st Fix - MEP & Finishes
43229 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-02-12 | 2026-02-23 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-03-07 |  | 2026-03-18 |  | Tower A | Super Structure | L64 | MEP | Electrical 1st Fixes
43230 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-02-12 | 2026-02-28 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-03-07 |  | 2026-03-24 |  | Tower A | Super Structure | L64
43231 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-02-12 | 2026-03-19 | Wet Area Waterproofing | 100 | 0 |  | 2026-03-07 |  | 2026-04-10 |  | Tower A | Super Structure | L64
44110 | Tower A - Super Structure - Finishes & MEP - L53 to L58 | Not Ready | Façade Works - MEP & Finishes | 2026-04-07 | 2026-04-17 | Accessories & Alignment | 100 | 0 |  | 2026-03-07 |  | 2026-03-19 |  | Tower A | Super Structure | L53 | Façade | Façade Works
44110 | Tower A - Super Structure - Finishes & MEP - L53 to L58 | Not Ready | Façade Works - MEP & Finishes | 2026-04-07 | 2026-04-17 | Accessories & Alignment | 100 | 0 |  | 2026-03-07 |  | 2026-03-19 |  | Tower A | Super Structure | L53
45599 |  | Not Committed |  | 2025-12-31 | 2027-06-21 | Gypsum Plastering Works (Non-MEP Walls) | 100 | 0 |  | 2026-03-07 |  | 2027-09-16
45610 | Tower B - Super Structure - Finishes & MEP - L7 to L8 | Not Ready | Gypsum Plastering Works | 2025-12-31 | 2026-02-16 | L7-8 | 100 | 0 |  | 2026-03-07 |  | 2026-04-23 |  | Tower B | Super Structure | L7 | Finishes | Gypsum Plastering Works
45610 | Tower B - Super Structure - Finishes & MEP - L7 to L8 | Not Ready | Gypsum Plastering Works | 2025-12-31 | 2026-02-16 | L7-8 | 100 | 0 |  | 2026-03-07 |  | 2026-04-23 |  | Tower B | Super Structure | L7
9364 | T-15-11th Floor Flat Area | Not Ready | Door | 2026-03-30 | 2026-04-20 | Door | 100 | 0 |  | 2026-03-08 |  | 2026-04-02
10426 | T-21-Lift Lobby | Not Ready |  | 2026-04-10 | 2026-04-27 | 11F | 100 | 0 |  | 2026-03-08 |  | 2026-03-23
9185 | T-15-4th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-03-26 | 2026-06-01 | 2nd Coat Painting | 100 | 0 |  | 2026-03-09 |  | 2026-05-16
9243 | T-15-6th Floor Common Area | Not Ready | Window-Open Area | 2026-03-05 | 2026-03-13 | Window-Open Area | 100 | 0 |  | 2026-03-09 |  | 2026-03-15
9268 | T-15-7th Floor Common Area | Not Ready | Door-Shaft | 2026-03-09 | 2026-03-21 | Door-Shaft | 100 | 0 |  | 2026-03-09 |  | 2026-03-22
9289 | T-15-8th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-03-26 | 2026-06-01 | 2nd Coat Painting | 100 | 0 |  | 2026-03-09 |  | 2026-05-16
10232 | T-21-4th Floor Common Area | Not Ready | 1st Coat Painting | 2026-04-09 | 2026-05-02 | 1st Coat Painting | 100 | 0 |  | 2026-03-09 |  | 2026-03-30
11438 | T-19-11th Floor Flat Area | Not Ready | Dado | 2026-03-23 | 2026-04-20 | Dado | 100 | 0 |  | 2026-03-09 |  | 2026-04-05
43196 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-02-13 | 2026-02-24 | Cement Plastering in wet areas | 100 | 0 |  | 2026-03-09 |  | 2026-03-19 |  | Tower A | Super Structure | L62
8697 | T-14-6th Floor Common Area | Not Ready | Window-Open Area | 2026-02-04 | 2026-02-12 | Window-Open Area | 100 | 0 |  | 2026-03-10 |  | 2026-03-18
8850 | T-14-12th Floor Common Area | Not Ready | Flooring & skirting | 2026-02-13 | 2026-03-06 | Flooring & skirting | 100 | 0 |  | 2026-03-10 |  | 2026-03-30
10147 | T-21-1st Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-05-05 | 2026-07-10 | 2nd Coat Painting | 100 | 0 |  | 2026-03-10 |  | 2026-05-14
10418 | T-21-Lift | Not Ready | LMR ROOM | 2026-04-18 | 2026-06-23 | Lift Machine Rooms | 100 | 0 |  | 2026-03-10 |  | 2026-05-18
10961 | T-20-Staircase 1 | Not Ready |  | 2026-04-05 | 2026-04-16 | 12F-11F | 100 | 0 |  | 2026-03-10 |  | 2026-03-19
10975 | T-20-Staircase 2 | Not Ready |  | 2026-04-05 | 2026-04-16 | TF-12F | 100 | 0 |  | 2026-03-10 |  | 2026-03-19
11392 | T-19-9th Floor Flat Area | Not Ready | Door | 2026-04-13 | 2026-05-05 | Door | 100 | 0 |  | 2026-03-10 |  | 2026-03-30
11417 | T-19-10th Floor Flat Area | Not Ready | Window | 2026-04-13 | 2026-05-05 | Window | 100 | 0 |  | 2026-03-10 |  | 2026-03-30
11816 | T-18-5th Floor Common Area | Not Ready | Door-Shaft | 2026-05-18 | 2026-05-30 | Door-Shaft | 100 | 0 |  | 2026-03-10 |  | 2026-03-24
40420 | Tower A - Super Structure - Finishes & MEP - L65 to L66 | Not Ready | Partition Wall-Blockwork | 2026-02-14 | 2026-02-19 | Staircase Area | 100 | 0 |  | 2026-03-10 |  | 2026-03-14 |  | Tower A | Super Structure | L65
40423 | Tower A - Super Structure - Finishes & MEP - L66 to L67 | Not Ready | Partition Wall-Blockwork | 2026-02-14 | 2026-02-21 | Partition Walls | 100 | 0 |  | 2026-03-10 |  | 2026-03-17 |  | Tower A | Super Structure | L66
41282 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-02-17 | 2026-02-21 | Final Painting | 100 | 0 |  | 2026-03-10 |  | 2026-03-16 |  | Tower A | Super Structure | L20 | Finishes | Final Painting
41282 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-02-17 | 2026-02-21 | Final Painting | 100 | 0 |  | 2026-03-10 |  | 2026-03-16 |  | Tower A | Super Structure | L20 | Finishes | Final Painting
41282 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-02-17 | 2026-02-21 | Final Painting | 100 | 0 |  | 2026-03-10 |  | 2026-03-16 |  | Tower A | Super Structure | L20 | Finishes | Final Painting
41323 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-02-17 | 2026-02-24 | False Ceiling | 100 | 0 |  | 2026-03-10 |  | 2026-03-18 |  | Tower A | Super Structure | L23 | Finishes | False Ceiling
41351 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-02-17 | 2026-02-24 | HVAC Ducting | 100 | 0 |  | 2026-03-10 |  | 2026-03-18 |  | Tower A | Super Structure | L25 | MEP | HVAC Ducting
41913 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2026-02-07 | 2026-02-12 | Lobby Plastering | 100 | 0 |  | 2026-03-10 |  | 2026-03-16 |  | Tower A | Super Structure | L60 | Finishes | Lobby Plastering
41923 |  | Not Committed |  | 2026-02-07 | 2026-09-28 | L61-62 | 100 | 0 |  | 2026-03-10 |  | 2026-10-07
41923 |  | Not Committed |  | 2026-02-07 | 2026-09-28 | L61-62 | 100 | 0 |  | 2026-03-10 |  | 2026-10-07 |  |  |  |  | Finishes | Gypsum Plastering Works
41928 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2026-02-07 | 2026-02-10 | Lobby Blockwork | 100 | 0 |  | 2026-03-10 |  | 2026-03-13 |  | Tower A | Super Structure | L61 | Finishes | Blockwork
42105 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2026-02-14 | 2026-02-19 | Lobby Plastering | 100 | 0 |  | 2026-03-10 |  | 2026-03-16 |  | Tower A | Super Structure | L72 | Finishes | Lobby Plastering
42115 |  | Not Committed |  | 2026-02-14 | 2026-12-08 | L73-74 | 100 | 0 |  | 2026-03-10 |  | 2026-12-15
42115 |  | Not Committed |  | 2026-02-14 | 2026-12-08 | L73-74 | 100 | 0 |  | 2026-03-10 |  | 2026-12-15 |  |  |  |  | Finishes | Gypsum Plastering Works
42120 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2026-02-14 | 2026-02-17 | Lobby Blockwork | 100 | 0 |  | 2026-03-10 |  | 2026-03-13 |  | Tower A | Super Structure | L73 | Finishes | Blockwork
45289 |  | Not Ready |  | 2026-01-02 | 2026-01-16 | L13-14 | 100 | 0 |  | 2026-03-10 |  | 2026-03-25
45289 |  | Not Ready |  | 2026-01-02 | 2026-01-16 | L13-14 | 100 | 0 |  | 2026-03-10 |  | 2026-03-25 |  |  |  |  | Finishes | Gypsum Plastering Works
45290 | Tower B - Super Structure - Core & Outer Slab L13-14 | Not Ready | RCC Works - Vertical | 2026-01-02 | 2026-01-13 | Outer Columns_TA | 100 | 0 |  | 2026-03-10 |  | 2026-03-21 |  | Tower B | Super Structure | L13 | RCC Sub Structure | RCC Works - Vertical
45445 |  | Not Committed |  | 2026-01-02 | 2026-02-03 | L10-11 | 100 | 0 |  | 2026-03-10 |  | 2026-04-10
45445 |  | Not Committed |  | 2026-01-02 | 2026-02-03 | L10-11 | 100 | 0 |  | 2026-03-10 |  | 2026-04-10 |  |  |  |  | Finishes | Gypsum Plastering Works
45446 | Tower B - Super Structure - Finishes & MEP - L10 to L11 | Not Ready | Partition Wall-Blockwork | 2026-01-02 | 2026-01-19 | De-shuttering & Area clearance | 100 | 0 |  | 2026-03-10 |  | 2026-03-27 |  | Tower B | Super Structure | L10
45990 |  | Not Committed |  | 2026-01-02 | 2026-12-15 | P5-6 Level | 100 | 0 |  | 2026-03-10 |  | 2027-02-24
46005 |  | Not Committed |  | 2026-01-02 | 2026-04-30 | Floor Area | 100 | 0 |  | 2026-03-10 |  | 2026-07-07
46006 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | Ceiling Painting/ PT Marking - MEP & Finishes | 2026-01-02 | 2026-01-07 | Ceiling Painting/ PT Marking | 100 | 0 |  | 2026-03-10 |  | 2026-03-16 |  | Tower B | Super Structure |  | Finishes | Ceiling Painting/ PT Marking
46034 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-01-02 | 2026-01-24 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-03-10 |  | 2026-04-02 |  | Tower B | Super Structure |  | MEP | FPS 1st Fix - MEP & Finishes
46035 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-01-02 | 2026-01-24 | PHE 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-03-10 |  | 2026-04-02 |  | Tower B | Super Structure
46036 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-01-02 | 2026-01-19 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-03-10 |  | 2026-03-27 |  | Tower B | Super Structure |  | MEP | Electrical 1st Fixes
8813 | T-14-11th Floor Flat Area | Not Ready | Toilet flooring | 2026-02-07 | 2026-03-12 | Toilet flooring | 100 | 0 |  | 2026-03-11 |  | 2026-04-12
9159 | T-15-3rd Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-03-28 | 2026-06-03 | 2nd Coat Painting | 100 | 0 |  | 2026-03-11 |  | 2026-05-19
10362 | T-21-9th Floor Common Area | Not Ready | 1st Coat Painting | 2026-04-15 | 2026-05-07 | 1st Coat Painting | 100 | 0 |  | 2026-03-11 |  | 2026-04-04
10670 | T-20-1st Floor Common Area | Not Ready | Flooring & skirting | 2026-04-05 | 2026-04-27 | Flooring & skirting | 100 | 0 |  | 2026-03-11 |  | 2026-03-31
10697 | T-20-2nd Floor Common Area | Not Ready | Putty | 2026-04-05 | 2026-05-14 | Putty | 100 | 0 |  | 2026-03-11 |  | 2026-04-17
40114 | Tower A - Super Structure - Finishes & MEP - Sub Station | Not Ready | Sub Station - High Side Services | 2026-03-13 | 2026-03-30 | Cable Tray Fixing | 100 | 0 |  | 2026-03-11 |  | 2026-03-27 |  | Tower A | Super Structure
40122 | Tower A - Super Structure - Finishes & MEP - DG Sets | Not Ready |  | 2026-03-13 | 2026-04-16 | DG Placing | 100 | 0 |  | 2026-03-11 |  | 2026-04-14 |  | Tower A | Super Structure
40537 | Tower A - Super Structure - Finishes & MEP - L63 to L64 | Not Ready | Gypsum Plastering Works | 2026-02-16 | 2026-03-05 | L63-64 | 100 | 0 |  | 2026-03-11 |  | 2026-03-27 |  | Tower A | Super Structure | L63 | Finishes | Gypsum Plastering Works
40537 | Tower A - Super Structure - Finishes & MEP - L63 to L64 | Not Ready | Gypsum Plastering Works | 2026-02-16 | 2026-03-05 | L63-64 | 100 | 0 |  | 2026-03-11 |  | 2026-03-27 |  | Tower A | Super Structure | L63
41297 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-02-18 | 2026-02-23 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-03-11 |  | 2026-03-17 |  | Tower A | Super Structure | L21 | MEP | Electrical
41308 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-02-18 | 2026-02-20 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-03-11 |  | 2026-03-14 |  | Tower A | Super Structure | L22 | MEP | FPS 2nd Fix - MEP & Finishes
41309 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-02-18 | 2026-02-23 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-03-11 |  | 2026-03-17 |  | Tower A | Super Structure | L22 | MEP | Electrical 2nd Fix - MEP & Finishes
41310 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-02-18 | 2026-02-25 | FAPA Device Fixing | 100 | 0 |  | 2026-03-11 |  | 2026-03-19 |  | Tower A | Super Structure | L22
41310 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-02-18 | 2026-02-25 | FAPA Device Fixing | 100 | 0 |  | 2026-03-11 |  | 2026-03-19 |  | Tower A | Super Structure | L22
41310 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-02-18 | 2026-02-25 | FAPA Device Fixing | 100 | 0 |  | 2026-03-11 |  | 2026-03-19 |  | Tower A | Super Structure | L22
41310 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-02-18 | 2026-02-25 | FAPA Device Fixing | 100 | 0 |  | 2026-03-11 |  | 2026-03-19 |  | Tower A | Super Structure | L22
41311 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-02-18 | 2026-02-20 | HVAC Grill Fixing | 100 | 0 |  | 2026-03-11 |  | 2026-03-14 |  | Tower A | Super Structure | L22 | MEP | HVAC Grill Fixing
41338 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-02-18 | 2026-02-28 | Flooring & Dado | 100 | 0 |  | 2026-03-11 |  | 2026-03-23 |  | Tower A | Super Structure | L24 | Finishes | Flooring & Dado
43127 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-02-16 | 2026-02-23 | Door & Window Frame work | 100 | 0 |  | 2026-03-11 |  | 2026-03-18 |  | Tower A | Super Structure | L58 | Finishes | Door & Window Frame work
43970 | Tower A - Super Structure - Finishes & MEP - L7 to L15 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-04-10 | 2026-05-09 | Staircase Window | 100 | 0 |  | 2026-03-11 |  | 2026-04-09 |  | Tower A | Super Structure | L7
43974 |  | Not Committed |  | 2026-04-10 | 2026-06-20 | L15-25 | 100 | 0 |  | 2026-03-11 |  | 2026-05-21
43974 |  | Not Committed |  | 2026-04-10 | 2026-06-20 | L15-25 | 100 | 0 |  | 2026-03-11 |  | 2026-05-21
43975 | Tower A - Super Structure - Finishes & MEP - L15 to L25 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-04-10 | 2026-05-15 | Staircase Wall & Ceiling finishes | 100 | 0 |  | 2026-03-11 |  | 2026-04-15 |  | Tower A | Super Structure | L15
43976 | Tower A - Super Structure - Finishes & MEP - L15 to L25 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-04-10 | 2026-06-03 | Staircase Flooring | 100 | 0 |  | 2026-03-11 |  | 2026-05-04 |  | Tower A | Super Structure | L15 | Finishes | Staircase Flooring
46673 |  | Not Committed |  | 2026-01-03 | 2027-02-08 | L8-9 | 100 | 0 |  | 2026-03-11 |  | 2027-04-14
46673 |  | Not Committed |  | 2026-01-03 | 2027-02-08 | L8-9 | 100 | 0 |  | 2026-03-11 |  | 2027-04-14 |  |  |  |  | Finishes | Gypsum Plastering Works
46674 |  | Not Committed |  | 2026-01-03 | 2026-02-10 | MEP 1st Fixes | 100 | 0 |  | 2026-03-11 |  | 2026-04-17
46675 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-01-03 | 2026-01-10 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-03-11 |  | 2026-03-19 |  | Tower B | Super Structure | L8 | MEP | FPS 1st Fix - MEP & Finishes
46676 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-01-03 | 2026-01-08 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-03-11 |  | 2026-03-17 |  | Tower B | Super Structure | L8 | MEP | Electrical 1st Fixes
46677 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-01-03 | 2026-01-10 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-03-11 |  | 2026-03-19 |  | Tower B | Super Structure | L8
8639 | T-14-4th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-02-24 | 2026-05-02 | 2nd Coat Painting | 100 | 0 |  | 2026-03-12 |  | 2026-05-19
8743 | T-14-8th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-02-24 | 2026-05-02 | 2nd Coat Painting | 100 | 0 |  | 2026-03-12 |  | 2026-05-19
8841 | T-14-12th Floor Flat Area | Not Ready | Flooring & skirting | 2026-02-07 | 2026-03-23 | Flooring & skirting | 100 | 0 |  | 2026-03-12 |  | 2026-04-24
9854 | T-16-10th Floor Flat Area | Not Ready | Toilets False Celing | 2026-04-01 | 2026-05-05 | Toilets False Celing | 100 | 0 |  | 2026-03-12 |  | 2026-04-15
9875 | T-16-11th Floor Flat Area | Not Ready | Waterproofing | 2026-03-28 | 2026-04-30 | Waterproofing | 100 | 0 |  | 2026-03-12 |  | 2026-04-12
10991 | T-20- Elevation A | Not Ready |  | 2026-04-10 | 2026-07-02 | Elevation-A | 100 | 0 |  | 2026-03-12 |  | 2026-06-04
11424 | T-19-11th Floor Common Area | Not Ready | Flooring & skirting | 2026-04-03 | 2026-04-25 | Flooring & skirting | 100 | 0 |  | 2026-03-12 |  | 2026-04-03
11938 | T-18-10th Floor Flat Area | Not Ready | Door | 2026-05-21 | 2026-06-12 | Door | 100 | 0 |  | 2026-03-12 |  | 2026-04-02
11963 | T-18-11th Floor Flat Area | Not Ready | Window | 2026-05-21 | 2026-06-12 | Window | 100 | 0 |  | 2026-03-12 |  | 2026-04-02
40092 |  | Not Committed |  | 2026-02-11 | 2026-09-24 | Pump Room (B2-B1-GF in Zone 1) | 100 | 0 |  | 2026-03-12 |  | 2026-10-12
40093 | Tower A - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2026-02-11 | 2026-03-18 | Tank Waterproofing | 100 | 0 |  | 2026-03-12 |  | 2026-04-16 |  | Tower A | Super Structure
43179 |  | Not Committed |  | 2026-02-17 | 2026-05-23 | Finishes after 1st Fix | 100 | 0 |  | 2026-03-12 |  | 2026-04-29
43180 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-02-17 | 2026-03-12 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-03-12 |  | 2026-04-03 |  | Tower A | Super Structure | L61 | Finishes | Blockwork
44027 | Tower A - Super Structure - Finishes & MEP - P1 to P3 | Started | Façade Works - MEP & Finishes | 2026-03-12 | 2026-03-16 | Al. Frame section (Mullion & Transom) Installation | 100 | 62 | Units | 2026-03-12 | 2025-03-26 | 2026-06-10 |  | Tower A | Super Structure |  | Façade | Façade Works
45443 | Tower B - Super Structure - Finishes & MEP - L9 to L10 | Not Ready | Partition Wall-Blockwork | 2026-01-05 | 2026-01-12 | Partition Walls | 100 | 0 |  | 2026-03-12 |  | 2026-03-20 |  | Tower B | Super Structure | L9
48230 |  | Not Committed |  | 2025-09-16 | 2026-05-15 | Basement | 100 | 0 |  | 2026-03-12 |  | 2026-11-02
48236 |  | Not Committed |  | 2025-09-16 | 2025-11-27 | B2 to B1 | 100 | 0 |  | 2026-03-12 |  | 2026-05-21
48236 |  | Not Committed |  | 2025-09-16 | 2025-11-27 | B2 to B1 | 100 | 0 |  | 2026-03-12 |  | 2026-05-21
48236 |  | Not Committed |  | 2025-09-16 | 2025-11-27 | B2 to B1 | 100 | 0 |  | 2026-03-12 |  | 2026-05-21
48237 | Retail & Clubhouse - Sub structure - B2 to B1 | Not Ready |  | 2025-09-16 | 2025-10-10 | VDF Flooring | 100 | 0 |  | 2026-03-12 |  | 2026-04-03 |  | Club House | Sub Structure | B2
48237 | Retail & Clubhouse - Sub structure - B2 to B1 | Not Ready |  | 2025-09-16 | 2025-10-10 | VDF Flooring | 100 | 0 |  | 2026-03-12 |  | 2026-04-03 |  | Club House | Sub Structure | B2
48241 |  | Not Committed |  | 2025-11-19 | 2026-01-29 | B1 to GF | 100 | 0 |  | 2026-03-12 |  | 2026-05-21
48241 |  | Not Committed |  | 2025-11-19 | 2026-01-29 | B1 to GF | 100 | 0 |  | 2026-03-12 |  | 2026-05-21
48241 |  | Not Committed |  | 2025-11-19 | 2026-01-29 | B1 to GF | 100 | 0 |  | 2026-03-12 |  | 2026-05-21
48242 | Retail & Clubhouse - Sub structure - B1 to GF | Not Ready |  | 2025-11-19 | 2025-12-11 | VDF Flooring | 100 | 0 |  | 2026-03-12 |  | 2026-04-03 |  | Club House | Sub Structure | B1
48242 | Retail & Clubhouse - Sub structure - B1 to GF | Not Ready |  | 2025-11-19 | 2025-12-11 | VDF Flooring | 100 | 0 |  | 2026-03-12 |  | 2026-04-03 |  | Club House | Sub Structure | B1
48246 | Retail & Clubhouse - Sub structure - B1 to GF | Not Ready |  | 2025-11-19 | 2025-12-23 | Retail, BOH Lift Lobby | 100 | 0 |  | 2026-03-12 |  | 2026-04-15 |  | Club House | Sub Structure | B1
48247 | Retail & Clubhouse - Sub structure - B1 to GF | Not Ready |  | 2025-11-19 | 2025-12-23 | Retail Toilets | 100 | 0 |  | 2026-03-12 |  | 2026-04-15 |  | Club House | Sub Structure | B1
8799 | T-14-11th Floor Common Area | Not Ready | Putty | 2026-02-13 | 2026-03-23 | Putty | 100 | 0 |  | 2026-03-13 |  | 2026-04-18
9345 | T-15-11th Floor Common Area | Not Ready | Putty | 2026-03-19 | 2026-04-28 | Putty | 100 | 0 |  | 2026-03-13 |  | 2026-04-22
9787 | T-16-7th Floor Common Area | Not Ready | Putty | 2026-03-28 | 2026-05-07 | Putty | 100 | 0 |  | 2026-03-13 |  | 2026-04-18
10416 |  | Not Ready |  | 2026-04-16 | 2026-11-21 | TF | 100 | 0 |  | 2026-03-13 |  | 2026-10-19
10417 |  | Not Ready |  | 2026-04-16 | 2026-11-21 | Finishing Works | 100 | 0 |  | 2026-03-13 |  | 2026-10-19
11736 | T-18-2nd Floor Common Area | Not Ready | Flooring & skirting | 2026-05-23 | 2026-06-14 | Flooring & skirting | 100 | 0 |  | 2026-03-13 |  | 2026-04-06
11763 | T-18-3rd Floor Common Area | Not Ready | Putty | 2026-05-23 | 2026-06-30 | Putty | 100 | 0 |  | 2026-03-13 |  | 2026-04-22
11869 | T-18-7th Floor Common Area | Not Ready | Window-Open Area | 2026-05-26 | 2026-06-02 | Window-Open Area | 100 | 0 |  | 2026-03-13 |  | 2026-03-20
11966 | T-18-11th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-06-03 | 2026-08-25 | 1st Coat Painting | 100 | 0 |  | 2026-03-13 |  | 2026-06-02
41929 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2026-02-11 | 2026-02-16 | Lobby Plastering | 100 | 0 |  | 2026-03-13 |  | 2026-03-19 |  | Tower A | Super Structure | L61 | Finishes | Lobby Plastering
41939 |  | Not Committed |  | 2026-02-11 | 2026-10-06 | L62-63 | 100 | 0 |  | 2026-03-13 |  | 2026-10-13
41939 |  | Not Committed |  | 2026-02-11 | 2026-10-06 | L62-63 | 100 | 0 |  | 2026-03-13 |  | 2026-10-13 |  |  |  |  | Finishes | Gypsum Plastering Works
41944 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2026-02-11 | 2026-02-13 | Lobby Blockwork | 100 | 0 |  | 2026-03-13 |  | 2026-03-17 |  | Tower A | Super Structure | L62 | Finishes | Blockwork
42121 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2026-02-18 | 2026-02-23 | Lobby Plastering | 100 | 0 |  | 2026-03-13 |  | 2026-03-19 |  | Tower A | Super Structure | L73 | Finishes | Lobby Plastering
42131 |  | Not Committed |  | 2026-02-18 | 2026-12-14 | L74-75 | 100 | 0 |  | 2026-03-13 |  | 2026-12-21
42131 |  | Not Committed |  | 2026-02-18 | 2026-12-14 | L74-75 | 100 | 0 |  | 2026-03-13 |  | 2026-12-21 |  |  |  |  | Finishes | Gypsum Plastering Works
42136 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2026-02-18 | 2026-02-20 | Lobby Blockwork | 100 | 0 |  | 2026-03-13 |  | 2026-03-17 |  | Tower A | Super Structure | L74 | Finishes | Blockwork
43074 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-04-13 | 2026-04-29 | Flooring & Dado works | 100 | 0 |  | 2026-03-13 |  | 2026-03-31 |  | Tower A | Super Structure | L55 | Finishes | Flooring & Dado
43215 |  | Not Committed |  | 2026-02-18 | 2026-06-05 | Finishes after 1st Fix | 100 | 0 |  | 2026-03-13 |  | 2026-05-14
43216 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-02-18 | 2026-03-13 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-03-13 |  | 2026-04-04 |  | Tower A | Super Structure | L63 | Finishes | Blockwork
44113 | Tower A - Super Structure - Finishes & MEP - L58 to L63 | Not Ready | Façade Works - MEP & Finishes | 2026-04-13 | 2026-04-23 | DGU Assembly Installation | 100 | 0 |  | 2026-03-13 |  | 2026-03-25 |  | Tower A | Super Structure | L58 | Façade | Façade Works
44114 | Tower A - Super Structure - Finishes & MEP - L58 to L63 | Not Ready | Façade Works - MEP & Finishes | 2026-04-13 | 2026-05-06 | Installation of highly reflective metal sheet | 100 | 0 |  | 2026-03-13 |  | 2026-04-06 |  | Tower A | Super Structure | L58 | Façade | Façade Works
44115 | Tower A - Super Structure - Finishes & MEP - L58 to L63 | Not Ready | Façade Works - MEP & Finishes | 2026-04-13 | 2026-04-23 | Fixing of Backlit Laminated Glass assembly & ACP Panels | 100 | 0 |  | 2026-03-13 |  | 2026-03-25 |  | Tower A | Super Structure | L58 | Façade | Façade Works
44116 | Tower A - Super Structure - Finishes & MEP - L58 to L63 | Not Ready | Façade Works - MEP & Finishes | 2026-04-13 | 2026-04-23 | Fixing of Louvers | 100 | 0 |  | 2026-03-13 |  | 2026-03-25 |  | Tower A | Super Structure | L58 | Façade | Façade Works
44116 | Tower A - Super Structure - Finishes & MEP - L58 to L63 | Not Ready | Façade Works - MEP & Finishes | 2026-04-13 | 2026-04-23 | Fixing of Louvers | 100 | 0 |  | 2026-03-13 |  | 2026-03-25 |  | Tower A | Super Structure | L58
48037 |  | Not Committed |  | 2025-11-20 | 2026-05-06 | Super-Structure_Club House | 100 | 0 |  | 2026-03-13 |  | 2026-09-02
48038 |  | Not Committed |  | 2025-11-20 | 2026-01-12 | CH00-CH01 (4.7m) | 100 | 0 |  | 2026-03-13 |  | 2026-05-05
48039 | Club House - Super structure - CH00 to CH01 | Not Ready |  | 2025-11-20 | 2025-12-24 | Columns_CH | 100 | 0 |  | 2026-03-13 |  | 2026-04-16 |  | Club House | Super Structure | CH00
48040 | Club House - Super structure - CH00 to CH01 | Not Ready |  | 2025-11-20 | 2025-12-12 | Staircase_CH | 100 | 0 |  | 2026-03-13 |  | 2026-04-04 |  | Club House | Super Structure | CH00
8613 | T-14-3rd Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-02-26 | 2026-05-05 | 2nd Coat Painting | 100 | 0 |  | 2026-03-14 |  | 2026-05-21
8722 | T-14-7th Floor Common Area | Not Ready | Door-Shaft | 2026-02-07 | 2026-02-20 | Door-Shaft | 100 | 0 |  | 2026-03-14 |  | 2026-03-27
8794 | T-14-10th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-02-14 | 2026-05-09 | 1st Coat Painting | 100 | 0 |  | 2026-03-14 |  | 2026-06-05
8816 | T-14-11th Floor Flat Area | Not Ready | Putty | 2026-02-11 | 2026-05-06 | Putty | 100 | 0 |  | 2026-03-14 |  | 2026-06-06
11894 | T-18-8th Floor Common Area | Not Ready | Door-Shaft | 2026-05-29 | 2026-06-11 | Door-Shaft | 100 | 0 |  | 2026-03-14 |  | 2026-03-27
41312 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-02-21 | 2026-02-24 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-03-14 |  | 2026-03-18 |  | Tower A | Super Structure | L22
8844 | T-14-12th Floor Flat Area | Not Ready | Door | 2026-03-09 | 2026-04-01 | Door | 100 | 0 |  | 2026-03-15 |  | 2026-04-09
10151 | T-21-1st Floor Common Area | Not Ready | Putty | 2026-04-16 | 2026-05-25 | Putty | 100 | 0 |  | 2026-03-15 |  | 2026-04-24
10856 | T-20-8th Floor Common Area | Not Ready | 1st Coat Painting | 2026-04-09 | 2026-05-02 | 1st Coat Painting | 100 | 0 |  | 2026-03-15 |  | 2026-04-06
11322 | T-19-6th Floor Common Area | Not Ready | Door-Shaft | 2026-03-29 | 2026-04-11 | Door-Shaft | 100 | 0 |  | 2026-03-15 |  | 2026-03-29
9244 | T-15-6th Floor Common Area | Not Ready | 1st Coat Painting | 2026-03-13 | 2026-04-05 | 1st Coat Painting | 100 | 0 |  | 2026-03-16 |  | 2026-04-07
9708 | T-16-4th Floor Common Area | Not Ready | Flooring & skirting | 2026-04-03 | 2026-04-25 | Flooring & skirting | 100 | 0 |  | 2026-03-16 |  | 2026-04-07
9735 | T-16-5th Floor Common Area | Not Ready | Putty | 2026-04-03 | 2026-05-12 | Putty | 100 | 0 |  | 2026-03-16 |  | 2026-04-23
9838 | T-16-9th Floor Common Area | Not Ready | Flooring & skirting | 2026-04-09 | 2026-04-30 | Flooring & skirting | 100 | 0 |  | 2026-03-16 |  | 2026-04-07
11439 | T-19-11th Floor Flat Area | Not Ready | Toilet flooring | 2026-03-31 | 2026-05-04 | Toilet flooring | 100 | 0 |  | 2026-03-16 |  | 2026-04-19
43244 |  | Not Committed |  | 2026-02-20 | 2026-10-31 | L65-66 (Refuge) (Club House) | 100 | 0 |  | 2026-03-16 |  | 2026-10-14
43245 |  | Not Committed |  | 2026-02-20 | 2026-04-08 | MEP 1st Fixes | 100 | 0 |  | 2026-03-16 |  | 2026-04-30
43246 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-02-20 | 2026-03-10 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-03-16 |  | 2026-04-01 |  | Tower A | Super Structure | L65 | MEP | FPS 1st Fix - MEP & Finishes
43247 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-02-20 | 2026-03-04 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-03-16 |  | 2026-03-26 |  | Tower A | Super Structure | L65 | MEP | Electrical 1st Fixes
43248 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-02-20 | 2026-03-10 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-03-16 |  | 2026-04-01 |  | Tower A | Super Structure | L65
43249 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-02-20 | 2026-03-27 | Wet Area Waterproofing | 100 | 0 |  | 2026-03-16 |  | 2026-04-18 |  | Tower A | Super Structure | L65
45963 |  | Not Committed |  | 2026-01-08 | 2026-12-23 | P4-5 Level | 100 | 0 |  | 2026-03-16 |  | 2027-03-04
45978 |  | Not Committed |  | 2026-01-08 | 2026-05-07 | Floor Area | 100 | 0 |  | 2026-03-16 |  | 2026-07-14
45979 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | Ceiling Painting/ PT Marking - MEP & Finishes | 2026-01-08 | 2026-01-13 | Ceiling Painting/ PT Marking | 100 | 0 |  | 2026-03-16 |  | 2026-03-21 |  | Tower B | Super Structure |  | Finishes | Ceiling Painting/ PT Marking
46007 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-01-08 | 2026-01-31 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-03-16 |  | 2026-04-08 |  | Tower B | Super Structure |  | MEP | FPS 1st Fix - MEP & Finishes
46008 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-01-08 | 2026-01-31 | PHE 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-03-16 |  | 2026-04-08 |  | Tower B | Super Structure
46009 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-01-08 | 2026-01-24 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-03-16 |  | 2026-04-02 |  | Tower B | Super Structure |  | MEP | Electrical 1st Fixes
46038 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-01-08 | 2026-01-24 | HVAC Ducting/ Fan Installations | 100 | 0 |  | 2026-03-16 |  | 2026-04-02 |  | Tower B | Super Structure |  | MEP | HVAC Ducting
8835 | T-14-12th Floor Flat Area | Not Ready | Waterproofing | 2026-02-13 | 2026-03-18 | Waterproofing | 100 | 0 |  | 2026-03-17 |  | 2026-04-17
9806 | T-16-8th Floor Flat Area | Not Ready | Door | 2026-04-21 | 2026-05-13 | Door | 100 | 0 |  | 2026-03-17 |  | 2026-04-07
9881 | T-16-11th Floor Flat Area | Not Ready | Flooring & skirting | 2026-04-03 | 2026-05-18 | Flooring & skirting | 100 | 0 |  | 2026-03-17 |  | 2026-04-30
10412 | T-21-11th Floor Common Area | Not Ready | Door-Shaft | 2026-04-27 | 2026-05-11 | Door-Shaft | 100 | 0 |  | 2026-03-17 |  | 2026-03-31
10419 | T-21-Lift | Not Ready | STAIRCASE HR | 2026-04-22 | 2026-06-27 | Staircase Headrooms | 100 | 0 |  | 2026-03-17 |  | 2026-05-24
10881 | T-20-9th Floor Common Area | Not Ready | Window-Open Area | 2026-04-18 | 2026-04-26 | Window-Open Area | 100 | 0 |  | 2026-03-17 |  | 2026-03-24
11479 |  | Not Ready |  | 2026-05-07 | 2026-10-09 | Staircase-1 | 100 | 0 |  | 2026-03-17 |  | 2026-08-20
41027 |  | Not Committed |  | 2026-02-21 | 2026-12-19 | L75-76 | 100 | 0 |  | 2026-03-17 |  | 2026-12-28
41027 |  | Not Committed |  | 2026-02-21 | 2026-12-19 | L75-76 | 100 | 0 |  | 2026-03-17 |  | 2026-12-28 |  |  |  |  | Finishes | Gypsum Plastering Works
41032 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2026-02-21 | 2026-02-24 | Lobby Blockwork | 100 | 0 |  | 2026-03-17 |  | 2026-03-20 |  | Tower A | Super Structure | L75 | Finishes | Blockwork
41298 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-02-24 | 2026-02-28 | Final Painting | 100 | 0 |  | 2026-03-17 |  | 2026-03-23 |  | Tower A | Super Structure | L21 | Finishes | Final Painting
41298 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-02-24 | 2026-02-28 | Final Painting | 100 | 0 |  | 2026-03-17 |  | 2026-03-23 |  | Tower A | Super Structure | L21 | Finishes | Final Painting
41298 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-02-24 | 2026-02-28 | Final Painting | 100 | 0 |  | 2026-03-17 |  | 2026-03-23 |  | Tower A | Super Structure | L21 | Finishes | Final Painting
41339 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-02-24 | 2026-03-04 | False Ceiling | 100 | 0 |  | 2026-03-17 |  | 2026-03-25 |  | Tower A | Super Structure | L24 | Finishes | False Ceiling
41367 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-02-24 | 2026-03-04 | HVAC Ducting | 100 | 0 |  | 2026-03-17 |  | 2026-03-25 |  | Tower A | Super Structure | L26 | MEP | HVAC Ducting
41945 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2026-02-14 | 2026-02-19 | Lobby Plastering | 100 | 0 |  | 2026-03-17 |  | 2026-03-23 |  | Tower A | Super Structure | L62 | Finishes | Lobby Plastering
41955 |  | Not Committed |  | 2026-02-14 | 2026-10-12 | L63-64 | 100 | 0 |  | 2026-03-17 |  | 2026-10-19
41955 |  | Not Committed |  | 2026-02-14 | 2026-10-12 | L63-64 | 100 | 0 |  | 2026-03-17 |  | 2026-10-19 |  |  |  |  | Finishes | Gypsum Plastering Works
41960 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2026-02-14 | 2026-02-17 | Lobby Blockwork | 100 | 0 |  | 2026-03-17 |  | 2026-03-20 |  | Tower A | Super Structure | L63 | Finishes | Blockwork
42137 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2026-02-21 | 2026-02-26 | Lobby Plastering | 100 | 0 |  | 2026-03-17 |  | 2026-03-23 |  | Tower A | Super Structure | L74 | Finishes | Lobby Plastering
45291 | Tower B - Super Structure - Core & Outer Slab L13-14 | Not Ready | RCC Works - Slab | 2026-01-09 | 2026-01-16 | Outer Slab_TA | 100 | 0 |  | 2026-03-17 |  | 2026-03-25 |  | Tower B | Super Structure | L13 | RCC Sub Structure | RCC Works - Slab
9216 | T-15-5th Floor Common Area | Not Ready | Door-Shaft | 2026-03-14 | 2026-03-28 | Door-Shaft | 100 | 0 |  | 2026-03-18 |  | 2026-03-29
9366 | T-15-11th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-04-01 | 2026-06-23 | 1st Coat Painting | 100 | 0 |  | 2026-03-18 |  | 2026-06-09
10259 | T-21-5th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-04-20 | 2026-05-23 | 2nd Coat Painting | 100 | 0 |  | 2026-03-18 |  | 2026-04-21
10387 | T-21-11th Floor Common Area | Not Ready | Window-Open Area | 2026-04-23 | 2026-05-02 | Window-Open Area | 100 | 0 |  | 2026-03-18 |  | 2026-03-25
10938 | T-20-Lift | Not Ready | LMR ROOM | 2026-04-29 | 2026-07-04 | Lift Machine Rooms | 100 | 0 |  | 2026-03-18 |  | 2026-05-25
10940 | T-20-Lift | Not Ready | PARAPET | 2026-04-27 | 2026-07-02 | Parapets | 100 | 0 |  | 2026-03-18 |  | 2026-05-24
12000 | T-18-Staircase 1 | Not Ready |  | 2026-06-03 | 2026-06-14 | TF-12F | 100 | 0 |  | 2026-03-18 |  | 2026-03-31
40313 |  | Not Committed |  | 2026-02-11 | 2026-04-04 | L76-77 | 100 | 0 |  | 2026-03-18 |  | 2026-04-27
40313 |  | Not Committed |  | 2026-02-11 | 2026-04-04 | L76-77 | 100 | 0 |  | 2026-03-18 |  | 2026-04-27 |  |  |  |  | Finishes | Gypsum Plastering Works
40314 | Tower A - Super Structure - Finishes & MEP - L76 to L77 | Not Ready | Partition Wall-Blockwork | 2026-02-11 | 2026-02-27 | De-shuttering & Area clearance | 100 | 0 |  | 2026-03-18 |  | 2026-04-04 |  | Tower A | Super Structure | L76
40424 | Tower A - Super Structure - Finishes & MEP - L66 to L67 | Not Ready | Partition Wall-Blockwork | 2026-02-23 | 2026-02-27 | Staircase Area | 100 | 0 |  | 2026-03-18 |  | 2026-03-23 |  | Tower A | Super Structure | L66
40427 | Tower A - Super Structure - Finishes & MEP - L67 to L68 | Not Ready | Partition Wall-Blockwork | 2026-02-23 | 2026-03-02 | Partition Walls | 100 | 0 |  | 2026-03-18 |  | 2026-03-25 |  | Tower A | Super Structure | L67
41313 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-02-25 | 2026-03-02 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-03-18 |  | 2026-03-24 |  | Tower A | Super Structure | L22 | MEP | Electrical
41324 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-02-25 | 2026-02-27 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-03-18 |  | 2026-03-21 |  | Tower A | Super Structure | L23 | MEP | FPS 2nd Fix - MEP & Finishes
41325 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-02-25 | 2026-03-02 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-03-18 |  | 2026-03-24 |  | Tower A | Super Structure | L23 | MEP | Electrical 2nd Fix - MEP & Finishes
41326 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-02-25 | 2026-03-05 | FAPA Device Fixing | 100 | 0 |  | 2026-03-18 |  | 2026-03-26 |  | Tower A | Super Structure | L23
41326 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-02-25 | 2026-03-05 | FAPA Device Fixing | 100 | 0 |  | 2026-03-18 |  | 2026-03-26 |  | Tower A | Super Structure | L23
41326 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-02-25 | 2026-03-05 | FAPA Device Fixing | 100 | 0 |  | 2026-03-18 |  | 2026-03-26 |  | Tower A | Super Structure | L23
41326 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-02-25 | 2026-03-05 | FAPA Device Fixing | 100 | 0 |  | 2026-03-18 |  | 2026-03-26 |  | Tower A | Super Structure | L23
41327 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-02-25 | 2026-02-27 | HVAC Grill Fixing | 100 | 0 |  | 2026-03-18 |  | 2026-03-21 |  | Tower A | Super Structure | L23 | MEP | HVAC Grill Fixing
41354 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-02-25 | 2026-03-09 | Flooring & Dado | 100 | 0 |  | 2026-03-18 |  | 2026-03-30 |  | Tower A | Super Structure | L25 | Finishes | Flooring & Dado
44581 |  | Not Committed |  | 2026-03-20 | 2026-08-21 | Final MEP fix & Finishes (after Tower A High Side) | 100 | 0 |  | 2026-03-18 |  | 2026-08-04
44582 |  | Not Committed |  | 2026-03-20 | 2026-04-30 | B3 to B2 | 100 | 0 |  | 2026-03-18 |  | 2026-04-28
44582 |  | Not Committed |  | 2026-03-20 | 2026-04-30 | B3 to B2 | 100 | 0 |  | 2026-03-18 |  | 2026-04-28
44582 |  | Not Committed |  | 2026-03-20 | 2026-04-30 | B3 to B2 | 100 | 0 |  | 2026-03-18 |  | 2026-04-28
44583 |  | Not Ready | MEP fix & Finishes | 2026-03-20 | 2026-03-27 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2026-03-18 |  | 2026-03-25 |  |  |  |  | MEP | FPS final fixes
44583 |  | Not Ready | MEP fix & Finishes | 2026-03-20 | 2026-03-27 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2026-03-18 |  | 2026-03-25 |  |  |  |  | MEP | FPS final fixes
44630 |  | Not Committed |  | 2026-03-20 | 2026-07-04 | Landscape on P5 level | 100 | 0 |  | 2026-03-18 |  | 2026-07-02
44631 |  | Not Ready | MEP fix & Finishes | 2026-03-20 | 2026-05-12 | Above Terrace Structure/ Hardscape works | 100 | 0 |  | 2026-03-18 |  | 2026-05-09
44631 |  | Not Ready | MEP fix & Finishes | 2026-03-20 | 2026-05-12 | Above Terrace Structure/ Hardscape works | 100 | 0 |  | 2026-03-18 |  | 2026-05-09
44632 |  | Not Ready | MEP fix & Finishes | 2026-03-20 | 2026-05-12 | Tower A canopy at P5 | 100 | 0 |  | 2026-03-18 |  | 2026-05-09
44632 |  | Not Ready | MEP fix & Finishes | 2026-03-20 | 2026-05-12 | Tower A canopy at P5 | 100 | 0 |  | 2026-03-18 |  | 2026-05-09
8698 | T-14-6th Floor Common Area | Not Ready | 1st Coat Painting | 2026-02-12 | 2026-03-05 | 1st Coat Painting | 100 | 0 |  | 2026-03-19 |  | 2026-04-09
8814 | T-14-11th Floor Flat Area | Not Ready | Toilets False Celing | 2026-02-16 | 2026-03-21 | Toilets False Celing | 100 | 0 |  | 2026-03-19 |  | 2026-04-21
9831 | T-16-9th Floor Flat Area | Not Ready | Window | 2026-04-23 | 2026-05-15 | Window | 100 | 0 |  | 2026-03-19 |  | 2026-04-10
10443 | T-21-Staircase 1 | Not Ready |  | 2026-04-16 | 2026-04-27 | 10F-09F | 100 | 0 |  | 2026-03-19 |  | 2026-03-28
10457 | T-21-Staircase 2 | Not Ready |  | 2026-04-16 | 2026-04-27 | 11F-10F | 100 | 0 |  | 2026-03-19 |  | 2026-03-28
11420 | T-19-10th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-04-07 | 2026-06-29 | 1st Coat Painting | 100 | 0 |  | 2026-03-19 |  | 2026-06-11
11442 | T-19-11th Floor Flat Area | Not Ready | Putty | 2026-04-03 | 2026-06-25 | Putty | 100 | 0 |  | 2026-03-19 |  | 2026-06-11
40059 | Tower A - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2026-02-24 | 2026-03-04 | Jump platform installation | 100 | 0 |  | 2026-03-19 |  | 2026-03-27 |  | Tower A | Super Structure
40059 | Tower A - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2026-02-24 | 2026-03-04 | Jump platform installation | 100 | 0 |  | 2026-03-19 |  | 2026-03-27 |  | Tower A | Super Structure
40059 | Tower A - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2026-02-24 | 2026-03-04 | Jump platform installation | 100 | 0 |  | 2026-03-19 |  | 2026-03-27 |  | Tower A | Super Structure
40538 | Tower A - Super Structure - Finishes & MEP - L64 to L65 | Not Ready | Gypsum Plastering Works | 2026-02-24 | 2026-03-13 | L64-65 | 100 | 0 |  | 2026-03-19 |  | 2026-04-04 |  | Tower A | Super Structure | L64 | Finishes | Gypsum Plastering Works
40538 | Tower A - Super Structure - Finishes & MEP - L64 to L65 | Not Ready | Gypsum Plastering Works | 2026-02-24 | 2026-03-13 | L64-65 | 100 | 0 |  | 2026-03-19 |  | 2026-04-04 |  | Tower A | Super Structure | L64
41383 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-02-25 | 2026-03-06 | HVAC Ducting | 100 | 0 |  | 2026-03-19 |  | 2026-03-27 |  | Tower A | Super Structure | L27 | MEP | HVAC Ducting
43092 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-04-18 | 2026-05-06 | Flooring & Dado works | 100 | 0 |  | 2026-03-19 |  | 2026-04-06 |  | Tower A | Super Structure | L56 | Finishes | Flooring & Dado
43145 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-02-24 | 2026-03-04 | Door & Window Frame work | 100 | 0 |  | 2026-03-19 |  | 2026-03-26 |  | Tower A | Super Structure | L59 | Finishes | Door & Window Frame work
44118 |  | Not Ready |  | 2026-04-18 | 2026-05-23 | L63-68 (double ht. for CH) | 100 | 0 |  | 2026-03-19 |  | 2026-04-23
44119 | Tower A - Super Structure - Finishes & MEP - L63 to L68 | Not Ready | Façade Works - MEP & Finishes | 2026-04-18 | 2026-04-29 | Al. Frame section (Mullion & Transom) Installation | 100 | 0 |  | 2026-03-19 |  | 2026-03-31 |  | Tower A | Super Structure | L63 | Façade | Façade Works
46678 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-01-12 | 2026-01-29 | Wet Area Waterproofing | 100 | 0 |  | 2026-03-19 |  | 2026-04-06 |  | Tower B | Super Structure | L8
8670 | T-14-5th Floor Common Area | Not Ready | Door-Shaft | 2026-02-13 | 2026-02-26 | Door-Shaft | 100 | 0 |  | 2026-03-20 |  | 2026-04-02
10751 | T-20-4th Floor Common Area | Not Ready | Window-Open Area | 2026-04-13 | 2026-04-21 | Window-Open Area | 100 | 0 |  | 2026-03-20 |  | 2026-03-27
10906 | T-20-11th Floor Common Area | Not Ready | Door-Shaft | 2026-04-22 | 2026-05-06 | Door-Shaft | 100 | 0 |  | 2026-03-20 |  | 2026-04-03
10962 | T-20-Staircase 1 | Not Ready |  | 2026-04-16 | 2026-04-27 | 11F-10F | 100 | 0 |  | 2026-03-20 |  | 2026-03-31
10976 | T-20-Staircase 2 | Not Ready |  | 2026-04-16 | 2026-04-27 | 12F-11F | 100 | 0 |  | 2026-03-20 |  | 2026-03-31
11242 | T-19-3rd Floor Common Area | Not Ready | Flooring & skirting | 2026-04-03 | 2026-04-25 | Flooring & skirting | 100 | 0 |  | 2026-03-20 |  | 2026-04-11
11269 | T-19-4th Floor Common Area | Not Ready | Putty | 2026-04-03 | 2026-05-13 | Putty | 100 | 0 |  | 2026-03-20 |  | 2026-04-25
11399 | T-19-9th Floor Common Area | Not Ready | Putty | 2026-04-09 | 2026-05-18 | Putty | 100 | 0 |  | 2026-03-20 |  | 2026-04-26
11418 | T-19-10th Floor Flat Area | Not Ready | Door | 2026-04-23 | 2026-05-16 | Door | 100 | 0 |  | 2026-03-20 |  | 2026-04-13
11443 | T-19-11th Floor Flat Area | Not Ready | Window | 2026-04-23 | 2026-05-16 | Window | 100 | 0 |  | 2026-03-20 |  | 2026-04-13
41033 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2026-02-25 | 2026-03-02 | Lobby Plastering | 100 | 0 |  | 2026-03-20 |  | 2026-03-26 |  | Tower A | Super Structure | L75 | Finishes | Lobby Plastering
41043 |  | Not Committed |  | 2026-02-25 | 2026-12-26 | L76-77 | 100 | 0 |  | 2026-03-20 |  | 2027-01-02
41043 |  | Not Committed |  | 2026-02-25 | 2026-12-26 | L76-77 | 100 | 0 |  | 2026-03-20 |  | 2027-01-02 |  |  |  |  | Finishes | Gypsum Plastering Works
41048 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2026-02-25 | 2026-02-27 | Lobby Blockwork | 100 | 0 |  | 2026-03-20 |  | 2026-03-24 |  | Tower A | Super Structure | L76 | Finishes | Blockwork
41961 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2026-02-18 | 2026-02-23 | Lobby Plastering | 100 | 0 |  | 2026-03-20 |  | 2026-03-26 |  | Tower A | Super Structure | L63 | Finishes | Lobby Plastering
41971 |  | Not Committed |  | 2026-02-18 | 2026-10-17 | L64-65 | 100 | 0 |  | 2026-03-20 |  | 2026-10-26
41971 |  | Not Committed |  | 2026-02-18 | 2026-10-17 | L64-65 | 100 | 0 |  | 2026-03-20 |  | 2026-10-26 |  |  |  |  | Finishes | Gypsum Plastering Works
41976 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2026-02-18 | 2026-02-20 | Lobby Blockwork | 100 | 0 |  | 2026-03-20 |  | 2026-03-24 |  | Tower A | Super Structure | L64 | Finishes | Blockwork
43197 |  | Not Committed |  | 2026-02-25 | 2026-05-30 | Finishes after 1st Fix | 100 | 0 |  | 2026-03-20 |  | 2026-05-08
43198 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-02-25 | 2026-03-20 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-03-20 |  | 2026-04-11 |  | Tower A | Super Structure | L62 | Finishes | Blockwork
45444 | Tower B - Super Structure - Finishes & MEP - L9 to L10 | Not Ready | Partition Wall-Blockwork | 2026-01-13 | 2026-01-17 | Staircase Area | 100 | 0 |  | 2026-03-20 |  | 2026-03-26 |  | Tower B | Super Structure | L9
48205 |  | Not Committed |  | 2025-11-27 | 2026-06-06 | Retail Area Masonry (GF to P4) | 100 | 0 |  | 2026-03-20 |  | 2026-12-04
48207 | Retail - Super structure - R1 to CH00 | Not Ready |  | 2025-11-27 | 2026-01-07 | R1 to CH00 | 100 | 0 |  | 2026-03-20 |  | 2026-04-29 |  | Retail | Super Structure
9400 | T-15-Staircase 1 | Not Ready |  | 2026-04-01 | 2026-04-11 | TF-12F | 100 | 0 |  | 2026-03-21 |  | 2026-03-30
10205 | T-21-3rd Floor Common Area | Not Ready | Window-Open Area | 2026-04-23 | 2026-05-02 | Window-Open Area | 100 | 0 |  | 2026-03-21 |  | 2026-03-28
11870 | T-18-7th Floor Common Area | Not Ready | 1st Coat Painting | 2026-06-02 | 2026-06-24 | 1st Coat Painting | 100 | 0 |  | 2026-03-21 |  | 2026-04-14
39258 | Retail - Sub structure - B3 to B2 | Not Ready | RCC Works - Slab | 2025-10-11 | 2025-10-30 | Slab_NTA | 100 | 0 |  | 2026-03-21 |  | 2026-04-08 |  | Retail | Sub Structure | B3 | RCC Sub Structure | RCC Works - Slab
39258 | Retail - Sub structure - B3 to B2 | Not Ready | RCC Works - Slab | 2025-10-11 | 2025-10-30 | Slab_NTA | 100 | 0 |  | 2026-03-21 |  | 2026-04-08 |  | Retail | Sub Structure | B3
41328 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-02-28 | 2026-03-04 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-03-21 |  | 2026-03-25 |  | Tower A | Super Structure | L23
41399 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-02-27 | 2026-03-09 | HVAC Ducting | 100 | 0 |  | 2026-03-21 |  | 2026-03-28 |  | Tower A | Super Structure | L28 | MEP | HVAC Ducting
45936 |  | Not Committed |  | 2026-01-14 | 2027-01-01 | P3-4 Level | 100 | 0 |  | 2026-03-21 |  | 2027-03-12
45951 |  | Not Committed |  | 2026-01-14 | 2026-05-13 | Floor Area | 100 | 0 |  | 2026-03-21 |  | 2026-07-21
45952 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | Ceiling Painting/ PT Marking - MEP & Finishes | 2026-01-14 | 2026-01-19 | Ceiling Painting/ PT Marking | 100 | 0 |  | 2026-03-21 |  | 2026-03-27 |  | Tower B | Super Structure |  | Finishes | Ceiling Painting/ PT Marking
45980 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-01-14 | 2026-02-06 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-03-21 |  | 2026-04-14 |  | Tower B | Super Structure |  | MEP | FPS 1st Fix - MEP & Finishes
45981 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-01-14 | 2026-02-06 | PHE 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-03-21 |  | 2026-04-14 |  | Tower B | Super Structure
45982 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-01-14 | 2026-01-31 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-03-21 |  | 2026-04-08 |  | Tower B | Super Structure |  | MEP | Electrical 1st Fixes
46011 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-01-14 | 2026-01-31 | HVAC Ducting/ Fan Installations | 100 | 0 |  | 2026-03-21 |  | 2026-04-08 |  | Tower B | Super Structure |  | MEP | HVAC Ducting
46037 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-01-14 | 2026-01-24 | FAPA Cabling | 100 | 0 |  | 2026-03-21 |  | 2026-04-02 |  | Tower B | Super Structure
46661 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-01-14 | 2026-01-24 | Cement Plastering in wet areas | 100 | 0 |  | 2026-03-21 |  | 2026-04-02 |  | Tower B | Super Structure | L7
10936 |  | Not Ready |  | 2026-04-27 | 2026-12-03 | TF | 100 | 0 |  | 2026-03-22 |  | 2026-10-27
10937 |  | Not Ready |  | 2026-04-27 | 2026-12-03 | Finishing Works | 100 | 0 |  | 2026-03-22 |  | 2026-10-27
10992 | T-20- Elevation-B | Not Ready |  | 2026-04-22 | 2026-07-14 | Elevation-B | 100 | 0 |  | 2026-03-22 |  | 2026-06-14
11964 | T-18-11th Floor Flat Area | Not Ready | Door | 2026-06-01 | 2026-06-23 | Door | 100 | 0 |  | 2026-03-22 |  | 2026-04-16
8825 | T-14-11th Floor Common Area | Not Ready | Putty | 2026-02-24 | 2026-04-04 | Putty | 100 | 0 |  | 2026-03-23 |  | 2026-05-01
9269 | T-15-7th Floor Common Area | Not Ready | Window-Open Area | 2026-03-21 | 2026-03-31 | Window-Open Area | 100 | 0 |  | 2026-03-23 |  | 2026-03-30
10946 | T-20-Lift Lobby | Not Ready |  | 2026-04-22 | 2026-05-09 | 11F | 100 | 0 |  | 2026-03-23 |  | 2026-04-11
41415 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-03-02 | 2026-03-11 | HVAC Ducting | 100 | 0 |  | 2026-03-23 |  | 2026-03-31 |  | Tower A | Super Structure | L29 | MEP | HVAC Ducting
43972 | Tower A - Super Structure - Finishes & MEP - L7 to L15 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-04-22 | 2026-05-04 | Staircase cabling | 100 | 0 |  | 2026-03-23 |  | 2026-04-03 |  | Tower A | Super Structure | L7
45611 | Tower B - Super Structure - Finishes & MEP - L8 to L9 | Not Ready | Gypsum Plastering Works | 2026-01-15 | 2026-03-04 | L8-9 | 100 | 0 |  | 2026-03-23 |  | 2026-05-09 |  | Tower B | Super Structure | L8 | Finishes | Gypsum Plastering Works
45611 | Tower B - Super Structure - Finishes & MEP - L8 to L9 | Not Ready | Gypsum Plastering Works | 2026-01-15 | 2026-03-04 | L8-9 | 100 | 0 |  | 2026-03-23 |  | 2026-05-09 |  | Tower B | Super Structure | L8
9813 | T-16-8th Floor Common Area | Not Ready | Putty | 2026-04-14 | 2026-05-23 | Putty | 100 | 0 |  | 2026-03-24 |  | 2026-05-01
10337 | T-21-8th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-05-02 | 2026-06-04 | 2nd Coat Painting | 100 | 0 |  | 2026-03-24 |  | 2026-04-27
10427 | T-21-Lift Lobby | Not Ready |  | 2026-04-27 | 2026-05-14 | 10F | 100 | 0 |  | 2026-03-24 |  | 2026-04-12
11440 | T-19-11th Floor Flat Area | Not Ready | Toilets False Celing | 2026-04-09 | 2026-05-13 | Toilets False Celing | 100 | 0 |  | 2026-03-24 |  | 2026-04-23
11971 | T-18-11th Floor Common Area | Not Ready | Putty | 2026-06-09 | 2026-07-17 | Putty | 100 | 0 |  | 2026-03-24 |  | 2026-04-30
40125 |  | Not Committed |  | 2026-02-23 | 2026-09-01 | STP (GF-P1-P2 in Zone 2) | 100 | 0 |  | 2026-03-24 |  | 2026-10-01
40126 | Tower A - Super Structure - Finishes & MEP - STP | Not Ready |  | 2026-02-23 | 2026-07-16 | Equipment Installation | 100 | 0 |  | 2026-03-24 |  | 2026-08-21 |  | Tower A | Super Structure
40932 | Tower A - Super Structure - Finishes & MEP - L65 to Terrace | Not Ready |  | 2026-02-17 | 2026-04-10 | FHC & Accessories fixing | 100 | 0 |  | 2026-03-24 |  | 2026-05-16 |  | Tower A | Super Structure | L65
40934 | Tower A - Super Structure - Finishes & MEP - L65 to Terrace | Not Ready |  | 2026-02-17 | 2026-04-10 | Soil & Waste Downtake piping in Plumbing Shaft | 100 | 0 |  | 2026-03-24 |  | 2026-05-16 |  | Tower A | Super Structure | L65
40938 | Tower A - Super Structure - Finishes & MEP - L65 to Terrace | Not Ready |  | 2026-02-17 | 2026-04-10 | HVAC Shaft Ducting | 100 | 0 |  | 2026-03-24 |  | 2026-05-16 |  | Tower A | Super Structure | L65 | MEP | HVAC Grill Fixing
41049 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2026-02-28 | 2026-03-06 | Lobby Plastering | 100 | 0 |  | 2026-03-24 |  | 2026-03-30 |  | Tower A | Super Structure | L76 | Finishes | Lobby Plastering
41314 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-03-04 | 2026-03-09 | Final Painting | 100 | 0 |  | 2026-03-24 |  | 2026-03-30 |  | Tower A | Super Structure | L22 | Finishes | Final Painting
41314 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-03-04 | 2026-03-09 | Final Painting | 100 | 0 |  | 2026-03-24 |  | 2026-03-30 |  | Tower A | Super Structure | L22 | Finishes | Final Painting
41314 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-03-04 | 2026-03-09 | Final Painting | 100 | 0 |  | 2026-03-24 |  | 2026-03-30 |  | Tower A | Super Structure | L22 | Finishes | Final Painting
41355 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-03-04 | 2026-03-11 | False Ceiling | 100 | 0 |  | 2026-03-24 |  | 2026-04-01 |  | Tower A | Super Structure | L25 | Finishes | False Ceiling
41977 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2026-02-21 | 2026-02-26 | Lobby Plastering | 100 | 0 |  | 2026-03-24 |  | 2026-03-30 |  | Tower A | Super Structure | L64 | Finishes | Lobby Plastering
41987 |  | Not Committed |  | 2026-02-21 | 2026-10-24 | L65-66 | 100 | 0 |  | 2026-03-24 |  | 2026-10-31
41987 |  | Not Committed |  | 2026-02-21 | 2026-10-24 | L65-66 | 100 | 0 |  | 2026-03-24 |  | 2026-10-31 |  |  |  |  | Finishes | Gypsum Plastering Works
41992 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2026-02-21 | 2026-02-24 | Lobby Blockwork | 100 | 0 |  | 2026-03-24 |  | 2026-03-27 |  | Tower A | Super Structure | L65 | Finishes | Blockwork
42147 |  | Not Committed |  | 2026-02-28 | 2026-12-30 | L77-78 | 100 | 0 |  | 2026-03-24 |  | 2027-01-06
42147 |  | Not Committed |  | 2026-02-28 | 2026-12-30 | L77-78 | 100 | 0 |  | 2026-03-24 |  | 2027-01-06 |  |  |  |  | Finishes | Gypsum Plastering Works
42152 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2026-02-28 | 2026-03-04 | Lobby Blockwork | 100 | 0 |  | 2026-03-24 |  | 2026-03-27 |  | Tower A | Super Structure | L77 | Finishes | Blockwork
43262 |  | Not Committed |  | 2026-02-28 | 2026-10-12 | L66-67 | 100 | 0 |  | 2026-03-24 |  | 2026-09-23
43262 |  | Not Committed |  | 2026-02-28 | 2026-10-12 | L66-67 | 100 | 0 |  | 2026-03-24 |  | 2026-09-23 |  |  |  |  | Finishes | Gypsum Plastering Works
43263 |  | Not Committed |  | 2026-02-28 | 2026-03-30 | MEP 1st Fixes | 100 | 0 |  | 2026-03-24 |  | 2026-04-21
43264 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-02-28 | 2026-03-09 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-03-24 |  | 2026-03-31 |  | Tower A | Super Structure | L66 | MEP | FPS 1st Fix - MEP & Finishes
43265 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-02-28 | 2026-03-06 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-03-24 |  | 2026-03-28 |  | Tower A | Super Structure | L66 | MEP | Electrical 1st Fixes
43266 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-02-28 | 2026-03-09 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-03-24 |  | 2026-03-31 |  | Tower A | Super Structure | L66
43267 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-02-28 | 2026-03-18 | Wet Area Waterproofing | 100 | 0 |  | 2026-03-24 |  | 2026-04-09 |  | Tower A | Super Structure | L66
44577 |  | Not Committed |  | 2025-08-09 | 2025-12-22 | P4 to P5 | 100 | 0 |  | 2026-03-24 |  | 2026-07-29
44577 |  | Not Committed |  | 2025-08-09 | 2025-12-22 | P4 to P5 | 100 | 0 |  | 2026-03-24 |  | 2026-07-29
44577 |  | Not Committed |  | 2025-08-09 | 2025-12-22 | P4 to P5 | 100 | 0 |  | 2026-03-24 |  | 2026-07-29
44578 | NTA_Zone 2 - Super Structure - P4 to P5 | Not Ready | Finishes (Lobby & Floor Area) | 2025-08-09 | 2025-10-07 | VDF Flooring | 100 | 0 |  | 2026-03-24 |  | 2026-05-15 |  | NTA_Zone 2 | Super Structure
44578 | NTA_Zone 2 - Super Structure - P4 to P5 | Not Ready | Finishes (Lobby & Floor Area) | 2025-08-09 | 2025-10-07 | VDF Flooring | 100 | 0 |  | 2026-03-24 |  | 2026-05-15 |  | NTA_Zone 2 | Super Structure
45593 |  | Not Committed |  | 2026-01-16 | 2027-07-06 | MEP Shaft Masonry | 100 | 0 |  | 2026-03-24 |  | 2027-10-04
45594 | Tower B - Super Structure - Finishes & MEP | Not Ready | MEP Shaft Masonry | 2026-01-16 | 2026-02-14 | B3-GF-L7 | 100 | 0 |  | 2026-03-24 |  | 2026-04-22 |  | Tower B | Super Structure
9136 | T-15-2nd Floor Common Area | Not Ready | Flooring & skirting | 2026-03-19 | 2026-04-11 | Flooring & skirting | 100 | 0 |  | 2026-03-25 |  | 2026-04-15
9163 | T-15-3rd Floor Common Area | Not Ready | Putty | 2026-03-19 | 2026-04-28 | Putty | 100 | 0 |  | 2026-03-25 |  | 2026-05-02
9294 | T-15-8th Floor Common Area | Not Ready | Door-Shaft | 2026-03-26 | 2026-04-08 | Door-Shaft | 100 | 0 |  | 2026-03-25 |  | 2026-04-08
10112 | T-21-GF Flat Area | Not Ready | 2nd Coat Painting | 2026-05-22 | 2026-07-26 | 2nd Coat Painting | 100 | 0 |  | 2026-03-25 |  | 2026-05-29
10667 | T-20-1st Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-05-16 | 2026-07-21 | 2nd Coat Painting | 100 | 0 |  | 2026-03-25 |  | 2026-05-28
10831 | T-20-7th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-04-21 | 2026-05-24 | 2nd Coat Painting | 100 | 0 |  | 2026-03-25 |  | 2026-04-28
10882 | T-20-9th Floor Common Area | Not Ready | 1st Coat Painting | 2026-04-26 | 2026-05-19 | 1st Coat Painting | 100 | 0 |  | 2026-03-25 |  | 2026-04-15
10939 | T-20-Lift | Not Ready | STAIRCASE HR | 2026-05-05 | 2026-07-09 | Staircase Headrooms | 100 | 0 |  | 2026-03-25 |  | 2026-06-01
11817 | T-18-5th Floor Common Area | Not Ready | Window-Open Area | 2026-05-31 | 2026-06-08 | Window-Open Area | 100 | 0 |  | 2026-03-25 |  | 2026-04-02
41329 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-03-05 | 2026-03-10 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-03-25 |  | 2026-03-31 |  | Tower A | Super Structure | L23 | MEP | Electrical
41340 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-03-05 | 2026-03-07 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-03-25 |  | 2026-03-28 |  | Tower A | Super Structure | L24 | MEP | FPS 2nd Fix - MEP & Finishes
41341 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-03-05 | 2026-03-10 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-03-25 |  | 2026-03-31 |  | Tower A | Super Structure | L24 | MEP | Electrical 2nd Fix - MEP & Finishes
41342 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-05 | 2026-03-12 | FAPA Device Fixing | 100 | 0 |  | 2026-03-25 |  | 2026-04-02 |  | Tower A | Super Structure | L24
41342 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-05 | 2026-03-12 | FAPA Device Fixing | 100 | 0 |  | 2026-03-25 |  | 2026-04-02 |  | Tower A | Super Structure | L24
41342 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-05 | 2026-03-12 | FAPA Device Fixing | 100 | 0 |  | 2026-03-25 |  | 2026-04-02 |  | Tower A | Super Structure | L24
41342 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-05 | 2026-03-12 | FAPA Device Fixing | 100 | 0 |  | 2026-03-25 |  | 2026-04-02 |  | Tower A | Super Structure | L24
41343 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-03-05 | 2026-03-07 | HVAC Grill Fixing | 100 | 0 |  | 2026-03-25 |  | 2026-03-28 |  | Tower A | Super Structure | L24 | MEP | HVAC Grill Fixing
41370 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-03-05 | 2026-03-16 | Flooring & Dado | 100 | 0 |  | 2026-03-25 |  | 2026-04-06 |  | Tower A | Super Structure | L26 | Finishes | Flooring & Dado
41431 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-03-05 | 2026-03-12 | HVAC Ducting | 100 | 0 |  | 2026-03-25 |  | 2026-04-02 |  | Tower A | Super Structure | L30 | MEP | HVAC Ducting
43110 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-04-24 | 2026-05-12 | Flooring & Dado works | 100 | 0 |  | 2026-03-25 |  | 2026-04-11 |  | Tower A | Super Structure | L57 | Finishes | Flooring & Dado
44117 | Tower A - Super Structure - Finishes & MEP - L58 to L63 | Not Ready | Façade Works - MEP & Finishes | 2026-04-24 | 2026-05-06 | Accessories & Alignment | 100 | 0 |  | 2026-03-25 |  | 2026-04-06 |  | Tower A | Super Structure | L58 | Façade | Façade Works
44117 | Tower A - Super Structure - Finishes & MEP - L58 to L63 | Not Ready | Façade Works - MEP & Finishes | 2026-04-24 | 2026-05-06 | Accessories & Alignment | 100 | 0 |  | 2026-03-25 |  | 2026-04-06 |  | Tower A | Super Structure | L58
45292 |  | Not Ready |  | 2026-01-17 | 2026-02-02 | L14-15 | 100 | 0 |  | 2026-03-25 |  | 2026-04-09
45292 |  | Not Ready |  | 2026-01-17 | 2026-02-02 | L14-15 | 100 | 0 |  | 2026-03-25 |  | 2026-04-09 |  |  |  |  | Finishes | Gypsum Plastering Works
45293 | Tower B - Super Structure - Core & Outer Slab L14-15 | Not Ready | RCC Works - Vertical | 2026-01-17 | 2026-01-29 | Outer Columns_TA | 100 | 0 |  | 2026-03-25 |  | 2026-04-06 |  | Tower B | Super Structure | L14 | RCC Sub Structure | RCC Works - Vertical
45449 |  | Not Committed |  | 2026-01-17 | 2026-02-18 | L11-12 | 100 | 0 |  | 2026-03-25 |  | 2026-04-25
45449 |  | Not Committed |  | 2026-01-17 | 2026-02-18 | L11-12 | 100 | 0 |  | 2026-03-25 |  | 2026-04-25 |  |  |  |  | Finishes | Gypsum Plastering Works
45450 | Tower B - Super Structure - Finishes & MEP - L11 to L12 | Not Ready | Partition Wall-Blockwork | 2026-01-17 | 2026-02-04 | De-shuttering & Area clearance | 100 | 0 |  | 2026-03-25 |  | 2026-04-11 |  | Tower B | Super Structure | L11
47957 | Tower B | Not Committed | Award of Packages | 2026-02-27 | 2026-09-25 | Elevator | 100 | 0 |  | 2026-03-25 |  | 2026-10-21 |  | Tower B | --
47957 | Tower B | Not Committed | Award of Packages | 2026-02-27 | 2026-09-25 | Elevator | 100 | 0 |  | 2026-03-25 |  | 2026-10-21 |  | Tower B | --
9399 |  | Not Ready |  | 2026-04-01 | 2026-09-02 | Staircase-1 | 100 | 0 |  | 2026-03-26 |  | 2026-08-28
10388 | T-21-11th Floor Common Area | Not Ready | 1st Coat Painting | 2026-05-02 | 2026-05-23 | 1st Coat Painting | 100 | 0 |  | 2026-03-26 |  | 2026-04-19
40428 | Tower A - Super Structure - Finishes & MEP - L67 to L68 | Not Ready | Partition Wall-Blockwork | 2026-03-04 | 2026-03-09 | Staircase Area | 100 | 0 |  | 2026-03-26 |  | 2026-03-31 |  | Tower A | Super Structure | L67
40431 | Tower A - Super Structure - Finishes & MEP - L68 to L69 | Not Ready | Partition Wall-Blockwork | 2026-03-04 | 2026-03-11 | Partition Walls | 100 | 0 |  | 2026-03-26 |  | 2026-04-02 |  | Tower A | Super Structure | L68
44584 |  | Not Ready | MEP fix & Finishes | 2026-03-28 | 2026-04-04 | FAPA Device Fixing | 100 | 0 |  | 2026-03-26 |  | 2026-04-02
44584 |  | Not Ready | MEP fix & Finishes | 2026-03-28 | 2026-04-04 | FAPA Device Fixing | 100 | 0 |  | 2026-03-26 |  | 2026-04-02
44584 |  | Not Ready | MEP fix & Finishes | 2026-03-28 | 2026-04-04 | FAPA Device Fixing | 100 | 0 |  | 2026-03-26 |  | 2026-04-02
44584 |  | Not Ready | MEP fix & Finishes | 2026-03-28 | 2026-04-04 | FAPA Device Fixing | 100 | 0 |  | 2026-03-26 |  | 2026-04-02
44588 |  | Not Committed |  | 2026-03-28 | 2026-05-09 | B2 to B1 | 100 | 0 |  | 2026-03-26 |  | 2026-05-07
44588 |  | Not Committed |  | 2026-03-28 | 2026-05-09 | B2 to B1 | 100 | 0 |  | 2026-03-26 |  | 2026-05-07
44588 |  | Not Committed |  | 2026-03-28 | 2026-05-09 | B2 to B1 | 100 | 0 |  | 2026-03-26 |  | 2026-05-07
44589 |  | Not Ready | MEP fix & Finishes | 2026-03-28 | 2026-04-04 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2026-03-26 |  | 2026-04-02 |  |  |  |  | MEP | FPS final fixes
44589 |  | Not Ready | MEP fix & Finishes | 2026-03-28 | 2026-04-04 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2026-03-26 |  | 2026-04-02 |  |  |  |  | MEP | FPS final fixes
46691 |  | Not Committed |  | 2026-01-19 | 2027-02-22 | L9-10 | 100 | 0 |  | 2026-03-26 |  | 2027-04-26
46691 |  | Not Committed |  | 2026-01-19 | 2027-02-22 | L9-10 | 100 | 0 |  | 2026-03-26 |  | 2027-04-26 |  |  |  |  | Finishes | Gypsum Plastering Works
46692 |  | Not Committed |  | 2026-01-19 | 2026-02-25 | MEP 1st Fixes | 100 | 0 |  | 2026-03-26 |  | 2026-05-04
46693 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-01-19 | 2026-01-27 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-03-26 |  | 2026-04-03 |  | Tower B | Super Structure | L9 | MEP | FPS 1st Fix - MEP & Finishes
46694 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-01-19 | 2026-01-23 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-03-26 |  | 2026-04-01 |  | Tower B | Super Structure | L9 | MEP | Electrical 1st Fixes
46695 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-01-19 | 2026-01-27 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-03-26 |  | 2026-04-03 |  | Tower B | Super Structure | L9
8590 | T-14-2nd Floor Common Area | Not Ready | Flooring & skirting | 2026-02-18 | 2026-03-12 | Flooring & skirting | 100 | 0 |  | 2026-03-27 |  | 2026-04-18
8617 | T-14-3rd Floor Common Area | Not Ready | Putty | 2026-02-18 | 2026-03-30 | Putty | 100 | 0 |  | 2026-03-27 |  | 2026-05-06
9731 | T-16-5th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-04-25 | 2026-07-01 | 2nd Coat Painting | 100 | 0 |  | 2026-03-27 |  | 2026-06-01
9783 | T-16-7th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-04-25 | 2026-07-01 | 2nd Coat Painting | 100 | 0 |  | 2026-03-27 |  | 2026-06-01
9878 | T-16-11th Floor Flat Area | Not Ready | Dado | 2026-04-14 | 2026-05-12 | Dado | 100 | 0 |  | 2026-03-27 |  | 2026-04-21
10724 | T-20-3rd Floor Common Area | Not Ready | Door-Shaft | 2026-04-22 | 2026-05-06 | Door-Shaft | 100 | 0 |  | 2026-03-27 |  | 2026-04-10
11450 | T-19-11th Floor Common Area | Not Ready | Flooring & skirting | 2026-04-20 | 2026-05-13 | Flooring & skirting | 100 | 0 |  | 2026-03-27 |  | 2026-04-16
11845 | T-18-6th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-06-08 | 2026-07-10 | 2nd Coat Painting | 100 | 0 |  | 2026-03-27 |  | 2026-04-28
40060 | Tower A - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2026-03-05 | 2026-03-16 | Guide Rail Installation by rising platform (only car guide rails) | 100 | 0 |  | 2026-03-27 |  | 2026-04-08 |  | Tower A | Super Structure
40539 | Tower A - Super Structure - Finishes & MEP - L65 to L66 | Not Ready | Gypsum Plastering Works | 2026-03-05 | 2026-03-21 | L65-66 | 100 | 0 |  | 2026-03-27 |  | 2026-04-13 |  | Tower A | Super Structure | L65 | Finishes | Gypsum Plastering Works
40539 | Tower A - Super Structure - Finishes & MEP - L65 to L66 | Not Ready | Gypsum Plastering Works | 2026-03-05 | 2026-03-21 | L65-66 | 100 | 0 |  | 2026-03-27 |  | 2026-04-13 |  | Tower A | Super Structure | L65
41386 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-03-06 | 2026-03-18 | Flooring & Dado | 100 | 0 |  | 2026-03-27 |  | 2026-04-08 |  | Tower A | Super Structure | L27 | Finishes | Flooring & Dado
41447 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-03-06 | 2026-03-14 | HVAC Ducting | 100 | 0 |  | 2026-03-27 |  | 2026-04-04 |  | Tower A | Super Structure | L31 | MEP | HVAC Ducting
41993 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2026-02-25 | 2026-03-02 | Lobby Plastering | 100 | 0 |  | 2026-03-27 |  | 2026-04-02 |  | Tower A | Super Structure | L65 | Finishes | Lobby Plastering
42003 |  | Not Committed |  | 2026-02-25 | 2026-10-30 | L66-67 | 100 | 0 |  | 2026-03-27 |  | 2026-11-06
42003 |  | Not Committed |  | 2026-02-25 | 2026-10-30 | L66-67 | 100 | 0 |  | 2026-03-27 |  | 2026-11-06 |  |  |  |  | Finishes | Gypsum Plastering Works
42008 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2026-02-25 | 2026-02-27 | Lobby Blockwork | 100 | 0 |  | 2026-03-27 |  | 2026-03-31 |  | Tower A | Super Structure | L66 | Finishes | Blockwork
42153 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2026-03-05 | 2026-03-10 | Lobby Plastering | 100 | 0 |  | 2026-03-27 |  | 2026-04-02 |  | Tower A | Super Structure | L77 | Finishes | Lobby Plastering
43146 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-04-24 | 2026-05-12 | Flooring & Dado works | 100 | 0 |  | 2026-03-27 |  | 2026-04-13 |  | Tower A | Super Structure | L59 | Finishes | Flooring & Dado
43163 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-03-05 | 2026-03-12 | Door & Window Frame work | 100 | 0 |  | 2026-03-27 |  | 2026-04-03 |  | Tower A | Super Structure | L60 | Finishes | Door & Window Frame work
45447 | Tower B - Super Structure - Finishes & MEP - L10 to L11 | Not Ready | Partition Wall-Blockwork | 2026-01-20 | 2026-01-28 | Partition Walls | 100 | 0 |  | 2026-03-27 |  | 2026-04-04 |  | Tower B | Super Structure | L10
45909 |  | Not Committed |  | 2026-01-20 | 2027-01-09 | P2-3 Level | 100 | 0 |  | 2026-03-27 |  | 2027-03-20
45924 |  | Not Committed |  | 2026-01-20 | 2026-04-01 | Floor Area | 100 | 0 |  | 2026-03-27 |  | 2026-06-08
45925 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | Ceiling Painting/ PT Marking - MEP & Finishes | 2026-01-20 | 2026-01-24 | Ceiling Painting/ PT Marking | 100 | 0 |  | 2026-03-27 |  | 2026-04-02 |  | Tower B | Super Structure |  | Finishes | Ceiling Painting/ PT Marking
45953 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-01-20 | 2026-02-12 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-03-27 |  | 2026-04-20 |  | Tower B | Super Structure |  | MEP | FPS 1st Fix - MEP & Finishes
45954 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-01-20 | 2026-02-12 | PHE 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-03-27 |  | 2026-04-20 |  | Tower B | Super Structure
45955 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-01-20 | 2026-02-06 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-03-27 |  | 2026-04-14 |  | Tower B | Super Structure |  | MEP | Electrical 1st Fixes
45984 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-01-20 | 2026-02-06 | HVAC Ducting/ Fan Installations | 100 | 0 |  | 2026-03-27 |  | 2026-04-14 |  | Tower B | Super Structure |  | MEP | HVAC Ducting
46010 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-01-20 | 2026-01-31 | FAPA Cabling | 100 | 0 |  | 2026-03-27 |  | 2026-04-08 |  | Tower B | Super Structure
8723 | T-14-7th Floor Common Area | Not Ready | Window-Open Area | 2026-02-20 | 2026-02-28 | Window-Open Area | 100 | 0 |  | 2026-03-28 |  | 2026-04-04
8748 | T-14-8th Floor Common Area | Not Ready | Door-Shaft | 2026-02-24 | 2026-03-09 | Door-Shaft | 100 | 0 |  | 2026-03-28 |  | 2026-04-10
10752 | T-20-4th Floor Common Area | Not Ready | 1st Coat Painting | 2026-04-21 | 2026-05-13 | 1st Coat Painting | 100 | 0 |  | 2026-03-28 |  | 2026-04-19
11895 | T-18-8th Floor Common Area | Not Ready | Window-Open Area | 2026-06-11 | 2026-06-18 | Window-Open Area | 100 | 0 |  | 2026-03-28 |  | 2026-04-03
11985 | T-18-Lift Lobby | Not Ready |  | 2026-06-14 | 2026-06-30 | 12F | 100 | 0 |  | 2026-03-28 |  | 2026-04-11
40115 | Tower A - Super Structure - Finishes & MEP - Sub Station | Not Ready | Sub Station - High Side Services | 2026-03-31 | 2026-04-28 | Cable Laying & Termination | 100 | 0 |  | 2026-03-28 |  | 2026-04-25 |  | Tower A | Super Structure
40123 | Tower A - Super Structure - Finishes & MEP - DG Sets | Not Ready |  | 2026-03-31 | 2026-06-10 | DG Sync Panel Installation | 100 | 0 |  | 2026-03-28 |  | 2026-06-08 |  | Tower A | Super Structure
40435 | Tower A - Super Structure - Finishes & MEP - L69 to L70 | Not Ready | Partition Wall-Blockwork | 2026-03-06 | 2026-03-13 | Partition Walls | 100 | 0 |  | 2026-03-28 |  | 2026-04-04 |  | Tower A | Super Structure | L69
41344 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-03-09 | 2026-03-11 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-03-28 |  | 2026-04-01 |  | Tower A | Super Structure | L24
43977 | Tower A - Super Structure - Finishes & MEP - L15 to L25 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-04-28 | 2026-06-03 | Staircase Window | 100 | 0 |  | 2026-03-28 |  | 2026-05-04 |  | Tower A | Super Structure | L15
9832 | T-16-9th Floor Flat Area | Not Ready | Door | 2026-05-05 | 2026-05-27 | Door | 100 | 0 |  | 2026-03-29 |  | 2026-04-19
9857 | T-16-10th Floor Flat Area | Not Ready | Window | 2026-05-05 | 2026-05-27 | Window | 100 | 0 |  | 2026-03-29 |  | 2026-04-19
10206 | T-21-3rd Floor Common Area | Not Ready | 1st Coat Painting | 2026-05-02 | 2026-05-23 | 1st Coat Painting | 100 | 0 |  | 2026-03-29 |  | 2026-04-20
10355 | T-21-9th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-05-07 | 2026-07-12 | 2nd Coat Painting | 100 | 0 |  | 2026-03-29 |  | 2026-06-04
10444 | T-21-Staircase 1 | Not Ready |  | 2026-04-27 | 2026-05-08 | 09F-08F | 100 | 0 |  | 2026-03-29 |  | 2026-04-08
10458 | T-21-Staircase 2 | Not Ready |  | 2026-04-27 | 2026-05-08 | 10F-09F | 100 | 0 |  | 2026-03-29 |  | 2026-04-08
11348 | T-19-7th Floor Common Area | Not Ready | Door-Shaft | 2026-04-15 | 2026-04-28 | Door-Shaft | 100 | 0 |  | 2026-03-29 |  | 2026-04-11
11464 |  | Not Ready |  | 2026-05-19 | 2027-01-06 | Lift lobby | 100 | 0 |  | 2026-03-29 |  | 2026-11-18
11494 |  | Not Ready |  | 2026-05-19 | 2026-10-20 | Staircase-2 | 100 | 0 |  | 2026-03-29 |  | 2026-08-31
11920 | T-18-9th Floor Common Area | Not Ready | Door-Shaft | 2026-06-14 | 2026-06-27 | Door-Shaft | 100 | 0 |  | 2026-03-29 |  | 2026-04-11
9217 | T-15-5th Floor Common Area | Not Ready | Window-Open Area | 2026-03-28 | 2026-04-05 | Window-Open Area | 100 | 0 |  | 2026-03-30 |  | 2026-04-07
9371 | T-15-11th Floor Common Area | Not Ready | Putty | 2026-04-06 | 2026-05-15 | Putty | 100 | 0 |  | 2026-03-30 |  | 2026-05-06
11323 | T-19-6th Floor Common Area | Not Ready | Window-Open Area | 2026-04-11 | 2026-04-19 | Window-Open Area | 100 | 0 |  | 2026-03-30 |  | 2026-04-06
11444 | T-19-11th Floor Flat Area | Not Ready | Door | 2026-05-05 | 2026-05-27 | Door | 100 | 0 |  | 2026-03-30 |  | 2026-04-23
11999 |  | Not Ready |  | 2026-06-03 | 2026-11-06 | Staircase-1 | 100 | 0 |  | 2026-03-30 |  | 2026-09-01
40042 |  | Not Ready |  | 2026-02-28 | 2026-07-03 | BMU Installation | 100 | 0 |  | 2026-03-30 |  | 2026-08-06
40042 |  | Not Ready |  | 2026-02-28 | 2026-07-03 | BMU Installation | 100 | 0 |  | 2026-03-30 |  | 2026-08-06
40043 | Tower A | Not Ready | BMU Installation | 2026-02-28 | 2026-04-04 | Pedestal & Support Structure | 100 | 0 |  | 2026-03-30 |  | 2026-05-05 |  | Tower A | --
40462 | Tower A - Super Structure - Finishes & MEP - Above Terrace | Not Ready | Partition Wall-Blockwork | 2026-02-28 | 2026-03-12 | MEP related works | 100 | 0 |  | 2026-03-30 |  | 2026-04-10 |  | Tower A | Super Structure
40463 | Tower A - Super Structure - Finishes & MEP - Above Terrace | Not Ready | Partition Wall-Blockwork | 2026-02-28 | 2026-03-12 | LMR Masonry | 100 | 0 |  | 2026-03-30 |  | 2026-04-10 |  | Tower A | Super Structure
40464 | Tower A - Super Structure - Finishes & MEP - Above Terrace | Not Ready | Partition Wall-Blockwork | 2026-02-28 | 2026-03-12 | Terrace Area works | 100 | 0 |  | 2026-03-30 |  | 2026-04-10 |  | Tower A | Super Structure
41402 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-03-09 | 2026-03-20 | Flooring & Dado | 100 | 0 |  | 2026-03-30 |  | 2026-04-09 |  | Tower A | Super Structure | L28 | Finishes | Flooring & Dado
41463 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-03-09 | 2026-03-17 | HVAC Ducting | 100 | 0 |  | 2026-03-30 |  | 2026-04-06 |  | Tower A | Super Structure | L32 | MEP | HVAC Ducting
47961 | Tower B | Not Committed | Award of Packages | 2026-01-19 | 2026-05-04 | BMU | 100 | 0 |  | 2026-03-30 |  | 2026-07-10 |  | Tower B | --
8851 | T-14-12th Floor Common Area | Not Ready | Putty | 2026-03-07 | 2026-04-15 | Putty | 100 | 0 |  | 2026-03-31 |  | 2026-05-08
9270 | T-15-7th Floor Common Area | Not Ready | 1st Coat Painting | 2026-03-31 | 2026-04-21 | 1st Coat Painting | 100 | 0 |  | 2026-03-31 |  | 2026-04-23
9385 | T-15-Lift Lobby | Not Ready |  | 2026-04-11 | 2026-04-28 | 12F | 100 | 0 |  | 2026-03-31 |  | 2026-04-16
9401 | T-15-Staircase 1 | Not Ready |  | 2026-04-11 | 2026-04-22 | 12F-11F | 100 | 0 |  | 2026-03-31 |  | 2026-04-10
9415 | T-15-Staircase 2 | Not Ready |  | 2026-04-11 | 2026-04-22 | TF-12F | 100 | 0 |  | 2026-03-31 |  | 2026-04-10
9864 | T-16-11th Floor Common Area | Not Ready | Flooring & skirting | 2026-04-25 | 2026-05-18 | Flooring & skirting | 100 | 0 |  | 2026-03-31 |  | 2026-04-22
9919 |  | Not Ready |  | 2026-05-29 | 2026-10-30 | Staircase-1 | 100 | 0 |  | 2026-03-31 |  | 2026-09-02
10178 | T-21-2nd Floor Common Area | Not Ready | Door-Shaft | 2026-05-03 | 2026-05-16 | Door-Shaft | 100 | 0 |  | 2026-03-31 |  | 2026-04-11
11733 | T-18-2nd Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-06-27 | 2026-09-18 | 2nd Coat Painting | 100 | 0 |  | 2026-03-31 |  | 2026-06-22
40439 | Tower A - Super Structure - Finishes & MEP - L70 to L71 | Not Ready | Partition Wall-Blockwork | 2026-03-09 | 2026-03-16 | Partition Walls | 100 | 0 |  | 2026-03-31 |  | 2026-04-07 |  | Tower A | Super Structure | L70
41330 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-03-11 | 2026-03-16 | Final Painting | 100 | 0 |  | 2026-03-31 |  | 2026-04-06 |  | Tower A | Super Structure | L23 | Finishes | Final Painting
41330 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-03-11 | 2026-03-16 | Final Painting | 100 | 0 |  | 2026-03-31 |  | 2026-04-06 |  | Tower A | Super Structure | L23 | Finishes | Final Painting
41330 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-03-11 | 2026-03-16 | Final Painting | 100 | 0 |  | 2026-03-31 |  | 2026-04-06 |  | Tower A | Super Structure | L23 | Finishes | Final Painting
41371 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-03-11 | 2026-03-18 | False Ceiling | 100 | 0 |  | 2026-03-31 |  | 2026-04-08 |  | Tower A | Super Structure | L26 | Finishes | False Ceiling
41418 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-03-11 | 2026-03-23 | Flooring & Dado | 100 | 0 |  | 2026-03-31 |  | 2026-04-11 |  | Tower A | Super Structure | L29 | Finishes | Flooring & Dado
41479 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-03-11 | 2026-03-19 | HVAC Ducting | 100 | 0 |  | 2026-03-31 |  | 2026-04-08 |  | Tower A | Super Structure | L33 | MEP | HVAC Ducting
42009 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2026-02-28 | 2026-03-06 | Lobby Plastering | 100 | 0 |  | 2026-03-31 |  | 2026-04-06 |  | Tower A | Super Structure | L66 | Finishes | Lobby Plastering
42019 |  | Not Committed |  | 2026-02-28 | 2026-11-05 | L67-68 | 100 | 0 |  | 2026-03-31 |  | 2026-11-12
42019 |  | Not Committed |  | 2026-02-28 | 2026-11-05 | L67-68 | 100 | 0 |  | 2026-03-31 |  | 2026-11-12 |  |  |  |  | Finishes | Gypsum Plastering Works
42024 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2026-02-28 | 2026-03-04 | Lobby Blockwork | 100 | 0 |  | 2026-03-31 |  | 2026-04-03 |  | Tower A | Super Structure | L67 | Finishes | Blockwork
43128 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-04-30 | 2026-05-18 | Flooring & Dado works | 100 | 0 |  | 2026-03-31 |  | 2026-04-17 |  | Tower A | Super Structure | L58 | Finishes | Flooring & Dado
44120 | Tower A - Super Structure - Finishes & MEP - L63 to L68 | Not Ready | Façade Works - MEP & Finishes | 2026-04-30 | 2026-05-12 | DGU Assembly Installation | 100 | 0 |  | 2026-03-31 |  | 2026-04-11 |  | Tower A | Super Structure | L63 | Façade | Façade Works
44121 | Tower A - Super Structure - Finishes & MEP - L63 to L68 | Not Ready | Façade Works - MEP & Finishes | 2026-04-30 | 2026-05-23 | Installation of highly reflective metal sheet | 100 | 0 |  | 2026-03-31 |  | 2026-04-23 |  | Tower A | Super Structure | L63 | Façade | Façade Works
44122 | Tower A - Super Structure - Finishes & MEP - L63 to L68 | Not Ready | Façade Works - MEP & Finishes | 2026-04-30 | 2026-05-12 | Fixing of Backlit Laminated Glass assembly & ACP Panels | 100 | 0 |  | 2026-03-31 |  | 2026-04-11 |  | Tower A | Super Structure | L63 | Façade | Façade Works
44123 | Tower A - Super Structure - Finishes & MEP - L63 to L68 | Not Ready | Façade Works - MEP & Finishes | 2026-04-30 | 2026-05-12 | Fixing of Louvers | 100 | 0 |  | 2026-03-31 |  | 2026-04-11 |  | Tower A | Super Structure | L63 | Façade | Façade Works
44123 | Tower A - Super Structure - Finishes & MEP - L63 to L68 | Not Ready | Façade Works - MEP & Finishes | 2026-04-30 | 2026-05-12 | Fixing of Louvers | 100 | 0 |  | 2026-03-31 |  | 2026-04-11 |  | Tower A | Super Structure | L63
8838 | T-14-12th Floor Flat Area | Not Ready | Dado | 2026-03-02 | 2026-03-30 | Dado | 100 | 0 |  | 2026-04-01 |  | 2026-04-29
8842 | T-14-12th Floor Flat Area | Not Ready | Putty | 2026-03-02 | 2026-05-24 | Putty | 100 | 0 |  | 2026-04-01 |  | 2026-06-24
10129 | T-21-GF Common Area | Not Ready | 2nd Coat Painting | 2026-05-29 | 2026-08-13 | 2nd Coat Painting | 100 | 0 |  | 2026-04-01 |  | 2026-06-17
10413 | T-21-11th Floor Common Area | Not Ready | Window-Open Area | 2026-05-11 | 2026-05-18 | Window-Open Area | 100 | 0 |  | 2026-04-01 |  | 2026-04-08
10671 | T-20-1st Floor Common Area | Not Ready | Putty | 2026-04-27 | 2026-06-05 | Putty | 100 | 0 |  | 2026-04-01 |  | 2026-05-09
10963 | T-20-Staircase 1 | Not Ready |  | 2026-04-27 | 2026-05-09 | 10F-09F | 100 | 0 |  | 2026-04-01 |  | 2026-04-14
10977 | T-20-Staircase 2 | Not Ready |  | 2026-04-27 | 2026-05-09 | 11F-10F | 100 | 0 |  | 2026-04-01 |  | 2026-04-14
11265 | T-19-4th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-05-02 | 2026-07-07 | 2nd Coat Painting | 100 | 0 |  | 2026-04-01 |  | 2026-06-06
11369 | T-19-8th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-05-02 | 2026-07-07 | 2nd Coat Painting | 100 | 0 |  | 2026-04-01 |  | 2026-06-06
12001 | T-18-Staircase 1 | Not Ready |  | 2026-06-14 | 2026-06-25 | 12F-11F | 100 | 0 |  | 2026-04-01 |  | 2026-04-12
12015 | T-18-Staircase 2 | Not Ready |  | 2026-06-14 | 2026-06-25 | TF-12F | 100 | 0 |  | 2026-04-01 |  | 2026-04-12
41345 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-03-12 | 2026-03-17 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-04-01 |  | 2026-04-07 |  | Tower A | Super Structure | L24 | MEP | Electrical
41356 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-03-12 | 2026-03-14 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-04-01 |  | 2026-04-04 |  | Tower A | Super Structure | L25 | MEP | FPS 2nd Fix - MEP & Finishes
41357 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-03-12 | 2026-03-17 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-04-01 |  | 2026-04-07 |  | Tower A | Super Structure | L25 | MEP | Electrical 2nd Fix - MEP & Finishes
41358 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-12 | 2026-03-19 | FAPA Device Fixing | 100 | 0 |  | 2026-04-01 |  | 2026-04-09 |  | Tower A | Super Structure | L25
41358 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-12 | 2026-03-19 | FAPA Device Fixing | 100 | 0 |  | 2026-04-01 |  | 2026-04-09 |  | Tower A | Super Structure | L25
41358 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-12 | 2026-03-19 | FAPA Device Fixing | 100 | 0 |  | 2026-04-01 |  | 2026-04-09 |  | Tower A | Super Structure | L25
41358 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-12 | 2026-03-19 | FAPA Device Fixing | 100 | 0 |  | 2026-04-01 |  | 2026-04-09 |  | Tower A | Super Structure | L25
41359 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-03-12 | 2026-03-14 | HVAC Grill Fixing | 100 | 0 |  | 2026-04-01 |  | 2026-04-04 |  | Tower A | Super Structure | L25 | MEP | HVAC Grill Fixing
43280 |  | Not Committed |  | 2026-03-10 | 2026-10-17 | L67-68 | 100 | 0 |  | 2026-04-01 |  | 2026-09-30
43280 |  | Not Committed |  | 2026-03-10 | 2026-10-17 | L67-68 | 100 | 0 |  | 2026-04-01 |  | 2026-09-30 |  |  |  |  | Finishes | Gypsum Plastering Works
43281 |  | Not Committed |  | 2026-03-10 | 2026-04-07 | MEP 1st Fixes | 100 | 0 |  | 2026-04-01 |  | 2026-04-29
43282 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-03-10 | 2026-03-17 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-04-01 |  | 2026-04-08 |  | Tower A | Super Structure | L67 | MEP | FPS 1st Fix - MEP & Finishes
43283 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-03-10 | 2026-03-14 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-04-01 |  | 2026-04-06 |  | Tower A | Super Structure | L67 | MEP | Electrical 1st Fixes
43284 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-03-10 | 2026-03-17 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-04-01 |  | 2026-04-08 |  | Tower A | Super Structure | L67
43285 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-03-10 | 2026-03-26 | Wet Area Waterproofing | 100 | 0 |  | 2026-04-01 |  | 2026-04-17 |  | Tower A | Super Structure | L67
45294 | Tower B - Super Structure - Core & Outer Slab L14-15 | Not Ready | RCC Works - Slab | 2026-01-24 | 2026-02-02 | Outer Slab_TA | 100 | 0 |  | 2026-04-01 |  | 2026-04-09 |  | Tower B | Super Structure | L14 | RCC Sub Structure | RCC Works - Slab
11790 | T-18-4th Floor Common Area | Not Ready | Door-Shaft | 2026-06-09 | 2026-06-22 | Door-Shaft | 100 | 0 |  | 2026-04-02 |  | 2026-04-15
12031 | T-18- Elevation A | Not Ready |  | 2026-06-19 | 2026-09-10 | Elevation-A | 100 | 0 |  | 2026-04-02 |  | 2026-06-24
40443 | Tower A - Super Structure - Finishes & MEP - L71 to L72 | Not Ready | Partition Wall-Blockwork | 2026-03-11 | 2026-03-18 | Partition Walls | 100 | 0 |  | 2026-04-02 |  | 2026-04-09 |  | Tower A | Super Structure | L71
41387 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-03-12 | 2026-03-20 | False Ceiling | 100 | 0 |  | 2026-04-02 |  | 2026-04-10 |  | Tower A | Super Structure | L27 | Finishes | False Ceiling
41434 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-03-13 | 2026-03-24 | Flooring & Dado | 100 | 0 |  | 2026-04-02 |  | 2026-04-14 |  | Tower A | Super Structure | L30 | Finishes | Flooring & Dado
41495 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-03-13 | 2026-03-20 | HVAC Ducting | 100 | 0 |  | 2026-04-02 |  | 2026-04-10 |  | Tower A | Super Structure | L34 | MEP | HVAC Ducting
45882 |  | Not Committed |  | 2026-01-27 | 2027-01-18 | P1-2 Level | 100 | 0 |  | 2026-04-02 |  | 2027-03-30
45897 |  | Not Committed |  | 2026-01-27 | 2026-04-07 | Floor Area | 100 | 0 |  | 2026-04-02 |  | 2026-06-13
45898 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | Ceiling Painting/ PT Marking - MEP & Finishes | 2026-01-27 | 2026-01-31 | Ceiling Painting/ PT Marking | 100 | 0 |  | 2026-04-02 |  | 2026-04-08 |  | Tower B | Super Structure |  | Finishes | Ceiling Painting/ PT Marking
45926 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-01-27 | 2026-02-18 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-04-02 |  | 2026-04-25 |  | Tower B | Super Structure |  | MEP | FPS 1st Fix - MEP & Finishes
45927 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-01-27 | 2026-02-18 | PHE 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-04-02 |  | 2026-04-25 |  | Tower B | Super Structure
45928 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-01-27 | 2026-02-12 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-04-02 |  | 2026-04-20 |  | Tower B | Super Structure |  | MEP | Electrical 1st Fixes
45957 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-01-27 | 2026-02-12 | HVAC Ducting/ Fan Installations | 100 | 0 |  | 2026-04-02 |  | 2026-04-20 |  | Tower B | Super Structure |  | MEP | HVAC Ducting
45983 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-01-27 | 2026-02-06 | FAPA Cabling | 100 | 0 |  | 2026-04-02 |  | 2026-04-14 |  | Tower B | Super Structure
46039 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | VDF/ Grade Slab - MEP & Finishes | 2026-01-27 | 2026-01-31 | VDF/ Grade Slab | 100 | 0 |  | 2026-04-02 |  | 2026-04-08 |  | Tower B | Super Structure
8671 | T-14-5th Floor Common Area | Not Ready | Window-Open Area | 2026-02-26 | 2026-03-05 | Window-Open Area | 100 | 0 |  | 2026-04-03 |  | 2026-04-10
9762 | T-16-6th Floor Common Area | Not Ready | Door-Shaft | 2026-04-20 | 2026-05-04 | Door-Shaft | 100 | 0 |  | 2026-04-03 |  | 2026-04-17
9879 | T-16-11th Floor Flat Area | Not Ready | Toilet flooring | 2026-04-22 | 2026-05-26 | Toilet flooring | 100 | 0 |  | 2026-04-03 |  | 2026-05-07
11239 | T-19-3rd Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-05-04 | 2026-07-09 | 2nd Coat Painting | 100 | 0 |  | 2026-04-03 |  | 2026-06-10
11509 |  | Not Ready |  | 2026-05-24 | 2026-11-18 | External Finishes | 100 | 0 |  | 2026-04-03 |  | 2026-09-27
11510 |  | Not Ready |  | 2026-05-24 | 2026-11-18 | External Painting | 100 | 0 |  | 2026-04-03 |  | 2026-09-27
11818 | T-18-5th Floor Common Area | Not Ready | 1st Coat Painting | 2026-06-08 | 2026-06-29 | 1st Coat Painting | 100 | 0 |  | 2026-04-03 |  | 2026-04-24
40432 | Tower A - Super Structure - Finishes & MEP - L68 to L69 | Not Ready | Partition Wall-Blockwork | 2026-03-12 | 2026-03-17 | Staircase Area | 100 | 0 |  | 2026-04-03 |  | 2026-04-08 |  | Tower A | Super Structure | L68
42025 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2026-03-05 | 2026-03-10 | Lobby Plastering | 100 | 0 |  | 2026-04-03 |  | 2026-04-09 |  | Tower A | Super Structure | L67 | Finishes | Lobby Plastering
42035 |  | Not Committed |  | 2026-03-05 | 2026-11-11 | L68-69 | 100 | 0 |  | 2026-04-03 |  | 2026-11-18
42035 |  | Not Committed |  | 2026-03-05 | 2026-11-11 | L68-69 | 100 | 0 |  | 2026-04-03 |  | 2026-11-18 |  |  |  |  | Finishes | Gypsum Plastering Works
42040 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2026-03-05 | 2026-03-07 | Lobby Blockwork | 100 | 0 |  | 2026-04-03 |  | 2026-04-07 |  | Tower A | Super Structure | L68 | Finishes | Blockwork
43964 | Tower A - Super Structure - Finishes & MEP - GF to L7 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-05-05 | 2026-05-28 | Staircase Railing | 100 | 0 |  | 2026-04-03 |  | 2026-04-27 |  | Tower A | Super Structure | GF
43971 | Tower A - Super Structure - Finishes & MEP - L7 to L15 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-05-05 | 2026-05-28 | Staircase Railing | 100 | 0 |  | 2026-04-03 |  | 2026-04-27 |  | Tower A | Super Structure | L7
43981 |  | Not Committed |  | 2026-05-05 | 2026-07-15 | L25-35 | 100 | 0 |  | 2026-04-03 |  | 2026-06-15
43981 |  | Not Committed |  | 2026-05-05 | 2026-07-15 | L25-35 | 100 | 0 |  | 2026-04-03 |  | 2026-06-15
43982 | Tower A - Super Structure - Finishes & MEP - L25 to L35 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-05-05 | 2026-06-09 | Staircase Wall & Ceiling finishes | 100 | 0 |  | 2026-04-03 |  | 2026-05-09 |  | Tower A | Super Structure | L25
43983 | Tower A - Super Structure - Finishes & MEP - L25 to L35 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-05-05 | 2026-06-26 | Staircase Flooring | 100 | 0 |  | 2026-04-03 |  | 2026-05-28 |  | Tower A | Super Structure | L25 | Finishes | Staircase Flooring
44585 |  | Not Ready | MEP fix & Finishes | 2026-04-06 | 2026-04-13 | HVAC Fans fixing | 100 | 0 |  | 2026-04-03 |  | 2026-04-10 |  |  |  |  | MEP | HVAC Grill Fixing
44585 |  | Not Ready | MEP fix & Finishes | 2026-04-06 | 2026-04-13 | HVAC Fans fixing | 100 | 0 |  | 2026-04-03 |  | 2026-04-10 |  |  |  |  | MEP | HVAC Grill Fixing
44590 |  | Not Ready | MEP fix & Finishes | 2026-04-06 | 2026-04-13 | FAPA Device Fixing | 100 | 0 |  | 2026-04-03 |  | 2026-04-10
44590 |  | Not Ready | MEP fix & Finishes | 2026-04-06 | 2026-04-13 | FAPA Device Fixing | 100 | 0 |  | 2026-04-03 |  | 2026-04-10
44590 |  | Not Ready | MEP fix & Finishes | 2026-04-06 | 2026-04-13 | FAPA Device Fixing | 100 | 0 |  | 2026-04-03 |  | 2026-04-10
44590 |  | Not Ready | MEP fix & Finishes | 2026-04-06 | 2026-04-13 | FAPA Device Fixing | 100 | 0 |  | 2026-04-03 |  | 2026-04-10
44594 |  | Not Committed |  | 2026-04-06 | 2026-05-18 | B1 to GF | 100 | 0 |  | 2026-04-03 |  | 2026-05-15
44594 |  | Not Committed |  | 2026-04-06 | 2026-05-18 | B1 to GF | 100 | 0 |  | 2026-04-03 |  | 2026-05-15
44594 |  | Not Committed |  | 2026-04-06 | 2026-05-18 | B1 to GF | 100 | 0 |  | 2026-04-03 |  | 2026-05-15
44595 |  | Not Ready | MEP fix & Finishes | 2026-04-06 | 2026-04-13 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2026-04-03 |  | 2026-04-10 |  |  |  |  | MEP | FPS final fixes
44595 |  | Not Ready | MEP fix & Finishes | 2026-04-06 | 2026-04-13 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2026-04-03 |  | 2026-04-10 |  |  |  |  | MEP | FPS final fixes
46696 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-01-28 | 2026-02-13 | Wet Area Waterproofing | 100 | 0 |  | 2026-04-03 |  | 2026-04-21 |  | Tower B | Super Structure | L9
10907 | T-20-11th Floor Common Area | Not Ready | Window-Open Area | 2026-05-06 | 2026-05-13 | Window-Open Area | 100 | 0 |  | 2026-04-04 |  | 2026-04-11
10932 | T-20-11th Floor Common Area | Not Ready | Door-Shaft | 2026-05-09 | 2026-05-22 | Door-Shaft | 100 | 0 |  | 2026-04-04 |  | 2026-04-17
11296 | T-19-5th Floor Common Area | Not Ready | Door-Shaft | 2026-04-20 | 2026-05-04 | Door-Shaft | 100 | 0 |  | 2026-04-04 |  | 2026-04-17
11425 | T-19-11th Floor Common Area | Not Ready | Putty | 2026-04-25 | 2026-06-04 | Putty | 100 | 0 |  | 2026-04-04 |  | 2026-05-11
11896 | T-18-8th Floor Common Area | Not Ready | 1st Coat Painting | 2026-06-18 | 2026-07-10 | 1st Coat Painting | 100 | 0 |  | 2026-04-04 |  | 2026-04-26
40321 |  | Not Committed |  | 2026-02-28 | 2026-04-07 | L77-78 | 100 | 0 |  | 2026-04-04 |  | 2026-05-07
40321 |  | Not Committed |  | 2026-02-28 | 2026-04-07 | L77-78 | 100 | 0 |  | 2026-04-04 |  | 2026-05-07 |  |  |  |  | Finishes | Gypsum Plastering Works
40322 | Tower A - Super Structure - Finishes & MEP - L77 to L78 | Not Ready | Partition Wall-Blockwork | 2026-02-28 | 2026-03-18 | De-shuttering & Area clearance | 100 | 0 |  | 2026-04-04 |  | 2026-04-22 |  | Tower A | Super Structure | L77
40447 | Tower A - Super Structure - Finishes & MEP - L72 to L73 | Not Ready | Partition Wall-Blockwork | 2026-03-13 | 2026-03-20 | Partition Walls | 100 | 0 |  | 2026-04-04 |  | 2026-04-11 |  | Tower A | Super Structure | L72
40540 | Tower A - Super Structure - Finishes & MEP - L66 to L67 | Not Ready | Gypsum Plastering Works | 2026-03-13 | 2026-03-30 | L66-67 | 100 | 0 |  | 2026-04-04 |  | 2026-04-21 |  | Tower A | Super Structure | L66 | Finishes | Gypsum Plastering Works
40540 | Tower A - Super Structure - Finishes & MEP - L66 to L67 | Not Ready | Gypsum Plastering Works | 2026-03-13 | 2026-03-30 | L66-67 | 100 | 0 |  | 2026-04-04 |  | 2026-04-21 |  | Tower A | Super Structure | L66
40936 | Tower A - Super Structure - Finishes & MEP - L65 to Terrace | Not Ready |  | 2026-02-28 | 2026-04-04 | Shaft Cabling in Electrical & ELV Shaft | 100 | 0 |  | 2026-04-04 |  | 2026-05-11 |  | Tower A | Super Structure | L65
41360 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-03-16 | 2026-03-18 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-04-04 |  | 2026-04-08 |  | Tower A | Super Structure | L25
41403 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-03-14 | 2026-03-23 | False Ceiling | 100 | 0 |  | 2026-04-04 |  | 2026-04-11 |  | Tower A | Super Structure | L28 | Finishes | False Ceiling
41450 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-03-14 | 2026-03-26 | Flooring & Dado | 100 | 0 |  | 2026-04-04 |  | 2026-04-16 |  | Tower A | Super Structure | L31 | Finishes | Flooring & Dado
41511 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-03-14 | 2026-03-23 | HVAC Ducting | 100 | 0 |  | 2026-04-04 |  | 2026-04-13 |  | Tower A | Super Structure | L35 | MEP | HVAC Ducting
43164 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-04-30 | 2026-05-18 | Flooring & Dado works | 100 | 0 |  | 2026-04-04 |  | 2026-04-21 |  | Tower A | Super Structure | L60 | Finishes | Flooring & Dado
43181 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-03-13 | 2026-03-20 | Door & Window Frame work | 100 | 0 |  | 2026-04-04 |  | 2026-04-11 |  | Tower A | Super Structure | L61 | Finishes | Door & Window Frame work
45448 | Tower B - Super Structure - Finishes & MEP - L10 to L11 | Not Ready | Partition Wall-Blockwork | 2026-01-29 | 2026-02-03 | Staircase Area | 100 | 0 |  | 2026-04-04 |  | 2026-04-10 |  | Tower B | Super Structure | L10
48238 | Retail & Clubhouse - Sub structure - B2 to B1 | Not Ready |  | 2025-10-11 | 2025-10-29 | MEP Rooms - Plaster & IPS | 100 | 0 |  | 2026-04-04 |  | 2026-04-21 |  | Club House | Sub Structure | B2
48238 | Retail & Clubhouse - Sub structure - B2 to B1 | Not Ready |  | 2025-10-11 | 2025-10-29 | MEP Rooms - Plaster & IPS | 100 | 0 |  | 2026-04-04 |  | 2026-04-21 |  | Club House | Sub Structure | B2
48239 | Retail & Clubhouse - Sub structure - B2 to B1 | Not Ready |  | 2025-10-11 | 2025-11-04 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2026-04-04 |  | 2026-04-27 |  | Club House | Sub Structure | B2
48239 | Retail & Clubhouse - Sub structure - B2 to B1 | Not Ready |  | 2025-10-11 | 2025-11-04 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2026-04-04 |  | 2026-04-27 |  | Club House | Sub Structure | B2
48243 | Retail & Clubhouse - Sub structure - B1 to GF | Not Ready |  | 2025-12-12 | 2025-12-30 | MEP Rooms - Plaster & IPS | 100 | 0 |  | 2026-04-04 |  | 2026-04-21 |  | Club House | Sub Structure | B1
48243 | Retail & Clubhouse - Sub structure - B1 to GF | Not Ready |  | 2025-12-12 | 2025-12-30 | MEP Rooms - Plaster & IPS | 100 | 0 |  | 2026-04-04 |  | 2026-04-21 |  | Club House | Sub Structure | B1
48244 | Retail & Clubhouse - Sub structure - B1 to GF | Not Ready |  | 2025-12-12 | 2026-01-05 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2026-04-04 |  | 2026-04-27 |  | Club House | Sub Structure | B1
48244 | Retail & Clubhouse - Sub structure - B1 to GF | Not Ready |  | 2025-12-12 | 2026-01-05 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2026-04-04 |  | 2026-04-27 |  | Club House | Sub Structure | B1
8724 | T-14-7th Floor Common Area | Not Ready | 1st Coat Painting | 2026-02-28 | 2026-03-22 | 1st Coat Painting | 100 | 0 |  | 2026-04-05 |  | 2026-04-26
9133 | T-15-2nd Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-04-24 | 2026-07-16 | 2nd Coat Painting | 100 | 0 |  | 2026-04-05 |  | 2026-06-27
9245 | T-15-6th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-04-05 | 2026-05-08 | 2nd Coat Painting | 100 | 0 |  | 2026-04-05 |  | 2026-05-09
9431 | T-15- Elevation A | Not Ready |  | 2026-04-17 | 2026-07-09 | Elevation-A | 100 | 0 |  | 2026-04-05 |  | 2026-06-27
8879 |  | Not Ready |  | 2026-04-04 | 2026-09-06 | Staircase-1 | 100 | 0 |  | 2026-04-06 |  | 2026-09-07
9860 | T-16-10th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-04-28 | 2026-07-20 | 1st Coat Painting | 100 | 0 |  | 2026-04-06 |  | 2026-06-28
9882 | T-16-11th Floor Flat Area | Not Ready | Putty | 2026-04-25 | 2026-07-17 | Putty | 100 | 0 |  | 2026-04-06 |  | 2026-06-29
40436 | Tower A - Super Structure - Finishes & MEP - L69 to L70 | Not Ready | Partition Wall-Blockwork | 2026-03-14 | 2026-03-19 | Staircase Area | 100 | 0 |  | 2026-04-06 |  | 2026-04-10 |  | Tower A | Super Structure | L69
41419 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-03-17 | 2026-03-25 | False Ceiling | 100 | 0 |  | 2026-04-06 |  | 2026-04-14 |  | Tower A | Super Structure | L29 | Finishes | False Ceiling
43217 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-03-14 | 2026-03-21 | Door & Window Frame work | 100 | 0 |  | 2026-04-06 |  | 2026-04-13 |  | Tower A | Super Structure | L63 | Finishes | Door & Window Frame work
44125 |  | Not Ready |  | 2026-05-07 | 2026-06-11 | L68-73 | 100 | 0 |  | 2026-04-06 |  | 2026-05-12
44126 | Tower A - Super Structure - Finishes & MEP - L68 to L73 | Not Ready | Façade Works - MEP & Finishes | 2026-05-07 | 2026-05-18 | Al. Frame section (Mullion & Transom) Installation | 100 | 0 |  | 2026-04-06 |  | 2026-04-17 |  | Tower A | Super Structure | L68 | Façade | Façade Works
46679 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-01-30 | 2026-02-10 | Cement Plastering in wet areas | 100 | 0 |  | 2026-04-06 |  | 2026-04-17 |  | Tower B | Super Structure | L8
9384 |  | Not Ready |  | 2026-04-11 | 2026-12-01 | Lift lobby | 100 | 0 |  | 2026-04-07 |  | 2026-11-26
9414 |  | Not Ready |  | 2026-04-11 | 2026-09-14 | Staircase-2 | 100 | 0 |  | 2026-04-07 |  | 2026-09-08
11324 | T-19-6th Floor Common Area | Not Ready | 1st Coat Painting | 2026-04-19 | 2026-05-12 | 1st Coat Painting | 100 | 0 |  | 2026-04-07 |  | 2026-04-28
11710 | T-18-1st Floor Common Area | Not Ready | Flooring & skirting | 2026-06-14 | 2026-07-06 | Flooring & skirting | 100 | 0 |  | 2026-04-07 |  | 2026-04-30
11737 | T-18-2nd Floor Common Area | Not Ready | Putty | 2026-06-14 | 2026-07-22 | Putty | 100 | 0 |  | 2026-04-07 |  | 2026-05-15
40079 | Tower A - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2026-03-16 | 2026-03-26 | Plumb check & door centre line by Lift agency for lobby blockwork | 100 | 0 |  | 2026-04-07 |  | 2026-04-18 |  | Tower A | Super Structure
40079 | Tower A - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2026-03-16 | 2026-03-26 | Plumb check & door centre line by Lift agency for lobby blockwork | 100 | 0 |  | 2026-04-07 |  | 2026-04-18 |  | Tower A | Super Structure
40079 | Tower A - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2026-03-16 | 2026-03-26 | Plumb check & door centre line by Lift agency for lobby blockwork | 100 | 0 |  | 2026-04-07 |  | 2026-04-18 |  | Tower A | Super Structure
40080 | Tower A - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2026-03-16 | 2026-03-26 | Shaft clearance & White Wash up to LMR | 100 | 0 |  | 2026-04-07 |  | 2026-04-18 |  | Tower A | Super Structure
40080 | Tower A - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2026-03-16 | 2026-03-26 | Shaft clearance & White Wash up to LMR | 100 | 0 |  | 2026-04-07 |  | 2026-04-18 |  | Tower A | Super Structure
40085 | Tower A - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2026-03-16 | 2026-05-25 | LMR Works | 100 | 0 |  | 2026-04-07 |  | 2026-06-18 |  | Tower A | Super Structure
40085 | Tower A - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2026-03-16 | 2026-05-25 | LMR Works | 100 | 0 |  | 2026-04-07 |  | 2026-06-18 |  | Tower A | Super Structure
40451 | Tower A - Super Structure - Finishes & MEP - L73 to L74 | Not Ready | Partition Wall-Blockwork | 2026-03-16 | 2026-03-23 | Partition Walls | 100 | 0 |  | 2026-04-07 |  | 2026-04-14 |  | Tower A | Super Structure | L73
41346 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-03-18 | 2026-03-23 | Final Painting | 100 | 0 |  | 2026-04-07 |  | 2026-04-13 |  | Tower A | Super Structure | L24 | Finishes | Final Painting
41346 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-03-18 | 2026-03-23 | Final Painting | 100 | 0 |  | 2026-04-07 |  | 2026-04-13 |  | Tower A | Super Structure | L24 | Finishes | Final Painting
41346 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-03-18 | 2026-03-23 | Final Painting | 100 | 0 |  | 2026-04-07 |  | 2026-04-13 |  | Tower A | Super Structure | L24 | Finishes | Final Painting
41466 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-03-17 | 2026-03-28 | Flooring & Dado | 100 | 0 |  | 2026-04-07 |  | 2026-04-17 |  | Tower A | Super Structure | L32 | Finishes | Flooring & Dado
42041 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2026-03-09 | 2026-03-13 | Lobby Plastering | 100 | 0 |  | 2026-04-07 |  | 2026-04-13 |  | Tower A | Super Structure | L68 | Finishes | Lobby Plastering
42051 |  | Not Committed |  | 2026-03-09 | 2026-11-17 | L69-70 | 100 | 0 |  | 2026-04-07 |  | 2026-11-24
42051 |  | Not Committed |  | 2026-03-09 | 2026-11-17 | L69-70 | 100 | 0 |  | 2026-04-07 |  | 2026-11-24 |  |  |  |  | Finishes | Gypsum Plastering Works
42056 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2026-03-09 | 2026-03-11 | Lobby Blockwork | 100 | 0 |  | 2026-04-07 |  | 2026-04-10 |  | Tower A | Super Structure | L69 | Finishes | Blockwork
45612 | Tower B - Super Structure - Finishes & MEP - L9 to L10 | Not Ready | Gypsum Plastering Works | 2026-01-31 | 2026-03-19 | L9-10 | 100 | 0 |  | 2026-04-07 |  | 2026-05-25 |  | Tower B | Super Structure | L9 | Finishes | Gypsum Plastering Works
45612 | Tower B - Super Structure - Finishes & MEP - L9 to L10 | Not Ready | Gypsum Plastering Works | 2026-01-31 | 2026-03-19 | L9-10 | 100 | 0 |  | 2026-04-07 |  | 2026-05-25 |  | Tower B | Super Structure | L9
8587 | T-14-2nd Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-03-26 | 2026-06-17 | 2nd Coat Painting | 100 | 0 |  | 2026-04-08 |  | 2026-06-30
8699 | T-14-6th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-03-06 | 2026-04-08 | 2nd Coat Painting | 100 | 0 |  | 2026-04-08 |  | 2026-05-11
8839 | T-14-12th Floor Flat Area | Not Ready | Toilet flooring | 2026-03-09 | 2026-04-11 | Toilet flooring | 100 | 0 |  | 2026-04-08 |  | 2026-05-12
9218 | T-15-5th Floor Common Area | Not Ready | 1st Coat Painting | 2026-04-05 | 2026-04-27 | 1st Coat Painting | 100 | 0 |  | 2026-04-08 |  | 2026-04-30
9320 | T-15-9th Floor Common Area | Not Ready | Door-Shaft | 2026-04-11 | 2026-04-24 | Door-Shaft | 100 | 0 |  | 2026-04-08 |  | 2026-04-21
9682 | T-16-3rd Floor Common Area | Not Ready | Flooring & skirting | 2026-04-25 | 2026-05-18 | Flooring & skirting | 100 | 0 |  | 2026-04-08 |  | 2026-04-30
9709 | T-16-4th Floor Common Area | Not Ready | Putty | 2026-04-25 | 2026-06-03 | Putty | 100 | 0 |  | 2026-04-08 |  | 2026-05-15
9839 | T-16-9th Floor Common Area | Not Ready | Putty | 2026-04-30 | 2026-06-09 | Putty | 100 | 0 |  | 2026-04-08 |  | 2026-05-18
9858 | T-16-10th Floor Flat Area | Not Ready | Door | 2026-05-16 | 2026-06-06 | Door | 100 | 0 |  | 2026-04-08 |  | 2026-04-30
9883 | T-16-11th Floor Flat Area | Not Ready | Window | 2026-05-16 | 2026-06-06 | Window | 100 | 0 |  | 2026-04-08 |  | 2026-04-30
40061 | Tower A - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2026-03-17 | 2026-04-01 | Guide Rail installation for CWT (up to LMR) | 100 | 0 |  | 2026-04-08 |  | 2026-04-24 |  | Tower A | Super Structure
40061 | Tower A - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2026-03-17 | 2026-04-01 | Guide Rail installation for CWT (up to LMR) | 100 | 0 |  | 2026-04-08 |  | 2026-04-24 |  | Tower A | Super Structure
40440 | Tower A - Super Structure - Finishes & MEP - L70 to L71 | Not Ready | Partition Wall-Blockwork | 2026-03-17 | 2026-03-21 | Staircase Area | 100 | 0 |  | 2026-04-08 |  | 2026-04-13 |  | Tower A | Super Structure | L70
41361 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-03-19 | 2026-03-24 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-04-08 |  | 2026-04-14 |  | Tower A | Super Structure | L25 | MEP | Electrical
41372 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-03-19 | 2026-03-21 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-04-08 |  | 2026-04-11 |  | Tower A | Super Structure | L26 | MEP | FPS 2nd Fix - MEP & Finishes
41373 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-03-19 | 2026-03-24 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-04-08 |  | 2026-04-14 |  | Tower A | Super Structure | L26 | MEP | Electrical 2nd Fix - MEP & Finishes
41374 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-19 | 2026-03-26 | FAPA Device Fixing | 100 | 0 |  | 2026-04-08 |  | 2026-04-16 |  | Tower A | Super Structure | L26
41374 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-19 | 2026-03-26 | FAPA Device Fixing | 100 | 0 |  | 2026-04-08 |  | 2026-04-16 |  | Tower A | Super Structure | L26
41374 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-19 | 2026-03-26 | FAPA Device Fixing | 100 | 0 |  | 2026-04-08 |  | 2026-04-16 |  | Tower A | Super Structure | L26
41374 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-19 | 2026-03-26 | FAPA Device Fixing | 100 | 0 |  | 2026-04-08 |  | 2026-04-16 |  | Tower A | Super Structure | L26
41375 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-03-19 | 2026-03-21 | HVAC Grill Fixing | 100 | 0 |  | 2026-04-08 |  | 2026-04-11 |  | Tower A | Super Structure | L26 | MEP | HVAC Grill Fixing
41435 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-03-19 | 2026-03-26 | False Ceiling | 100 | 0 |  | 2026-04-08 |  | 2026-04-16 |  | Tower A | Super Structure | L30 | Finishes | False Ceiling
41482 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-03-19 | 2026-03-31 | Flooring & Dado | 100 | 0 |  | 2026-04-08 |  | 2026-04-20 |  | Tower A | Super Structure | L33 | Finishes | Flooring & Dado
41527 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-03-18 | 2026-03-26 | HVAC Ducting | 100 | 0 |  | 2026-04-08 |  | 2026-04-16 |  | Tower A | Super Structure | L36 | MEP | HVAC Ducting
45852 |  | Not Committed |  | 2026-02-02 | 2027-11-01 | GF-P1 | 100 | 0 |  | 2026-04-08 |  | 2027-12-22
45867 |  | Not Committed |  | 2026-02-02 | 2027-11-01 | Floor Area (Grand Entrance) | 100 | 0 |  | 2026-04-08 |  | 2027-12-22
45868 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-02-02 | 2026-02-24 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-04-08 |  | 2026-05-02 |  | Tower B | Super Structure | GF | MEP | FPS 1st Fix - MEP & Finishes
45899 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-02-02 | 2026-02-24 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-04-08 |  | 2026-05-02 |  | Tower B | Super Structure |  | MEP | FPS 1st Fix - MEP & Finishes
45900 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-02-02 | 2026-02-24 | PHE 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-04-08 |  | 2026-05-02 |  | Tower B | Super Structure
45901 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-02-02 | 2026-02-18 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-04-08 |  | 2026-04-25 |  | Tower B | Super Structure |  | MEP | Electrical 1st Fixes
45930 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-02-02 | 2026-02-18 | HVAC Ducting/ Fan Installations | 100 | 0 |  | 2026-04-08 |  | 2026-04-25 |  | Tower B | Super Structure |  | MEP | HVAC Ducting
45956 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-02-02 | 2026-02-12 | FAPA Cabling | 100 | 0 |  | 2026-04-08 |  | 2026-04-20 |  | Tower B | Super Structure
46012 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | VDF/ Grade Slab - MEP & Finishes | 2026-02-02 | 2026-03-26 | VDF/ Grade Slab & Apt. finishes | 100 | 0 |  | 2026-04-08 |  | 2026-06-02 |  | Tower B | Super Structure
46040 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-02-02 | 2026-02-09 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-04-08 |  | 2026-04-16 |  | Tower B | Super Structure |  | MEP | FPS 2nd Fix - MEP & Finishes
46041 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-02-02 | 2026-02-09 | FAPA Device Fixing | 100 | 0 |  | 2026-04-08 |  | 2026-04-16 |  | Tower B | Super Structure
46041 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-02-02 | 2026-02-09 | FAPA Device Fixing | 100 | 0 |  | 2026-04-08 |  | 2026-04-16 |  | Tower B | Super Structure
46041 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-02-02 | 2026-02-09 | FAPA Device Fixing | 100 | 0 |  | 2026-04-08 |  | 2026-04-16 |  | Tower B | Super Structure
46041 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-02-02 | 2026-02-09 | FAPA Device Fixing | 100 | 0 |  | 2026-04-08 |  | 2026-04-16 |  | Tower B | Super Structure
48213 | Retail & Clubhouse - Sub structure - B3 to B2 | Not Ready |  | 2025-10-30 | 2025-12-10 | B3 to B2 | 100 | 0 |  | 2026-04-08 |  | 2026-05-20 |  | Club House | Sub Structure | B3
48213 | Retail & Clubhouse - Sub structure - B3 to B2 | Not Ready |  | 2025-10-30 | 2025-12-10 | B3 to B2 | 100 | 0 |  | 2026-04-08 |  | 2026-05-20 |  | Club House | Sub Structure | B3
48213 | Retail & Clubhouse - Sub structure - B3 to B2 | Not Ready |  | 2025-10-30 | 2025-12-10 | B3 to B2 | 100 | 0 |  | 2026-04-08 |  | 2026-05-20 |  | Club House | Sub Structure | B3
9295 | T-15-8th Floor Common Area | Not Ready | Window-Open Area | 2026-04-08 | 2026-04-16 | Window-Open Area | 100 | 0 |  | 2026-04-09 |  | 2026-04-16
10414 | T-21-11th Floor Common Area | Not Ready | 1st Coat Painting | 2026-05-19 | 2026-06-09 | 1st Coat Painting | 100 | 0 |  | 2026-04-09 |  | 2026-05-04
10445 | T-21-Staircase 1 | Not Ready |  | 2026-05-08 | 2026-05-19 | 08F-07F | 100 | 0 |  | 2026-04-09 |  | 2026-04-21
10459 | T-21-Staircase 2 | Not Ready |  | 2026-05-08 | 2026-05-19 | 09F-08F | 100 | 0 |  | 2026-04-09 |  | 2026-04-21
10632 | T-20-GF Flat Area | Not Ready | 2nd Coat Painting | 2026-06-02 | 2026-08-06 | 2nd Coat Painting | 100 | 0 |  | 2026-04-09 |  | 2026-06-14
10779 | T-20-5th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-05-02 | 2026-06-04 | 2nd Coat Painting | 100 | 0 |  | 2026-04-09 |  | 2026-05-10
39224 |  | Not Ready |  | 2025-09-30 | 2025-11-11 | End Terminations @ DG Connections and Electrical Equipment (B01 and GF) | 100 | 0 |  | 2026-04-09 |  | 2026-05-20
39259 |  | Not Committed |  | 2025-10-30 | 2025-12-30 | B2 to B1 | 100 | 0 |  | 2026-04-09 |  | 2026-06-16
39259 |  | Not Committed |  | 2025-10-30 | 2025-12-30 | B2 to B1 | 100 | 0 |  | 2026-04-09 |  | 2026-06-16
39259 |  | Not Committed |  | 2025-10-30 | 2025-12-30 | B2 to B1 | 100 | 0 |  | 2026-04-09 |  | 2026-06-16
39260 | Retail - Sub structure - B2 to B1 | Not Ready | Retaining Wall RCC Works | 2025-10-30 | 2025-11-10 | Retaining Wall_lift 1 | 100 | 0 |  | 2026-04-09 |  | 2026-04-17 |  | Retail | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
39260 | Retail - Sub structure - B2 to B1 | Not Ready | Retaining Wall RCC Works | 2025-10-30 | 2025-11-10 | Retaining Wall_lift 1 | 100 | 0 |  | 2026-04-09 |  | 2026-04-17 |  | Retail | Sub Structure | B2
40455 | Tower A - Super Structure - Finishes & MEP - L74 to L75 | Not Ready | Partition Wall-Blockwork | 2026-03-18 | 2026-03-25 | Partition Walls | 100 | 0 |  | 2026-04-09 |  | 2026-04-16 |  | Tower A | Super Structure | L74
43298 |  | Not Committed |  | 2026-03-18 | 2026-10-17 | L68-69 | 100 | 0 |  | 2026-04-09 |  | 2026-09-30
43298 |  | Not Committed |  | 2026-03-18 | 2026-10-17 | L68-69 | 100 | 0 |  | 2026-04-09 |  | 2026-09-30 |  |  |  |  | Finishes | Gypsum Plastering Works
43299 |  | Not Committed |  | 2026-03-18 | 2026-04-15 | MEP 1st Fixes | 100 | 0 |  | 2026-04-09 |  | 2026-05-08
43300 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-03-18 | 2026-03-25 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-04-09 |  | 2026-04-16 |  | Tower A | Super Structure | L68 | MEP | FPS 1st Fix - MEP & Finishes
43301 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-03-18 | 2026-03-23 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-04-09 |  | 2026-04-14 |  | Tower A | Super Structure | L68 | MEP | Electrical 1st Fixes
43302 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-03-18 | 2026-03-25 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-04-09 |  | 2026-04-16 |  | Tower A | Super Structure | L68
43303 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-03-18 | 2026-04-03 | Wet Area Waterproofing | 100 | 0 |  | 2026-04-09 |  | 2026-04-25 |  | Tower A | Super Structure | L68
43973 | Tower A - Super Structure - Finishes & MEP - L7 to L15 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-05-11 | 2026-05-28 | Staircase Light Fixtures & Devices fixing | 100 | 0 |  | 2026-04-09 |  | 2026-04-27 |  | Tower A | Super Structure | L7
45295 |  | Not Ready |  | 2026-02-03 | 2026-02-17 | L15-16 | 100 | 0 |  | 2026-04-09 |  | 2026-04-24
45295 |  | Not Ready |  | 2026-02-03 | 2026-02-17 | L15-16 | 100 | 0 |  | 2026-04-09 |  | 2026-04-24 |  |  |  |  | Finishes | Gypsum Plastering Works
45296 | Tower B - Super Structure - Core & Outer Slab L15-16 | Not Ready | RCC Works - Vertical | 2026-02-03 | 2026-02-13 | Outer Columns_TA | 100 | 0 |  | 2026-04-09 |  | 2026-04-21 |  | Tower B | Super Structure | L15 | RCC Sub Structure | RCC Works - Vertical
45453 |  | Not Committed |  | 2026-02-03 | 2026-03-06 | L12-13 | 100 | 0 |  | 2026-04-09 |  | 2026-05-12
45453 |  | Not Committed |  | 2026-02-03 | 2026-03-06 | L12-13 | 100 | 0 |  | 2026-04-09 |  | 2026-05-12 |  |  |  |  | Finishes | Gypsum Plastering Works
45454 | Tower B - Super Structure - Finishes & MEP - L12 to L13 | Not Ready | Partition Wall-Blockwork | 2026-02-03 | 2026-02-19 | De-shuttering & Area clearance | 100 | 0 |  | 2026-04-09 |  | 2026-04-27 |  | Tower B | Super Structure | L12
45731 |  | Not Committed |  | 2026-02-03 | 2026-05-20 | L7-L15 | 100 | 0 |  | 2026-04-09 |  | 2026-07-29
45731 |  | Not Committed |  | 2026-02-03 | 2026-05-20 | L7-L15 | 100 | 0 |  | 2026-04-09 |  | 2026-07-29
45732 | Tower B - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2026-02-03 | 2026-02-25 | FHR Shaft Risers | 100 | 0 |  | 2026-04-09 |  | 2026-05-04 |  | Tower B | Super Structure | L7
45734 | Tower B - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2026-02-03 | 2026-03-27 | Domestic Water & Flushing Riser in Plumbing Shaft | 100 | 0 |  | 2026-04-09 |  | 2026-06-03 |  | Tower B | Super Structure | L7
45736 | Tower B - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2026-02-03 | 2026-03-10 | Shaft Cable Tray in Electrical Shaft | 100 | 0 |  | 2026-04-09 |  | 2026-05-15 |  | Tower B | Super Structure | L7
11984 |  | Not Ready |  | 2026-06-14 | 2027-02-04 | Lift lobby | 100 | 0 |  | 2026-04-10 |  | 2026-11-30
12014 |  | Not Ready |  | 2026-06-14 | 2026-11-17 | Staircase-2 | 100 | 0 |  | 2026-04-10 |  | 2026-09-11
40444 | Tower A - Super Structure - Finishes & MEP - L71 to L72 | Not Ready | Partition Wall-Blockwork | 2026-03-19 | 2026-03-24 | Staircase Area | 100 | 0 |  | 2026-04-10 |  | 2026-04-15 |  | Tower A | Super Structure | L71
40466 |  | Not Committed |  | 2026-03-13 | 2026-04-24 | Terrace Waterproofing | 100 | 0 |  | 2026-04-10 |  | 2026-05-25
40467 | Tower A - Super Structure - Finishes & MEP - Above Terrace | Not Ready | Waterproofing | 2026-03-13 | 2026-03-20 | Area clearance & preparation | 100 | 0 |  | 2026-04-10 |  | 2026-04-18 |  | Tower A | Super Structure
41388 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-03-20 | 2026-03-24 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-04-10 |  | 2026-04-14 |  | Tower A | Super Structure | L27 | MEP | FPS 2nd Fix - MEP & Finishes
41389 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-03-20 | 2026-03-26 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-04-10 |  | 2026-04-16 |  | Tower A | Super Structure | L27 | MEP | Electrical 2nd Fix - MEP & Finishes
41390 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-20 | 2026-03-28 | FAPA Device Fixing | 100 | 0 |  | 2026-04-10 |  | 2026-04-18 |  | Tower A | Super Structure | L27
41390 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-20 | 2026-03-28 | FAPA Device Fixing | 100 | 0 |  | 2026-04-10 |  | 2026-04-18 |  | Tower A | Super Structure | L27
41390 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-20 | 2026-03-28 | FAPA Device Fixing | 100 | 0 |  | 2026-04-10 |  | 2026-04-18 |  | Tower A | Super Structure | L27
41390 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-20 | 2026-03-28 | FAPA Device Fixing | 100 | 0 |  | 2026-04-10 |  | 2026-04-18 |  | Tower A | Super Structure | L27
41391 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-03-20 | 2026-03-24 | HVAC Grill Fixing | 100 | 0 |  | 2026-04-10 |  | 2026-04-14 |  | Tower A | Super Structure | L27 | MEP | HVAC Grill Fixing
41451 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-03-20 | 2026-03-28 | False Ceiling | 100 | 0 |  | 2026-04-10 |  | 2026-04-18 |  | Tower A | Super Structure | L31 | Finishes | False Ceiling
41498 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-03-21 | 2026-04-01 | Flooring & Dado | 100 | 0 |  | 2026-04-10 |  | 2026-04-22 |  | Tower A | Super Structure | L34 | Finishes | Flooring & Dado
42057 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2026-03-12 | 2026-03-17 | Lobby Plastering | 100 | 0 |  | 2026-04-10 |  | 2026-04-16 |  | Tower A | Super Structure | L69 | Finishes | Lobby Plastering
43268 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-03-19 | 2026-03-30 | Cement Plastering in wet areas | 100 | 0 |  | 2026-04-10 |  | 2026-04-21 |  | Tower A | Super Structure | L66
44572 | NTA_Zone 2 - Super Structure - P2 to P3 | Not Ready | Finishes (Lobby & Floor Area) | 2025-07-09 | 2025-08-19 | Staircase Finishes | 100 | 0 |  | 2026-04-10 |  | 2026-05-15 |  | NTA_Zone 2 | Super Structure
44572 | NTA_Zone 2 - Super Structure - P2 to P3 | Not Ready | Finishes (Lobby & Floor Area) | 2025-07-09 | 2025-08-19 | Staircase Finishes | 100 | 0 |  | 2026-04-10 |  | 2026-05-15 |  | NTA_Zone 2 | Super Structure
44575 | NTA_Zone 2 - Super Structure - P3 to P4 | Not Ready | Finishes (Lobby & Floor Area) | 2025-08-09 | 2025-09-18 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2026-04-10 |  | 2026-05-15 |  | NTA_Zone 2 | Super Structure
44575 | NTA_Zone 2 - Super Structure - P3 to P4 | Not Ready | Finishes (Lobby & Floor Area) | 2025-08-09 | 2025-09-18 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2026-04-10 |  | 2026-05-15 |  | NTA_Zone 2 | Super Structure
46709 |  | Not Committed |  | 2026-02-04 | 2027-03-08 | L10-11 | 100 | 0 |  | 2026-04-10 |  | 2027-05-08
46709 |  | Not Committed |  | 2026-02-04 | 2027-03-08 | L10-11 | 100 | 0 |  | 2026-04-10 |  | 2027-05-08 |  |  |  |  | Finishes | Gypsum Plastering Works
46710 |  | Not Committed |  | 2026-02-04 | 2026-03-13 | MEP 1st Fixes | 100 | 0 |  | 2026-04-10 |  | 2026-05-19
46711 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-02-04 | 2026-02-11 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-04-10 |  | 2026-04-18 |  | Tower B | Super Structure | L10 | MEP | FPS 1st Fix - MEP & Finishes
46712 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-02-04 | 2026-02-09 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-04-10 |  | 2026-04-16 |  | Tower B | Super Structure | L10 | MEP | Electrical 1st Fixes
46713 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-02-04 | 2026-02-11 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-04-10 |  | 2026-04-18 |  | Tower B | Super Structure | L10
8644 | T-14-4th Floor Common Area | Not Ready | Door-Shaft | 2026-03-07 | 2026-03-20 | Door-Shaft | 100 | 0 |  | 2026-04-11 |  | 2026-04-24
8672 | T-14-5th Floor Common Area | Not Ready | 1st Coat Painting | 2026-03-06 | 2026-03-28 | 1st Coat Painting | 100 | 0 |  | 2026-04-11 |  | 2026-05-02
8749 | T-14-8th Floor Common Area | Not Ready | Window-Open Area | 2026-03-09 | 2026-03-17 | Window-Open Area | 100 | 0 |  | 2026-04-11 |  | 2026-04-19
9402 | T-15-Staircase 1 | Not Ready |  | 2026-04-22 | 2026-05-04 | 11F-10F | 100 | 0 |  | 2026-04-11 |  | 2026-04-22
9416 | T-15-Staircase 2 | Not Ready |  | 2026-04-22 | 2026-05-04 | 12F-11F | 100 | 0 |  | 2026-04-11 |  | 2026-04-22
9880 | T-16-11th Floor Flat Area | Not Ready | Toilets False Celing | 2026-04-30 | 2026-06-03 | Toilets False Celing | 100 | 0 |  | 2026-04-11 |  | 2026-05-12
9904 |  | Not Ready |  | 2026-06-09 | 2027-01-29 | Lift lobby | 100 | 0 |  | 2026-04-11 |  | 2026-12-01
9934 |  | Not Ready |  | 2026-06-09 | 2026-11-12 | Staircase-2 | 100 | 0 |  | 2026-04-11 |  | 2026-09-12
10725 | T-20-3rd Floor Common Area | Not Ready | Window-Open Area | 2026-05-06 | 2026-05-13 | Window-Open Area | 100 | 0 |  | 2026-04-11 |  | 2026-04-18
40459 | Tower A - Super Structure - Finishes & MEP - L75 to L76 | Not Ready | Partition Wall-Blockwork | 2026-03-20 | 2026-03-27 | Partition Walls | 100 | 0 |  | 2026-04-11 |  | 2026-04-18 |  | Tower A | Super Structure | L75
41376 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-03-23 | 2026-03-25 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-04-11 |  | 2026-04-15 |  | Tower A | Super Structure | L26
41543 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-03-21 | 2026-03-30 | HVAC Ducting | 100 | 0 |  | 2026-04-11 |  | 2026-04-20 |  | Tower A | Super Structure | L37 | MEP | HVAC Ducting
43232 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-03-20 | 2026-03-31 | Cement Plastering in wet areas | 100 | 0 |  | 2026-04-11 |  | 2026-04-22 |  | Tower A | Super Structure | L64
43316 |  | Not Committed |  | 2026-03-20 | 2026-10-17 | L69-70 | 100 | 0 |  | 2026-04-11 |  | 2026-09-30
43316 |  | Not Committed |  | 2026-03-20 | 2026-10-17 | L69-70 | 100 | 0 |  | 2026-04-11 |  | 2026-09-30 |  |  |  |  | Finishes | Gypsum Plastering Works
43317 |  | Not Committed |  | 2026-03-20 | 2026-04-17 | MEP 1st Fixes | 100 | 0 |  | 2026-04-11 |  | 2026-05-11
43318 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-03-20 | 2026-03-27 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-04-11 |  | 2026-04-18 |  | Tower A | Super Structure | L69 | MEP | FPS 1st Fix - MEP & Finishes
43319 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-03-20 | 2026-03-25 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-04-11 |  | 2026-04-16 |  | Tower A | Super Structure | L69 | MEP | Electrical 1st Fixes
43320 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-03-20 | 2026-03-27 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-04-11 |  | 2026-04-18 |  | Tower A | Super Structure | L69
43321 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-03-20 | 2026-04-06 | Wet Area Waterproofing | 100 | 0 |  | 2026-04-11 |  | 2026-04-28 |  | Tower A | Super Structure | L69
44124 | Tower A - Super Structure - Finishes & MEP - L63 to L68 | Not Ready | Façade Works - MEP & Finishes | 2026-05-13 | 2026-05-23 | Accessories & Alignment | 100 | 0 |  | 2026-04-11 |  | 2026-04-23 |  | Tower A | Super Structure | L63 | Façade | Façade Works
44124 | Tower A - Super Structure - Finishes & MEP - L63 to L68 | Not Ready | Façade Works - MEP & Finishes | 2026-05-13 | 2026-05-23 | Accessories & Alignment | 100 | 0 |  | 2026-04-11 |  | 2026-04-23 |  | Tower A | Super Structure | L63
44586 |  | Not Ready | MEP fix & Finishes | 2026-04-14 | 2026-04-24 | Final Painting | 100 | 0 |  | 2026-04-11 |  | 2026-04-22 |  |  |  |  | Finishes | Final Painting
44586 |  | Not Ready | MEP fix & Finishes | 2026-04-14 | 2026-04-24 | Final Painting | 100 | 0 |  | 2026-04-11 |  | 2026-04-22 |  |  |  |  | Finishes | Final Painting
44586 |  | Not Ready | MEP fix & Finishes | 2026-04-14 | 2026-04-24 | Final Painting | 100 | 0 |  | 2026-04-11 |  | 2026-04-22 |  |  |  |  | Finishes | Final Painting
44591 |  | Not Ready | MEP fix & Finishes | 2026-04-14 | 2026-04-21 | HVAC Fans fixing | 100 | 0 |  | 2026-04-11 |  | 2026-04-18 |  |  |  |  | MEP | HVAC Grill Fixing
44591 |  | Not Ready | MEP fix & Finishes | 2026-04-14 | 2026-04-21 | HVAC Fans fixing | 100 | 0 |  | 2026-04-11 |  | 2026-04-18 |  |  |  |  | MEP | HVAC Grill Fixing
44596 |  | Not Ready | MEP fix & Finishes | 2026-04-14 | 2026-04-21 | FAPA Device Fixing | 100 | 0 |  | 2026-04-11 |  | 2026-04-18
44596 |  | Not Ready | MEP fix & Finishes | 2026-04-14 | 2026-04-21 | FAPA Device Fixing | 100 | 0 |  | 2026-04-11 |  | 2026-04-18
44596 |  | Not Ready | MEP fix & Finishes | 2026-04-14 | 2026-04-21 | FAPA Device Fixing | 100 | 0 |  | 2026-04-11 |  | 2026-04-18
44596 |  | Not Ready | MEP fix & Finishes | 2026-04-14 | 2026-04-21 | FAPA Device Fixing | 100 | 0 |  | 2026-04-11 |  | 2026-04-18
44606 |  | Not Committed |  | 2026-04-14 | 2026-05-26 | P1 to P2 | 100 | 0 |  | 2026-04-11 |  | 2026-05-23
44606 |  | Not Committed |  | 2026-04-14 | 2026-05-26 | P1 to P2 | 100 | 0 |  | 2026-04-11 |  | 2026-05-23
44606 |  | Not Committed |  | 2026-04-14 | 2026-05-26 | P1 to P2 | 100 | 0 |  | 2026-04-11 |  | 2026-05-23
44607 |  | Not Ready | MEP fix & Finishes | 2026-04-14 | 2026-04-21 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2026-04-11 |  | 2026-04-18 |  |  |  |  | MEP | FPS final fixes
44607 |  | Not Ready | MEP fix & Finishes | 2026-04-14 | 2026-04-21 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2026-04-11 |  | 2026-04-18 |  |  |  |  | MEP | FPS final fixes
45451 | Tower B - Super Structure - Finishes & MEP - L11 to L12 | Not Ready | Partition Wall-Blockwork | 2026-02-05 | 2026-02-12 | Partition Walls | 100 | 0 |  | 2026-04-11 |  | 2026-04-20 |  | Tower B | Super Structure | L11
48041 | Club House - Super structure - CH00 to CH01 | Not Ready |  | 2025-12-19 | 2026-01-12 | Slab_CH | 100 | 0 |  | 2026-04-11 |  | 2026-05-05 |  | Club House | Super Structure | CH00
9429 |  | Not Ready |  | 2026-04-17 | 2026-10-12 | External Finishes | 100 | 0 |  | 2026-04-12 |  | 2026-10-07
9430 |  | Not Ready |  | 2026-04-17 | 2026-10-12 | External Painting | 100 | 0 |  | 2026-04-12 |  | 2026-10-07
10179 | T-21-2nd Floor Common Area | Not Ready | Window-Open Area | 2026-05-16 | 2026-05-23 | Window-Open Area | 100 | 0 |  | 2026-04-12 |  | 2026-04-20
10908 | T-20-11th Floor Common Area | Not Ready | 1st Coat Painting | 2026-05-13 | 2026-06-04 | 1st Coat Painting | 100 | 0 |  | 2026-04-12 |  | 2026-05-03
10947 | T-20-Lift Lobby | Not Ready |  | 2026-05-09 | 2026-05-25 | 10F | 100 | 0 |  | 2026-04-12 |  | 2026-04-27
11216 | T-19-2nd Floor Common Area | Not Ready | Flooring & skirting | 2026-04-25 | 2026-05-18 | Flooring & skirting | 100 | 0 |  | 2026-04-12 |  | 2026-05-03
11243 | T-19-3rd Floor Common Area | Not Ready | Putty | 2026-04-25 | 2026-06-04 | Putty | 100 | 0 |  | 2026-04-12 |  | 2026-05-19
11349 | T-19-7th Floor Common Area | Not Ready | Window-Open Area | 2026-04-28 | 2026-05-06 | Window-Open Area | 100 | 0 |  | 2026-04-12 |  | 2026-04-19
11374 | T-19-8th Floor Common Area | Not Ready | Door-Shaft | 2026-05-02 | 2026-05-15 | Door-Shaft | 100 | 0 |  | 2026-04-12 |  | 2026-04-25
11921 | T-18-9th Floor Common Area | Not Ready | Window-Open Area | 2026-06-27 | 2026-07-04 | Window-Open Area | 100 | 0 |  | 2026-04-12 |  | 2026-04-23
11980 | T-18-Lift | Not Ready | PARAPET | 2026-07-06 | 2026-09-10 | Parapets | 100 | 0 |  | 2026-04-12 |  | 2026-06-15
11986 | T-18-Lift Lobby | Not Ready |  | 2026-06-30 | 2026-07-17 | 11F | 100 | 0 |  | 2026-04-12 |  | 2026-05-01
12032 | T-18- Elevation-B | Not Ready |  | 2026-06-30 | 2026-09-21 | Elevation-B | 100 | 0 |  | 2026-04-12 |  | 2026-07-04
8774 | T-14-9th Floor Common Area | Not Ready | Door-Shaft | 2026-03-12 | 2026-03-26 | Door-Shaft | 100 | 0 |  | 2026-04-13 |  | 2026-04-27
8820 | T-14-11th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-03-16 | 2026-06-08 | 1st Coat Painting | 100 | 0 |  | 2026-04-13 |  | 2026-07-06
9190 | T-15-4th Floor Common Area | Not Ready | Door-Shaft | 2026-04-06 | 2026-04-19 | Door-Shaft | 100 | 0 |  | 2026-04-13 |  | 2026-04-26
10363 | T-21-9th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-05-24 | 2026-06-25 | 2nd Coat Painting | 100 | 0 |  | 2026-04-13 |  | 2026-05-17
10381 | T-21-10th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-05-24 | 2026-07-28 | 2nd Coat Painting | 100 | 0 |  | 2026-04-13 |  | 2026-06-20
10428 | T-21-Lift Lobby | Not Ready |  | 2026-05-14 | 2026-05-30 | 09F | 100 | 0 |  | 2026-04-13 |  | 2026-04-27
12002 | T-18-Staircase 1 | Not Ready |  | 2026-06-25 | 2026-07-06 | 11F-10F | 100 | 0 |  | 2026-04-13 |  | 2026-04-23
12016 | T-18-Staircase 2 | Not Ready |  | 2026-06-25 | 2026-07-06 | 12F-11F | 100 | 0 |  | 2026-04-13 |  | 2026-04-23
40064 | Tower A - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2026-03-21 | 2026-04-24 | Completion of Electrical Works | 100 | 0 |  | 2026-04-13 |  | 2026-05-19 |  | Tower A | Super Structure
40064 | Tower A - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2026-03-21 | 2026-04-24 | Completion of Electrical Works | 100 | 0 |  | 2026-04-13 |  | 2026-05-19 |  | Tower A | Super Structure
40448 | Tower A - Super Structure - Finishes & MEP - L72 to L73 | Not Ready | Partition Wall-Blockwork | 2026-03-21 | 2026-03-26 | Staircase Area | 100 | 0 |  | 2026-04-13 |  | 2026-04-17 |  | Tower A | Super Structure | L72
40541 | Tower A - Super Structure - Finishes & MEP - L67 to L68 | Not Ready | Gypsum Plastering Works | 2026-03-21 | 2026-04-07 | L67-68 | 100 | 0 |  | 2026-04-13 |  | 2026-04-29 |  | Tower A | Super Structure | L67 | Finishes | Gypsum Plastering Works
40541 | Tower A - Super Structure - Finishes & MEP - L67 to L68 | Not Ready | Gypsum Plastering Works | 2026-03-21 | 2026-04-07 | L67-68 | 100 | 0 |  | 2026-04-13 |  | 2026-04-29 |  | Tower A | Super Structure | L67
41404 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-03-23 | 2026-03-26 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-04-13 |  | 2026-04-15 |  | Tower A | Super Structure | L28 | MEP | FPS 2nd Fix - MEP & Finishes
41405 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-03-23 | 2026-03-28 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-04-13 |  | 2026-04-17 |  | Tower A | Super Structure | L28 | MEP | Electrical 2nd Fix - MEP & Finishes
41406 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-23 | 2026-03-31 | FAPA Device Fixing | 100 | 0 |  | 2026-04-13 |  | 2026-04-20 |  | Tower A | Super Structure | L28
41406 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-23 | 2026-03-31 | FAPA Device Fixing | 100 | 0 |  | 2026-04-13 |  | 2026-04-20 |  | Tower A | Super Structure | L28
41406 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-23 | 2026-03-31 | FAPA Device Fixing | 100 | 0 |  | 2026-04-13 |  | 2026-04-20 |  | Tower A | Super Structure | L28
41406 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-23 | 2026-03-31 | FAPA Device Fixing | 100 | 0 |  | 2026-04-13 |  | 2026-04-20 |  | Tower A | Super Structure | L28
41407 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-03-23 | 2026-03-26 | HVAC Grill Fixing | 100 | 0 |  | 2026-04-13 |  | 2026-04-15 |  | Tower A | Super Structure | L28 | MEP | HVAC Grill Fixing
41467 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-03-23 | 2026-03-31 | False Ceiling | 100 | 0 |  | 2026-04-13 |  | 2026-04-20 |  | Tower A | Super Structure | L32 | Finishes | False Ceiling
41514 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-03-23 | 2026-04-03 | Flooring & Dado | 100 | 0 |  | 2026-04-13 |  | 2026-04-24 |  | Tower A | Super Structure | L35 | Finishes | Flooring & Dado
43182 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-05-07 | 2026-05-23 | Flooring & Dado works | 100 | 0 |  | 2026-04-13 |  | 2026-04-29 |  | Tower A | Super Structure | L61 | Finishes | Flooring & Dado
43199 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-03-21 | 2026-03-28 | Door & Window Frame work | 100 | 0 |  | 2026-04-13 |  | 2026-04-20 |  | Tower A | Super Structure | L62 | Finishes | Door & Window Frame work
10857 | T-20-8th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-05-13 | 2026-06-15 | 2nd Coat Painting | 100 | 0 |  | 2026-04-14 |  | 2026-05-15
11946 | T-18-11th Floor Common Area | Not Ready | Door-Shaft | 2026-06-30 | 2026-07-14 | Door-Shaft | 100 | 0 |  | 2026-04-14 |  | 2026-04-29
40315 | Tower A - Super Structure - Finishes & MEP - L76 to L77 | Not Ready | Partition Wall-Blockwork | 2026-03-23 | 2026-03-30 | Partition Walls | 100 | 0 |  | 2026-04-14 |  | 2026-04-21 |  | Tower A | Super Structure | L76
41362 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-03-25 | 2026-03-30 | Final Painting | 100 | 0 |  | 2026-04-14 |  | 2026-04-20 |  | Tower A | Super Structure | L25 | Finishes | Final Painting
41362 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-03-25 | 2026-03-30 | Final Painting | 100 | 0 |  | 2026-04-14 |  | 2026-04-20 |  | Tower A | Super Structure | L25 | Finishes | Final Painting
41362 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-03-25 | 2026-03-30 | Final Painting | 100 | 0 |  | 2026-04-14 |  | 2026-04-20 |  | Tower A | Super Structure | L25 | Finishes | Final Painting
41392 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-03-24 | 2026-03-27 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-04-14 |  | 2026-04-17 |  | Tower A | Super Structure | L27
41420 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-03-25 | 2026-03-28 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-04-14 |  | 2026-04-17 |  | Tower A | Super Structure | L29 | MEP | FPS 2nd Fix - MEP & Finishes
41421 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-03-25 | 2026-03-31 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-04-14 |  | 2026-04-20 |  | Tower A | Super Structure | L29 | MEP | Electrical 2nd Fix - MEP & Finishes
41422 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-25 | 2026-04-02 | FAPA Device Fixing | 100 | 0 |  | 2026-04-14 |  | 2026-04-22 |  | Tower A | Super Structure | L29
41422 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-25 | 2026-04-02 | FAPA Device Fixing | 100 | 0 |  | 2026-04-14 |  | 2026-04-22 |  | Tower A | Super Structure | L29
41422 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-25 | 2026-04-02 | FAPA Device Fixing | 100 | 0 |  | 2026-04-14 |  | 2026-04-22 |  | Tower A | Super Structure | L29
41422 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-25 | 2026-04-02 | FAPA Device Fixing | 100 | 0 |  | 2026-04-14 |  | 2026-04-22 |  | Tower A | Super Structure | L29
41423 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-03-25 | 2026-03-28 | HVAC Grill Fixing | 100 | 0 |  | 2026-04-14 |  | 2026-04-17 |  | Tower A | Super Structure | L29 | MEP | HVAC Grill Fixing
41483 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-03-25 | 2026-04-02 | False Ceiling | 100 | 0 |  | 2026-04-14 |  | 2026-04-22 |  | Tower A | Super Structure | L33 | Finishes | False Ceiling
43334 |  | Not Committed |  | 2026-03-23 | 2026-10-24 | L70-71 | 100 | 0 |  | 2026-04-14 |  | 2026-10-07
43334 |  | Not Committed |  | 2026-03-23 | 2026-10-24 | L70-71 | 100 | 0 |  | 2026-04-14 |  | 2026-10-07 |  |  |  |  | Finishes | Gypsum Plastering Works
43335 |  | Not Committed |  | 2026-03-23 | 2026-04-20 | MEP 1st Fixes | 100 | 0 |  | 2026-04-14 |  | 2026-05-13
43336 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-03-23 | 2026-03-30 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-04-14 |  | 2026-04-21 |  | Tower A | Super Structure | L70 | MEP | FPS 1st Fix - MEP & Finishes
43337 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-03-23 | 2026-03-27 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-04-14 |  | 2026-04-18 |  | Tower A | Super Structure | L70 | MEP | Electrical 1st Fixes
43338 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-03-23 | 2026-03-30 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-04-14 |  | 2026-04-21 |  | Tower A | Super Structure | L70
43339 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-03-23 | 2026-04-08 | Wet Area Waterproofing | 100 | 0 |  | 2026-04-14 |  | 2026-04-30 |  | Tower A | Super Structure | L70
45903 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-02-07 | 2026-02-24 | HVAC Ducting/ Fan Installations | 100 | 0 |  | 2026-04-14 |  | 2026-05-02 |  | Tower B | Super Structure |  | MEP | HVAC Ducting
45929 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-02-07 | 2026-02-18 | FAPA Cabling | 100 | 0 |  | 2026-04-14 |  | 2026-04-25 |  | Tower B | Super Structure
45985 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | VDF/ Grade Slab - MEP & Finishes | 2026-02-07 | 2026-04-01 | VDF/ Grade Slab & Apt. finishes | 100 | 0 |  | 2026-04-14 |  | 2026-06-08 |  | Tower B | Super Structure
9432 | T-15- Elevation-B | Not Ready |  | 2026-04-28 | 2026-07-20 | Elevation-B | 100 | 0 |  | 2026-04-15 |  | 2026-07-07
9890 | T-16-11th Floor Common Area | Not Ready | Flooring & skirting | 2026-05-13 | 2026-06-03 | Flooring & skirting | 100 | 0 |  | 2026-04-15 |  | 2026-05-06
10964 | T-20-Staircase 1 | Not Ready |  | 2026-05-09 | 2026-05-20 | 09F-08F | 100 | 0 |  | 2026-04-15 |  | 2026-04-24
10978 | T-20-Staircase 2 | Not Ready |  | 2026-05-09 | 2026-05-20 | 10F-09F | 100 | 0 |  | 2026-04-15 |  | 2026-04-24
11978 | T-18-Lift | Not Ready | LMR ROOM | 2026-07-08 | 2026-09-12 | Lift Machine Rooms | 100 | 0 |  | 2026-04-15 |  | 2026-06-19
12029 |  | Not Ready |  | 2026-06-19 | 2026-12-15 | External Finishes | 100 | 0 |  | 2026-04-15 |  | 2026-10-10
12030 |  | Not Ready |  | 2026-06-19 | 2026-12-15 | External Painting | 100 | 0 |  | 2026-04-15 |  | 2026-10-10
40452 | Tower A - Super Structure - Finishes & MEP - L73 to L74 | Not Ready | Partition Wall-Blockwork | 2026-03-24 | 2026-03-28 | Staircase Area | 100 | 0 |  | 2026-04-15 |  | 2026-04-20 |  | Tower A | Super Structure | L73
41377 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-03-26 | 2026-03-31 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-04-15 |  | 2026-04-21 |  | Tower A | Super Structure | L26 | MEP | Electrical
41559 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-03-25 | 2026-04-02 | HVAC Ducting | 100 | 0 |  | 2026-04-15 |  | 2026-04-23 |  | Tower A | Super Structure | L38 | MEP | HVAC Ducting
43979 | Tower A - Super Structure - Finishes & MEP - L15 to L25 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-05-16 | 2026-05-28 | Staircase cabling | 100 | 0 |  | 2026-04-15 |  | 2026-04-27 |  | Tower A | Super Structure | L15
8788 | T-14-10th Floor Flat Area | Not Ready | Toilets False Celing | 2026-03-18 | 2026-04-21 | Toilets False Celing | 100 | 0 |  | 2026-04-16 |  | 2026-05-18
8840 | T-14-12th Floor Flat Area | Not Ready | Toilets False Celing | 2026-03-18 | 2026-04-21 | Toilets False Celing | 100 | 0 |  | 2026-04-16 |  | 2026-05-18
8864 |  | Not Ready |  | 2026-04-15 | 2026-12-05 | Lift lobby | 100 | 0 |  | 2026-04-16 |  | 2026-12-06
8894 |  | Not Ready |  | 2026-04-15 | 2026-09-17 | Staircase-2 | 100 | 0 |  | 2026-04-16 |  | 2026-09-18
9110 | T-15-1st Floor Common Area | Not Ready | Flooring & skirting | 2026-04-11 | 2026-05-04 | Flooring & skirting | 100 | 0 |  | 2026-04-16 |  | 2026-05-07
9137 | T-15-2nd Floor Common Area | Not Ready | Putty | 2026-04-11 | 2026-05-21 | Putty | 100 | 0 |  | 2026-04-16 |  | 2026-05-24
9949 |  | Not Ready |  | 2026-06-14 | 2026-12-09 | External Finishes | 100 | 0 |  | 2026-04-16 |  | 2026-10-11
9950 |  | Not Ready |  | 2026-06-14 | 2026-12-09 | External Painting | 100 | 0 |  | 2026-04-16 |  | 2026-10-11
10649 | T-20-GF Common Area | Not Ready | 2nd Coat Painting | 2026-06-10 | 2026-08-26 | 2nd Coat Painting | 100 | 0 |  | 2026-04-16 |  | 2026-07-01
11791 | T-18-4th Floor Common Area | Not Ready | Window-Open Area | 2026-06-22 | 2026-06-29 | Window-Open Area | 100 | 0 |  | 2026-04-16 |  | 2026-04-23
11871 | T-18-7th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-06-29 | 2026-08-01 | 2nd Coat Painting | 100 | 0 |  | 2026-04-16 |  | 2026-05-18
11979 | T-18-Lift | Not Ready | STAIRCASE HR | 2026-07-13 | 2026-09-17 | Staircase Headrooms | 100 | 0 |  | 2026-04-16 |  | 2026-06-21
39210 |  | Not Ready |  | 2025-05-26 | 2025-07-04 | End Terminations @ Transformer Connections and High Side Equipment | 100 | 0 |  | 2026-04-16 |  | 2026-05-27
40094 | Tower A - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2026-03-19 | 2026-04-04 | FPS & PHE Pumps foundation & handover to MEP | 100 | 0 |  | 2026-04-16 |  | 2026-05-05 |  | Tower A | Super Structure
41408 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-03-26 | 2026-03-30 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-04-16 |  | 2026-04-18 |  | Tower A | Super Structure | L28
41436 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-03-27 | 2026-03-30 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-04-16 |  | 2026-04-20 |  | Tower A | Super Structure | L30 | MEP | FPS 2nd Fix - MEP & Finishes
41437 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-03-27 | 2026-04-01 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-04-16 |  | 2026-04-22 |  | Tower A | Super Structure | L30 | MEP | Electrical 2nd Fix - MEP & Finishes
41438 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-27 | 2026-04-03 | FAPA Device Fixing | 100 | 0 |  | 2026-04-16 |  | 2026-04-24 |  | Tower A | Super Structure | L30
41438 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-27 | 2026-04-03 | FAPA Device Fixing | 100 | 0 |  | 2026-04-16 |  | 2026-04-24 |  | Tower A | Super Structure | L30
41438 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-27 | 2026-04-03 | FAPA Device Fixing | 100 | 0 |  | 2026-04-16 |  | 2026-04-24 |  | Tower A | Super Structure | L30
41438 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-27 | 2026-04-03 | FAPA Device Fixing | 100 | 0 |  | 2026-04-16 |  | 2026-04-24 |  | Tower A | Super Structure | L30
41439 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-03-27 | 2026-03-30 | HVAC Grill Fixing | 100 | 0 |  | 2026-04-16 |  | 2026-04-20 |  | Tower A | Super Structure | L30 | MEP | HVAC Grill Fixing
41499 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-03-27 | 2026-04-03 | False Ceiling | 100 | 0 |  | 2026-04-16 |  | 2026-04-24 |  | Tower A | Super Structure | L34 | Finishes | False Ceiling
41530 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-03-26 | 2026-04-07 | Flooring & Dado | 100 | 0 |  | 2026-04-16 |  | 2026-04-28 |  | Tower A | Super Structure | L36 | Finishes | Flooring & Dado
43352 |  | Not Committed |  | 2026-03-25 | 2026-10-24 | L71-72 | 100 | 0 |  | 2026-04-16 |  | 2026-10-07
43352 |  | Not Committed |  | 2026-03-25 | 2026-10-24 | L71-72 | 100 | 0 |  | 2026-04-16 |  | 2026-10-07 |  |  |  |  | Finishes | Gypsum Plastering Works
43353 |  | Not Committed |  | 2026-03-25 | 2026-04-22 | MEP 1st Fixes | 100 | 0 |  | 2026-04-16 |  | 2026-05-15
43354 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-03-25 | 2026-04-01 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-04-16 |  | 2026-04-23 |  | Tower A | Super Structure | L71 | MEP | FPS 1st Fix - MEP & Finishes
43355 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-03-25 | 2026-03-30 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-04-16 |  | 2026-04-21 |  | Tower A | Super Structure | L71 | MEP | Electrical 1st Fixes
43356 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-03-25 | 2026-04-01 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-04-16 |  | 2026-04-23 |  | Tower A | Super Structure | L71
43357 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-03-25 | 2026-04-10 | Wet Area Waterproofing | 100 | 0 |  | 2026-04-16 |  | 2026-05-04 |  | Tower A | Super Structure | L71
45297 | Tower B - Super Structure - Core & Outer Slab L15-16 | Not Ready | RCC Works - Slab | 2026-02-10 | 2026-02-17 | Outer Slab_TA | 100 | 0 |  | 2026-04-16 |  | 2026-04-24 |  | Tower B | Super Structure | L15 | RCC Sub Structure | RCC Works - Slab
46042 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2026-02-10 | 2026-02-18 | Final Painting | 100 | 0 |  | 2026-04-16 |  | 2026-04-25 |  | Tower B | Super Structure |  | Finishes | Final Painting
46042 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2026-02-10 | 2026-02-18 | Final Painting | 100 | 0 |  | 2026-04-16 |  | 2026-04-25 |  | Tower B | Super Structure |  | Finishes | Final Painting
46042 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2026-02-10 | 2026-02-18 | Final Painting | 100 | 0 |  | 2026-04-16 |  | 2026-04-25 |  | Tower B | Super Structure |  | Finishes | Final Painting
9296 | T-15-8th Floor Common Area | Not Ready | 1st Coat Painting | 2026-04-16 | 2026-05-08 | 1st Coat Painting | 100 | 0 |  | 2026-04-17 |  | 2026-05-08
9386 | T-15-Lift Lobby | Not Ready |  | 2026-04-28 | 2026-05-15 | 11F | 100 | 0 |  | 2026-04-17 |  | 2026-05-02
11451 | T-19-11th Floor Common Area | Not Ready | Putty | 2026-05-13 | 2026-06-20 | Putty | 100 | 0 |  | 2026-04-17 |  | 2026-05-27
40456 | Tower A - Super Structure - Finishes & MEP - L74 to L75 | Not Ready | Partition Wall-Blockwork | 2026-03-26 | 2026-03-31 | Staircase Area | 100 | 0 |  | 2026-04-17 |  | 2026-04-22 |  | Tower A | Super Structure | L74
41393 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-03-27 | 2026-04-02 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-04-17 |  | 2026-04-23 |  | Tower A | Super Structure | L27 | MEP | Electrical
41424 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-03-28 | 2026-04-01 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-04-17 |  | 2026-04-21 |  | Tower A | Super Structure | L29
44127 | Tower A - Super Structure - Finishes & MEP - L68 to L73 | Not Ready | Façade Works - MEP & Finishes | 2026-05-19 | 2026-05-30 | DGU Assembly Installation | 100 | 0 |  | 2026-04-17 |  | 2026-04-29 |  | Tower A | Super Structure | L68 | Façade | Façade Works
44128 | Tower A - Super Structure - Finishes & MEP - L68 to L73 | Not Ready | Façade Works - MEP & Finishes | 2026-05-19 | 2026-06-11 | Installation of highly reflective metal sheet | 100 | 0 |  | 2026-04-17 |  | 2026-05-12 |  | Tower A | Super Structure | L68 | Façade | Façade Works
44129 | Tower A - Super Structure - Finishes & MEP - L68 to L73 | Not Ready | Façade Works - MEP & Finishes | 2026-05-19 | 2026-05-30 | Fixing of Backlit Laminated Glass assembly & ACP Panels | 100 | 0 |  | 2026-04-17 |  | 2026-04-29 |  | Tower A | Super Structure | L68 | Façade | Façade Works
44130 | Tower A - Super Structure - Finishes & MEP - L68 to L73 | Not Ready | Façade Works - MEP & Finishes | 2026-05-19 | 2026-05-30 | Fixing of Louvers | 100 | 0 |  | 2026-04-17 |  | 2026-04-29 |  | Tower A | Super Structure | L68 | Façade | Façade Works
44130 | Tower A - Super Structure - Finishes & MEP - L68 to L73 | Not Ready | Façade Works - MEP & Finishes | 2026-05-19 | 2026-05-30 | Fixing of Louvers | 100 | 0 |  | 2026-04-17 |  | 2026-04-29 |  | Tower A | Super Structure | L68
9763 | T-16-6th Floor Common Area | Not Ready | Window-Open Area | 2026-05-04 | 2026-05-11 | Window-Open Area | 100 | 0 |  | 2026-04-18 |  | 2026-04-25
9884 | T-16-11th Floor Flat Area | Not Ready | Door | 2026-05-27 | 2026-06-17 | Door | 100 | 0 |  | 2026-04-18 |  | 2026-05-09
10698 | T-20-2nd Floor Common Area | Not Ready | Door-Shaft | 2026-05-14 | 2026-05-27 | Door-Shaft | 100 | 0 |  | 2026-04-18 |  | 2026-05-01
10933 | T-20-11th Floor Common Area | Not Ready | Window-Open Area | 2026-05-22 | 2026-05-29 | Window-Open Area | 100 | 0 |  | 2026-04-18 |  | 2026-04-28
11297 | T-19-5th Floor Common Area | Not Ready | Window-Open Area | 2026-05-04 | 2026-05-12 | Window-Open Area | 100 | 0 |  | 2026-04-18 |  | 2026-04-25
11446 | T-19-11th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-05-07 | 2026-07-28 | 1st Coat Painting | 100 | 0 |  | 2026-04-18 |  | 2026-07-11
40081 | Tower A - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2026-03-27 | 2026-04-11 | Bulk head light fix + Electrical works + Earthing | 100 | 0 |  | 2026-04-18 |  | 2026-05-06 |  | Tower A | Super Structure
40081 | Tower A - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2026-03-27 | 2026-04-11 | Bulk head light fix + Electrical works + Earthing | 100 | 0 |  | 2026-04-18 |  | 2026-05-06 |  | Tower A | Super Structure
40081 | Tower A - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2026-03-27 | 2026-04-11 | Bulk head light fix + Electrical works + Earthing | 100 | 0 |  | 2026-04-18 |  | 2026-05-06 |  | Tower A | Super Structure
40468 | Tower A - Super Structure - Finishes & MEP - Above Terrace | Not Ready | Waterproofing | 2026-03-21 | 2026-04-24 | Waterproofing with approved MS | 100 | 0 |  | 2026-04-18 |  | 2026-05-25 |  | Tower A | Super Structure
41452 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-03-28 | 2026-04-01 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-04-18 |  | 2026-04-22 |  | Tower A | Super Structure | L31 | MEP | FPS 2nd Fix - MEP & Finishes
41453 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-03-28 | 2026-04-03 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-04-18 |  | 2026-04-24 |  | Tower A | Super Structure | L31 | MEP | Electrical 2nd Fix - MEP & Finishes
41454 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-28 | 2026-04-06 | FAPA Device Fixing | 100 | 0 |  | 2026-04-18 |  | 2026-04-27 |  | Tower A | Super Structure | L31
41454 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-28 | 2026-04-06 | FAPA Device Fixing | 100 | 0 |  | 2026-04-18 |  | 2026-04-27 |  | Tower A | Super Structure | L31
41454 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-28 | 2026-04-06 | FAPA Device Fixing | 100 | 0 |  | 2026-04-18 |  | 2026-04-27 |  | Tower A | Super Structure | L31
41454 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-28 | 2026-04-06 | FAPA Device Fixing | 100 | 0 |  | 2026-04-18 |  | 2026-04-27 |  | Tower A | Super Structure | L31
41455 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-03-28 | 2026-04-01 | HVAC Grill Fixing | 100 | 0 |  | 2026-04-18 |  | 2026-04-22 |  | Tower A | Super Structure | L31 | MEP | HVAC Grill Fixing
41515 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-03-28 | 2026-04-06 | False Ceiling | 100 | 0 |  | 2026-04-18 |  | 2026-04-27 |  | Tower A | Super Structure | L35 | Finishes | False Ceiling
41575 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-03-28 | 2026-04-06 | HVAC Ducting | 100 | 0 |  | 2026-04-18 |  | 2026-04-27 |  | Tower A | Super Structure | L39 | MEP | HVAC Ducting
43286 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-03-27 | 2026-04-07 | Cement Plastering in wet areas | 100 | 0 |  | 2026-04-18 |  | 2026-04-29 |  | Tower A | Super Structure | L67
43370 |  | Not Committed |  | 2026-03-27 | 2026-10-24 | L72-73 (Refuge) | 100 | 0 |  | 2026-04-18 |  | 2026-10-07
43371 |  | Not Committed |  | 2026-03-27 | 2026-04-24 | MEP 1st Fixes | 100 | 0 |  | 2026-04-18 |  | 2026-05-18
43372 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-03-27 | 2026-04-03 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-04-18 |  | 2026-04-25 |  | Tower A | Super Structure | L72 | MEP | FPS 1st Fix - MEP & Finishes
43373 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-03-27 | 2026-04-01 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-04-18 |  | 2026-04-23 |  | Tower A | Super Structure | L72 | MEP | Electrical 1st Fixes
43374 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-03-27 | 2026-04-03 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-04-18 |  | 2026-04-25 |  | Tower A | Super Structure | L72
43375 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-03-27 | 2026-04-13 | Wet Area Waterproofing | 100 | 0 |  | 2026-04-18 |  | 2026-05-06 |  | Tower A | Super Structure | L72
46714 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-02-12 | 2026-02-28 | Wet Area Waterproofing | 100 | 0 |  | 2026-04-18 |  | 2026-05-07 |  | Tower B | Super Structure | L10
8564 | T-14-1st Floor Common Area | Not Ready | Flooring & skirting | 2026-03-12 | 2026-04-04 | Flooring & skirting | 100 | 0 |  | 2026-04-19 |  | 2026-05-10
8591 | T-14-2nd Floor Common Area | Not Ready | Putty | 2026-03-12 | 2026-04-21 | Putty | 100 | 0 |  | 2026-04-19 |  | 2026-05-29
8800 | T-14-11th Floor Common Area | Not Ready | Door-Shaft | 2026-03-23 | 2026-04-06 | Door-Shaft | 100 | 0 |  | 2026-04-19 |  | 2026-05-03
9380 | T-15-Lift | Not Ready | PARAPET | 2026-05-05 | 2026-07-09 | Parapets | 100 | 0 |  | 2026-04-19 |  | 2026-06-26
9788 | T-16-7th Floor Common Area | Not Ready | Door-Shaft | 2026-05-07 | 2026-05-20 | Door-Shaft | 100 | 0 |  | 2026-04-19 |  | 2026-05-02
10094 | T-21-Basement Floor | Not Ready | 2nd Coat Painting | 2026-06-18 | 2026-09-03 | 2nd Coat Painting | 100 | 0 |  | 2026-04-19 |  | 2026-07-04
10726 | T-20-3rd Floor Common Area | Not Ready | 1st Coat Painting | 2026-05-13 | 2026-06-04 | 1st Coat Painting | 100 | 0 |  | 2026-04-19 |  | 2026-05-10
10875 | T-20-9th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-05-19 | 2026-07-23 | 2nd Coat Painting | 100 | 0 |  | 2026-04-19 |  | 2026-06-24
8750 | T-14-8th Floor Common Area | Not Ready | 1st Coat Painting | 2026-03-17 | 2026-04-08 | 1st Coat Painting | 100 | 0 |  | 2026-04-20 |  | 2026-05-12
8856 |  | Not Ready |  | 2026-04-18 | 2026-11-24 | TF | 100 | 0 |  | 2026-04-20 |  | 2026-11-25
8857 |  | Not Ready |  | 2026-04-18 | 2026-11-24 | Finishing Works | 100 | 0 |  | 2026-04-20 |  | 2026-11-25
11350 | T-19-7th Floor Common Area | Not Ready | 1st Coat Painting | 2026-05-06 | 2026-05-28 | 1st Coat Painting | 100 | 0 |  | 2026-04-20 |  | 2026-05-13
11456 |  | Not Ready |  | 2026-06-09 | 2027-01-14 | TF | 100 | 0 |  | 2026-04-20 |  | 2026-11-25
11457 |  | Not Ready |  | 2026-06-09 | 2027-01-14 | Finishing Works | 100 | 0 |  | 2026-04-20 |  | 2026-11-25
39261 | Retail - Sub structure - B2 to B1 | Not Ready | Retaining Wall RCC Works | 2025-11-07 | 2025-11-18 | Retaining Wall_lift 2 | 100 | 0 |  | 2026-04-20 |  | 2026-04-28 |  | Retail | Sub Structure | B2 | RCC Super Structure | Retaining Wall RCC Works
39261 | Retail - Sub structure - B2 to B1 | Not Ready | Retaining Wall RCC Works | 2025-11-07 | 2025-11-18 | Retaining Wall_lift 2 | 100 | 0 |  | 2026-04-20 |  | 2026-04-28 |  | Retail | Sub Structure | B2
40460 | Tower A - Super Structure - Finishes & MEP - L75 to L76 | Not Ready | Partition Wall-Blockwork | 2026-03-28 | 2026-04-02 | Staircase Area | 100 | 0 |  | 2026-04-20 |  | 2026-04-24 |  | Tower A | Super Structure | L75
41409 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-03-30 | 2026-04-04 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-04-20 |  | 2026-04-24 |  | Tower A | Super Structure | L28 | MEP | Electrical
41440 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-03-31 | 2026-04-02 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-04-20 |  | 2026-04-23 |  | Tower A | Super Structure | L30
41546 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-03-30 | 2026-04-10 | Flooring & Dado | 100 | 0 |  | 2026-04-20 |  | 2026-05-02 |  | Tower A | Super Structure | L37 | Finishes | Flooring & Dado
43250 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-03-28 | 2026-04-08 | Cement Plastering in wet areas | 100 | 0 |  | 2026-04-20 |  | 2026-04-30 |  | Tower A | Super Structure | L65
44592 |  | Not Ready | MEP fix & Finishes | 2026-04-22 | 2026-05-04 | Final Painting | 100 | 0 |  | 2026-04-20 |  | 2026-04-30 |  |  |  |  | Finishes | Final Painting
44592 |  | Not Ready | MEP fix & Finishes | 2026-04-22 | 2026-05-04 | Final Painting | 100 | 0 |  | 2026-04-20 |  | 2026-04-30 |  |  |  |  | Finishes | Final Painting
44592 |  | Not Ready | MEP fix & Finishes | 2026-04-22 | 2026-05-04 | Final Painting | 100 | 0 |  | 2026-04-20 |  | 2026-04-30 |  |  |  |  | Finishes | Final Painting
44597 |  | Not Ready | MEP fix & Finishes | 2026-04-22 | 2026-04-29 | HVAC Fans fixing | 100 | 0 |  | 2026-04-20 |  | 2026-04-27 |  |  |  |  | MEP | HVAC Grill Fixing
44597 |  | Not Ready | MEP fix & Finishes | 2026-04-22 | 2026-04-29 | HVAC Fans fixing | 100 | 0 |  | 2026-04-20 |  | 2026-04-27 |  |  |  |  | MEP | HVAC Grill Fixing
44608 |  | Not Ready | MEP fix & Finishes | 2026-04-22 | 2026-04-29 | FAPA Device Fixing | 100 | 0 |  | 2026-04-20 |  | 2026-04-27
44608 |  | Not Ready | MEP fix & Finishes | 2026-04-22 | 2026-04-29 | FAPA Device Fixing | 100 | 0 |  | 2026-04-20 |  | 2026-04-27
44608 |  | Not Ready | MEP fix & Finishes | 2026-04-22 | 2026-04-29 | FAPA Device Fixing | 100 | 0 |  | 2026-04-20 |  | 2026-04-27
44608 |  | Not Ready | MEP fix & Finishes | 2026-04-22 | 2026-04-29 | FAPA Device Fixing | 100 | 0 |  | 2026-04-20 |  | 2026-04-27
44612 |  | Not Committed |  | 2026-04-22 | 2026-06-04 | P2 to P3 | 100 | 0 |  | 2026-04-20 |  | 2026-06-02
44612 |  | Not Committed |  | 2026-04-22 | 2026-06-04 | P2 to P3 | 100 | 0 |  | 2026-04-20 |  | 2026-06-02
44612 |  | Not Committed |  | 2026-04-22 | 2026-06-04 | P2 to P3 | 100 | 0 |  | 2026-04-20 |  | 2026-06-02
44613 |  | Not Ready | MEP fix & Finishes | 2026-04-22 | 2026-04-29 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2026-04-20 |  | 2026-04-27 |  |  |  |  | MEP | FPS final fixes
44613 |  | Not Ready | MEP fix & Finishes | 2026-04-22 | 2026-04-29 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2026-04-20 |  | 2026-04-27 |  |  |  |  | MEP | FPS final fixes
45452 | Tower B - Super Structure - Finishes & MEP - L11 to L12 | Not Ready | Partition Wall-Blockwork | 2026-02-13 | 2026-02-18 | Staircase Area | 100 | 0 |  | 2026-04-20 |  | 2026-04-25 |  | Tower B | Super Structure | L11
45902 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-02-13 | 2026-02-24 | FAPA Cabling | 100 | 0 |  | 2026-04-20 |  | 2026-05-02 |  | Tower B | Super Structure
45958 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | VDF/ Grade Slab - MEP & Finishes | 2026-02-13 | 2026-04-07 | VDF/ Grade Slab & Apt. finishes | 100 | 0 |  | 2026-04-20 |  | 2026-06-13 |  | Tower B | Super Structure
9705 | T-16-4th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-05-23 | 2026-07-28 | 2nd Coat Painting | 100 | 0 |  | 2026-04-21 |  | 2026-06-26
9809 | T-16-8th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-05-23 | 2026-07-28 | 2nd Coat Painting | 100 | 0 |  | 2026-04-21 |  | 2026-06-26
10180 | T-21-2nd Floor Common Area | Not Ready | 1st Coat Painting | 2026-05-24 | 2026-06-15 | 1st Coat Painting | 100 | 0 |  | 2026-04-21 |  | 2026-05-13
40542 | Tower A - Super Structure - Finishes & MEP - L68 to L69 | Not Ready | Gypsum Plastering Works | 2026-03-30 | 2026-04-15 | L68-69 | 100 | 0 |  | 2026-04-21 |  | 2026-05-08 |  | Tower A | Super Structure | L68 | Finishes | Gypsum Plastering Works
40542 | Tower A - Super Structure - Finishes & MEP - L68 to L69 | Not Ready | Gypsum Plastering Works | 2026-03-30 | 2026-04-15 | L68-69 | 100 | 0 |  | 2026-04-21 |  | 2026-05-08 |  | Tower A | Super Structure | L68
41378 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-01 | 2026-04-06 | Final Painting | 100 | 0 |  | 2026-04-21 |  | 2026-04-27 |  | Tower A | Super Structure | L26 | Finishes | Final Painting
41378 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-01 | 2026-04-06 | Final Painting | 100 | 0 |  | 2026-04-21 |  | 2026-04-27 |  | Tower A | Super Structure | L26 | Finishes | Final Painting
41378 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-01 | 2026-04-06 | Final Painting | 100 | 0 |  | 2026-04-21 |  | 2026-04-27 |  | Tower A | Super Structure | L26 | Finishes | Final Painting
41425 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-04-01 | 2026-04-07 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-04-21 |  | 2026-04-27 |  | Tower A | Super Structure | L29 | MEP | Electrical
41468 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-03-31 | 2026-04-03 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-04-21 |  | 2026-04-23 |  | Tower A | Super Structure | L32 | MEP | FPS 2nd Fix - MEP & Finishes
41469 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-03-31 | 2026-04-06 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-04-21 |  | 2026-04-25 |  | Tower A | Super Structure | L32 | MEP | Electrical 2nd Fix - MEP & Finishes
41470 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-31 | 2026-04-08 | FAPA Device Fixing | 100 | 0 |  | 2026-04-21 |  | 2026-04-28 |  | Tower A | Super Structure | L32
41470 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-31 | 2026-04-08 | FAPA Device Fixing | 100 | 0 |  | 2026-04-21 |  | 2026-04-28 |  | Tower A | Super Structure | L32
41470 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-31 | 2026-04-08 | FAPA Device Fixing | 100 | 0 |  | 2026-04-21 |  | 2026-04-28 |  | Tower A | Super Structure | L32
41470 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-31 | 2026-04-08 | FAPA Device Fixing | 100 | 0 |  | 2026-04-21 |  | 2026-04-28 |  | Tower A | Super Structure | L32
41471 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-03-31 | 2026-04-03 | HVAC Grill Fixing | 100 | 0 |  | 2026-04-21 |  | 2026-04-23 |  | Tower A | Super Structure | L32 | MEP | HVAC Grill Fixing
43200 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-05-13 | 2026-05-30 | Flooring & Dado works | 100 | 0 |  | 2026-04-21 |  | 2026-05-08 |  | Tower A | Super Structure | L62 | Finishes | Flooring & Dado
43388 |  | Not Committed |  | 2026-03-30 | 2026-10-30 | L73-74 | 100 | 0 |  | 2026-04-21 |  | 2026-10-13
43388 |  | Not Committed |  | 2026-03-30 | 2026-10-30 | L73-74 | 100 | 0 |  | 2026-04-21 |  | 2026-10-13 |  |  |  |  | Finishes | Gypsum Plastering Works
43389 |  | Not Committed |  | 2026-03-30 | 2026-04-27 | MEP 1st Fixes | 100 | 0 |  | 2026-04-21 |  | 2026-05-20
43390 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-03-30 | 2026-04-06 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-04-21 |  | 2026-04-28 |  | Tower A | Super Structure | L73 | MEP | FPS 1st Fix - MEP & Finishes
43391 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-03-30 | 2026-04-03 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-04-21 |  | 2026-04-25 |  | Tower A | Super Structure | L73 | MEP | Electrical 1st Fixes
43392 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-03-30 | 2026-04-06 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-04-21 |  | 2026-04-28 |  | Tower A | Super Structure | L73
43393 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-03-30 | 2026-04-15 | Wet Area Waterproofing | 100 | 0 |  | 2026-04-21 |  | 2026-05-08 |  | Tower A | Super Structure | L73
43984 | Tower A - Super Structure - Finishes & MEP - L25 to L35 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-05-22 | 2026-06-26 | Staircase Window | 100 | 0 |  | 2026-04-21 |  | 2026-05-28 |  | Tower A | Super Structure | L25
46697 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-02-14 | 2026-02-25 | Cement Plastering in wet areas | 100 | 0 |  | 2026-04-21 |  | 2026-05-04 |  | Tower B | Super Structure | L9
8909 |  | Not Ready |  | 2026-04-21 | 2026-10-15 | External Finishes | 100 | 0 |  | 2026-04-22 |  | 2026-10-16
8910 |  | Not Ready |  | 2026-04-21 | 2026-10-15 | External Painting | 100 | 0 |  | 2026-04-22 |  | 2026-10-16
9321 | T-15-9th Floor Common Area | Not Ready | Window-Open Area | 2026-04-24 | 2026-05-03 | Window-Open Area | 100 | 0 |  | 2026-04-22 |  | 2026-04-29
10233 | T-21-4th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-05-24 | 2026-06-25 | 2nd Coat Painting | 100 | 0 |  | 2026-04-22 |  | 2026-05-26
10446 | T-21-Staircase 1 | Not Ready |  | 2026-05-20 | 2026-05-30 | 07F-06F | 100 | 0 |  | 2026-04-22 |  | 2026-05-03
10460 | T-21-Staircase 2 | Not Ready |  | 2026-05-20 | 2026-05-30 | 08F-07F | 100 | 0 |  | 2026-04-22 |  | 2026-05-03
40095 | Tower A - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2026-03-25 | 2026-04-28 | Pipe & Support Fabrication | 100 | 0 |  | 2026-04-22 |  | 2026-05-29 |  | Tower A | Super Structure
40316 | Tower A - Super Structure - Finishes & MEP - L76 to L77 | Not Ready | Partition Wall-Blockwork | 2026-03-31 | 2026-04-04 | Staircase Area | 100 | 0 |  | 2026-04-22 |  | 2026-04-27 |  | Tower A | Super Structure | L76
40323 | Tower A - Super Structure - Finishes & MEP - L77 to L78 | Not Ready | Partition Wall-Blockwork | 2026-03-25 | 2026-04-01 | Partition Walls | 100 | 0 |  | 2026-04-22 |  | 2026-04-30 |  | Tower A | Super Structure | L77
41456 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-04-01 | 2026-04-04 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-04-22 |  | 2026-04-25 |  | Tower A | Super Structure | L31
41484 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-04-02 | 2026-04-06 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-04-22 |  | 2026-04-25 |  | Tower A | Super Structure | L33 | MEP | FPS 2nd Fix - MEP & Finishes
41485 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-04-02 | 2026-04-08 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-04-22 |  | 2026-04-28 |  | Tower A | Super Structure | L33 | MEP | Electrical 2nd Fix - MEP & Finishes
41486 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-02 | 2026-04-10 | FAPA Device Fixing | 100 | 0 |  | 2026-04-22 |  | 2026-04-30 |  | Tower A | Super Structure | L33
41486 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-02 | 2026-04-10 | FAPA Device Fixing | 100 | 0 |  | 2026-04-22 |  | 2026-04-30 |  | Tower A | Super Structure | L33
41486 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-02 | 2026-04-10 | FAPA Device Fixing | 100 | 0 |  | 2026-04-22 |  | 2026-04-30 |  | Tower A | Super Structure | L33
41486 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-02 | 2026-04-10 | FAPA Device Fixing | 100 | 0 |  | 2026-04-22 |  | 2026-04-30 |  | Tower A | Super Structure | L33
41487 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-04-02 | 2026-04-06 | HVAC Grill Fixing | 100 | 0 |  | 2026-04-22 |  | 2026-04-25 |  | Tower A | Super Structure | L33 | MEP | HVAC Grill Fixing
41531 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-04-01 | 2026-04-09 | False Ceiling | 100 | 0 |  | 2026-04-22 |  | 2026-04-30 |  | Tower A | Super Structure | L36 | Finishes | False Ceiling
41591 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-04-01 | 2026-04-09 | HVAC Ducting | 100 | 0 |  | 2026-04-22 |  | 2026-04-30 |  | Tower A | Super Structure | L40 | MEP | HVAC Ducting
43269 |  | Not Committed |  | 2026-03-31 | 2026-07-17 | Finishes after 1st Fix | 100 | 0 |  | 2026-04-22 |  | 2026-08-13
43270 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-03-31 | 2026-04-22 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-04-22 |  | 2026-05-15 |  | Tower A | Super Structure | L66 | Finishes | Blockwork
45613 | Tower B - Super Structure - Finishes & MEP - L10 to L11 | Not Ready | Gypsum Plastering Works | 2026-02-16 | 2026-04-03 | L10-11 | 100 | 0 |  | 2026-04-22 |  | 2026-06-10 |  | Tower B | Super Structure | L10 | Finishes | Gypsum Plastering Works
45613 | Tower B - Super Structure - Finishes & MEP - L10 to L11 | Not Ready | Gypsum Plastering Works | 2026-02-16 | 2026-04-03 | L10-11 | 100 | 0 |  | 2026-04-22 |  | 2026-06-10 |  | Tower B | Super Structure | L10
9346 | T-15-11th Floor Common Area | Not Ready | Door-Shaft | 2026-04-28 | 2026-05-12 | Door-Shaft | 100 | 0 |  | 2026-04-23 |  | 2026-05-07
9378 | T-15-Lift | Not Ready | LMR ROOM | 2026-05-07 | 2026-07-11 | Lift Machine Rooms | 100 | 0 |  | 2026-04-23 |  | 2026-06-29
9403 | T-15-Staircase 1 | Not Ready |  | 2026-05-05 | 2026-05-15 | 10F-09F | 100 | 0 |  | 2026-04-23 |  | 2026-05-05
9417 | T-15-Staircase 2 | Not Ready |  | 2026-05-05 | 2026-05-15 | 11F-10F | 100 | 0 |  | 2026-04-23 |  | 2026-05-05
9679 | T-16-3rd Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-05-26 | 2026-07-30 | 2nd Coat Painting | 100 | 0 |  | 2026-04-23 |  | 2026-06-27
9865 | T-16-11th Floor Common Area | Not Ready | Putty | 2026-05-18 | 2026-06-25 | Putty | 100 | 0 |  | 2026-04-23 |  | 2026-06-01
11764 | T-18-3rd Floor Common Area | Not Ready | Door-Shaft | 2026-06-30 | 2026-07-14 | Door-Shaft | 100 | 0 |  | 2026-04-23 |  | 2026-05-08
40543 | Tower A - Super Structure - Finishes & MEP - L69 to L70 | Not Ready | Gypsum Plastering Works | 2026-04-01 | 2026-04-17 | L69-70 | 100 | 0 |  | 2026-04-23 |  | 2026-05-11 |  | Tower A | Super Structure | L69 | Finishes | Gypsum Plastering Works
40543 | Tower A - Super Structure - Finishes & MEP - L69 to L70 | Not Ready | Gypsum Plastering Works | 2026-04-01 | 2026-04-17 | L69-70 | 100 | 0 |  | 2026-04-23 |  | 2026-05-11 |  | Tower A | Super Structure | L69
41394 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-02 | 2026-04-08 | Final Painting | 100 | 0 |  | 2026-04-23 |  | 2026-04-29 |  | Tower A | Super Structure | L27 | Finishes | Final Painting
41394 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-02 | 2026-04-08 | Final Painting | 100 | 0 |  | 2026-04-23 |  | 2026-04-29 |  | Tower A | Super Structure | L27 | Finishes | Final Painting
41394 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-02 | 2026-04-08 | Final Painting | 100 | 0 |  | 2026-04-23 |  | 2026-04-29 |  | Tower A | Super Structure | L27 | Finishes | Final Painting
41441 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-04-03 | 2026-04-08 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-04-23 |  | 2026-04-29 |  | Tower A | Super Structure | L30 | MEP | Electrical
41562 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-04-02 | 2026-04-14 | Flooring & Dado | 100 | 0 |  | 2026-04-23 |  | 2026-05-06 |  | Tower A | Super Structure | L38 | Finishes | Flooring & Dado
43233 |  | Not Committed |  | 2026-04-01 | 2026-06-17 | Finishes after 1st Fix | 100 | 0 |  | 2026-04-23 |  | 2026-07-09
43234 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-04-01 | 2026-04-23 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-04-23 |  | 2026-05-16 |  | Tower A | Super Structure | L64 | Finishes | Blockwork
43406 |  | Not Committed |  | 2026-04-01 | 2026-10-30 | L74-75 | 100 | 0 |  | 2026-04-23 |  | 2026-10-13
43406 |  | Not Committed |  | 2026-04-01 | 2026-10-30 | L74-75 | 100 | 0 |  | 2026-04-23 |  | 2026-10-13 |  |  |  |  | Finishes | Gypsum Plastering Works
43407 |  | Not Committed |  | 2026-04-01 | 2026-04-20 | MEP 1st Fixes | 100 | 0 |  | 2026-04-23 |  | 2026-05-13
43408 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-04-01 | 2026-04-08 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-04-23 |  | 2026-04-30 |  | Tower A | Super Structure | L74 | MEP | FPS 1st Fix - MEP & Finishes
43409 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-04-01 | 2026-04-06 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-04-23 |  | 2026-04-28 |  | Tower A | Super Structure | L74 | MEP | Electrical 1st Fixes
43410 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-04-01 | 2026-04-08 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-04-23 |  | 2026-04-30 |  | Tower A | Super Structure | L74
43411 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-04-01 | 2026-04-17 | Wet Area Waterproofing | 100 | 0 |  | 2026-04-23 |  | 2026-05-11 |  | Tower A | Super Structure | L74
44132 |  | Not Ready |  | 2026-05-25 | 2026-06-29 | L73-78 | 100 | 0 |  | 2026-04-23 |  | 2026-05-30
44133 | Tower A - Super Structure - Finishes & MEP - L73 to L78 | Not Ready | Façade Works - MEP & Finishes | 2026-05-25 | 2026-06-05 | Al. Frame section (Mullion & Transom) Installation | 100 | 0 |  | 2026-04-23 |  | 2026-05-06 |  | Tower A | Super Structure | L73 | Façade | Façade Works
44587 |  | Not Ready | MEP fix & Finishes | 2026-04-25 | 2026-04-30 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-04-23 |  | 2026-04-28
44587 |  | Not Ready | MEP fix & Finishes | 2026-04-25 | 2026-04-30 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-04-23 |  | 2026-04-28
44587 |  | Not Ready | MEP fix & Finishes | 2026-04-25 | 2026-04-30 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-04-23 |  | 2026-04-28
9736 | T-16-5th Floor Common Area | Not Ready | Door-Shaft | 2026-05-13 | 2026-05-26 | Door-Shaft | 100 | 0 |  | 2026-04-24 |  | 2026-05-08
11480 | T-19-Staircase 1 | Not Ready |  | 2026-05-07 | 2026-05-18 | TF-12F | 100 | 0 |  | 2026-04-24 |  | 2026-05-04
11792 | T-18-4th Floor Common Area | Not Ready | 1st Coat Painting | 2026-06-29 | 2026-07-21 | 1st Coat Painting | 100 | 0 |  | 2026-04-24 |  | 2026-05-19
11922 | T-18-9th Floor Common Area | Not Ready | 1st Coat Painting | 2026-07-04 | 2026-07-27 | 1st Coat Painting | 100 | 0 |  | 2026-04-24 |  | 2026-05-16
12003 | T-18-Staircase 1 | Not Ready |  | 2026-07-06 | 2026-07-17 | 10F-09F | 100 | 0 |  | 2026-04-24 |  | 2026-05-04
12017 | T-18-Staircase 2 | Not Ready |  | 2026-07-06 | 2026-07-17 | 11F-10F | 100 | 0 |  | 2026-04-24 |  | 2026-05-04
41472 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-04-03 | 2026-04-07 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-04-24 |  | 2026-04-27 |  | Tower A | Super Structure | L32
41500 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-04-04 | 2026-04-07 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-04-24 |  | 2026-04-28 |  | Tower A | Super Structure | L34 | MEP | FPS 2nd Fix - MEP & Finishes
41501 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-04-04 | 2026-04-09 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-04-24 |  | 2026-04-30 |  | Tower A | Super Structure | L34 | MEP | Electrical 2nd Fix - MEP & Finishes
41502 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-04 | 2026-04-11 | FAPA Device Fixing | 100 | 0 |  | 2026-04-24 |  | 2026-05-04 |  | Tower A | Super Structure | L34
41502 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-04 | 2026-04-11 | FAPA Device Fixing | 100 | 0 |  | 2026-04-24 |  | 2026-05-04 |  | Tower A | Super Structure | L34
41502 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-04 | 2026-04-11 | FAPA Device Fixing | 100 | 0 |  | 2026-04-24 |  | 2026-05-04 |  | Tower A | Super Structure | L34
41502 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-04 | 2026-04-11 | FAPA Device Fixing | 100 | 0 |  | 2026-04-24 |  | 2026-05-04 |  | Tower A | Super Structure | L34
41503 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-04-04 | 2026-04-07 | HVAC Grill Fixing | 100 | 0 |  | 2026-04-24 |  | 2026-04-28 |  | Tower A | Super Structure | L34 | MEP | HVAC Grill Fixing
45298 |  | Not Ready |  | 2026-02-18 | 2026-02-28 | L16-17 | 100 | 0 |  | 2026-04-24 |  | 2026-05-11
45298 |  | Not Ready |  | 2026-02-18 | 2026-02-28 | L16-17 | 100 | 0 |  | 2026-04-24 |  | 2026-05-11 |  |  |  |  | Finishes | Gypsum Plastering Works
45299 | Tower B - Super Structure - Core & Outer Slab L16-17 | Not Ready | RCC Works - Vertical | 2026-02-18 | 2026-02-26 | Outer Columns_TA | 100 | 0 |  | 2026-04-24 |  | 2026-05-07 |  | Tower B | Super Structure | L16 | RCC Sub Structure | RCC Works - Vertical
45457 |  | Not Committed |  | 2026-02-18 | 2026-03-21 | L13-14 | 100 | 0 |  | 2026-04-24 |  | 2026-05-28
45457 |  | Not Committed |  | 2026-02-18 | 2026-03-21 | L13-14 | 100 | 0 |  | 2026-04-24 |  | 2026-05-28 |  |  |  |  | Finishes | Gypsum Plastering Works
45458 | Tower B - Super Structure - Finishes & MEP - L13 to L14 | Not Ready | Partition Wall-Blockwork | 2026-02-18 | 2026-03-07 | De-shuttering & Area clearance | 100 | 0 |  | 2026-04-24 |  | 2026-05-13 |  | Tower B | Super Structure | L13
8645 | T-14-4th Floor Common Area | Not Ready | Window-Open Area | 2026-03-20 | 2026-03-28 | Window-Open Area | 100 | 0 |  | 2026-04-25 |  | 2026-05-02
9271 | T-15-7th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-04-27 | 2026-05-30 | 2nd Coat Painting | 100 | 0 |  | 2026-04-25 |  | 2026-05-29
9379 | T-15-Lift | Not Ready | STAIRCASE HR | 2026-05-11 | 2026-07-15 | Staircase Headrooms | 100 | 0 |  | 2026-04-25 |  | 2026-06-29
10152 | T-21-1st Floor Common Area | Not Ready | Door-Shaft | 2026-05-25 | 2026-06-07 | Door-Shaft | 100 | 0 |  | 2026-04-25 |  | 2026-05-09
10965 | T-20-Staircase 1 | Not Ready |  | 2026-05-20 | 2026-05-30 | 08F-07F | 100 | 0 |  | 2026-04-25 |  | 2026-05-05
10979 | T-20-Staircase 2 | Not Ready |  | 2026-05-20 | 2026-05-30 | 09F-08F | 100 | 0 |  | 2026-04-25 |  | 2026-05-05
11707 | T-18-1st Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-07-24 | 2026-09-29 | 2nd Coat Painting | 100 | 0 |  | 2026-04-25 |  | 2026-07-01
40544 | Tower A - Super Structure - Finishes & MEP - L70 to L71 | Not Ready | Gypsum Plastering Works | 2026-04-03 | 2026-04-20 | L70-71 | 100 | 0 |  | 2026-04-25 |  | 2026-05-13 |  | Tower A | Super Structure | L70 | Finishes | Gypsum Plastering Works
40544 | Tower A - Super Structure - Finishes & MEP - L70 to L71 | Not Ready | Gypsum Plastering Works | 2026-04-03 | 2026-04-20 | L70-71 | 100 | 0 |  | 2026-04-25 |  | 2026-05-13 |  | Tower A | Super Structure | L70
41410 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-04 | 2026-04-10 | Final Painting | 100 | 0 |  | 2026-04-25 |  | 2026-04-30 |  | Tower A | Super Structure | L28 | Finishes | Final Painting
41410 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-04 | 2026-04-10 | Final Painting | 100 | 0 |  | 2026-04-25 |  | 2026-04-30 |  | Tower A | Super Structure | L28 | Finishes | Final Painting
41410 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-04 | 2026-04-10 | Final Painting | 100 | 0 |  | 2026-04-25 |  | 2026-04-30 |  | Tower A | Super Structure | L28 | Finishes | Final Painting
41457 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-04-04 | 2026-04-10 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-04-25 |  | 2026-05-02 |  | Tower A | Super Structure | L31 | MEP | Electrical
41488 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-04-06 | 2026-04-09 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-04-25 |  | 2026-04-29 |  | Tower A | Super Structure | L33
41547 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-04-04 | 2026-04-13 | False Ceiling | 100 | 0 |  | 2026-04-25 |  | 2026-05-05 |  | Tower A | Super Structure | L37 | Finishes | False Ceiling
41607 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-04-04 | 2026-04-13 | HVAC Ducting | 100 | 0 |  | 2026-04-25 |  | 2026-05-05 |  | Tower A | Super Structure | L41 | MEP | HVAC Ducting
42164 |  | Not Committed |  | 2026-04-03 | 2026-10-30 | L75-76 | 100 | 0 |  | 2026-04-25 |  | 2026-10-13
42164 |  | Not Committed |  | 2026-04-03 | 2026-10-30 | L75-76 | 100 | 0 |  | 2026-04-25 |  | 2026-10-13 |  |  |  |  | Finishes | Gypsum Plastering Works
42165 |  | Not Committed |  | 2026-04-03 | 2026-04-22 | MEP 1st Fixes | 100 | 0 |  | 2026-04-25 |  | 2026-05-15
42166 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-04-03 | 2026-04-10 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-04-25 |  | 2026-05-04 |  | Tower A | Super Structure | L75 | MEP | FPS 1st Fix - MEP & Finishes
42167 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-04-03 | 2026-04-08 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-04-25 |  | 2026-04-30 |  | Tower A | Super Structure | L75 | MEP | Electrical 1st Fixes
42168 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-04-03 | 2026-04-10 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-04-25 |  | 2026-05-04 |  | Tower A | Super Structure | L75
42169 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-04-03 | 2026-04-20 | Wet Area Waterproofing | 100 | 0 |  | 2026-04-25 |  | 2026-05-13 |  | Tower A | Super Structure | L75
45931 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | VDF/ Grade Slab - MEP & Finishes | 2026-02-19 | 2026-02-24 | VDF/ Grade Slab | 100 | 0 |  | 2026-04-25 |  | 2026-05-02 |  | Tower B | Super Structure
46043 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2026-02-19 | 2026-02-19 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-04-25 |  | 2026-04-27 |  | Tower B | Super Structure
46043 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2026-02-19 | 2026-02-19 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-04-25 |  | 2026-04-27 |  | Tower B | Super Structure
46043 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2026-02-19 | 2026-02-19 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-04-25 |  | 2026-04-27 |  | Tower B | Super Structure
46727 |  | Not Committed |  | 2026-02-19 | 2027-03-23 | L11-12 | 100 | 0 |  | 2026-04-25 |  | 2027-05-21
46727 |  | Not Committed |  | 2026-02-19 | 2027-03-23 | L11-12 | 100 | 0 |  | 2026-04-25 |  | 2027-05-21 |  |  |  |  | Finishes | Gypsum Plastering Works
46728 |  | Not Committed |  | 2026-02-19 | 2026-03-28 | MEP 1st Fixes | 100 | 0 |  | 2026-04-25 |  | 2026-06-04
46729 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-02-19 | 2026-02-26 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-04-25 |  | 2026-05-05 |  | Tower B | Super Structure | L11 | MEP | FPS 1st Fix - MEP & Finishes
46730 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-02-19 | 2026-02-24 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-04-25 |  | 2026-05-02 |  | Tower B | Super Structure | L11 | MEP | Electrical 1st Fixes
46731 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-02-19 | 2026-02-26 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-04-25 |  | 2026-05-05 |  | Tower B | Super Structure | L11
47646 |  | Complete |  | 2026-04-25 | 2026-05-25 | Pour 7 (grid PB-K to PB-N) | 100 | 100 |  | 2026-04-25 | 2026-04-25 | 2026-05-25 | 2026-05-25
47647 |  | Complete |  | 2026-04-25 | 2026-05-13 | Columns/ Walls_NTA | 100 | 100 |  | 2026-04-25 | 2026-04-25 | 2026-05-13 | 2026-05-13
47647 |  | Complete |  | 2026-04-25 | 2026-05-13 | Columns/ Walls_NTA | 100 | 100 |  | 2026-04-25 | 2026-04-25 | 2026-05-13 | 2026-05-13 |  |  |  | RCC Sub Structure | RCC Works - Vertical
9764 | T-16-6th Floor Common Area | Not Ready | 1st Coat Painting | 2026-05-12 | 2026-06-02 | 1st Coat Painting | 100 | 0 |  | 2026-04-26 |  | 2026-05-20
11270 | T-19-4th Floor Common Area | Not Ready | Door-Shaft | 2026-05-13 | 2026-05-26 | Door-Shaft | 100 | 0 |  | 2026-04-26 |  | 2026-05-10
11298 | T-19-5th Floor Common Area | Not Ready | 1st Coat Painting | 2026-05-12 | 2026-06-03 | 1st Coat Painting | 100 | 0 |  | 2026-04-26 |  | 2026-05-17
11375 | T-19-8th Floor Common Area | Not Ready | Window-Open Area | 2026-05-15 | 2026-05-22 | Window-Open Area | 100 | 0 |  | 2026-04-26 |  | 2026-05-03
9191 | T-15-4th Floor Common Area | Not Ready | Window-Open Area | 2026-04-19 | 2026-04-27 | Window-Open Area | 100 | 0 |  | 2026-04-27 |  | 2026-05-05
11325 | T-19-6th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-05-12 | 2026-06-13 | 2nd Coat Painting | 100 | 0 |  | 2026-04-27 |  | 2026-05-29
11400 | T-19-9th Floor Common Area | Not Ready | Door-Shaft | 2026-05-19 | 2026-06-01 | Door-Shaft | 100 | 0 |  | 2026-04-27 |  | 2026-05-10
40116 | Tower A - Super Structure - Finishes & MEP - Sub Station | Not Ready | Sub Station - High Side Services | 2026-04-29 | 2026-05-22 | MS Shutter Fixing & FRD Door Fixing | 100 | 0 |  | 2026-04-27 |  | 2026-05-20 |  | Tower A | Super Structure
41426 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-07 | 2026-04-13 | Final Painting | 100 | 0 |  | 2026-04-27 |  | 2026-05-04 |  | Tower A | Super Structure | L29 | Finishes | Final Painting
41426 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-07 | 2026-04-13 | Final Painting | 100 | 0 |  | 2026-04-27 |  | 2026-05-04 |  | Tower A | Super Structure | L29 | Finishes | Final Painting
41426 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-07 | 2026-04-13 | Final Painting | 100 | 0 |  | 2026-04-27 |  | 2026-05-04 |  | Tower A | Super Structure | L29 | Finishes | Final Painting
41516 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-04-06 | 2026-04-09 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-04-27 |  | 2026-04-30 |  | Tower A | Super Structure | L35 | MEP | FPS 2nd Fix - MEP & Finishes
41517 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-04-06 | 2026-04-11 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-04-27 |  | 2026-05-04 |  | Tower A | Super Structure | L35 | MEP | Electrical 2nd Fix - MEP & Finishes
41518 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-06 | 2026-04-14 | FAPA Device Fixing | 100 | 0 |  | 2026-04-27 |  | 2026-05-06 |  | Tower A | Super Structure | L35
41518 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-06 | 2026-04-14 | FAPA Device Fixing | 100 | 0 |  | 2026-04-27 |  | 2026-05-06 |  | Tower A | Super Structure | L35
41518 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-06 | 2026-04-14 | FAPA Device Fixing | 100 | 0 |  | 2026-04-27 |  | 2026-05-06 |  | Tower A | Super Structure | L35
41518 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-06 | 2026-04-14 | FAPA Device Fixing | 100 | 0 |  | 2026-04-27 |  | 2026-05-06 |  | Tower A | Super Structure | L35
41519 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-04-06 | 2026-04-09 | HVAC Grill Fixing | 100 | 0 |  | 2026-04-27 |  | 2026-04-30 |  | Tower A | Super Structure | L35 | MEP | HVAC Grill Fixing
41578 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-04-06 | 2026-04-17 | Flooring & Dado | 100 | 0 |  | 2026-04-27 |  | 2026-05-09 |  | Tower A | Super Structure | L39 | Finishes | Flooring & Dado
43218 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-05-19 | 2026-06-05 | Flooring & Dado works | 100 | 0 |  | 2026-04-27 |  | 2026-05-14 |  | Tower A | Super Structure | L63 | Finishes | Flooring & Dado
43304 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-04-04 | 2026-04-15 | Cement Plastering in wet areas | 100 | 0 |  | 2026-04-27 |  | 2026-05-08 |  | Tower A | Super Structure | L68
43966 | Tower A - Super Structure - Finishes & MEP - GF to L7 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-05-29 | 2026-06-15 | Staircase Light Fixtures & Devices fixing | 100 | 0 |  | 2026-04-27 |  | 2026-05-15 |  | Tower A | Super Structure | GF
43978 | Tower A - Super Structure - Finishes & MEP - L15 to L25 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-05-29 | 2026-06-20 | Staircase Railing | 100 | 0 |  | 2026-04-27 |  | 2026-05-21 |  | Tower A | Super Structure | L15
43988 |  | Not Committed |  | 2026-05-29 | 2026-08-12 | L35-45 | 100 | 0 |  | 2026-04-27 |  | 2026-07-08
43988 |  | Not Committed |  | 2026-05-29 | 2026-08-12 | L35-45 | 100 | 0 |  | 2026-04-27 |  | 2026-07-08
43989 | Tower A - Super Structure - Finishes & MEP - L35 to L45 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-05-29 | 2026-07-02 | Staircase Wall & Ceiling finishes | 100 | 0 |  | 2026-04-27 |  | 2026-06-03 |  | Tower A | Super Structure | L35
43990 | Tower A - Super Structure - Finishes & MEP - L35 to L45 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-05-29 | 2026-07-22 | Staircase Flooring | 100 | 0 |  | 2026-04-27 |  | 2026-06-20 |  | Tower A | Super Structure | L35 | Finishes | Staircase Flooring
45455 | Tower B - Super Structure - Finishes & MEP - L12 to L13 | Not Ready | Partition Wall-Blockwork | 2026-02-20 | 2026-02-27 | Partition Walls | 100 | 0 |  | 2026-04-27 |  | 2026-05-06 |  | Tower B | Super Structure | L12
8725 | T-14-7th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-03-28 | 2026-04-30 | 2nd Coat Painting | 100 | 0 |  | 2026-04-28 |  | 2026-06-01
8775 | T-14-9th Floor Common Area | Not Ready | Window-Open Area | 2026-03-26 | 2026-04-03 | Window-Open Area | 100 | 0 |  | 2026-04-28 |  | 2026-05-05
9376 |  | Not Ready |  | 2026-05-05 | 2026-12-09 | TF | 100 | 0 |  | 2026-04-28 |  | 2026-12-04
9377 |  | Not Ready |  | 2026-05-05 | 2026-12-09 | Finishing Works | 100 | 0 |  | 2026-04-28 |  | 2026-12-04
10389 | T-21-11th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-06-09 | 2026-07-12 | 2nd Coat Painting | 100 | 0 |  | 2026-04-28 |  | 2026-05-31
10407 | T-21-11th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-06-09 | 2026-08-13 | 2nd Coat Painting | 100 | 0 |  | 2026-04-28 |  | 2026-07-03
10429 | T-21-Lift Lobby | Not Ready |  | 2026-05-30 | 2026-06-16 | 08F | 100 | 0 |  | 2026-04-28 |  | 2026-05-17
10948 | T-20-Lift Lobby | Not Ready |  | 2026-05-26 | 2026-06-11 | 09F | 100 | 0 |  | 2026-04-28 |  | 2026-05-15
11213 | T-19-2nd Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-06-01 | 2026-08-22 | 2nd Coat Painting | 100 | 0 |  | 2026-04-28 |  | 2026-07-20
40545 | Tower A - Super Structure - Finishes & MEP - L71 to L72 | Not Ready | Gypsum Plastering Works | 2026-04-06 | 2026-04-22 | L71-72 | 100 | 0 |  | 2026-04-28 |  | 2026-05-15 |  | Tower A | Super Structure | L71 | Finishes | Gypsum Plastering Works
40545 | Tower A - Super Structure - Finishes & MEP - L71 to L72 | Not Ready | Gypsum Plastering Works | 2026-04-06 | 2026-04-22 | L71-72 | 100 | 0 |  | 2026-04-28 |  | 2026-05-15 |  | Tower A | Super Structure | L71
41473 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-04-07 | 2026-04-13 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-04-28 |  | 2026-05-04 |  | Tower A | Super Structure | L32 | MEP | Electrical
41504 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-04-08 | 2026-04-10 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-04-28 |  | 2026-05-02 |  | Tower A | Super Structure | L34
42182 |  | Not Committed |  | 2026-04-06 | 2026-10-30 | L76-77 | 100 | 0 |  | 2026-04-28 |  | 2026-10-13
42182 |  | Not Committed |  | 2026-04-06 | 2026-10-30 | L76-77 | 100 | 0 |  | 2026-04-28 |  | 2026-10-13 |  |  |  |  | Finishes | Gypsum Plastering Works
42183 |  | Not Committed |  | 2026-04-06 | 2026-05-05 | MEP 1st Fixes | 100 | 0 |  | 2026-04-28 |  | 2026-05-28
42184 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-04-06 | 2026-04-13 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-04-28 |  | 2026-05-06 |  | Tower A | Super Structure | L76 | MEP | FPS 1st Fix - MEP & Finishes
42185 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-04-06 | 2026-04-10 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-04-28 |  | 2026-05-04 |  | Tower A | Super Structure | L76 | MEP | Electrical 1st Fixes
42186 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-04-06 | 2026-04-13 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-04-28 |  | 2026-05-06 |  | Tower A | Super Structure | L76
42187 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-04-06 | 2026-04-22 | Wet Area Waterproofing | 100 | 0 |  | 2026-04-28 |  | 2026-05-15 |  | Tower A | Super Structure | L76
44598 |  | Not Ready | MEP fix & Finishes | 2026-04-30 | 2026-05-12 | Final Painting | 100 | 0 |  | 2026-04-28 |  | 2026-05-09 |  |  |  |  | Finishes | Final Painting
44598 |  | Not Ready | MEP fix & Finishes | 2026-04-30 | 2026-05-12 | Final Painting | 100 | 0 |  | 2026-04-28 |  | 2026-05-09 |  |  |  |  | Finishes | Final Painting
44598 |  | Not Ready | MEP fix & Finishes | 2026-04-30 | 2026-05-12 | Final Painting | 100 | 0 |  | 2026-04-28 |  | 2026-05-09 |  |  |  |  | Finishes | Final Painting
44609 |  | Not Ready | MEP fix & Finishes | 2026-04-30 | 2026-05-08 | HVAC Fans fixing | 100 | 0 |  | 2026-04-28 |  | 2026-05-06 |  |  |  |  | MEP | HVAC Grill Fixing
44609 |  | Not Ready | MEP fix & Finishes | 2026-04-30 | 2026-05-08 | HVAC Fans fixing | 100 | 0 |  | 2026-04-28 |  | 2026-05-06 |  |  |  |  | MEP | HVAC Grill Fixing
44614 |  | Not Ready | MEP fix & Finishes | 2026-04-30 | 2026-05-08 | FAPA Device Fixing | 100 | 0 |  | 2026-04-28 |  | 2026-05-06
44614 |  | Not Ready | MEP fix & Finishes | 2026-04-30 | 2026-05-08 | FAPA Device Fixing | 100 | 0 |  | 2026-04-28 |  | 2026-05-06
44614 |  | Not Ready | MEP fix & Finishes | 2026-04-30 | 2026-05-08 | FAPA Device Fixing | 100 | 0 |  | 2026-04-28 |  | 2026-05-06
44614 |  | Not Ready | MEP fix & Finishes | 2026-04-30 | 2026-05-08 | FAPA Device Fixing | 100 | 0 |  | 2026-04-28 |  | 2026-05-06
44618 |  | Not Committed |  | 2026-04-30 | 2026-06-12 | P3 to P4 | 100 | 0 |  | 2026-04-28 |  | 2026-06-10
44618 |  | Not Committed |  | 2026-04-30 | 2026-06-12 | P3 to P4 | 100 | 0 |  | 2026-04-28 |  | 2026-06-10
44618 |  | Not Committed |  | 2026-04-30 | 2026-06-12 | P3 to P4 | 100 | 0 |  | 2026-04-28 |  | 2026-06-10
44619 |  | Not Ready | MEP fix & Finishes | 2026-04-30 | 2026-05-08 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2026-04-28 |  | 2026-05-06 |  |  |  |  | MEP | FPS final fixes
44619 |  | Not Ready | MEP fix & Finishes | 2026-04-30 | 2026-05-08 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2026-04-28 |  | 2026-05-06 |  |  |  |  | MEP | FPS final fixes
48240 | Retail & Clubhouse - Sub structure - B2 to B1 | Not Ready |  | 2025-11-05 | 2025-11-27 | Staircase Finishes | 100 | 0 |  | 2026-04-28 |  | 2026-05-21 |  | Club House | Sub Structure | B2
48240 | Retail & Clubhouse - Sub structure - B2 to B1 | Not Ready |  | 2025-11-05 | 2025-11-27 | Staircase Finishes | 100 | 0 |  | 2026-04-28 |  | 2026-05-21 |  | Club House | Sub Structure | B2
48245 | Retail & Clubhouse - Sub structure - B1 to GF | Not Ready |  | 2026-01-06 | 2026-01-29 | Staircase Finishes | 100 | 0 |  | 2026-04-28 |  | 2026-05-21 |  | Club House | Sub Structure | B1
48245 | Retail & Clubhouse - Sub structure - B1 to GF | Not Ready |  | 2026-01-06 | 2026-01-29 | Staircase Finishes | 100 | 0 |  | 2026-04-28 |  | 2026-05-21 |  | Club House | Sub Structure | B1
10934 | T-20-11th Floor Common Area | Not Ready | 1st Coat Painting | 2026-05-30 | 2026-06-20 | 1st Coat Painting | 100 | 0 |  | 2026-04-29 |  | 2026-05-20
11819 | T-18-5th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-07-10 | 2026-08-12 | 2nd Coat Painting | 100 | 0 |  | 2026-04-29 |  | 2026-05-30
39262 | Retail - Sub structure - B2 to B1 | Not Ready | RCC Works - Vertical | 2025-11-17 | 2025-12-19 | Columns/ Walls_NTA | 100 | 0 |  | 2026-04-29 |  | 2026-06-02 |  | Retail | Sub Structure | B2 | RCC Sub Structure | RCC Works - Vertical
39262 | Retail - Sub structure - B2 to B1 | Not Ready | RCC Works - Vertical | 2025-11-17 | 2025-12-19 | Columns/ Walls_NTA | 100 | 0 |  | 2026-04-29 |  | 2026-06-02 |  | Retail | Sub Structure | B2
41442 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-09 | 2026-04-14 | Final Painting | 100 | 0 |  | 2026-04-29 |  | 2026-05-06 |  | Tower A | Super Structure | L30 | Finishes | Final Painting
41442 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-09 | 2026-04-14 | Final Painting | 100 | 0 |  | 2026-04-29 |  | 2026-05-06 |  | Tower A | Super Structure | L30 | Finishes | Final Painting
41442 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-09 | 2026-04-14 | Final Painting | 100 | 0 |  | 2026-04-29 |  | 2026-05-06 |  | Tower A | Super Structure | L30 | Finishes | Final Painting
41489 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-04-09 | 2026-04-15 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-04-29 |  | 2026-05-06 |  | Tower A | Super Structure | L33 | MEP | Electrical
41563 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-04-08 | 2026-04-16 | False Ceiling | 100 | 0 |  | 2026-04-29 |  | 2026-05-08 |  | Tower A | Super Structure | L38 | Finishes | False Ceiling
41623 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-04-08 | 2026-04-16 | HVAC Ducting | 100 | 0 |  | 2026-04-29 |  | 2026-05-08 |  | Tower A | Super Structure | L42 | MEP | HVAC Ducting
42211 |  | Not Committed |  | 2026-05-02 | 2026-05-23 | MEP final fix & Finishes | 100 | 0 |  | 2026-04-29 |  | 2026-05-21
42212 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-05-02 | 2026-05-07 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-04-29 |  | 2026-05-05 |  | Tower A | Super Structure | L7 | Finishes | Door & Window Fixing
42229 |  | Not Committed |  | 2026-05-02 | 2026-05-23 | MEP final fix & Finishes | 100 | 0 |  | 2026-04-29 |  | 2026-05-21
42230 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-05-02 | 2026-05-07 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-04-29 |  | 2026-05-05 |  | Tower A | Super Structure | L8 | Finishes | Door & Window Fixing
42247 |  | Not Committed |  | 2026-05-02 | 2026-05-23 | MEP final fix & Finishes | 100 | 0 |  | 2026-04-29 |  | 2026-05-21
42248 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-05-02 | 2026-05-07 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-04-29 |  | 2026-05-05 |  | Tower A | Super Structure | L9 | Finishes | Door & Window Fixing
43322 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-04-07 | 2026-04-17 | Cement Plastering in wet areas | 100 | 0 |  | 2026-04-29 |  | 2026-05-11 |  | Tower A | Super Structure | L69
44131 | Tower A - Super Structure - Finishes & MEP - L68 to L73 | Not Ready | Façade Works - MEP & Finishes | 2026-06-01 | 2026-06-11 | Accessories & Alignment | 100 | 0 |  | 2026-04-29 |  | 2026-05-12 |  | Tower A | Super Structure | L68 | Façade | Façade Works
44131 | Tower A - Super Structure - Finishes & MEP - L68 to L73 | Not Ready | Façade Works - MEP & Finishes | 2026-06-01 | 2026-06-11 | Accessories & Alignment | 100 | 0 |  | 2026-04-29 |  | 2026-05-12 |  | Tower A | Super Structure | L68
9107 | T-15-1st Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-05-23 | 2026-07-27 | 2nd Coat Painting | 100 | 0 |  | 2026-04-30 |  | 2026-07-04
9322 | T-15-9th Floor Common Area | Not Ready | 1st Coat Painting | 2026-05-04 | 2026-05-25 | 1st Coat Painting | 100 | 0 |  | 2026-04-30 |  | 2026-05-25
11947 | T-18-11th Floor Common Area | Not Ready | Window-Open Area | 2026-07-14 | 2026-07-21 | Window-Open Area | 100 | 0 |  | 2026-04-30 |  | 2026-05-07
40063 | Tower A - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2026-04-08 | 2026-04-24 | Roping & Car Fixing | 100 | 0 |  | 2026-04-30 |  | 2026-05-19 |  | Tower A | Super Structure
40063 | Tower A - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2026-04-08 | 2026-04-24 | Roping & Car Fixing | 100 | 0 |  | 2026-04-30 |  | 2026-05-19 |  | Tower A | Super Structure
40324 | Tower A - Super Structure - Finishes & MEP - L77 to L78 | Not Ready | Partition Wall-Blockwork | 2026-04-02 | 2026-04-07 | Staircase Area | 100 | 0 |  | 2026-04-30 |  | 2026-05-07 |  | Tower A | Super Structure | L77
40546 | Tower A - Super Structure - Finishes & MEP - L72 to L73 | Not Ready | Gypsum Plastering Works | 2026-04-08 | 2026-04-24 | L72-73 | 100 | 0 |  | 2026-04-30 |  | 2026-05-18 |  | Tower A | Super Structure | L72 | Finishes | Gypsum Plastering Works
40546 | Tower A - Super Structure - Finishes & MEP - L72 to L73 | Not Ready | Gypsum Plastering Works | 2026-04-08 | 2026-04-24 | L72-73 | 100 | 0 |  | 2026-04-30 |  | 2026-05-18 |  | Tower A | Super Structure | L72
41520 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-04-09 | 2026-04-13 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-04-30 |  | 2026-05-05 |  | Tower A | Super Structure | L35
41532 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-04-09 | 2026-04-13 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-04-30 |  | 2026-05-05 |  | Tower A | Super Structure | L36 | MEP | FPS 2nd Fix - MEP & Finishes
41533 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-04-09 | 2026-04-15 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-04-30 |  | 2026-05-07 |  | Tower A | Super Structure | L36 | MEP | Electrical 2nd Fix - MEP & Finishes
41534 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-09 | 2026-04-17 | FAPA Device Fixing | 100 | 0 |  | 2026-04-30 |  | 2026-05-09 |  | Tower A | Super Structure | L36
41534 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-09 | 2026-04-17 | FAPA Device Fixing | 100 | 0 |  | 2026-04-30 |  | 2026-05-09 |  | Tower A | Super Structure | L36
41534 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-09 | 2026-04-17 | FAPA Device Fixing | 100 | 0 |  | 2026-04-30 |  | 2026-05-09 |  | Tower A | Super Structure | L36
41534 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-09 | 2026-04-17 | FAPA Device Fixing | 100 | 0 |  | 2026-04-30 |  | 2026-05-09 |  | Tower A | Super Structure | L36
41535 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-04-09 | 2026-04-13 | HVAC Grill Fixing | 100 | 0 |  | 2026-04-30 |  | 2026-05-05 |  | Tower A | Super Structure | L36 | MEP | HVAC Grill Fixing
41594 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-04-09 | 2026-04-21 | Flooring & Dado | 100 | 0 |  | 2026-04-30 |  | 2026-05-13 |  | Tower A | Super Structure | L40 | Finishes | Flooring & Dado
43287 |  | Not Committed |  | 2026-04-08 | 2026-07-24 | Finishes after 1st Fix | 100 | 0 |  | 2026-04-30 |  | 2026-08-21
43288 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-04-08 | 2026-04-30 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-04-30 |  | 2026-05-23 |  | Tower A | Super Structure | L67 | Finishes | Blockwork
48221 |  | Not Committed |  | 2026-01-08 | 2026-09-10 | Retail Area MEP 1st Fix (GF to P4) (FF works + Tap-off for Ele.+HVAC+PHE) | 100 | 0 |  | 2026-04-30 |  | 2027-03-04
48223 | Retail - Super structure - R1 to CH00 | Not Ready |  | 2026-01-08 | 2026-03-02 | R1 to CH00 | 100 | 0 |  | 2026-04-30 |  | 2026-06-23 |  | Retail | Super Structure
8846 | T-14-12th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-04-04 | 2026-06-26 | 1st Coat Painting | 100 | 0 |  | 2026-05-01 |  | 2026-07-21
9656 | T-16-2nd Floor Common Area | Not Ready | Flooring & skirting | 2026-05-18 | 2026-06-09 | Flooring & skirting | 100 | 0 |  | 2026-05-01 |  | 2026-05-25
9683 | T-16-3rd Floor Common Area | Not Ready | Putty | 2026-05-18 | 2026-06-25 | Putty | 100 | 0 |  | 2026-05-01 |  | 2026-06-09
11711 | T-18-1st Floor Common Area | Not Ready | Putty | 2026-07-06 | 2026-08-13 | Putty | 100 | 0 |  | 2026-05-01 |  | 2026-06-08
11972 | T-18-11th Floor Common Area | Not Ready | Door-Shaft /Staircase Fire Door | 2026-07-17 | 2026-07-30 | Door-Shaft /Staircase Fire Door | 100 | 0 |  | 2026-05-01 |  | 2026-05-14
8826 | T-14-11th Floor Common Area | Not Ready | Door-Shaft | 2026-04-04 | 2026-04-17 | Door-Shaft | 100 | 0 |  | 2026-05-02 |  | 2026-05-15
9814 | T-16-8th Floor Common Area | Not Ready | Door-Shaft | 2026-05-23 | 2026-06-05 | Door-Shaft | 100 | 0 |  | 2026-05-02 |  | 2026-05-16
10699 | T-20-2nd Floor Common Area | Not Ready | Window-Open Area | 2026-05-28 | 2026-06-04 | Window-Open Area | 100 | 0 |  | 2026-05-02 |  | 2026-05-09
11976 |  | Not Ready |  | 2026-07-06 | 2027-02-11 | TF | 100 | 0 |  | 2026-05-02 |  | 2026-12-07
11977 |  | Not Ready |  | 2026-07-06 | 2027-02-11 | Finishing Works | 100 | 0 |  | 2026-05-02 |  | 2026-12-07
11987 | T-18-Lift Lobby | Not Ready |  | 2026-07-17 | 2026-08-02 | 10F | 100 | 0 |  | 2026-05-02 |  | 2026-05-17
41458 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-10 | 2026-04-16 | Final Painting | 100 | 0 |  | 2026-05-02 |  | 2026-05-08 |  | Tower A | Super Structure | L31 | Finishes | Final Painting
41458 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-10 | 2026-04-16 | Final Painting | 100 | 0 |  | 2026-05-02 |  | 2026-05-08 |  | Tower A | Super Structure | L31 | Finishes | Final Painting
41458 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-10 | 2026-04-16 | Final Painting | 100 | 0 |  | 2026-05-02 |  | 2026-05-08 |  | Tower A | Super Structure | L31 | Finishes | Final Painting
41505 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-04-11 | 2026-04-16 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-05-02 |  | 2026-05-08 |  | Tower A | Super Structure | L34 | MEP | Electrical
43251 |  | Not Committed |  | 2026-04-09 | 2026-07-10 | Finishes after 1st Fix | 100 | 0 |  | 2026-05-02 |  | 2026-08-06
43252 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-04-09 | 2026-05-02 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-05-02 |  | 2026-05-25 |  | Tower A | Super Structure | L65 | Finishes | Blockwork
43340 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-04-09 | 2026-04-20 | Cement Plastering in wet areas | 100 | 0 |  | 2026-05-02 |  | 2026-05-13 |  | Tower A | Super Structure | L70
43412 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-04-09 | 2026-04-20 | Cement Plastering in wet areas | 100 | 0 |  | 2026-05-02 |  | 2026-05-13 |  | Tower A | Super Structure | L74
44593 |  | Not Ready | MEP fix & Finishes | 2026-05-05 | 2026-05-09 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-05-02 |  | 2026-05-07
44593 |  | Not Ready | MEP fix & Finishes | 2026-05-05 | 2026-05-09 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-05-02 |  | 2026-05-07
44593 |  | Not Ready | MEP fix & Finishes | 2026-05-05 | 2026-05-09 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-05-02 |  | 2026-05-07
45300 | Tower B - Super Structure - Core & Outer Slab L16-17 | Not Ready | RCC Works - Slab | 2026-02-23 | 2026-02-28 | Outer Slab_TA | 100 | 0 |  | 2026-05-02 |  | 2026-05-11 |  | Tower B | Super Structure | L16 | RCC Sub Structure | RCC Works - Slab
45767 |  | Not Ready |  | 2026-02-25 | 2027-02-20 | Basement MEP & Finishes | 100 | 0 |  | 2026-05-02 |  | 2027-05-03
45824 |  | Not Committed |  | 2026-02-25 | 2027-02-04 | B1 Level | 100 | 0 |  | 2026-05-02 |  | 2027-04-15
45839 |  | Not Committed |  | 2026-02-25 | 2026-06-01 | Floor Area | 100 | 0 |  | 2026-05-02 |  | 2026-08-11
45840 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | Ceiling Painting/ PT Marking - MEP & Finishes | 2026-02-25 | 2026-03-02 | Ceiling Painting/ PT Marking | 100 | 0 |  | 2026-05-02 |  | 2026-05-08 |  | Tower B | Sub Structure | B1 | Finishes | Ceiling Painting/ PT Marking
45869 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-02-25 | 2026-03-20 | PHE 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-05-02 |  | 2026-05-26 |  | Tower B | Super Structure | GF
45870 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-02-25 | 2026-03-14 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-05-02 |  | 2026-05-20 |  | Tower B | Super Structure | GF | MEP | Electrical 1st Fixes
45904 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | VDF/ Grade Slab - MEP & Finishes | 2026-02-25 | 2026-03-02 | VDF/ Grade Slab | 100 | 0 |  | 2026-05-02 |  | 2026-05-08 |  | Tower B | Super Structure
45932 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-02-25 | 2026-03-05 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-05-02 |  | 2026-05-11 |  | Tower B | Super Structure |  | MEP | FPS 2nd Fix - MEP & Finishes
45933 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-02-25 | 2026-03-05 | FAPA Device Fixing | 100 | 0 |  | 2026-05-02 |  | 2026-05-11 |  | Tower B | Super Structure
45933 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-02-25 | 2026-03-05 | FAPA Device Fixing | 100 | 0 |  | 2026-05-02 |  | 2026-05-11 |  | Tower B | Super Structure
45933 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-02-25 | 2026-03-05 | FAPA Device Fixing | 100 | 0 |  | 2026-05-02 |  | 2026-05-11 |  | Tower B | Super Structure
45933 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-02-25 | 2026-03-05 | FAPA Device Fixing | 100 | 0 |  | 2026-05-02 |  | 2026-05-11 |  | Tower B | Super Structure
47649 |  | Complete |  | 2026-05-02 | 2026-06-01 | Pour 8 (grid PB-D to PB-K) | 100 | 100 |  | 2026-05-02 | 2026-05-02 | 2026-06-01 | 2026-06-01
47650 |  | Complete |  | 2026-05-02 | 2026-05-19 | Columns/ Walls_NTA | 100 | 100 |  | 2026-05-02 | 2026-05-02 | 2026-05-19 | 2026-05-19
47650 |  | Complete |  | 2026-05-02 | 2026-05-19 | Columns/ Walls_NTA | 100 | 100 |  | 2026-05-02 | 2026-05-02 | 2026-05-19 | 2026-05-19 |  |  |  | RCC Sub Structure | RCC Works - Vertical
8561 | T-14-1st Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-04-23 | 2026-06-28 | 2nd Coat Painting | 100 | 0 |  | 2026-05-03 |  | 2026-07-08
8646 | T-14-4th Floor Common Area | Not Ready | 1st Coat Painting | 2026-03-28 | 2026-04-20 | 1st Coat Painting | 100 | 0 |  | 2026-05-03 |  | 2026-05-27
9164 | T-15-3rd Floor Common Area | Not Ready | Door-Shaft | 2026-04-28 | 2026-05-12 | Door-Shaft | 100 | 0 |  | 2026-05-03 |  | 2026-05-17
9387 | T-15-Lift Lobby | Not Ready |  | 2026-05-15 | 2026-06-01 | 10F | 100 | 0 |  | 2026-05-03 |  | 2026-05-19
9789 | T-16-7th Floor Common Area | Not Ready | Window-Open Area | 2026-05-20 | 2026-05-28 | Window-Open Area | 100 | 0 |  | 2026-05-03 |  | 2026-05-10
8801 | T-14-11th Floor Common Area | Not Ready | Window-Open Area | 2026-04-06 | 2026-04-14 | Window-Open Area | 100 | 0 |  | 2026-05-04 |  | 2026-05-11
9896 |  | Not Ready |  | 2026-07-01 | 2027-02-06 | TF | 100 | 0 |  | 2026-05-04 |  | 2026-12-08
9897 |  | Not Ready |  | 2026-07-01 | 2027-02-06 | Finishing Works | 100 | 0 |  | 2026-05-04 |  | 2026-12-08
10447 | T-21-Staircase 1 | Not Ready |  | 2026-05-30 | 2026-06-10 | 06F-05F | 100 | 0 |  | 2026-05-04 |  | 2026-05-17
10461 | T-21-Staircase 2 | Not Ready |  | 2026-05-30 | 2026-06-10 | 07F-06F | 100 | 0 |  | 2026-05-04 |  | 2026-05-17
10614 | T-20-Basement Floor | Not Ready | 2nd Coat Painting | 2026-06-29 | 2026-09-15 | 2nd Coat Painting | 100 | 0 |  | 2026-05-04 |  | 2026-07-19
10883 | T-20-9th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-06-04 | 2026-07-07 | 2nd Coat Painting | 100 | 0 |  | 2026-05-04 |  | 2026-06-07
10901 | T-20-10th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-06-04 | 2026-08-08 | 2nd Coat Painting | 100 | 0 |  | 2026-05-04 |  | 2026-07-08
11190 | T-19-1st Floor Common Area | Not Ready | Flooring & skirting | 2026-05-19 | 2026-06-09 | Flooring & skirting | 100 | 0 |  | 2026-05-04 |  | 2026-05-25
11217 | T-19-2nd Floor Common Area | Not Ready | Putty | 2026-05-19 | 2026-06-25 | Putty | 100 | 0 |  | 2026-05-04 |  | 2026-06-11
11376 | T-19-8th Floor Common Area | Not Ready | 1st Coat Painting | 2026-05-23 | 2026-06-13 | 1st Coat Painting | 100 | 0 |  | 2026-05-04 |  | 2026-05-28
11465 | T-19-Lift Lobby | Not Ready |  | 2026-05-19 | 2026-06-04 | 12F | 100 | 0 |  | 2026-05-04 |  | 2026-05-19
40547 | Tower A - Super Structure - Finishes & MEP - L73 to L74 | Not Ready | Gypsum Plastering Works | 2026-04-10 | 2026-04-27 | L73-74 | 100 | 0 |  | 2026-05-04 |  | 2026-05-20 |  | Tower A | Super Structure | L73 | Finishes | Gypsum Plastering Works
40547 | Tower A - Super Structure - Finishes & MEP - L73 to L74 | Not Ready | Gypsum Plastering Works | 2026-04-10 | 2026-04-27 | L73-74 | 100 | 0 |  | 2026-05-04 |  | 2026-05-20 |  | Tower A | Super Structure | L73
41579 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-04-11 | 2026-04-20 | False Ceiling | 100 | 0 |  | 2026-05-04 |  | 2026-05-12 |  | Tower A | Super Structure | L39 | Finishes | False Ceiling
41639 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-04-11 | 2026-04-20 | HVAC Ducting | 100 | 0 |  | 2026-05-04 |  | 2026-05-12 |  | Tower A | Super Structure | L43 | MEP | HVAC Ducting
41652 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-04-11 | 2026-04-17 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-05-04 |  | 2026-05-09 |  | Tower A | Super Structure | L44 | MEP | FPS 1st Fix - MEP & Finishes
41653 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-04-11 | 2026-04-15 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-05-04 |  | 2026-05-07 |  | Tower A | Super Structure | L44 | MEP | Electrical 1st Fixes
43980 | Tower A - Super Structure - Finishes & MEP - L15 to L25 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-06-04 | 2026-06-20 | Staircase Light Fixtures & Devices fixing | 100 | 0 |  | 2026-05-04 |  | 2026-05-21 |  | Tower A | Super Structure | L15
45733 | Tower B - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2026-02-26 | 2026-04-20 | FHC & Accessories fixing | 100 | 0 |  | 2026-05-04 |  | 2026-06-26 |  | Tower B | Super Structure | L7
45735 | Tower B - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2026-02-26 | 2026-04-20 | Soil & Waste Downtake piping in Plumbing Shaft | 100 | 0 |  | 2026-05-04 |  | 2026-06-26 |  | Tower B | Super Structure | L7
45739 | Tower B - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2026-02-26 | 2026-04-20 | HVAC Shaft Ducting | 100 | 0 |  | 2026-05-04 |  | 2026-06-26 |  | Tower B | Super Structure | L7 | MEP | HVAC Grill Fixing
8880 | T-14-Staircase 1 | Not Ready |  | 2026-04-04 | 2026-04-15 | TF-12F | 100 | 0 |  | 2026-05-05 |  | 2026-05-17
11481 | T-19-Staircase 1 | Not Ready |  | 2026-05-19 | 2026-05-29 | 12F-11F | 100 | 0 |  | 2026-05-05 |  | 2026-05-17
11495 | T-19-Staircase 2 | Not Ready |  | 2026-05-19 | 2026-05-29 | TF-12F | 100 | 0 |  | 2026-05-05 |  | 2026-05-17
12004 | T-18-Staircase 1 | Not Ready |  | 2026-07-17 | 2026-07-28 | 09F-08F | 100 | 0 |  | 2026-05-05 |  | 2026-05-16
12018 | T-18-Staircase 2 | Not Ready |  | 2026-07-17 | 2026-07-28 | 10F-09F | 100 | 0 |  | 2026-05-05 |  | 2026-05-16
40044 | Tower A | Not Ready | BMU Installation | 2026-04-06 | 2026-07-03 | BMU Installation | 100 | 0 |  | 2026-05-05 |  | 2026-08-06 |  | Tower A | --
40044 | Tower A | Not Ready | BMU Installation | 2026-04-06 | 2026-07-03 | BMU Installation | 100 | 0 |  | 2026-05-05 |  | 2026-08-06 |  | Tower A | --
40096 | Tower A - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2026-04-06 | 2026-05-11 | Support & Pipe Installation | 100 | 0 |  | 2026-05-05 |  | 2026-06-10 |  | Tower A | Super Structure
41474 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-13 | 2026-04-18 | Final Painting | 100 | 0 |  | 2026-05-05 |  | 2026-05-09 |  | Tower A | Super Structure | L32 | Finishes | Final Painting
41474 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-13 | 2026-04-18 | Final Painting | 100 | 0 |  | 2026-05-05 |  | 2026-05-09 |  | Tower A | Super Structure | L32 | Finishes | Final Painting
41474 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-13 | 2026-04-18 | Final Painting | 100 | 0 |  | 2026-05-05 |  | 2026-05-09 |  | Tower A | Super Structure | L32 | Finishes | Final Painting
41521 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-04-13 | 2026-04-18 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-05-05 |  | 2026-05-11 |  | Tower A | Super Structure | L35 | MEP | Electrical
41536 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-04-13 | 2026-04-16 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-05-05 |  | 2026-05-08 |  | Tower A | Super Structure | L36
41548 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-04-13 | 2026-04-16 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-05-05 |  | 2026-05-08 |  | Tower A | Super Structure | L37 | MEP | FPS 2nd Fix - MEP & Finishes
41549 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-04-13 | 2026-04-18 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-05-05 |  | 2026-05-11 |  | Tower A | Super Structure | L37 | MEP | Electrical 2nd Fix - MEP & Finishes
41550 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-13 | 2026-04-21 | FAPA Device Fixing | 100 | 0 |  | 2026-05-05 |  | 2026-05-13 |  | Tower A | Super Structure | L37
41550 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-13 | 2026-04-21 | FAPA Device Fixing | 100 | 0 |  | 2026-05-05 |  | 2026-05-13 |  | Tower A | Super Structure | L37
41550 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-13 | 2026-04-21 | FAPA Device Fixing | 100 | 0 |  | 2026-05-05 |  | 2026-05-13 |  | Tower A | Super Structure | L37
41550 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-13 | 2026-04-21 | FAPA Device Fixing | 100 | 0 |  | 2026-05-05 |  | 2026-05-13 |  | Tower A | Super Structure | L37
41551 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-04-13 | 2026-04-16 | HVAC Grill Fixing | 100 | 0 |  | 2026-05-05 |  | 2026-05-08 |  | Tower A | Super Structure | L37 | MEP | HVAC Grill Fixing
41610 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-04-13 | 2026-04-24 | Flooring & Dado | 100 | 0 |  | 2026-05-05 |  | 2026-05-16 |  | Tower A | Super Structure | L41 | Finishes | Flooring & Dado
42170 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-04-11 | 2026-04-22 | Cement Plastering in wet areas | 100 | 0 |  | 2026-05-05 |  | 2026-05-15 |  | Tower A | Super Structure | L75
43358 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-04-11 | 2026-04-22 | Cement Plastering in wet areas | 100 | 0 |  | 2026-05-05 |  | 2026-05-15 |  | Tower A | Super Structure | L71
46732 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-02-27 | 2026-03-17 | Wet Area Waterproofing | 100 | 0 |  | 2026-05-05 |  | 2026-05-22 |  | Tower B | Super Structure | L11
8776 | T-14-9th Floor Common Area | Not Ready | 1st Coat Painting | 2026-04-03 | 2026-04-25 | 1st Coat Painting | 100 | 0 |  | 2026-05-06 |  | 2026-05-26
9192 | T-15-4th Floor Common Area | Not Ready | 1st Coat Painting | 2026-04-27 | 2026-05-20 | 1st Coat Painting | 100 | 0 |  | 2026-05-06 |  | 2026-05-28
9404 | T-15-Staircase 1 | Not Ready |  | 2026-05-15 | 2026-05-26 | 09F-08F | 100 | 0 |  | 2026-05-06 |  | 2026-05-16
9418 | T-15-Staircase 2 | Not Ready |  | 2026-05-15 | 2026-05-26 | 10F-09F | 100 | 0 |  | 2026-05-06 |  | 2026-05-16
9886 | T-16-11th Floor Flat Area | Not Ready | 1st Coat Painting | 2026-05-29 | 2026-08-20 | 1st Coat Painting | 100 | 0 |  | 2026-05-06 |  | 2026-07-26
10966 | T-20-Staircase 1 | Not Ready |  | 2026-05-31 | 2026-06-11 | 07F-06F | 100 | 0 |  | 2026-05-06 |  | 2026-05-18
10980 | T-20-Staircase 2 | Not Ready |  | 2026-05-31 | 2026-06-11 | 08F-07F | 100 | 0 |  | 2026-05-06 |  | 2026-05-18
11897 | T-18-8th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-07-21 | 2026-08-24 | 2nd Coat Painting | 100 | 0 |  | 2026-05-06 |  | 2026-06-06
40082 | Tower A - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2026-04-13 | 2026-04-20 | Jump platform installation | 100 | 0 |  | 2026-05-06 |  | 2026-05-14 |  | Tower A | Super Structure
40082 | Tower A - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2026-04-13 | 2026-04-20 | Jump platform installation | 100 | 0 |  | 2026-05-06 |  | 2026-05-14 |  | Tower A | Super Structure
40082 | Tower A - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2026-04-13 | 2026-04-20 | Jump platform installation | 100 | 0 |  | 2026-05-06 |  | 2026-05-14 |  | Tower A | Super Structure
40548 | Tower A - Super Structure - Finishes & MEP - L74 to L75 | Not Ready | Gypsum Plastering Works | 2026-04-13 | 2026-04-29 | L74-75 | 100 | 0 |  | 2026-05-06 |  | 2026-05-22 |  | Tower A | Super Structure | L74 | Finishes | Gypsum Plastering Works
40548 | Tower A - Super Structure - Finishes & MEP - L74 to L75 | Not Ready | Gypsum Plastering Works | 2026-04-13 | 2026-04-29 | L74-75 | 100 | 0 |  | 2026-05-06 |  | 2026-05-22 |  | Tower A | Super Structure | L74
41490 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-15 | 2026-04-21 | Final Painting | 100 | 0 |  | 2026-05-06 |  | 2026-05-12 |  | Tower A | Super Structure | L33 | Finishes | Final Painting
41490 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-15 | 2026-04-21 | Final Painting | 100 | 0 |  | 2026-05-06 |  | 2026-05-12 |  | Tower A | Super Structure | L33 | Finishes | Final Painting
41490 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-15 | 2026-04-21 | Final Painting | 100 | 0 |  | 2026-05-06 |  | 2026-05-12 |  | Tower A | Super Structure | L33 | Finishes | Final Painting
42213 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-05-08 | 2026-05-11 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-05-06 |  | 2026-05-08 |  | Tower A | Super Structure | L7 | MEP | FPS 2nd Fix - MEP & Finishes
42214 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-05-08 | 2026-05-11 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-05-06 |  | 2026-05-08 |  | Tower A | Super Structure | L7 | MEP | Electrical 2nd Fix - MEP & Finishes
42231 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-05-08 | 2026-05-11 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-05-06 |  | 2026-05-08 |  | Tower A | Super Structure | L8 | MEP | FPS 2nd Fix - MEP & Finishes
42232 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-05-08 | 2026-05-11 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-05-06 |  | 2026-05-08 |  | Tower A | Super Structure | L8 | MEP | Electrical 2nd Fix - MEP & Finishes
42249 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-05-08 | 2026-05-11 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-05-06 |  | 2026-05-08 |  | Tower A | Super Structure | L9 | MEP | FPS 2nd Fix - MEP & Finishes
42250 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-05-08 | 2026-05-11 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-05-06 |  | 2026-05-08 |  | Tower A | Super Structure | L9 | MEP | Electrical 2nd Fix - MEP & Finishes
42265 |  | Not Committed |  | 2026-05-08 | 2026-05-30 | MEP final fix & Finishes | 100 | 0 |  | 2026-05-06 |  | 2026-05-28
42266 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-05-08 | 2026-05-13 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-05-06 |  | 2026-05-11 |  | Tower A | Super Structure | L10 | Finishes | Door & Window Fixing
42283 |  | Not Committed |  | 2026-05-08 | 2026-05-30 | MEP final fix & Finishes | 100 | 0 |  | 2026-05-06 |  | 2026-05-28
42284 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-05-08 | 2026-05-13 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-05-06 |  | 2026-05-11 |  | Tower A | Super Structure | L11 | Finishes | Door & Window Fixing
42301 |  | Not Committed |  | 2026-05-08 | 2026-05-30 | MEP final fix & Finishes | 100 | 0 |  | 2026-05-06 |  | 2026-05-28
42302 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-05-08 | 2026-05-13 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-05-06 |  | 2026-05-11 |  | Tower A | Super Structure | L12 | Finishes | Door & Window Fixing
44134 | Tower A - Super Structure - Finishes & MEP - L73 to L78 | Not Ready | Façade Works - MEP & Finishes | 2026-06-06 | 2026-06-17 | DGU Assembly Installation | 100 | 0 |  | 2026-05-06 |  | 2026-05-18 |  | Tower A | Super Structure | L73 | Façade | Façade Works
44135 | Tower A - Super Structure - Finishes & MEP - L73 to L78 | Not Ready | Façade Works - MEP & Finishes | 2026-06-06 | 2026-06-29 | Installation of highly reflective metal sheet | 100 | 0 |  | 2026-05-06 |  | 2026-05-30 |  | Tower A | Super Structure | L73 | Façade | Façade Works
44136 | Tower A - Super Structure - Finishes & MEP - L73 to L78 | Not Ready | Façade Works - MEP & Finishes | 2026-06-06 | 2026-06-17 | Fixing of Backlit Laminated Glass assembly & ACP Panels | 100 | 0 |  | 2026-05-06 |  | 2026-05-18 |  | Tower A | Super Structure | L73 | Façade | Façade Works
44137 | Tower A - Super Structure - Finishes & MEP - L73 to L78 | Not Ready | Façade Works - MEP & Finishes | 2026-06-06 | 2026-06-17 | Fixing of Louvers | 100 | 0 |  | 2026-05-06 |  | 2026-05-18 |  | Tower A | Super Structure | L73 | Façade | Façade Works
44137 | Tower A - Super Structure - Finishes & MEP - L73 to L78 | Not Ready | Façade Works - MEP & Finishes | 2026-06-06 | 2026-06-17 | Fixing of Louvers | 100 | 0 |  | 2026-05-06 |  | 2026-05-18 |  | Tower A | Super Structure | L73
45456 | Tower B - Super Structure - Finishes & MEP - L12 to L13 | Not Ready | Partition Wall-Blockwork | 2026-02-28 | 2026-03-06 | Staircase Area | 100 | 0 |  | 2026-05-06 |  | 2026-05-12 |  | Tower B | Super Structure | L12
48042 |  | Not Committed |  | 2026-01-13 | 2026-03-28 | CH01-CH02 (4.45) | 100 | 0 |  | 2026-05-06 |  | 2026-07-21
48043 | Club House - Super structure - CH01 to CH02 | Not Ready |  | 2026-01-13 | 2026-02-17 | Columns_CH | 100 | 0 |  | 2026-05-06 |  | 2026-06-10 |  | Club House | Super Structure | CH01
48044 | Club House - Super structure - CH01 to CH02 | Not Ready |  | 2026-01-13 | 2026-02-05 | Staircase_CH | 100 | 0 |  | 2026-05-06 |  | 2026-05-29 |  | Club House | Super Structure | CH01
48208 |  | Not Committed |  | 2026-01-13 | 2026-05-23 | Club House Masonry | 100 | 0 |  | 2026-05-06 |  | 2026-09-22
48209 | Club House - Super structure - CH00 to CH01 | Not Ready |  | 2026-01-13 | 2026-02-17 | CH00-CH01 (P4-5) | 100 | 0 |  | 2026-05-06 |  | 2026-06-10 |  | Club House | Super Structure | CH00
8618 | T-14-3rd Floor Common Area | Not Ready | Door-Shaft | 2026-03-30 | 2026-04-11 | Door-Shaft | 100 | 0 |  | 2026-05-07 |  | 2026-05-20
9372 | T-15-11th Floor Common Area | Not Ready | Door-Shaft | 2026-05-15 | 2026-05-28 | Door-Shaft | 100 | 0 |  | 2026-05-07 |  | 2026-05-20
9891 | T-16-11th Floor Common Area | Not Ready | Putty | 2026-06-03 | 2026-07-11 | Putty | 100 | 0 |  | 2026-05-07 |  | 2026-06-16
41595 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-04-15 | 2026-04-23 | False Ceiling | 100 | 0 |  | 2026-05-07 |  | 2026-05-15 |  | Tower A | Super Structure | L40 | Finishes | False Ceiling
41654 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-04-15 | 2026-04-17 | FAPA Cabling | 100 | 0 |  | 2026-05-07 |  | 2026-05-09 |  | Tower A | Super Structure | L44
43376 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-04-14 | 2026-04-24 | Cement Plastering in wet areas | 100 | 0 |  | 2026-05-07 |  | 2026-05-18 |  | Tower A | Super Structure | L72
43424 |  | Not Committed |  | 2026-04-08 | 2026-10-30 | L77-78 | 100 | 0 |  | 2026-05-07 |  | 2026-10-13
43424 |  | Not Committed |  | 2026-04-08 | 2026-10-30 | L77-78 | 100 | 0 |  | 2026-05-07 |  | 2026-10-13 |  |  |  |  | Finishes | Gypsum Plastering Works
43425 |  | Not Committed |  | 2026-04-08 | 2026-05-07 | MEP 1st Fixes | 100 | 0 |  | 2026-05-07 |  | 2026-06-06
43426 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-04-08 | 2026-04-15 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-05-07 |  | 2026-05-15 |  | Tower A | Super Structure | L77 | MEP | FPS 1st Fix - MEP & Finishes
43427 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-04-08 | 2026-04-13 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-05-07 |  | 2026-05-13 |  | Tower A | Super Structure | L77 | MEP | Electrical 1st Fixes
43428 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-04-08 | 2026-04-15 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-05-07 |  | 2026-05-15 |  | Tower A | Super Structure | L77
43429 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-04-08 | 2026-04-24 | Wet Area Waterproofing | 100 | 0 |  | 2026-05-07 |  | 2026-05-25 |  | Tower A | Super Structure | L77
44610 |  | Not Ready | MEP fix & Finishes | 2026-05-09 | 2026-05-20 | Final Painting | 100 | 0 |  | 2026-05-07 |  | 2026-05-18 |  |  |  |  | Finishes | Final Painting
44610 |  | Not Ready | MEP fix & Finishes | 2026-05-09 | 2026-05-20 | Final Painting | 100 | 0 |  | 2026-05-07 |  | 2026-05-18 |  |  |  |  | Finishes | Final Painting
44610 |  | Not Ready | MEP fix & Finishes | 2026-05-09 | 2026-05-20 | Final Painting | 100 | 0 |  | 2026-05-07 |  | 2026-05-18 |  |  |  |  | Finishes | Final Painting
44615 |  | Not Ready | MEP fix & Finishes | 2026-05-09 | 2026-05-16 | HVAC Fans fixing | 100 | 0 |  | 2026-05-07 |  | 2026-05-14 |  |  |  |  | MEP | HVAC Grill Fixing
44615 |  | Not Ready | MEP fix & Finishes | 2026-05-09 | 2026-05-16 | HVAC Fans fixing | 100 | 0 |  | 2026-05-07 |  | 2026-05-14 |  |  |  |  | MEP | HVAC Grill Fixing
44620 |  | Not Ready | MEP fix & Finishes | 2026-05-09 | 2026-05-16 | FAPA Device Fixing | 100 | 0 |  | 2026-05-07 |  | 2026-05-14
44620 |  | Not Ready | MEP fix & Finishes | 2026-05-09 | 2026-05-16 | FAPA Device Fixing | 100 | 0 |  | 2026-05-07 |  | 2026-05-14
44620 |  | Not Ready | MEP fix & Finishes | 2026-05-09 | 2026-05-16 | FAPA Device Fixing | 100 | 0 |  | 2026-05-07 |  | 2026-05-14
44620 |  | Not Ready | MEP fix & Finishes | 2026-05-09 | 2026-05-16 | FAPA Device Fixing | 100 | 0 |  | 2026-05-07 |  | 2026-05-14
44624 |  | Not Committed |  | 2026-05-09 | 2026-06-20 | P4 to P5 | 100 | 0 |  | 2026-05-07 |  | 2026-06-18
44624 |  | Not Committed |  | 2026-05-09 | 2026-06-20 | P4 to P5 | 100 | 0 |  | 2026-05-07 |  | 2026-06-18
44624 |  | Not Committed |  | 2026-05-09 | 2026-06-20 | P4 to P5 | 100 | 0 |  | 2026-05-07 |  | 2026-06-18
44625 |  | Not Ready | MEP fix & Finishes | 2026-05-09 | 2026-05-16 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2026-05-07 |  | 2026-05-14 |  |  |  |  | MEP | FPS final fixes
44625 |  | Not Ready | MEP fix & Finishes | 2026-05-09 | 2026-05-16 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2026-05-07 |  | 2026-05-14 |  |  |  |  | MEP | FPS final fixes
46715 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-03-02 | 2026-03-13 | Cement Plastering in wet areas | 100 | 0 |  | 2026-05-07 |  | 2026-05-19 |  | Tower B | Super Structure | L10
9111 | T-15-1st Floor Common Area | Not Ready | Putty | 2026-05-05 | 2026-06-11 | Putty | 100 | 0 |  | 2026-05-08 |  | 2026-06-17
9347 | T-15-11th Floor Common Area | Not Ready | Window-Open Area | 2026-05-12 | 2026-05-20 | Window-Open Area | 100 | 0 |  | 2026-05-08 |  | 2026-05-15
11948 | T-18-11th Floor Common Area | Not Ready | 1st Coat Painting | 2026-07-21 | 2026-08-12 | 1st Coat Painting | 100 | 0 |  | 2026-05-08 |  | 2026-05-29
40549 | Tower A - Super Structure - Finishes & MEP - L75 to L76 | Not Ready | Gypsum Plastering Works | 2026-04-15 | 2026-05-02 | L75-76 | 100 | 0 |  | 2026-05-08 |  | 2026-05-25 |  | Tower A | Super Structure | L75 | Finishes | Gypsum Plastering Works
40549 | Tower A - Super Structure - Finishes & MEP - L75 to L76 | Not Ready | Gypsum Plastering Works | 2026-04-15 | 2026-05-02 | L75-76 | 100 | 0 |  | 2026-05-08 |  | 2026-05-25 |  | Tower A | Super Structure | L75
41506 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-17 | 2026-04-22 | Final Painting | 100 | 0 |  | 2026-05-08 |  | 2026-05-14 |  | Tower A | Super Structure | L34 | Finishes | Final Painting
41506 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-17 | 2026-04-22 | Final Painting | 100 | 0 |  | 2026-05-08 |  | 2026-05-14 |  | Tower A | Super Structure | L34 | Finishes | Final Painting
41506 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-17 | 2026-04-22 | Final Painting | 100 | 0 |  | 2026-05-08 |  | 2026-05-14 |  | Tower A | Super Structure | L34 | Finishes | Final Painting
41537 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-04-16 | 2026-04-22 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-05-08 |  | 2026-05-14 |  | Tower A | Super Structure | L36 | MEP | Electrical
41552 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-04-16 | 2026-04-20 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-05-08 |  | 2026-05-12 |  | Tower A | Super Structure | L37
41564 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-04-16 | 2026-04-20 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-05-08 |  | 2026-05-12 |  | Tower A | Super Structure | L38 | MEP | FPS 2nd Fix - MEP & Finishes
41565 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-04-16 | 2026-04-22 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-05-08 |  | 2026-05-14 |  | Tower A | Super Structure | L38 | MEP | Electrical 2nd Fix - MEP & Finishes
41566 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-16 | 2026-04-24 | FAPA Device Fixing | 100 | 0 |  | 2026-05-08 |  | 2026-05-16 |  | Tower A | Super Structure | L38
41566 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-16 | 2026-04-24 | FAPA Device Fixing | 100 | 0 |  | 2026-05-08 |  | 2026-05-16 |  | Tower A | Super Structure | L38
41566 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-16 | 2026-04-24 | FAPA Device Fixing | 100 | 0 |  | 2026-05-08 |  | 2026-05-16 |  | Tower A | Super Structure | L38
41566 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-16 | 2026-04-24 | FAPA Device Fixing | 100 | 0 |  | 2026-05-08 |  | 2026-05-16 |  | Tower A | Super Structure | L38
41567 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-04-16 | 2026-04-20 | HVAC Grill Fixing | 100 | 0 |  | 2026-05-08 |  | 2026-05-12 |  | Tower A | Super Structure | L38 | MEP | HVAC Grill Fixing
41626 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-04-16 | 2026-04-28 | Flooring & Dado | 100 | 0 |  | 2026-05-08 |  | 2026-05-20 |  | Tower A | Super Structure | L42 | Finishes | Flooring & Dado
45614 | Tower B - Super Structure - Finishes & MEP - L11 to L12 | Not Ready | Gypsum Plastering Works | 2026-03-04 | 2026-04-18 | L11-12 | 100 | 0 |  | 2026-05-08 |  | 2026-06-25 |  | Tower B | Super Structure | L11 | Finishes | Gypsum Plastering Works
45614 | Tower B - Super Structure - Finishes & MEP - L11 to L12 | Not Ready | Gypsum Plastering Works | 2026-03-04 | 2026-04-18 | L11-12 | 100 | 0 |  | 2026-05-08 |  | 2026-06-25 |  | Tower B | Super Structure | L11
45797 |  | Not Committed |  | 2026-03-04 | 2027-02-12 | B2 Level | 100 | 0 |  | 2026-05-08 |  | 2027-04-23
45812 |  | Not Committed |  | 2026-03-04 | 2026-05-13 | Floor Area | 100 | 0 |  | 2026-05-08 |  | 2026-07-21
45813 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | Ceiling Painting/ PT Marking - MEP & Finishes | 2026-03-04 | 2026-03-09 | Ceiling Painting/ PT Marking | 100 | 0 |  | 2026-05-08 |  | 2026-05-14 |  | Tower B | Sub Structure | B2 | Finishes | Ceiling Painting/ PT Marking
45841 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-03-04 | 2026-04-07 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-05-08 |  | 2026-06-13 |  | Tower B | Sub Structure | B1 | MEP | FPS 1st Fix - MEP & Finishes
45842 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-03-04 | 2026-04-07 | PHE 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-05-08 |  | 2026-06-13 |  | Tower B | Sub Structure | B1
45843 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-03-04 | 2026-04-07 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-05-08 |  | 2026-06-13 |  | Tower B | Sub Structure | B1 | MEP | Electrical 1st Fixes
45872 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-03-04 | 2026-03-20 | HVAC Ducting/ Fan Installations | 100 | 0 |  | 2026-05-08 |  | 2026-05-26 |  | Tower B | Super Structure | GF | MEP | HVAC Ducting
45905 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-03-04 | 2026-03-11 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-05-08 |  | 2026-05-16 |  | Tower B | Super Structure |  | MEP | FPS 2nd Fix - MEP & Finishes
45906 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-04 | 2026-03-11 | FAPA Device Fixing | 100 | 0 |  | 2026-05-08 |  | 2026-05-16 |  | Tower B | Super Structure
45906 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-04 | 2026-03-11 | FAPA Device Fixing | 100 | 0 |  | 2026-05-08 |  | 2026-05-16 |  | Tower B | Super Structure
45906 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-04 | 2026-03-11 | FAPA Device Fixing | 100 | 0 |  | 2026-05-08 |  | 2026-05-16 |  | Tower B | Super Structure
45906 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-04 | 2026-03-11 | FAPA Device Fixing | 100 | 0 |  | 2026-05-08 |  | 2026-05-16 |  | Tower B | Super Structure
47648 |  | Complete |  | 2026-05-08 | 2026-05-25 | Slab_NTA | 100 | 100 |  | 2026-05-08 | 2026-05-08 | 2026-05-25 | 2026-05-25
47648 |  | Complete |  | 2026-05-08 | 2026-05-25 | Slab_NTA | 100 | 100 |  | 2026-05-08 | 2026-05-08 | 2026-05-25 | 2026-05-25 |  |  |  | RCC Sub Structure | RCC Works - Slab
8852 | T-14-12th Floor Common Area | Not Ready | Door-Shaft | 2026-04-15 | 2026-04-28 | Door-Shaft | 100 | 0 |  | 2026-05-09 |  | 2026-05-20
8860 | T-14-Lift | Not Ready | PARAPET | 2026-04-18 | 2026-06-24 | Parapets | 100 | 0 |  | 2026-05-09 |  | 2026-07-16
9737 | T-16-5th Floor Common Area | Not Ready | Window-Open Area | 2026-05-26 | 2026-06-02 | Window-Open Area | 100 | 0 |  | 2026-05-09 |  | 2026-05-16
11511 | T-19- Elevation A | Not Ready |  | 2026-05-24 | 2026-08-13 | Elevation-A | 100 | 0 |  | 2026-05-09 |  | 2026-07-29
11765 | T-18-3rd Floor Common Area | Not Ready | Window-Open Area | 2026-07-14 | 2026-07-21 | Window-Open Area | 100 | 0 |  | 2026-05-09 |  | 2026-05-16
41655 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-04-17 | 2026-04-25 | HVAC Ducting | 100 | 0 |  | 2026-05-09 |  | 2026-05-18 |  | Tower A | Super Structure | L44 | MEP | HVAC Ducting
41668 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-04-17 | 2026-04-23 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-05-09 |  | 2026-05-15 |  | Tower A | Super Structure | L45 | MEP | FPS 1st Fix - MEP & Finishes
41669 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-04-17 | 2026-04-21 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-05-09 |  | 2026-05-13 |  | Tower A | Super Structure | L45 | MEP | Electrical 1st Fixes
42215 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-05-12 | 2026-05-16 | False Ceiling | 100 | 0 |  | 2026-05-09 |  | 2026-05-14 |  | Tower A | Super Structure | L7 | Finishes | False Ceiling
42233 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-05-12 | 2026-05-16 | False Ceiling | 100 | 0 |  | 2026-05-09 |  | 2026-05-14 |  | Tower A | Super Structure | L8 | Finishes | False Ceiling
42251 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-05-12 | 2026-05-16 | False Ceiling | 100 | 0 |  | 2026-05-09 |  | 2026-05-14 |  | Tower A | Super Structure | L9 | Finishes | False Ceiling
43305 |  | Not Committed |  | 2026-04-16 | 2026-07-31 | Finishes after 1st Fix | 100 | 0 |  | 2026-05-09 |  | 2026-08-27
43306 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-04-16 | 2026-05-09 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-05-09 |  | 2026-06-02 |  | Tower A | Super Structure | L68 | Finishes | Blockwork
43394 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-04-16 | 2026-04-27 | Cement Plastering in wet areas | 100 | 0 |  | 2026-05-09 |  | 2026-05-20 |  | Tower A | Super Structure | L73
43986 | Tower A - Super Structure - Finishes & MEP - L25 to L35 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-06-10 | 2026-06-20 | Staircase cabling | 100 | 0 |  | 2026-05-09 |  | 2026-05-21 |  | Tower A | Super Structure | L25
9219 | T-15-5th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-05-09 | 2026-06-10 | 2nd Coat Painting | 100 | 0 |  | 2026-05-10 |  | 2026-06-13
10153 | T-21-1st Floor Common Area | Not Ready | Window-Open Area | 2026-06-07 | 2026-06-15 | Window-Open Area | 100 | 0 |  | 2026-05-10 |  | 2026-05-17
10672 | T-20-1st Floor Common Area | Not Ready | Door-Shaft | 2026-06-05 | 2026-06-18 | Door-Shaft | 100 | 0 |  | 2026-05-10 |  | 2026-05-24
10700 | T-20-2nd Floor Common Area | Not Ready | 1st Coat Painting | 2026-06-04 | 2026-06-26 | 1st Coat Painting | 100 | 0 |  | 2026-05-10 |  | 2026-06-02
11672 | T-18-GF Flat Area | Not Ready | 2nd Coat Painting | 2026-08-10 | 2026-10-16 | 2nd Coat Painting | 100 | 0 |  | 2026-05-10 |  | 2026-07-16
8565 | T-14-1st Floor Common Area | Not Ready | Putty | 2026-04-04 | 2026-05-13 | Putty | 100 | 0 |  | 2026-05-11 |  | 2026-06-18
9790 | T-16-7th Floor Common Area | Not Ready | 1st Coat Painting | 2026-05-28 | 2026-06-18 | 1st Coat Painting | 100 | 0 |  | 2026-05-11 |  | 2026-06-04
9920 | T-16-Staircase 1 | Not Ready |  | 2026-05-29 | 2026-06-09 | TF-12F | 100 | 0 |  | 2026-05-11 |  | 2026-05-23
10753 | T-20-4th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-06-04 | 2026-07-07 | 2nd Coat Painting | 100 | 0 |  | 2026-05-11 |  | 2026-06-12
11271 | T-19-4th Floor Common Area | Not Ready | Window-Open Area | 2026-05-26 | 2026-06-03 | Window-Open Area | 100 | 0 |  | 2026-05-11 |  | 2026-05-18
11401 | T-19-9th Floor Common Area | Not Ready | Window-Open Area | 2026-06-01 | 2026-06-08 | Window-Open Area | 100 | 0 |  | 2026-05-11 |  | 2026-05-17
11915 | T-18-9th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-07-27 | 2026-10-01 | 2nd Coat Painting | 100 | 0 |  | 2026-05-11 |  | 2026-07-14
40550 | Tower A - Super Structure - Finishes & MEP - L76 to L77 | Not Ready | Gypsum Plastering Works | 2026-04-17 | 2026-05-05 | L76-77 | 100 | 0 |  | 2026-05-11 |  | 2026-05-28 |  | Tower A | Super Structure | L76 | Finishes | Gypsum Plastering Works
40550 | Tower A - Super Structure - Finishes & MEP - L76 to L77 | Not Ready | Gypsum Plastering Works | 2026-04-17 | 2026-05-05 | L76-77 | 100 | 0 |  | 2026-05-11 |  | 2026-05-28 |  | Tower A | Super Structure | L76
40937 | Tower A - Super Structure - Finishes & MEP - L65 to Terrace | Not Ready |  | 2026-04-06 | 2026-04-28 | Electrical Rising Mains | 100 | 0 |  | 2026-05-11 |  | 2026-06-04 |  | Tower A | Super Structure | L65
41522 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-18 | 2026-04-24 | Final Painting | 100 | 0 |  | 2026-05-11 |  | 2026-05-16 |  | Tower A | Super Structure | L35 | Finishes | Final Painting
41522 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-18 | 2026-04-24 | Final Painting | 100 | 0 |  | 2026-05-11 |  | 2026-05-16 |  | Tower A | Super Structure | L35 | Finishes | Final Painting
41522 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-18 | 2026-04-24 | Final Painting | 100 | 0 |  | 2026-05-11 |  | 2026-05-16 |  | Tower A | Super Structure | L35 | Finishes | Final Painting
41611 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-04-18 | 2026-04-27 | False Ceiling | 100 | 0 |  | 2026-05-11 |  | 2026-05-19 |  | Tower A | Super Structure | L41 | Finishes | False Ceiling
44599 |  | Not Ready | MEP fix & Finishes | 2026-05-13 | 2026-05-18 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-05-11 |  | 2026-05-15
44599 |  | Not Ready | MEP fix & Finishes | 2026-05-13 | 2026-05-18 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-05-11 |  | 2026-05-15
44599 |  | Not Ready | MEP fix & Finishes | 2026-05-13 | 2026-05-18 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-05-11 |  | 2026-05-15
44633 |  | Not Ready | MEP fix & Finishes | 2026-05-13 | 2026-07-04 | Softscape Works | 100 | 0 |  | 2026-05-11 |  | 2026-07-02
45301 |  | Not Ready |  | 2026-03-02 | 2026-03-13 | L17-18 | 100 | 0 |  | 2026-05-11 |  | 2026-05-26
45301 |  | Not Ready |  | 2026-03-02 | 2026-03-13 | L17-18 | 100 | 0 |  | 2026-05-11 |  | 2026-05-26 |  |  |  |  | Finishes | Gypsum Plastering Works
45302 | Tower B - Super Structure - Core & Outer Slab L17-18 | Not Ready | RCC Works - Vertical | 2026-03-02 | 2026-03-11 | Outer Columns_TA | 100 | 0 |  | 2026-05-11 |  | 2026-05-22 |  | Tower B | Super Structure | L17 | RCC Sub Structure | RCC Works - Vertical
45461 |  | Not Committed |  | 2026-03-02 | 2026-04-02 | L14-15 | 100 | 0 |  | 2026-05-11 |  | 2026-06-12
45461 |  | Not Committed |  | 2026-03-02 | 2026-04-02 | L14-15 | 100 | 0 |  | 2026-05-11 |  | 2026-06-12 |  |  |  |  | Finishes | Gypsum Plastering Works
45462 | Tower B - Super Structure - Finishes & MEP - L14 to L15 | Not Ready | Partition Wall-Blockwork | 2026-03-02 | 2026-03-19 | De-shuttering & Area clearance | 100 | 0 |  | 2026-05-11 |  | 2026-05-29 |  | Tower B | Super Structure | L14
45934 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2026-03-06 | 2026-03-14 | Final Painting | 100 | 0 |  | 2026-05-11 |  | 2026-05-20 |  | Tower B | Super Structure |  | Finishes | Final Painting
45934 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2026-03-06 | 2026-03-14 | Final Painting | 100 | 0 |  | 2026-05-11 |  | 2026-05-20 |  | Tower B | Super Structure |  | Finishes | Final Painting
45934 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2026-03-06 | 2026-03-14 | Final Painting | 100 | 0 |  | 2026-05-11 |  | 2026-05-20 |  | Tower B | Super Structure |  | Finishes | Final Painting
8673 | T-14-5th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-04-08 | 2026-05-12 | 2nd Coat Painting | 100 | 0 |  | 2026-05-12 |  | 2026-06-14
8802 | T-14-11th Floor Common Area | Not Ready | 1st Coat Painting | 2026-04-14 | 2026-05-07 | 1st Coat Painting | 100 | 0 |  | 2026-05-12 |  | 2026-06-04
11426 | T-19-11th Floor Common Area | Not Ready | Door-Shaft | 2026-06-04 | 2026-06-17 | Door-Shaft | 100 | 0 |  | 2026-05-12 |  | 2026-05-25
41553 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-04-20 | 2026-04-25 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-05-12 |  | 2026-05-18 |  | Tower A | Super Structure | L37 | MEP | Electrical
41568 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-04-20 | 2026-04-23 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-05-12 |  | 2026-05-15 |  | Tower A | Super Structure | L38
41580 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-04-20 | 2026-04-23 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-05-12 |  | 2026-05-15 |  | Tower A | Super Structure | L39 | MEP | FPS 2nd Fix - MEP & Finishes
41581 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-04-20 | 2026-04-25 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-05-12 |  | 2026-05-18 |  | Tower A | Super Structure | L39 | MEP | Electrical 2nd Fix - MEP & Finishes
41582 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-20 | 2026-04-28 | FAPA Device Fixing | 100 | 0 |  | 2026-05-12 |  | 2026-05-20 |  | Tower A | Super Structure | L39
41582 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-20 | 2026-04-28 | FAPA Device Fixing | 100 | 0 |  | 2026-05-12 |  | 2026-05-20 |  | Tower A | Super Structure | L39
41582 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-20 | 2026-04-28 | FAPA Device Fixing | 100 | 0 |  | 2026-05-12 |  | 2026-05-20 |  | Tower A | Super Structure | L39
41582 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-20 | 2026-04-28 | FAPA Device Fixing | 100 | 0 |  | 2026-05-12 |  | 2026-05-20 |  | Tower A | Super Structure | L39
41583 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-04-20 | 2026-04-23 | HVAC Grill Fixing | 100 | 0 |  | 2026-05-12 |  | 2026-05-15 |  | Tower A | Super Structure | L39 | MEP | HVAC Grill Fixing
41642 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-04-20 | 2026-05-02 | Flooring & Dado | 100 | 0 |  | 2026-05-12 |  | 2026-05-23 |  | Tower A | Super Structure | L43 | Finishes | Flooring & Dado
42267 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-05-14 | 2026-05-16 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-05-12 |  | 2026-05-14 |  | Tower A | Super Structure | L10 | MEP | FPS 2nd Fix - MEP & Finishes
42268 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-05-14 | 2026-05-16 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-05-12 |  | 2026-05-14 |  | Tower A | Super Structure | L10 | MEP | Electrical 2nd Fix - MEP & Finishes
42285 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-05-14 | 2026-05-16 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-05-12 |  | 2026-05-14 |  | Tower A | Super Structure | L11 | MEP | FPS 2nd Fix - MEP & Finishes
42286 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-05-14 | 2026-05-16 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-05-12 |  | 2026-05-14 |  | Tower A | Super Structure | L11 | MEP | Electrical 2nd Fix - MEP & Finishes
42303 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-05-14 | 2026-05-16 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-05-12 |  | 2026-05-14 |  | Tower A | Super Structure | L12 | MEP | FPS 2nd Fix - MEP & Finishes
42304 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-05-14 | 2026-05-16 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-05-12 |  | 2026-05-14 |  | Tower A | Super Structure | L12 | MEP | Electrical 2nd Fix - MEP & Finishes
42319 |  | Not Committed |  | 2026-05-14 | 2026-06-05 | MEP final fix & Finishes | 100 | 0 |  | 2026-05-12 |  | 2026-06-03
42320 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-05-14 | 2026-05-19 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-05-12 |  | 2026-05-16 |  | Tower A | Super Structure | L13 | Finishes | Door & Window Fixing
42337 |  | Not Committed |  | 2026-05-14 | 2026-06-05 | MEP final fix & Finishes | 100 | 0 |  | 2026-05-12 |  | 2026-06-03
42338 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-05-14 | 2026-05-19 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-05-12 |  | 2026-05-16 |  | Tower A | Super Structure | L14 | Finishes | Door & Window Fixing
42351 |  | Not Committed |  | 2026-05-14 | 2026-06-05 | MEP final fix & Finishes | 100 | 0 |  | 2026-05-12 |  | 2026-06-03
42352 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-05-14 | 2026-05-19 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-05-12 |  | 2026-05-16 |  | Tower A | Super Structure | L15 | Finishes | Door & Window Fixing
43323 |  | Not Committed |  | 2026-04-18 | 2026-06-17 | Finishes after 1st Fix | 100 | 0 |  | 2026-05-12 |  | 2026-06-30
43324 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-04-18 | 2026-05-12 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-05-12 |  | 2026-06-04 |  | Tower A | Super Structure | L69 | Finishes | Blockwork
46745 |  | Not Committed |  | 2026-03-07 | 2027-04-06 | L12-13 | 100 | 0 |  | 2026-05-12 |  | 2027-06-02
46745 |  | Not Committed |  | 2026-03-07 | 2027-04-06 | L12-13 | 100 | 0 |  | 2026-05-12 |  | 2027-06-02 |  |  |  |  | Finishes | Gypsum Plastering Works
46746 |  | Not Committed |  | 2026-03-07 | 2026-04-13 | MEP 1st Fixes | 100 | 0 |  | 2026-05-12 |  | 2026-06-19
46747 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-03-07 | 2026-03-14 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-05-12 |  | 2026-05-20 |  | Tower B | Super Structure | L12 | MEP | FPS 1st Fix - MEP & Finishes
46748 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-03-07 | 2026-03-12 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-05-12 |  | 2026-05-18 |  | Tower B | Super Structure | L12 | MEP | Electrical 1st Fixes
46749 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-03-07 | 2026-03-14 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-05-12 |  | 2026-05-20 |  | Tower B | Super Structure | L12
8858 | T-14-Lift | Not Ready | LMR ROOM | 2026-04-21 | 2026-06-26 | Lift Machine Rooms | 100 | 0 |  | 2026-05-13 |  | 2026-07-17
41670 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-04-21 | 2026-04-23 | FAPA Cabling | 100 | 0 |  | 2026-05-13 |  | 2026-05-15 |  | Tower A | Super Structure | L45
45459 | Tower B - Super Structure - Finishes & MEP - L13 to L14 | Not Ready | Partition Wall-Blockwork | 2026-03-09 | 2026-03-16 | Partition Walls | 100 | 0 |  | 2026-05-13 |  | 2026-05-21 |  | Tower B | Super Structure | L13
11460 | T-19-Lift | Not Ready | PARAPET | 2026-06-09 | 2026-08-13 | Parapets | 100 | 0 |  | 2026-05-14 |  | 2026-07-21
40083 | Tower A - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2026-04-21 | 2026-05-02 | Guide Rail Installation by rising platform (only car guide rails) | 100 | 0 |  | 2026-05-14 |  | 2026-05-26 |  | Tower A | Super Structure
41538 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-22 | 2026-04-28 | Final Painting | 100 | 0 |  | 2026-05-14 |  | 2026-05-20 |  | Tower A | Super Structure | L36 | Finishes | Final Painting
41538 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-22 | 2026-04-28 | Final Painting | 100 | 0 |  | 2026-05-14 |  | 2026-05-20 |  | Tower A | Super Structure | L36 | Finishes | Final Painting
41538 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-22 | 2026-04-28 | Final Painting | 100 | 0 |  | 2026-05-14 |  | 2026-05-20 |  | Tower A | Super Structure | L36 | Finishes | Final Painting
41627 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-04-22 | 2026-04-30 | False Ceiling | 100 | 0 |  | 2026-05-14 |  | 2026-05-22 |  | Tower A | Super Structure | L42 | Finishes | False Ceiling
42171 |  | Not Committed |  | 2026-04-21 | 2026-07-10 | Finishes after 1st Fix | 100 | 0 |  | 2026-05-14 |  | 2026-07-08
42172 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-04-21 | 2026-05-14 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-05-14 |  | 2026-06-06 |  | Tower A | Super Structure | L75 | Finishes | Blockwork
43341 |  | Not Committed |  | 2026-04-21 | 2026-06-23 | Finishes after 1st Fix | 100 | 0 |  | 2026-05-14 |  | 2026-07-06
43342 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-04-21 | 2026-05-14 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-05-14 |  | 2026-06-06 |  | Tower A | Super Structure | L70 | Finishes | Blockwork
43413 |  | Not Committed |  | 2026-04-21 | 2026-07-04 | Finishes after 1st Fix | 100 | 0 |  | 2026-05-14 |  | 2026-07-02
43414 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-04-21 | 2026-05-14 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-05-14 |  | 2026-06-06 |  | Tower A | Super Structure | L74 | Finishes | Blockwork
45768 |  | Not Committed |  | 2026-03-10 | 2027-02-20 | B3 Level | 100 | 0 |  | 2026-05-14 |  | 2027-05-03
45783 |  | Not Committed |  | 2026-03-10 | 2026-06-06 | Floor Area | 100 | 0 |  | 2026-05-14 |  | 2026-08-19
45784 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | Ceiling Painting/ PT Marking - MEP & Finishes | 2026-03-10 | 2026-03-14 | Ceiling Painting/ PT Marking | 100 | 0 |  | 2026-05-14 |  | 2026-05-20 |  | Tower B | Sub Structure | B3 | Finishes | Ceiling Painting/ PT Marking
45790 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | Hume Pipe Laying & Alied Ground Works - MEP & Finishes | 2026-03-10 | 2026-04-13 | Hume pipe laying & allied ground works | 100 | 0 |  | 2026-05-14 |  | 2026-06-19 |  | Tower B | Sub Structure | B3
45814 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-03-10 | 2026-04-01 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-05-14 |  | 2026-06-08 |  | Tower B | Sub Structure | B2 | MEP | FPS 1st Fix - MEP & Finishes
45815 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-03-10 | 2026-04-01 | PHE 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-05-14 |  | 2026-06-08 |  | Tower B | Sub Structure | B2
45816 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-03-10 | 2026-03-26 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-05-14 |  | 2026-06-02 |  | Tower B | Sub Structure | B2 | MEP | Electrical 1st Fixes
45845 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-03-10 | 2026-03-26 | HVAC Ducting/ Fan Installations | 100 | 0 |  | 2026-05-14 |  | 2026-06-02 |  | Tower B | Sub Structure | B1 | MEP | HVAC Ducting
45871 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-03-10 | 2026-03-20 | FAPA Cabling | 100 | 0 |  | 2026-05-14 |  | 2026-05-26 |  | Tower B | Super Structure | GF
47651 |  | Complete |  | 2026-05-14 | 2026-06-01 | Slab_NTA | 100 | 100 |  | 2026-05-14 | 2026-05-14 | 2026-06-01 | 2026-06-01
47651 |  | Complete |  | 2026-05-14 | 2026-06-01 | Slab_NTA | 100 | 100 |  | 2026-05-14 | 2026-05-14 | 2026-06-01 | 2026-06-01 |  |  |  | RCC Sub Structure | RCC Works - Slab
8859 | T-14-Lift | Not Ready | STAIRCASE HR | 2026-04-25 | 2026-06-30 | Staircase Headrooms | 100 | 0 |  | 2026-05-15 |  | 2026-07-19
8865 | T-14-Lift Lobby | Not Ready |  | 2026-04-15 | 2026-05-02 | 12F | 100 | 0 |  | 2026-05-15 |  | 2026-05-31
9072 | T-15-GF Flat Area | Not Ready | 2nd Coat Painting | 2026-06-08 | 2026-08-13 | 2nd Coat Painting | 100 | 0 |  | 2026-05-15 |  | 2026-07-19
9297 | T-15-8th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-05-20 | 2026-06-22 | 2nd Coat Painting | 100 | 0 |  | 2026-05-15 |  | 2026-06-17
11973 | T-18-11th Floor Common Area | Not Ready | Window-Open Area | 2026-07-30 | 2026-08-06 | Window-Open Area | 100 | 0 |  | 2026-05-15 |  | 2026-05-22
41569 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-04-23 | 2026-04-29 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-05-15 |  | 2026-05-21 |  | Tower A | Super Structure | L38 | MEP | Electrical
41584 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-04-23 | 2026-04-27 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-05-15 |  | 2026-05-19 |  | Tower A | Super Structure | L39
41596 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-04-23 | 2026-04-27 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-05-15 |  | 2026-05-19 |  | Tower A | Super Structure | L40 | MEP | FPS 2nd Fix - MEP & Finishes
41597 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-04-23 | 2026-04-29 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-05-15 |  | 2026-05-21 |  | Tower A | Super Structure | L40 | MEP | Electrical 2nd Fix - MEP & Finishes
41598 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-23 | 2026-05-02 | FAPA Device Fixing | 100 | 0 |  | 2026-05-15 |  | 2026-05-23 |  | Tower A | Super Structure | L40
41598 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-23 | 2026-05-02 | FAPA Device Fixing | 100 | 0 |  | 2026-05-15 |  | 2026-05-23 |  | Tower A | Super Structure | L40
41598 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-23 | 2026-05-02 | FAPA Device Fixing | 100 | 0 |  | 2026-05-15 |  | 2026-05-23 |  | Tower A | Super Structure | L40
41598 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-23 | 2026-05-02 | FAPA Device Fixing | 100 | 0 |  | 2026-05-15 |  | 2026-05-23 |  | Tower A | Super Structure | L40
41599 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-04-23 | 2026-04-27 | HVAC Grill Fixing | 100 | 0 |  | 2026-05-15 |  | 2026-05-19 |  | Tower A | Super Structure | L40 | MEP | HVAC Grill Fixing
41671 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-04-23 | 2026-05-02 | HVAC Ducting | 100 | 0 |  | 2026-05-15 |  | 2026-05-23 |  | Tower A | Super Structure | L45 | MEP | HVAC Ducting
41684 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-04-23 | 2026-04-29 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-05-15 |  | 2026-05-21 |  | Tower A | Super Structure | L46 | MEP | FPS 1st Fix - MEP & Finishes
41685 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-04-23 | 2026-04-27 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-05-15 |  | 2026-05-19 |  | Tower A | Super Structure | L46 | MEP | Electrical 1st Fixes
42216 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-05-18 | 2026-05-20 | PHE Final Fixes | 100 | 0 |  | 2026-05-15 |  | 2026-05-18 |  | Tower A | Super Structure | L7
42234 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-05-18 | 2026-05-20 | PHE Final Fixes | 100 | 0 |  | 2026-05-15 |  | 2026-05-18 |  | Tower A | Super Structure | L8
42252 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-05-18 | 2026-05-20 | PHE Final Fixes | 100 | 0 |  | 2026-05-15 |  | 2026-05-18 |  | Tower A | Super Structure | L9
42269 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-05-18 | 2026-05-22 | False Ceiling | 100 | 0 |  | 2026-05-15 |  | 2026-05-20 |  | Tower A | Super Structure | L10 | Finishes | False Ceiling
42287 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-05-18 | 2026-05-22 | False Ceiling | 100 | 0 |  | 2026-05-15 |  | 2026-05-20 |  | Tower A | Super Structure | L11 | Finishes | False Ceiling
42305 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-05-18 | 2026-05-22 | False Ceiling | 100 | 0 |  | 2026-05-15 |  | 2026-05-20 |  | Tower A | Super Structure | L12 | Finishes | False Ceiling
44616 |  | Not Ready | MEP fix & Finishes | 2026-05-18 | 2026-05-29 | Final Painting | 100 | 0 |  | 2026-05-15 |  | 2026-05-26 |  |  |  |  | Finishes | Final Painting
44616 |  | Not Ready | MEP fix & Finishes | 2026-05-18 | 2026-05-29 | Final Painting | 100 | 0 |  | 2026-05-15 |  | 2026-05-26 |  |  |  |  | Finishes | Final Painting
44616 |  | Not Ready | MEP fix & Finishes | 2026-05-18 | 2026-05-29 | Final Painting | 100 | 0 |  | 2026-05-15 |  | 2026-05-26 |  |  |  |  | Finishes | Final Painting
44621 |  | Not Ready | MEP fix & Finishes | 2026-05-18 | 2026-05-25 | HVAC Fans fixing | 100 | 0 |  | 2026-05-15 |  | 2026-05-22 |  |  |  |  | MEP | HVAC Grill Fixing
44621 |  | Not Ready | MEP fix & Finishes | 2026-05-18 | 2026-05-25 | HVAC Fans fixing | 100 | 0 |  | 2026-05-15 |  | 2026-05-22 |  |  |  |  | MEP | HVAC Grill Fixing
44626 |  | Not Ready | MEP fix & Finishes | 2026-05-18 | 2026-05-25 | FAPA Device Fixing | 100 | 0 |  | 2026-05-15 |  | 2026-05-22
44626 |  | Not Ready | MEP fix & Finishes | 2026-05-18 | 2026-05-25 | FAPA Device Fixing | 100 | 0 |  | 2026-05-15 |  | 2026-05-22
44626 |  | Not Ready | MEP fix & Finishes | 2026-05-18 | 2026-05-25 | FAPA Device Fixing | 100 | 0 |  | 2026-05-15 |  | 2026-05-22
44626 |  | Not Ready | MEP fix & Finishes | 2026-05-18 | 2026-05-25 | FAPA Device Fixing | 100 | 0 |  | 2026-05-15 |  | 2026-05-22
45737 | Tower B - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2026-03-11 | 2026-04-14 | Shaft Cabling in Electrical & ELV Shaft | 100 | 0 |  | 2026-05-15 |  | 2026-06-20 |  | Tower B | Super Structure | L7
8827 | T-14-11th Floor Common Area | Not Ready | Window-Open Area | 2026-04-17 | 2026-04-25 | Window-Open Area | 100 | 0 |  | 2026-05-16 |  | 2026-05-22
9348 | T-15-11th Floor Common Area | Not Ready | 1st Coat Painting | 2026-05-20 | 2026-06-10 | 1st Coat Painting | 100 | 0 |  | 2026-05-16 |  | 2026-06-09
9710 | T-16-4th Floor Common Area | Not Ready | Door-Shaft | 2026-06-03 | 2026-06-16 | Door-Shaft | 100 | 0 |  | 2026-05-16 |  | 2026-05-27
9765 | T-16-6th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-06-02 | 2026-07-05 | 2nd Coat Painting | 100 | 0 |  | 2026-05-16 |  | 2026-06-19
10949 | T-20-Lift Lobby | Not Ready |  | 2026-06-11 | 2026-06-27 | 08F | 100 | 0 |  | 2026-05-16 |  | 2026-06-02
11458 | T-19-Lift | Not Ready | LMR ROOM | 2026-06-11 | 2026-08-17 | Lift Machine Rooms | 100 | 0 |  | 2026-05-16 |  | 2026-07-22
11738 | T-18-2nd Floor Common Area | Not Ready | Door-Shaft | 2026-07-22 | 2026-08-04 | Door-Shaft | 100 | 0 |  | 2026-05-16 |  | 2026-05-27
42188 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-04-23 | 2026-05-05 | Cement Plastering in wet areas | 100 | 0 |  | 2026-05-16 |  | 2026-05-28 |  | Tower A | Super Structure | L76
43271 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-04-23 | 2026-04-30 | Door & Window Frame work | 100 | 0 |  | 2026-05-16 |  | 2026-05-23 |  | Tower A | Super Structure | L66 | Finishes | Door & Window Frame work
43359 |  | Not Committed |  | 2026-04-23 | 2026-06-29 | Finishes after 1st Fix | 100 | 0 |  | 2026-05-16 |  | 2026-07-11
43360 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-04-23 | 2026-05-16 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-05-16 |  | 2026-06-09 |  | Tower A | Super Structure | L71 | Finishes | Blockwork
44576 | NTA_Zone 2 - Super Structure - P3 to P4 | Not Ready | Finishes (Lobby & Floor Area) | 2025-09-24 | 2025-10-30 | Staircase Finishes | 100 | 0 |  | 2026-05-16 |  | 2026-06-20 |  | NTA_Zone 2 | Super Structure
44576 | NTA_Zone 2 - Super Structure - P3 to P4 | Not Ready | Finishes (Lobby & Floor Area) | 2025-09-24 | 2025-10-30 | Staircase Finishes | 100 | 0 |  | 2026-05-16 |  | 2026-06-20 |  | NTA_Zone 2 | Super Structure
44579 | NTA_Zone 2 - Super Structure - P4 to P5 | Not Ready | Finishes (Lobby & Floor Area) | 2025-10-13 | 2025-11-17 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2026-05-16 |  | 2026-06-20 |  | NTA_Zone 2 | Super Structure
44579 | NTA_Zone 2 - Super Structure - P4 to P5 | Not Ready | Finishes (Lobby & Floor Area) | 2025-10-13 | 2025-11-17 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2026-05-16 |  | 2026-06-20 |  | NTA_Zone 2 | Super Structure
45907 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2026-03-12 | 2026-03-20 | Final Painting | 100 | 0 |  | 2026-05-16 |  | 2026-05-26 |  | Tower B | Super Structure |  | Finishes | Final Painting
45907 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2026-03-12 | 2026-03-20 | Final Painting | 100 | 0 |  | 2026-05-16 |  | 2026-05-26 |  | Tower B | Super Structure |  | Finishes | Final Painting
45907 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2026-03-12 | 2026-03-20 | Final Painting | 100 | 0 |  | 2026-05-16 |  | 2026-05-26 |  | Tower B | Super Structure |  | Finishes | Final Painting
9405 | T-15-Staircase 1 | Not Ready |  | 2026-05-26 | 2026-06-06 | 08F-07F | 100 | 0 |  | 2026-05-17 |  | 2026-05-26
9419 | T-15-Staircase 2 | Not Ready |  | 2026-05-26 | 2026-06-06 | 09F-08F | 100 | 0 |  | 2026-05-17 |  | 2026-05-26
9738 | T-16-5th Floor Common Area | Not Ready | 1st Coat Painting | 2026-06-02 | 2026-06-24 | 1st Coat Painting | 100 | 0 |  | 2026-05-17 |  | 2026-06-06
9815 | T-16-8th Floor Common Area | Not Ready | Window-Open Area | 2026-06-05 | 2026-06-13 | Window-Open Area | 100 | 0 |  | 2026-05-17 |  | 2026-05-24
11351 | T-19-7th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-06-03 | 2026-07-06 | 2nd Coat Painting | 100 | 0 |  | 2026-05-17 |  | 2026-06-18
11689 | T-18-GF Common Area | Not Ready | 2nd Coat Painting | 2026-08-19 | 2026-11-05 | 2nd Coat Painting | 100 | 0 |  | 2026-05-17 |  | 2026-08-02
11766 | T-18-3rd Floor Common Area | Not Ready | 1st Coat Painting | 2026-07-21 | 2026-08-12 | 1st Coat Painting | 100 | 0 |  | 2026-05-17 |  | 2026-06-07
12005 | T-18-Staircase 1 | Not Ready |  | 2026-07-28 | 2026-08-07 | 08F-07F | 100 | 0 |  | 2026-05-17 |  | 2026-05-29
12019 | T-18-Staircase 2 | Not Ready |  | 2026-07-28 | 2026-08-07 | 09F-08F | 100 | 0 |  | 2026-05-17 |  | 2026-05-29
8526 | T-14-GF Flat Area | Not Ready | 2nd Coat Painting | 2026-05-10 | 2026-07-15 | 2nd Coat Painting | 100 | 0 |  | 2026-05-18 |  | 2026-07-25
8751 | T-14-8th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-04-20 | 2026-05-23 | 2nd Coat Painting | 100 | 0 |  | 2026-05-18 |  | 2026-06-21
8881 | T-14-Staircase 1 | Not Ready |  | 2026-04-15 | 2026-04-26 | 12F-11F | 100 | 0 |  | 2026-05-18 |  | 2026-05-27
8895 | T-14-Staircase 2 | Not Ready |  | 2026-04-15 | 2026-04-26 | TF-12F | 100 | 0 |  | 2026-05-18 |  | 2026-05-27
9165 | T-15-3rd Floor Common Area | Not Ready | Window-Open Area | 2026-05-12 | 2026-05-20 | Window-Open Area | 100 | 0 |  | 2026-05-18 |  | 2026-05-25
9653 | T-16-2nd Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-06-22 | 2026-09-12 | 2nd Coat Painting | 100 | 0 |  | 2026-05-18 |  | 2026-08-09
10154 | T-21-1st Floor Common Area | Not Ready | 1st Coat Painting | 2026-06-15 | 2026-07-07 | 1st Coat Painting | 100 | 0 |  | 2026-05-18 |  | 2026-06-11
10430 | T-21-Lift Lobby | Not Ready |  | 2026-06-16 | 2026-07-02 | 07F | 100 | 0 |  | 2026-05-18 |  | 2026-06-02
10448 | T-21-Staircase 1 | Not Ready |  | 2026-06-10 | 2026-06-21 | 05F-04F | 100 | 0 |  | 2026-05-18 |  | 2026-05-27
10462 | T-21-Staircase 2 | Not Ready |  | 2026-06-10 | 2026-06-21 | 06F-05F | 100 | 0 |  | 2026-05-18 |  | 2026-05-27
11402 | T-19-9th Floor Common Area | Not Ready | 1st Coat Painting | 2026-06-08 | 2026-06-30 | 1st Coat Painting | 100 | 0 |  | 2026-05-18 |  | 2026-06-09
11482 | T-19-Staircase 1 | Not Ready |  | 2026-05-29 | 2026-06-09 | 11F-10F | 100 | 0 |  | 2026-05-18 |  | 2026-05-29
11496 | T-19-Staircase 2 | Not Ready |  | 2026-05-29 | 2026-06-09 | 12F-11F | 100 | 0 |  | 2026-05-18 |  | 2026-05-29
11988 | T-18-Lift Lobby | Not Ready |  | 2026-08-02 | 2026-08-19 | 09F | 100 | 0 |  | 2026-05-18 |  | 2026-06-01
41554 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-25 | 2026-05-02 | Final Painting | 100 | 0 |  | 2026-05-18 |  | 2026-05-23 |  | Tower A | Super Structure | L37 | Finishes | Final Painting
41554 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-25 | 2026-05-02 | Final Painting | 100 | 0 |  | 2026-05-18 |  | 2026-05-23 |  | Tower A | Super Structure | L37 | Finishes | Final Painting
41554 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-25 | 2026-05-02 | Final Painting | 100 | 0 |  | 2026-05-18 |  | 2026-05-23 |  | Tower A | Super Structure | L37 | Finishes | Final Painting
41643 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-04-25 | 2026-05-05 | False Ceiling | 100 | 0 |  | 2026-05-18 |  | 2026-05-26 |  | Tower A | Super Structure | L43 | Finishes | False Ceiling
41658 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-04-25 | 2026-05-08 | Flooring & Dado | 100 | 0 |  | 2026-05-18 |  | 2026-05-30 |  | Tower A | Super Structure | L44 | Finishes | Flooring & Dado
42321 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-05-20 | 2026-05-22 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-05-18 |  | 2026-05-20 |  | Tower A | Super Structure | L13 | MEP | FPS 2nd Fix - MEP & Finishes
42322 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-05-20 | 2026-05-22 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-05-18 |  | 2026-05-20 |  | Tower A | Super Structure | L13 | MEP | Electrical 2nd Fix - MEP & Finishes
42339 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-05-20 | 2026-05-22 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-05-18 |  | 2026-05-20 |  | Tower A | Super Structure | L14 | MEP | FPS 2nd Fix - MEP & Finishes
42340 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-05-20 | 2026-05-22 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-05-18 |  | 2026-05-20 |  | Tower A | Super Structure | L14 | MEP | Electrical 2nd Fix - MEP & Finishes
42353 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-05-20 | 2026-05-22 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-05-18 |  | 2026-05-20 |  | Tower A | Super Structure | L15 | MEP | FPS 2nd Fix - MEP & Finishes
42354 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-05-20 | 2026-05-22 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-05-18 |  | 2026-05-20 |  | Tower A | Super Structure | L15 | MEP | Electrical 2nd Fix - MEP & Finishes
42373 |  | Not Committed |  | 2026-05-20 | 2026-06-11 | MEP final fix & Finishes | 100 | 0 |  | 2026-05-18 |  | 2026-06-09
42374 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-05-20 | 2026-05-25 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-05-18 |  | 2026-05-22 |  | Tower A | Super Structure | L16 | Finishes | Door & Window Fixing
42391 |  | Not Committed |  | 2026-05-20 | 2026-06-11 | MEP final fix & Finishes | 100 | 0 |  | 2026-05-18 |  | 2026-06-09
42392 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-05-20 | 2026-05-25 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-05-18 |  | 2026-05-22 |  | Tower A | Super Structure | L17 | Finishes | Door & Window Fixing
42409 |  | Not Committed |  | 2026-05-20 | 2026-06-11 | MEP final fix & Finishes | 100 | 0 |  | 2026-05-18 |  | 2026-06-09
42410 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-05-20 | 2026-05-25 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-05-18 |  | 2026-05-22 |  | Tower A | Super Structure | L18 | Finishes | Door & Window Fixing
43235 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-04-24 | 2026-05-12 | Door & Window Frame work | 100 | 0 |  | 2026-05-18 |  | 2026-06-04 |  | Tower A | Super Structure | L64 | Finishes | Door & Window Frame work
44138 | Tower A - Super Structure - Finishes & MEP - L73 to L78 | Not Ready | Façade Works - MEP & Finishes | 2026-06-18 | 2026-06-29 | Accessories & Alignment | 100 | 0 |  | 2026-05-18 |  | 2026-05-30 |  | Tower A | Super Structure | L73 | Façade | Façade Works
44138 | Tower A - Super Structure - Finishes & MEP - L73 to L78 | Not Ready | Façade Works - MEP & Finishes | 2026-06-18 | 2026-06-29 | Accessories & Alignment | 100 | 0 |  | 2026-05-18 |  | 2026-05-30 |  | Tower A | Super Structure | L73
45303 | Tower B - Super Structure - Core & Outer Slab L17-18 | Not Ready | RCC Works - Slab | 2026-03-07 | 2026-03-13 | Outer Slab_TA | 100 | 0 |  | 2026-05-18 |  | 2026-05-26 |  | Tower B | Super Structure | L17 | RCC Sub Structure | RCC Works - Slab
9840 | T-16-9th Floor Common Area | Not Ready | Door-Shaft | 2026-06-09 | 2026-06-22 | Door-Shaft | 100 | 0 |  | 2026-05-19 |  | 2026-06-01
10422 | T-21-Lift | Not Ready | Water Tanks including Finishes | 2026-06-23 | 2026-08-11 | Water Tanks including Finishes | 100 | 0 |  | 2026-05-19 |  | 2026-07-07
10909 | T-20-11th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-06-20 | 2026-07-23 | 2nd Coat Painting | 100 | 0 |  | 2026-05-19 |  | 2026-06-19
10927 | T-20-11th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-06-20 | 2026-08-26 | 2nd Coat Painting | 100 | 0 |  | 2026-05-19 |  | 2026-07-22
10967 | T-20-Staircase 1 | Not Ready |  | 2026-06-11 | 2026-06-22 | 06F-05F | 100 | 0 |  | 2026-05-19 |  | 2026-05-30
10981 | T-20-Staircase 2 | Not Ready |  | 2026-06-11 | 2026-06-22 | 07F-06F | 100 | 0 |  | 2026-05-19 |  | 2026-05-30
11272 | T-19-4th Floor Common Area | Not Ready | 1st Coat Painting | 2026-06-03 | 2026-06-24 | 1st Coat Painting | 100 | 0 |  | 2026-05-19 |  | 2026-06-11
11512 | T-19- Elevation-B | Not Ready |  | 2026-06-04 | 2026-08-26 | Elevation-B | 100 | 0 |  | 2026-05-19 |  | 2026-08-08
40065 | Tower A - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2026-04-25 | 2026-04-30 | Slow Speed Testing | 100 | 0 |  | 2026-05-19 |  | 2026-05-25 |  | Tower A | Super Structure
40065 | Tower A - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2026-04-25 | 2026-04-30 | Slow Speed Testing | 100 | 0 |  | 2026-05-19 |  | 2026-05-25 |  | Tower A | Super Structure
40551 | Tower A - Super Structure - Finishes & MEP - L77 to L78 | Not Ready | Gypsum Plastering Works | 2026-04-20 | 2026-05-07 | L77-78 | 100 | 0 |  | 2026-05-19 |  | 2026-06-06 |  | Tower A | Super Structure | L77 | Finishes | Gypsum Plastering Works
40551 | Tower A - Super Structure - Finishes & MEP - L77 to L78 | Not Ready | Gypsum Plastering Works | 2026-04-20 | 2026-05-07 | L77-78 | 100 | 0 |  | 2026-05-19 |  | 2026-06-06 |  | Tower A | Super Structure | L77
41585 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-04-27 | 2026-05-04 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-05-19 |  | 2026-05-25 |  | Tower A | Super Structure | L39 | MEP | Electrical
41600 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-04-27 | 2026-04-30 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-05-19 |  | 2026-05-22 |  | Tower A | Super Structure | L40
41612 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-04-27 | 2026-04-30 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-05-19 |  | 2026-05-22 |  | Tower A | Super Structure | L41 | MEP | FPS 2nd Fix - MEP & Finishes
41613 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-04-27 | 2026-05-04 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-05-19 |  | 2026-05-25 |  | Tower A | Super Structure | L41 | MEP | Electrical 2nd Fix - MEP & Finishes
41614 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-27 | 2026-05-06 | FAPA Device Fixing | 100 | 0 |  | 2026-05-19 |  | 2026-05-28 |  | Tower A | Super Structure | L41
41614 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-27 | 2026-05-06 | FAPA Device Fixing | 100 | 0 |  | 2026-05-19 |  | 2026-05-28 |  | Tower A | Super Structure | L41
41614 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-27 | 2026-05-06 | FAPA Device Fixing | 100 | 0 |  | 2026-05-19 |  | 2026-05-28 |  | Tower A | Super Structure | L41
41614 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-27 | 2026-05-06 | FAPA Device Fixing | 100 | 0 |  | 2026-05-19 |  | 2026-05-28 |  | Tower A | Super Structure | L41
41615 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-04-27 | 2026-04-30 | HVAC Grill Fixing | 100 | 0 |  | 2026-05-19 |  | 2026-05-22 |  | Tower A | Super Structure | L41 | MEP | HVAC Grill Fixing
41686 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-04-27 | 2026-04-29 | FAPA Cabling | 100 | 0 |  | 2026-05-19 |  | 2026-05-21 |  | Tower A | Super Structure | L46
42217 | Tower A - Super Structure - Finishes & MEP - L7 to L8 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-05-21 | 2026-05-23 | Painting Works | 100 | 0 |  | 2026-05-19 |  | 2026-05-21 |  | Tower A | Super Structure | L7 | Finishes | Painting Works
42235 | Tower A - Super Structure - Finishes & MEP - L8 to L9 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-05-21 | 2026-05-23 | Painting Works | 100 | 0 |  | 2026-05-19 |  | 2026-05-21 |  | Tower A | Super Structure | L8 | Finishes | Painting Works
42253 | Tower A - Super Structure - Finishes & MEP - L9 to L10 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-05-21 | 2026-05-23 | Painting Works | 100 | 0 |  | 2026-05-19 |  | 2026-05-21 |  | Tower A | Super Structure | L9 | Finishes | Painting Works
43377 |  | Not Committed |  | 2026-04-25 | 2026-07-04 | Finishes after 1st Fix | 100 | 0 |  | 2026-05-19 |  | 2026-07-18
43378 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-04-25 | 2026-05-19 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-05-19 |  | 2026-06-11 |  | Tower A | Super Structure | L72 | Finishes | Blockwork
44611 |  | Not Ready | MEP fix & Finishes | 2026-05-21 | 2026-05-26 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-05-19 |  | 2026-05-23
44611 |  | Not Ready | MEP fix & Finishes | 2026-05-21 | 2026-05-26 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-05-19 |  | 2026-05-23
44611 |  | Not Ready | MEP fix & Finishes | 2026-05-21 | 2026-05-26 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-05-19 |  | 2026-05-23
8911 | T-14- Elevation A | Not Ready |  | 2026-04-21 | 2026-07-13 | Elevation-A | 100 | 0 |  | 2026-05-20 |  | 2026-08-11
9315 | T-15-9th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-05-25 | 2026-07-29 | 2nd Coat Painting | 100 | 0 |  | 2026-05-20 |  | 2026-07-26
9388 | T-15-Lift Lobby | Not Ready |  | 2026-06-01 | 2026-06-17 | 09F | 100 | 0 |  | 2026-05-20 |  | 2026-06-05
11244 | T-19-3rd Floor Common Area | Not Ready | Door-Shaft | 2026-06-04 | 2026-06-17 | Door-Shaft | 100 | 0 |  | 2026-05-20 |  | 2026-06-02
11459 | T-19-Lift | Not Ready | STAIRCASE HR | 2026-06-16 | 2026-08-21 | Staircase Headrooms | 100 | 0 |  | 2026-05-20 |  | 2026-07-27
11466 | T-19-Lift Lobby | Not Ready |  | 2026-06-04 | 2026-06-20 | 11F | 100 | 0 |  | 2026-05-20 |  | 2026-06-05
45785 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-03-16 | 2026-04-07 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-05-20 |  | 2026-06-13 |  | Tower B | Sub Structure | B3 | MEP | FPS 1st Fix - MEP & Finishes
45786 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-03-16 | 2026-04-07 | PHE 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-05-20 |  | 2026-06-13 |  | Tower B | Sub Structure | B3
45787 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-03-16 | 2026-04-01 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-05-20 |  | 2026-06-08 |  | Tower B | Sub Structure | B3 | MEP | Electrical 1st Fixes
45818 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-03-16 | 2026-04-01 | HVAC Ducting/ Fan Installations | 100 | 0 |  | 2026-05-20 |  | 2026-06-08 |  | Tower B | Sub Structure | B2 | MEP | HVAC Ducting
45935 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2026-03-16 | 2026-04-01 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-05-20 |  | 2026-06-08 |  | Tower B | Super Structure
45935 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2026-03-16 | 2026-04-01 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-05-20 |  | 2026-06-08 |  | Tower B | Super Structure
45935 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2026-03-16 | 2026-04-01 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-05-20 |  | 2026-06-08 |  | Tower B | Super Structure
46750 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-03-16 | 2026-04-01 | Wet Area Waterproofing | 100 | 0 |  | 2026-05-20 |  | 2026-06-08 |  | Tower B | Super Structure | L12
48218 | Retail & Clubhouse - Sub structure - B3 to B2 | Not Ready |  | 2025-12-10 | 2026-02-20 | B3 to B2 (MEP Rooms) | 100 | 0 |  | 2026-05-20 |  | 2026-08-04 |  | Club House | Sub Structure | B3
8619 | T-14-3rd Floor Common Area | Not Ready | Window-Open Area | 2026-04-11 | 2026-04-20 | Window-Open Area | 100 | 0 |  | 2026-05-21 |  | 2026-05-29
8853 | T-14-12th Floor Common Area | Not Ready | Window-Open Area | 2026-04-28 | 2026-05-07 | Window-Open Area | 100 | 0 |  | 2026-05-21 |  | 2026-05-30
9373 | T-15-11th Floor Common Area | Not Ready | Window-Open Area | 2026-05-28 | 2026-06-05 | Window-Open Area | 100 | 0 |  | 2026-05-21 |  | 2026-05-27
9905 | T-16-Lift Lobby | Not Ready |  | 2026-06-09 | 2026-06-25 | 12F | 100 | 0 |  | 2026-05-21 |  | 2026-06-04
10473 | T-21- Elevation-C | Not Ready |  | 2026-06-21 | 2026-09-12 | Elevation-C | 100 | 0 |  | 2026-05-21 |  | 2026-08-09
39225 |  | Not Ready |  | 2025-11-06 | 2026-01-08 | Shut Down for Hooking Up with Centurion Electrical Shaft with T & C | 100 | 0 |  | 2026-05-21 |  | 2026-07-22
40117 | Tower A - Super Structure - Finishes & MEP - Sub Station | Not Ready | Sub Station - High Side Services | 2026-05-23 | 2026-06-10 | Transformer Charging | 100 | 0 |  | 2026-05-21 |  | 2026-06-08 |  | Tower A | Super Structure
40124 | Tower A - Super Structure - Finishes & MEP - DG Sets | Not Ready |  | 2026-05-23 | 2026-06-27 | Testing & Commissioning | 100 | 0 |  | 2026-05-21 |  | 2026-06-25 |  | Tower A | Super Structure
40124 | Tower A - Super Structure - Finishes & MEP - DG Sets | Not Ready |  | 2026-05-23 | 2026-06-27 | Testing & Commissioning | 100 | 0 |  | 2026-05-21 |  | 2026-06-25 |  | Tower A | Super Structure
41570 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-29 | 2026-05-06 | Final Painting | 100 | 0 |  | 2026-05-21 |  | 2026-05-28 |  | Tower A | Super Structure | L38 | Finishes | Final Painting
41570 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-29 | 2026-05-06 | Final Painting | 100 | 0 |  | 2026-05-21 |  | 2026-05-28 |  | Tower A | Super Structure | L38 | Finishes | Final Painting
41570 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-29 | 2026-05-06 | Final Painting | 100 | 0 |  | 2026-05-21 |  | 2026-05-28 |  | Tower A | Super Structure | L38 | Finishes | Final Painting
41687 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-04-29 | 2026-05-08 | HVAC Ducting | 100 | 0 |  | 2026-05-21 |  | 2026-05-30 |  | Tower A | Super Structure | L46 | MEP | HVAC Ducting
41700 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-04-29 | 2026-05-06 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-05-21 |  | 2026-05-28 |  | Tower A | Super Structure | L47 | MEP | FPS 1st Fix - MEP & Finishes
41701 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-04-29 | 2026-05-04 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-05-21 |  | 2026-05-25 |  | Tower A | Super Structure | L47 | MEP | Electrical 1st Fixes
42270 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-05-23 | 2026-05-26 | PHE Final Fixes | 100 | 0 |  | 2026-05-21 |  | 2026-05-23 |  | Tower A | Super Structure | L10
42288 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-05-23 | 2026-05-26 | PHE Final Fixes | 100 | 0 |  | 2026-05-21 |  | 2026-05-23 |  | Tower A | Super Structure | L11
42306 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-05-23 | 2026-05-26 | PHE Final Fixes | 100 | 0 |  | 2026-05-21 |  | 2026-05-23 |  | Tower A | Super Structure | L12
42323 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-05-23 | 2026-05-29 | False Ceiling | 100 | 0 |  | 2026-05-21 |  | 2026-05-26 |  | Tower A | Super Structure | L13 | Finishes | False Ceiling
42341 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-05-23 | 2026-05-29 | False Ceiling | 100 | 0 |  | 2026-05-21 |  | 2026-05-26 |  | Tower A | Super Structure | L14 | Finishes | False Ceiling
42355 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-05-23 | 2026-05-29 | False Ceiling | 100 | 0 |  | 2026-05-21 |  | 2026-05-26 |  | Tower A | Super Structure | L15 | Finishes | False Ceiling
43395 |  | Not Committed |  | 2026-04-28 | 2026-07-10 | Finishes after 1st Fix | 100 | 0 |  | 2026-05-21 |  | 2026-07-25
43396 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-04-28 | 2026-05-21 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-05-21 |  | 2026-06-13 |  | Tower A | Super Structure | L73 | Finishes | Blockwork
43985 | Tower A - Super Structure - Finishes & MEP - L25 to L35 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-06-22 | 2026-07-15 | Staircase Railing | 100 | 0 |  | 2026-05-21 |  | 2026-06-15 |  | Tower A | Super Structure | L25
43995 |  | Not Committed |  | 2026-06-22 | 2026-09-18 | L45-55 | 100 | 0 |  | 2026-05-21 |  | 2026-07-29
43995 |  | Not Committed |  | 2026-06-22 | 2026-09-18 | L45-55 | 100 | 0 |  | 2026-05-21 |  | 2026-07-29
43996 | Tower A - Super Structure - Finishes & MEP - L45 to L55 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-06-22 | 2026-07-29 | Staircase Wall & Ceiling finishes | 100 | 0 |  | 2026-05-21 |  | 2026-06-26 |  | Tower A | Super Structure | L45
43997 | Tower A - Super Structure - Finishes & MEP - L45 to L55 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-06-22 | 2026-08-20 | Staircase Flooring | 100 | 0 |  | 2026-05-21 |  | 2026-07-15 |  | Tower A | Super Structure | L45 | Finishes | Staircase Flooring
45460 | Tower B - Super Structure - Finishes & MEP - L13 to L14 | Not Ready | Partition Wall-Blockwork | 2026-03-17 | 2026-03-21 | Staircase Area | 100 | 0 |  | 2026-05-21 |  | 2026-05-28 |  | Tower B | Super Structure | L13
9089 | T-15-GF Common Area | Not Ready | 2nd Coat Painting | 2026-06-16 | 2026-09-01 | 2nd Coat Painting | 100 | 0 |  | 2026-05-22 |  | 2026-08-07
40133 | Tower A - Super Structure - Finishes & MEP - MEP Service Floors | Not Ready |  | 2026-04-17 | 2026-08-06 | Testing & Commissioning | 100 | 0 |  | 2026-05-22 |  | 2026-09-14 |  | Tower A | Super Structure
40133 | Tower A - Super Structure - Finishes & MEP - MEP Service Floors | Not Ready |  | 2026-04-17 | 2026-08-06 | Testing & Commissioning | 100 | 0 |  | 2026-05-22 |  | 2026-09-14 |  | Tower A | Super Structure
40560 | Tower A - Super Structure - Finishes & MEP | Not Ready | MEP Shaft Masonry | 2026-04-17 | 2026-05-22 | L65-L77 | 100 | 0 |  | 2026-05-22 |  | 2026-06-27 |  | Tower A | Super Structure
41601 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-04-30 | 2026-05-07 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-05-22 |  | 2026-05-29 |  | Tower A | Super Structure | L40 | MEP | Electrical
41616 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-04-30 | 2026-05-05 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-05-22 |  | 2026-05-26 |  | Tower A | Super Structure | L41
41628 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-04-30 | 2026-05-05 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-05-22 |  | 2026-05-26 |  | Tower A | Super Structure | L42 | MEP | FPS 2nd Fix - MEP & Finishes
41629 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-04-30 | 2026-05-07 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-05-22 |  | 2026-05-29 |  | Tower A | Super Structure | L42 | MEP | Electrical 2nd Fix - MEP & Finishes
41630 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-30 | 2026-05-09 | FAPA Device Fixing | 100 | 0 |  | 2026-05-22 |  | 2026-06-01 |  | Tower A | Super Structure | L42
41630 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-30 | 2026-05-09 | FAPA Device Fixing | 100 | 0 |  | 2026-05-22 |  | 2026-06-01 |  | Tower A | Super Structure | L42
41630 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-30 | 2026-05-09 | FAPA Device Fixing | 100 | 0 |  | 2026-05-22 |  | 2026-06-01 |  | Tower A | Super Structure | L42
41630 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-30 | 2026-05-09 | FAPA Device Fixing | 100 | 0 |  | 2026-05-22 |  | 2026-06-01 |  | Tower A | Super Structure | L42
41631 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-04-30 | 2026-05-05 | HVAC Grill Fixing | 100 | 0 |  | 2026-05-22 |  | 2026-05-26 |  | Tower A | Super Structure | L42 | MEP | HVAC Grill Fixing
46733 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-03-18 | 2026-03-28 | Cement Plastering in wet areas | 100 | 0 |  | 2026-05-22 |  | 2026-06-04 |  | Tower B | Super Structure | L11
8769 | T-14-9th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-04-25 | 2026-06-30 | 2nd Coat Painting | 100 | 0 |  | 2026-05-23 |  | 2026-07-29
8828 | T-14-11th Floor Common Area | Not Ready | 1st Coat Painting | 2026-04-25 | 2026-05-18 | 1st Coat Painting | 100 | 0 |  | 2026-05-23 |  | 2026-06-14
10415 | T-21-11th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-07-07 | 2026-08-08 | 2nd Coat Painting | 100 | 0 |  | 2026-05-23 |  | 2026-06-25
11187 | T-19-1st Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-06-27 | 2026-09-02 | 2nd Coat Painting | 100 | 0 |  | 2026-05-23 |  | 2026-07-26
11974 | T-18-11th Floor Common Area | Not Ready | 1st Coat Painting | 2026-08-06 | 2026-08-29 | 1st Coat Painting | 100 | 0 |  | 2026-05-23 |  | 2026-06-14
41659 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-05-02 | 2026-05-11 | False Ceiling | 100 | 0 |  | 2026-05-23 |  | 2026-06-02 |  | Tower A | Super Structure | L44 | Finishes | False Ceiling
41674 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-05-02 | 2026-05-14 | Flooring & Dado | 100 | 0 |  | 2026-05-23 |  | 2026-06-05 |  | Tower A | Super Structure | L45 | Finishes | Flooring & Dado
42375 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-05-26 | 2026-05-29 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-05-23 |  | 2026-05-26 |  | Tower A | Super Structure | L16 | MEP | FPS 2nd Fix - MEP & Finishes
42376 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-05-26 | 2026-05-29 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-05-23 |  | 2026-05-26 |  | Tower A | Super Structure | L16 | MEP | Electrical 2nd Fix - MEP & Finishes
42393 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-05-26 | 2026-05-29 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-05-23 |  | 2026-05-26 |  | Tower A | Super Structure | L17 | MEP | FPS 2nd Fix - MEP & Finishes
42394 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-05-26 | 2026-05-29 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-05-23 |  | 2026-05-26 |  | Tower A | Super Structure | L17 | MEP | Electrical 2nd Fix - MEP & Finishes
42411 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-05-26 | 2026-05-29 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-05-23 |  | 2026-05-26 |  | Tower A | Super Structure | L18 | MEP | FPS 2nd Fix - MEP & Finishes
42412 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-05-26 | 2026-05-29 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-05-23 |  | 2026-05-26 |  | Tower A | Super Structure | L18 | MEP | Electrical 2nd Fix - MEP & Finishes
42427 |  | Not Committed |  | 2026-05-26 | 2026-06-17 | MEP final fix & Finishes | 100 | 0 |  | 2026-05-23 |  | 2026-06-15
42428 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-05-26 | 2026-06-01 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-05-23 |  | 2026-05-29 |  | Tower A | Super Structure | L19 | Finishes | Door & Window Fixing
42445 |  | Not Committed |  | 2026-05-26 | 2026-06-17 | MEP final fix & Finishes | 100 | 0 |  | 2026-05-23 |  | 2026-06-15
42446 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-05-26 | 2026-06-01 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-05-23 |  | 2026-05-29 |  | Tower A | Super Structure | L20 | Finishes | Door & Window Fixing
42463 |  | Not Committed |  | 2026-05-26 | 2026-06-17 | MEP final fix & Finishes | 100 | 0 |  | 2026-05-23 |  | 2026-06-15
42464 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-05-26 | 2026-06-01 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-05-23 |  | 2026-05-29 |  | Tower A | Super Structure | L21 | Finishes | Door & Window Fixing
44018 |  | Not Committed |  | 2026-07-31 | 2026-09-25 | GF-P1 | 100 | 0 |  | 2026-05-23 |  | 2026-07-04
44019 | Tower A - Super Structure - Finishes & MEP - GF to P1 | Not Ready | Façade Works - MEP & Finishes | 2026-07-31 | 2026-08-21 | Al. Frame section (Mullion & Transom) Installation | 100 | 0 |  | 2026-05-23 |  | 2026-06-11 |  | Tower A | Super Structure | GF | Façade | Façade Works
44025 | Tower A - Super Structure - Finishes & MEP - GF to P1 | Not Ready | Façade Works - MEP & Finishes | 2026-07-31 | 2026-09-16 | Entrance Canopy | 100 | 0 |  | 2026-05-23 |  | 2026-07-04 |  | Tower A | Super Structure | GF | Façade | Façade Works
44622 |  | Not Ready | MEP fix & Finishes | 2026-05-26 | 2026-06-06 | Final Painting | 100 | 0 |  | 2026-05-23 |  | 2026-06-04 |  |  |  |  | Finishes | Final Painting
44622 |  | Not Ready | MEP fix & Finishes | 2026-05-26 | 2026-06-06 | Final Painting | 100 | 0 |  | 2026-05-23 |  | 2026-06-04 |  |  |  |  | Finishes | Final Painting
44622 |  | Not Ready | MEP fix & Finishes | 2026-05-26 | 2026-06-06 | Final Painting | 100 | 0 |  | 2026-05-23 |  | 2026-06-04 |  |  |  |  | Finishes | Final Painting
44627 |  | Not Ready | MEP fix & Finishes | 2026-05-26 | 2026-06-03 | HVAC Fans fixing | 100 | 0 |  | 2026-05-23 |  | 2026-06-01 |  |  |  |  | MEP | HVAC Grill Fixing
44627 |  | Not Ready | MEP fix & Finishes | 2026-05-26 | 2026-06-03 | HVAC Fans fixing | 100 | 0 |  | 2026-05-23 |  | 2026-06-01 |  |  |  |  | MEP | HVAC Grill Fixing
45615 | Tower B - Super Structure - Finishes & MEP - L12 to L13 | Not Ready | Gypsum Plastering Works | 2026-03-19 | 2026-05-05 | L12-13 | 100 | 0 |  | 2026-05-23 |  | 2026-07-10 |  | Tower B | Super Structure | L12 | Finishes | Gypsum Plastering Works
45615 | Tower B - Super Structure - Finishes & MEP - L12 to L13 | Not Ready | Gypsum Plastering Works | 2026-03-19 | 2026-05-05 | L12-13 | 100 | 0 |  | 2026-05-23 |  | 2026-07-10 |  | Tower B | Super Structure | L12
9921 | T-16-Staircase 1 | Not Ready |  | 2026-06-09 | 2026-06-19 | 12F-11F | 100 | 0 |  | 2026-05-24 |  | 2026-06-02
9935 | T-16-Staircase 2 | Not Ready |  | 2026-06-09 | 2026-06-19 | TF-12F | 100 | 0 |  | 2026-05-24 |  | 2026-06-02
8543 | T-14-GF Common Area | Not Ready | 2nd Coat Painting | 2026-05-18 | 2026-08-02 | 2nd Coat Painting | 100 | 0 |  | 2026-05-25 |  | 2026-08-09
9138 | T-15-2nd Floor Common Area | Not Ready | Door-Shaft | 2026-05-21 | 2026-06-03 | Door-Shaft | 100 | 0 |  | 2026-05-25 |  | 2026-06-08
9816 | T-16-8th Floor Common Area | Not Ready | 1st Coat Painting | 2026-06-13 | 2026-07-05 | 1st Coat Painting | 100 | 0 |  | 2026-05-25 |  | 2026-06-19
10421 | T-21-Lift | Not Ready | OTS Covers | 2026-06-27 | 2026-07-30 | OTS Covers | 100 | 0 |  | 2026-05-25 |  | 2026-06-24
10673 | T-20-1st Floor Common Area | Not Ready | Window-Open Area | 2026-06-18 | 2026-06-26 | Window-Open Area | 100 | 0 |  | 2026-05-25 |  | 2026-06-02
40066 | Tower A - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2026-05-02 | 2026-05-07 | Balancing, Load Testing, High Speed Testing | 100 | 0 |  | 2026-05-25 |  | 2026-06-01 |  | Tower A | Super Structure
40066 | Tower A - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2026-05-02 | 2026-05-07 | Balancing, Load Testing, High Speed Testing | 100 | 0 |  | 2026-05-25 |  | 2026-06-01 |  | Tower A | Super Structure
40087 | Tower A - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2026-05-02 | 2026-06-06 | Completion of Electrical Works | 100 | 0 |  | 2026-05-25 |  | 2026-06-30 |  | Tower A | Super Structure
40087 | Tower A - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2026-05-02 | 2026-06-06 | Completion of Electrical Works | 100 | 0 |  | 2026-05-25 |  | 2026-06-30 |  | Tower A | Super Structure
41586 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-05-04 | 2026-05-09 | Final Painting | 100 | 0 |  | 2026-05-25 |  | 2026-06-01 |  | Tower A | Super Structure | L39 | Finishes | Final Painting
41586 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-05-04 | 2026-05-09 | Final Painting | 100 | 0 |  | 2026-05-25 |  | 2026-06-01 |  | Tower A | Super Structure | L39 | Finishes | Final Painting
41586 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-05-04 | 2026-05-09 | Final Painting | 100 | 0 |  | 2026-05-25 |  | 2026-06-01 |  | Tower A | Super Structure | L39 | Finishes | Final Painting
41702 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-05-04 | 2026-05-06 | FAPA Cabling | 100 | 0 |  | 2026-05-25 |  | 2026-05-28 |  | Tower A | Super Structure | L47
42271 | Tower A - Super Structure - Finishes & MEP - L10 to L11 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-05-28 | 2026-05-30 | Painting Works | 100 | 0 |  | 2026-05-25 |  | 2026-05-28 |  | Tower A | Super Structure | L10 | Finishes | Painting Works
42289 | Tower A - Super Structure - Finishes & MEP - L11 to L12 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-05-28 | 2026-05-30 | Painting Works | 100 | 0 |  | 2026-05-25 |  | 2026-05-28 |  | Tower A | Super Structure | L11 | Finishes | Painting Works
42307 | Tower A - Super Structure - Finishes & MEP - L12 to L13 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-05-28 | 2026-05-30 | Painting Works | 100 | 0 |  | 2026-05-25 |  | 2026-05-28 |  | Tower A | Super Structure | L12 | Finishes | Painting Works
43289 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-05-02 | 2026-05-09 | Door & Window Frame work | 100 | 0 |  | 2026-05-25 |  | 2026-06-02 |  | Tower A | Super Structure | L67 | Finishes | Door & Window Frame work
43430 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-04-25 | 2026-05-07 | Cement Plastering in wet areas | 100 | 0 |  | 2026-05-25 |  | 2026-06-06 |  | Tower A | Super Structure | L77
9166 | T-15-3rd Floor Common Area | Not Ready | 1st Coat Painting | 2026-05-20 | 2026-06-10 | 1st Coat Painting | 100 | 0 |  | 2026-05-26 |  | 2026-06-17
9630 | T-16-1st Floor Common Area | Not Ready | Flooring & skirting | 2026-06-09 | 2026-07-01 | Flooring & skirting | 100 | 0 |  | 2026-05-26 |  | 2026-06-16
9657 | T-16-2nd Floor Common Area | Not Ready | Putty | 2026-06-09 | 2026-07-17 | Putty | 100 | 0 |  | 2026-05-26 |  | 2026-07-02
9951 | T-16- Elevation A | Not Ready |  | 2026-06-14 | 2026-09-05 | Elevation-A | 100 | 0 |  | 2026-05-26 |  | 2026-08-17
10942 | T-20-Lift | Not Ready | Water Tanks including Finishes | 2026-07-04 | 2026-08-24 | Water Tanks including Finishes | 100 | 0 |  | 2026-05-26 |  | 2026-07-13
11191 | T-19-1st Floor Common Area | Not Ready | Putty | 2026-06-09 | 2026-07-17 | Putty | 100 | 0 |  | 2026-05-26 |  | 2026-07-06
11427 | T-19-11th Floor Common Area | Not Ready | Window-Open Area | 2026-06-17 | 2026-06-24 | Window-Open Area | 100 | 0 |  | 2026-05-26 |  | 2026-06-06
11923 | T-18-9th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-08-12 | 2026-09-15 | 2nd Coat Painting | 100 | 0 |  | 2026-05-26 |  | 2026-06-26
11941 | T-18-10th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-08-12 | 2026-10-19 | 2nd Coat Painting | 100 | 0 |  | 2026-05-26 |  | 2026-07-30
40084 | Tower A - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2026-05-04 | 2026-05-19 | Guide Rail installation for CWT (up to LMR) | 100 | 0 |  | 2026-05-26 |  | 2026-06-12 |  | Tower A | Super Structure
40084 | Tower A - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2026-05-04 | 2026-05-19 | Guide Rail installation for CWT (up to LMR) | 100 | 0 |  | 2026-05-26 |  | 2026-06-12 |  | Tower A | Super Structure
41617 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-05-05 | 2026-05-11 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-05-26 |  | 2026-06-02 |  | Tower A | Super Structure | L41 | MEP | Electrical
41632 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-05-05 | 2026-05-08 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-05-26 |  | 2026-05-30 |  | Tower A | Super Structure | L42
41644 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-05-05 | 2026-05-08 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-05-26 |  | 2026-05-30 |  | Tower A | Super Structure | L43 | MEP | FPS 2nd Fix - MEP & Finishes
41645 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-05-05 | 2026-05-11 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-05-26 |  | 2026-06-02 |  | Tower A | Super Structure | L43 | MEP | Electrical 2nd Fix - MEP & Finishes
41646 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-05-05 | 2026-05-13 | FAPA Device Fixing | 100 | 0 |  | 2026-05-26 |  | 2026-06-04 |  | Tower A | Super Structure | L43
41646 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-05-05 | 2026-05-13 | FAPA Device Fixing | 100 | 0 |  | 2026-05-26 |  | 2026-06-04 |  | Tower A | Super Structure | L43
41646 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-05-05 | 2026-05-13 | FAPA Device Fixing | 100 | 0 |  | 2026-05-26 |  | 2026-06-04 |  | Tower A | Super Structure | L43
41646 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-05-05 | 2026-05-13 | FAPA Device Fixing | 100 | 0 |  | 2026-05-26 |  | 2026-06-04 |  | Tower A | Super Structure | L43
41647 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-05-05 | 2026-05-08 | HVAC Grill Fixing | 100 | 0 |  | 2026-05-26 |  | 2026-05-30 |  | Tower A | Super Structure | L43 | MEP | HVAC Grill Fixing
43253 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-05-04 | 2026-05-20 | Door & Window Frame work | 100 | 0 |  | 2026-05-26 |  | 2026-06-12 |  | Tower A | Super Structure | L65 | Finishes | Door & Window Frame work
45304 |  | Not Ready |  | 2026-03-14 | 2026-03-25 | L18-19 | 100 | 0 |  | 2026-05-26 |  | 2026-06-11
45304 |  | Not Ready |  | 2026-03-14 | 2026-03-25 | L18-19 | 100 | 0 |  | 2026-05-26 |  | 2026-06-11 |  |  |  |  | Finishes | Gypsum Plastering Works
45305 | Tower B - Super Structure - Core & Outer Slab L18-19 | Not Ready | RCC Works - Vertical | 2026-03-14 | 2026-03-23 | Outer Columns_TA | 100 | 0 |  | 2026-05-26 |  | 2026-06-08 |  | Tower B | Super Structure | L18 | RCC Sub Structure | RCC Works - Vertical
45465 |  | Not Committed |  | 2026-03-14 | 2026-04-14 | L15-16 | 100 | 0 |  | 2026-05-26 |  | 2026-06-27
45465 |  | Not Committed |  | 2026-03-14 | 2026-04-14 | L15-16 | 100 | 0 |  | 2026-05-26 |  | 2026-06-27 |  |  |  |  | Finishes | Gypsum Plastering Works
45466 | Tower B - Super Structure - Finishes & MEP - L15 to L16 | Not Ready | Partition Wall-Blockwork | 2026-03-14 | 2026-03-31 | De-shuttering & Area clearance | 100 | 0 |  | 2026-05-26 |  | 2026-06-13 |  | Tower B | Super Structure | L15
45789 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-03-21 | 2026-04-07 | HVAC Ducting/ Fan Installations | 100 | 0 |  | 2026-05-26 |  | 2026-06-13 |  | Tower B | Sub Structure | B3 | MEP | HVAC Ducting
45817 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-03-21 | 2026-04-01 | FAPA Cabling | 100 | 0 |  | 2026-05-26 |  | 2026-06-08 |  | Tower B | Sub Structure | B2
45873 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-03-21 | 2026-04-18 | Flooring & Dado | 100 | 0 |  | 2026-05-26 |  | 2026-06-25 |  | Tower B | Super Structure | GF | Finishes | Flooring & Dado
45908 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2026-03-21 | 2026-04-07 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-05-26 |  | 2026-06-13 |  | Tower B | Super Structure
45908 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2026-03-21 | 2026-04-07 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-05-26 |  | 2026-06-13 |  | Tower B | Super Structure
45908 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2026-03-21 | 2026-04-07 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-05-26 |  | 2026-06-13 |  | Tower B | Super Structure
47666 |  | Not Committed |  | 2026-05-26 | 2026-09-02 | Retaining Wall_lift 1 (Grid PA-04 to PB-N) | 100 | 0 |  | 2026-05-26 |  | 2027-01-19
47667 |  | Not Ready |  | 2026-05-26 | 2026-06-08 | Section 1_lift 1 | 100 | 0 |  | 2026-05-26 |  | 2026-06-08
47667 |  | Not Ready |  | 2026-05-26 | 2026-06-08 | Section 1_lift 1 | 100 | 0 |  | 2026-05-26 |  | 2026-06-08 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47669 |  | Not Ready |  | 2026-05-26 | 2026-06-08 | Section 3_lift 1 | 100 | 0 |  | 2026-05-26 |  | 2026-06-08
47669 |  | Not Ready |  | 2026-05-26 | 2026-06-08 | Section 3_lift 1 | 100 | 0 |  | 2026-05-26 |  | 2026-06-08 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47690 |  | Not Committed |  | 2026-05-26 | 2026-07-17 | Pour 7 (grid PB-K to PB-N) | 100 | 0 |  | 2026-05-26 |  | 2026-07-17
47691 |  | Not Ready |  | 2026-05-26 | 2026-06-12 | Columns/ Walls_NTA | 100 | 0 |  | 2026-05-26 |  | 2026-06-12
47691 |  | Not Ready |  | 2026-05-26 | 2026-06-12 | Columns/ Walls_NTA | 100 | 0 |  | 2026-05-26 |  | 2026-06-12 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
9406 | T-15-Staircase 1 | Not Ready |  | 2026-06-06 | 2026-06-17 | 07F-06F | 100 | 0 |  | 2026-05-27 |  | 2026-06-09
9420 | T-15-Staircase 2 | Not Ready |  | 2026-06-06 | 2026-06-17 | 08F-07F | 100 | 0 |  | 2026-05-27 |  | 2026-06-09
10207 | T-21-3rd Floor Common Area | Not Ready | 2nd Coat Painting | 2026-06-25 | 2026-07-28 | 2nd Coat Painting | 100 | 0 |  | 2026-05-27 |  | 2026-06-30
39263 | Retail - Sub structure - B2 to B1 | Not Ready | RCC Works - Slab | 2025-12-09 | 2025-12-30 | Slab_NTA | 100 | 0 |  | 2026-05-27 |  | 2026-06-16 |  | Retail | Sub Structure | B2 | RCC Sub Structure | RCC Works - Slab
39263 | Retail - Sub structure - B2 to B1 | Not Ready | RCC Works - Slab | 2025-12-09 | 2025-12-30 | Slab_NTA | 100 | 0 |  | 2026-05-27 |  | 2026-06-16 |  | Retail | Sub Structure | B2
8882 | T-14-Staircase 1 | Not Ready |  | 2026-04-26 | 2026-05-08 | 11F-10F | 100 | 0 |  | 2026-05-28 |  | 2026-06-10
8896 | T-14-Staircase 2 | Not Ready |  | 2026-04-26 | 2026-05-08 | 12F-11F | 100 | 0 |  | 2026-05-28 |  | 2026-06-10
9374 | T-15-11th Floor Common Area | Not Ready | 1st Coat Painting | 2026-06-05 | 2026-06-27 | 1st Coat Painting | 100 | 0 |  | 2026-05-28 |  | 2026-06-18
9711 | T-16-4th Floor Common Area | Not Ready | Window-Open Area | 2026-06-16 | 2026-06-24 | Window-Open Area | 100 | 0 |  | 2026-05-28 |  | 2026-06-01
10449 | T-21-Staircase 1 | Not Ready |  | 2026-06-21 | 2026-07-02 | 04F-03F | 100 | 0 |  | 2026-05-28 |  | 2026-06-08
10463 | T-21-Staircase 2 | Not Ready |  | 2026-06-21 | 2026-07-02 | 05F-04F | 100 | 0 |  | 2026-05-28 |  | 2026-06-08
10474 | T-21- Elevation-D | Not Ready |  | 2026-07-02 | 2026-09-23 | Elevation-D | 100 | 0 |  | 2026-05-28 |  | 2026-08-17
11452 | T-19-11th Floor Common Area | Not Ready | Door-Shaft | 2026-06-20 | 2026-07-03 | Door-Shaft | 100 | 0 |  | 2026-05-28 |  | 2026-06-12
11739 | T-18-2nd Floor Common Area | Not Ready | Window-Open Area | 2026-08-04 | 2026-08-12 | Window-Open Area | 100 | 0 |  | 2026-05-28 |  | 2026-06-04
39211 |  | Not Ready |  | 2025-06-30 | 2025-08-18 | Shut Down for Hooking Up with Centurion Electrical Shaft with T & C | 100 | 0 |  | 2026-05-28 |  | 2026-07-15
41703 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-05-06 | 2026-05-14 | HVAC Ducting | 100 | 0 |  | 2026-05-28 |  | 2026-06-05 |  | Tower A | Super Structure | L47 | MEP | HVAC Ducting
41716 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-05-06 | 2026-05-12 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-05-28 |  | 2026-06-03 |  | Tower A | Super Structure | L48 | MEP | FPS 1st Fix - MEP & Finishes
41717 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-05-06 | 2026-05-09 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-05-28 |  | 2026-06-01 |  | Tower A | Super Structure | L48 | MEP | Electrical 1st Fixes
42324 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-05-30 | 2026-06-02 | PHE Final Fixes | 100 | 0 |  | 2026-05-28 |  | 2026-05-30 |  | Tower A | Super Structure | L13
42342 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-05-30 | 2026-06-02 | PHE Final Fixes | 100 | 0 |  | 2026-05-28 |  | 2026-05-30 |  | Tower A | Super Structure | L14
42356 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-05-30 | 2026-06-02 | PHE Final Fixes | 100 | 0 |  | 2026-05-28 |  | 2026-05-30 |  | Tower A | Super Structure | L15
42377 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-05-30 | 2026-06-04 | False Ceiling | 100 | 0 |  | 2026-05-28 |  | 2026-06-02 |  | Tower A | Super Structure | L16 | Finishes | False Ceiling
42395 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-05-30 | 2026-06-04 | False Ceiling | 100 | 0 |  | 2026-05-28 |  | 2026-06-02 |  | Tower A | Super Structure | L17 | Finishes | False Ceiling
42413 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-05-30 | 2026-06-04 | False Ceiling | 100 | 0 |  | 2026-05-28 |  | 2026-06-02 |  | Tower A | Super Structure | L18 | Finishes | False Ceiling
43987 | Tower A - Super Structure - Finishes & MEP - L25 to L35 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-06-27 | 2026-07-15 | Staircase Light Fixtures & Devices fixing | 100 | 0 |  | 2026-05-28 |  | 2026-06-15 |  | Tower A | Super Structure | L25
44617 |  | Not Ready | MEP fix & Finishes | 2026-05-30 | 2026-06-04 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-05-28 |  | 2026-06-02
44617 |  | Not Ready | MEP fix & Finishes | 2026-05-30 | 2026-06-04 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-05-28 |  | 2026-06-02
44617 |  | Not Ready | MEP fix & Finishes | 2026-05-30 | 2026-06-04 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-05-28 |  | 2026-06-02
46763 |  | Not Committed |  | 2026-03-23 | 2027-04-20 | L13-14 (Refuge) | 100 | 0 |  | 2026-05-28 |  | 2027-06-14
46764 |  | Not Committed |  | 2026-03-23 | 2026-04-28 | MEP 1st Fixes | 100 | 0 |  | 2026-05-28 |  | 2026-07-04
46765 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-03-23 | 2026-03-30 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-05-28 |  | 2026-06-05 |  | Tower B | Super Structure | L13 | MEP | FPS 1st Fix - MEP & Finishes
46766 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-03-23 | 2026-03-27 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-05-28 |  | 2026-06-03 |  | Tower B | Super Structure | L13 | MEP | Electrical 1st Fixes
46767 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-03-23 | 2026-03-30 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-05-28 |  | 2026-06-05 |  | Tower B | Super Structure | L13
40097 | Tower A - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2026-04-29 | 2026-05-16 | Pumps & Accessories Installation | 100 | 0 |  | 2026-05-29 |  | 2026-06-16 |  | Tower A | Super Structure
41602 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-05-07 | 2026-05-13 | Final Painting | 100 | 0 |  | 2026-05-29 |  | 2026-06-04 |  | Tower A | Super Structure | L40 | Finishes | Final Painting
41602 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-05-07 | 2026-05-13 | Final Painting | 100 | 0 |  | 2026-05-29 |  | 2026-06-04 |  | Tower A | Super Structure | L40 | Finishes | Final Painting
41602 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-05-07 | 2026-05-13 | Final Painting | 100 | 0 |  | 2026-05-29 |  | 2026-06-04 |  | Tower A | Super Structure | L40 | Finishes | Final Painting
42189 |  | Not Committed |  | 2026-05-06 | 2026-07-24 | Finishes after 1st Fix | 100 | 0 |  | 2026-05-29 |  | 2026-07-22
42190 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-05-06 | 2026-05-29 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-05-29 |  | 2026-06-20 |  | Tower A | Super Structure | L76 | Finishes | Blockwork
45463 | Tower B - Super Structure - Finishes & MEP - L14 to L15 | Not Ready | Partition Wall-Blockwork | 2026-03-20 | 2026-03-27 | Partition Walls | 100 | 0 |  | 2026-05-29 |  | 2026-06-06 |  | Tower B | Super Structure | L14
8592 | T-14-2nd Floor Common Area | Not Ready | Door-Shaft | 2026-04-21 | 2026-05-05 | Door-Shaft | 100 | 0 |  | 2026-05-30 |  | 2026-06-13
8620 | T-14-3rd Floor Common Area | Not Ready | 1st Coat Painting | 2026-04-20 | 2026-05-12 | 1st Coat Painting | 100 | 0 |  | 2026-05-30 |  | 2026-06-21
8912 | T-14- Elevation-B | Not Ready |  | 2026-05-02 | 2026-07-23 | Elevation-B | 100 | 0 |  | 2026-05-30 |  | 2026-08-21
11299 | T-19-5th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-06-13 | 2026-07-16 | 2nd Coat Painting | 100 | 0 |  | 2026-05-30 |  | 2026-07-01
11483 | T-19-Staircase 1 | Not Ready |  | 2026-06-09 | 2026-06-20 | 10F-09F | 100 | 0 |  | 2026-05-30 |  | 2026-06-09
11497 | T-19-Staircase 2 | Not Ready |  | 2026-06-09 | 2026-06-20 | 11F-10F | 100 | 0 |  | 2026-05-30 |  | 2026-06-09
12006 | T-18-Staircase 1 | Not Ready |  | 2026-08-07 | 2026-08-19 | 07F-06F | 100 | 0 |  | 2026-05-30 |  | 2026-06-08
12020 | T-18-Staircase 2 | Not Ready |  | 2026-08-07 | 2026-08-19 | 08F-07F | 100 | 0 |  | 2026-05-30 |  | 2026-06-08
41633 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-05-08 | 2026-05-14 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-05-30 |  | 2026-06-05 |  | Tower A | Super Structure | L42 | MEP | Electrical
41648 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-05-08 | 2026-05-12 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-05-30 |  | 2026-06-03 |  | Tower A | Super Structure | L43
41675 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-05-08 | 2026-05-16 | False Ceiling | 100 | 0 |  | 2026-05-30 |  | 2026-06-08 |  | Tower A | Super Structure | L45 | Finishes | False Ceiling
41690 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-05-08 | 2026-05-20 | Flooring & Dado | 100 | 0 |  | 2026-05-30 |  | 2026-06-11 |  | Tower A | Super Structure | L46 | Finishes | Flooring & Dado
42429 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-06-02 | 2026-06-04 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-05-30 |  | 2026-06-02 |  | Tower A | Super Structure | L19 | MEP | FPS 2nd Fix - MEP & Finishes
42430 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-06-02 | 2026-06-04 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-05-30 |  | 2026-06-02 |  | Tower A | Super Structure | L19 | MEP | Electrical 2nd Fix - MEP & Finishes
42447 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-06-02 | 2026-06-04 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-05-30 |  | 2026-06-02 |  | Tower A | Super Structure | L20 | MEP | FPS 2nd Fix - MEP & Finishes
42448 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-06-02 | 2026-06-04 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-05-30 |  | 2026-06-02 |  | Tower A | Super Structure | L20 | MEP | Electrical 2nd Fix - MEP & Finishes
42465 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-06-02 | 2026-06-04 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-05-30 |  | 2026-06-02 |  | Tower A | Super Structure | L21 | MEP | FPS 2nd Fix - MEP & Finishes
42466 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-06-02 | 2026-06-04 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-05-30 |  | 2026-06-02 |  | Tower A | Super Structure | L21 | MEP | Electrical 2nd Fix - MEP & Finishes
42481 |  | Not Committed |  | 2026-06-02 | 2026-06-23 | MEP final fix & Finishes | 100 | 0 |  | 2026-05-30 |  | 2026-06-20
42482 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-06-02 | 2026-06-06 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-05-30 |  | 2026-06-04 |  | Tower A | Super Structure | L22 | Finishes | Door & Window Fixing
42499 |  | Not Committed |  | 2026-06-02 | 2026-06-23 | MEP final fix & Finishes | 100 | 0 |  | 2026-05-30 |  | 2026-06-20
42500 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-06-02 | 2026-06-06 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-05-30 |  | 2026-06-04 |  | Tower A | Super Structure | L23 | Finishes | Door & Window Fixing
42517 |  | Not Committed |  | 2026-06-02 | 2026-06-16 | MEP final fix & Finishes | 100 | 0 |  | 2026-05-30 |  | 2026-06-13
42518 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-06-02 | 2026-06-06 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-05-30 |  | 2026-06-04 |  | Tower A | Super Structure | L24 | Finishes | Door & Window Fixing
8854 | T-14-12th Floor Common Area | Not Ready | 1st Coat Painting | 2026-05-07 | 2026-05-28 | 1st Coat Painting | 100 | 0 |  | 2026-05-31 |  | 2026-06-21
10968 | T-20-Staircase 1 | Not Ready |  | 2026-06-22 | 2026-07-02 | 05F-04F | 100 | 0 |  | 2026-05-31 |  | 2026-06-13
10982 | T-20-Staircase 2 | Not Ready |  | 2026-06-22 | 2026-07-02 | 06F-05F | 100 | 0 |  | 2026-05-31 |  | 2026-06-13
11793 | T-18-4th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-08-12 | 2026-09-15 | 2nd Coat Painting | 100 | 0 |  | 2026-05-31 |  | 2026-07-03
8866 | T-14-Lift Lobby | Not Ready |  | 2026-05-02 | 2026-05-19 | 11F | 100 | 0 |  | 2026-06-01 |  | 2026-06-17
40067 | Tower A - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2026-05-08 | 2026-05-13 | 3rd Party Testing & Commissioning | 100 | 0 |  | 2026-06-01 |  | 2026-06-06 |  | Tower A | Super Structure
40067 | Tower A - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2026-05-08 | 2026-05-13 | 3rd Party Testing & Commissioning | 100 | 0 |  | 2026-06-01 |  | 2026-06-06 |  | Tower A | Super Structure
41718 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-05-09 | 2026-05-12 | FAPA Cabling | 100 | 0 |  | 2026-06-01 |  | 2026-06-03 |  | Tower A | Super Structure | L48
42325 | Tower A - Super Structure - Finishes & MEP - L13 to L14 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-03 | 2026-06-05 | Painting Works | 100 | 0 |  | 2026-06-01 |  | 2026-06-03 |  | Tower A | Super Structure | L13 | Finishes | Painting Works
42343 | Tower A - Super Structure - Finishes & MEP - L14 to L15 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-03 | 2026-06-05 | Painting Works | 100 | 0 |  | 2026-06-01 |  | 2026-06-03 |  | Tower A | Super Structure | L14 | Finishes | Painting Works
42357 | Tower A - Super Structure - Finishes & MEP - L15 to L16 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-03 | 2026-06-05 | Painting Works | 100 | 0 |  | 2026-06-01 |  | 2026-06-03 |  | Tower A | Super Structure | L15 | Finishes | Painting Works
9712 | T-16-4th Floor Common Area | Not Ready | 1st Coat Painting | 2026-06-24 | 2026-07-16 | 1st Coat Painting | 100 | 0 |  | 2026-06-02 |  | 2026-06-24
9841 | T-16-9th Floor Common Area | Not Ready | Window-Open Area | 2026-06-22 | 2026-06-30 | Window-Open Area | 100 | 0 |  | 2026-06-02 |  | 2026-06-09
9866 | T-16-11th Floor Common Area | Not Ready | Door-Shaft | 2026-06-25 | 2026-07-08 | Door-Shaft | 100 | 0 |  | 2026-06-02 |  | 2026-06-16
10941 | T-20-Lift | Not Ready | OTS Covers | 2026-07-09 | 2026-08-11 | OTS Covers | 100 | 0 |  | 2026-06-02 |  | 2026-07-03
11989 | T-18-Lift Lobby | Not Ready |  | 2026-08-20 | 2026-09-05 | 08F | 100 | 0 |  | 2026-06-02 |  | 2026-06-18
41618 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-05-11 | 2026-05-16 | Final Painting | 100 | 0 |  | 2026-06-02 |  | 2026-06-08 |  | Tower A | Super Structure | L41 | Finishes | Final Painting
41618 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-05-11 | 2026-05-16 | Final Painting | 100 | 0 |  | 2026-06-02 |  | 2026-06-08 |  | Tower A | Super Structure | L41 | Finishes | Final Painting
41618 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-05-11 | 2026-05-16 | Final Painting | 100 | 0 |  | 2026-06-02 |  | 2026-06-08 |  | Tower A | Super Structure | L41 | Finishes | Final Painting
41660 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-05-11 | 2026-05-14 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-06-02 |  | 2026-06-05 |  | Tower A | Super Structure | L44 | MEP | FPS 2nd Fix - MEP & Finishes
41661 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-05-11 | 2026-05-16 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-06-02 |  | 2026-06-08 |  | Tower A | Super Structure | L44 | MEP | Electrical 2nd Fix - MEP & Finishes
41662 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-05-11 | 2026-05-19 | FAPA Device Fixing | 100 | 0 |  | 2026-06-02 |  | 2026-06-10 |  | Tower A | Super Structure | L44
41662 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-05-11 | 2026-05-19 | FAPA Device Fixing | 100 | 0 |  | 2026-06-02 |  | 2026-06-10 |  | Tower A | Super Structure | L44
41662 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-05-11 | 2026-05-19 | FAPA Device Fixing | 100 | 0 |  | 2026-06-02 |  | 2026-06-10 |  | Tower A | Super Structure | L44
41662 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-05-11 | 2026-05-19 | FAPA Device Fixing | 100 | 0 |  | 2026-06-02 |  | 2026-06-10 |  | Tower A | Super Structure | L44
41663 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-05-11 | 2026-05-14 | HVAC Grill Fixing | 100 | 0 |  | 2026-06-02 |  | 2026-06-05 |  | Tower A | Super Structure | L44 | MEP | HVAC Grill Fixing
44628 |  | Not Ready | MEP fix & Finishes | 2026-06-04 | 2026-06-15 | Final Painting | 100 | 0 |  | 2026-06-02 |  | 2026-06-12 |  |  |  |  | Finishes | Final Painting
44628 |  | Not Ready | MEP fix & Finishes | 2026-06-04 | 2026-06-15 | Final Painting | 100 | 0 |  | 2026-06-02 |  | 2026-06-12 |  |  |  |  | Finishes | Final Painting
44628 |  | Not Ready | MEP fix & Finishes | 2026-06-04 | 2026-06-15 | Final Painting | 100 | 0 |  | 2026-06-02 |  | 2026-06-12 |  |  |  |  | Finishes | Final Painting
45788 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-03-27 | 2026-04-07 | FAPA Cabling | 100 | 0 |  | 2026-06-02 |  | 2026-06-13 |  | Tower B | Sub Structure | B3
45846 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | VDF/ Grade Slab - MEP & Finishes | 2026-03-27 | 2026-04-01 | VDF/ Grade Slab | 100 | 0 |  | 2026-06-02 |  | 2026-06-08 |  | Tower B | Sub Structure | B1
46013 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-03-27 | 2026-04-03 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-06-02 |  | 2026-06-10 |  | Tower B | Super Structure |  | MEP | FPS 2nd Fix - MEP & Finishes
46014 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-27 | 2026-04-03 | FAPA Device Fixing | 100 | 0 |  | 2026-06-02 |  | 2026-06-10 |  | Tower B | Super Structure
46014 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-27 | 2026-04-03 | FAPA Device Fixing | 100 | 0 |  | 2026-06-02 |  | 2026-06-10 |  | Tower B | Super Structure
46014 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-27 | 2026-04-03 | FAPA Device Fixing | 100 | 0 |  | 2026-06-02 |  | 2026-06-10 |  | Tower B | Super Structure
46014 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-03-27 | 2026-04-03 | FAPA Device Fixing | 100 | 0 |  | 2026-06-02 |  | 2026-06-10 |  | Tower B | Super Structure
47693 |  | Not Committed |  | 2026-06-02 | 2026-08-28 | Pour 8 (grid PB-D to PB-K) | 100 | 0 |  | 2026-06-02 |  | 2027-01-19
47694 |  | Not Ready |  | 2026-06-02 | 2026-06-18 | Columns/ Walls_NTA | 100 | 0 |  | 2026-06-02 |  | 2026-06-18
47694 |  | Not Ready |  | 2026-06-02 | 2026-06-18 | Columns/ Walls_NTA | 100 | 0 |  | 2026-06-02 |  | 2026-06-18 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
47804 |  | Not Committed |  | 2026-05-02 | 2027-07-28 | Masonry Works (incl. de-shutt, PT mark, B/W) | 100 | 0 |  | 2026-06-02 |  | 2027-11-12
47806 |  | Not Ready |  | 2026-06-02 | 2026-07-18 | B2 to B1 | 100 | 0 |  | 2026-06-02 |  | 2026-07-18
47806 |  | Not Ready |  | 2026-06-02 | 2026-07-18 | B2 to B1 | 100 | 0 |  | 2026-06-02 |  | 2026-07-18
47806 |  | Not Ready |  | 2026-06-02 | 2026-07-18 | B2 to B1 | 100 | 0 |  | 2026-06-02 |  | 2026-07-18
9922 | T-16-Staircase 1 | Not Ready |  | 2026-06-19 | 2026-07-01 | 11F-10F | 100 | 0 |  | 2026-06-03 |  | 2026-06-13
9936 | T-16-Staircase 2 | Not Ready |  | 2026-06-19 | 2026-07-01 | 12F-11F | 100 | 0 |  | 2026-06-03 |  | 2026-06-13
10431 | T-21-Lift Lobby | Not Ready |  | 2026-07-02 | 2026-07-18 | 06F | 100 | 0 |  | 2026-06-03 |  | 2026-06-18
10674 | T-20-1st Floor Common Area | Not Ready | 1st Coat Painting | 2026-06-26 | 2026-07-18 | 1st Coat Painting | 100 | 0 |  | 2026-06-03 |  | 2026-06-24
10950 | T-20-Lift Lobby | Not Ready |  | 2026-06-27 | 2026-07-14 | 07F | 100 | 0 |  | 2026-06-03 |  | 2026-06-18
11245 | T-19-3rd Floor Common Area | Not Ready | Window-Open Area | 2026-06-17 | 2026-06-24 | Window-Open Area | 100 | 0 |  | 2026-06-03 |  | 2026-06-14
41649 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-05-12 | 2026-05-18 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-06-03 |  | 2026-06-09 |  | Tower A | Super Structure | L43 | MEP | Electrical
41719 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-05-12 | 2026-05-20 | HVAC Ducting | 100 | 0 |  | 2026-06-03 |  | 2026-06-11 |  | Tower A | Super Structure | L48 | MEP | HVAC Ducting
41732 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-05-12 | 2026-05-18 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-06-03 |  | 2026-06-09 |  | Tower A | Super Structure | L49 | MEP | FPS 1st Fix - MEP & Finishes
41733 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-05-12 | 2026-05-15 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-06-03 |  | 2026-06-06 |  | Tower A | Super Structure | L49 | MEP | Electrical 1st Fixes
42378 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-06-05 | 2026-06-08 | PHE Final Fixes | 100 | 0 |  | 2026-06-03 |  | 2026-06-05 |  | Tower A | Super Structure | L16
42396 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-06-05 | 2026-06-08 | PHE Final Fixes | 100 | 0 |  | 2026-06-03 |  | 2026-06-05 |  | Tower A | Super Structure | L17
42414 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-06-05 | 2026-06-08 | PHE Final Fixes | 100 | 0 |  | 2026-06-03 |  | 2026-06-05 |  | Tower A | Super Structure | L18
42431 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-06-05 | 2026-06-10 | False Ceiling | 100 | 0 |  | 2026-06-03 |  | 2026-06-08 |  | Tower A | Super Structure | L19 | Finishes | False Ceiling
42449 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-06-05 | 2026-06-10 | False Ceiling | 100 | 0 |  | 2026-06-03 |  | 2026-06-08 |  | Tower A | Super Structure | L20 | Finishes | False Ceiling
42467 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-06-05 | 2026-06-10 | False Ceiling | 100 | 0 |  | 2026-06-03 |  | 2026-06-08 |  | Tower A | Super Structure | L21 | Finishes | False Ceiling
43307 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-05-11 | 2026-05-18 | Door & Window Frame work | 100 | 0 |  | 2026-06-03 |  | 2026-06-10 |  | Tower A | Super Structure | L68 | Finishes | Door & Window Frame work
43991 | Tower A - Super Structure - Finishes & MEP - L35 to L45 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-07-03 | 2026-08-12 | Staircase Window | 100 | 0 |  | 2026-06-03 |  | 2026-07-08 |  | Tower A | Super Structure | L35
43993 | Tower A - Super Structure - Finishes & MEP - L35 to L45 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-07-03 | 2026-07-15 | Staircase cabling | 100 | 0 |  | 2026-06-03 |  | 2026-06-15 |  | Tower A | Super Structure | L35
45306 | Tower B - Super Structure - Core & Outer Slab L18-19 | Not Ready | RCC Works - Slab | 2026-03-19 | 2026-03-25 | Outer Slab_TA | 100 | 0 |  | 2026-06-03 |  | 2026-06-11 |  | Tower B | Super Structure | L18 | RCC Sub Structure | RCC Works - Slab
9323 | T-15-9th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-06-10 | 2026-07-13 | 2nd Coat Painting | 100 | 0 |  | 2026-06-04 |  | 2026-07-07
9341 | T-15-10th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-06-10 | 2026-08-16 | 2nd Coat Painting | 100 | 0 |  | 2026-06-04 |  | 2026-08-07
11654 | T-18-Basement Floor | Not Ready | 2nd Coat Painting | 2026-09-07 | 2026-11-25 | 2nd Coat Painting | 100 | 0 |  | 2026-06-04 |  | 2026-08-21
40098 | Tower A - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2026-05-06 | 2026-05-22 | Exhaust Piping & Insulation | 100 | 0 |  | 2026-06-04 |  | 2026-06-22 |  | Tower A | Super Structure
9791 | T-16-7th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-06-24 | 2026-07-27 | 2nd Coat Painting | 100 | 0 |  | 2026-06-05 |  | 2026-07-09
9898 | T-16-Lift | Not Ready | LMR ROOM | 2026-07-03 | 2026-09-07 | Lift Machine Rooms | 100 | 0 |  | 2026-06-05 |  | 2026-08-11
9900 | T-16-Lift | Not Ready | PARAPET | 2026-07-01 | 2026-09-05 | Parapets | 100 | 0 |  | 2026-06-05 |  | 2026-08-11
9906 | T-16-Lift Lobby | Not Ready |  | 2026-06-25 | 2026-07-11 | 11F | 100 | 0 |  | 2026-06-05 |  | 2026-06-24
9952 | T-16- Elevation-B | Not Ready |  | 2026-06-25 | 2026-09-16 | Elevation-B | 100 | 0 |  | 2026-06-05 |  | 2026-08-27
10993 | T-20- Elevation-C | Not Ready |  | 2026-07-02 | 2026-09-23 | Elevation-C | 100 | 0 |  | 2026-06-05 |  | 2026-08-27
11740 | T-18-2nd Floor Common Area | Not Ready | 1st Coat Painting | 2026-08-12 | 2026-09-04 | 1st Coat Painting | 100 | 0 |  | 2026-06-05 |  | 2026-06-25
41634 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-05-14 | 2026-05-20 | Final Painting | 100 | 0 |  | 2026-06-05 |  | 2026-06-11 |  | Tower A | Super Structure | L42 | Finishes | Final Painting
41634 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-05-14 | 2026-05-20 | Final Painting | 100 | 0 |  | 2026-06-05 |  | 2026-06-11 |  | Tower A | Super Structure | L42 | Finishes | Final Painting
41634 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-05-14 | 2026-05-20 | Final Painting | 100 | 0 |  | 2026-06-05 |  | 2026-06-11 |  | Tower A | Super Structure | L42 | Finishes | Final Painting
41664 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-05-14 | 2026-05-18 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-06-05 |  | 2026-06-09 |  | Tower A | Super Structure | L44
41691 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-05-14 | 2026-05-22 | False Ceiling | 100 | 0 |  | 2026-06-05 |  | 2026-06-13 |  | Tower A | Super Structure | L46 | Finishes | False Ceiling
41706 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-05-14 | 2026-05-26 | Flooring & Dado | 100 | 0 |  | 2026-06-05 |  | 2026-06-17 |  | Tower A | Super Structure | L47 | Finishes | Flooring & Dado
42483 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-06-08 | 2026-06-10 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-06-05 |  | 2026-06-08 |  | Tower A | Super Structure | L22 | MEP | FPS 2nd Fix - MEP & Finishes
42484 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-06-08 | 2026-06-10 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-06-05 |  | 2026-06-08 |  | Tower A | Super Structure | L22 | MEP | Electrical 2nd Fix - MEP & Finishes
42501 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-06-08 | 2026-06-10 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-06-05 |  | 2026-06-08 |  | Tower A | Super Structure | L23 | MEP | FPS 2nd Fix - MEP & Finishes
42502 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-06-08 | 2026-06-10 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-06-05 |  | 2026-06-08 |  | Tower A | Super Structure | L23 | MEP | Electrical 2nd Fix - MEP & Finishes
42519 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-06-08 | 2026-06-10 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-06-05 |  | 2026-06-08 |  | Tower A | Super Structure | L24 | MEP | FPS 2nd Fix - MEP & Finishes
42520 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-06-08 | 2026-06-10 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-06-05 |  | 2026-06-08 |  | Tower A | Super Structure | L24 | MEP | Electrical 2nd Fix - MEP & Finishes
42535 |  | Not Committed |  | 2026-06-08 | 2026-06-29 | MEP final fix & Finishes | 100 | 0 |  | 2026-06-05 |  | 2026-06-26
42536 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-06-08 | 2026-06-12 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-06-05 |  | 2026-06-10 |  | Tower A | Super Structure | L25 | Finishes | Door & Window Fixing
42553 |  | Not Committed |  | 2026-06-08 | 2026-06-29 | MEP final fix & Finishes | 100 | 0 |  | 2026-06-05 |  | 2026-06-26
42554 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-06-08 | 2026-06-12 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-06-05 |  | 2026-06-10 |  | Tower A | Super Structure | L26 | Finishes | Door & Window Fixing
42571 |  | Not Committed |  | 2026-06-08 | 2026-06-29 | MEP final fix & Finishes | 100 | 0 |  | 2026-06-05 |  | 2026-06-26
42572 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-06-08 | 2026-06-12 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-06-05 |  | 2026-06-10 |  | Tower A | Super Structure | L27 | Finishes | Door & Window Fixing
43236 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-05-13 | 2026-06-17 | Flooring & Dado works | 100 | 0 |  | 2026-06-05 |  | 2026-07-09 |  | Tower A | Super Structure | L64 | Finishes | Flooring & Dado
43325 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-05-13 | 2026-05-20 | Door & Window Frame work | 100 | 0 |  | 2026-06-05 |  | 2026-06-12 |  | Tower A | Super Structure | L69 | Finishes | Door & Window Frame work
44623 |  | Not Ready | MEP fix & Finishes | 2026-06-08 | 2026-06-12 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-06-05 |  | 2026-06-10
44623 |  | Not Ready | MEP fix & Finishes | 2026-06-08 | 2026-06-12 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-06-05 |  | 2026-06-10
44623 |  | Not Ready | MEP fix & Finishes | 2026-06-08 | 2026-06-12 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-06-05 |  | 2026-06-10
46768 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-03-31 | 2026-04-16 | Wet Area Waterproofing | 100 | 0 |  | 2026-06-05 |  | 2026-06-23 |  | Tower B | Super Structure | L13
48045 | Club House - Super structure - CH01 to CH02 | Not Ready |  | 2026-02-12 | 2026-02-28 | Slab_CH | 100 | 0 |  | 2026-06-05 |  | 2026-06-22 |  | Club House | Super Structure | CH01
9389 | T-15-Lift Lobby | Not Ready |  | 2026-06-17 | 2026-07-03 | 08F | 100 | 0 |  | 2026-06-06 |  | 2026-06-20
11377 | T-19-8th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-06-24 | 2026-07-27 | 2nd Coat Painting | 100 | 0 |  | 2026-06-06 |  | 2026-07-07
11467 | T-19-Lift Lobby | Not Ready |  | 2026-06-20 | 2026-07-07 | 10F | 100 | 0 |  | 2026-06-06 |  | 2026-06-22
40068 | Tower A - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2026-05-14 | 2026-05-19 | Obtaining PWD Lisence | 100 | 0 |  | 2026-06-06 |  | 2026-06-12 |  | Tower A | Super Structure
40068 | Tower A - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2026-05-14 | 2026-05-19 | Obtaining PWD Lisence | 100 | 0 |  | 2026-06-06 |  | 2026-06-12 |  | Tower A | Super Structure
41734 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-05-15 | 2026-05-18 | FAPA Cabling | 100 | 0 |  | 2026-06-06 |  | 2026-06-09 |  | Tower A | Super Structure | L49
42379 | Tower A - Super Structure - Finishes & MEP - L16 to L17 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-09 | 2026-06-11 | Painting Works | 100 | 0 |  | 2026-06-06 |  | 2026-06-09 |  | Tower A | Super Structure | L16 | Finishes | Painting Works
42397 | Tower A - Super Structure - Finishes & MEP - L17 to L18 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-09 | 2026-06-11 | Painting Works | 100 | 0 |  | 2026-06-06 |  | 2026-06-09 |  | Tower A | Super Structure | L17 | Finishes | Painting Works
42415 | Tower A - Super Structure - Finishes & MEP - L18 to L19 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-09 | 2026-06-11 | Painting Works | 100 | 0 |  | 2026-06-06 |  | 2026-06-09 |  | Tower A | Super Structure | L18 | Finishes | Painting Works
43431 |  | Not Committed |  | 2026-05-08 | 2026-08-26 | Finishes after 1st Fix | 100 | 0 |  | 2026-06-06 |  | 2026-08-12
43432 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-05-08 | 2026-06-01 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-06-06 |  | 2026-06-30 |  | Tower A | Super Structure | L77 | Finishes | Blockwork
45464 | Tower B - Super Structure - Finishes & MEP - L14 to L15 | Not Ready | Partition Wall-Blockwork | 2026-03-28 | 2026-04-02 | Staircase Area | 100 | 0 |  | 2026-06-06 |  | 2026-06-12 |  | Tower B | Super Structure | L14
8777 | T-14-9th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-05-12 | 2026-06-14 | 2nd Coat Painting | 100 | 0 |  | 2026-06-07 |  | 2026-07-10
8795 | T-14-10th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-05-12 | 2026-07-17 | 2nd Coat Painting | 100 | 0 |  | 2026-06-07 |  | 2026-08-13
11152 | T-19-GF Flat Area | Not Ready | 2nd Coat Painting | 2026-07-14 | 2026-09-18 | 2nd Coat Painting | 100 | 0 |  | 2026-06-07 |  | 2026-08-11
11428 | T-19-11th Floor Common Area | Not Ready | 1st Coat Painting | 2026-06-24 | 2026-07-16 | 1st Coat Painting | 100 | 0 |  | 2026-06-07 |  | 2026-06-29
41676 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-05-16 | 2026-05-20 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-06-08 |  | 2026-06-11 |  | Tower A | Super Structure | L45 | MEP | FPS 2nd Fix - MEP & Finishes
41677 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-05-16 | 2026-05-22 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-06-08 |  | 2026-06-13 |  | Tower A | Super Structure | L45 | MEP | Electrical 2nd Fix - MEP & Finishes
41678 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-05-16 | 2026-05-25 | FAPA Device Fixing | 100 | 0 |  | 2026-06-08 |  | 2026-06-16 |  | Tower A | Super Structure | L45
41678 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-05-16 | 2026-05-25 | FAPA Device Fixing | 100 | 0 |  | 2026-06-08 |  | 2026-06-16 |  | Tower A | Super Structure | L45
41678 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-05-16 | 2026-05-25 | FAPA Device Fixing | 100 | 0 |  | 2026-06-08 |  | 2026-06-16 |  | Tower A | Super Structure | L45
41678 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-05-16 | 2026-05-25 | FAPA Device Fixing | 100 | 0 |  | 2026-06-08 |  | 2026-06-16 |  | Tower A | Super Structure | L45
41679 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-05-16 | 2026-05-20 | HVAC Grill Fixing | 100 | 0 |  | 2026-06-08 |  | 2026-06-11 |  | Tower A | Super Structure | L45 | MEP | HVAC Grill Fixing
42173 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-05-15 | 2026-05-22 | Door & Window Frame work | 100 | 0 |  | 2026-06-08 |  | 2026-06-15 |  | Tower A | Super Structure | L75 | Finishes | Door & Window Frame work
43343 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-05-15 | 2026-05-22 | Door & Window Frame work | 100 | 0 |  | 2026-06-08 |  | 2026-06-15 |  | Tower A | Super Structure | L70 | Finishes | Door & Window Frame work
43415 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-05-15 | 2026-05-22 | Door & Window Frame work | 100 | 0 |  | 2026-06-08 |  | 2026-06-15 |  | Tower A | Super Structure | L74 | Finishes | Door & Window Frame work
45819 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | VDF/ Grade Slab - MEP & Finishes | 2026-04-02 | 2026-04-07 | VDF/ Grade Slab | 100 | 0 |  | 2026-06-08 |  | 2026-06-13 |  | Tower B | Sub Structure | B2
45844 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-04-02 | 2026-04-24 | FAPA Cabling | 100 | 0 |  | 2026-06-08 |  | 2026-07-01 |  | Tower B | Sub Structure | B1
45847 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-04-02 | 2026-04-18 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-06-08 |  | 2026-06-25 |  | Tower B | Sub Structure | B1 | MEP | FPS 2nd Fix - MEP & Finishes
45848 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-02 | 2026-04-18 | FAPA Device Fixing | 100 | 0 |  | 2026-06-08 |  | 2026-06-25 |  | Tower B | Sub Structure | B1
45848 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-02 | 2026-04-18 | FAPA Device Fixing | 100 | 0 |  | 2026-06-08 |  | 2026-06-25 |  | Tower B | Sub Structure | B1
45848 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-02 | 2026-04-18 | FAPA Device Fixing | 100 | 0 |  | 2026-06-08 |  | 2026-06-25 |  | Tower B | Sub Structure | B1
45848 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-02 | 2026-04-18 | FAPA Device Fixing | 100 | 0 |  | 2026-06-08 |  | 2026-06-25 |  | Tower B | Sub Structure | B1
45986 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-04-02 | 2026-04-09 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-06-08 |  | 2026-06-16 |  | Tower B | Super Structure |  | MEP | FPS 2nd Fix - MEP & Finishes
45987 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-02 | 2026-04-09 | FAPA Device Fixing | 100 | 0 |  | 2026-06-08 |  | 2026-06-16 |  | Tower B | Super Structure
45987 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-02 | 2026-04-09 | FAPA Device Fixing | 100 | 0 |  | 2026-06-08 |  | 2026-06-16 |  | Tower B | Super Structure
45987 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-02 | 2026-04-09 | FAPA Device Fixing | 100 | 0 |  | 2026-06-08 |  | 2026-06-16 |  | Tower B | Super Structure
45987 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-02 | 2026-04-09 | FAPA Device Fixing | 100 | 0 |  | 2026-06-08 |  | 2026-06-16 |  | Tower B | Super Structure
46751 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-04-02 | 2026-04-13 | Cement Plastering in wet areas | 100 | 0 |  | 2026-06-08 |  | 2026-06-19 |  | Tower B | Super Structure | L12
9054 | T-15-Basement Floor | Not Ready | 2nd Coat Painting | 2026-07-06 | 2026-09-21 | 2nd Coat Painting | 100 | 0 |  | 2026-06-09 |  | 2026-08-25
9139 | T-15-2nd Floor Common Area | Not Ready | Window-Open Area | 2026-06-03 | 2026-06-10 | Window-Open Area | 100 | 0 |  | 2026-06-09 |  | 2026-06-16
9899 | T-16-Lift | Not Ready | STAIRCASE HR | 2026-07-07 | 2026-09-11 | Staircase Headrooms | 100 | 0 |  | 2026-06-09 |  | 2026-08-13
10450 | T-21-Staircase 1 | Not Ready |  | 2026-07-02 | 2026-07-13 | 03F-02F | 100 | 0 |  | 2026-06-09 |  | 2026-06-21
10464 | T-21-Staircase 2 | Not Ready |  | 2026-07-02 | 2026-07-13 | 04F-03F | 100 | 0 |  | 2026-06-09 |  | 2026-06-21
11712 | T-18-1st Floor Common Area | Not Ready | Door-Shaft | 2026-08-13 | 2026-08-27 | Door-Shaft | 100 | 0 |  | 2026-06-09 |  | 2026-06-22
12007 | T-18-Staircase 1 | Not Ready |  | 2026-08-20 | 2026-08-31 | 06F-05F | 100 | 0 |  | 2026-06-09 |  | 2026-06-21
12021 | T-18-Staircase 2 | Not Ready |  | 2026-08-20 | 2026-08-31 | 07F-06F | 100 | 0 |  | 2026-06-09 |  | 2026-06-21
40118 | Tower A - Super Structure - Finishes & MEP - Sub Station | Not Ready | Sub Station - High Side Services | 2026-06-11 | 2026-06-27 | Testing & Commissioning | 100 | 0 |  | 2026-06-09 |  | 2026-06-25 |  | Tower A | Super Structure
40118 | Tower A - Super Structure - Finishes & MEP - Sub Station | Not Ready | Sub Station - High Side Services | 2026-06-11 | 2026-06-27 | Testing & Commissioning | 100 | 0 |  | 2026-06-09 |  | 2026-06-25 |  | Tower A | Super Structure
41650 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-05-18 | 2026-05-23 | Final Painting | 100 | 0 |  | 2026-06-09 |  | 2026-06-15 |  | Tower A | Super Structure | L43 | Finishes | Final Painting
41650 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-05-18 | 2026-05-23 | Final Painting | 100 | 0 |  | 2026-06-09 |  | 2026-06-15 |  | Tower A | Super Structure | L43 | Finishes | Final Painting
41650 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-05-18 | 2026-05-23 | Final Painting | 100 | 0 |  | 2026-06-09 |  | 2026-06-15 |  | Tower A | Super Structure | L43 | Finishes | Final Painting
41665 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-05-18 | 2026-05-23 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-06-09 |  | 2026-06-15 |  | Tower A | Super Structure | L44 | MEP | Electrical
41735 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-05-18 | 2026-05-26 | HVAC Ducting | 100 | 0 |  | 2026-06-09 |  | 2026-06-17 |  | Tower A | Super Structure | L49 | MEP | HVAC Ducting
41748 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-05-18 | 2026-05-23 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-06-09 |  | 2026-06-15 |  | Tower A | Super Structure | L50 | MEP | FPS 1st Fix - MEP & Finishes
41749 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-05-18 | 2026-05-21 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-06-09 |  | 2026-06-12 |  | Tower A | Super Structure | L50 | MEP | Electrical 1st Fixes
42432 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-06-11 | 2026-06-13 | PHE Final Fixes | 100 | 0 |  | 2026-06-09 |  | 2026-06-11 |  | Tower A | Super Structure | L19
42450 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-06-11 | 2026-06-13 | PHE Final Fixes | 100 | 0 |  | 2026-06-09 |  | 2026-06-11 |  | Tower A | Super Structure | L20
42468 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-06-11 | 2026-06-13 | PHE Final Fixes | 100 | 0 |  | 2026-06-09 |  | 2026-06-11 |  | Tower A | Super Structure | L21
42485 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-06-11 | 2026-06-16 | False Ceiling | 100 | 0 |  | 2026-06-09 |  | 2026-06-13 |  | Tower A | Super Structure | L22 | Finishes | False Ceiling
42503 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-06-11 | 2026-06-16 | False Ceiling | 100 | 0 |  | 2026-06-09 |  | 2026-06-13 |  | Tower A | Super Structure | L23 | Finishes | False Ceiling
42521 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-06-11 | 2026-06-11 | False Ceiling | 100 | 0 |  | 2026-06-09 |  | 2026-06-09 |  | Tower A | Super Structure | L24 | Finishes | False Ceiling
43992 | Tower A - Super Structure - Finishes & MEP - L35 to L45 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-07-09 | 2026-08-05 | Staircase Railing | 100 | 0 |  | 2026-06-09 |  | 2026-07-02 |  | Tower A | Super Structure | L35
43998 | Tower A - Super Structure - Finishes & MEP - L45 to L55 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-07-09 | 2026-08-20 | Staircase Window | 100 | 0 |  | 2026-06-09 |  | 2026-07-15 |  | Tower A | Super Structure | L45
44002 |  | Not Committed |  | 2026-07-09 | 2026-10-03 | L55-65 | 100 | 0 |  | 2026-06-09 |  | 2026-08-12
44002 |  | Not Committed |  | 2026-07-09 | 2026-10-03 | L55-65 | 100 | 0 |  | 2026-06-09 |  | 2026-08-12
44004 | Tower A - Super Structure - Finishes & MEP - L55 to L65 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-07-09 | 2026-09-07 | Staircase Flooring | 100 | 0 |  | 2026-06-09 |  | 2026-08-05 |  | Tower A | Super Structure | L55 | Finishes | Staircase Flooring
45616 | Tower B - Super Structure - Finishes & MEP - L13 to L14 | Not Ready | Gypsum Plastering Works | 2026-04-03 | 2026-05-20 | L13-14 | 100 | 0 |  | 2026-06-09 |  | 2026-07-29 |  | Tower B | Super Structure | L13 | Finishes | Gypsum Plastering Works
45616 | Tower B - Super Structure - Finishes & MEP - L13 to L14 | Not Ready | Gypsum Plastering Works | 2026-04-03 | 2026-05-20 | L13-14 | 100 | 0 |  | 2026-06-09 |  | 2026-07-29 |  | Tower B | Super Structure | L13
47668 |  | Not Ready |  | 2026-06-09 | 2026-06-20 | Section 2_lift 1 | 100 | 0 |  | 2026-06-09 |  | 2026-06-20
47668 |  | Not Ready |  | 2026-06-09 | 2026-06-20 | Section 2_lift 1 | 100 | 0 |  | 2026-06-09 |  | 2026-06-20 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47670 |  | Not Ready |  | 2026-06-09 | 2026-06-20 | Section 4_lift 1 | 100 | 0 |  | 2026-06-09 |  | 2026-06-20
47670 |  | Not Ready |  | 2026-06-09 | 2026-06-20 | Section 4_lift 1 | 100 | 0 |  | 2026-06-09 |  | 2026-06-20 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47678 |  | Not Committed |  | 2026-06-09 | 2026-09-10 | Retaining Wall_lift 2 | 100 | 0 |  | 2026-06-09 |  | 2027-01-28
47678 |  | Not Committed |  | 2026-06-09 | 2026-09-10 | Retaining Wall_lift 2 | 100 | 0 |  | 2026-06-09 |  | 2027-01-28 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47679 |  | Not Ready |  | 2026-06-09 | 2026-06-16 | Section 1_lift 2 | 100 | 0 |  | 2026-06-09 |  | 2026-06-16
47679 |  | Not Ready |  | 2026-06-09 | 2026-06-16 | Section 1_lift 2 | 100 | 0 |  | 2026-06-09 |  | 2026-06-16 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47681 |  | Not Ready |  | 2026-06-09 | 2026-06-16 | Section 3_lift 2 | 100 | 0 |  | 2026-06-09 |  | 2026-06-16
47681 |  | Not Ready |  | 2026-06-09 | 2026-06-16 | Section 3_lift 2 | 100 | 0 |  | 2026-06-09 |  | 2026-06-16 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
9407 | T-15-Staircase 1 | Not Ready |  | 2026-06-17 | 2026-06-28 | 06F-05F | 100 | 0 |  | 2026-06-10 |  | 2026-06-21
9421 | T-15-Staircase 2 | Not Ready |  | 2026-06-17 | 2026-06-28 | 07F-06F | 100 | 0 |  | 2026-06-10 |  | 2026-06-21
9684 | T-16-3rd Floor Common Area | Not Ready | Door-Shaft | 2026-06-25 | 2026-07-08 | Door-Shaft | 100 | 0 |  | 2026-06-10 |  | 2026-06-24
9842 | T-16-9th Floor Common Area | Not Ready | 1st Coat Painting | 2026-06-30 | 2026-07-21 | 1st Coat Painting | 100 | 0 |  | 2026-06-10 |  | 2026-07-01
11484 | T-19-Staircase 1 | Not Ready |  | 2026-06-20 | 2026-07-01 | 09F-08F | 100 | 0 |  | 2026-06-10 |  | 2026-06-21
11498 | T-19-Staircase 2 | Not Ready |  | 2026-06-20 | 2026-07-01 | 10F-09F | 100 | 0 |  | 2026-06-10 |  | 2026-06-21
11949 | T-18-11th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-08-29 | 2026-10-01 | 2nd Coat Painting | 100 | 0 |  | 2026-06-10 |  | 2026-07-11
11967 | T-18-11th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-08-29 | 2026-11-05 | 2nd Coat Painting | 100 | 0 |  | 2026-06-10 |  | 2026-08-15
42522 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-06-12 | 2026-06-12 | PHE Final Fixes | 100 | 0 |  | 2026-06-10 |  | 2026-06-10 |  | Tower A | Super Structure | L24
43361 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-05-18 | 2026-05-25 | Door & Window Frame work | 100 | 0 |  | 2026-06-10 |  | 2026-06-17 |  | Tower A | Super Structure | L71 | Finishes | Door & Window Frame work
46015 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-04 | 2026-04-13 | Final Painting | 100 | 0 |  | 2026-06-10 |  | 2026-06-19 |  | Tower B | Super Structure |  | Finishes | Final Painting
46015 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-04 | 2026-04-13 | Final Painting | 100 | 0 |  | 2026-06-10 |  | 2026-06-19 |  | Tower B | Super Structure |  | Finishes | Final Painting
46015 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-04 | 2026-04-13 | Final Painting | 100 | 0 |  | 2026-06-10 |  | 2026-06-19 |  | Tower B | Super Structure |  | Finishes | Final Painting
8883 | T-14-Staircase 1 | Not Ready |  | 2026-05-08 | 2026-05-19 | 10F-09F | 100 | 0 |  | 2026-06-11 |  | 2026-06-22
8897 | T-14-Staircase 2 | Not Ready |  | 2026-05-08 | 2026-05-19 | 11F-10F | 100 | 0 |  | 2026-06-11 |  | 2026-06-22
11395 | T-19-9th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-06-30 | 2026-09-04 | 2nd Coat Painting | 100 | 0 |  | 2026-06-11 |  | 2026-08-15
41680 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-05-20 | 2026-05-23 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-06-11 |  | 2026-06-15 |  | Tower A | Super Structure | L45
41707 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-05-20 | 2026-05-29 | False Ceiling | 100 | 0 |  | 2026-06-11 |  | 2026-06-19 |  | Tower A | Super Structure | L47 | Finishes | False Ceiling
41722 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-05-20 | 2026-06-02 | Flooring & Dado | 100 | 0 |  | 2026-06-11 |  | 2026-06-23 |  | Tower A | Super Structure | L48 | Finishes | Flooring & Dado
42523 | Tower A - Super Structure - Finishes & MEP - L24 to L25 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-13 | 2026-06-16 | Painting Works | 100 | 0 |  | 2026-06-11 |  | 2026-06-13 |  | Tower A | Super Structure | L24 | Finishes | Painting Works
42537 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-06-13 | 2026-06-16 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-06-11 |  | 2026-06-13 |  | Tower A | Super Structure | L25 | MEP | FPS 2nd Fix - MEP & Finishes
42538 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-06-13 | 2026-06-16 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-06-11 |  | 2026-06-13 |  | Tower A | Super Structure | L25 | MEP | Electrical 2nd Fix - MEP & Finishes
42555 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-06-13 | 2026-06-16 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-06-11 |  | 2026-06-13 |  | Tower A | Super Structure | L26 | MEP | FPS 2nd Fix - MEP & Finishes
42556 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-06-13 | 2026-06-16 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-06-11 |  | 2026-06-13 |  | Tower A | Super Structure | L26 | MEP | Electrical 2nd Fix - MEP & Finishes
42573 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-06-13 | 2026-06-16 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-06-11 |  | 2026-06-13 |  | Tower A | Super Structure | L27 | MEP | FPS 2nd Fix - MEP & Finishes
42574 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-06-13 | 2026-06-16 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-06-11 |  | 2026-06-13 |  | Tower A | Super Structure | L27 | MEP | Electrical 2nd Fix - MEP & Finishes
42589 |  | Not Committed |  | 2026-06-13 | 2026-07-04 | MEP final fix & Finishes | 100 | 0 |  | 2026-06-11 |  | 2026-07-02
42590 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-06-13 | 2026-06-18 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-06-11 |  | 2026-06-16 |  | Tower A | Super Structure | L28 | Finishes | Door & Window Fixing
42607 |  | Not Committed |  | 2026-06-13 | 2026-07-04 | MEP final fix & Finishes | 100 | 0 |  | 2026-06-11 |  | 2026-07-02
42608 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-06-13 | 2026-06-18 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-06-11 |  | 2026-06-16 |  | Tower A | Super Structure | L29 | Finishes | Door & Window Fixing
42625 |  | Not Committed |  | 2026-06-13 | 2026-07-04 | MEP final fix & Finishes | 100 | 0 |  | 2026-06-11 |  | 2026-07-02
42626 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-06-13 | 2026-06-18 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-06-11 |  | 2026-06-16 |  | Tower A | Super Structure | L30 | Finishes | Door & Window Fixing
44020 | Tower A - Super Structure - Finishes & MEP - GF to P1 | Not Ready | Façade Works - MEP & Finishes | 2026-08-29 | 2026-09-10 | DGU Assembly Installation | 100 | 0 |  | 2026-06-11 |  | 2026-06-23 |  | Tower A | Super Structure | GF | Façade | Façade Works
44021 | Tower A - Super Structure - Finishes & MEP - GF to P1 | Not Ready | Façade Works - MEP & Finishes | 2026-08-29 | 2026-09-10 | Installation of highly reflective metal sheet | 100 | 0 |  | 2026-06-11 |  | 2026-06-23 |  | Tower A | Super Structure | GF | Façade | Façade Works
44022 | Tower A - Super Structure - Finishes & MEP - GF to P1 | Not Ready | Façade Works - MEP & Finishes | 2026-08-29 | 2026-09-10 | Fixing of Backlit Laminated Glass assembly & ACP Panels | 100 | 0 |  | 2026-06-11 |  | 2026-06-23 |  | Tower A | Super Structure | GF | Façade | Façade Works
44023 | Tower A - Super Structure - Finishes & MEP - GF to P1 | Not Ready | Façade Works - MEP & Finishes | 2026-08-29 | 2026-09-10 | Fixing of Louvers | 100 | 0 |  | 2026-06-11 |  | 2026-06-23 |  | Tower A | Super Structure | GF | Façade | Façade Works
44023 | Tower A - Super Structure - Finishes & MEP - GF to P1 | Not Ready | Façade Works - MEP & Finishes | 2026-08-29 | 2026-09-10 | Fixing of Louvers | 100 | 0 |  | 2026-06-11 |  | 2026-06-23 |  | Tower A | Super Structure | GF
45307 |  | Not Ready |  | 2026-03-26 | 2026-04-06 | L19-20 | 100 | 0 |  | 2026-06-11 |  | 2026-06-26
45307 |  | Not Ready |  | 2026-03-26 | 2026-04-06 | L19-20 | 100 | 0 |  | 2026-06-11 |  | 2026-06-26 |  |  |  |  | Finishes | Gypsum Plastering Works
45308 | Tower B - Super Structure - Core & Outer Slab L19-20 | Not Ready | RCC Works - Vertical | 2026-03-26 | 2026-04-03 | Outer Columns_TA | 100 | 0 |  | 2026-06-11 |  | 2026-06-23 |  | Tower B | Super Structure | L19 | RCC Sub Structure | RCC Works - Vertical
45469 |  | Not Committed |  | 2026-03-26 | 2026-04-25 | L16-17 | 100 | 0 |  | 2026-06-11 |  | 2026-07-14
45469 |  | Not Committed |  | 2026-03-26 | 2026-04-25 | L16-17 | 100 | 0 |  | 2026-06-11 |  | 2026-07-14 |  |  |  |  | Finishes | Gypsum Plastering Works
45470 | Tower B - Super Structure - Finishes & MEP - L16 to L17 | Not Ready | Partition Wall-Blockwork | 2026-03-26 | 2026-04-11 | De-shuttering & Area clearance | 100 | 0 |  | 2026-06-11 |  | 2026-06-29 |  | Tower B | Super Structure | L16
48224 |  | Not Committed |  | 2026-02-18 | 2026-08-07 | Club House MEP 1st Fix | 100 | 0 |  | 2026-06-11 |  | 2026-12-03
48225 | Club House - Super structure - CH00 to CH01 | Not Ready |  | 2026-02-18 | 2026-03-25 | CH00-CH01 | 100 | 0 |  | 2026-06-11 |  | 2026-07-16 |  | Club House | Super Structure | CH00
8508 | T-14-Basement Floor | Not Ready | 2nd Coat Painting | 2026-06-06 | 2026-08-22 | 2nd Coat Painting | 100 | 0 |  | 2026-06-12 |  | 2026-08-28
9627 | T-16-1st Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-07-19 | 2026-09-24 | 2nd Coat Painting | 100 | 0 |  | 2026-06-12 |  | 2026-08-15
11218 | T-19-2nd Floor Common Area | Not Ready | Door-Shaft | 2026-06-25 | 2026-07-09 | Door-Shaft | 100 | 0 |  | 2026-06-12 |  | 2026-06-23
41750 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-05-21 | 2026-05-23 | FAPA Cabling | 100 | 0 |  | 2026-06-12 |  | 2026-06-15 |  | Tower A | Super Structure | L50
42433 | Tower A - Super Structure - Finishes & MEP - L19 to L20 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-15 | 2026-06-17 | Painting Works | 100 | 0 |  | 2026-06-12 |  | 2026-06-15 |  | Tower A | Super Structure | L19 | Finishes | Painting Works
42451 | Tower A - Super Structure - Finishes & MEP - L20 to L21 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-15 | 2026-06-17 | Painting Works | 100 | 0 |  | 2026-06-12 |  | 2026-06-15 |  | Tower A | Super Structure | L20 | Finishes | Painting Works
42469 | Tower A - Super Structure - Finishes & MEP - L21 to L22 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-15 | 2026-06-17 | Painting Works | 100 | 0 |  | 2026-06-12 |  | 2026-06-15 |  | Tower A | Super Structure | L21 | Finishes | Painting Works
43379 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-05-20 | 2026-05-28 | Door & Window Frame work | 100 | 0 |  | 2026-06-12 |  | 2026-06-19 |  | Tower A | Super Structure | L72 | Finishes | Door & Window Frame work
44139 |  | Started |  | 2026-05-20 | 2026-11-09 | Leave Out Bay | 100 | 0 |  | 2026-06-12 | 2025-07-09 | 2026-11-18
44140 |  | Not Committed |  | 2026-05-20 | 2026-06-06 | Hoist Removal | 100 | 0 |  | 2026-06-12 |  | 2026-06-30
44141 | Tower A | Not Ready | Leave Out Bay - Hoist Removal | 2026-05-20 | 2026-06-06 | Removal of 1 set of twin cage hoists | 100 | 0 |  | 2026-06-12 |  | 2026-06-30 |  | Tower A | --
46781 |  | Not Committed |  | 2026-04-03 | 2027-05-05 | L14-15 | 100 | 0 |  | 2026-06-12 |  | 2027-06-25
46781 |  | Not Committed |  | 2026-04-03 | 2027-05-05 | L14-15 | 100 | 0 |  | 2026-06-12 |  | 2027-06-25 |  |  |  |  | Finishes | Gypsum Plastering Works
46782 |  | Not Committed |  | 2026-04-03 | 2026-05-11 | MEP 1st Fixes | 100 | 0 |  | 2026-06-12 |  | 2026-07-22
46783 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-04-03 | 2026-04-10 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-06-12 |  | 2026-06-20 |  | Tower B | Super Structure | L14 | MEP | FPS 1st Fix - MEP & Finishes
46784 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-04-03 | 2026-04-08 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-06-12 |  | 2026-06-18 |  | Tower B | Super Structure | L14 | MEP | Electrical 1st Fixes
46785 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-04-03 | 2026-04-10 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-06-12 |  | 2026-06-20 |  | Tower B | Super Structure | L14
10727 | T-20-3rd Floor Common Area | Not Ready | 2nd Coat Painting | 2026-07-07 | 2026-08-08 | 2nd Coat Painting | 100 | 0 |  | 2026-06-13 |  | 2026-07-14
10935 | T-20-11th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-07-18 | 2026-08-20 | 2nd Coat Painting | 100 | 0 |  | 2026-06-13 |  | 2026-07-14
11453 | T-19-11th Floor Common Area | Not Ready | Window-Open Area | 2026-07-03 | 2026-07-11 | Window-Open Area | 100 | 0 |  | 2026-06-13 |  | 2026-06-20
41692 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-05-22 | 2026-05-26 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-06-13 |  | 2026-06-17 |  | Tower A | Super Structure | L46 | MEP | FPS 2nd Fix - MEP & Finishes
41693 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-05-22 | 2026-05-29 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-06-13 |  | 2026-06-19 |  | Tower A | Super Structure | L46 | MEP | Electrical 2nd Fix - MEP & Finishes
41694 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-05-22 | 2026-06-01 | FAPA Device Fixing | 100 | 0 |  | 2026-06-13 |  | 2026-06-22 |  | Tower A | Super Structure | L46
41694 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-05-22 | 2026-06-01 | FAPA Device Fixing | 100 | 0 |  | 2026-06-13 |  | 2026-06-22 |  | Tower A | Super Structure | L46
41694 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-05-22 | 2026-06-01 | FAPA Device Fixing | 100 | 0 |  | 2026-06-13 |  | 2026-06-22 |  | Tower A | Super Structure | L46
41694 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-05-22 | 2026-06-01 | FAPA Device Fixing | 100 | 0 |  | 2026-06-13 |  | 2026-06-22 |  | Tower A | Super Structure | L46
41695 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-05-22 | 2026-05-26 | HVAC Grill Fixing | 100 | 0 |  | 2026-06-13 |  | 2026-06-17 |  | Tower A | Super Structure | L46 | MEP | HVAC Grill Fixing
43326 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-06-01 | 2026-06-17 | Flooring & Dado works | 100 | 0 |  | 2026-06-13 |  | 2026-06-30 |  | Tower A | Super Structure | L69 | Finishes | Flooring & Dado
44629 |  | Not Ready | MEP fix & Finishes | 2026-06-16 | 2026-06-20 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-06-13 |  | 2026-06-18
44629 |  | Not Ready | MEP fix & Finishes | 2026-06-16 | 2026-06-20 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-06-13 |  | 2026-06-18
44629 |  | Not Ready | MEP fix & Finishes | 2026-06-16 | 2026-06-20 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-06-13 |  | 2026-06-18
45467 | Tower B - Super Structure - Finishes & MEP - L15 to L16 | Not Ready | Partition Wall-Blockwork | 2026-04-01 | 2026-04-08 | Partition Walls | 100 | 0 |  | 2026-06-13 |  | 2026-06-22 |  | Tower B | Super Structure | L15
45791 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | Surface Drain/ Manhole Works - MEP & Finishes | 2026-04-08 | 2026-04-24 | Surface Drain/ Manhole works | 100 | 0 |  | 2026-06-13 |  | 2026-07-01 |  | Tower B | Sub Structure | B3
45820 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-04-08 | 2026-04-15 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-06-13 |  | 2026-06-22 |  | Tower B | Sub Structure | B2 | MEP | FPS 2nd Fix - MEP & Finishes
45821 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-08 | 2026-04-15 | FAPA Device Fixing | 100 | 0 |  | 2026-06-13 |  | 2026-06-22 |  | Tower B | Sub Structure | B2
45821 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-08 | 2026-04-15 | FAPA Device Fixing | 100 | 0 |  | 2026-06-13 |  | 2026-06-22 |  | Tower B | Sub Structure | B2
45821 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-08 | 2026-04-15 | FAPA Device Fixing | 100 | 0 |  | 2026-06-13 |  | 2026-06-22 |  | Tower B | Sub Structure | B2
45821 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-08 | 2026-04-15 | FAPA Device Fixing | 100 | 0 |  | 2026-06-13 |  | 2026-06-22 |  | Tower B | Sub Structure | B2
45959 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-04-08 | 2026-04-15 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-06-13 |  | 2026-06-22 |  | Tower B | Super Structure |  | MEP | FPS 2nd Fix - MEP & Finishes
45960 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-08 | 2026-04-15 | FAPA Device Fixing | 100 | 0 |  | 2026-06-13 |  | 2026-06-22 |  | Tower B | Super Structure
45960 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-08 | 2026-04-15 | FAPA Device Fixing | 100 | 0 |  | 2026-06-13 |  | 2026-06-22 |  | Tower B | Super Structure
45960 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-08 | 2026-04-15 | FAPA Device Fixing | 100 | 0 |  | 2026-06-13 |  | 2026-06-22 |  | Tower B | Super Structure
45960 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-04-08 | 2026-04-15 | FAPA Device Fixing | 100 | 0 |  | 2026-06-13 |  | 2026-06-22 |  | Tower B | Super Structure
8593 | T-14-2nd Floor Common Area | Not Ready | Window-Open Area | 2026-05-05 | 2026-05-12 | Window-Open Area | 100 | 0 |  | 2026-06-14 |  | 2026-06-21
9193 | T-15-4th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-06-10 | 2026-07-13 | 2nd Coat Painting | 100 | 0 |  | 2026-06-14 |  | 2026-07-17
9923 | T-16-Staircase 1 | Not Ready |  | 2026-07-01 | 2026-07-11 | 10F-09F | 100 | 0 |  | 2026-06-14 |  | 2026-06-26
9937 | T-16-Staircase 2 | Not Ready |  | 2026-07-01 | 2026-07-11 | 11F-10F | 100 | 0 |  | 2026-06-14 |  | 2026-06-26
10969 | T-20-Staircase 1 | Not Ready |  | 2026-07-02 | 2026-07-14 | 04F-03F | 100 | 0 |  | 2026-06-14 |  | 2026-06-23
10983 | T-20-Staircase 2 | Not Ready |  | 2026-07-02 | 2026-07-14 | 05F-04F | 100 | 0 |  | 2026-06-14 |  | 2026-06-23
11169 | T-19-GF Common Area | Not Ready | 2nd Coat Painting | 2026-07-22 | 2026-10-08 | 2nd Coat Painting | 100 | 0 |  | 2026-06-14 |  | 2026-09-02
8647 | T-14-4th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-05-12 | 2026-06-14 | 2nd Coat Painting | 100 | 0 |  | 2026-06-15 |  | 2026-07-16
10994 | T-20- Elevation-D | Not Ready |  | 2026-07-14 | 2026-10-06 | Elevation-D | 100 | 0 |  | 2026-06-15 |  | 2026-09-06
11246 | T-19-3rd Floor Common Area | Not Ready | 1st Coat Painting | 2026-06-24 | 2026-07-16 | 1st Coat Painting | 100 | 0 |  | 2026-06-15 |  | 2026-07-07
41666 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-05-23 | 2026-05-30 | Final Painting | 100 | 0 |  | 2026-06-15 |  | 2026-06-20 |  | Tower A | Super Structure | L44 | Finishes | Final Painting
41666 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-05-23 | 2026-05-30 | Final Painting | 100 | 0 |  | 2026-06-15 |  | 2026-06-20 |  | Tower A | Super Structure | L44 | Finishes | Final Painting
41666 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-05-23 | 2026-05-30 | Final Painting | 100 | 0 |  | 2026-06-15 |  | 2026-06-20 |  | Tower A | Super Structure | L44 | Finishes | Final Painting
41681 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-05-23 | 2026-05-30 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-06-15 |  | 2026-06-20 |  | Tower A | Super Structure | L45 | MEP | Electrical
41751 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-05-23 | 2026-06-02 | HVAC Ducting | 100 | 0 |  | 2026-06-15 |  | 2026-06-23 |  | Tower A | Super Structure | L50 | MEP | HVAC Ducting
41764 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-05-23 | 2026-05-30 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-06-15 |  | 2026-06-20 |  | Tower A | Super Structure | L51 | MEP | FPS 1st Fix - MEP & Finishes
41765 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-05-23 | 2026-05-28 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-06-15 |  | 2026-06-18 |  | Tower A | Super Structure | L51 | MEP | Electrical 1st Fixes
42486 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-06-17 | 2026-06-19 | PHE Final Fixes | 100 | 0 |  | 2026-06-15 |  | 2026-06-17 |  | Tower A | Super Structure | L22
42504 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-06-17 | 2026-06-19 | PHE Final Fixes | 100 | 0 |  | 2026-06-15 |  | 2026-06-17 |  | Tower A | Super Structure | L23
42539 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-06-17 | 2026-06-22 | False Ceiling | 100 | 0 |  | 2026-06-15 |  | 2026-06-19 |  | Tower A | Super Structure | L25 | Finishes | False Ceiling
42557 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-06-17 | 2026-06-22 | False Ceiling | 100 | 0 |  | 2026-06-15 |  | 2026-06-19 |  | Tower A | Super Structure | L26 | Finishes | False Ceiling
42575 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-06-17 | 2026-06-22 | False Ceiling | 100 | 0 |  | 2026-06-15 |  | 2026-06-19 |  | Tower A | Super Structure | L27 | Finishes | False Ceiling
43397 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-05-22 | 2026-05-30 | Door & Window Frame work | 100 | 0 |  | 2026-06-15 |  | 2026-06-22 |  | Tower A | Super Structure | L73 | Finishes | Door & Window Frame work
43994 | Tower A - Super Structure - Finishes & MEP - L35 to L45 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-07-18 | 2026-08-07 | Staircase Light Fixtures & Devices fixing | 100 | 0 |  | 2026-06-15 |  | 2026-07-02 |  | Tower A | Super Structure | L35
44000 | Tower A - Super Structure - Finishes & MEP - L45 to L55 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-07-18 | 2026-07-31 | Staircase cabling | 100 | 0 |  | 2026-06-15 |  | 2026-06-26 |  | Tower A | Super Structure | L45
44003 | Tower A - Super Structure - Finishes & MEP - L55 to L65 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-07-18 | 2026-08-22 | Staircase Wall & Ceiling finishes | 100 | 0 |  | 2026-06-15 |  | 2026-07-15 |  | Tower A | Super Structure | L55
10181 | T-21-2nd Floor Common Area | Not Ready | 2nd Coat Painting | 2026-07-17 | 2026-08-20 | 2nd Coat Painting | 100 | 0 |  | 2026-06-16 |  | 2026-07-20
40099 | Tower A - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2026-05-18 | 2026-06-10 | Panel Installation | 100 | 0 |  | 2026-06-16 |  | 2026-07-09 |  | Tower A | Super Structure
40099 | Tower A - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2026-05-18 | 2026-06-10 | Panel Installation | 100 | 0 |  | 2026-06-16 |  | 2026-07-09 |  | Tower A | Super Structure
43416 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-06-18 | 2026-07-04 | Flooring & Dado works | 100 | 0 |  | 2026-06-16 |  | 2026-07-02 |  | Tower A | Super Structure | L74 | Finishes | Flooring & Dado
45988 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-10 | 2026-04-18 | Final Painting | 100 | 0 |  | 2026-06-16 |  | 2026-06-25 |  | Tower B | Super Structure |  | Finishes | Final Painting
45988 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-10 | 2026-04-18 | Final Painting | 100 | 0 |  | 2026-06-16 |  | 2026-06-25 |  | Tower B | Super Structure |  | Finishes | Final Painting
45988 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-10 | 2026-04-18 | Final Painting | 100 | 0 |  | 2026-06-16 |  | 2026-06-25 |  | Tower B | Super Structure |  | Finishes | Final Painting
9140 | T-15-2nd Floor Common Area | Not Ready | 1st Coat Painting | 2026-06-10 | 2026-07-02 | 1st Coat Painting | 100 | 0 |  | 2026-06-17 |  | 2026-07-08
9631 | T-16-1st Floor Common Area | Not Ready | Putty | 2026-07-01 | 2026-08-07 | Putty | 100 | 0 |  | 2026-06-17 |  | 2026-07-27
9867 | T-16-11th Floor Common Area | Not Ready | Window-Open Area | 2026-07-08 | 2026-07-16 | Window-Open Area | 100 | 0 |  | 2026-06-17 |  | 2026-06-25
9892 | T-16-11th Floor Common Area | Not Ready | Door-Shaft | 2026-07-11 | 2026-07-24 | Door-Shaft | 100 | 0 |  | 2026-06-17 |  | 2026-07-01
39264 |  | Not Committed |  | 2025-12-29 | 2026-02-20 | B1 to GF | 100 | 0 |  | 2026-06-17 |  | 2026-08-17
39264 |  | Not Committed |  | 2025-12-29 | 2026-02-20 | B1 to GF | 100 | 0 |  | 2026-06-17 |  | 2026-08-17
39264 |  | Not Committed |  | 2025-12-29 | 2026-02-20 | B1 to GF | 100 | 0 |  | 2026-06-17 |  | 2026-08-17
39265 | Retail - Sub structure - B1 to GF | Not Ready | Retaining Wall RCC Works | 2025-12-29 | 2026-01-06 | Retaining Wall_lift 1 | 100 | 0 |  | 2026-06-17 |  | 2026-06-25 |  | Retail | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
39265 | Retail - Sub structure - B1 to GF | Not Ready | Retaining Wall RCC Works | 2025-12-29 | 2026-01-06 | Retaining Wall_lift 1 | 100 | 0 |  | 2026-06-17 |  | 2026-06-25 |  | Retail | Sub Structure | B1
41696 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-05-26 | 2026-05-30 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-06-17 |  | 2026-06-20 |  | Tower A | Super Structure | L46
41723 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-05-26 | 2026-06-04 | False Ceiling | 100 | 0 |  | 2026-06-17 |  | 2026-06-25 |  | Tower A | Super Structure | L48 | Finishes | False Ceiling
41738 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-05-26 | 2026-06-08 | Flooring & Dado | 100 | 0 |  | 2026-06-17 |  | 2026-06-29 |  | Tower A | Super Structure | L49 | Finishes | Flooring & Dado
42591 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-06-19 | 2026-06-22 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-06-17 |  | 2026-06-19 |  | Tower A | Super Structure | L28 | MEP | FPS 2nd Fix - MEP & Finishes
42592 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-06-19 | 2026-06-22 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-06-17 |  | 2026-06-19 |  | Tower A | Super Structure | L28 | MEP | Electrical 2nd Fix - MEP & Finishes
42609 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-06-19 | 2026-06-22 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-06-17 |  | 2026-06-19 |  | Tower A | Super Structure | L29 | MEP | FPS 2nd Fix - MEP & Finishes
42610 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-06-19 | 2026-06-22 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-06-17 |  | 2026-06-19 |  | Tower A | Super Structure | L29 | MEP | Electrical 2nd Fix - MEP & Finishes
42627 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-06-19 | 2026-06-22 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-06-17 |  | 2026-06-19 |  | Tower A | Super Structure | L30 | MEP | FPS 2nd Fix - MEP & Finishes
42628 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-06-19 | 2026-06-22 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-06-17 |  | 2026-06-19 |  | Tower A | Super Structure | L30 | MEP | Electrical 2nd Fix - MEP & Finishes
42643 |  | Not Committed |  | 2026-06-19 | 2026-07-10 | MEP final fix & Finishes | 100 | 0 |  | 2026-06-17 |  | 2026-07-08
42644 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-06-19 | 2026-06-24 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-06-17 |  | 2026-06-22 |  | Tower A | Super Structure | L31 | Finishes | Door & Window Fixing
42661 |  | Not Committed |  | 2026-06-19 | 2026-07-10 | MEP final fix & Finishes | 100 | 0 |  | 2026-06-17 |  | 2026-07-08
42662 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-06-19 | 2026-06-24 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-06-17 |  | 2026-06-22 |  | Tower A | Super Structure | L32 | Finishes | Door & Window Fixing
42679 |  | Not Committed |  | 2026-06-19 | 2026-07-10 | MEP final fix & Finishes | 100 | 0 |  | 2026-06-17 |  | 2026-07-08
42680 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-06-19 | 2026-06-24 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-06-17 |  | 2026-06-22 |  | Tower A | Super Structure | L33 | Finishes | Door & Window Fixing
8867 | T-14-Lift Lobby | Not Ready |  | 2026-05-19 | 2026-06-04 | 10F | 100 | 0 |  | 2026-06-18 |  | 2026-07-06
9112 | T-15-1st Floor Common Area | Not Ready | Door-Shaft | 2026-06-11 | 2026-06-25 | Door-Shaft | 100 | 0 |  | 2026-06-18 |  | 2026-07-01
40086 | Tower A - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2026-05-26 | 2026-06-06 | Roping & Car Fixing | 100 | 0 |  | 2026-06-18 |  | 2026-06-30 |  | Tower A | Super Structure
40086 | Tower A - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2026-05-26 | 2026-06-06 | Roping & Car Fixing | 100 | 0 |  | 2026-06-18 |  | 2026-06-30 |  | Tower A | Super Structure
41766 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-05-28 | 2026-05-30 | FAPA Cabling | 100 | 0 |  | 2026-06-18 |  | 2026-06-20 |  | Tower A | Super Structure | L51
42487 | Tower A - Super Structure - Finishes & MEP - L22 to L23 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-20 | 2026-06-23 | Painting Works | 100 | 0 |  | 2026-06-18 |  | 2026-06-20 |  | Tower A | Super Structure | L22 | Finishes | Painting Works
42505 | Tower A - Super Structure - Finishes & MEP - L23 to L24 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-20 | 2026-06-23 | Painting Works | 100 | 0 |  | 2026-06-18 |  | 2026-06-20 |  | Tower A | Super Structure | L23 | Finishes | Painting Works
45309 | Tower B - Super Structure - Core & Outer Slab L19-20 | Not Ready | RCC Works - Slab | 2026-03-31 | 2026-04-06 | Outer Slab_TA | 100 | 0 |  | 2026-06-18 |  | 2026-06-26 |  | Tower B | Super Structure | L19 | RCC Sub Structure | RCC Works - Slab
8566 | T-14-1st Floor Common Area | Not Ready | Door-Shaft | 2026-05-13 | 2026-05-26 | Door-Shaft | 100 | 0 |  | 2026-06-19 |  | 2026-07-03
9349 | T-15-11th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-06-27 | 2026-07-29 | 2nd Coat Painting | 100 | 0 |  | 2026-06-19 |  | 2026-07-23
9367 | T-15-11th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-06-27 | 2026-09-01 | 2nd Coat Painting | 100 | 0 |  | 2026-06-19 |  | 2026-08-26
10432 | T-21-Lift Lobby | Not Ready |  | 2026-07-18 | 2026-08-04 | 05F | 100 | 0 |  | 2026-06-19 |  | 2026-07-05
10951 | T-20-Lift Lobby | Not Ready |  | 2026-07-14 | 2026-07-30 | 06F | 100 | 0 |  | 2026-06-19 |  | 2026-07-07
11990 | T-18-Lift Lobby | Not Ready |  | 2026-09-05 | 2026-09-21 | 07F | 100 | 0 |  | 2026-06-19 |  | 2026-07-06
41708 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-05-29 | 2026-06-02 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-06-19 |  | 2026-06-23 |  | Tower A | Super Structure | L47 | MEP | FPS 2nd Fix - MEP & Finishes
41709 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-05-29 | 2026-06-04 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-06-19 |  | 2026-06-25 |  | Tower A | Super Structure | L47 | MEP | Electrical 2nd Fix - MEP & Finishes
41710 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-05-29 | 2026-06-06 | FAPA Device Fixing | 100 | 0 |  | 2026-06-19 |  | 2026-06-27 |  | Tower A | Super Structure | L47
41710 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-05-29 | 2026-06-06 | FAPA Device Fixing | 100 | 0 |  | 2026-06-19 |  | 2026-06-27 |  | Tower A | Super Structure | L47
41710 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-05-29 | 2026-06-06 | FAPA Device Fixing | 100 | 0 |  | 2026-06-19 |  | 2026-06-27 |  | Tower A | Super Structure | L47
41710 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-05-29 | 2026-06-06 | FAPA Device Fixing | 100 | 0 |  | 2026-06-19 |  | 2026-06-27 |  | Tower A | Super Structure | L47
41711 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-05-29 | 2026-06-02 | HVAC Grill Fixing | 100 | 0 |  | 2026-06-19 |  | 2026-06-23 |  | Tower A | Super Structure | L47 | MEP | HVAC Grill Fixing
43344 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-06-06 | 2026-06-23 | Flooring & Dado works | 100 | 0 |  | 2026-06-19 |  | 2026-07-06 |  | Tower A | Super Structure | L70 | Finishes | Flooring & Dado
44600 |  | Not Committed |  | 2026-06-22 | 2026-08-21 | GF to P1 | 100 | 0 |  | 2026-06-19 |  | 2026-08-04
44600 |  | Not Committed |  | 2026-06-22 | 2026-08-21 | GF to P1 | 100 | 0 |  | 2026-06-19 |  | 2026-08-04
44600 |  | Not Committed |  | 2026-06-22 | 2026-08-21 | GF to P1 | 100 | 0 |  | 2026-06-19 |  | 2026-08-04
44601 |  | Not Ready | MEP fix & Finishes | 2026-06-22 | 2026-06-29 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2026-06-19 |  | 2026-06-26 |  |  |  |  | MEP | FPS final fixes
44601 |  | Not Ready | MEP fix & Finishes | 2026-06-22 | 2026-06-29 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2026-06-19 |  | 2026-06-26 |  |  |  |  | MEP | FPS final fixes
45874 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | False Ceiling - MEP & Finishes | 2026-04-14 | 2026-05-13 | False Ceiling (Modular) | 100 | 0 |  | 2026-06-19 |  | 2026-07-21 |  | Tower B | Super Structure | GF | Finishes | False Ceiling
46016 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2026-04-14 | 2026-04-30 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-06-19 |  | 2026-07-07 |  | Tower B | Super Structure
46016 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2026-04-14 | 2026-04-30 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-06-19 |  | 2026-07-07 |  | Tower B | Super Structure
46016 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2026-04-14 | 2026-04-30 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-06-19 |  | 2026-07-07 |  | Tower B | Super Structure
9739 | T-16-5th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-07-05 | 2026-08-06 | 2nd Coat Painting | 100 | 0 |  | 2026-06-20 |  | 2026-07-23
11982 | T-18-Lift | Not Ready | Water Tanks including Finishes | 2026-09-12 | 2026-11-03 | Water Tanks including Finishes | 100 | 0 |  | 2026-06-20 |  | 2026-08-11
41682 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-05-30 | 2026-06-05 | Final Painting | 100 | 0 |  | 2026-06-20 |  | 2026-06-26 |  | Tower A | Super Structure | L45 | Finishes | Final Painting
41682 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-05-30 | 2026-06-05 | Final Painting | 100 | 0 |  | 2026-06-20 |  | 2026-06-26 |  | Tower A | Super Structure | L45 | Finishes | Final Painting
41682 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-05-30 | 2026-06-05 | Final Painting | 100 | 0 |  | 2026-06-20 |  | 2026-06-26 |  | Tower A | Super Structure | L45 | Finishes | Final Painting
41697 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-05-30 | 2026-06-05 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-06-20 |  | 2026-06-26 |  | Tower A | Super Structure | L46 | MEP | Electrical
41767 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-05-30 | 2026-06-08 | HVAC Ducting | 100 | 0 |  | 2026-06-20 |  | 2026-06-29 |  | Tower A | Super Structure | L51 | MEP | HVAC Ducting
41780 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-05-30 | 2026-06-05 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-06-20 |  | 2026-06-26 |  | Tower A | Super Structure | L52 | MEP | FPS 1st Fix - MEP & Finishes
41781 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-05-30 | 2026-06-03 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-06-20 |  | 2026-06-24 |  | Tower A | Super Structure | L52 | MEP | Electrical 1st Fixes
42540 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-06-23 | 2026-06-25 | PHE Final Fixes | 100 | 0 |  | 2026-06-20 |  | 2026-06-23 |  | Tower A | Super Structure | L25
42558 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-06-23 | 2026-06-25 | PHE Final Fixes | 100 | 0 |  | 2026-06-20 |  | 2026-06-23 |  | Tower A | Super Structure | L26
42576 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-06-23 | 2026-06-25 | PHE Final Fixes | 100 | 0 |  | 2026-06-20 |  | 2026-06-23 |  | Tower A | Super Structure | L27
42593 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-06-23 | 2026-06-27 | False Ceiling | 100 | 0 |  | 2026-06-20 |  | 2026-06-25 |  | Tower A | Super Structure | L28 | Finishes | False Ceiling
42611 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-06-23 | 2026-06-27 | False Ceiling | 100 | 0 |  | 2026-06-20 |  | 2026-06-25 |  | Tower A | Super Structure | L29 | Finishes | False Ceiling
42629 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-06-23 | 2026-06-27 | False Ceiling | 100 | 0 |  | 2026-06-20 |  | 2026-06-25 |  | Tower A | Super Structure | L30 | Finishes | False Ceiling
45738 | Tower B - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2026-04-15 | 2026-05-20 | Electrical Rising Mains | 100 | 0 |  | 2026-06-20 |  | 2026-07-29 |  | Tower B | Super Structure | L7
46786 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-04-11 | 2026-04-28 | Wet Area Waterproofing | 100 | 0 |  | 2026-06-20 |  | 2026-07-08 |  | Tower B | Super Structure | L14
9390 | T-15-Lift Lobby | Not Ready |  | 2026-07-03 | 2026-07-20 | 07F | 100 | 0 |  | 2026-06-21 |  | 2026-07-09
11454 | T-19-11th Floor Common Area | Not Ready | 1st Coat Painting | 2026-07-11 | 2026-08-01 | 1st Coat Painting | 100 | 0 |  | 2026-06-21 |  | 2026-07-12
8594 | T-14-2nd Floor Common Area | Not Ready | 1st Coat Painting | 2026-05-12 | 2026-06-03 | 1st Coat Painting | 100 | 0 |  | 2026-06-22 |  | 2026-07-14
8803 | T-14-11th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-05-29 | 2026-06-30 | 2nd Coat Painting | 100 | 0 |  | 2026-06-22 |  | 2026-07-24
8821 | T-14-11th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-05-29 | 2026-08-02 | 2nd Coat Painting | 100 | 0 |  | 2026-06-22 |  | 2026-08-24
9408 | T-15-Staircase 1 | Not Ready |  | 2026-06-28 | 2026-07-09 | 05F-04F | 100 | 0 |  | 2026-06-22 |  | 2026-07-02
9422 | T-15-Staircase 2 | Not Ready |  | 2026-06-28 | 2026-07-09 | 06F-05F | 100 | 0 |  | 2026-06-22 |  | 2026-07-02
10451 | T-21-Staircase 1 | Not Ready |  | 2026-07-13 | 2026-07-24 | 02F-01F | 100 | 0 |  | 2026-06-22 |  | 2026-07-01
10465 | T-21-Staircase 2 | Not Ready |  | 2026-07-13 | 2026-07-24 | 03F-02F | 100 | 0 |  | 2026-06-22 |  | 2026-07-01
11485 | T-19-Staircase 1 | Not Ready |  | 2026-07-01 | 2026-07-12 | 08F-07F | 100 | 0 |  | 2026-06-22 |  | 2026-07-01
11499 | T-19-Staircase 2 | Not Ready |  | 2026-07-01 | 2026-07-12 | 09F-08F | 100 | 0 |  | 2026-06-22 |  | 2026-07-01
11981 | T-18-Lift | Not Ready | OTS Covers | 2026-09-17 | 2026-10-21 | OTS Covers | 100 | 0 |  | 2026-06-22 |  | 2026-07-26
12008 | T-18-Staircase 1 | Not Ready |  | 2026-08-31 | 2026-09-10 | 05F-04F | 100 | 0 |  | 2026-06-22 |  | 2026-07-03
12022 | T-18-Staircase 2 | Not Ready |  | 2026-08-31 | 2026-09-10 | 06F-05F | 100 | 0 |  | 2026-06-22 |  | 2026-07-03
42174 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-06-24 | 2026-07-10 | Flooring & Dado works | 100 | 0 |  | 2026-06-22 |  | 2026-07-08 |  | Tower A | Super Structure | L75 | Finishes | Flooring & Dado
42191 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-05-30 | 2026-06-06 | Door & Window Frame work | 100 | 0 |  | 2026-06-22 |  | 2026-06-29 |  | Tower A | Super Structure | L76 | Finishes | Door & Window Frame work
44580 | NTA_Zone 2 - Super Structure - P4 to P5 | Not Ready | Finishes (Lobby & Floor Area) | 2025-11-18 | 2025-12-22 | Staircase Finishes | 100 | 0 |  | 2026-06-22 |  | 2026-07-29 |  | NTA_Zone 2 | Super Structure
44580 | NTA_Zone 2 - Super Structure - P4 to P5 | Not Ready | Finishes (Lobby & Floor Area) | 2025-11-18 | 2025-12-22 | Staircase Finishes | 100 | 0 |  | 2026-06-22 |  | 2026-07-29 |  | NTA_Zone 2 | Super Structure
45468 | Tower B - Super Structure - Finishes & MEP - L15 to L16 | Not Ready | Partition Wall-Blockwork | 2026-04-09 | 2026-04-14 | Staircase Area | 100 | 0 |  | 2026-06-22 |  | 2026-06-27 |  | Tower B | Super Structure | L15
45822 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-16 | 2026-04-24 | Final Painting | 100 | 0 |  | 2026-06-22 |  | 2026-07-01 |  | Tower B | Sub Structure | B2 | Finishes | Final Painting
45822 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-16 | 2026-04-24 | Final Painting | 100 | 0 |  | 2026-06-22 |  | 2026-07-01 |  | Tower B | Sub Structure | B2 | Finishes | Final Painting
45822 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-16 | 2026-04-24 | Final Painting | 100 | 0 |  | 2026-06-22 |  | 2026-07-01 |  | Tower B | Sub Structure | B2 | Finishes | Final Painting
45961 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-16 | 2026-04-24 | Final Painting | 100 | 0 |  | 2026-06-22 |  | 2026-07-01 |  | Tower B | Super Structure |  | Finishes | Final Painting
45961 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-16 | 2026-04-24 | Final Painting | 100 | 0 |  | 2026-06-22 |  | 2026-07-01 |  | Tower B | Super Structure |  | Finishes | Final Painting
45961 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-16 | 2026-04-24 | Final Painting | 100 | 0 |  | 2026-06-22 |  | 2026-07-01 |  | Tower B | Super Structure |  | Finishes | Final Painting
47671 |  | Not Ready |  | 2026-06-22 | 2026-07-03 | Section 5_lift 1 | 100 | 0 |  | 2026-06-22 |  | 2026-07-03
47671 |  | Not Ready |  | 2026-06-22 | 2026-07-03 | Section 5_lift 1 | 100 | 0 |  | 2026-06-22 |  | 2026-07-03 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47673 |  | Not Ready |  | 2026-06-22 | 2026-07-03 | Section 7_lift 1 | 100 | 0 |  | 2026-06-22 |  | 2026-07-03
47673 |  | Not Ready |  | 2026-06-22 | 2026-07-03 | Section 7_lift 1 | 100 | 0 |  | 2026-06-22 |  | 2026-07-03 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47680 |  | Not Ready |  | 2026-06-22 | 2026-06-29 | Section 2_lift 2 | 100 | 0 |  | 2026-06-22 |  | 2026-06-29
47680 |  | Not Ready |  | 2026-06-22 | 2026-06-29 | Section 2_lift 2 | 100 | 0 |  | 2026-06-22 |  | 2026-06-29 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47682 |  | Not Ready |  | 2026-06-22 | 2026-06-29 | Section 4_lift 2 | 100 | 0 |  | 2026-06-22 |  | 2026-06-29
47682 |  | Not Ready |  | 2026-06-22 | 2026-06-29 | Section 4_lift 2 | 100 | 0 |  | 2026-06-22 |  | 2026-06-29 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
8884 | T-14-Staircase 1 | Not Ready |  | 2026-05-19 | 2026-05-29 | 09F-08F | 100 | 0 |  | 2026-06-23 |  | 2026-07-02
8898 | T-14-Staircase 2 | Not Ready |  | 2026-05-19 | 2026-05-29 | 10F-09F | 100 | 0 |  | 2026-06-23 |  | 2026-07-02
11468 | T-19-Lift Lobby | Not Ready |  | 2026-07-07 | 2026-07-23 | 09F | 100 | 0 |  | 2026-06-23 |  | 2026-07-11
11713 | T-18-1st Floor Common Area | Not Ready | Window-Open Area | 2026-08-27 | 2026-09-04 | Window-Open Area | 100 | 0 |  | 2026-06-23 |  | 2026-06-29
41712 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-06-02 | 2026-06-05 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-06-23 |  | 2026-06-26 |  | Tower A | Super Structure | L47
41739 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-06-02 | 2026-06-10 | False Ceiling | 100 | 0 |  | 2026-06-23 |  | 2026-07-01 |  | Tower A | Super Structure | L49 | Finishes | False Ceiling
41754 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-06-02 | 2026-06-13 | Flooring & Dado | 100 | 0 |  | 2026-06-23 |  | 2026-07-04 |  | Tower A | Super Structure | L50 | Finishes | Flooring & Dado
42645 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-06-25 | 2026-06-27 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-06-23 |  | 2026-06-25 |  | Tower A | Super Structure | L31 | MEP | FPS 2nd Fix - MEP & Finishes
42646 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-06-25 | 2026-06-27 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-06-23 |  | 2026-06-25 |  | Tower A | Super Structure | L31 | MEP | Electrical 2nd Fix - MEP & Finishes
42663 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-06-25 | 2026-06-27 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-06-23 |  | 2026-06-25 |  | Tower A | Super Structure | L32 | MEP | FPS 2nd Fix - MEP & Finishes
42664 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-06-25 | 2026-06-27 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-06-23 |  | 2026-06-25 |  | Tower A | Super Structure | L32 | MEP | Electrical 2nd Fix - MEP & Finishes
42681 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-06-25 | 2026-06-27 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-06-23 |  | 2026-06-25 |  | Tower A | Super Structure | L33 | MEP | FPS 2nd Fix - MEP & Finishes
42682 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-06-25 | 2026-06-27 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-06-23 |  | 2026-06-25 |  | Tower A | Super Structure | L33 | MEP | Electrical 2nd Fix - MEP & Finishes
42697 |  | Not Committed |  | 2026-06-25 | 2026-07-21 | MEP final fix & Finishes | 100 | 0 |  | 2026-06-23 |  | 2026-07-15
42698 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-06-25 | 2026-06-30 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-06-23 |  | 2026-06-27 |  | Tower A | Super Structure | L34 | Finishes | Door & Window Fixing
42715 |  | Not Committed |  | 2026-06-25 | 2026-07-25 | MEP final fix & Finishes | 100 | 0 |  | 2026-06-23 |  | 2026-07-17
42716 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-06-25 | 2026-06-30 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-06-23 |  | 2026-06-27 |  | Tower A | Super Structure | L35 | Finishes | Door & Window Fixing
42733 |  | Not Committed |  | 2026-06-25 | 2026-07-21 | MEP final fix & Finishes | 100 | 0 |  | 2026-06-23 |  | 2026-07-15
42734 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-06-25 | 2026-06-30 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-06-23 |  | 2026-06-27 |  | Tower A | Super Structure | L36 | Finishes | Door & Window Fixing
44024 | Tower A - Super Structure - Finishes & MEP - GF to P1 | Not Ready | Façade Works - MEP & Finishes | 2026-09-11 | 2026-09-25 | Accessories & Alignment | 100 | 0 |  | 2026-06-23 |  | 2026-07-04 |  | Tower A | Super Structure | GF | Façade | Façade Works
44024 | Tower A - Super Structure - Finishes & MEP - GF to P1 | Not Ready | Façade Works - MEP & Finishes | 2026-09-11 | 2026-09-25 | Accessories & Alignment | 100 | 0 |  | 2026-06-23 |  | 2026-07-04 |  | Tower A | Super Structure | GF
46769 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-04-17 | 2026-04-28 | Cement Plastering in wet areas | 100 | 0 |  | 2026-06-23 |  | 2026-07-04 |  | Tower B | Super Structure | L13
48046 |  | Not Committed |  | 2026-03-02 | 2026-03-28 | Pool slab | 100 | 0 |  | 2026-06-23 |  | 2026-07-21
48047 | Club House - Super structure - CH01 to CH02 | Not Ready |  | 2026-03-02 | 2026-03-13 | Bottom slab | 100 | 0 |  | 2026-06-23 |  | 2026-07-03 |  | Club House | Super Structure | CH01
48050 |  | Not Committed |  | 2026-03-02 | 2026-04-17 | CH02-CH03 (4.45) | 100 | 0 |  | 2026-06-23 |  | 2026-08-13
48051 | Club House - Super structure - CH02 to CH03 | Not Ready |  | 2026-03-02 | 2026-04-06 | Columns_CH | 100 | 0 |  | 2026-06-23 |  | 2026-07-30 |  | Club House | Super Structure | CH02
48052 | Club House - Super structure - CH02 to CH03 | Not Ready |  | 2026-03-02 | 2026-03-25 | Staircase_CH | 100 | 0 |  | 2026-06-23 |  | 2026-07-16 |  | Club House | Super Structure | CH02
48210 | Club House - Super structure - CH01 to CH02 | Not Ready |  | 2026-03-02 | 2026-04-06 | CH01-CH02 (P5-6) | 100 | 0 |  | 2026-06-23 |  | 2026-07-30 |  | Club House | Super Structure | CH01
10970 | T-20-Staircase 1 | Not Ready |  | 2026-07-14 | 2026-07-24 | 03F-02F | 100 | 0 |  | 2026-06-24 |  | 2026-07-06
10984 | T-20-Staircase 2 | Not Ready |  | 2026-07-14 | 2026-07-24 | 04F-03F | 100 | 0 |  | 2026-06-24 |  | 2026-07-06
11219 | T-19-2nd Floor Common Area | Not Ready | Window-Open Area | 2026-07-09 | 2026-07-16 | Window-Open Area | 100 | 0 |  | 2026-06-24 |  | 2026-07-02
41782 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-06-03 | 2026-06-05 | FAPA Cabling | 100 | 0 |  | 2026-06-24 |  | 2026-06-26 |  | Tower A | Super Structure | L52
42541 | Tower A - Super Structure - Finishes & MEP - L25 to L26 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-26 | 2026-06-29 | Painting Works | 100 | 0 |  | 2026-06-24 |  | 2026-06-26 |  | Tower A | Super Structure | L25 | Finishes | Painting Works
42559 | Tower A - Super Structure - Finishes & MEP - L26 to L27 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-26 | 2026-06-29 | Painting Works | 100 | 0 |  | 2026-06-24 |  | 2026-06-26 |  | Tower A | Super Structure | L26 | Finishes | Painting Works
42577 | Tower A - Super Structure - Finishes & MEP - L27 to L28 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-26 | 2026-06-29 | Painting Works | 100 | 0 |  | 2026-06-24 |  | 2026-06-26 |  | Tower A | Super Structure | L27 | Finishes | Painting Works
44185 |  | Started |  | 2026-06-08 | 2026-09-10 | Façade Closure at Left Out Bay (front side) | 100 | 0 |  | 2026-06-24 | 2025-07-09 | 2026-09-23
44198 |  | Started |  | 2026-06-24 | 2026-07-17 | L25-35 | 100 | 0 |  | 2026-06-24 | 2025-07-09 | 2026-08-14
44198 |  | Started |  | 2026-06-24 | 2026-07-17 | L25-35 | 100 | 0 |  | 2026-06-24 | 2025-07-09 | 2026-08-14
44199 | Tower A - Super Structure - Finishes & MEP - L25 to L35 | Started |  | 2026-06-24 | 2026-07-01 | Al. Frame Section Installation | 100 | 0 |  | 2026-06-24 | 2025-07-09 | 2026-07-28 |  | Tower A | Super Structure | L25
45617 | Tower B - Super Structure - Finishes & MEP - L14 to L15 | Not Ready | Gypsum Plastering Works | 2026-04-15 | 2026-06-02 | L14-15 | 100 | 0 |  | 2026-06-24 |  | 2026-08-18 |  | Tower B | Super Structure | L14 | Finishes | Gypsum Plastering Works
45617 | Tower B - Super Structure - Finishes & MEP - L14 to L15 | Not Ready | Gypsum Plastering Works | 2026-04-15 | 2026-06-02 | L14-15 | 100 | 0 |  | 2026-06-24 |  | 2026-08-18 |  | Tower B | Super Structure | L14
48253 |  | Not Committed |  | 2026-03-04 | 2026-05-13 | R1 to CH00 | 100 | 0 |  | 2026-06-24 |  | 2026-09-09
48254 | Retail - Super structure - R1 to CH00 | Not Ready |  | 2026-03-04 | 2026-05-13 | Toilets | 100 | 0 |  | 2026-06-24 |  | 2026-09-09 |  | Retail | Super Structure
48255 | Retail - Super structure - R1 to CH00 | Not Ready |  | 2026-03-04 | 2026-05-13 | Staircase Finishes | 100 | 0 |  | 2026-06-24 |  | 2026-09-09 |  | Retail | Super Structure
48255 | Retail - Super structure - R1 to CH00 | Not Ready |  | 2026-03-04 | 2026-05-13 | Staircase Finishes | 100 | 0 |  | 2026-06-24 |  | 2026-09-09 |  | Retail | Super Structure
9685 | T-16-3rd Floor Common Area | Not Ready | Window-Open Area | 2026-07-08 | 2026-07-16 | Window-Open Area | 100 | 0 |  | 2026-06-25 |  | 2026-07-03
9817 | T-16-8th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-07-16 | 2026-08-19 | 2nd Coat Painting | 100 | 0 |  | 2026-06-25 |  | 2026-07-28
9907 | T-16-Lift Lobby | Not Ready |  | 2026-07-11 | 2026-07-28 | 10F | 100 | 0 |  | 2026-06-25 |  | 2026-07-10
12033 | T-18- Elevation-C | Not Ready |  | 2026-09-10 | 2026-12-04 | Elevation-C | 100 | 0 |  | 2026-06-25 |  | 2026-09-16
41724 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-06-04 | 2026-06-08 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-06-25 |  | 2026-06-29 |  | Tower A | Super Structure | L48 | MEP | FPS 2nd Fix - MEP & Finishes
41725 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-06-04 | 2026-06-10 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-06-25 |  | 2026-07-01 |  | Tower A | Super Structure | L48 | MEP | Electrical 2nd Fix - MEP & Finishes
41726 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-06-04 | 2026-06-12 | FAPA Device Fixing | 100 | 0 |  | 2026-06-25 |  | 2026-07-03 |  | Tower A | Super Structure | L48
41726 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-06-04 | 2026-06-12 | FAPA Device Fixing | 100 | 0 |  | 2026-06-25 |  | 2026-07-03 |  | Tower A | Super Structure | L48
41726 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-06-04 | 2026-06-12 | FAPA Device Fixing | 100 | 0 |  | 2026-06-25 |  | 2026-07-03 |  | Tower A | Super Structure | L48
41726 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-06-04 | 2026-06-12 | FAPA Device Fixing | 100 | 0 |  | 2026-06-25 |  | 2026-07-03 |  | Tower A | Super Structure | L48
41727 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-06-04 | 2026-06-08 | HVAC Grill Fixing | 100 | 0 |  | 2026-06-25 |  | 2026-06-29 |  | Tower A | Super Structure | L48 | MEP | HVAC Grill Fixing
43362 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-06-12 | 2026-06-29 | Flooring & Dado works | 100 | 0 |  | 2026-06-25 |  | 2026-07-11 |  | Tower A | Super Structure | L71 | Finishes | Flooring & Dado
45849 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-20 | 2026-05-13 | Final Painting | 100 | 0 |  | 2026-06-25 |  | 2026-07-21 |  | Tower B | Sub Structure | B1 | Finishes | Final Painting
45849 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-20 | 2026-05-13 | Final Painting | 100 | 0 |  | 2026-06-25 |  | 2026-07-21 |  | Tower B | Sub Structure | B1 | Finishes | Final Painting
45849 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2026-04-20 | 2026-05-13 | Final Painting | 100 | 0 |  | 2026-06-25 |  | 2026-07-21 |  | Tower B | Sub Structure | B1 | Finishes | Final Painting
45989 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2026-04-20 | 2026-05-07 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-06-25 |  | 2026-07-14 |  | Tower B | Super Structure
45989 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2026-04-20 | 2026-05-07 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-06-25 |  | 2026-07-14 |  | Tower B | Super Structure
45989 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2026-04-20 | 2026-05-07 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-06-25 |  | 2026-07-14 |  | Tower B | Super Structure
9868 | T-16-11th Floor Common Area | Not Ready | 1st Coat Painting | 2026-07-16 | 2026-08-06 | 1st Coat Painting | 100 | 0 |  | 2026-06-26 |  | 2026-07-18
11403 | T-19-9th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-07-16 | 2026-08-19 | 2nd Coat Painting | 100 | 0 |  | 2026-06-26 |  | 2026-07-27
11421 | T-19-10th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-07-16 | 2026-09-21 | 2nd Coat Painting | 100 | 0 |  | 2026-06-26 |  | 2026-08-29
39266 | Retail - Sub structure - B1 to GF | Not Ready | Retaining Wall RCC Works | 2026-01-05 | 2026-01-14 | Retaining Wall_lift 2 | 100 | 0 |  | 2026-06-26 |  | 2026-07-06 |  | Retail | Sub Structure | B1 | RCC Super Structure | Retaining Wall RCC Works
39266 | Retail - Sub structure - B1 to GF | Not Ready | Retaining Wall RCC Works | 2026-01-05 | 2026-01-14 | Retaining Wall_lift 2 | 100 | 0 |  | 2026-06-26 |  | 2026-07-06 |  | Retail | Sub Structure | B1
40119 | Tower A - Super Structure - Finishes & MEP - Sub Station | Not Ready | Sub Station - High Side Services | 2026-06-29 | 2026-07-09 | Obtain PWD Lisence | 100 | 0 |  | 2026-06-26 |  | 2026-07-07 |  | Tower A | Super Structure
41698 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-05 | 2026-06-11 | Final Painting | 100 | 0 |  | 2026-06-26 |  | 2026-07-02 |  | Tower A | Super Structure | L46 | Finishes | Final Painting
41698 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-05 | 2026-06-11 | Final Painting | 100 | 0 |  | 2026-06-26 |  | 2026-07-02 |  | Tower A | Super Structure | L46 | Finishes | Final Painting
41698 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-05 | 2026-06-11 | Final Painting | 100 | 0 |  | 2026-06-26 |  | 2026-07-02 |  | Tower A | Super Structure | L46 | Finishes | Final Painting
41713 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-06-05 | 2026-06-11 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-06-26 |  | 2026-07-02 |  | Tower A | Super Structure | L47 | MEP | Electrical
41783 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-06-05 | 2026-06-13 | HVAC Ducting | 100 | 0 |  | 2026-06-26 |  | 2026-07-04 |  | Tower A | Super Structure | L52 | MEP | HVAC Ducting
41796 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-06-05 | 2026-06-11 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-06-26 |  | 2026-07-02 |  | Tower A | Super Structure | L53 | MEP | FPS 1st Fix - MEP & Finishes
41797 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-06-05 | 2026-06-09 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-06-26 |  | 2026-06-30 |  | Tower A | Super Structure | L53 | MEP | Electrical 1st Fixes
42594 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-06-29 | 2026-07-01 | PHE Final Fixes | 100 | 0 |  | 2026-06-26 |  | 2026-06-29 |  | Tower A | Super Structure | L28
42612 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-06-29 | 2026-07-01 | PHE Final Fixes | 100 | 0 |  | 2026-06-26 |  | 2026-06-29 |  | Tower A | Super Structure | L29
42630 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-06-29 | 2026-07-01 | PHE Final Fixes | 100 | 0 |  | 2026-06-26 |  | 2026-06-29 |  | Tower A | Super Structure | L30
42647 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-06-29 | 2026-07-03 | False Ceiling | 100 | 0 |  | 2026-06-26 |  | 2026-07-01 |  | Tower A | Super Structure | L31 | Finishes | False Ceiling
42665 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-06-29 | 2026-07-03 | False Ceiling | 100 | 0 |  | 2026-06-26 |  | 2026-07-01 |  | Tower A | Super Structure | L32 | Finishes | False Ceiling
42683 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-06-29 | 2026-07-03 | False Ceiling | 100 | 0 |  | 2026-06-26 |  | 2026-07-01 |  | Tower A | Super Structure | L33 | Finishes | False Ceiling
44005 | Tower A - Super Structure - Finishes & MEP - L55 to L65 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-08-13 | 2026-09-23 | Staircase Window | 100 | 0 |  | 2026-06-26 |  | 2026-08-05 |  | Tower A | Super Structure | L55
44009 |  | Not Committed |  | 2026-08-13 | 2026-10-22 | L65-77 | 100 | 0 |  | 2026-06-26 |  | 2026-09-01
44011 | Tower A - Super Structure - Finishes & MEP - L65 to L77 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-08-13 | 2026-10-13 | Staircase Flooring | 100 | 0 |  | 2026-06-26 |  | 2026-08-26 |  | Tower A | Super Structure | L65 | Finishes | Staircase Flooring
44266 |  | Not Ready |  | 2026-06-29 | 2026-11-11 | Statutory Approvals - Fire NOC_Zone 1 | 100 | 0 |  | 2026-06-26 |  | 2027-05-24
44268 |  | Not Ready |  | 2026-06-29 | 2026-07-09 | DG Set License by Chief Electrical Inspector | 100 | 0 |  | 2026-06-26 |  | 2026-07-28
45310 |  | Not Ready |  | 2026-04-07 | 2026-04-17 | L20-21 | 100 | 0 |  | 2026-06-26 |  | 2026-07-11
45310 |  | Not Ready |  | 2026-04-07 | 2026-04-17 | L20-21 | 100 | 0 |  | 2026-06-26 |  | 2026-07-11 |  |  |  |  | Finishes | Gypsum Plastering Works
45311 | Tower B - Super Structure - Core & Outer Slab L20-21 | Not Ready | RCC Works - Vertical | 2026-04-07 | 2026-04-15 | Outer Columns_TA | 100 | 0 |  | 2026-06-26 |  | 2026-07-08 |  | Tower B | Super Structure | L20 | RCC Sub Structure | RCC Works - Vertical
45473 |  | Not Committed |  | 2026-04-07 | 2026-05-08 | L17-18 | 100 | 0 |  | 2026-06-26 |  | 2026-07-31
45473 |  | Not Committed |  | 2026-04-07 | 2026-05-08 | L17-18 | 100 | 0 |  | 2026-06-26 |  | 2026-07-31 |  |  |  |  | Finishes | Gypsum Plastering Works
45474 | Tower B - Super Structure - Finishes & MEP - L17 to L18 | Not Ready | Partition Wall-Blockwork | 2026-04-07 | 2026-04-23 | De-shuttering & Area clearance | 100 | 0 |  | 2026-06-26 |  | 2026-07-15 |  | Tower B | Super Structure | L17
9592 | T-16-GF Flat Area | Not Ready | 2nd Coat Painting | 2026-08-05 | 2026-10-11 | 2nd Coat Painting | 100 | 0 |  | 2026-06-27 |  | 2026-08-31
9924 | T-16-Staircase 1 | Not Ready |  | 2026-07-11 | 2026-07-22 | 09F-08F | 100 | 0 |  | 2026-06-27 |  | 2026-07-09
9938 | T-16-Staircase 2 | Not Ready |  | 2026-07-11 | 2026-07-22 | 10F-09F | 100 | 0 |  | 2026-06-27 |  | 2026-07-09
40100 | Tower A - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2026-05-30 | 2026-06-22 | Cable Tray & Cabling Work | 100 | 0 |  | 2026-06-27 |  | 2026-07-23 |  | Tower A | Super Structure
44602 |  | Not Ready | MEP fix & Finishes | 2026-06-30 | 2026-07-07 | FAPA Device Fixing | 100 | 0 |  | 2026-06-27 |  | 2026-07-04
44602 |  | Not Ready | MEP fix & Finishes | 2026-06-30 | 2026-07-07 | FAPA Device Fixing | 100 | 0 |  | 2026-06-27 |  | 2026-07-04
44602 |  | Not Ready | MEP fix & Finishes | 2026-06-30 | 2026-07-07 | FAPA Device Fixing | 100 | 0 |  | 2026-06-27 |  | 2026-07-04
44602 |  | Not Ready | MEP fix & Finishes | 2026-06-30 | 2026-07-07 | FAPA Device Fixing | 100 | 0 |  | 2026-06-27 |  | 2026-07-04
46799 |  | Not Committed |  | 2026-04-15 | 2027-05-20 | L15-16 | 100 | 0 |  | 2026-06-27 |  | 2027-07-07
46799 |  | Not Committed |  | 2026-04-15 | 2027-05-20 | L15-16 | 100 | 0 |  | 2026-06-27 |  | 2027-07-07 |  |  |  |  | Finishes | Gypsum Plastering Works
46800 |  | Not Committed |  | 2026-04-15 | 2026-05-22 | MEP 1st Fixes | 100 | 0 |  | 2026-06-27 |  | 2026-08-08
46801 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-04-15 | 2026-04-22 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-06-27 |  | 2026-07-06 |  | Tower B | Super Structure | L15 | MEP | FPS 1st Fix - MEP & Finishes
46802 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-04-15 | 2026-04-20 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-06-27 |  | 2026-07-03 |  | Tower B | Super Structure | L15 | MEP | Electrical 1st Fixes
46803 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-04-15 | 2026-04-22 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-06-27 |  | 2026-07-06 |  | Tower B | Super Structure | L15
9433 | T-15- Elevation-C | Not Ready |  | 2026-07-09 | 2026-09-30 | Elevation-C | 100 | 0 |  | 2026-06-28 |  | 2026-09-18
41728 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-06-08 | 2026-06-11 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-06-29 |  | 2026-07-02 |  | Tower A | Super Structure | L48
41755 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-06-08 | 2026-06-16 | False Ceiling | 100 | 0 |  | 2026-06-29 |  | 2026-07-07 |  | Tower A | Super Structure | L50 | Finishes | False Ceiling
41770 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-06-08 | 2026-06-19 | Flooring & Dado | 100 | 0 |  | 2026-06-29 |  | 2026-07-10 |  | Tower A | Super Structure | L51 | Finishes | Flooring & Dado
42699 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-07-01 | 2026-07-03 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-06-29 |  | 2026-07-01 |  | Tower A | Super Structure | L34 | MEP | FPS 2nd Fix - MEP & Finishes
42700 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-07-01 | 2026-07-03 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-06-29 |  | 2026-07-01 |  | Tower A | Super Structure | L34 | MEP | Electrical 2nd Fix - MEP & Finishes
42717 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-07-01 | 2026-07-03 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-06-29 |  | 2026-07-01 |  | Tower A | Super Structure | L35 | MEP | FPS 2nd Fix - MEP & Finishes
42718 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-07-01 | 2026-07-03 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-06-29 |  | 2026-07-01 |  | Tower A | Super Structure | L35 | MEP | Electrical 2nd Fix - MEP & Finishes
42735 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-07-01 | 2026-07-03 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-06-29 |  | 2026-07-01 |  | Tower A | Super Structure | L36 | MEP | FPS 2nd Fix - MEP & Finishes
42736 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-07-01 | 2026-07-03 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-06-29 |  | 2026-07-01 |  | Tower A | Super Structure | L36 | MEP | Electrical 2nd Fix - MEP & Finishes
42751 |  | Not Committed |  | 2026-07-01 | 2026-08-01 | MEP final fix & Finishes | 100 | 0 |  | 2026-06-29 |  | 2026-07-22
42752 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-07-01 | 2026-07-06 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-06-29 |  | 2026-07-03 |  | Tower A | Super Structure | L37 | Finishes | Door & Window Fixing
42769 |  | Not Committed |  | 2026-07-01 | 2026-08-01 | MEP final fix & Finishes | 100 | 0 |  | 2026-06-29 |  | 2026-07-22
42770 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-07-01 | 2026-07-06 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-06-29 |  | 2026-07-03 |  | Tower A | Super Structure | L38 | Finishes | Door & Window Fixing
42787 |  | Not Committed |  | 2026-07-01 | 2026-08-01 | MEP final fix & Finishes | 100 | 0 |  | 2026-06-29 |  | 2026-07-22
42788 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-07-01 | 2026-07-06 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-06-29 |  | 2026-07-03 |  | Tower A | Super Structure | L39 | Finishes | Door & Window Fixing
43254 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-06-06 | 2026-07-10 | Flooring & Dado works | 100 | 0 |  | 2026-06-29 |  | 2026-08-06 |  | Tower A | Super Structure | L65 | Finishes | Flooring & Dado
45471 | Tower B - Super Structure - Finishes & MEP - L16 to L17 | Not Ready | Partition Wall-Blockwork | 2026-04-13 | 2026-04-20 | Partition Walls | 100 | 0 |  | 2026-06-29 |  | 2026-07-07 |  | Tower B | Super Structure | L16
9381 | T-15-Lift | Not Ready | OTS Covers | 2026-07-15 | 2026-08-18 | OTS Covers | 100 | 0 |  | 2026-06-30 |  | 2026-08-02
9382 | T-15-Lift | Not Ready | Water Tanks including Finishes | 2026-07-11 | 2026-08-30 | Water Tanks including Finishes | 100 | 0 |  | 2026-06-30 |  | 2026-08-19
9835 | T-16-9th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-07-21 | 2026-09-26 | 2nd Coat Painting | 100 | 0 |  | 2026-06-30 |  | 2026-09-05
11714 | T-18-1st Floor Common Area | Not Ready | 1st Coat Painting | 2026-09-04 | 2026-09-25 | 1st Coat Painting | 100 | 0 |  | 2026-06-30 |  | 2026-07-21
40088 | Tower A - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2026-06-08 | 2026-06-12 | Slow Speed Testing | 100 | 0 |  | 2026-06-30 |  | 2026-07-06 |  | Tower A | Super Structure
40088 | Tower A - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2026-06-08 | 2026-06-12 | Slow Speed Testing | 100 | 0 |  | 2026-06-30 |  | 2026-07-06 |  | Tower A | Super Structure
41798 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-06-09 | 2026-06-11 | FAPA Cabling | 100 | 0 |  | 2026-06-30 |  | 2026-07-02 |  | Tower A | Super Structure | L53
42595 | Tower A - Super Structure - Finishes & MEP - L28 to L29 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-07-02 | 2026-07-04 | Painting Works | 100 | 0 |  | 2026-06-30 |  | 2026-07-02 |  | Tower A | Super Structure | L28 | Finishes | Painting Works
42613 | Tower A - Super Structure - Finishes & MEP - L29 to L30 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-07-02 | 2026-07-04 | Painting Works | 100 | 0 |  | 2026-06-30 |  | 2026-07-02 |  | Tower A | Super Structure | L29 | Finishes | Painting Works
42631 | Tower A - Super Structure - Finishes & MEP - L30 to L31 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-07-02 | 2026-07-04 | Painting Works | 100 | 0 |  | 2026-06-30 |  | 2026-07-02 |  | Tower A | Super Structure | L30 | Finishes | Painting Works
43433 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-06-02 | 2026-06-09 | Door & Window Frame work | 100 | 0 |  | 2026-06-30 |  | 2026-07-08 |  | Tower A | Super Structure | L77 | Finishes | Door & Window Frame work
44142 |  | Not Committed |  | 2026-06-08 | 2026-09-10 | Façade Closure at Left Out Bay (back side) | 100 | 0 |  | 2026-06-30 |  | 2026-09-23
44143 |  | Not Committed |  | 2026-06-08 | 2026-06-30 | L7-15 | 100 | 0 |  | 2026-06-30 |  | 2026-07-25
44143 |  | Not Committed |  | 2026-06-08 | 2026-06-30 | L7-15 | 100 | 0 |  | 2026-06-30 |  | 2026-07-25
44144 | Tower A - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2026-06-08 | 2026-06-15 | Al. Frame Section Installation | 100 | 0 |  | 2026-06-30 |  | 2026-07-08 |  | Tower A | Super Structure | L7
44186 |  | Not Committed |  | 2026-06-08 | 2026-06-30 | L7-15 | 100 | 0 |  | 2026-06-30 |  | 2026-07-25
44186 |  | Not Committed |  | 2026-06-08 | 2026-06-30 | L7-15 | 100 | 0 |  | 2026-06-30 |  | 2026-07-25
44187 | Tower A - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2026-06-08 | 2026-06-15 | Al. Frame Section Installation | 100 | 0 |  | 2026-06-30 |  | 2026-07-08 |  | Tower A | Super Structure | L7
47692 |  | Not Ready |  | 2026-06-30 | 2026-07-17 | Slab_NTA | 100 | 0 |  | 2026-06-30 |  | 2026-07-17
47692 |  | Not Ready |  | 2026-06-30 | 2026-07-17 | Slab_NTA | 100 | 0 |  | 2026-06-30 |  | 2026-07-17 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
10155 | T-21-1st Floor Common Area | Not Ready | 2nd Coat Painting | 2026-08-03 | 2026-09-05 | 2nd Coat Painting | 100 | 0 |  | 2026-07-01 |  | 2026-08-02
41740 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-06-10 | 2026-06-13 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-07-01 |  | 2026-07-04 |  | Tower A | Super Structure | L49 | MEP | FPS 2nd Fix - MEP & Finishes
41741 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-06-10 | 2026-06-16 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-07-01 |  | 2026-07-07 |  | Tower A | Super Structure | L49 | MEP | Electrical 2nd Fix - MEP & Finishes
41742 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-06-10 | 2026-06-18 | FAPA Device Fixing | 100 | 0 |  | 2026-07-01 |  | 2026-07-09 |  | Tower A | Super Structure | L49
41742 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-06-10 | 2026-06-18 | FAPA Device Fixing | 100 | 0 |  | 2026-07-01 |  | 2026-07-09 |  | Tower A | Super Structure | L49
41742 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-06-10 | 2026-06-18 | FAPA Device Fixing | 100 | 0 |  | 2026-07-01 |  | 2026-07-09 |  | Tower A | Super Structure | L49
41742 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-06-10 | 2026-06-18 | FAPA Device Fixing | 100 | 0 |  | 2026-07-01 |  | 2026-07-09 |  | Tower A | Super Structure | L49
41743 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-06-10 | 2026-06-13 | HVAC Grill Fixing | 100 | 0 |  | 2026-07-01 |  | 2026-07-04 |  | Tower A | Super Structure | L49 | MEP | HVAC Grill Fixing
43380 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-06-18 | 2026-07-04 | Flooring & Dado works | 100 | 0 |  | 2026-07-01 |  | 2026-07-18 |  | Tower A | Super Structure | L72 | Finishes | Flooring & Dado
45792 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | VDF/ Grade Slab - MEP & Finishes | 2026-04-25 | 2026-04-30 | VDF/ Grade Slab | 100 | 0 |  | 2026-07-01 |  | 2026-07-07 |  | Tower B | Sub Structure | B3
45823 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2026-04-25 | 2026-05-13 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-07-01 |  | 2026-07-21 |  | Tower B | Sub Structure | B2
45823 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2026-04-25 | 2026-05-13 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-07-01 |  | 2026-07-21 |  | Tower B | Sub Structure | B2
45823 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2026-04-25 | 2026-05-13 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-07-01 |  | 2026-07-21 |  | Tower B | Sub Structure | B2
45962 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2026-04-25 | 2026-05-13 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-07-01 |  | 2026-07-21 |  | Tower B | Super Structure
45962 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2026-04-25 | 2026-05-13 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-07-01 |  | 2026-07-21 |  | Tower B | Super Structure
45962 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2026-04-25 | 2026-05-13 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-07-01 |  | 2026-07-21 |  | Tower B | Super Structure
9113 | T-15-1st Floor Common Area | Not Ready | Window-Open Area | 2026-06-25 | 2026-07-02 | Window-Open Area | 100 | 0 |  | 2026-07-02 |  | 2026-07-09
9893 | T-16-11th Floor Common Area | Not Ready | Window-Open Area | 2026-07-24 | 2026-08-01 | Window-Open Area | 100 | 0 |  | 2026-07-02 |  | 2026-07-09
10452 | T-21-Staircase 1 | Not Ready |  | 2026-07-24 | 2026-08-04 | 01F-GF | 100 | 0 |  | 2026-07-02 |  | 2026-07-14
10466 | T-21-Staircase 2 | Not Ready |  | 2026-07-24 | 2026-08-04 | 02F-01F | 100 | 0 |  | 2026-07-02 |  | 2026-07-14
11134 | T-19-Basement Floor | Not Ready | 2nd Coat Painting | 2026-08-11 | 2026-10-28 | 2nd Coat Painting | 100 | 0 |  | 2026-07-02 |  | 2026-09-17
11273 | T-19-4th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-07-16 | 2026-08-19 | 2nd Coat Painting | 100 | 0 |  | 2026-07-02 |  | 2026-08-02
11486 | T-19-Staircase 1 | Not Ready |  | 2026-07-12 | 2026-07-23 | 07F-06F | 100 | 0 |  | 2026-07-02 |  | 2026-07-13
11500 | T-19-Staircase 2 | Not Ready |  | 2026-07-12 | 2026-07-23 | 08F-07F | 100 | 0 |  | 2026-07-02 |  | 2026-07-13
41714 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-11 | 2026-06-17 | Final Painting | 100 | 0 |  | 2026-07-02 |  | 2026-07-08 |  | Tower A | Super Structure | L47 | Finishes | Final Painting
41714 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-11 | 2026-06-17 | Final Painting | 100 | 0 |  | 2026-07-02 |  | 2026-07-08 |  | Tower A | Super Structure | L47 | Finishes | Final Painting
41714 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-11 | 2026-06-17 | Final Painting | 100 | 0 |  | 2026-07-02 |  | 2026-07-08 |  | Tower A | Super Structure | L47 | Finishes | Final Painting
41729 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-06-11 | 2026-06-17 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-07-02 |  | 2026-07-08 |  | Tower A | Super Structure | L48 | MEP | Electrical
41799 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-06-11 | 2026-06-19 | HVAC Ducting | 100 | 0 |  | 2026-07-02 |  | 2026-07-10 |  | Tower A | Super Structure | L53 | MEP | HVAC Ducting
41812 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-06-11 | 2026-06-17 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-07-02 |  | 2026-07-08 |  | Tower A | Super Structure | L54 | MEP | FPS 1st Fix - MEP & Finishes
41813 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-06-11 | 2026-06-15 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-07-02 |  | 2026-07-06 |  | Tower A | Super Structure | L54 | MEP | Electrical 1st Fixes
42648 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-07-04 | 2026-07-07 | PHE Final Fixes | 100 | 0 |  | 2026-07-02 |  | 2026-07-04 |  | Tower A | Super Structure | L31
42666 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-07-04 | 2026-07-07 | PHE Final Fixes | 100 | 0 |  | 2026-07-02 |  | 2026-07-04 |  | Tower A | Super Structure | L32
42684 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-07-04 | 2026-07-07 | PHE Final Fixes | 100 | 0 |  | 2026-07-02 |  | 2026-07-04 |  | Tower A | Super Structure | L33
42701 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-07-04 | 2026-07-09 | False Ceiling | 100 | 0 |  | 2026-07-02 |  | 2026-07-07 |  | Tower A | Super Structure | L34 | Finishes | False Ceiling
42719 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-07-04 | 2026-07-11 | False Ceiling | 100 | 0 |  | 2026-07-02 |  | 2026-07-09 |  | Tower A | Super Structure | L35 | Finishes | False Ceiling
42737 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-07-04 | 2026-07-09 | False Ceiling | 100 | 0 |  | 2026-07-02 |  | 2026-07-07 |  | Tower A | Super Structure | L36 | Finishes | False Ceiling
43999 | Tower A - Super Structure - Finishes & MEP - L45 to L55 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-08-24 | 2026-09-18 | Staircase Railing | 100 | 0 |  | 2026-07-02 |  | 2026-07-29 |  | Tower A | Super Structure | L45
44007 | Tower A - Super Structure - Finishes & MEP - L55 to L65 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-08-24 | 2026-09-03 | Staircase cabling | 100 | 0 |  | 2026-07-02 |  | 2026-07-15 |  | Tower A | Super Structure | L55
44010 | Tower A - Super Structure - Finishes & MEP - L65 to L77 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-08-24 | 2026-10-03 | Staircase Wall & Ceiling finishes | 100 | 0 |  | 2026-07-02 |  | 2026-08-12 |  | Tower A | Super Structure | L65
8885 | T-14-Staircase 1 | Not Ready |  | 2026-05-30 | 2026-06-10 | 08F-07F | 100 | 0 |  | 2026-07-03 |  | 2026-07-13
8899 | T-14-Staircase 2 | Not Ready |  | 2026-05-30 | 2026-06-10 | 09F-08F | 100 | 0 |  | 2026-07-03 |  | 2026-07-13
9409 | T-15-Staircase 1 | Not Ready |  | 2026-07-09 | 2026-07-20 | 04F-03F | 100 | 0 |  | 2026-07-03 |  | 2026-07-12
9423 | T-15-Staircase 2 | Not Ready |  | 2026-07-09 | 2026-07-20 | 05F-04F | 100 | 0 |  | 2026-07-03 |  | 2026-07-12
9658 | T-16-2nd Floor Common Area | Not Ready | Door-Shaft | 2026-07-17 | 2026-07-30 | Door-Shaft | 100 | 0 |  | 2026-07-03 |  | 2026-07-16
10701 | T-20-2nd Floor Common Area | Not Ready | 2nd Coat Painting | 2026-07-29 | 2026-09-01 | 2nd Coat Painting | 100 | 0 |  | 2026-07-03 |  | 2026-08-03
11220 | T-19-2nd Floor Common Area | Not Ready | 1st Coat Painting | 2026-07-16 | 2026-08-07 | 1st Coat Painting | 100 | 0 |  | 2026-07-03 |  | 2026-07-24
42192 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-07-06 | 2026-07-24 | Flooring & Dado works | 100 | 0 |  | 2026-07-03 |  | 2026-07-22 |  | Tower A | Super Structure | L76 | Finishes | Flooring & Dado
45312 | Tower B - Super Structure - Core & Outer Slab L20-21 | Not Ready | RCC Works - Slab | 2026-04-11 | 2026-04-17 | Outer Slab_TA | 100 | 0 |  | 2026-07-03 |  | 2026-07-11 |  | Tower B | Super Structure | L20 | RCC Sub Structure | RCC Works - Slab
8567 | T-14-1st Floor Common Area | Not Ready | Window-Open Area | 2026-05-27 | 2026-06-03 | Window-Open Area | 100 | 0 |  | 2026-07-04 |  | 2026-07-11
9609 | T-16-GF Common Area | Not Ready | 2nd Coat Painting | 2026-08-12 | 2026-10-29 | 2nd Coat Painting | 100 | 0 |  | 2026-07-04 |  | 2026-09-22
9686 | T-16-3rd Floor Common Area | Not Ready | 1st Coat Painting | 2026-07-16 | 2026-08-06 | 1st Coat Painting | 100 | 0 |  | 2026-07-04 |  | 2026-07-26
11767 | T-18-3rd Floor Common Area | Not Ready | 2nd Coat Painting | 2026-09-15 | 2026-10-19 | 2nd Coat Painting | 100 | 0 |  | 2026-07-04 |  | 2026-08-07
12009 | T-18-Staircase 1 | Not Ready |  | 2026-09-10 | 2026-09-21 | 04F-03F | 100 | 0 |  | 2026-07-04 |  | 2026-07-14
12023 | T-18-Staircase 2 | Not Ready |  | 2026-09-10 | 2026-09-21 | 05F-04F | 100 | 0 |  | 2026-07-04 |  | 2026-07-14
41744 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-06-13 | 2026-06-17 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-07-04 |  | 2026-07-08 |  | Tower A | Super Structure | L49
41771 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-06-13 | 2026-06-22 | False Ceiling | 100 | 0 |  | 2026-07-04 |  | 2026-07-14 |  | Tower A | Super Structure | L51 | Finishes | False Ceiling
41786 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-06-13 | 2026-06-25 | Flooring & Dado | 100 | 0 |  | 2026-07-04 |  | 2026-07-17 |  | Tower A | Super Structure | L52 | Finishes | Flooring & Dado
42753 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-07-07 | 2026-07-09 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-07-04 |  | 2026-07-07 |  | Tower A | Super Structure | L37 | MEP | FPS 2nd Fix - MEP & Finishes
42754 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-07-07 | 2026-07-09 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-07-04 |  | 2026-07-07 |  | Tower A | Super Structure | L37 | MEP | Electrical 2nd Fix - MEP & Finishes
42771 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-07-07 | 2026-07-09 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-07-04 |  | 2026-07-07 |  | Tower A | Super Structure | L38 | MEP | FPS 2nd Fix - MEP & Finishes
42772 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-07-07 | 2026-07-09 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-07-04 |  | 2026-07-07 |  | Tower A | Super Structure | L38 | MEP | Electrical 2nd Fix - MEP & Finishes
42789 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-07-07 | 2026-07-09 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-07-04 |  | 2026-07-07 |  | Tower A | Super Structure | L39 | MEP | FPS 2nd Fix - MEP & Finishes
42790 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-07-07 | 2026-07-09 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-07-04 |  | 2026-07-07 |  | Tower A | Super Structure | L39 | MEP | Electrical 2nd Fix - MEP & Finishes
42805 |  | Not Committed |  | 2026-07-07 | 2026-08-12 | MEP final fix & Finishes | 100 | 0 |  | 2026-07-04 |  | 2026-07-29
42806 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-07-07 | 2026-07-11 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-07-04 |  | 2026-07-09 |  | Tower A | Super Structure | L40 | Finishes | Door & Window Fixing
42823 |  | Not Committed |  | 2026-07-07 | 2026-08-12 | MEP final fix & Finishes | 100 | 0 |  | 2026-07-04 |  | 2026-07-29
42824 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-07-07 | 2026-07-11 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-07-04 |  | 2026-07-09 |  | Tower A | Super Structure | L41 | Finishes | Door & Window Fixing
42841 |  | Not Committed |  | 2026-07-07 | 2026-08-12 | MEP final fix & Finishes | 100 | 0 |  | 2026-07-04 |  | 2026-07-29
42842 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-07-07 | 2026-07-11 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-07-04 |  | 2026-07-09 |  | Tower A | Super Structure | L42 | Finishes | Door & Window Fixing
47674 |  | Not Ready |  | 2026-07-04 | 2026-07-17 | Section 8_lift 1 | 100 | 0 |  | 2026-07-04 |  | 2026-07-17
47674 |  | Not Ready |  | 2026-07-04 | 2026-07-17 | Section 8_lift 1 | 100 | 0 |  | 2026-07-04 |  | 2026-07-17 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47683 |  | Not Ready |  | 2026-07-04 | 2026-07-11 | Section 5_lift 2 | 100 | 0 |  | 2026-07-04 |  | 2026-07-11
47683 |  | Not Ready |  | 2026-07-04 | 2026-07-11 | Section 5_lift 2 | 100 | 0 |  | 2026-07-04 |  | 2026-07-11 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47685 |  | Not Ready |  | 2026-07-04 | 2026-07-11 | Section 7_lift 2 | 100 | 0 |  | 2026-07-04 |  | 2026-07-11
47685 |  | Not Ready |  | 2026-07-04 | 2026-07-11 | Section 7_lift 2 | 100 | 0 |  | 2026-07-04 |  | 2026-07-11 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
48048 | Club House - Super structure - CH01 to CH02 | Not Ready |  | 2026-03-14 | 2026-03-20 | Walls | 100 | 0 |  | 2026-07-04 |  | 2026-07-10 |  | Club House | Super Structure | CH01
11975 | T-18-11th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-09-25 | 2026-10-29 | 2nd Coat Painting | 100 | 0 |  | 2026-07-05 |  | 2026-08-06
12034 | T-18- Elevation-D | Not Ready |  | 2026-09-21 | 2026-12-15 | Elevation-D | 100 | 0 |  | 2026-07-05 |  | 2026-09-26
10433 | T-21-Lift Lobby | Not Ready |  | 2026-08-04 | 2026-08-21 | 04F | 100 | 0 |  | 2026-07-06 |  | 2026-07-20
40089 | Tower A - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2026-06-13 | 2026-06-20 | Balancing, Load Testing, High Speed Testing | 100 | 0 |  | 2026-07-06 |  | 2026-07-15 |  | Tower A | Super Structure
40089 | Tower A - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2026-06-13 | 2026-06-20 | Balancing, Load Testing, High Speed Testing | 100 | 0 |  | 2026-07-06 |  | 2026-07-15 |  | Tower A | Super Structure
41814 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-06-15 | 2026-06-17 | FAPA Cabling | 100 | 0 |  | 2026-07-06 |  | 2026-07-08 |  | Tower A | Super Structure | L54
42649 | Tower A - Super Structure - Finishes & MEP - L31 to L32 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-07-08 | 2026-07-10 | Painting Works | 100 | 0 |  | 2026-07-06 |  | 2026-07-08 |  | Tower A | Super Structure | L31 | Finishes | Painting Works
42667 | Tower A - Super Structure - Finishes & MEP - L32 to L33 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-07-08 | 2026-07-10 | Painting Works | 100 | 0 |  | 2026-07-06 |  | 2026-07-08 |  | Tower A | Super Structure | L32 | Finishes | Painting Works
42685 | Tower A - Super Structure - Finishes & MEP - L33 to L34 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-07-08 | 2026-07-10 | Painting Works | 100 | 0 |  | 2026-07-06 |  | 2026-07-08 |  | Tower A | Super Structure | L33 | Finishes | Painting Works
44603 |  | Not Ready | MEP fix & Finishes | 2026-07-08 | 2026-07-16 | HVAC Fans fixing | 100 | 0 |  | 2026-07-06 |  | 2026-07-14 |  |  |  |  | MEP | HVAC Grill Fixing
44603 |  | Not Ready | MEP fix & Finishes | 2026-07-08 | 2026-07-16 | HVAC Fans fixing | 100 | 0 |  | 2026-07-06 |  | 2026-07-14 |  |  |  |  | MEP | HVAC Grill Fixing
46804 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-04-23 | 2026-05-11 | Wet Area Waterproofing | 100 | 0 |  | 2026-07-06 |  | 2026-07-25 |  | Tower B | Super Structure | L15
8847 | T-14-12th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-06-14 | 2026-08-19 | 2nd Coat Painting | 100 | 0 |  | 2026-07-07 |  | 2026-09-14
8868 | T-14-Lift Lobby | Not Ready |  | 2026-06-04 | 2026-06-20 | 09F | 100 | 0 |  | 2026-07-07 |  | 2026-07-22
10971 | T-20-Staircase 1 | Not Ready |  | 2026-07-24 | 2026-08-04 | 02F-01F | 100 | 0 |  | 2026-07-07 |  | 2026-07-18
10985 | T-20-Staircase 2 | Not Ready |  | 2026-07-24 | 2026-08-04 | 03F-02F | 100 | 0 |  | 2026-07-07 |  | 2026-07-18
11192 | T-19-1st Floor Common Area | Not Ready | Door-Shaft | 2026-07-17 | 2026-07-30 | Door-Shaft | 100 | 0 |  | 2026-07-07 |  | 2026-07-20
11991 | T-18-Lift Lobby | Not Ready |  | 2026-09-21 | 2026-10-09 | 06F | 100 | 0 |  | 2026-07-07 |  | 2026-07-22
39267 | Retail - Sub structure - B1 to GF | Not Ready | RCC Works - Vertical | 2026-01-13 | 2026-02-03 | Columns/ Walls_NTA | 100 | 0 |  | 2026-07-07 |  | 2026-07-27 |  | Retail | Sub Structure | B1 | RCC Sub Structure | RCC Works - Vertical
39267 | Retail - Sub structure - B1 to GF | Not Ready | RCC Works - Vertical | 2026-01-13 | 2026-02-03 | Columns/ Walls_NTA | 100 | 0 |  | 2026-07-07 |  | 2026-07-27 |  | Retail | Sub Structure | B1
41756 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-06-16 | 2026-06-19 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-07-07 |  | 2026-07-10 |  | Tower A | Super Structure | L50 | MEP | FPS 2nd Fix - MEP & Finishes
41757 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-06-16 | 2026-06-22 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-07-07 |  | 2026-07-14 |  | Tower A | Super Structure | L50 | MEP | Electrical 2nd Fix - MEP & Finishes
41758 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-06-16 | 2026-06-24 | FAPA Device Fixing | 100 | 0 |  | 2026-07-07 |  | 2026-07-16 |  | Tower A | Super Structure | L50
41758 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-06-16 | 2026-06-24 | FAPA Device Fixing | 100 | 0 |  | 2026-07-07 |  | 2026-07-16 |  | Tower A | Super Structure | L50
41758 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-06-16 | 2026-06-24 | FAPA Device Fixing | 100 | 0 |  | 2026-07-07 |  | 2026-07-16 |  | Tower A | Super Structure | L50
41758 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-06-16 | 2026-06-24 | FAPA Device Fixing | 100 | 0 |  | 2026-07-07 |  | 2026-07-16 |  | Tower A | Super Structure | L50
41759 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-06-16 | 2026-06-19 | HVAC Grill Fixing | 100 | 0 |  | 2026-07-07 |  | 2026-07-10 |  | Tower A | Super Structure | L50 | MEP | HVAC Grill Fixing
43398 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-06-24 | 2026-07-10 | Flooring & Dado works | 100 | 0 |  | 2026-07-07 |  | 2026-07-25 |  | Tower A | Super Structure | L73 | Finishes | Flooring & Dado
45472 | Tower B - Super Structure - Finishes & MEP - L16 to L17 | Not Ready | Partition Wall-Blockwork | 2026-04-21 | 2026-04-25 | Staircase Area | 100 | 0 |  | 2026-07-07 |  | 2026-07-14 |  | Tower B | Super Structure | L16
45793 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-05-02 | 2026-05-09 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-07-07 |  | 2026-07-16 |  | Tower B | Sub Structure | B3 | MEP | FPS 2nd Fix - MEP & Finishes
45794 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-05-02 | 2026-05-09 | FAPA Device Fixing | 100 | 0 |  | 2026-07-07 |  | 2026-07-16 |  | Tower B | Sub Structure | B3
45794 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-05-02 | 2026-05-09 | FAPA Device Fixing | 100 | 0 |  | 2026-07-07 |  | 2026-07-16 |  | Tower B | Sub Structure | B3
45794 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-05-02 | 2026-05-09 | FAPA Device Fixing | 100 | 0 |  | 2026-07-07 |  | 2026-07-16 |  | Tower B | Sub Structure | B3
45794 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-05-02 | 2026-05-09 | FAPA Device Fixing | 100 | 0 |  | 2026-07-07 |  | 2026-07-16 |  | Tower B | Sub Structure | B3
9434 | T-15- Elevation-D | Not Ready |  | 2026-07-20 | 2026-10-12 | Elevation-D | 100 | 0 |  | 2026-07-08 |  | 2026-09-30
10423 | T-21-Lift | Not Ready | Waterproofing | 2026-08-12 | 2026-11-21 | Waterproofing | 100 | 0 |  | 2026-07-08 |  | 2026-10-17
10952 | T-20-Lift Lobby | Not Ready |  | 2026-07-30 | 2026-08-16 | 05F | 100 | 0 |  | 2026-07-08 |  | 2026-07-23
41730 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-17 | 2026-06-23 | Final Painting | 100 | 0 |  | 2026-07-08 |  | 2026-07-15 |  | Tower A | Super Structure | L48 | Finishes | Final Painting
41730 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-17 | 2026-06-23 | Final Painting | 100 | 0 |  | 2026-07-08 |  | 2026-07-15 |  | Tower A | Super Structure | L48 | Finishes | Final Painting
41730 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-17 | 2026-06-23 | Final Painting | 100 | 0 |  | 2026-07-08 |  | 2026-07-15 |  | Tower A | Super Structure | L48 | Finishes | Final Painting
41745 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-06-17 | 2026-06-23 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-07-08 |  | 2026-07-15 |  | Tower A | Super Structure | L49 | MEP | Electrical
41815 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-06-17 | 2026-06-25 | HVAC Ducting | 100 | 0 |  | 2026-07-08 |  | 2026-07-17 |  | Tower A | Super Structure | L54 | MEP | HVAC Ducting
41828 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-06-17 | 2026-06-23 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-07-08 |  | 2026-07-15 |  | Tower A | Super Structure | L55 | MEP | FPS 1st Fix - MEP & Finishes
41829 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-06-17 | 2026-06-20 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-07-08 |  | 2026-07-11 |  | Tower A | Super Structure | L55 | MEP | Electrical 1st Fixes
42702 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-07-10 | 2026-07-14 | PHE Final Fixes | 100 | 0 |  | 2026-07-08 |  | 2026-07-10 |  | Tower A | Super Structure | L34
42738 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-07-10 | 2026-07-14 | PHE Final Fixes | 100 | 0 |  | 2026-07-08 |  | 2026-07-10 |  | Tower A | Super Structure | L36
42755 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-07-10 | 2026-07-16 | False Ceiling | 100 | 0 |  | 2026-07-08 |  | 2026-07-14 |  | Tower A | Super Structure | L37 | Finishes | False Ceiling
42773 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-07-10 | 2026-07-16 | False Ceiling | 100 | 0 |  | 2026-07-08 |  | 2026-07-14 |  | Tower A | Super Structure | L38 | Finishes | False Ceiling
42791 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-07-10 | 2026-07-16 | False Ceiling | 100 | 0 |  | 2026-07-08 |  | 2026-07-14 |  | Tower A | Super Structure | L39 | Finishes | False Ceiling
44001 | Tower A - Super Structure - Finishes & MEP - L45 to L55 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-08-29 | 2026-09-18 | Staircase Light Fixtures & Devices fixing | 100 | 0 |  | 2026-07-08 |  | 2026-07-29 |  | Tower A | Super Structure | L45
44145 | Tower A - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2026-06-16 | 2026-06-23 | Glass Assembly Installation | 100 | 0 |  | 2026-07-08 |  | 2026-07-17 |  | Tower A | Super Structure | L7
44146 | Tower A - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2026-06-16 | 2026-06-22 | ACP Sheet & Insulation fixing | 100 | 0 |  | 2026-07-08 |  | 2026-07-16 |  | Tower A | Super Structure | L7
44147 | Tower A - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2026-06-16 | 2026-06-22 | Fixing of Louvers | 100 | 0 |  | 2026-07-08 |  | 2026-07-16 |  | Tower A | Super Structure | L7 | Façade | Façade Works
44147 | Tower A - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2026-06-16 | 2026-06-22 | Fixing of Louvers | 100 | 0 |  | 2026-07-08 |  | 2026-07-16 |  | Tower A | Super Structure | L7
44149 |  | Not Committed |  | 2026-06-16 | 2026-07-08 | L15-25 | 100 | 0 |  | 2026-07-08 |  | 2026-08-05
44149 |  | Not Committed |  | 2026-06-16 | 2026-07-08 | L15-25 | 100 | 0 |  | 2026-07-08 |  | 2026-08-05
44150 | Tower A - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2026-06-16 | 2026-06-23 | Al. Frame Section Installation | 100 | 0 |  | 2026-07-08 |  | 2026-07-17 |  | Tower A | Super Structure | L15
44188 | Tower A - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2026-06-16 | 2026-06-23 | Glass Assembly Installation | 100 | 0 |  | 2026-07-08 |  | 2026-07-17 |  | Tower A | Super Structure | L7
44189 | Tower A - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2026-06-16 | 2026-06-22 | ACP Sheet & Insulation fixing | 100 | 0 |  | 2026-07-08 |  | 2026-07-16 |  | Tower A | Super Structure | L7
44190 | Tower A - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2026-06-16 | 2026-06-22 | Fixing of Louvers | 100 | 0 |  | 2026-07-08 |  | 2026-07-16 |  | Tower A | Super Structure | L7 | Façade | Façade Works
44190 | Tower A - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2026-06-16 | 2026-06-22 | Fixing of Louvers | 100 | 0 |  | 2026-07-08 |  | 2026-07-16 |  | Tower A | Super Structure | L7
44192 |  | Not Committed |  | 2026-06-16 | 2026-07-08 | L15-25 | 100 | 0 |  | 2026-07-08 |  | 2026-08-05
44192 |  | Not Committed |  | 2026-06-16 | 2026-07-08 | L15-25 | 100 | 0 |  | 2026-07-08 |  | 2026-08-05
44193 | Tower A - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2026-06-16 | 2026-06-23 | Al. Frame Section Installation | 100 | 0 |  | 2026-07-08 |  | 2026-07-17 |  | Tower A | Super Structure | L15
44267 |  | Not Ready |  | 2026-07-10 | 2026-07-23 | Sub-Station License by Chief Electrical Inspector | 100 | 0 |  | 2026-07-08 |  | 2026-08-11
46787 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-04-29 | 2026-05-11 | Cement Plastering in wet areas | 100 | 0 |  | 2026-07-08 |  | 2026-07-22 |  | Tower B | Super Structure | L14
44251 |  | Not Ready |  | 2026-07-11 | 2026-12-10 | Club House Interior Fit-out | 100 | 0 |  | 2026-07-09 |  | 2026-11-24
44252 |  | Not Ready | Interior Fit-out | 2026-07-11 | 2026-09-10 | Wood works | 100 | 0 |  | 2026-07-09 |  | 2026-09-07
44253 |  | Not Ready | Interior Fit-out | 2026-07-11 | 2026-08-22 | Interior Glass Partitions | 100 | 0 |  | 2026-07-09 |  | 2026-08-20
44254 |  | Not Ready | Interior Fit-out | 2026-07-11 | 2026-08-22 | Wall Panelling Works | 100 | 0 |  | 2026-07-09 |  | 2026-08-20
45618 | Tower B - Super Structure - Finishes & MEP - L15 to L16 | Not Ready | Gypsum Plastering Works | 2026-04-27 | 2026-06-13 | L15-16 | 100 | 0 |  | 2026-07-09 |  | 2026-09-02 |  | Tower B | Super Structure | L15 | Finishes | Gypsum Plastering Works
45618 | Tower B - Super Structure - Finishes & MEP - L15 to L16 | Not Ready | Gypsum Plastering Works | 2026-04-27 | 2026-06-13 | L15-16 | 100 | 0 |  | 2026-07-09 |  | 2026-09-02 |  | Tower B | Super Structure | L15
9114 | T-15-1st Floor Common Area | Not Ready | 1st Coat Painting | 2026-07-02 | 2026-07-24 | 1st Coat Painting | 100 | 0 |  | 2026-07-10 |  | 2026-07-30
9391 | T-15-Lift Lobby | Not Ready |  | 2026-07-20 | 2026-08-05 | 06F | 100 | 0 |  | 2026-07-10 |  | 2026-07-26
9894 | T-16-11th Floor Common Area | Not Ready | 1st Coat Painting | 2026-08-01 | 2026-08-24 | 1st Coat Painting | 100 | 0 |  | 2026-07-10 |  | 2026-08-03
9925 | T-16-Staircase 1 | Not Ready |  | 2026-07-22 | 2026-08-02 | 08F-07F | 100 | 0 |  | 2026-07-10 |  | 2026-07-22
9939 | T-16-Staircase 2 | Not Ready |  | 2026-07-22 | 2026-08-02 | 09F-08F | 100 | 0 |  | 2026-07-10 |  | 2026-07-22
41760 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-06-19 | 2026-06-23 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-07-10 |  | 2026-07-15 |  | Tower A | Super Structure | L50
41787 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-06-19 | 2026-06-27 | False Ceiling | 100 | 0 |  | 2026-07-10 |  | 2026-07-21 |  | Tower A | Super Structure | L52 | Finishes | False Ceiling
41802 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-06-19 | 2026-07-01 | Flooring & Dado | 100 | 0 |  | 2026-07-10 |  | 2026-07-24 |  | Tower A | Super Structure | L53 | Finishes | Flooring & Dado
42720 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-07-16 | 2026-07-18 | PHE Final Fixes | 100 | 0 |  | 2026-07-10 |  | 2026-07-14 |  | Tower A | Super Structure | L35
42807 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-07-16 | 2026-07-18 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-07-10 |  | 2026-07-14 |  | Tower A | Super Structure | L40 | MEP | FPS 2nd Fix - MEP & Finishes
42808 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-07-16 | 2026-07-18 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-07-10 |  | 2026-07-14 |  | Tower A | Super Structure | L40 | MEP | Electrical 2nd Fix - MEP & Finishes
42825 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-07-16 | 2026-07-18 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-07-10 |  | 2026-07-14 |  | Tower A | Super Structure | L41 | MEP | FPS 2nd Fix - MEP & Finishes
42826 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-07-16 | 2026-07-18 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-07-10 |  | 2026-07-14 |  | Tower A | Super Structure | L41 | MEP | Electrical 2nd Fix - MEP & Finishes
42843 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-07-16 | 2026-07-18 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-07-10 |  | 2026-07-14 |  | Tower A | Super Structure | L42 | MEP | FPS 2nd Fix - MEP & Finishes
42844 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-07-16 | 2026-07-18 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-07-10 |  | 2026-07-14 |  | Tower A | Super Structure | L42 | MEP | Electrical 2nd Fix - MEP & Finishes
42859 |  | Not Committed |  | 2026-07-16 | 2026-08-25 | MEP final fix & Finishes | 100 | 0 |  | 2026-07-10 |  | 2026-08-05
42860 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-07-16 | 2026-07-22 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-07-10 |  | 2026-07-16 |  | Tower A | Super Structure | L43 | Finishes | Door & Window Fixing
42877 |  | Not Committed |  | 2026-07-16 | 2026-08-25 | MEP final fix & Finishes | 100 | 0 |  | 2026-07-10 |  | 2026-08-05
42878 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-07-16 | 2026-07-22 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-07-10 |  | 2026-07-16 |  | Tower A | Super Structure | L44 | Finishes | Door & Window Fixing
42895 |  | Not Committed |  | 2026-07-16 | 2026-08-25 | MEP final fix & Finishes | 100 | 0 |  | 2026-07-10 |  | 2026-08-05
42896 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-07-16 | 2026-07-22 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-07-10 |  | 2026-07-16 |  | Tower A | Super Structure | L45 | Finishes | Door & Window Fixing
9908 | T-16-Lift Lobby | Not Ready |  | 2026-07-28 | 2026-08-13 | 09F | 100 | 0 |  | 2026-07-11 |  | 2026-07-26
11429 | T-19-11th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-08-01 | 2026-09-04 | 2nd Coat Painting | 100 | 0 |  | 2026-07-11 |  | 2026-08-11
11447 | T-19-11th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-08-01 | 2026-10-08 | 2nd Coat Painting | 100 | 0 |  | 2026-07-11 |  | 2026-09-14
41830 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-06-20 | 2026-06-23 | FAPA Cabling | 100 | 0 |  | 2026-07-11 |  | 2026-07-15 |  | Tower A | Super Structure | L55
42703 | Tower A - Super Structure - Finishes & MEP - L34 to L35 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-07-17 | 2026-07-21 | Painting Works | 100 | 0 |  | 2026-07-11 |  | 2026-07-15 |  | Tower A | Super Structure | L34 | Finishes | Painting Works
42739 | Tower A - Super Structure - Finishes & MEP - L36 to L37 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-07-17 | 2026-07-21 | Painting Works | 100 | 0 |  | 2026-07-11 |  | 2026-07-15 |  | Tower A | Super Structure | L36 | Finishes | Painting Works
45313 |  | Not Ready |  | 2026-04-18 | 2026-05-07 | L21-22 (Service Floor) | 100 | 0 |  | 2026-07-11 |  | 2026-07-30
45314 | Tower B - Super Structure - Core & Outer Slab L21-22 | Not Ready | RCC Works - Vertical | 2026-04-18 | 2026-05-02 | Outer Columns_TA | 100 | 0 |  | 2026-07-11 |  | 2026-07-25 |  | Tower B | Super Structure | L21 | RCC Sub Structure | RCC Works - Vertical
45477 |  | Not Committed |  | 2026-04-18 | 2026-05-20 | L18-19 | 100 | 0 |  | 2026-07-11 |  | 2026-08-20
45477 |  | Not Committed |  | 2026-04-18 | 2026-05-20 | L18-19 | 100 | 0 |  | 2026-07-11 |  | 2026-08-20 |  |  |  |  | Finishes | Gypsum Plastering Works
45478 | Tower B - Super Structure - Finishes & MEP - L18 to L19 | Not Ready | Partition Wall-Blockwork | 2026-04-18 | 2026-05-06 | De-shuttering & Area clearance | 100 | 0 |  | 2026-07-11 |  | 2026-08-01 |  | Tower B | Super Structure | L18
47382 |  | Not Ready |  | 2026-04-18 | 2028-02-19 | Façade Works_TB | 100 | 0 |  | 2026-07-11 |  | 2028-04-29
47406 |  | Not Committed |  | 2026-04-18 | 2027-07-10 | Typical Floors | 100 | 0 |  | 2026-07-11 |  | 2027-09-20
47407 |  | Not Committed |  | 2026-04-18 | 2026-06-11 | L7-13 | 100 | 0 |  | 2026-07-11 |  | 2026-09-10
47408 | Tower B - Super Structure - Finishes & MEP - L7 to L13 | Not Ready | Façade Works - MEP & Finishes | 2026-04-18 | 2026-05-12 | Al. Frame section (Mullion & Transom) Installation | 100 | 0 |  | 2026-07-11 |  | 2026-08-08 |  | Tower B | Super Structure | L7 | Façade | Façade Works
48049 | Club House - Super structure - CH01 to CH02 | Not Ready |  | 2026-03-21 | 2026-03-28 | Top slab outside pool area | 100 | 0 |  | 2026-07-11 |  | 2026-07-21 |  | Club House | Super Structure | CH01
8568 | T-14-1st Floor Common Area | Not Ready | 1st Coat Painting | 2026-06-03 | 2026-06-25 | 1st Coat Painting | 100 | 0 |  | 2026-07-12 |  | 2026-08-03
11469 | T-19-8th Floor | Not Ready |  | 2026-07-23 | 2026-08-08 | 08F | 100 | 0 |  | 2026-07-12 |  | 2026-07-28
9410 | T-15-Staircase 1 | Not Ready |  | 2026-07-20 | 2026-07-30 | 03F-02F | 100 | 0 |  | 2026-07-13 |  | 2026-07-24
9424 | T-15-Staircase 2 | Not Ready |  | 2026-07-20 | 2026-07-30 | 04F-03F | 100 | 0 |  | 2026-07-13 |  | 2026-07-24
8886 | T-14-Staircase 1 | Not Ready |  | 2026-06-10 | 2026-06-20 | 07F-06F | 100 | 0 |  | 2026-07-14 |  | 2026-07-25
8900 | T-14-Staircase 2 | Not Ready |  | 2026-06-10 | 2026-06-20 | 08F-07F | 100 | 0 |  | 2026-07-14 |  | 2026-07-25
9375 | T-15-11th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-07-24 | 2026-08-27 | 2nd Coat Painting | 100 | 0 |  | 2026-07-14 |  | 2026-08-17
10943 | T-20-Lift | Not Ready | Waterproofing | 2026-08-24 | 2026-12-03 | Waterproofing | 100 | 0 |  | 2026-07-14 |  | 2026-10-21
11487 | T-19-Staircase 1 | Not Ready |  | 2026-07-23 | 2026-08-03 | 06F-05F | 100 | 0 |  | 2026-07-14 |  | 2026-07-23
11501 | T-19-Staircase 2 | Not Ready |  | 2026-07-23 | 2026-08-03 | 07F-06F | 100 | 0 |  | 2026-07-14 |  | 2026-07-23
41772 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-06-22 | 2026-06-25 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-07-14 |  | 2026-07-17 |  | Tower A | Super Structure | L51 | MEP | FPS 2nd Fix - MEP & Finishes
41773 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-06-22 | 2026-06-27 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-07-14 |  | 2026-07-21 |  | Tower A | Super Structure | L51 | MEP | Electrical 2nd Fix - MEP & Finishes
41774 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-06-22 | 2026-06-30 | FAPA Device Fixing | 100 | 0 |  | 2026-07-14 |  | 2026-07-23 |  | Tower A | Super Structure | L51
41774 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-06-22 | 2026-06-30 | FAPA Device Fixing | 100 | 0 |  | 2026-07-14 |  | 2026-07-23 |  | Tower A | Super Structure | L51
41774 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-06-22 | 2026-06-30 | FAPA Device Fixing | 100 | 0 |  | 2026-07-14 |  | 2026-07-23 |  | Tower A | Super Structure | L51
41774 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-06-22 | 2026-06-30 | FAPA Device Fixing | 100 | 0 |  | 2026-07-14 |  | 2026-07-23 |  | Tower A | Super Structure | L51
41775 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-06-22 | 2026-06-25 | HVAC Grill Fixing | 100 | 0 |  | 2026-07-14 |  | 2026-07-17 |  | Tower A | Super Structure | L51 | MEP | HVAC Grill Fixing
46817 |  | Not Committed |  | 2026-04-27 | 2027-05-28 | L16-17 | 100 | 0 |  | 2026-07-14 |  | 2027-07-15
46817 |  | Not Committed |  | 2026-04-27 | 2027-05-28 | L16-17 | 100 | 0 |  | 2026-07-14 |  | 2027-07-15 |  |  |  |  | Finishes | Gypsum Plastering Works
46818 |  | Not Committed |  | 2026-04-27 | 2026-06-04 | MEP 1st Fixes | 100 | 0 |  | 2026-07-14 |  | 2026-08-27
46819 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-04-27 | 2026-05-05 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-07-14 |  | 2026-07-23 |  | Tower B | Super Structure | L16 | MEP | FPS 1st Fix - MEP & Finishes
46820 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-04-27 | 2026-05-02 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-07-14 |  | 2026-07-21 |  | Tower B | Super Structure | L16 | MEP | Electrical 1st Fixes
46821 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-04-27 | 2026-05-05 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-07-14 |  | 2026-07-23 |  | Tower B | Super Structure | L16
9843 | T-16-9th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-08-07 | 2026-09-09 | 2nd Coat Painting | 100 | 0 |  | 2026-07-15 |  | 2026-08-17
9861 | T-16-10th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-08-07 | 2026-10-13 | 2nd Coat Painting | 100 | 0 |  | 2026-07-15 |  | 2026-09-20
10453 | T-21-Staircase 1 | Not Ready |  | 2026-08-04 | 2026-08-14 | GF-BF | 100 | 0 |  | 2026-07-15 |  | 2026-07-26
10467 | T-21-Staircase 2 | Not Ready |  | 2026-08-04 | 2026-08-14 | 01F-GF | 100 | 0 |  | 2026-07-15 |  | 2026-07-26
12010 | T-18-Staircase 1 | Not Ready |  | 2026-09-21 | 2026-10-03 | 03F-02F | 100 | 0 |  | 2026-07-15 |  | 2026-07-24
12024 | T-18-Staircase 2 | Not Ready |  | 2026-09-21 | 2026-10-03 | 04F-03F | 100 | 0 |  | 2026-07-15 |  | 2026-07-24
40090 | Tower A - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2026-06-22 | 2026-06-26 | 3rd Party Testing & Commissioning | 100 | 0 |  | 2026-07-15 |  | 2026-07-22 |  | Tower A | Super Structure
40090 | Tower A - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2026-06-22 | 2026-06-26 | 3rd Party Testing & Commissioning | 100 | 0 |  | 2026-07-15 |  | 2026-07-22 |  | Tower A | Super Structure
41746 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-23 | 2026-06-29 | Final Painting | 100 | 0 |  | 2026-07-15 |  | 2026-07-22 |  | Tower A | Super Structure | L49 | Finishes | Final Painting
41746 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-23 | 2026-06-29 | Final Painting | 100 | 0 |  | 2026-07-15 |  | 2026-07-22 |  | Tower A | Super Structure | L49 | Finishes | Final Painting
41746 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-23 | 2026-06-29 | Final Painting | 100 | 0 |  | 2026-07-15 |  | 2026-07-22 |  | Tower A | Super Structure | L49 | Finishes | Final Painting
41761 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-06-23 | 2026-06-29 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-07-15 |  | 2026-07-22 |  | Tower A | Super Structure | L50 | MEP | Electrical
41762 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-23 | 2026-06-29 | Final Painting | 100 | 0 |  | 2026-07-15 |  | 2026-07-22 |  | Tower A | Super Structure | L50 | Finishes | Final Painting
41762 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-23 | 2026-06-29 | Final Painting | 100 | 0 |  | 2026-07-15 |  | 2026-07-22 |  | Tower A | Super Structure | L50 | Finishes | Final Painting
41762 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-23 | 2026-06-29 | Final Painting | 100 | 0 |  | 2026-07-15 |  | 2026-07-22 |  | Tower A | Super Structure | L50 | Finishes | Final Painting
41831 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-06-23 | 2026-07-01 | HVAC Ducting | 100 | 0 |  | 2026-07-15 |  | 2026-07-24 |  | Tower A | Super Structure | L55 | MEP | HVAC Ducting
41844 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-06-23 | 2026-06-29 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-07-15 |  | 2026-07-22 |  | Tower A | Super Structure | L56 | MEP | FPS 1st Fix - MEP & Finishes
41845 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-06-23 | 2026-06-26 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-07-15 |  | 2026-07-18 |  | Tower A | Super Structure | L56 | MEP | Electrical 1st Fixes
42721 | Tower A - Super Structure - Finishes & MEP - L35 to L36 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-07-23 | 2026-07-25 | Painting Works | 100 | 0 |  | 2026-07-15 |  | 2026-07-17 |  | Tower A | Super Structure | L35 | Finishes | Painting Works
42756 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-07-23 | 2026-07-25 | PHE Final Fixes | 100 | 0 |  | 2026-07-15 |  | 2026-07-17 |  | Tower A | Super Structure | L37
42774 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-07-23 | 2026-07-25 | PHE Final Fixes | 100 | 0 |  | 2026-07-15 |  | 2026-07-17 |  | Tower A | Super Structure | L38
42792 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-07-23 | 2026-07-25 | PHE Final Fixes | 100 | 0 |  | 2026-07-15 |  | 2026-07-17 |  | Tower A | Super Structure | L39
42809 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-07-23 | 2026-07-29 | False Ceiling | 100 | 0 |  | 2026-07-15 |  | 2026-07-21 |  | Tower A | Super Structure | L40 | Finishes | False Ceiling
42827 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-07-23 | 2026-07-29 | False Ceiling | 100 | 0 |  | 2026-07-15 |  | 2026-07-21 |  | Tower A | Super Structure | L41 | Finishes | False Ceiling
42845 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-07-23 | 2026-07-29 | False Ceiling | 100 | 0 |  | 2026-07-15 |  | 2026-07-21 |  | Tower A | Super Structure | L42 | Finishes | False Ceiling
44006 | Tower A - Super Structure - Finishes & MEP - L55 to L65 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-09-04 | 2026-10-03 | Staircase Railing | 100 | 0 |  | 2026-07-15 |  | 2026-08-12 |  | Tower A | Super Structure | L55
44012 | Tower A - Super Structure - Finishes & MEP - L65 to L77 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-09-04 | 2026-10-15 | Staircase Window | 100 | 0 |  | 2026-07-15 |  | 2026-08-26 |  | Tower A | Super Structure | L65
44286 |  | Not Committed |  | 2026-07-23 | 2026-09-21 | Testing & Commissioning and Handover | 100 | 0 |  | 2026-07-15 |  | 2026-09-11
44287 |  | Not Ready |  | 2026-07-23 | 2026-09-21 | Integrated T&C | 100 | 0 |  | 2026-07-15 |  | 2026-09-11
44604 |  | Not Ready | MEP fix & Finishes | 2026-07-23 | 2026-08-05 | Final Painting | 100 | 0 |  | 2026-07-15 |  | 2026-07-28 |  |  |  |  | Finishes | Final Painting
44604 |  | Not Ready | MEP fix & Finishes | 2026-07-23 | 2026-08-05 | Final Painting | 100 | 0 |  | 2026-07-15 |  | 2026-07-28 |  |  |  |  | Finishes | Final Painting
44604 |  | Not Ready | MEP fix & Finishes | 2026-07-23 | 2026-08-05 | Final Painting | 100 | 0 |  | 2026-07-15 |  | 2026-07-28 |  |  |  |  | Finishes | Final Painting
45475 | Tower B - Super Structure - Finishes & MEP - L17 to L18 | Not Ready | Partition Wall-Blockwork | 2026-04-24 | 2026-05-02 | Partition Walls | 100 | 0 |  | 2026-07-15 |  | 2026-07-24 |  | Tower B | Super Structure | L17
39212 |  | Not Ready |  | 2025-09-02 | 2025-10-14 | Disengaging / Handing Over / Taking Over | 100 | 0 |  | 2026-07-16 |  | 2026-08-26
40101 | Tower A - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2026-06-17 | 2026-07-03 | Connections & Termination Works | 100 | 0 |  | 2026-07-16 |  | 2026-08-06 |  | Tower A | Super Structure
45795 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2026-05-11 | 2026-05-19 | Final Painting | 100 | 0 |  | 2026-07-16 |  | 2026-07-28 |  | Tower B | Sub Structure | B3 | Finishes | Final Painting
45795 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2026-05-11 | 2026-05-19 | Final Painting | 100 | 0 |  | 2026-07-16 |  | 2026-07-28 |  | Tower B | Sub Structure | B3 | Finishes | Final Painting
45795 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2026-05-11 | 2026-05-19 | Final Painting | 100 | 0 |  | 2026-07-16 |  | 2026-07-28 |  | Tower B | Sub Structure | B3 | Finishes | Final Painting
8621 | T-14-3rd Floor Common Area | Not Ready | 2nd Coat Painting | 2026-06-14 | 2026-07-17 | 2nd Coat Painting | 100 | 0 |  | 2026-07-17 |  | 2026-08-18
8829 | T-14-11th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-06-25 | 2026-07-28 | 2nd Coat Painting | 100 | 0 |  | 2026-07-17 |  | 2026-08-19
9659 | T-16-2nd Floor Common Area | Not Ready | Window-Open Area | 2026-07-30 | 2026-08-06 | Window-Open Area | 100 | 0 |  | 2026-07-17 |  | 2026-07-27
41776 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-06-25 | 2026-06-29 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-07-17 |  | 2026-07-22 |  | Tower A | Super Structure | L51
41803 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-06-25 | 2026-07-03 | False Ceiling | 100 | 0 |  | 2026-07-17 |  | 2026-07-28 |  | Tower A | Super Structure | L53 | Finishes | False Ceiling
41818 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-06-25 | 2026-07-07 | Flooring & Dado | 100 | 0 |  | 2026-07-17 |  | 2026-07-31 |  | Tower A | Super Structure | L54 | Finishes | Flooring & Dado
42861 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-07-25 | 2026-07-29 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-07-17 |  | 2026-07-21 |  | Tower A | Super Structure | L43 | MEP | FPS 2nd Fix - MEP & Finishes
42862 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-07-25 | 2026-07-29 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-07-17 |  | 2026-07-21 |  | Tower A | Super Structure | L43 | MEP | Electrical 2nd Fix - MEP & Finishes
42879 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-07-25 | 2026-07-29 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-07-17 |  | 2026-07-21 |  | Tower A | Super Structure | L44 | MEP | FPS 2nd Fix - MEP & Finishes
42880 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-07-25 | 2026-07-29 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-07-17 |  | 2026-07-21 |  | Tower A | Super Structure | L44 | MEP | Electrical 2nd Fix - MEP & Finishes
42897 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-07-25 | 2026-07-29 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-07-17 |  | 2026-07-21 |  | Tower A | Super Structure | L45 | MEP | FPS 2nd Fix - MEP & Finishes
42898 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-07-25 | 2026-07-29 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-07-17 |  | 2026-07-21 |  | Tower A | Super Structure | L45 | MEP | Electrical 2nd Fix - MEP & Finishes
42913 |  | Not Committed |  | 2026-07-25 | 2026-08-31 | MEP final fix & Finishes | 100 | 0 |  | 2026-07-17 |  | 2026-08-12
42914 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-07-25 | 2026-07-31 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-07-17 |  | 2026-07-23 |  | Tower A | Super Structure | L46 | Finishes | Door & Window Fixing
42931 |  | Not Committed |  | 2026-07-25 | 2026-08-31 | MEP final fix & Finishes | 100 | 0 |  | 2026-07-17 |  | 2026-08-12
42932 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-07-25 | 2026-07-31 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-07-17 |  | 2026-07-23 |  | Tower A | Super Structure | L47 | Finishes | Door & Window Fixing
42949 |  | Not Committed |  | 2026-07-25 | 2026-08-31 | MEP final fix & Finishes | 100 | 0 |  | 2026-07-17 |  | 2026-08-12
42950 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-07-25 | 2026-07-31 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-07-17 |  | 2026-07-23 |  | Tower A | Super Structure | L48 | Finishes | Door & Window Fixing
44148 | Tower A - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2026-06-24 | 2026-06-30 | Accessories & Alignment | 100 | 0 |  | 2026-07-17 |  | 2026-07-25 |  | Tower A | Super Structure | L7 | Façade | Façade Works
44148 | Tower A - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2026-06-24 | 2026-06-30 | Accessories & Alignment | 100 | 0 |  | 2026-07-17 |  | 2026-07-25 |  | Tower A | Super Structure | L7
44151 | Tower A - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2026-06-24 | 2026-07-01 | Glass Assembly Installation | 100 | 0 |  | 2026-07-17 |  | 2026-07-28 |  | Tower A | Super Structure | L15
44152 | Tower A - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2026-06-24 | 2026-06-30 | ACP Sheet & Insulation fixing | 100 | 0 |  | 2026-07-17 |  | 2026-07-25 |  | Tower A | Super Structure | L15
44153 | Tower A - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2026-06-24 | 2026-06-30 | Fixing of Louvers | 100 | 0 |  | 2026-07-17 |  | 2026-07-25 |  | Tower A | Super Structure | L15 | Façade | Façade Works
44153 | Tower A - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2026-06-24 | 2026-06-30 | Fixing of Louvers | 100 | 0 |  | 2026-07-17 |  | 2026-07-25 |  | Tower A | Super Structure | L15
44155 |  | Not Committed |  | 2026-06-24 | 2026-07-17 | L25-35 | 100 | 0 |  | 2026-07-17 |  | 2026-08-14
44155 |  | Not Committed |  | 2026-06-24 | 2026-07-17 | L25-35 | 100 | 0 |  | 2026-07-17 |  | 2026-08-14
44156 | Tower A - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2026-06-24 | 2026-07-01 | Al. Frame Section Installation | 100 | 0 |  | 2026-07-17 |  | 2026-07-28 |  | Tower A | Super Structure | L25
44191 | Tower A - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2026-06-24 | 2026-06-30 | Accessories & Alignment | 100 | 0 |  | 2026-07-17 |  | 2026-07-25 |  | Tower A | Super Structure | L7 | Façade | Façade Works
44191 | Tower A - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2026-06-24 | 2026-06-30 | Accessories & Alignment | 100 | 0 |  | 2026-07-17 |  | 2026-07-25 |  | Tower A | Super Structure | L7
44194 | Tower A - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2026-06-24 | 2026-07-01 | Glass Assembly Installation | 100 | 0 |  | 2026-07-17 |  | 2026-07-28 |  | Tower A | Super Structure | L15
44195 | Tower A - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2026-06-24 | 2026-06-30 | ACP Sheet & Insulation fixing | 100 | 0 |  | 2026-07-17 |  | 2026-07-25 |  | Tower A | Super Structure | L15
44196 | Tower A - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2026-06-24 | 2026-06-30 | Fixing of Louvers | 100 | 0 |  | 2026-07-17 |  | 2026-07-25 |  | Tower A | Super Structure | L15 | Façade | Façade Works
44196 | Tower A - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2026-06-24 | 2026-06-30 | Fixing of Louvers | 100 | 0 |  | 2026-07-17 |  | 2026-07-25 |  | Tower A | Super Structure | L15
48248 |  | Not Committed |  | 2026-03-26 | 2026-10-24 | Club House Finishes | 100 | 0 |  | 2026-07-17 |  | 2027-02-13
48249 | Retail - Super structure - CH00 to CH01 | Not Ready |  | 2026-03-26 | 2026-07-10 | CH00-CH01 (P4-5) | 100 | 0 |  | 2026-07-17 |  | 2026-11-10 |  | Retail | Super Structure | CH00
8862 | T-14-Lift | Not Ready | Water Tanks including Finishes | 2026-06-26 | 2026-08-14 | Water Tanks including Finishes | 100 | 0 |  | 2026-07-18 |  | 2026-09-05
9167 | T-15-3rd Floor Common Area | Not Ready | 2nd Coat Painting | 2026-07-13 | 2026-08-16 | 2nd Coat Painting | 100 | 0 |  | 2026-07-18 |  | 2026-08-20
10675 | T-20-1st Floor Common Area | Not Ready | 2nd Coat Painting | 2026-08-14 | 2026-09-17 | 2nd Coat Painting | 100 | 0 |  | 2026-07-18 |  | 2026-08-18
41846 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-06-26 | 2026-06-29 | FAPA Cabling | 100 | 0 |  | 2026-07-18 |  | 2026-07-22 |  | Tower A | Super Structure | L56
42757 | Tower A - Super Structure - Finishes & MEP - L37 to L38 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-07-30 | 2026-08-01 | Painting Works | 100 | 0 |  | 2026-07-18 |  | 2026-07-22 |  | Tower A | Super Structure | L37 | Finishes | Painting Works
42775 | Tower A - Super Structure - Finishes & MEP - L38 to L39 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-07-30 | 2026-08-01 | Painting Works | 100 | 0 |  | 2026-07-18 |  | 2026-07-22 |  | Tower A | Super Structure | L38 | Finishes | Painting Works
42793 | Tower A - Super Structure - Finishes & MEP - L39 to L40 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-07-30 | 2026-08-01 | Painting Works | 100 | 0 |  | 2026-07-18 |  | 2026-07-22 |  | Tower A | Super Structure | L39 | Finishes | Painting Works
47677 |  | Not Ready |  | 2026-07-24 | 2026-08-07 | Section 11_lift 1 | 100 | 0 |  | 2026-07-18 |  | 2026-08-01
47677 |  | Not Ready |  | 2026-07-24 | 2026-08-07 | Section 11_lift 1 | 100 | 0 |  | 2026-07-18 |  | 2026-08-01 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47686 |  | Not Ready |  | 2026-07-24 | 2026-08-01 | Section 8_lift 2 | 100 | 0 |  | 2026-07-18 |  | 2026-07-28
47686 |  | Not Ready |  | 2026-07-24 | 2026-08-01 | Section 8_lift 2 | 100 | 0 |  | 2026-07-18 |  | 2026-07-28 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
10972 | T-20-Staircase 1 | Not Ready |  | 2026-08-04 | 2026-08-16 | 01F-GF | 100 | 0 |  | 2026-07-19 |  | 2026-07-28
10986 | T-20-Staircase 2 | Not Ready |  | 2026-08-04 | 2026-08-16 | 02F-01F | 100 | 0 |  | 2026-07-19 |  | 2026-07-28
8861 | T-14-Lift | Not Ready | OTS Covers | 2026-06-30 | 2026-08-02 | OTS Covers | 100 | 0 |  | 2026-07-20 |  | 2026-08-21
10434 | T-21-Lift Lobby | Not Ready |  | 2026-08-21 | 2026-09-07 | 03F | 100 | 0 |  | 2026-07-21 |  | 2026-08-05
11193 | T-19-1st Floor Common Area | Not Ready | Window-Open Area | 2026-07-30 | 2026-08-07 | Window-Open Area | 100 | 0 |  | 2026-07-21 |  | 2026-07-28
41788 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-06-27 | 2026-07-01 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-07-21 |  | 2026-07-24 |  | Tower A | Super Structure | L52 | MEP | FPS 2nd Fix - MEP & Finishes
41789 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-06-27 | 2026-07-03 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-07-21 |  | 2026-07-28 |  | Tower A | Super Structure | L52 | MEP | Electrical 2nd Fix - MEP & Finishes
41790 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-06-27 | 2026-07-06 | FAPA Device Fixing | 100 | 0 |  | 2026-07-21 |  | 2026-07-30 |  | Tower A | Super Structure | L52
41790 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-06-27 | 2026-07-06 | FAPA Device Fixing | 100 | 0 |  | 2026-07-21 |  | 2026-07-30 |  | Tower A | Super Structure | L52
41790 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-06-27 | 2026-07-06 | FAPA Device Fixing | 100 | 0 |  | 2026-07-21 |  | 2026-07-30 |  | Tower A | Super Structure | L52
41790 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-06-27 | 2026-07-06 | FAPA Device Fixing | 100 | 0 |  | 2026-07-21 |  | 2026-07-30 |  | Tower A | Super Structure | L52
41791 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-06-27 | 2026-07-01 | HVAC Grill Fixing | 100 | 0 |  | 2026-07-21 |  | 2026-07-24 |  | Tower A | Super Structure | L52 | MEP | HVAC Grill Fixing
45315 | Tower B - Super Structure - Core & Outer Slab L21-22 | Not Ready | RCC Works - Slab | 2026-04-28 | 2026-05-07 | Outer Slab_TA | 100 | 0 |  | 2026-07-21 |  | 2026-07-30 |  | Tower B | Super Structure | L21 | RCC Sub Structure | RCC Works - Slab
45850 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2026-05-14 | 2026-06-01 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-07-21 |  | 2026-08-11 |  | Tower B | Sub Structure | B1
45850 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2026-05-14 | 2026-06-01 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-07-21 |  | 2026-08-11 |  | Tower B | Sub Structure | B1
45850 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2026-05-14 | 2026-06-01 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-07-21 |  | 2026-08-11 |  | Tower B | Sub Structure | B1
45875 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-05-14 | 2026-05-21 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-07-21 |  | 2026-07-30 |  | Tower B | Super Structure | GF | MEP | FPS 2nd Fix - MEP & Finishes
9574 | T-16-Basement Floor | Not Ready | 2nd Coat Painting | 2026-09-02 | 2026-11-20 | 2nd Coat Painting | 100 | 0 |  | 2026-07-22 |  | 2026-10-06
40091 | Tower A - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2026-06-27 | 2026-07-02 | Obtaining PWD Lisence | 100 | 0 |  | 2026-07-22 |  | 2026-07-29 |  | Tower A | Super Structure
40091 | Tower A - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2026-06-27 | 2026-07-02 | Obtaining PWD Lisence | 100 | 0 |  | 2026-07-22 |  | 2026-07-29 |  | Tower A | Super Structure
41777 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-06-29 | 2026-07-04 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-07-22 |  | 2026-07-29 |  | Tower A | Super Structure | L51 | MEP | Electrical
41778 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-29 | 2026-07-04 | Final Painting | 100 | 0 |  | 2026-07-22 |  | 2026-07-29 |  | Tower A | Super Structure | L51 | Finishes | Final Painting
41778 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-29 | 2026-07-04 | Final Painting | 100 | 0 |  | 2026-07-22 |  | 2026-07-29 |  | Tower A | Super Structure | L51 | Finishes | Final Painting
41778 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-06-29 | 2026-07-04 | Final Painting | 100 | 0 |  | 2026-07-22 |  | 2026-07-29 |  | Tower A | Super Structure | L51 | Finishes | Final Painting
41847 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-06-29 | 2026-07-07 | HVAC Ducting | 100 | 0 |  | 2026-07-22 |  | 2026-07-31 |  | Tower A | Super Structure | L56 | MEP | HVAC Ducting
41860 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-06-29 | 2026-07-04 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-07-22 |  | 2026-07-29 |  | Tower A | Super Structure | L57 | MEP | FPS 1st Fix - MEP & Finishes
41861 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-06-29 | 2026-07-02 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-07-22 |  | 2026-07-25 |  | Tower A | Super Structure | L57 | MEP | Electrical 1st Fixes
42810 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-08-01 | 2026-08-05 | PHE Final Fixes | 100 | 0 |  | 2026-07-22 |  | 2026-07-24 |  | Tower A | Super Structure | L40
42828 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-08-01 | 2026-08-05 | PHE Final Fixes | 100 | 0 |  | 2026-07-22 |  | 2026-07-24 |  | Tower A | Super Structure | L41
42846 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-08-01 | 2026-08-05 | PHE Final Fixes | 100 | 0 |  | 2026-07-22 |  | 2026-07-24 |  | Tower A | Super Structure | L42
42863 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-08-01 | 2026-08-07 | False Ceiling | 100 | 0 |  | 2026-07-22 |  | 2026-07-28 |  | Tower A | Super Structure | L43 | Finishes | False Ceiling
42881 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-08-01 | 2026-08-07 | False Ceiling | 100 | 0 |  | 2026-07-22 |  | 2026-07-28 |  | Tower A | Super Structure | L44 | Finishes | False Ceiling
42899 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-08-01 | 2026-08-07 | False Ceiling | 100 | 0 |  | 2026-07-22 |  | 2026-07-28 |  | Tower A | Super Structure | L45 | Finishes | False Ceiling
44008 | Tower A - Super Structure - Finishes & MEP - L55 to L65 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-09-11 | 2026-10-03 | Staircase Light Fixtures & Devices fixing | 100 | 0 |  | 2026-07-22 |  | 2026-08-12 |  | Tower A | Super Structure | L55
8869 | T-14-Lift Lobby | Not Ready |  | 2026-06-20 | 2026-07-07 | 08F | 100 | 0 |  | 2026-07-23 |  | 2026-08-10
9926 | T-16-Staircase 1 | Not Ready |  | 2026-08-03 | 2026-08-13 | 07F-06F | 100 | 0 |  | 2026-07-23 |  | 2026-08-01
9940 | T-16-Staircase 2 | Not Ready |  | 2026-08-03 | 2026-08-13 | 08F-07F | 100 | 0 |  | 2026-07-23 |  | 2026-08-01
11462 | T-19-Lift | Not Ready | Water Tanks including Finishes | 2026-08-17 | 2026-10-06 | Water Tanks including Finishes | 100 | 0 |  | 2026-07-23 |  | 2026-09-10
11992 | T-18-Lift Lobby | Not Ready |  | 2026-10-09 | 2026-10-25 | 05F | 100 | 0 |  | 2026-07-23 |  | 2026-08-11
39226 |  | Not Ready |  | 2025-12-30 | 2026-03-03 | Disangaging / Handing Over / Taking Over | 100 | 0 |  | 2026-07-23 |  | 2026-09-23
40102 | Tower A - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2026-06-23 | 2026-07-16 | Pump Testing & Commissioning | 100 | 0 |  | 2026-07-23 |  | 2026-08-21 |  | Tower A | Super Structure
43434 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-08-06 | 2026-08-26 | Flooring & Dado works | 100 | 0 |  | 2026-07-23 |  | 2026-08-12 |  | Tower A | Super Structure | L77 | Finishes | Flooring & Dado
46822 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-05-06 | 2026-05-22 | Wet Area Waterproofing | 100 | 0 |  | 2026-07-23 |  | 2026-08-13 |  | Tower B | Super Structure | L16
9713 | T-16-4th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-08-07 | 2026-09-09 | 2nd Coat Painting | 100 | 0 |  | 2026-07-24 |  | 2026-08-26
10953 | T-20-Lift Lobby | Not Ready |  | 2026-08-17 | 2026-09-02 | 04F | 100 | 0 |  | 2026-07-24 |  | 2026-08-08
11488 | T-19-Staircase 1 | Not Ready |  | 2026-08-03 | 2026-08-13 | 05F-04F | 100 | 0 |  | 2026-07-24 |  | 2026-08-05
11502 | T-19-Staircase 2 | Not Ready |  | 2026-08-03 | 2026-08-13 | 06F-05F | 100 | 0 |  | 2026-07-24 |  | 2026-08-05
11741 | T-18-2nd Floor Common Area | Not Ready | 2nd Coat Painting | 2026-10-08 | 2026-11-11 | 2nd Coat Painting | 100 | 0 |  | 2026-07-24 |  | 2026-08-26
41792 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-07-01 | 2026-07-04 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-07-24 |  | 2026-07-29 |  | Tower A | Super Structure | L52
41819 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-07-01 | 2026-07-09 | False Ceiling | 100 | 0 |  | 2026-07-24 |  | 2026-08-04 |  | Tower A | Super Structure | L54 | Finishes | False Ceiling
41834 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-07-01 | 2026-07-14 | Flooring & Dado | 100 | 0 |  | 2026-07-24 |  | 2026-08-07 |  | Tower A | Super Structure | L55 | Finishes | Flooring & Dado
42915 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-08-07 | 2026-08-11 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-07-24 |  | 2026-07-28 |  | Tower A | Super Structure | L46 | MEP | FPS 2nd Fix - MEP & Finishes
42916 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-08-07 | 2026-08-11 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-07-24 |  | 2026-07-28 |  | Tower A | Super Structure | L46 | MEP | Electrical 2nd Fix - MEP & Finishes
42933 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-08-07 | 2026-08-11 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-07-24 |  | 2026-07-28 |  | Tower A | Super Structure | L47 | MEP | FPS 2nd Fix - MEP & Finishes
42934 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-08-07 | 2026-08-11 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-07-24 |  | 2026-07-28 |  | Tower A | Super Structure | L47 | MEP | Electrical 2nd Fix - MEP & Finishes
42951 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-08-07 | 2026-08-11 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-07-24 |  | 2026-07-28 |  | Tower A | Super Structure | L48 | MEP | FPS 2nd Fix - MEP & Finishes
42952 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-08-07 | 2026-08-11 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-07-24 |  | 2026-07-28 |  | Tower A | Super Structure | L48 | MEP | Electrical 2nd Fix - MEP & Finishes
42967 |  | Not Committed |  | 2026-08-07 | 2026-09-05 | MEP final fix & Finishes | 100 | 0 |  | 2026-07-24 |  | 2026-08-20
42968 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-08-07 | 2026-08-13 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-07-24 |  | 2026-07-30 |  | Tower A | Super Structure | L49 | Finishes | Door & Window Fixing
42985 |  | Not Committed |  | 2026-08-07 | 2026-08-29 | MEP final fix & Finishes | 100 | 0 |  | 2026-07-24 |  | 2026-08-11
42986 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-08-07 | 2026-08-13 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-07-24 |  | 2026-07-30 |  | Tower A | Super Structure | L50 | Finishes | Door & Window Fixing
43003 |  | Not Committed |  | 2026-08-07 | 2026-09-05 | MEP final fix & Finishes | 100 | 0 |  | 2026-07-24 |  | 2026-08-20
43004 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-08-07 | 2026-08-13 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-07-24 |  | 2026-07-30 |  | Tower A | Super Structure | L51 | Finishes | Door & Window Fixing
43272 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-06-30 | 2026-07-17 | Flooring & Dado works | 100 | 0 |  | 2026-07-24 |  | 2026-08-13 |  | Tower A | Super Structure | L66 | Finishes | Flooring & Dado
45476 | Tower B - Super Structure - Finishes & MEP - L17 to L18 | Not Ready | Partition Wall-Blockwork | 2026-05-04 | 2026-05-08 | Staircase Area | 100 | 0 |  | 2026-07-24 |  | 2026-07-31 |  | Tower B | Super Structure | L17
48053 | Club House - Super structure - CH02 to CH03 | Not Ready |  | 2026-04-01 | 2026-04-17 | Slab_CH | 100 | 0 |  | 2026-07-24 |  | 2026-08-13 |  | Club House | Super Structure | CH02
48095 |  | Not Committed |  | 2026-04-01 | 2026-08-28 | CHW Plant Room | 100 | 0 |  | 2026-07-24 |  | 2026-12-21
48096 |  | Not Ready |  | 2026-04-01 | 2026-06-11 | Low side | 100 | 0 |  | 2026-07-24 |  | 2026-10-10
9411 | T-15-Staircase 1 | Not Ready |  | 2026-07-31 | 2026-08-11 | 02F-01F | 100 | 0 |  | 2026-07-25 |  | 2026-08-03
9425 | T-15-Staircase 2 | Not Ready |  | 2026-07-31 | 2026-08-11 | 03F-02F | 100 | 0 |  | 2026-07-25 |  | 2026-08-03
12011 | T-18-Staircase 1 | Not Ready |  | 2026-10-03 | 2026-10-14 | 02F-01F | 100 | 0 |  | 2026-07-25 |  | 2026-08-05
12025 | T-18-Staircase 2 | Not Ready |  | 2026-10-03 | 2026-10-14 | 03F-02F | 100 | 0 |  | 2026-07-25 |  | 2026-08-05
41862 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-07-02 | 2026-07-04 | FAPA Cabling | 100 | 0 |  | 2026-07-25 |  | 2026-07-29 |  | Tower A | Super Structure | L57
42811 | Tower A - Super Structure - Finishes & MEP - L40 to L41 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-08-08 | 2026-08-12 | Painting Works | 100 | 0 |  | 2026-07-25 |  | 2026-07-29 |  | Tower A | Super Structure | L40 | Finishes | Painting Works
42829 | Tower A - Super Structure - Finishes & MEP - L41 to L42 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-08-08 | 2026-08-12 | Painting Works | 100 | 0 |  | 2026-07-25 |  | 2026-07-29 |  | Tower A | Super Structure | L41 | Finishes | Painting Works
42847 | Tower A - Super Structure - Finishes & MEP - L42 to L43 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-08-08 | 2026-08-12 | Painting Works | 100 | 0 |  | 2026-07-25 |  | 2026-07-29 |  | Tower A | Super Structure | L42 | Finishes | Painting Works
44228 |  | Not Committed |  | 2026-07-01 | 2026-11-09 | Hoist Corridor Finishes | 100 | 0 |  | 2026-07-25 |  | 2026-11-18
44229 | Tower A - Super Structure - Finishes & MEP - L7 to L15 | Not Ready | Hoist Corridor Finishes | 2026-07-01 | 2026-08-29 | L7-15 | 100 | 0 |  | 2026-07-25 |  | 2026-09-26 |  | Tower A | Super Structure | L7
44229 | Tower A - Super Structure - Finishes & MEP - L7 to L15 | Not Ready | Hoist Corridor Finishes | 2026-07-01 | 2026-08-29 | L7-15 | 100 | 0 |  | 2026-07-25 |  | 2026-09-26 |  | Tower A | Super Structure | L7
46805 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-05-12 | 2026-05-22 | Cement Plastering in wet areas | 100 | 0 |  | 2026-07-25 |  | 2026-08-08 |  | Tower B | Super Structure | L15
8887 | T-14-Staircase 1 | Not Ready |  | 2026-06-20 | 2026-07-01 | 06F-05F | 100 | 0 |  | 2026-07-26 |  | 2026-08-07
8901 | T-14-Staircase 2 | Not Ready |  | 2026-06-20 | 2026-07-01 | 07F-06F | 100 | 0 |  | 2026-07-26 |  | 2026-08-07
9392 | T-15-Lift Lobby | Not Ready |  | 2026-08-05 | 2026-08-22 | 05F | 100 | 0 |  | 2026-07-27 |  | 2026-08-12
9909 | T-16-Lift Lobby | Not Ready |  | 2026-08-13 | 2026-08-31 | 08F | 100 | 0 |  | 2026-07-27 |  | 2026-08-12
10468 | T-21-Staircase 2 | Not Ready |  | 2026-08-16 | 2026-08-27 | GF-BF | 100 | 0 |  | 2026-07-27 |  | 2026-08-06
9632 | T-16-1st Floor Common Area | Not Ready | Door-Shaft | 2026-08-08 | 2026-08-22 | Door-Shaft | 100 | 0 |  | 2026-07-28 |  | 2026-08-10
9660 | T-16-2nd Floor Common Area | Not Ready | 1st Coat Painting | 2026-08-07 | 2026-08-29 | 1st Coat Painting | 100 | 0 |  | 2026-07-28 |  | 2026-08-18
11461 | T-19-Lift | Not Ready | OTS Covers | 2026-08-21 | 2026-09-23 | OTS Covers | 100 | 0 |  | 2026-07-28 |  | 2026-08-30
39268 | Retail - Sub structure - B1 to GF | Not Ready | RCC Works - Slab | 2026-02-02 | 2026-02-20 | Slab_NTA | 100 | 0 |  | 2026-07-28 |  | 2026-08-17 |  | Retail | Sub Structure | B1 | RCC Sub Structure | RCC Works - Slab
39268 | Retail - Sub structure - B1 to GF | Not Ready | RCC Works - Slab | 2026-02-02 | 2026-02-20 | Slab_NTA | 100 | 0 |  | 2026-07-28 |  | 2026-08-17 |  | Retail | Sub Structure | B1
41804 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-07-03 | 2026-07-07 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-07-28 |  | 2026-07-31 |  | Tower A | Super Structure | L53 | MEP | FPS 2nd Fix - MEP & Finishes
41805 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-07-03 | 2026-07-09 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-07-28 |  | 2026-08-04 |  | Tower A | Super Structure | L53 | MEP | Electrical 2nd Fix - MEP & Finishes
41806 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-07-03 | 2026-07-11 | FAPA Device Fixing | 100 | 0 |  | 2026-07-28 |  | 2026-08-06 |  | Tower A | Super Structure | L53
41806 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-07-03 | 2026-07-11 | FAPA Device Fixing | 100 | 0 |  | 2026-07-28 |  | 2026-08-06 |  | Tower A | Super Structure | L53
41806 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-07-03 | 2026-07-11 | FAPA Device Fixing | 100 | 0 |  | 2026-07-28 |  | 2026-08-06 |  | Tower A | Super Structure | L53
41806 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-07-03 | 2026-07-11 | FAPA Device Fixing | 100 | 0 |  | 2026-07-28 |  | 2026-08-06 |  | Tower A | Super Structure | L53
41807 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-07-03 | 2026-07-07 | HVAC Grill Fixing | 100 | 0 |  | 2026-07-28 |  | 2026-07-31 |  | Tower A | Super Structure | L53 | MEP | HVAC Grill Fixing
44154 | Tower A - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2026-07-02 | 2026-07-08 | Accessories & Alignment | 100 | 0 |  | 2026-07-28 |  | 2026-08-05 |  | Tower A | Super Structure | L15 | Façade | Façade Works
44154 | Tower A - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2026-07-02 | 2026-07-08 | Accessories & Alignment | 100 | 0 |  | 2026-07-28 |  | 2026-08-05 |  | Tower A | Super Structure | L15
44157 | Tower A - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2026-07-02 | 2026-07-09 | Glass Assembly Installation | 100 | 0 |  | 2026-07-28 |  | 2026-08-06 |  | Tower A | Super Structure | L25
44158 | Tower A - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2026-07-02 | 2026-07-08 | ACP Sheet & Insulation fixing | 100 | 0 |  | 2026-07-28 |  | 2026-08-05 |  | Tower A | Super Structure | L25
44159 | Tower A - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2026-07-02 | 2026-07-08 | Fixing of Louvers | 100 | 0 |  | 2026-07-28 |  | 2026-08-05 |  | Tower A | Super Structure | L25 | Façade | Façade Works
44159 | Tower A - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2026-07-02 | 2026-07-08 | Fixing of Louvers | 100 | 0 |  | 2026-07-28 |  | 2026-08-05 |  | Tower A | Super Structure | L25
44161 |  | Not Committed |  | 2026-07-02 | 2026-08-01 | L35-45 | 100 | 0 |  | 2026-07-28 |  | 2026-08-25
44161 |  | Not Committed |  | 2026-07-02 | 2026-08-01 | L35-45 | 100 | 0 |  | 2026-07-28 |  | 2026-08-25
44162 | Tower A - Super Structure - Finishes & MEP - L35 to L45 | Not Ready |  | 2026-07-02 | 2026-07-09 | Al. Frame Section Installation | 100 | 0 |  | 2026-07-28 |  | 2026-08-06 |  | Tower A | Super Structure | L35
44197 | Tower A - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2026-07-02 | 2026-07-08 | Accessories & Alignment | 100 | 0 |  | 2026-07-28 |  | 2026-08-05 |  | Tower A | Super Structure | L15 | Façade | Façade Works
44197 | Tower A - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2026-07-02 | 2026-07-08 | Accessories & Alignment | 100 | 0 |  | 2026-07-28 |  | 2026-08-05 |  | Tower A | Super Structure | L15
44200 | Tower A - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2026-07-02 | 2026-07-09 | Glass Assembly Installation | 100 | 0 |  | 2026-07-28 |  | 2026-08-06 |  | Tower A | Super Structure | L25
44201 | Tower A - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2026-07-02 | 2026-07-08 | ACP Sheet & Insulation fixing | 100 | 0 |  | 2026-07-28 |  | 2026-08-05 |  | Tower A | Super Structure | L25
44202 | Tower A - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2026-07-02 | 2026-07-08 | Fixing of Louvers | 100 | 0 |  | 2026-07-28 |  | 2026-08-05 |  | Tower A | Super Structure | L25 | Façade | Façade Works
44202 | Tower A - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2026-07-02 | 2026-07-08 | Fixing of Louvers | 100 | 0 |  | 2026-07-28 |  | 2026-08-05 |  | Tower A | Super Structure | L25
44204 |  | Not Committed |  | 2026-07-02 | 2026-08-01 | L35-45 | 100 | 0 |  | 2026-07-28 |  | 2026-08-25
44204 |  | Not Committed |  | 2026-07-02 | 2026-08-01 | L35-45 | 100 | 0 |  | 2026-07-28 |  | 2026-08-25
44205 | Tower A - Super Structure - Finishes & MEP - L35 to L45 | Not Ready |  | 2026-07-02 | 2026-07-09 | Al. Frame Section Installation | 100 | 0 |  | 2026-07-28 |  | 2026-08-06 |  | Tower A | Super Structure | L35
45619 | Tower B - Super Structure - Finishes & MEP - L16 to L17 | Not Ready | Gypsum Plastering Works | 2026-05-09 | 2026-06-25 | L16-17 | 100 | 0 |  | 2026-07-28 |  | 2026-09-19 |  | Tower B | Super Structure | L16 | Finishes | Gypsum Plastering Works
45619 | Tower B - Super Structure - Finishes & MEP - L16 to L17 | Not Ready | Gypsum Plastering Works | 2026-05-09 | 2026-06-25 | L16-17 | 100 | 0 |  | 2026-07-28 |  | 2026-09-19 |  | Tower B | Super Structure | L16
45796 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2026-05-20 | 2026-06-06 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-07-28 |  | 2026-08-19 |  | Tower B | Sub Structure | B3
45796 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2026-05-20 | 2026-06-06 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-07-28 |  | 2026-08-19 |  | Tower B | Sub Structure | B3
45796 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Floor Area | Not Ready | Parking Mirror/ Signage Fixing - MEP & Finishes | 2026-05-20 | 2026-06-06 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-07-28 |  | 2026-08-19 |  | Tower B | Sub Structure | B3
45876 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-05-20 | 2026-05-28 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-07-28 |  | 2026-08-06 |  | Tower B | Super Structure | GF | MEP | Electrical 2nd Fix - MEP & Finishes
10973 | T-20-Staircase 1 | Not Ready |  | 2026-08-17 | 2026-08-27 | GF-BF | 100 | 0 |  | 2026-07-29 |  | 2026-08-09
10987 | T-20-Staircase 2 | Not Ready |  | 2026-08-17 | 2026-08-27 | 01F-GF | 100 | 0 |  | 2026-07-29 |  | 2026-08-09
11194 | T-19-1st Floor Common Area | Not Ready | 1st Coat Painting | 2026-08-07 | 2026-08-30 | 1st Coat Painting | 100 | 0 |  | 2026-07-29 |  | 2026-08-19
11470 | T-19-Lift Lobby | Not Ready |  | 2026-08-08 | 2026-08-26 | 07F | 100 | 0 |  | 2026-07-29 |  | 2026-08-12
41793 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-07-04 | 2026-07-10 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-07-29 |  | 2026-08-05 |  | Tower A | Super Structure | L52 | MEP | Electrical
41794 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-07-04 | 2026-07-10 | Final Painting | 100 | 0 |  | 2026-07-29 |  | 2026-08-05 |  | Tower A | Super Structure | L52 | Finishes | Final Painting
41794 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-07-04 | 2026-07-10 | Final Painting | 100 | 0 |  | 2026-07-29 |  | 2026-08-05 |  | Tower A | Super Structure | L52 | Finishes | Final Painting
41794 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-07-04 | 2026-07-10 | Final Painting | 100 | 0 |  | 2026-07-29 |  | 2026-08-05 |  | Tower A | Super Structure | L52 | Finishes | Final Painting
41863 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-07-04 | 2026-07-14 | HVAC Ducting | 100 | 0 |  | 2026-07-29 |  | 2026-08-07 |  | Tower A | Super Structure | L57 | MEP | HVAC Ducting
41876 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-07-04 | 2026-07-10 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-07-29 |  | 2026-08-05 |  | Tower A | Super Structure | L58 | MEP | FPS 1st Fix - MEP & Finishes
41877 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-07-04 | 2026-07-08 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-07-29 |  | 2026-08-01 |  | Tower A | Super Structure | L58 | MEP | Electrical 1st Fixes
42864 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-08-14 | 2026-08-19 | PHE Final Fixes | 100 | 0 |  | 2026-07-29 |  | 2026-07-31 |  | Tower A | Super Structure | L43
42882 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-08-14 | 2026-08-19 | PHE Final Fixes | 100 | 0 |  | 2026-07-29 |  | 2026-07-31 |  | Tower A | Super Structure | L44
42900 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-08-14 | 2026-08-19 | PHE Final Fixes | 100 | 0 |  | 2026-07-29 |  | 2026-07-31 |  | Tower A | Super Structure | L45
42917 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-08-14 | 2026-08-21 | False Ceiling | 100 | 0 |  | 2026-07-29 |  | 2026-08-04 |  | Tower A | Super Structure | L46 | Finishes | False Ceiling
42935 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-08-14 | 2026-08-21 | False Ceiling | 100 | 0 |  | 2026-07-29 |  | 2026-08-04 |  | Tower A | Super Structure | L47 | Finishes | False Ceiling
42953 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-08-14 | 2026-08-21 | False Ceiling | 100 | 0 |  | 2026-07-29 |  | 2026-08-04 |  | Tower A | Super Structure | L48 | Finishes | False Ceiling
44014 | Tower A - Super Structure - Finishes & MEP - L65 to L77 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-09-19 | 2026-10-03 | Staircase cabling | 100 | 0 |  | 2026-07-29 |  | 2026-08-12 |  | Tower A | Super Structure | L65
44276 |  | Not Ready |  | 2026-07-03 | 2026-12-14 | Statutory Approvals - OC_Zone 1 | 100 | 0 |  | 2026-07-29 |  | 2027-06-28
44277 |  | Not Ready |  | 2026-07-03 | 2026-07-29 | Lift Commissioning with Permanent Power | 100 | 0 |  | 2026-07-29 |  | 2026-08-26
44605 |  | Not Ready | MEP fix & Finishes | 2026-08-14 | 2026-08-21 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-07-29 |  | 2026-08-04
44605 |  | Not Ready | MEP fix & Finishes | 2026-08-14 | 2026-08-21 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-07-29 |  | 2026-08-04
44605 |  | Not Ready | MEP fix & Finishes | 2026-08-14 | 2026-08-21 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2026-07-29 |  | 2026-08-04
45595 | Tower B - Super Structure - Finishes & MEP | Not Ready | MEP Shaft Masonry | 2026-05-21 | 2026-06-13 | L7-L15 | 100 | 0 |  | 2026-07-29 |  | 2026-08-26 |  | Tower B | Super Structure
45595 | Tower B - Super Structure - Finishes & MEP | Not Ready | MEP Shaft Masonry | 2026-05-21 | 2026-06-13 | L7-L15 | 100 | 0 |  | 2026-07-29 |  | 2026-08-26 |  | Tower B | Super Structure
9869 | T-16-11th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-08-24 | 2026-09-26 | 2nd Coat Painting | 100 | 0 |  | 2026-07-30 |  | 2026-09-01
9887 | T-16-11th Floor Flat Area | Not Ready | 2nd Coat Painting | 2026-08-24 | 2026-10-29 | 2nd Coat Painting | 100 | 0 |  | 2026-07-30 |  | 2026-10-05
11513 | T-19- Elevation-C | Not Ready |  | 2026-08-14 | 2026-11-07 | Elevation-C | 100 | 0 |  | 2026-07-30 |  | 2026-10-19
44255 |  | Not Ready | Interior Fit-out | 2026-08-20 | 2026-09-28 | Ceiling Works | 100 | 0 |  | 2026-07-30 |  | 2026-09-07
44257 |  | Not Ready |  | 2026-06-29 | 2026-12-14 | External Development | 100 | 0 |  | 2026-07-30 |  | 2027-06-25
44257 |  | Not Ready |  | 2026-06-29 | 2026-12-14 | External Development | 100 | 0 |  | 2026-07-30 |  | 2027-06-25
44258 |  | Not Ready | External Development | 2026-06-29 | 2026-09-16 | Above Terrace MEP | 100 | 0 |  | 2026-07-30 |  | 2026-10-21
44260 |  | Not Ready | External Development | 2026-06-29 | 2026-09-16 | Inlet Line for Fire Tanks | 100 | 0 |  | 2026-07-30 |  | 2026-10-21
44560 |  | Not Committed |  | 2025-12-23 | 2026-04-27 | GF to P1 | 100 | 0 |  | 2026-07-30 |  | 2026-12-08
44560 |  | Not Committed |  | 2025-12-23 | 2026-04-27 | GF to P1 | 100 | 0 |  | 2026-07-30 |  | 2026-12-08
44560 |  | Not Committed |  | 2025-12-23 | 2026-04-27 | GF to P1 | 100 | 0 |  | 2026-07-30 |  | 2026-12-08
44561 | NTA_Zone 2 - Super Structure - GF to P1 | Not Ready | Finishes (Lobby & Floor Area) | 2025-12-23 | 2026-02-14 | IPS Flooring in STP, Sub-Stn & DG Area | 100 | 0 |  | 2026-07-30 |  | 2026-09-26 |  | NTA_Zone 2 | Super Structure | GF
45316 |  | Not Ready |  | 2026-05-08 | 2026-05-19 | L22-23 | 100 | 0 |  | 2026-07-30 |  | 2026-08-19
45316 |  | Not Ready |  | 2026-05-08 | 2026-05-19 | L22-23 | 100 | 0 |  | 2026-07-30 |  | 2026-08-19 |  |  |  |  | Finishes | Gypsum Plastering Works
45317 | Tower B - Super Structure - Core & Outer Slab L22-23 | Not Ready | RCC Works - Vertical | 2026-05-08 | 2026-05-16 | Outer Columns_TA | 100 | 0 |  | 2026-07-30 |  | 2026-08-13 |  | Tower B | Super Structure | L22 | RCC Sub Structure | RCC Works - Vertical
45481 |  | Not Committed |  | 2026-05-08 | 2026-06-09 | L19-20 | 100 | 0 |  | 2026-07-30 |  | 2026-09-04
45481 |  | Not Committed |  | 2026-05-08 | 2026-06-09 | L19-20 | 100 | 0 |  | 2026-07-30 |  | 2026-09-04 |  |  |  |  | Finishes | Gypsum Plastering Works
45482 | Tower B - Super Structure - Finishes & MEP - L19 to L20 | Not Ready | Partition Wall-Blockwork | 2026-05-08 | 2026-05-25 | De-shuttering & Area clearance | 100 | 0 |  | 2026-07-30 |  | 2026-08-21 |  | Tower B | Super Structure | L19
10475 |  | Not Ready | De-Snagging & Handing Over | 2026-09-16 | 2026-12-26 | De-Snagging & Handing Over | 100 | 0 |  | 2026-07-31 |  | 2026-11-10
41808 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-07-07 | 2026-07-10 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-07-31 |  | 2026-08-05 |  | Tower A | Super Structure | L53
41835 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-07-07 | 2026-07-16 | False Ceiling | 100 | 0 |  | 2026-07-31 |  | 2026-08-11 |  | Tower A | Super Structure | L55 | Finishes | False Ceiling
41850 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-07-07 | 2026-07-21 | Flooring & Dado | 100 | 0 |  | 2026-07-31 |  | 2026-08-14 |  | Tower A | Super Structure | L56 | Finishes | Flooring & Dado
42969 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-08-21 | 2026-08-24 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-07-31 |  | 2026-08-04 |  | Tower A | Super Structure | L49 | MEP | FPS 2nd Fix - MEP & Finishes
42970 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-08-21 | 2026-08-24 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-07-31 |  | 2026-08-04 |  | Tower A | Super Structure | L49 | MEP | Electrical 2nd Fix - MEP & Finishes
42987 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-08-21 | 2026-08-24 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-07-31 |  | 2026-08-04 |  | Tower A | Super Structure | L50 | MEP | FPS 2nd Fix - MEP & Finishes
42988 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-08-21 | 2026-08-24 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-07-31 |  | 2026-08-04 |  | Tower A | Super Structure | L50 | MEP | Electrical 2nd Fix - MEP & Finishes
43005 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-08-21 | 2026-08-24 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-07-31 |  | 2026-08-04 |  | Tower A | Super Structure | L51 | MEP | FPS 2nd Fix - MEP & Finishes
43006 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-08-21 | 2026-08-24 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-07-31 |  | 2026-08-04 |  | Tower A | Super Structure | L51 | MEP | Electrical 2nd Fix - MEP & Finishes
43021 |  | Not Committed |  | 2026-08-21 | 2026-09-12 | MEP final fix & Finishes | 100 | 0 |  | 2026-07-31 |  | 2026-08-26
43022 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-08-21 | 2026-08-26 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-07-31 |  | 2026-08-06 |  | Tower A | Super Structure | L52 | Finishes | Door & Window Fixing
43039 |  | Not Committed |  | 2026-08-21 | 2026-09-12 | MEP final fix & Finishes | 100 | 0 |  | 2026-07-31 |  | 2026-08-26
43040 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-08-21 | 2026-08-26 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-07-31 |  | 2026-08-06 |  | Tower A | Super Structure | L53 | Finishes | Door & Window Fixing
43057 |  | Not Committed |  | 2026-08-21 | 2026-09-12 | MEP final fix & Finishes | 100 | 0 |  | 2026-07-31 |  | 2026-08-26
43058 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-08-21 | 2026-08-26 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-07-31 |  | 2026-08-06 |  | Tower A | Super Structure | L54 | Finishes | Door & Window Fixing
43290 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-07-06 | 2026-07-24 | Flooring & Dado works | 100 | 0 |  | 2026-07-31 |  | 2026-08-21 |  | Tower A | Super Structure | L67 | Finishes | Flooring & Dado
46835 |  | Not Committed |  | 2026-05-09 | 2027-06-09 | L17-18 | 100 | 0 |  | 2026-07-31 |  | 2027-07-23
46835 |  | Not Committed |  | 2026-05-09 | 2027-06-09 | L17-18 | 100 | 0 |  | 2026-07-31 |  | 2027-07-23 |  |  |  |  | Finishes | Gypsum Plastering Works
46836 |  | Not Committed |  | 2026-05-09 | 2026-06-16 | MEP 1st Fixes | 100 | 0 |  | 2026-07-31 |  | 2026-09-11
46837 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-05-09 | 2026-05-16 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-07-31 |  | 2026-08-11 |  | Tower B | Super Structure | L17 | MEP | FPS 1st Fix - MEP & Finishes
46838 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-05-09 | 2026-05-14 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-07-31 |  | 2026-08-07 |  | Tower B | Super Structure | L17 | MEP | Electrical 1st Fixes
46839 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-05-09 | 2026-05-16 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-07-31 |  | 2026-08-11 |  | Tower B | Super Structure | L17
48101 |  | Not Committed |  | 2026-05-20 | 2026-12-29 | Ext. Development, T/C & Handover | 100 | 0 |  | 2026-07-31 |  | 2027-03-29
48104 |  | Not Committed |  | 2026-05-20 | 2026-10-19 | Swimming Pool Finishes | 100 | 0 |  | 2026-07-31 |  | 2026-12-28
48226 | Club House - Super structure - CH01 to CH02 | Not Ready |  | 2026-04-07 | 2026-05-12 | CH01-CH02 | 100 | 0 |  | 2026-07-31 |  | 2026-09-08 |  | Club House | Super Structure | CH01
41878 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-07-08 | 2026-07-10 | FAPA Cabling | 100 | 0 |  | 2026-08-01 |  | 2026-08-05 |  | Tower A | Super Structure | L58
42865 | Tower A - Super Structure - Finishes & MEP - L43 to L44 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-08-22 | 2026-08-25 | Painting Works | 100 | 0 |  | 2026-08-01 |  | 2026-08-05 |  | Tower A | Super Structure | L43 | Finishes | Painting Works
42883 | Tower A - Super Structure - Finishes & MEP - L44 to L45 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-08-22 | 2026-08-25 | Painting Works | 100 | 0 |  | 2026-08-01 |  | 2026-08-05 |  | Tower A | Super Structure | L44 | Finishes | Painting Works
42901 | Tower A - Super Structure - Finishes & MEP - L45 to L46 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-08-22 | 2026-08-25 | Painting Works | 100 | 0 |  | 2026-08-01 |  | 2026-08-05 |  | Tower A | Super Structure | L45 | Finishes | Painting Works
45479 | Tower B - Super Structure - Finishes & MEP - L18 to L19 | Not Ready | Partition Wall-Blockwork | 2026-05-07 | 2026-05-14 | Partition Walls | 100 | 0 |  | 2026-08-01 |  | 2026-08-12 |  | Tower B | Super Structure | L18
9927 | T-16-Staircase 1 | Not Ready |  | 2026-08-13 | 2026-08-25 | 06F-05F | 100 | 0 |  | 2026-08-02 |  | 2026-08-14
9941 | T-16-Staircase 2 | Not Ready |  | 2026-08-13 | 2026-08-25 | 07F-06F | 100 | 0 |  | 2026-08-02 |  | 2026-08-14
11247 | T-19-3rd Floor Common Area | Not Ready | 2nd Coat Painting | 2026-08-19 | 2026-09-21 | 2nd Coat Painting | 100 | 0 |  | 2026-08-03 |  | 2026-09-05
9412 | T-15-Staircase 1 | Not Ready |  | 2026-08-11 | 2026-08-22 | 01F-GF | 100 | 0 |  | 2026-08-04 |  | 2026-08-17
9426 | T-15-Staircase 2 | Not Ready |  | 2026-08-11 | 2026-08-22 | 02F-01F | 100 | 0 |  | 2026-08-04 |  | 2026-08-17
41820 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-07-09 | 2026-07-14 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-08-04 |  | 2026-08-07 |  | Tower A | Super Structure | L54 | MEP | FPS 2nd Fix - MEP & Finishes
41821 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-07-09 | 2026-07-16 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-08-04 |  | 2026-08-11 |  | Tower A | Super Structure | L54 | MEP | Electrical 2nd Fix - MEP & Finishes
41822 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-07-09 | 2026-07-18 | FAPA Device Fixing | 100 | 0 |  | 2026-08-04 |  | 2026-08-13 |  | Tower A | Super Structure | L54
41822 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-07-09 | 2026-07-18 | FAPA Device Fixing | 100 | 0 |  | 2026-08-04 |  | 2026-08-13 |  | Tower A | Super Structure | L54
41822 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-07-09 | 2026-07-18 | FAPA Device Fixing | 100 | 0 |  | 2026-08-04 |  | 2026-08-13 |  | Tower A | Super Structure | L54
41822 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-07-09 | 2026-07-18 | FAPA Device Fixing | 100 | 0 |  | 2026-08-04 |  | 2026-08-13 |  | Tower A | Super Structure | L54
41823 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-07-09 | 2026-07-14 | HVAC Grill Fixing | 100 | 0 |  | 2026-08-04 |  | 2026-08-07 |  | Tower A | Super Structure | L54 | MEP | HVAC Grill Fixing
45877 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-05-26 | 2026-06-03 | FAPA Device Fixing | 100 | 0 |  | 2026-08-04 |  | 2026-08-13 |  | Tower B | Super Structure | GF
45877 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-05-26 | 2026-06-03 | FAPA Device Fixing | 100 | 0 |  | 2026-08-04 |  | 2026-08-13 |  | Tower B | Super Structure | GF
45877 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-05-26 | 2026-06-03 | FAPA Device Fixing | 100 | 0 |  | 2026-08-04 |  | 2026-08-13 |  | Tower B | Super Structure | GF
45877 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-05-26 | 2026-06-03 | FAPA Device Fixing | 100 | 0 |  | 2026-08-04 |  | 2026-08-13 |  | Tower B | Super Structure | GF
47689 |  | Not Ready |  | 2026-08-21 | 2026-08-28 | Section 11_lift 2 | 100 | 0 |  | 2026-08-04 |  | 2026-08-12
47689 |  | Not Ready |  | 2026-08-21 | 2026-08-28 | Section 11_lift 2 | 100 | 0 |  | 2026-08-04 |  | 2026-08-12 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
48231 |  | Not Committed |  | 2026-02-20 | 2026-05-15 | B3 to B2 | 100 | 0 |  | 2026-08-04 |  | 2026-11-02
48231 |  | Not Committed |  | 2026-02-20 | 2026-05-15 | B3 to B2 | 100 | 0 |  | 2026-08-04 |  | 2026-11-02
48231 |  | Not Committed |  | 2026-02-20 | 2026-05-15 | B3 to B2 | 100 | 0 |  | 2026-08-04 |  | 2026-11-02
48232 | Retail & Clubhouse - Sub structure - B3 to B2 | Not Ready |  | 2026-02-20 | 2026-03-28 | VDF Flooring | 100 | 0 |  | 2026-08-04 |  | 2026-09-11 |  | Club House | Sub Structure | B3
48232 | Retail & Clubhouse - Sub structure - B3 to B2 | Not Ready |  | 2026-02-20 | 2026-03-28 | VDF Flooring | 100 | 0 |  | 2026-08-04 |  | 2026-09-11 |  | Club House | Sub Structure | B3
11455 | T-19-11th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-08-30 | 2026-10-03 | 2nd Coat Painting | 100 | 0 |  | 2026-08-05 |  | 2026-09-05
41809 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-07-10 | 2026-07-17 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-08-05 |  | 2026-08-12 |  | Tower A | Super Structure | L53 | MEP | Electrical
41810 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-07-10 | 2026-07-17 | Final Painting | 100 | 0 |  | 2026-08-05 |  | 2026-08-12 |  | Tower A | Super Structure | L53 | Finishes | Final Painting
41810 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-07-10 | 2026-07-17 | Final Painting | 100 | 0 |  | 2026-08-05 |  | 2026-08-12 |  | Tower A | Super Structure | L53 | Finishes | Final Painting
41810 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-07-10 | 2026-07-17 | Final Painting | 100 | 0 |  | 2026-08-05 |  | 2026-08-12 |  | Tower A | Super Structure | L53 | Finishes | Final Painting
41879 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-07-10 | 2026-07-21 | HVAC Ducting | 100 | 0 |  | 2026-08-05 |  | 2026-08-14 |  | Tower A | Super Structure | L58 | MEP | HVAC Ducting
41892 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-07-10 | 2026-07-17 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-08-05 |  | 2026-08-12 |  | Tower A | Super Structure | L59 | MEP | FPS 1st Fix - MEP & Finishes
41893 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-07-10 | 2026-07-15 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-08-05 |  | 2026-08-08 |  | Tower A | Super Structure | L59 | MEP | Electrical 1st Fixes
42918 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-08-25 | 2026-08-27 | PHE Final Fixes | 100 | 0 |  | 2026-08-05 |  | 2026-08-07 |  | Tower A | Super Structure | L46
42936 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-08-25 | 2026-08-27 | PHE Final Fixes | 100 | 0 |  | 2026-08-05 |  | 2026-08-07 |  | Tower A | Super Structure | L47
42954 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-08-25 | 2026-08-27 | PHE Final Fixes | 100 | 0 |  | 2026-08-05 |  | 2026-08-07 |  | Tower A | Super Structure | L48
42971 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-08-25 | 2026-08-29 | False Ceiling | 100 | 0 |  | 2026-08-05 |  | 2026-08-11 |  | Tower A | Super Structure | L49 | Finishes | False Ceiling
42989 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-08-25 | 2026-08-25 | False Ceiling | 100 | 0 |  | 2026-08-05 |  | 2026-08-05 |  | Tower A | Super Structure | L50 | Finishes | False Ceiling
43007 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-08-25 | 2026-08-29 | False Ceiling | 100 | 0 |  | 2026-08-05 |  | 2026-08-11 |  | Tower A | Super Structure | L51 | Finishes | False Ceiling
44230 | Tower A - Super Structure - Finishes & MEP - L15 to L25 | Not Ready | Hoist Corridor Finishes | 2026-07-09 | 2026-09-07 | L15-25 | 100 | 0 |  | 2026-08-05 |  | 2026-10-07 |  | Tower A | Super Structure | L15
44230 | Tower A - Super Structure - Finishes & MEP - L15 to L25 | Not Ready | Hoist Corridor Finishes | 2026-07-09 | 2026-09-07 | L15-25 | 100 | 0 |  | 2026-08-05 |  | 2026-10-07 |  | Tower A | Super Structure | L15
8595 | T-14-2nd Floor Common Area | Not Ready | 2nd Coat Painting | 2026-07-06 | 2026-08-07 | 2nd Coat Painting | 100 | 0 |  | 2026-08-06 |  | 2026-09-06
8855 | T-14-12th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-07-17 | 2026-08-19 | 2nd Coat Painting | 100 | 0 |  | 2026-08-06 |  | 2026-09-09
10435 | T-21-Lift Lobby | Not Ready |  | 2026-09-07 | 2026-09-23 | 02F | 100 | 0 |  | 2026-08-06 |  | 2026-08-25
11489 | T-19-Staircase 1 | Not Ready |  | 2026-08-14 | 2026-08-26 | 04F-03F | 100 | 0 |  | 2026-08-06 |  | 2026-08-17
11503 | T-19-Staircase 2 | Not Ready |  | 2026-08-14 | 2026-08-26 | 05F-04F | 100 | 0 |  | 2026-08-06 |  | 2026-08-17
12012 | T-18-Staircase 1 | Not Ready |  | 2026-10-14 | 2026-10-25 | 01F-GF | 100 | 0 |  | 2026-08-06 |  | 2026-08-19
12026 | T-18-Staircase 2 | Not Ready |  | 2026-10-14 | 2026-10-25 | 02F-01F | 100 | 0 |  | 2026-08-06 |  | 2026-08-19
42990 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-08-26 | 2026-08-26 | PHE Final Fixes | 100 | 0 |  | 2026-08-06 |  | 2026-08-06 |  | Tower A | Super Structure | L50
44160 | Tower A - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2026-07-10 | 2026-07-17 | Accessories & Alignment | 100 | 0 |  | 2026-08-06 |  | 2026-08-14 |  | Tower A | Super Structure | L25 | Façade | Façade Works
44160 | Tower A - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2026-07-10 | 2026-07-17 | Accessories & Alignment | 100 | 0 |  | 2026-08-06 |  | 2026-08-14 |  | Tower A | Super Structure | L25
44163 | Tower A - Super Structure - Finishes & MEP - L35 to L45 | Not Ready |  | 2026-07-10 | 2026-07-18 | Glass Assembly Installation | 100 | 0 |  | 2026-08-06 |  | 2026-08-18 |  | Tower A | Super Structure | L35
44164 | Tower A - Super Structure - Finishes & MEP - L35 to L45 | Not Ready |  | 2026-07-10 | 2026-07-17 | ACP Sheet & Insulation fixing | 100 | 0 |  | 2026-08-06 |  | 2026-08-14 |  | Tower A | Super Structure | L35
44165 | Tower A - Super Structure - Finishes & MEP - L35 to L45 | Not Ready |  | 2026-07-10 | 2026-07-17 | Fixing of Louvers | 100 | 0 |  | 2026-08-06 |  | 2026-08-14 |  | Tower A | Super Structure | L35 | Façade | Façade Works
44165 | Tower A - Super Structure - Finishes & MEP - L35 to L45 | Not Ready |  | 2026-07-10 | 2026-07-17 | Fixing of Louvers | 100 | 0 |  | 2026-08-06 |  | 2026-08-14 |  | Tower A | Super Structure | L35
44167 |  | Not Committed |  | 2026-07-10 | 2026-08-21 | L45-55 | 100 | 0 |  | 2026-08-06 |  | 2026-09-02
44167 |  | Not Committed |  | 2026-07-10 | 2026-08-21 | L45-55 | 100 | 0 |  | 2026-08-06 |  | 2026-09-02
44168 | Tower A - Super Structure - Finishes & MEP - L45 to L55 | Not Ready |  | 2026-07-10 | 2026-07-18 | Al. Frame Section Installation | 100 | 0 |  | 2026-08-06 |  | 2026-08-18 |  | Tower A | Super Structure | L45
44203 | Tower A - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2026-07-10 | 2026-07-17 | Accessories & Alignment | 100 | 0 |  | 2026-08-06 |  | 2026-08-14 |  | Tower A | Super Structure | L25 | Façade | Façade Works
44203 | Tower A - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2026-07-10 | 2026-07-17 | Accessories & Alignment | 100 | 0 |  | 2026-08-06 |  | 2026-08-14 |  | Tower A | Super Structure | L25
44206 | Tower A - Super Structure - Finishes & MEP - L35 to L45 | Not Ready |  | 2026-07-10 | 2026-07-18 | Glass Assembly Installation | 100 | 0 |  | 2026-08-06 |  | 2026-08-18 |  | Tower A | Super Structure | L35
44207 | Tower A - Super Structure - Finishes & MEP - L35 to L45 | Not Ready |  | 2026-07-10 | 2026-07-17 | ACP Sheet & Insulation fixing | 100 | 0 |  | 2026-08-06 |  | 2026-08-14 |  | Tower A | Super Structure | L35
44208 | Tower A - Super Structure - Finishes & MEP - L35 to L45 | Not Ready |  | 2026-07-10 | 2026-07-17 | Fixing of Louvers | 100 | 0 |  | 2026-08-06 |  | 2026-08-14 |  | Tower A | Super Structure | L35 | Façade | Façade Works
44208 | Tower A - Super Structure - Finishes & MEP - L35 to L45 | Not Ready |  | 2026-07-10 | 2026-07-17 | Fixing of Louvers | 100 | 0 |  | 2026-08-06 |  | 2026-08-14 |  | Tower A | Super Structure | L35
44210 |  | Not Committed |  | 2026-07-10 | 2026-08-21 | L45-55 | 100 | 0 |  | 2026-08-06 |  | 2026-09-02
44210 |  | Not Committed |  | 2026-07-10 | 2026-08-21 | L45-55 | 100 | 0 |  | 2026-08-06 |  | 2026-09-02
44211 | Tower A - Super Structure - Finishes & MEP - L45 to L55 | Not Ready |  | 2026-07-10 | 2026-07-18 | Al. Frame Section Installation | 100 | 0 |  | 2026-08-06 |  | 2026-08-18 |  | Tower A | Super Structure | L45
9141 | T-15-2nd Floor Common Area | Not Ready | 2nd Coat Painting | 2026-08-04 | 2026-09-07 | 2nd Coat Painting | 100 | 0 |  | 2026-08-07 |  | 2026-09-10
41824 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-07-16 | 2026-07-21 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-08-07 |  | 2026-08-12 |  | Tower A | Super Structure | L54
41851 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-07-16 | 2026-07-25 | False Ceiling | 100 | 0 |  | 2026-08-07 |  | 2026-08-19 |  | Tower A | Super Structure | L56 | Finishes | False Ceiling
41866 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-07-16 | 2026-07-30 | Flooring & Dado | 100 | 0 |  | 2026-08-07 |  | 2026-08-22 |  | Tower A | Super Structure | L57 | Finishes | Flooring & Dado
42991 | Tower A - Super Structure - Finishes & MEP - L50 to L51 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-08-27 | 2026-08-29 | Painting Works | 100 | 0 |  | 2026-08-07 |  | 2026-08-11 |  | Tower A | Super Structure | L50 | Finishes | Painting Works
43023 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-08-27 | 2026-08-29 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-08-07 |  | 2026-08-11 |  | Tower A | Super Structure | L52 | MEP | FPS 2nd Fix - MEP & Finishes
43024 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-08-27 | 2026-08-29 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-08-07 |  | 2026-08-11 |  | Tower A | Super Structure | L52 | MEP | Electrical 2nd Fix - MEP & Finishes
43041 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-08-27 | 2026-08-29 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-08-07 |  | 2026-08-11 |  | Tower A | Super Structure | L53 | MEP | FPS 2nd Fix - MEP & Finishes
43042 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-08-27 | 2026-08-29 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-08-07 |  | 2026-08-11 |  | Tower A | Super Structure | L53 | MEP | Electrical 2nd Fix - MEP & Finishes
43059 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-08-27 | 2026-08-29 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-08-07 |  | 2026-08-11 |  | Tower A | Super Structure | L54 | MEP | FPS 2nd Fix - MEP & Finishes
43060 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-08-27 | 2026-08-29 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-08-07 |  | 2026-08-11 |  | Tower A | Super Structure | L54 | MEP | Electrical 2nd Fix - MEP & Finishes
43075 |  | Not Committed |  | 2026-08-27 | 2026-09-21 | MEP final fix & Finishes | 100 | 0 |  | 2026-08-07 |  | 2026-09-01
43076 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-08-27 | 2026-09-01 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-08-07 |  | 2026-08-13 |  | Tower A | Super Structure | L55 | Finishes | Door & Window Fixing
43093 |  | Not Committed |  | 2026-08-27 | 2026-09-21 | MEP final fix & Finishes | 100 | 0 |  | 2026-08-07 |  | 2026-09-01
43094 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-08-27 | 2026-09-01 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-08-07 |  | 2026-08-13 |  | Tower A | Super Structure | L56 | Finishes | Door & Window Fixing
43111 |  | Not Committed |  | 2026-08-27 | 2026-09-21 | MEP final fix & Finishes | 100 | 0 |  | 2026-08-07 |  | 2026-09-01
43112 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-08-27 | 2026-09-01 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-08-07 |  | 2026-08-13 |  | Tower A | Super Structure | L57 | Finishes | Door & Window Fixing
43308 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-07-11 | 2026-07-31 | Flooring & Dado works | 100 | 0 |  | 2026-08-07 |  | 2026-08-27 |  | Tower A | Super Structure | L68 | Finishes | Flooring & Dado
45318 | Tower B - Super Structure - Core & Outer Slab L22-23 | Not Ready | RCC Works - Slab | 2026-05-13 | 2026-05-19 | Outer Slab_TA | 100 | 0 |  | 2026-08-07 |  | 2026-08-19 |  | Tower B | Super Structure | L22 | RCC Sub Structure | RCC Works - Slab
8888 | T-14-Staircase 1 | Not Ready |  | 2026-07-01 | 2026-07-13 | 05F-04F | 100 | 0 |  | 2026-08-08 |  | 2026-08-17
8902 | T-14-Staircase 2 | Not Ready |  | 2026-07-01 | 2026-07-13 | 06F-05F | 100 | 0 |  | 2026-08-08 |  | 2026-08-17
11715 | T-18-1st Floor Common Area | Not Ready | 2nd Coat Painting | 2026-10-24 | 2026-11-27 | 2nd Coat Painting | 100 | 0 |  | 2026-08-08 |  | 2026-09-11
41894 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-07-17 | 2026-07-21 | FAPA Cabling | 100 | 0 |  | 2026-08-08 |  | 2026-08-12 |  | Tower A | Super Structure | L59
42919 | Tower A - Super Structure - Finishes & MEP - L46 to L47 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-08-28 | 2026-08-31 | Painting Works | 100 | 0 |  | 2026-08-08 |  | 2026-08-12 |  | Tower A | Super Structure | L46 | Finishes | Painting Works
42937 | Tower A - Super Structure - Finishes & MEP - L47 to L48 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-08-28 | 2026-08-31 | Painting Works | 100 | 0 |  | 2026-08-08 |  | 2026-08-12 |  | Tower A | Super Structure | L47 | Finishes | Painting Works
42955 | Tower A - Super Structure - Finishes & MEP - L48 to L49 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-08-28 | 2026-08-31 | Painting Works | 100 | 0 |  | 2026-08-08 |  | 2026-08-12 |  | Tower A | Super Structure | L48 | Finishes | Painting Works
46662 |  | Not Committed |  | 2026-05-13 | 2026-07-16 | Finishes after 1st Fix | 100 | 0 |  | 2026-08-08 |  | 2026-10-17
46663 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-05-13 | 2026-05-23 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-08-08 |  | 2026-08-24 |  | Tower B | Super Structure | L7 | Finishes | Blockwork
47409 | Tower B - Super Structure - Finishes & MEP - L7 to L13 | Not Ready | Façade Works - MEP & Finishes | 2026-05-13 | 2026-05-23 | DGU Assembly Installation | 100 | 0 |  | 2026-08-08 |  | 2026-08-24 |  | Tower B | Super Structure | L7 | Façade | Façade Works
47410 | Tower B - Super Structure - Finishes & MEP - L7 to L13 | Not Ready | Façade Works - MEP & Finishes | 2026-05-13 | 2026-06-11 | Installation of highly reflective metal sheet | 100 | 0 |  | 2026-08-08 |  | 2026-09-10 |  | Tower B | Super Structure | L7 | Façade | Façade Works
47411 | Tower B - Super Structure - Finishes & MEP - L7 to L13 | Not Ready | Façade Works - MEP & Finishes | 2026-05-13 | 2026-05-30 | Fixing of Backlit Laminated Glass assembly & ACP Panels | 100 | 0 |  | 2026-08-08 |  | 2026-08-29 |  | Tower B | Super Structure | L7 | Façade | Façade Works
47412 | Tower B - Super Structure - Finishes & MEP - L7 to L13 | Not Ready | Façade Works - MEP & Finishes | 2026-05-13 | 2026-05-30 | Fixing of Louvers | 100 | 0 |  | 2026-08-08 |  | 2026-08-29 |  | Tower B | Super Structure | L7 | Façade | Façade Works
47412 | Tower B - Super Structure - Finishes & MEP - L7 to L13 | Not Ready | Façade Works - MEP & Finishes | 2026-05-13 | 2026-05-30 | Fixing of Louvers | 100 | 0 |  | 2026-08-08 |  | 2026-08-29 |  | Tower B | Super Structure | L7
10954 | T-20-Lift Lobby | Not Ready |  | 2026-09-02 | 2026-09-18 | 03F | 100 | 0 |  | 2026-08-09 |  | 2026-08-25
11514 | T-19- Elevation-D | Not Ready |  | 2026-08-26 | 2026-11-18 | Elevation-D | 100 | 0 |  | 2026-08-09 |  | 2026-10-29
10988 | T-20-Staircase 2 | Not Ready |  | 2026-08-27 | 2026-09-07 | GF-BF | 100 | 0 |  | 2026-08-10 |  | 2026-08-19
8870 | T-14-Lift Lobby | Not Ready |  | 2026-07-07 | 2026-07-23 | 07F | 100 | 0 |  | 2026-08-11 |  | 2026-08-27
9633 | T-16-1st Floor Common Area | Not Ready | Window-Open Area | 2026-08-22 | 2026-08-29 | Window-Open Area | 100 | 0 |  | 2026-08-11 |  | 2026-08-18
41836 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-07-18 | 2026-07-23 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-08-11 |  | 2026-08-14 |  | Tower A | Super Structure | L55 | MEP | FPS 2nd Fix - MEP & Finishes
41837 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-07-18 | 2026-07-25 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-08-11 |  | 2026-08-19 |  | Tower A | Super Structure | L55 | MEP | Electrical 2nd Fix - MEP & Finishes
41838 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-07-18 | 2026-07-29 | FAPA Device Fixing | 100 | 0 |  | 2026-08-11 |  | 2026-08-21 |  | Tower A | Super Structure | L55
41838 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-07-18 | 2026-07-29 | FAPA Device Fixing | 100 | 0 |  | 2026-08-11 |  | 2026-08-21 |  | Tower A | Super Structure | L55
41838 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-07-18 | 2026-07-29 | FAPA Device Fixing | 100 | 0 |  | 2026-08-11 |  | 2026-08-21 |  | Tower A | Super Structure | L55
41838 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-07-18 | 2026-07-29 | FAPA Device Fixing | 100 | 0 |  | 2026-08-11 |  | 2026-08-21 |  | Tower A | Super Structure | L55
41839 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-07-18 | 2026-07-23 | HVAC Grill Fixing | 100 | 0 |  | 2026-08-11 |  | 2026-08-14 |  | Tower A | Super Structure | L55 | MEP | HVAC Grill Fixing
46840 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-05-18 | 2026-06-04 | Wet Area Waterproofing | 100 | 0 |  | 2026-08-11 |  | 2026-08-31 |  | Tower B | Super Structure | L17
8913 | T-14- Elevation-C | Not Ready |  | 2026-07-13 | 2026-10-05 | Elevation-C | 100 | 0 |  | 2026-08-12 |  | 2026-11-04
9902 | T-16-Lift | Not Ready | Water Tanks including Finishes | 2026-09-07 | 2026-10-27 | Water Tanks including Finishes | 100 | 0 |  | 2026-08-12 |  | 2026-09-30
11983 | T-18-Lift | Not Ready | Waterproofing | 2026-11-03 | 2027-02-11 | Waterproofing | 100 | 0 |  | 2026-08-12 |  | 2026-11-19
11993 | T-18-Lift Lobby | Not Ready |  | 2026-10-25 | 2026-11-12 | 04F | 100 | 0 |  | 2026-08-12 |  | 2026-08-26
41825 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-07-23 | 2026-07-30 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-08-12 |  | 2026-08-20 |  | Tower A | Super Structure | L54 | MEP | Electrical
41826 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-07-23 | 2026-07-30 | Final Painting | 100 | 0 |  | 2026-08-12 |  | 2026-08-20 |  | Tower A | Super Structure | L54 | Finishes | Final Painting
41826 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-07-23 | 2026-07-30 | Final Painting | 100 | 0 |  | 2026-08-12 |  | 2026-08-20 |  | Tower A | Super Structure | L54 | Finishes | Final Painting
41826 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-07-23 | 2026-07-30 | Final Painting | 100 | 0 |  | 2026-08-12 |  | 2026-08-20 |  | Tower A | Super Structure | L54 | Finishes | Final Painting
41895 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-07-23 | 2026-08-01 | HVAC Ducting | 100 | 0 |  | 2026-08-12 |  | 2026-08-22 |  | Tower A | Super Structure | L59 | MEP | HVAC Ducting
41908 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-07-23 | 2026-07-30 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-08-12 |  | 2026-08-20 |  | Tower A | Super Structure | L60 | MEP | FPS 1st Fix - MEP & Finishes
41909 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-07-23 | 2026-07-28 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-08-12 |  | 2026-08-18 |  | Tower A | Super Structure | L60 | MEP | Electrical 1st Fixes
42972 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-08-31 | 2026-09-02 | PHE Final Fixes | 100 | 0 |  | 2026-08-12 |  | 2026-08-14 |  | Tower A | Super Structure | L49
43008 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-08-31 | 2026-09-02 | PHE Final Fixes | 100 | 0 |  | 2026-08-12 |  | 2026-08-14 |  | Tower A | Super Structure | L51
43025 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-08-31 | 2026-09-04 | False Ceiling | 100 | 0 |  | 2026-08-12 |  | 2026-08-19 |  | Tower A | Super Structure | L52 | Finishes | False Ceiling
43043 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-08-31 | 2026-09-04 | False Ceiling | 100 | 0 |  | 2026-08-12 |  | 2026-08-19 |  | Tower A | Super Structure | L53 | Finishes | False Ceiling
43061 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-08-31 | 2026-09-04 | False Ceiling | 100 | 0 |  | 2026-08-12 |  | 2026-08-19 |  | Tower A | Super Structure | L54 | Finishes | False Ceiling
44013 | Tower A - Super Structure - Finishes & MEP - L65 to L77 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-10-05 | 2026-10-22 | Staircase Railing | 100 | 0 |  | 2026-08-12 |  | 2026-09-01 |  | Tower A | Super Structure | L65
45480 | Tower B - Super Structure - Finishes & MEP - L18 to L19 | Not Ready | Partition Wall-Blockwork | 2026-05-15 | 2026-05-20 | Staircase Area | 100 | 0 |  | 2026-08-12 |  | 2026-08-20 |  | Tower B | Super Structure | L18
9393 | T-15-Lift Lobby | Not Ready |  | 2026-08-22 | 2026-09-08 | 04F | 100 | 0 |  | 2026-08-13 |  | 2026-08-31
9910 | T-16-Lift Lobby | Not Ready |  | 2026-08-31 | 2026-09-16 | 07F | 100 | 0 |  | 2026-08-13 |  | 2026-08-27
11471 | T-19-Lift Lobby | Not Ready |  | 2026-08-26 | 2026-09-11 | 06F | 100 | 0 |  | 2026-08-13 |  | 2026-08-29
40103 | Tower A - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2026-07-10 | 2026-07-30 | Wiring & Light Fixture | 100 | 0 |  | 2026-08-13 |  | 2026-09-02 |  | Tower A | Super Structure
45878 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-06-04 | 2026-06-11 | HVAC Grill Fixing | 100 | 0 |  | 2026-08-13 |  | 2026-08-24 |  | Tower B | Super Structure | GF | MEP | HVAC Grill Fixing
46823 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-05-23 | 2026-06-04 | Cement Plastering in wet areas | 100 | 0 |  | 2026-08-13 |  | 2026-08-27 |  | Tower B | Super Structure | L16
9901 | T-16-Lift | Not Ready | OTS Covers | 2026-09-11 | 2026-10-15 | OTS Covers | 100 | 0 |  | 2026-08-14 |  | 2026-09-15
41840 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-07-25 | 2026-07-30 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-08-14 |  | 2026-08-20 |  | Tower A | Super Structure | L55
41867 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-07-25 | 2026-08-05 | False Ceiling | 100 | 0 |  | 2026-08-14 |  | 2026-08-25 |  | Tower A | Super Structure | L57 | Finishes | False Ceiling
41882 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-07-25 | 2026-08-08 | Flooring & Dado | 100 | 0 |  | 2026-08-14 |  | 2026-08-28 |  | Tower A | Super Structure | L58 | Finishes | Flooring & Dado
43077 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-09-02 | 2026-09-04 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-08-14 |  | 2026-08-19 |  | Tower A | Super Structure | L55 | MEP | FPS 2nd Fix - MEP & Finishes
43078 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-09-02 | 2026-09-04 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-08-14 |  | 2026-08-19 |  | Tower A | Super Structure | L55 | MEP | Electrical 2nd Fix - MEP & Finishes
43095 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-09-02 | 2026-09-04 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-08-14 |  | 2026-08-19 |  | Tower A | Super Structure | L56 | MEP | FPS 2nd Fix - MEP & Finishes
43096 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-09-02 | 2026-09-04 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-08-14 |  | 2026-08-19 |  | Tower A | Super Structure | L56 | MEP | Electrical 2nd Fix - MEP & Finishes
43113 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-09-02 | 2026-09-04 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-08-14 |  | 2026-08-19 |  | Tower A | Super Structure | L57 | MEP | FPS 2nd Fix - MEP & Finishes
43114 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-09-02 | 2026-09-04 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-08-14 |  | 2026-08-19 |  | Tower A | Super Structure | L57 | MEP | Electrical 2nd Fix - MEP & Finishes
43129 |  | Not Committed |  | 2026-09-02 | 2026-09-28 | MEP final fix & Finishes | 100 | 0 |  | 2026-08-14 |  | 2026-09-07
43130 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-09-02 | 2026-09-07 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-08-14 |  | 2026-08-21 |  | Tower A | Super Structure | L58 | Finishes | Door & Window Fixing
43147 |  | Not Committed |  | 2026-09-02 | 2026-09-28 | MEP final fix & Finishes | 100 | 0 |  | 2026-08-14 |  | 2026-09-07
43148 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-09-02 | 2026-09-07 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-08-14 |  | 2026-08-21 |  | Tower A | Super Structure | L59 | Finishes | Door & Window Fixing
43165 |  | Not Committed |  | 2026-09-02 | 2026-09-28 | MEP final fix & Finishes | 100 | 0 |  | 2026-08-14 |  | 2026-09-07
43166 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-09-02 | 2026-09-07 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-08-14 |  | 2026-08-21 |  | Tower A | Super Structure | L60 | Finishes | Door & Window Fixing
44231 | Tower A - Super Structure - Finishes & MEP - L25 to L35 | Not Ready | Hoist Corridor Finishes | 2026-07-24 | 2026-09-24 | L25-35 | 100 | 0 |  | 2026-08-14 |  | 2026-10-15 |  | Tower A | Super Structure | L25
44231 | Tower A - Super Structure - Finishes & MEP - L25 to L35 | Not Ready | Hoist Corridor Finishes | 2026-07-24 | 2026-09-24 | L25-35 | 100 | 0 |  | 2026-08-14 |  | 2026-10-15 |  | Tower A | Super Structure | L25
45620 | Tower B - Super Structure - Finishes & MEP - L17 to L18 | Not Ready | Gypsum Plastering Works | 2026-05-21 | 2026-07-07 | L17-18 | 100 | 0 |  | 2026-08-14 |  | 2026-10-06 |  | Tower B | Super Structure | L17 | Finishes | Gypsum Plastering Works
45620 | Tower B - Super Structure - Finishes & MEP - L17 to L18 | Not Ready | Gypsum Plastering Works | 2026-05-21 | 2026-07-07 | L17-18 | 100 | 0 |  | 2026-08-14 |  | 2026-10-06 |  | Tower B | Super Structure | L17
48054 |  | Not Committed |  | 2026-04-18 | 2026-05-06 | CH03-Roof (4.45) (MEP level) | 100 | 0 |  | 2026-08-14 |  | 2026-09-02
48055 | Club House - Super structure - CH03 to Roof | Not Ready |  | 2026-04-18 | 2026-04-29 | Columns_CH | 100 | 0 |  | 2026-08-14 |  | 2026-08-27 |  | Club House | Super Structure | CH03
48056 | Club House - Super structure - CH03 to Roof | Not Ready |  | 2026-04-18 | 2026-04-29 | Staircase_CH | 100 | 0 |  | 2026-08-14 |  | 2026-08-27 |  | Club House | Super Structure | CH03
48211 | Club House - Super structure - CH02 to CH03 | Not Ready |  | 2026-04-18 | 2026-05-23 | CH02-CH03 (P6-7) | 100 | 0 |  | 2026-08-14 |  | 2026-09-22 |  | Club House | Super Structure | CH02
9928 | T-16-Staircase 1 | Not Ready |  | 2026-08-25 | 2026-09-05 | 05F-04F | 100 | 0 |  | 2026-08-15 |  | 2026-08-26
9942 | T-16-Staircase 2 | Not Ready |  | 2026-08-25 | 2026-09-05 | 06F-05F | 100 | 0 |  | 2026-08-15 |  | 2026-08-26
8889 | T-14-Staircase 1 | Not Ready |  | 2026-07-13 | 2026-07-23 | 04F-03F | 100 | 0 |  | 2026-08-18 |  | 2026-08-30
8903 | T-14-Staircase 2 | Not Ready |  | 2026-07-13 | 2026-07-23 | 05F-04F | 100 | 0 |  | 2026-08-18 |  | 2026-08-30
9413 | T-15-Staircase 1 | Not Ready |  | 2026-08-22 | 2026-09-02 | GF-BF | 100 | 0 |  | 2026-08-18 |  | 2026-08-30
9427 | T-15-Staircase 2 | Not Ready |  | 2026-08-22 | 2026-09-02 | 01F-GF | 100 | 0 |  | 2026-08-18 |  | 2026-08-30
9953 | T-16- Elevation-C | Not Ready |  | 2026-09-05 | 2026-11-28 | Elevation-C | 100 | 0 |  | 2026-08-18 |  | 2026-11-09
11490 | T-19-Staircase 1 | Not Ready |  | 2026-08-26 | 2026-09-05 | 03F-02F | 100 | 0 |  | 2026-08-18 |  | 2026-08-31
11504 | T-19-Staircase 2 | Not Ready |  | 2026-08-26 | 2026-09-05 | 04F-03F | 100 | 0 |  | 2026-08-18 |  | 2026-08-31
39269 |  | Not Committed |  | 2026-02-18 | 2026-06-10 | Super-Structure_Retail | 100 | 0 |  | 2026-08-18 |  | 2026-12-14
39270 |  | Not Committed |  | 2026-02-18 | 2026-04-13 | GF to R1 (6.61m) | 100 | 0 |  | 2026-08-18 |  | 2026-10-12
39271 | Retail - Super structure - GF to R1 | Not Ready | RCC Works - Vertical | 2026-02-18 | 2026-03-26 | Columns_RT | 100 | 0 |  | 2026-08-18 |  | 2026-09-23 |  | Retail | Super Structure | GF | RCC Sub Structure | RCC Works - Vertical
39271 | Retail - Super structure - GF to R1 | Not Ready | RCC Works - Vertical | 2026-02-18 | 2026-03-26 | Columns_RT | 100 | 0 |  | 2026-08-18 |  | 2026-09-23 |  | Retail | Super Structure | GF
39272 | Retail - Super structure - GF to R1 | Not Ready | RCC Works - Slab | 2026-02-18 | 2026-03-20 | Staircase_RT | 100 | 0 |  | 2026-08-18 |  | 2026-09-16 |  | Retail | Super Structure | GF | RCC Sub Structure | RCC Works - Slab
39272 | Retail - Super structure - GF to R1 | Not Ready | RCC Works - Slab | 2026-02-18 | 2026-03-20 | Staircase_RT | 100 | 0 |  | 2026-08-18 |  | 2026-09-16 |  | Retail | Super Structure | GF
41910 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-07-30 | 2026-08-01 | FAPA Cabling | 100 | 0 |  | 2026-08-18 |  | 2026-08-20 |  | Tower A | Super Structure | L60
42973 | Tower A - Super Structure - Finishes & MEP - L49 to L50 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-09-03 | 2026-09-05 | Painting Works | 100 | 0 |  | 2026-08-18 |  | 2026-08-20 |  | Tower A | Super Structure | L49 | Finishes | Painting Works
43009 | Tower A - Super Structure - Finishes & MEP - L51 to L52 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-09-03 | 2026-09-05 | Painting Works | 100 | 0 |  | 2026-08-18 |  | 2026-08-20 |  | Tower A | Super Structure | L51 | Finishes | Painting Works
44166 | Tower A - Super Structure - Finishes & MEP - L35 to L45 | Not Ready |  | 2026-07-25 | 2026-08-01 | Accessories & Alignment | 100 | 0 |  | 2026-08-18 |  | 2026-08-25 |  | Tower A | Super Structure | L35 | Façade | Façade Works
44166 | Tower A - Super Structure - Finishes & MEP - L35 to L45 | Not Ready |  | 2026-07-25 | 2026-08-01 | Accessories & Alignment | 100 | 0 |  | 2026-08-18 |  | 2026-08-25 |  | Tower A | Super Structure | L35
44169 | Tower A - Super Structure - Finishes & MEP - L45 to L55 | Not Ready |  | 2026-07-25 | 2026-08-04 | Glass Assembly Installation | 100 | 0 |  | 2026-08-18 |  | 2026-08-26 |  | Tower A | Super Structure | L45
44170 | Tower A - Super Structure - Finishes & MEP - L45 to L55 | Not Ready |  | 2026-07-25 | 2026-08-01 | ACP Sheet & Insulation fixing | 100 | 0 |  | 2026-08-18 |  | 2026-08-25 |  | Tower A | Super Structure | L45
44171 | Tower A - Super Structure - Finishes & MEP - L45 to L55 | Not Ready |  | 2026-07-25 | 2026-08-01 | Fixing of Louvers | 100 | 0 |  | 2026-08-18 |  | 2026-08-25 |  | Tower A | Super Structure | L45 | Façade | Façade Works
44171 | Tower A - Super Structure - Finishes & MEP - L45 to L55 | Not Ready |  | 2026-07-25 | 2026-08-01 | Fixing of Louvers | 100 | 0 |  | 2026-08-18 |  | 2026-08-25 |  | Tower A | Super Structure | L45
44173 |  | Not Committed |  | 2026-07-25 | 2026-09-01 | L55-65 | 100 | 0 |  | 2026-08-18 |  | 2026-09-11
44173 |  | Not Committed |  | 2026-07-25 | 2026-09-01 | L55-65 | 100 | 0 |  | 2026-08-18 |  | 2026-09-11
44174 | Tower A - Super Structure - Finishes & MEP - L55 to L65 | Not Ready |  | 2026-07-25 | 2026-08-04 | Al. Frame Section Installation | 100 | 0 |  | 2026-08-18 |  | 2026-08-26 |  | Tower A | Super Structure | L55
44209 | Tower A - Super Structure - Finishes & MEP - L35 to L45 | Not Ready |  | 2026-07-25 | 2026-08-01 | Accessories & Alignment | 100 | 0 |  | 2026-08-18 |  | 2026-08-25 |  | Tower A | Super Structure | L35 | Façade | Façade Works
44209 | Tower A - Super Structure - Finishes & MEP - L35 to L45 | Not Ready |  | 2026-07-25 | 2026-08-01 | Accessories & Alignment | 100 | 0 |  | 2026-08-18 |  | 2026-08-25 |  | Tower A | Super Structure | L35
44212 | Tower A - Super Structure - Finishes & MEP - L45 to L55 | Not Ready |  | 2026-07-25 | 2026-08-04 | Glass Assembly Installation | 100 | 0 |  | 2026-08-18 |  | 2026-08-26 |  | Tower A | Super Structure | L45
44213 | Tower A - Super Structure - Finishes & MEP - L45 to L55 | Not Ready |  | 2026-07-25 | 2026-08-01 | ACP Sheet & Insulation fixing | 100 | 0 |  | 2026-08-18 |  | 2026-08-25 |  | Tower A | Super Structure | L45
44214 | Tower A - Super Structure - Finishes & MEP - L45 to L55 | Not Ready |  | 2026-07-25 | 2026-08-01 | Fixing of Louvers | 100 | 0 |  | 2026-08-18 |  | 2026-08-25 |  | Tower A | Super Structure | L45 | Façade | Façade Works
44214 | Tower A - Super Structure - Finishes & MEP - L45 to L55 | Not Ready |  | 2026-07-25 | 2026-08-01 | Fixing of Louvers | 100 | 0 |  | 2026-08-18 |  | 2026-08-25 |  | Tower A | Super Structure | L45
44216 |  | Not Committed |  | 2026-07-25 | 2026-09-01 | L55-65 | 100 | 0 |  | 2026-08-18 |  | 2026-09-11
44216 |  | Not Committed |  | 2026-07-25 | 2026-09-01 | L55-65 | 100 | 0 |  | 2026-08-18 |  | 2026-09-11
44217 | Tower A - Super Structure - Finishes & MEP - L55 to L65 | Not Ready |  | 2026-07-25 | 2026-08-04 | Al. Frame Section Installation | 100 | 0 |  | 2026-08-18 |  | 2026-08-26 |  | Tower A | Super Structure | L55
9634 | T-16-1st Floor Common Area | Not Ready | 1st Coat Painting | 2026-08-29 | 2026-09-21 | 1st Coat Painting | 100 | 0 |  | 2026-08-19 |  | 2026-09-09
41852 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-07-31 | 2026-08-05 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-08-19 |  | 2026-08-22 |  | Tower A | Super Structure | L56 | MEP | FPS 2nd Fix - MEP & Finishes
41853 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-07-31 | 2026-08-07 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-08-19 |  | 2026-08-25 |  | Tower A | Super Structure | L56 | MEP | Electrical 2nd Fix - MEP & Finishes
41854 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-07-31 | 2026-08-11 | FAPA Device Fixing | 100 | 0 |  | 2026-08-19 |  | 2026-08-27 |  | Tower A | Super Structure | L56
41854 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-07-31 | 2026-08-11 | FAPA Device Fixing | 100 | 0 |  | 2026-08-19 |  | 2026-08-27 |  | Tower A | Super Structure | L56
41854 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-07-31 | 2026-08-11 | FAPA Device Fixing | 100 | 0 |  | 2026-08-19 |  | 2026-08-27 |  | Tower A | Super Structure | L56
41854 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-07-31 | 2026-08-11 | FAPA Device Fixing | 100 | 0 |  | 2026-08-19 |  | 2026-08-27 |  | Tower A | Super Structure | L56
41855 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-07-31 | 2026-08-05 | HVAC Grill Fixing | 100 | 0 |  | 2026-08-19 |  | 2026-08-22 |  | Tower A | Super Structure | L56 | MEP | HVAC Grill Fixing
45319 |  | Not Ready |  | 2026-05-20 | 2026-06-01 | L23-24 | 100 | 0 |  | 2026-08-19 |  | 2026-09-03
45319 |  | Not Ready |  | 2026-05-20 | 2026-06-01 | L23-24 | 100 | 0 |  | 2026-08-19 |  | 2026-09-03 |  |  |  |  | Finishes | Gypsum Plastering Works
45320 | Tower B - Super Structure - Core & Outer Slab L23-24 | Not Ready | RCC Works - Vertical | 2026-05-20 | 2026-05-29 | Outer Columns_TA | 100 | 0 |  | 2026-08-19 |  | 2026-08-31 |  | Tower B | Super Structure | L23 | RCC Sub Structure | RCC Works - Vertical
45485 |  | Not Committed |  | 2026-05-20 | 2026-06-20 | L20-21 | 100 | 0 |  | 2026-08-19 |  | 2026-09-22
45485 |  | Not Committed |  | 2026-05-20 | 2026-06-20 | L20-21 | 100 | 0 |  | 2026-08-19 |  | 2026-09-22 |  |  |  |  | Finishes | Gypsum Plastering Works
45486 | Tower B - Super Structure - Finishes & MEP - L20 to L21 | Not Ready | Partition Wall-Blockwork | 2026-05-20 | 2026-06-06 | De-shuttering & Area clearance | 100 | 0 |  | 2026-08-19 |  | 2026-09-05 |  | Tower B | Super Structure | L20
9383 | T-15-Lift | Not Ready | Waterproofing | 2026-08-30 | 2026-12-09 | Waterproofing | 100 | 0 |  | 2026-08-20 |  | 2026-12-01
12013 | T-18-Staircase 1 | Not Ready |  | 2026-10-25 | 2026-11-06 | GF-BF | 100 | 0 |  | 2026-08-20 |  | 2026-08-29
12027 | T-18-Staircase 2 | Not Ready |  | 2026-10-25 | 2026-11-06 | 01F-GF | 100 | 0 |  | 2026-08-20 |  | 2026-08-29
41841 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-08-01 | 2026-08-08 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-08-20 |  | 2026-08-26 |  | Tower A | Super Structure | L55 | MEP | Electrical
41842 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-08-01 | 2026-08-08 | Final Painting | 100 | 0 |  | 2026-08-20 |  | 2026-08-26 |  | Tower A | Super Structure | L55 | Finishes | Final Painting
41842 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-08-01 | 2026-08-08 | Final Painting | 100 | 0 |  | 2026-08-20 |  | 2026-08-26 |  | Tower A | Super Structure | L55 | Finishes | Final Painting
41842 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-08-01 | 2026-08-08 | Final Painting | 100 | 0 |  | 2026-08-20 |  | 2026-08-26 |  | Tower A | Super Structure | L55 | Finishes | Final Painting
41911 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-08-01 | 2026-08-12 | HVAC Ducting | 100 | 0 |  | 2026-08-20 |  | 2026-08-28 |  | Tower A | Super Structure | L60 | MEP | HVAC Ducting
41924 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-08-01 | 2026-08-08 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-08-20 |  | 2026-08-26 |  | Tower A | Super Structure | L61 | MEP | FPS 1st Fix - MEP & Finishes
41925 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-08-01 | 2026-08-06 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-08-20 |  | 2026-08-24 |  | Tower A | Super Structure | L61 | MEP | Electrical 1st Fixes
43026 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-09-05 | 2026-09-09 | PHE Final Fixes | 100 | 0 |  | 2026-08-20 |  | 2026-08-22 |  | Tower A | Super Structure | L52
43044 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-09-05 | 2026-09-09 | PHE Final Fixes | 100 | 0 |  | 2026-08-20 |  | 2026-08-22 |  | Tower A | Super Structure | L53
43062 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-09-05 | 2026-09-09 | PHE Final Fixes | 100 | 0 |  | 2026-08-20 |  | 2026-08-22 |  | Tower A | Super Structure | L54
43079 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-09-05 | 2026-09-11 | False Ceiling | 100 | 0 |  | 2026-08-20 |  | 2026-08-25 |  | Tower A | Super Structure | L55 | Finishes | False Ceiling
43097 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-09-05 | 2026-09-11 | False Ceiling | 100 | 0 |  | 2026-08-20 |  | 2026-08-25 |  | Tower A | Super Structure | L56 | Finishes | False Ceiling
43115 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-09-05 | 2026-09-11 | False Ceiling | 100 | 0 |  | 2026-08-20 |  | 2026-08-25 |  | Tower A | Super Structure | L57 | Finishes | False Ceiling
44015 | Tower A - Super Structure - Finishes & MEP - L65 to L77 | Not Ready | Staircase Finishes - MEP & Finishes | 2026-10-10 | 2026-10-22 | Staircase Light Fixtures & Devices fixing | 100 | 0 |  | 2026-08-20 |  | 2026-09-01 |  | Tower A | Super Structure | L65
46853 |  | Not Committed |  | 2026-05-21 | 2027-06-21 | L18-19 | 100 | 0 |  | 2026-08-20 |  | 2027-07-31
46853 |  | Not Committed |  | 2026-05-21 | 2027-06-21 | L18-19 | 100 | 0 |  | 2026-08-20 |  | 2027-07-31 |  |  |  |  | Finishes | Gypsum Plastering Works
46854 |  | Not Committed |  | 2026-05-21 | 2026-06-27 | MEP 1st Fixes | 100 | 0 |  | 2026-08-20 |  | 2026-09-29
46855 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-05-21 | 2026-05-29 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-08-20 |  | 2026-08-28 |  | Tower B | Super Structure | L18 | MEP | FPS 1st Fix - MEP & Finishes
46856 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-05-21 | 2026-05-26 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-08-20 |  | 2026-08-26 |  | Tower B | Super Structure | L18 | MEP | Electrical 1st Fixes
46857 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-05-21 | 2026-05-29 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-08-20 |  | 2026-08-28 |  | Tower B | Super Structure | L18
8569 | T-14-1st Floor Common Area | Not Ready | 2nd Coat Painting | 2026-07-22 | 2026-08-25 | 2nd Coat Painting | 100 | 0 |  | 2026-08-21 |  | 2026-09-22
40104 | Tower A - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2026-07-23 | 2026-08-20 | FAPA Cable Works | 100 | 0 |  | 2026-08-21 |  | 2026-09-16 |  | Tower A | Super Structure
40127 | Tower A - Super Structure - Finishes & MEP - STP | Not Ready |  | 2026-07-23 | 2026-09-01 | Testing & Commissioning | 100 | 0 |  | 2026-08-21 |  | 2026-10-01 |  | Tower A | Super Structure
40127 | Tower A - Super Structure - Finishes & MEP - STP | Not Ready |  | 2026-07-23 | 2026-09-01 | Testing & Commissioning | 100 | 0 |  | 2026-08-21 |  | 2026-10-01 |  | Tower A | Super Structure
44259 |  | Not Ready | External Development | 2026-07-23 | 2026-09-23 | External Fire Hydrant Line (Outlet) | 100 | 0 |  | 2026-08-21 |  | 2026-10-21
45483 | Tower B - Super Structure - Finishes & MEP - L19 to L20 | Not Ready | Partition Wall-Blockwork | 2026-05-26 | 2026-06-03 | Partition Walls | 100 | 0 |  | 2026-08-21 |  | 2026-08-29 |  | Tower B | Super Structure | L19
8914 | T-14- Elevation-D | Not Ready |  | 2026-07-23 | 2026-10-15 | Elevation-D | 100 | 0 |  | 2026-08-22 |  | 2026-11-14
9115 | T-15-1st Floor Common Area | Not Ready | 2nd Coat Painting | 2026-08-21 | 2026-09-23 | 2nd Coat Painting | 100 | 0 |  | 2026-08-22 |  | 2026-09-25
10995 |  | Not Ready | De-Snagging & Handing Over | 2026-09-28 | 2027-01-07 | De-Snagging & Handing Over | 100 | 0 |  | 2026-08-22 |  | 2026-12-01
41856 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-08-07 | 2026-08-12 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-08-22 |  | 2026-08-26 |  | Tower A | Super Structure | L56
41883 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-08-07 | 2026-08-19 | False Ceiling | 100 | 0 |  | 2026-08-22 |  | 2026-08-31 |  | Tower A | Super Structure | L58 | Finishes | False Ceiling
41898 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-08-07 | 2026-08-22 | Flooring & Dado | 100 | 0 |  | 2026-08-22 |  | 2026-09-03 |  | Tower A | Super Structure | L59 | Finishes | Flooring & Dado
43131 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-09-09 | 2026-09-11 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-08-22 |  | 2026-08-25 |  | Tower A | Super Structure | L58 | MEP | FPS 2nd Fix - MEP & Finishes
43132 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-09-09 | 2026-09-11 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-08-22 |  | 2026-08-25 |  | Tower A | Super Structure | L58 | MEP | Electrical 2nd Fix - MEP & Finishes
43149 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-09-09 | 2026-09-11 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-08-22 |  | 2026-08-25 |  | Tower A | Super Structure | L59 | MEP | FPS 2nd Fix - MEP & Finishes
43150 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-09-09 | 2026-09-11 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-08-22 |  | 2026-08-25 |  | Tower A | Super Structure | L59 | MEP | Electrical 2nd Fix - MEP & Finishes
43167 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-09-09 | 2026-09-11 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-08-22 |  | 2026-08-25 |  | Tower A | Super Structure | L60 | MEP | FPS 2nd Fix - MEP & Finishes
43168 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-09-09 | 2026-09-11 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-08-22 |  | 2026-08-25 |  | Tower A | Super Structure | L60 | MEP | Electrical 2nd Fix - MEP & Finishes
43183 |  | Not Committed |  | 2026-09-09 | 2026-10-06 | MEP final fix & Finishes | 100 | 0 |  | 2026-08-22 |  | 2026-09-14
43184 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-09-09 | 2026-09-14 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-08-22 |  | 2026-08-27 |  | Tower A | Super Structure | L61 | Finishes | Door & Window Fixing
43201 |  | Not Committed |  | 2026-09-09 | 2026-10-06 | MEP final fix & Finishes | 100 | 0 |  | 2026-08-22 |  | 2026-09-14
43202 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-09-09 | 2026-09-14 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-08-22 |  | 2026-08-27 |  | Tower A | Super Structure | L62 | Finishes | Door & Window Fixing
43219 |  | Not Committed |  | 2026-09-09 | 2026-09-26 | MEP final fix & Finishes | 100 | 0 |  | 2026-08-22 |  | 2026-09-05
43220 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-09-09 | 2026-09-14 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-08-22 |  | 2026-08-27 |  | Tower A | Super Structure | L63 | Finishes | Door & Window Fixing
48057 | Club House - Super structure - CH03 to Roof | Not Ready |  | 2026-04-24 | 2026-05-06 | Slab_CH | 100 | 0 |  | 2026-08-22 |  | 2026-09-02 |  | Club House | Super Structure | CH03
11221 | T-19-2nd Floor Common Area | Not Ready | 2nd Coat Painting | 2026-09-10 | 2026-10-14 | 2nd Coat Painting | 100 | 0 |  | 2026-08-23 |  | 2026-09-26
9895 | T-16-11th Floor Common Area | Not Ready | 2nd Coat Painting | 2026-09-21 | 2026-10-24 | 2nd Coat Painting | 100 | 0 |  | 2026-08-24 |  | 2026-09-27
41926 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-08-08 | 2026-08-12 | FAPA Cabling | 100 | 0 |  | 2026-08-24 |  | 2026-08-26 |  | Tower A | Super Structure | L61
43027 | Tower A - Super Structure - Finishes & MEP - L52 to L53 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-09-10 | 2026-09-12 | Painting Works | 100 | 0 |  | 2026-08-24 |  | 2026-08-26 |  | Tower A | Super Structure | L52 | Finishes | Painting Works
43045 | Tower A - Super Structure - Finishes & MEP - L53 to L54 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-09-10 | 2026-09-12 | Painting Works | 100 | 0 |  | 2026-08-24 |  | 2026-08-26 |  | Tower A | Super Structure | L53 | Finishes | Painting Works
43063 | Tower A - Super Structure - Finishes & MEP - L54 to L55 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-09-10 | 2026-09-12 | Painting Works | 100 | 0 |  | 2026-08-24 |  | 2026-08-26 |  | Tower A | Super Structure | L54 | Finishes | Painting Works
46664 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-05-25 | 2026-06-02 | Door & Window Frame work | 100 | 0 |  | 2026-08-24 |  | 2026-09-01 |  | Tower B | Super Structure | L7 | Finishes | Door & Window Frame work
46680 |  | Not Committed |  | 2026-05-25 | 2026-08-07 | Finishes after 1st Fix | 100 | 0 |  | 2026-08-24 |  | 2026-11-02
46681 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-05-25 | 2026-06-05 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-08-24 |  | 2026-09-04 |  | Tower B | Super Structure | L8 | Finishes | Blockwork
47413 | Tower B - Super Structure - Finishes & MEP - L7 to L13 | Not Ready | Façade Works - MEP & Finishes | 2026-05-25 | 2026-06-11 | Accessories & Alignment | 100 | 0 |  | 2026-08-24 |  | 2026-09-10 |  | Tower B | Super Structure | L7 | Façade | Façade Works
47413 | Tower B - Super Structure - Finishes & MEP - L7 to L13 | Not Ready | Façade Works - MEP & Finishes | 2026-05-25 | 2026-06-11 | Accessories & Alignment | 100 | 0 |  | 2026-08-24 |  | 2026-09-10 |  | Tower B | Super Structure | L7
41868 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-08-13 | 2026-08-19 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-08-25 |  | 2026-08-28 |  | Tower A | Super Structure | L57 | MEP | FPS 2nd Fix - MEP & Finishes
41869 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-08-13 | 2026-08-21 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-08-25 |  | 2026-08-31 |  | Tower A | Super Structure | L57 | MEP | Electrical 2nd Fix - MEP & Finishes
41870 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-08-13 | 2026-08-24 | FAPA Device Fixing | 100 | 0 |  | 2026-08-25 |  | 2026-09-02 |  | Tower A | Super Structure | L57
41870 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-08-13 | 2026-08-24 | FAPA Device Fixing | 100 | 0 |  | 2026-08-25 |  | 2026-09-02 |  | Tower A | Super Structure | L57
41870 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-08-13 | 2026-08-24 | FAPA Device Fixing | 100 | 0 |  | 2026-08-25 |  | 2026-09-02 |  | Tower A | Super Structure | L57
41870 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-08-13 | 2026-08-24 | FAPA Device Fixing | 100 | 0 |  | 2026-08-25 |  | 2026-09-02 |  | Tower A | Super Structure | L57
41871 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-08-13 | 2026-08-19 | HVAC Grill Fixing | 100 | 0 |  | 2026-08-25 |  | 2026-08-28 |  | Tower A | Super Structure | L57 | MEP | HVAC Grill Fixing
44232 | Tower A - Super Structure - Finishes & MEP - L35 to L45 | Not Ready | Hoist Corridor Finishes | 2026-08-08 | 2026-10-09 | L35-45 | 100 | 0 |  | 2026-08-25 |  | 2026-10-24 |  | Tower A | Super Structure | L35
44232 | Tower A - Super Structure - Finishes & MEP - L35 to L45 | Not Ready | Hoist Corridor Finishes | 2026-08-08 | 2026-10-09 | L35-45 | 100 | 0 |  | 2026-08-25 |  | 2026-10-24 |  | Tower A | Super Structure | L35
10436 | T-21-Lift Lobby | Not Ready |  | 2026-09-23 | 2026-10-10 | 01F | 100 | 0 |  | 2026-08-26 |  | 2026-09-09
10955 | T-20-Lift Lobby | Not Ready |  | 2026-09-18 | 2026-10-06 | 02F | 100 | 0 |  | 2026-08-26 |  | 2026-09-13
41857 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-08-14 | 2026-08-22 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-08-26 |  | 2026-09-01 |  | Tower A | Super Structure | L56 | MEP | Electrical
41858 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-08-14 | 2026-08-22 | Final Painting | 100 | 0 |  | 2026-08-26 |  | 2026-09-01 |  | Tower A | Super Structure | L56 | Finishes | Final Painting
41858 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-08-14 | 2026-08-22 | Final Painting | 100 | 0 |  | 2026-08-26 |  | 2026-09-01 |  | Tower A | Super Structure | L56 | Finishes | Final Painting
41858 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-08-14 | 2026-08-22 | Final Painting | 100 | 0 |  | 2026-08-26 |  | 2026-09-01 |  | Tower A | Super Structure | L56 | Finishes | Final Painting
41927 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-08-14 | 2026-08-25 | HVAC Ducting | 100 | 0 |  | 2026-08-26 |  | 2026-09-03 |  | Tower A | Super Structure | L61 | MEP | HVAC Ducting
41940 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-08-14 | 2026-08-22 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-08-26 |  | 2026-09-01 |  | Tower A | Super Structure | L62 | MEP | FPS 1st Fix - MEP & Finishes
41941 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-08-14 | 2026-08-20 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-08-26 |  | 2026-08-29 |  | Tower A | Super Structure | L62 | MEP | Electrical 1st Fixes
43080 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-09-12 | 2026-09-16 | PHE Final Fixes | 100 | 0 |  | 2026-08-26 |  | 2026-08-28 |  | Tower A | Super Structure | L55
43098 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-09-12 | 2026-09-16 | PHE Final Fixes | 100 | 0 |  | 2026-08-26 |  | 2026-08-28 |  | Tower A | Super Structure | L56
43116 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-09-12 | 2026-09-16 | PHE Final Fixes | 100 | 0 |  | 2026-08-26 |  | 2026-08-28 |  | Tower A | Super Structure | L57
43133 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-09-12 | 2026-09-19 | False Ceiling | 100 | 0 |  | 2026-08-26 |  | 2026-08-31 |  | Tower A | Super Structure | L58 | Finishes | False Ceiling
43151 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-09-12 | 2026-09-19 | False Ceiling | 100 | 0 |  | 2026-08-26 |  | 2026-08-31 |  | Tower A | Super Structure | L59 | Finishes | False Ceiling
43169 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-09-12 | 2026-09-19 | False Ceiling | 100 | 0 |  | 2026-08-26 |  | 2026-08-31 |  | Tower A | Super Structure | L60 | Finishes | False Ceiling
44172 | Tower A - Super Structure - Finishes & MEP - L45 to L55 | Not Ready |  | 2026-08-13 | 2026-08-21 | Accessories & Alignment | 100 | 0 |  | 2026-08-26 |  | 2026-09-02 |  | Tower A | Super Structure | L45 | Façade | Façade Works
44172 | Tower A - Super Structure - Finishes & MEP - L45 to L55 | Not Ready |  | 2026-08-13 | 2026-08-21 | Accessories & Alignment | 100 | 0 |  | 2026-08-26 |  | 2026-09-02 |  | Tower A | Super Structure | L45
44175 | Tower A - Super Structure - Finishes & MEP - L55 to L65 | Not Ready |  | 2026-08-13 | 2026-08-22 | Glass Assembly Installation | 100 | 0 |  | 2026-08-26 |  | 2026-09-03 |  | Tower A | Super Structure | L55
44176 | Tower A - Super Structure - Finishes & MEP - L55 to L65 | Not Ready |  | 2026-08-13 | 2026-08-21 | ACP Sheet & Insulation fixing | 100 | 0 |  | 2026-08-26 |  | 2026-09-02 |  | Tower A | Super Structure | L55
44177 | Tower A - Super Structure - Finishes & MEP - L55 to L65 | Not Ready |  | 2026-08-13 | 2026-08-21 | Fixing of Louvers | 100 | 0 |  | 2026-08-26 |  | 2026-09-02 |  | Tower A | Super Structure | L55 | Façade | Façade Works
44177 | Tower A - Super Structure - Finishes & MEP - L55 to L65 | Not Ready |  | 2026-08-13 | 2026-08-21 | Fixing of Louvers | 100 | 0 |  | 2026-08-26 |  | 2026-09-02 |  | Tower A | Super Structure | L55
44179 |  | Not Committed |  | 2026-08-13 | 2026-09-10 | L65-Terrace | 100 | 0 |  | 2026-08-26 |  | 2026-09-23
44179 |  | Not Committed |  | 2026-08-13 | 2026-09-10 | L65-Terrace | 100 | 0 |  | 2026-08-26 |  | 2026-09-23
44180 | Tower A - Super Structure - Finishes & MEP - L65 to L77 | Not Ready |  | 2026-08-13 | 2026-08-22 | Al. Frame Section Installation | 100 | 0 |  | 2026-08-26 |  | 2026-09-03 |  | Tower A | Super Structure | L65
44215 | Tower A - Super Structure - Finishes & MEP - L45 to L55 | Not Ready |  | 2026-08-13 | 2026-08-21 | Accessories & Alignment | 100 | 0 |  | 2026-08-26 |  | 2026-09-02 |  | Tower A | Super Structure | L45 | Façade | Façade Works
44215 | Tower A - Super Structure - Finishes & MEP - L45 to L55 | Not Ready |  | 2026-08-13 | 2026-08-21 | Accessories & Alignment | 100 | 0 |  | 2026-08-26 |  | 2026-09-02 |  | Tower A | Super Structure | L45
44218 | Tower A - Super Structure - Finishes & MEP - L55 to L65 | Not Ready |  | 2026-08-13 | 2026-08-22 | Glass Assembly Installation | 100 | 0 |  | 2026-08-26 |  | 2026-09-03 |  | Tower A | Super Structure | L55
44219 | Tower A - Super Structure - Finishes & MEP - L55 to L65 | Not Ready |  | 2026-08-13 | 2026-08-21 | ACP Sheet & Insulation fixing | 100 | 0 |  | 2026-08-26 |  | 2026-09-02 |  | Tower A | Super Structure | L55
44220 | Tower A - Super Structure - Finishes & MEP - L55 to L65 | Not Ready |  | 2026-08-13 | 2026-08-21 | Fixing of Louvers | 100 | 0 |  | 2026-08-26 |  | 2026-09-02 |  | Tower A | Super Structure | L55 | Façade | Façade Works
44220 | Tower A - Super Structure - Finishes & MEP - L55 to L65 | Not Ready |  | 2026-08-13 | 2026-08-21 | Fixing of Louvers | 100 | 0 |  | 2026-08-26 |  | 2026-09-02 |  | Tower A | Super Structure | L55
44222 |  | Not Committed |  | 2026-08-13 | 2026-09-10 | L65-Terrace | 100 | 0 |  | 2026-08-26 |  | 2026-09-23
44222 |  | Not Committed |  | 2026-08-13 | 2026-09-10 | L65-Terrace | 100 | 0 |  | 2026-08-26 |  | 2026-09-23
44223 | Tower A - Super Structure - Finishes & MEP - L65 to L77 | Not Ready |  | 2026-08-13 | 2026-08-22 | Al. Frame Section Installation | 100 | 0 |  | 2026-08-26 |  | 2026-09-03 |  | Tower A | Super Structure | L65
45321 | Tower B - Super Structure - Core & Outer Slab L23-24 | Not Ready | RCC Works - Slab | 2026-05-25 | 2026-06-01 | Outer Slab_TA | 100 | 0 |  | 2026-08-26 |  | 2026-09-03 |  | Tower B | Super Structure | L23 | RCC Sub Structure | RCC Works - Slab
9687 | T-16-3rd Floor Common Area | Not Ready | 2nd Coat Painting | 2026-09-09 | 2026-10-13 | 2nd Coat Painting | 100 | 0 |  | 2026-08-27 |  | 2026-09-30
9929 | T-16-Staircase 1 | Not Ready |  | 2026-09-05 | 2026-09-16 | 04F-03F | 100 | 0 |  | 2026-08-27 |  | 2026-09-05
9943 | T-16-Staircase 2 | Not Ready |  | 2026-09-05 | 2026-09-16 | 05F-04F | 100 | 0 |  | 2026-08-27 |  | 2026-09-05
11994 | T-18-Lift Lobby | Not Ready |  | 2026-11-12 | 2026-11-28 | 03F | 100 | 0 |  | 2026-08-27 |  | 2026-09-14
8871 | T-14-Lift Lobby | Not Ready |  | 2026-07-23 | 2026-08-08 | 06F | 100 | 0 |  | 2026-08-28 |  | 2026-09-14
9911 | T-16-Lift Lobby | Not Ready |  | 2026-09-16 | 2026-10-03 | 06F | 100 | 0 |  | 2026-08-28 |  | 2026-09-12
9954 | T-16- Elevation-D | Not Ready |  | 2026-09-16 | 2026-12-09 | Elevation-D | 100 | 0 |  | 2026-08-28 |  | 2026-11-19
41872 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-08-21 | 2026-08-25 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-08-28 |  | 2026-09-01 |  | Tower A | Super Structure | L57
41899 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-08-21 | 2026-08-29 | False Ceiling | 100 | 0 |  | 2026-08-28 |  | 2026-09-05 |  | Tower A | Super Structure | L59 | Finishes | False Ceiling
41914 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-08-21 | 2026-09-02 | Flooring & Dado | 100 | 0 |  | 2026-08-28 |  | 2026-09-10 |  | Tower A | Super Structure | L60 | Finishes | Flooring & Dado
43185 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-09-16 | 2026-09-19 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-08-28 |  | 2026-08-31 |  | Tower A | Super Structure | L61 | MEP | FPS 2nd Fix - MEP & Finishes
43186 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-09-16 | 2026-09-19 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-08-28 |  | 2026-08-31 |  | Tower A | Super Structure | L61 | MEP | Electrical 2nd Fix - MEP & Finishes
43203 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-09-16 | 2026-09-19 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-08-28 |  | 2026-08-31 |  | Tower A | Super Structure | L62 | MEP | FPS 2nd Fix - MEP & Finishes
43204 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-09-16 | 2026-09-19 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-08-28 |  | 2026-08-31 |  | Tower A | Super Structure | L62 | MEP | Electrical 2nd Fix - MEP & Finishes
43221 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-09-16 | 2026-09-19 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-08-28 |  | 2026-08-31 |  | Tower A | Super Structure | L63 | MEP | FPS 2nd Fix - MEP & Finishes
43222 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-09-16 | 2026-09-19 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-08-28 |  | 2026-08-31 |  | Tower A | Super Structure | L63 | MEP | Electrical 2nd Fix - MEP & Finishes
43237 |  | Not Committed |  | 2026-09-16 | 2026-10-31 | MEP final fix & Finishes | 100 | 0 |  | 2026-08-28 |  | 2026-10-14
43238 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-09-16 | 2026-09-26 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-08-28 |  | 2026-09-05 |  | Tower A | Super Structure | L64 | Finishes | Door & Window Fixing
43255 |  | Not Committed |  | 2026-09-16 | 2026-10-31 | MEP final fix & Finishes | 100 | 0 |  | 2026-08-28 |  | 2026-10-14
43256 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-09-16 | 2026-09-26 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-08-28 |  | 2026-09-05 |  | Tower A | Super Structure | L65 | Finishes | Door & Window Fixing
43273 |  | Not Committed |  | 2026-09-16 | 2026-10-12 | MEP final fix & Finishes | 100 | 0 |  | 2026-08-28 |  | 2026-09-23
43274 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-09-16 | 2026-09-23 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-08-28 |  | 2026-09-02 |  | Tower A | Super Structure | L66 | Finishes | Door & Window Fixing
46858 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-05-30 | 2026-06-16 | Wet Area Waterproofing | 100 | 0 |  | 2026-08-28 |  | 2026-09-16 |  | Tower B | Super Structure | L18
41942 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-08-22 | 2026-08-25 | FAPA Cabling | 100 | 0 |  | 2026-08-29 |  | 2026-09-01 |  | Tower A | Super Structure | L62
43081 | Tower A - Super Structure - Finishes & MEP - L55 to L56 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-09-18 | 2026-09-21 | Painting Works | 100 | 0 |  | 2026-08-29 |  | 2026-09-01 |  | Tower A | Super Structure | L55 | Finishes | Painting Works
43099 | Tower A - Super Structure - Finishes & MEP - L56 to L57 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-09-18 | 2026-09-21 | Painting Works | 100 | 0 |  | 2026-08-29 |  | 2026-09-01 |  | Tower A | Super Structure | L56 | Finishes | Painting Works
43117 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-09-18 | 2026-09-21 | Painting Works | 100 | 0 |  | 2026-08-29 |  | 2026-09-01 |  | Tower A | Super Structure | L57 | Finishes | Painting Works
45484 | Tower B - Super Structure - Finishes & MEP - L19 to L20 | Not Ready | Partition Wall-Blockwork | 2026-06-04 | 2026-06-09 | Staircase Area | 100 | 0 |  | 2026-08-29 |  | 2026-09-04 |  | Tower B | Super Structure | L19
11472 | T-19-Lift Lobby | Not Ready |  | 2026-09-11 | 2026-09-28 | 05F | 100 | 0 |  | 2026-08-30 |  | 2026-09-17
12028 | T-18-Staircase 2 | Not Ready |  | 2026-11-06 | 2026-11-17 | GF-BF | 100 | 0 |  | 2026-08-30 |  | 2026-09-11
8890 | T-14-Staircase 1 | Not Ready |  | 2026-07-23 | 2026-08-03 | 03F-02F | 100 | 0 |  | 2026-08-31 |  | 2026-09-11
8904 | T-14-Staircase 2 | Not Ready |  | 2026-07-23 | 2026-08-03 | 04F-03F | 100 | 0 |  | 2026-08-31 |  | 2026-09-11
9428 | T-15-Staircase 2 | Not Ready |  | 2026-09-02 | 2026-09-14 | GF-BF | 100 | 0 |  | 2026-08-31 |  | 2026-09-11
41884 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-08-24 | 2026-08-27 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-08-31 |  | 2026-09-03 |  | Tower A | Super Structure | L58 | MEP | FPS 2nd Fix - MEP & Finishes
41885 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-08-24 | 2026-08-29 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-08-31 |  | 2026-09-05 |  | Tower A | Super Structure | L58 | MEP | Electrical 2nd Fix - MEP & Finishes
41886 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-08-24 | 2026-09-01 | FAPA Device Fixing | 100 | 0 |  | 2026-08-31 |  | 2026-09-09 |  | Tower A | Super Structure | L58
41886 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-08-24 | 2026-09-01 | FAPA Device Fixing | 100 | 0 |  | 2026-08-31 |  | 2026-09-09 |  | Tower A | Super Structure | L58
41886 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-08-24 | 2026-09-01 | FAPA Device Fixing | 100 | 0 |  | 2026-08-31 |  | 2026-09-09 |  | Tower A | Super Structure | L58
41886 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-08-24 | 2026-09-01 | FAPA Device Fixing | 100 | 0 |  | 2026-08-31 |  | 2026-09-09 |  | Tower A | Super Structure | L58
41887 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-08-24 | 2026-08-27 | HVAC Grill Fixing | 100 | 0 |  | 2026-08-31 |  | 2026-09-03 |  | Tower A | Super Structure | L58 | MEP | HVAC Grill Fixing
46841 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-06-05 | 2026-06-16 | Cement Plastering in wet areas | 100 | 0 |  | 2026-08-31 |  | 2026-09-11 |  | Tower B | Super Structure | L17
9394 | T-15-Lift Lobby | Not Ready |  | 2026-09-08 | 2026-09-24 | 03F | 100 | 0 |  | 2026-09-01 |  | 2026-09-16
11491 | T-19-Staircase 1 | Not Ready |  | 2026-09-05 | 2026-09-16 | 02F-01F | 100 | 0 |  | 2026-09-01 |  | 2026-09-10
11505 | T-19-Staircase 2 | Not Ready |  | 2026-09-05 | 2026-09-16 | 03F-02F | 100 | 0 |  | 2026-09-01 |  | 2026-09-10
41873 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-08-25 | 2026-08-31 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-09-01 |  | 2026-09-07 |  | Tower A | Super Structure | L57 | MEP | Electrical
41874 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-08-25 | 2026-08-31 | Final Painting | 100 | 0 |  | 2026-09-01 |  | 2026-09-07 |  | Tower A | Super Structure | L57 | Finishes | Final Painting
41874 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-08-25 | 2026-08-31 | Final Painting | 100 | 0 |  | 2026-09-01 |  | 2026-09-07 |  | Tower A | Super Structure | L57 | Finishes | Final Painting
41874 | Tower A - Super Structure - Finishes & MEP - L57 to L58 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-08-25 | 2026-08-31 | Final Painting | 100 | 0 |  | 2026-09-01 |  | 2026-09-07 |  | Tower A | Super Structure | L57 | Finishes | Final Painting
41943 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-08-25 | 2026-09-02 | HVAC Ducting | 100 | 0 |  | 2026-09-01 |  | 2026-09-10 |  | Tower A | Super Structure | L62 | MEP | HVAC Ducting
41956 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-08-25 | 2026-08-31 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-09-01 |  | 2026-09-07 |  | Tower A | Super Structure | L63 | MEP | FPS 1st Fix - MEP & Finishes
41957 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-08-25 | 2026-08-28 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-09-01 |  | 2026-09-04 |  | Tower A | Super Structure | L63 | MEP | Electrical 1st Fixes
43134 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-09-21 | 2026-09-24 | PHE Final Fixes | 100 | 0 |  | 2026-09-01 |  | 2026-09-03 |  | Tower A | Super Structure | L58
43152 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-09-21 | 2026-09-24 | PHE Final Fixes | 100 | 0 |  | 2026-09-01 |  | 2026-09-03 |  | Tower A | Super Structure | L59
43170 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-09-21 | 2026-09-24 | PHE Final Fixes | 100 | 0 |  | 2026-09-01 |  | 2026-09-03 |  | Tower A | Super Structure | L60
43187 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-09-21 | 2026-09-26 | False Ceiling | 100 | 0 |  | 2026-09-01 |  | 2026-09-05 |  | Tower A | Super Structure | L61 | Finishes | False Ceiling
43205 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-09-21 | 2026-09-26 | False Ceiling | 100 | 0 |  | 2026-09-01 |  | 2026-09-05 |  | Tower A | Super Structure | L62 | Finishes | False Ceiling
43223 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-09-21 | 2026-09-21 | False Ceiling | 100 | 0 |  | 2026-09-01 |  | 2026-09-01 |  | Tower A | Super Structure | L63 | Finishes | False Ceiling
45621 | Tower B - Super Structure - Finishes & MEP - L18 to L19 | Not Ready | Gypsum Plastering Works | 2026-06-03 | 2026-07-21 | L18-19 | 100 | 0 |  | 2026-09-01 |  | 2026-10-22 |  | Tower B | Super Structure | L18 | Finishes | Gypsum Plastering Works
45621 | Tower B - Super Structure - Finishes & MEP - L18 to L19 | Not Ready | Gypsum Plastering Works | 2026-06-03 | 2026-07-21 | L18-19 | 100 | 0 |  | 2026-09-01 |  | 2026-10-22 |  | Tower B | Super Structure | L18
46665 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-06-03 | 2026-07-01 | Flooring & Dado works | 100 | 0 |  | 2026-09-01 |  | 2026-10-03 |  | Tower B | Super Structure | L7 | Finishes | Flooring & Dado
43224 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-09-23 | 2026-09-23 | PHE Final Fixes | 100 | 0 |  | 2026-09-02 |  | 2026-09-02 |  | Tower A | Super Structure | L63
44233 | Tower A - Super Structure - Finishes & MEP - L45 to L55 | Not Ready | Hoist Corridor Finishes | 2026-08-25 | 2026-10-23 | L45-55 | 100 | 0 |  | 2026-09-02 |  | 2026-11-02 |  | Tower A | Super Structure | L45
44233 | Tower A - Super Structure - Finishes & MEP - L45 to L55 | Not Ready | Hoist Corridor Finishes | 2026-08-25 | 2026-10-23 | L45-55 | 100 | 0 |  | 2026-09-02 |  | 2026-11-02 |  | Tower A | Super Structure | L45
41888 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-08-27 | 2026-08-31 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-09-03 |  | 2026-09-07 |  | Tower A | Super Structure | L58
41915 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-08-27 | 2026-09-04 | False Ceiling | 100 | 0 |  | 2026-09-03 |  | 2026-09-12 |  | Tower A | Super Structure | L60 | Finishes | False Ceiling
41930 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-08-27 | 2026-09-09 | Flooring & Dado | 100 | 0 |  | 2026-09-03 |  | 2026-09-18 |  | Tower A | Super Structure | L61 | Finishes | Flooring & Dado
43225 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-09-24 | 2026-09-26 | Painting Works | 100 | 0 |  | 2026-09-03 |  | 2026-09-05 |  | Tower A | Super Structure | L63 | Finishes | Painting Works
43275 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-09-24 | 2026-09-26 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-09-03 |  | 2026-09-05 |  | Tower A | Super Structure | L66 | MEP | FPS 2nd Fix - MEP & Finishes
43276 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-09-24 | 2026-09-26 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-09-03 |  | 2026-09-05 |  | Tower A | Super Structure | L66 | MEP | Electrical 2nd Fix - MEP & Finishes
43291 |  | Not Committed |  | 2026-09-24 | 2026-10-17 | MEP final fix & Finishes | 100 | 0 |  | 2026-09-03 |  | 2026-09-30
43292 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-09-24 | 2026-09-30 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-09-03 |  | 2026-09-09 |  | Tower A | Super Structure | L67 | Finishes | Door & Window Fixing
43309 |  | Not Committed |  | 2026-09-24 | 2026-10-17 | MEP final fix & Finishes | 100 | 0 |  | 2026-09-03 |  | 2026-09-30
43310 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-09-24 | 2026-09-30 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-09-03 |  | 2026-09-09 |  | Tower A | Super Structure | L68 | Finishes | Door & Window Fixing
43327 |  | Not Committed |  | 2026-09-24 | 2026-10-17 | MEP final fix & Finishes | 100 | 0 |  | 2026-09-03 |  | 2026-09-30
43328 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-09-24 | 2026-09-30 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-09-03 |  | 2026-09-09 |  | Tower A | Super Structure | L69 | Finishes | Door & Window Fixing
44178 | Tower A - Super Structure - Finishes & MEP - L55 to L65 | Not Ready |  | 2026-08-26 | 2026-09-01 | Accessories & Alignment | 100 | 0 |  | 2026-09-03 |  | 2026-09-11 |  | Tower A | Super Structure | L55 | Façade | Façade Works
44178 | Tower A - Super Structure - Finishes & MEP - L55 to L65 | Not Ready |  | 2026-08-26 | 2026-09-01 | Accessories & Alignment | 100 | 0 |  | 2026-09-03 |  | 2026-09-11 |  | Tower A | Super Structure | L55
44181 | Tower A - Super Structure - Finishes & MEP - L65 to L77 | Not Ready |  | 2026-08-26 | 2026-09-02 | Glass Assembly Installation | 100 | 0 |  | 2026-09-03 |  | 2026-09-12 |  | Tower A | Super Structure | L65
44182 | Tower A - Super Structure - Finishes & MEP - L65 to L77 | Not Ready |  | 2026-08-26 | 2026-09-01 | ACP Sheet & Insulation fixing | 100 | 0 |  | 2026-09-03 |  | 2026-09-11 |  | Tower A | Super Structure | L65
44183 | Tower A - Super Structure - Finishes & MEP - L65 to L77 | Not Ready |  | 2026-08-26 | 2026-09-01 | Fixing of Louvers | 100 | 0 |  | 2026-09-03 |  | 2026-09-11 |  | Tower A | Super Structure | L65 | Façade | Façade Works
44183 | Tower A - Super Structure - Finishes & MEP - L65 to L77 | Not Ready |  | 2026-08-26 | 2026-09-01 | Fixing of Louvers | 100 | 0 |  | 2026-09-03 |  | 2026-09-11 |  | Tower A | Super Structure | L65
44221 | Tower A - Super Structure - Finishes & MEP - L55 to L65 | Not Ready |  | 2026-08-26 | 2026-09-01 | Accessories & Alignment | 100 | 0 |  | 2026-09-03 |  | 2026-09-11 |  | Tower A | Super Structure | L55 | Façade | Façade Works
44221 | Tower A - Super Structure - Finishes & MEP - L55 to L65 | Not Ready |  | 2026-08-26 | 2026-09-01 | Accessories & Alignment | 100 | 0 |  | 2026-09-03 |  | 2026-09-11 |  | Tower A | Super Structure | L55
44224 | Tower A - Super Structure - Finishes & MEP - L65 to L77 | Not Ready |  | 2026-08-26 | 2026-09-02 | Glass Assembly Installation | 100 | 0 |  | 2026-09-03 |  | 2026-09-12 |  | Tower A | Super Structure | L65
44225 | Tower A - Super Structure - Finishes & MEP - L65 to L77 | Not Ready |  | 2026-08-26 | 2026-09-01 | ACP Sheet & Insulation fixing | 100 | 0 |  | 2026-09-03 |  | 2026-09-11 |  | Tower A | Super Structure | L65
44226 | Tower A - Super Structure - Finishes & MEP - L65 to L77 | Not Ready |  | 2026-08-26 | 2026-09-01 | Fixing of Louvers | 100 | 0 |  | 2026-09-03 |  | 2026-09-11 |  | Tower A | Super Structure | L65 | Façade | Façade Works
44226 | Tower A - Super Structure - Finishes & MEP - L65 to L77 | Not Ready |  | 2026-08-26 | 2026-09-01 | Fixing of Louvers | 100 | 0 |  | 2026-09-03 |  | 2026-09-11 |  | Tower A | Super Structure | L65
45322 |  | Not Ready |  | 2026-06-02 | 2026-06-12 | L24-25 | 100 | 0 |  | 2026-09-03 |  | 2026-09-21
45322 |  | Not Ready |  | 2026-06-02 | 2026-06-12 | L24-25 | 100 | 0 |  | 2026-09-03 |  | 2026-09-21 |  |  |  |  | Finishes | Gypsum Plastering Works
45323 | Tower B - Super Structure - Core & Outer Slab L24-25 | Not Ready | RCC Works - Vertical | 2026-06-02 | 2026-06-10 | Outer Columns_TA | 100 | 0 |  | 2026-09-03 |  | 2026-09-16 |  | Tower B | Super Structure | L24 | RCC Sub Structure | RCC Works - Vertical
45489 |  | Not Committed |  | 2026-06-02 | 2026-07-02 | L21-22 | 100 | 0 |  | 2026-09-03 |  | 2026-10-08
45489 |  | Not Committed |  | 2026-06-02 | 2026-07-02 | L21-22 | 100 | 0 |  | 2026-09-03 |  | 2026-10-08 |  |  |  |  | Finishes | Gypsum Plastering Works
45490 | Tower B - Super Structure - Finishes & MEP - L21 to L22 | Not Ready | Partition Wall-Blockwork | 2026-06-02 | 2026-06-18 | De-shuttering & Area clearance | 100 | 0 |  | 2026-09-03 |  | 2026-09-23 |  | Tower B | Super Structure | L21
48091 | Retail | Not Ready |  | 2026-05-07 | 2026-08-28 | Sub-Station Retail | 100 | 0 |  | 2026-09-03 |  | 2026-12-21 |  | Retail | --
48092 | Retail | Not Ready |  | 2026-05-07 | 2026-08-28 | DG Retail | 100 | 0 |  | 2026-09-03 |  | 2026-12-21 |  | Retail | --
48100 | Clubhouse | Not Ready |  | 2026-05-07 | 2026-08-28 | Club House Lifts (3 Nos.) | 100 | 0 |  | 2026-09-03 |  | 2026-12-21 |  | Club House | -- | --
41958 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-08-28 | 2026-08-31 | FAPA Cabling | 100 | 0 |  | 2026-09-04 |  | 2026-09-07 |  | Tower A | Super Structure | L63
43135 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-09-25 | 2026-09-28 | Painting Works | 100 | 0 |  | 2026-09-04 |  | 2026-09-07 |  | Tower A | Super Structure | L58 | Finishes | Painting Works
43153 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-09-25 | 2026-09-28 | Painting Works | 100 | 0 |  | 2026-09-04 |  | 2026-09-07 |  | Tower A | Super Structure | L59 | Finishes | Painting Works
43171 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-09-25 | 2026-09-28 | Painting Works | 100 | 0 |  | 2026-09-04 |  | 2026-09-07 |  | Tower A | Super Structure | L60 | Finishes | Painting Works
46682 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-06-06 | 2026-06-13 | Door & Window Frame work | 100 | 0 |  | 2026-09-04 |  | 2026-09-12 |  | Tower B | Super Structure | L8 | Finishes | Door & Window Frame work
46698 |  | Not Committed |  | 2026-06-06 | 2026-08-01 | Finishes after 1st Fix | 100 | 0 |  | 2026-09-04 |  | 2026-10-30
46699 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-06-06 | 2026-06-17 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-09-04 |  | 2026-09-18 |  | Tower B | Super Structure | L9 | Finishes | Blockwork
46871 |  | Not Committed |  | 2026-06-10 | 2027-07-05 | L19-20 | 100 | 0 |  | 2026-09-04 |  | 2027-08-12
46871 |  | Not Committed |  | 2026-06-10 | 2027-07-05 | L19-20 | 100 | 0 |  | 2026-09-04 |  | 2027-08-12 |  |  |  |  | Finishes | Gypsum Plastering Works
46872 |  | Not Committed |  | 2026-06-10 | 2026-07-17 | MEP 1st Fixes | 100 | 0 |  | 2026-09-04 |  | 2026-10-15
46873 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-06-10 | 2026-06-17 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-09-04 |  | 2026-09-12 |  | Tower B | Super Structure | L19 | MEP | FPS 1st Fix - MEP & Finishes
46874 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-06-10 | 2026-06-15 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-09-04 |  | 2026-09-10 |  | Tower B | Super Structure | L19 | MEP | Electrical 1st Fixes
46875 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-06-10 | 2026-06-17 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-09-04 |  | 2026-09-12 |  | Tower B | Super Structure | L19
41900 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-08-29 | 2026-09-02 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-09-05 |  | 2026-09-10 |  | Tower A | Super Structure | L59 | MEP | FPS 2nd Fix - MEP & Finishes
41901 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-08-29 | 2026-09-04 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-09-05 |  | 2026-09-12 |  | Tower A | Super Structure | L59 | MEP | Electrical 2nd Fix - MEP & Finishes
41902 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-08-29 | 2026-09-07 | FAPA Device Fixing | 100 | 0 |  | 2026-09-05 |  | 2026-09-16 |  | Tower A | Super Structure | L59
41902 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-08-29 | 2026-09-07 | FAPA Device Fixing | 100 | 0 |  | 2026-09-05 |  | 2026-09-16 |  | Tower A | Super Structure | L59
41902 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-08-29 | 2026-09-07 | FAPA Device Fixing | 100 | 0 |  | 2026-09-05 |  | 2026-09-16 |  | Tower A | Super Structure | L59
41902 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-08-29 | 2026-09-07 | FAPA Device Fixing | 100 | 0 |  | 2026-09-05 |  | 2026-09-16 |  | Tower A | Super Structure | L59
41903 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-08-29 | 2026-09-02 | HVAC Grill Fixing | 100 | 0 |  | 2026-09-05 |  | 2026-09-10 |  | Tower A | Super Structure | L59 | MEP | HVAC Grill Fixing
45487 | Tower B - Super Structure - Finishes & MEP - L20 to L21 | Not Ready | Partition Wall-Blockwork | 2026-06-08 | 2026-06-15 | Partition Walls | 100 | 0 |  | 2026-09-05 |  | 2026-09-14 |  | Tower B | Super Structure | L20
8863 | T-14-Lift | Not Ready | Waterproofing | 2026-08-14 | 2026-11-24 | Waterproofing | 100 | 0 |  | 2026-09-06 |  | 2026-12-15
9930 | T-16-Staircase 1 | Not Ready |  | 2026-09-16 | 2026-09-27 | 03F-02F | 100 | 0 |  | 2026-09-06 |  | 2026-09-18
9944 | T-16-Staircase 2 | Not Ready |  | 2026-09-16 | 2026-09-27 | 04F-03F | 100 | 0 |  | 2026-09-06 |  | 2026-09-18
11195 | T-19-1st Floor Common Area | Not Ready | 2nd Coat Painting | 2026-09-26 | 2026-10-30 | 2nd Coat Painting | 100 | 0 |  | 2026-09-07 |  | 2026-10-10
41889 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-08-31 | 2026-09-05 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-09-07 |  | 2026-09-14 |  | Tower A | Super Structure | L58 | MEP | Electrical
41890 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-08-31 | 2026-09-05 | Final Painting | 100 | 0 |  | 2026-09-07 |  | 2026-09-14 |  | Tower A | Super Structure | L58 | Finishes | Final Painting
41890 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-08-31 | 2026-09-05 | Final Painting | 100 | 0 |  | 2026-09-07 |  | 2026-09-14 |  | Tower A | Super Structure | L58 | Finishes | Final Painting
41890 | Tower A - Super Structure - Finishes & MEP - L58 to L59 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-08-31 | 2026-09-05 | Final Painting | 100 | 0 |  | 2026-09-07 |  | 2026-09-14 |  | Tower A | Super Structure | L58 | Finishes | Final Painting
41959 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-08-31 | 2026-09-09 | HVAC Ducting | 100 | 0 |  | 2026-09-07 |  | 2026-09-18 |  | Tower A | Super Structure | L63 | MEP | HVAC Ducting
41972 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-08-31 | 2026-09-05 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-09-07 |  | 2026-09-14 |  | Tower A | Super Structure | L64 | MEP | FPS 1st Fix - MEP & Finishes
41973 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-08-31 | 2026-09-03 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-09-07 |  | 2026-09-11 |  | Tower A | Super Structure | L64 | MEP | Electrical 1st Fixes
43188 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-09-28 | 2026-10-01 | PHE Final Fixes | 100 | 0 |  | 2026-09-07 |  | 2026-09-10 |  | Tower A | Super Structure | L61
43206 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-09-28 | 2026-10-01 | PHE Final Fixes | 100 | 0 |  | 2026-09-07 |  | 2026-09-10 |  | Tower A | Super Structure | L62
43239 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-09-28 | 2026-10-07 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-09-07 |  | 2026-09-16 |  | Tower A | Super Structure | L64 | MEP | FPS 2nd Fix - MEP & Finishes
43240 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-09-28 | 2026-10-07 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-09-07 |  | 2026-09-16 |  | Tower A | Super Structure | L64 | MEP | Electrical 2nd Fix - MEP & Finishes
43257 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-09-28 | 2026-10-07 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-09-07 |  | 2026-09-16 |  | Tower A | Super Structure | L65 | MEP | FPS 2nd Fix - MEP & Finishes
43258 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-09-28 | 2026-10-07 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-09-07 |  | 2026-09-16 |  | Tower A | Super Structure | L65 | MEP | Electrical 2nd Fix - MEP & Finishes
43277 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-09-28 | 2026-10-05 | False Ceiling | 100 | 0 |  | 2026-09-07 |  | 2026-09-12 |  | Tower A | Super Structure | L66 | Finishes | False Ceiling
40105 | Tower A - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2026-08-25 | 2026-09-11 | FAPA Device Fixing | 100 | 0 |  | 2026-09-09 |  | 2026-10-01 |  | Tower A | Super Structure
40105 | Tower A - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2026-08-25 | 2026-09-11 | FAPA Device Fixing | 100 | 0 |  | 2026-09-09 |  | 2026-10-01 |  | Tower A | Super Structure
40105 | Tower A - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2026-08-25 | 2026-09-11 | FAPA Device Fixing | 100 | 0 |  | 2026-09-09 |  | 2026-10-01 |  | Tower A | Super Structure
40105 | Tower A - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2026-08-25 | 2026-09-11 | FAPA Device Fixing | 100 | 0 |  | 2026-09-09 |  | 2026-10-01 |  | Tower A | Super Structure
44256 |  | Not Ready | Interior Fit-out | 2026-09-30 | 2026-12-10 | Furniture works | 100 | 0 |  | 2026-09-09 |  | 2026-11-24
48250 | Retail - Super structure - CH01 to CH02 | Not Ready |  | 2026-05-13 | 2026-09-03 | CH01-CH02 (P5-6) | 100 | 0 |  | 2026-09-09 |  | 2026-12-28 |  | Retail | Super Structure | CH01
10437 | T-21-Lift Lobby | Not Ready |  | 2026-10-10 | 2026-10-27 | GF | 100 | 0 |  | 2026-09-10 |  | 2026-09-28
41904 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-09-02 | 2026-09-05 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-09-10 |  | 2026-09-14 |  | Tower A | Super Structure | L59
41931 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-09-02 | 2026-09-11 | False Ceiling | 100 | 0 |  | 2026-09-10 |  | 2026-09-21 |  | Tower A | Super Structure | L61 | Finishes | False Ceiling
41946 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-09-02 | 2026-09-16 | Flooring & Dado | 100 | 0 |  | 2026-09-10 |  | 2026-09-25 |  | Tower A | Super Structure | L62 | Finishes | Flooring & Dado
43241 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-10-01 | 2026-10-19 | False Ceiling | 100 | 0 |  | 2026-09-10 |  | 2026-10-01 |  | Tower A | Super Structure | L64 | Finishes | False Ceiling
43259 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-10-01 | 2026-10-19 | False Ceiling | 100 | 0 |  | 2026-09-10 |  | 2026-10-01 |  | Tower A | Super Structure | L65 | Finishes | False Ceiling
43293 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-10-01 | 2026-10-05 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-09-10 |  | 2026-09-12 |  | Tower A | Super Structure | L67 | MEP | FPS 2nd Fix - MEP & Finishes
43294 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-10-01 | 2026-10-05 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-09-10 |  | 2026-09-12 |  | Tower A | Super Structure | L67 | MEP | Electrical 2nd Fix - MEP & Finishes
43311 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-10-01 | 2026-10-05 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-09-10 |  | 2026-09-12 |  | Tower A | Super Structure | L68 | MEP | FPS 2nd Fix - MEP & Finishes
43312 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-10-01 | 2026-10-05 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-09-10 |  | 2026-09-12 |  | Tower A | Super Structure | L68 | MEP | Electrical 2nd Fix - MEP & Finishes
43329 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-10-01 | 2026-10-05 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-09-10 |  | 2026-09-12 |  | Tower A | Super Structure | L69 | MEP | FPS 2nd Fix - MEP & Finishes
43330 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-10-01 | 2026-10-05 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-09-10 |  | 2026-09-12 |  | Tower A | Super Structure | L69 | MEP | Electrical 2nd Fix - MEP & Finishes
43345 |  | Not Committed |  | 2026-10-01 | 2026-10-24 | MEP final fix & Finishes | 100 | 0 |  | 2026-09-10 |  | 2026-10-07
43346 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-10-01 | 2026-10-07 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-09-10 |  | 2026-09-16 |  | Tower A | Super Structure | L70 | Finishes | Door & Window Fixing
43363 |  | Not Committed |  | 2026-10-01 | 2026-10-24 | MEP final fix & Finishes | 100 | 0 |  | 2026-09-10 |  | 2026-10-07
43364 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-10-01 | 2026-10-07 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-09-10 |  | 2026-09-16 |  | Tower A | Super Structure | L71 | Finishes | Door & Window Fixing
43381 |  | Not Committed |  | 2026-10-01 | 2026-10-24 | MEP final fix & Finishes | 100 | 0 |  | 2026-09-10 |  | 2026-10-07
43382 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-10-01 | 2026-10-07 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-09-10 |  | 2026-09-16 |  | Tower A | Super Structure | L72 | Finishes | Door & Window Fixing
45324 | Tower B - Super Structure - Core & Outer Slab L24-25 | Not Ready | RCC Works - Slab | 2026-06-06 | 2026-06-12 | Outer Slab_TA with Wall Reductions | 100 | 0 |  | 2026-09-10 |  | 2026-09-21 |  | Tower B | Super Structure | L24 | RCC Sub Structure | RCC Works - Slab
47414 |  | Not Committed |  | 2026-06-12 | 2026-08-13 | L13-18 | 100 | 0 |  | 2026-09-10 |  | 2026-11-06
47415 | Tower B - Super Structure - Finishes & MEP - L13 to L18 | Not Ready | Façade Works - MEP & Finishes | 2026-06-12 | 2026-07-04 | Al. Frame section (Mullion & Transom) Installation | 100 | 0 |  | 2026-09-10 |  | 2026-10-07 |  | Tower B | Super Structure | L13 | Façade | Façade Works
48061 |  | Not Committed |  | 2026-05-14 | 2026-10-23 | Retails Façade | 100 | 0 |  | 2026-09-10 |  | 2027-01-29
48062 |  | Not Committed |  | 2026-05-14 | 2026-10-23 | GF to CH00 | 100 | 0 |  | 2026-09-10 |  | 2027-01-29
48063 |  | Not Committed |  | 2026-05-14 | 2026-06-30 | dwg RT-02,07,09 | 100 | 0 |  | 2026-09-10 |  | 2026-10-30
48064 |  | Not Ready |  | 2026-05-14 | 2026-06-01 | Erection of Vertical steel tube with folded steel sheet | 100 | 0 |  | 2026-09-10 |  | 2026-09-29
11463 | T-19-Lift | Not Ready | Waterproofing | 2026-10-06 | 2027-01-14 | Waterproofing | 100 | 0 |  | 2026-09-11 |  | 2026-12-22
11492 | T-19-Staircase 1 | Not Ready |  | 2026-09-16 | 2026-09-28 | 01F-GF | 100 | 0 |  | 2026-09-11 |  | 2026-09-23
11506 | T-19-Staircase 2 | Not Ready |  | 2026-09-16 | 2026-09-28 | 02F-01F | 100 | 0 |  | 2026-09-11 |  | 2026-09-23
12035 |  | Not Ready |  | 2026-12-08 | 2027-03-18 | De-Snagging & Handing Over | 100 | 0 |  | 2026-09-11 |  | 2026-12-19
41974 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-09-03 | 2026-09-05 | FAPA Cabling | 100 | 0 |  | 2026-09-11 |  | 2026-09-14 |  | Tower A | Super Structure | L64
43189 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-03 | 2026-10-06 | Painting Works | 100 | 0 |  | 2026-09-11 |  | 2026-09-14 |  | Tower A | Super Structure | L61 | Finishes | Painting Works
43207 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-03 | 2026-10-06 | Painting Works | 100 | 0 |  | 2026-09-11 |  | 2026-09-14 |  | Tower A | Super Structure | L62 | Finishes | Painting Works
44234 | Tower A - Super Structure - Finishes & MEP - L55 to L65 | Not Ready | Hoist Corridor Finishes | 2026-09-02 | 2026-10-31 | L55-65 | 100 | 0 |  | 2026-09-11 |  | 2026-11-10 |  | Tower A | Super Structure | L55
44234 | Tower A - Super Structure - Finishes & MEP - L55 to L65 | Not Ready | Hoist Corridor Finishes | 2026-09-02 | 2026-10-31 | L55-65 | 100 | 0 |  | 2026-09-11 |  | 2026-11-10 |  | Tower A | Super Structure | L55
47698 |  | Complete |  | 2026-09-11 | 2026-10-07 | Slab_NTA | 100 | 100 |  | 2026-09-11 | 2025-01-31 | 2026-10-07 | 2025-01-31
47698 |  | Complete |  | 2026-09-11 | 2026-10-07 | Slab_NTA | 100 | 100 |  | 2026-09-11 | 2025-01-31 | 2026-10-07 | 2025-01-31 |  |  |  | RCC Sub Structure | RCC Works - Slab
48233 | Retail & Clubhouse - Sub structure - B3 to B2 | Not Ready |  | 2026-03-28 | 2026-04-15 | MEP Rooms - Plaster & IPS | 100 | 0 |  | 2026-09-11 |  | 2026-10-01 |  | Club House | Sub Structure | B3
48233 | Retail & Clubhouse - Sub structure - B3 to B2 | Not Ready |  | 2026-03-28 | 2026-04-15 | MEP Rooms - Plaster & IPS | 100 | 0 |  | 2026-09-11 |  | 2026-10-01 |  | Club House | Sub Structure | B3
48234 | Retail & Clubhouse - Sub structure - B3 to B2 | Not Ready |  | 2026-03-28 | 2026-04-21 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2026-09-11 |  | 2026-10-08 |  | Club House | Sub Structure | B3
48234 | Retail & Clubhouse - Sub structure - B3 to B2 | Not Ready |  | 2026-03-28 | 2026-04-21 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2026-09-11 |  | 2026-10-08 |  | Club House | Sub Structure | B3
8891 | T-14-Staircase 1 | Not Ready |  | 2026-08-03 | 2026-08-14 | 02F-01F | 100 | 0 |  | 2026-09-12 |  | 2026-09-25
8905 | T-14-Staircase 2 | Not Ready |  | 2026-08-03 | 2026-08-14 | 03F-02F | 100 | 0 |  | 2026-09-12 |  | 2026-09-25
41916 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-09-04 | 2026-09-09 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-09-12 |  | 2026-09-18 |  | Tower A | Super Structure | L60 | MEP | FPS 2nd Fix - MEP & Finishes
41917 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-09-04 | 2026-09-11 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-09-12 |  | 2026-09-21 |  | Tower A | Super Structure | L60 | MEP | Electrical 2nd Fix - MEP & Finishes
41918 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-09-04 | 2026-09-14 | FAPA Device Fixing | 100 | 0 |  | 2026-09-12 |  | 2026-09-24 |  | Tower A | Super Structure | L60
41918 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-09-04 | 2026-09-14 | FAPA Device Fixing | 100 | 0 |  | 2026-09-12 |  | 2026-09-24 |  | Tower A | Super Structure | L60
41918 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-09-04 | 2026-09-14 | FAPA Device Fixing | 100 | 0 |  | 2026-09-12 |  | 2026-09-24 |  | Tower A | Super Structure | L60
41918 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-09-04 | 2026-09-14 | FAPA Device Fixing | 100 | 0 |  | 2026-09-12 |  | 2026-09-24 |  | Tower A | Super Structure | L60
41919 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-09-04 | 2026-09-09 | HVAC Grill Fixing | 100 | 0 |  | 2026-09-12 |  | 2026-09-18 |  | Tower A | Super Structure | L60 | MEP | HVAC Grill Fixing
44184 | Tower A - Super Structure - Finishes & MEP - L65 to L77 | Not Ready |  | 2026-09-03 | 2026-09-10 | Accessories & Alignment | 100 | 0 |  | 2026-09-12 |  | 2026-09-23 |  | Tower A | Super Structure | L65 | Façade | Façade Works
44184 | Tower A - Super Structure - Finishes & MEP - L65 to L77 | Not Ready |  | 2026-09-03 | 2026-09-10 | Accessories & Alignment | 100 | 0 |  | 2026-09-12 |  | 2026-09-23 |  | Tower A | Super Structure | L65
44227 | Tower A - Super Structure - Finishes & MEP - L65 to L77 | Not Ready |  | 2026-09-03 | 2026-09-10 | Accessories & Alignment | 100 | 0 |  | 2026-09-12 |  | 2026-09-23 |  | Tower A | Super Structure | L65 | Façade | Façade Works
44227 | Tower A - Super Structure - Finishes & MEP - L65 to L77 | Not Ready |  | 2026-09-03 | 2026-09-10 | Accessories & Alignment | 100 | 0 |  | 2026-09-12 |  | 2026-09-23 |  | Tower A | Super Structure | L65
46683 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-06-15 | 2026-07-14 | Flooring & Dado works | 100 | 0 |  | 2026-09-12 |  | 2026-10-15 |  | Tower B | Super Structure | L8 | Finishes | Flooring & Dado
46701 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-06-15 | 2026-07-14 | Flooring & Dado works | 100 | 0 |  | 2026-09-12 |  | 2026-10-15 |  | Tower B | Super Structure | L9 | Finishes | Flooring & Dado
46876 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-06-18 | 2026-07-04 | Wet Area Waterproofing | 100 | 0 |  | 2026-09-12 |  | 2026-10-03 |  | Tower B | Super Structure | L19
9912 | T-16-Lift Lobby | Not Ready |  | 2026-10-03 | 2026-10-20 | 05F | 100 | 0 |  | 2026-09-13 |  | 2026-10-02
10956 | T-20-Lift Lobby | Not Ready |  | 2026-10-06 | 2026-10-22 | 01F | 100 | 0 |  | 2026-09-14 |  | 2026-09-30
41905 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-09-05 | 2026-09-12 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-09-14 |  | 2026-09-23 |  | Tower A | Super Structure | L59 | MEP | Electrical
41906 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-09-05 | 2026-09-12 | Final Painting | 100 | 0 |  | 2026-09-14 |  | 2026-09-23 |  | Tower A | Super Structure | L59 | Finishes | Final Painting
41906 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-09-05 | 2026-09-12 | Final Painting | 100 | 0 |  | 2026-09-14 |  | 2026-09-23 |  | Tower A | Super Structure | L59 | Finishes | Final Painting
41906 | Tower A - Super Structure - Finishes & MEP - L59 to L60 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-09-05 | 2026-09-12 | Final Painting | 100 | 0 |  | 2026-09-14 |  | 2026-09-23 |  | Tower A | Super Structure | L59 | Finishes | Final Painting
41975 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-09-05 | 2026-09-16 | HVAC Ducting | 100 | 0 |  | 2026-09-14 |  | 2026-09-25 |  | Tower A | Super Structure | L64 | MEP | HVAC Ducting
41988 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-09-05 | 2026-09-12 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-09-14 |  | 2026-09-23 |  | Tower A | Super Structure | L65 | MEP | FPS 1st Fix - MEP & Finishes
41989 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-09-05 | 2026-09-10 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-09-14 |  | 2026-09-19 |  | Tower A | Super Structure | L65 | MEP | Electrical 1st Fixes
43278 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-10-06 | 2026-10-08 | PHE Final Fixes | 100 | 0 |  | 2026-09-14 |  | 2026-09-18 |  | Tower A | Super Structure | L66
43295 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-10-06 | 2026-10-10 | False Ceiling | 100 | 0 |  | 2026-09-14 |  | 2026-09-21 |  | Tower A | Super Structure | L67 | Finishes | False Ceiling
43313 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-10-06 | 2026-10-10 | False Ceiling | 100 | 0 |  | 2026-09-14 |  | 2026-09-21 |  | Tower A | Super Structure | L68 | Finishes | False Ceiling
43331 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-10-06 | 2026-10-10 | False Ceiling | 100 | 0 |  | 2026-09-14 |  | 2026-09-21 |  | Tower A | Super Structure | L69 | Finishes | False Ceiling
45488 | Tower B - Super Structure - Finishes & MEP - L20 to L21 | Not Ready | Partition Wall-Blockwork | 2026-06-16 | 2026-06-20 | Staircase Area | 100 | 0 |  | 2026-09-14 |  | 2026-09-22 |  | Tower B | Super Structure | L20
8872 | T-14-Lift Lobby | Not Ready |  | 2026-08-08 | 2026-08-26 | 05F | 100 | 0 |  | 2026-09-15 |  | 2026-10-02
11995 | T-18-Lift Lobby | Not Ready |  | 2026-11-28 | 2026-12-15 | 02F | 100 | 0 |  | 2026-09-15 |  | 2026-10-01
9661 | T-16-2nd Floor Common Area | Not Ready | 2nd Coat Painting | 2026-10-01 | 2026-11-05 | 2nd Coat Painting | 100 | 0 |  | 2026-09-16 |  | 2026-10-20
44270 |  | Not Ready |  | 2026-08-25 | 2026-09-04 | Exhaust & Pressurization System Commissioning | 100 | 0 |  | 2026-09-16 |  | 2026-10-19
46859 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-06-17 | 2026-06-27 | Cement Plastering in wet areas | 100 | 0 |  | 2026-09-16 |  | 2026-09-29 |  | Tower B | Super Structure | L18
9395 | T-15-Lift Lobby | Not Ready |  | 2026-09-24 | 2026-10-12 | 02F | 100 | 0 |  | 2026-09-17 |  | 2026-10-05
11473 | T-19-Lift Lobby | Not Ready |  | 2026-09-28 | 2026-10-15 | 04F | 100 | 0 |  | 2026-09-18 |  | 2026-10-03
39273 | Retail - Super structure - GF to R1 | Not Ready | RCC Works - Slab | 2026-03-20 | 2026-04-13 | Slab_RT | 100 | 0 |  | 2026-09-18 |  | 2026-10-12 |  | Retail | Super Structure | GF | RCC Sub Structure | RCC Works - Slab
39273 | Retail - Super structure - GF to R1 | Not Ready | RCC Works - Slab | 2026-03-20 | 2026-04-13 | Slab_RT | 100 | 0 |  | 2026-09-18 |  | 2026-10-12 |  | Retail | Super Structure | GF
41920 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-09-09 | 2026-09-12 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-09-18 |  | 2026-09-23 |  | Tower A | Super Structure | L60
41947 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-09-09 | 2026-09-19 | False Ceiling | 100 | 0 |  | 2026-09-18 |  | 2026-09-28 |  | Tower A | Super Structure | L62 | Finishes | False Ceiling
41962 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-09-09 | 2026-09-24 | Flooring & Dado | 100 | 0 |  | 2026-09-18 |  | 2026-10-03 |  | Tower A | Super Structure | L63 | Finishes | Flooring & Dado
42175 |  | Not Committed |  | 2026-10-08 | 2026-10-30 | MEP final fix & Finishes | 100 | 0 |  | 2026-09-18 |  | 2026-10-13
42176 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-10-08 | 2026-10-13 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-09-18 |  | 2026-09-24 |  | Tower A | Super Structure | L75 | Finishes | Door & Window Fixing
42193 |  | Not Committed |  | 2026-10-08 | 2026-10-30 | MEP final fix & Finishes | 100 | 0 |  | 2026-09-18 |  | 2026-10-13
42194 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-10-08 | 2026-10-13 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-09-18 |  | 2026-09-24 |  | Tower A | Super Structure | L76 | Finishes | Door & Window Fixing
43347 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-10-08 | 2026-10-10 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-09-18 |  | 2026-09-21 |  | Tower A | Super Structure | L70 | MEP | FPS 2nd Fix - MEP & Finishes
43348 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-10-08 | 2026-10-10 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-09-18 |  | 2026-09-21 |  | Tower A | Super Structure | L70 | MEP | Electrical 2nd Fix - MEP & Finishes
43365 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-10-08 | 2026-10-10 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-09-18 |  | 2026-09-21 |  | Tower A | Super Structure | L71 | MEP | FPS 2nd Fix - MEP & Finishes
43366 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-10-08 | 2026-10-10 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-09-18 |  | 2026-09-21 |  | Tower A | Super Structure | L71 | MEP | Electrical 2nd Fix - MEP & Finishes
43383 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-10-08 | 2026-10-10 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-09-18 |  | 2026-09-21 |  | Tower A | Super Structure | L72 | MEP | FPS 2nd Fix - MEP & Finishes
43384 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-10-08 | 2026-10-10 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-09-18 |  | 2026-09-21 |  | Tower A | Super Structure | L72 | MEP | Electrical 2nd Fix - MEP & Finishes
43399 |  | Not Committed |  | 2026-10-08 | 2026-10-30 | MEP final fix & Finishes | 100 | 0 |  | 2026-09-18 |  | 2026-10-13
43400 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-10-08 | 2026-10-13 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-09-18 |  | 2026-09-24 |  | Tower A | Super Structure | L73 | Finishes | Door & Window Fixing
43417 |  | Not Committed |  | 2026-10-08 | 2026-10-30 | MEP final fix & Finishes | 100 | 0 |  | 2026-09-18 |  | 2026-10-13
43418 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-10-08 | 2026-10-13 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-09-18 |  | 2026-09-24 |  | Tower A | Super Structure | L74 | Finishes | Door & Window Fixing
43435 |  | Not Committed |  | 2026-10-08 | 2026-10-30 | MEP final fix & Finishes | 100 | 0 |  | 2026-09-18 |  | 2026-10-13
43436 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-10-08 | 2026-10-13 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2026-09-18 |  | 2026-09-24 |  | Tower A | Super Structure | L77 | Finishes | Door & Window Fixing
45622 | Tower B - Super Structure - Finishes & MEP - L19 to L20 | Not Ready | Gypsum Plastering Works | 2026-06-22 | 2026-08-12 | L19-20 | 100 | 0 |  | 2026-09-18 |  | 2026-11-06 |  | Tower B | Super Structure | L19 | Finishes | Gypsum Plastering Works
45622 | Tower B - Super Structure - Finishes & MEP - L19 to L20 | Not Ready | Gypsum Plastering Works | 2026-06-22 | 2026-08-12 | L19-20 | 100 | 0 |  | 2026-09-18 |  | 2026-11-06 |  | Tower B | Super Structure | L19
46700 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-06-18 | 2026-06-25 | Door & Window Frame work | 100 | 0 |  | 2026-09-18 |  | 2026-09-26 |  | Tower B | Super Structure | L9 | Finishes | Door & Window Frame work
46716 |  | Not Committed |  | 2026-06-18 | 2026-08-25 | Finishes after 1st Fix | 100 | 0 |  | 2026-09-18 |  | 2026-11-11
46717 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-06-18 | 2026-06-29 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-09-18 |  | 2026-09-30 |  | Tower B | Super Structure | L10 | Finishes | Blockwork
9931 | T-16-Staircase 1 | Not Ready |  | 2026-09-27 | 2026-10-09 | 02F-01F | 100 | 0 |  | 2026-09-19 |  | 2026-09-30
9945 | T-16-Staircase 2 | Not Ready |  | 2026-09-27 | 2026-10-09 | 03F-02F | 100 | 0 |  | 2026-09-19 |  | 2026-09-30
41990 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-09-10 | 2026-09-12 | FAPA Cabling | 100 | 0 |  | 2026-09-19 |  | 2026-09-23 |  | Tower A | Super Structure | L65
43279 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-09 | 2026-10-12 | Painting Works | 100 | 0 |  | 2026-09-19 |  | 2026-09-23 |  | Tower A | Super Structure | L66 | Finishes | Painting Works
41932 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-09-11 | 2026-09-16 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-09-21 |  | 2026-09-25 |  | Tower A | Super Structure | L61 | MEP | FPS 2nd Fix - MEP & Finishes
41933 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-09-11 | 2026-09-19 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-09-21 |  | 2026-09-28 |  | Tower A | Super Structure | L61 | MEP | Electrical 2nd Fix - MEP & Finishes
41934 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-09-11 | 2026-09-23 | FAPA Device Fixing | 100 | 0 |  | 2026-09-21 |  | 2026-10-01 |  | Tower A | Super Structure | L61
41934 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-09-11 | 2026-09-23 | FAPA Device Fixing | 100 | 0 |  | 2026-09-21 |  | 2026-10-01 |  | Tower A | Super Structure | L61
41934 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-09-11 | 2026-09-23 | FAPA Device Fixing | 100 | 0 |  | 2026-09-21 |  | 2026-10-01 |  | Tower A | Super Structure | L61
41934 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-09-11 | 2026-09-23 | FAPA Device Fixing | 100 | 0 |  | 2026-09-21 |  | 2026-10-01 |  | Tower A | Super Structure | L61
41935 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-09-11 | 2026-09-16 | HVAC Grill Fixing | 100 | 0 |  | 2026-09-21 |  | 2026-09-25 |  | Tower A | Super Structure | L61 | MEP | HVAC Grill Fixing
45325 |  | Not Ready |  | 2026-06-13 | 2026-06-24 | L25-26 | 100 | 0 |  | 2026-09-21 |  | 2026-10-07
45325 |  | Not Ready |  | 2026-06-13 | 2026-06-24 | L25-26 | 100 | 0 |  | 2026-09-21 |  | 2026-10-07 |  |  |  |  | Finishes | Gypsum Plastering Works
45326 | Tower B - Super Structure - Core & Outer Slab L25-26 | Not Ready | RCC Works - Vertical | 2026-06-13 | 2026-06-22 | Outer Columns_TA | 100 | 0 |  | 2026-09-21 |  | 2026-10-03 |  | Tower B | Super Structure | L25 | RCC Sub Structure | RCC Works - Vertical
45493 |  | Not Committed |  | 2026-06-13 | 2026-07-15 | L22-23 | 100 | 0 |  | 2026-09-21 |  | 2026-10-24
45493 |  | Not Committed |  | 2026-06-13 | 2026-07-15 | L22-23 | 100 | 0 |  | 2026-09-21 |  | 2026-10-24 |  |  |  |  | Finishes | Gypsum Plastering Works
45494 | Tower B - Super Structure - Finishes & MEP - L22 to L23 | Not Ready | Partition Wall-Blockwork | 2026-06-13 | 2026-06-30 | De-shuttering & Area clearance | 100 | 0 |  | 2026-09-21 |  | 2026-10-09 |  | Tower B | Super Structure | L22
45740 |  | Not Committed |  | 2026-06-13 | 2026-10-22 | L15-25 | 100 | 0 |  | 2026-09-21 |  | 2027-01-07
45740 |  | Not Committed |  | 2026-06-13 | 2026-10-22 | L15-25 | 100 | 0 |  | 2026-09-21 |  | 2027-01-07
45741 | Tower B - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2026-06-13 | 2026-07-06 | FHR Shaft Risers | 100 | 0 |  | 2026-09-21 |  | 2026-10-15 |  | Tower B | Super Structure | L15
45743 | Tower B - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2026-06-13 | 2026-08-08 | Domestic Water & Flushing Riser in Plumbing Shaft | 100 | 0 |  | 2026-09-21 |  | 2026-11-14 |  | Tower B | Super Structure | L15
45745 | Tower B - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2026-06-13 | 2026-07-18 | Shaft Cable Tray in Electrical Shaft | 100 | 0 |  | 2026-09-21 |  | 2026-10-28 |  | Tower B | Super Structure | L15
9435 |  | Not Ready | De-Snagging & Handing Over | 2026-10-05 | 2027-01-13 | De-Snagging & Handing Over | 100 | 0 |  | 2026-09-22 |  | 2027-01-03
46889 |  | Not Committed |  | 2026-06-22 | 2027-07-19 | L20-21 (Refuge) (MEP Transfer) | 100 | 0 |  | 2026-09-22 |  | 2027-08-24
46890 |  | Not Committed |  | 2026-06-22 | 2026-08-06 | MEP 1st Fixes | 100 | 0 |  | 2026-09-22 |  | 2026-10-31
46891 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-06-22 | 2026-06-29 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-09-22 |  | 2026-09-30 |  | Tower B | Super Structure | L20 | MEP | FPS 1st Fix - MEP & Finishes
46892 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-06-22 | 2026-06-26 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-09-22 |  | 2026-09-28 |  | Tower B | Super Structure | L20 | MEP | Electrical 1st Fixes
46893 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-06-22 | 2026-06-29 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-09-22 |  | 2026-09-30 |  | Tower B | Super Structure | L20
41921 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-09-12 | 2026-09-21 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-09-23 |  | 2026-09-30 |  | Tower A | Super Structure | L60 | MEP | Electrical
41922 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-09-12 | 2026-09-21 | Final Painting | 100 | 0 |  | 2026-09-23 |  | 2026-09-30 |  | Tower A | Super Structure | L60 | Finishes | Final Painting
41922 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-09-12 | 2026-09-21 | Final Painting | 100 | 0 |  | 2026-09-23 |  | 2026-09-30 |  | Tower A | Super Structure | L60 | Finishes | Final Painting
41922 | Tower A - Super Structure - Finishes & MEP - L60 to L61 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-09-12 | 2026-09-21 | Final Painting | 100 | 0 |  | 2026-09-23 |  | 2026-09-30 |  | Tower A | Super Structure | L60 | Finishes | Final Painting
41991 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-09-12 | 2026-09-24 | HVAC Ducting | 100 | 0 |  | 2026-09-23 |  | 2026-10-03 |  | Tower A | Super Structure | L65 | MEP | HVAC Ducting
42004 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-09-12 | 2026-09-21 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-09-23 |  | 2026-09-30 |  | Tower A | Super Structure | L66 | MEP | FPS 1st Fix - MEP & Finishes
42005 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-09-12 | 2026-09-18 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-09-23 |  | 2026-09-26 |  | Tower A | Super Structure | L66 | MEP | Electrical 1st Fixes
43296 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-10-12 | 2026-10-14 | PHE Final Fixes | 100 | 0 |  | 2026-09-23 |  | 2026-09-25 |  | Tower A | Super Structure | L67
43314 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-10-12 | 2026-10-14 | PHE Final Fixes | 100 | 0 |  | 2026-09-23 |  | 2026-09-25 |  | Tower A | Super Structure | L68
43332 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-10-12 | 2026-10-14 | PHE Final Fixes | 100 | 0 |  | 2026-09-23 |  | 2026-09-25 |  | Tower A | Super Structure | L69
43349 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-10-12 | 2026-10-16 | False Ceiling | 100 | 0 |  | 2026-09-23 |  | 2026-09-28 |  | Tower A | Super Structure | L70 | Finishes | False Ceiling
43367 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-10-12 | 2026-10-16 | False Ceiling | 100 | 0 |  | 2026-09-23 |  | 2026-09-28 |  | Tower A | Super Structure | L71 | Finishes | False Ceiling
43385 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-10-12 | 2026-10-16 | False Ceiling | 100 | 0 |  | 2026-09-23 |  | 2026-09-28 |  | Tower A | Super Structure | L72 | Finishes | False Ceiling
44235 | Tower A - Super Structure - Finishes & MEP - L65 to L77 | Not Ready | Hoist Corridor Finishes | 2026-09-11 | 2026-11-09 | L65-Terrace | 100 | 0 |  | 2026-09-23 |  | 2026-11-18 |  | Tower A | Super Structure | L65
44235 | Tower A - Super Structure - Finishes & MEP - L65 to L77 | Not Ready | Hoist Corridor Finishes | 2026-09-11 | 2026-11-09 | L65-Terrace | 100 | 0 |  | 2026-09-23 |  | 2026-11-18 |  | Tower A | Super Structure | L65
45491 | Tower B - Super Structure - Finishes & MEP - L21 to L22 | Not Ready | Partition Wall-Blockwork | 2026-06-19 | 2026-06-26 | Partition Walls | 100 | 0 |  | 2026-09-23 |  | 2026-10-01 |  | Tower B | Super Structure | L21
47547 |  | Not Committed |  | 2026-02-21 | 2026-03-26 | Pour 7 (grid PB-K to PB-N) | 100 | 0 |  | 2026-09-23 |  | 2026-10-28
47548 |  | Not Ready |  | 2026-02-21 | 2026-02-24 | Dressing & PCC | 100 | 0 |  | 2026-09-23 |  | 2026-09-26
47548 |  | Not Ready |  | 2026-02-21 | 2026-02-24 | Dressing & PCC | 100 | 0 |  | 2026-09-23 |  | 2026-09-26 |  |  |  |  | RCC Super Structure | Foundation RCC Works
47548 |  | Not Ready |  | 2026-02-21 | 2026-02-24 | Dressing & PCC | 100 | 0 |  | 2026-09-23 |  | 2026-09-26 |  |  |  |  | RCC Sub Structure | Raft RCC Works
48227 | Club House - Super structure - CH02 to CH03 | Not Ready |  | 2026-05-25 | 2026-06-29 | CH02-CH03 | 100 | 0 |  | 2026-09-23 |  | 2026-10-29 |  | Club House | Super Structure | CH02
11493 | T-19-Staircase 1 | Not Ready |  | 2026-09-28 | 2026-10-09 | GF-BF | 100 | 0 |  | 2026-09-24 |  | 2026-10-06
11507 | T-19-Staircase 2 | Not Ready |  | 2026-09-28 | 2026-10-09 | 01F-GF | 100 | 0 |  | 2026-09-24 |  | 2026-10-06
48065 |  | Not Ready |  | 2026-05-26 | 2026-06-12 | Aluminum sheet wrapping + Al. boxing | 100 | 0 |  | 2026-09-24 |  | 2026-10-12
41936 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-09-16 | 2026-09-21 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-09-25 |  | 2026-09-30 |  | Tower A | Super Structure | L61
41963 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-09-16 | 2026-09-26 | False Ceiling | 100 | 0 |  | 2026-09-25 |  | 2026-10-06 |  | Tower A | Super Structure | L63 | Finishes | False Ceiling
41978 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-09-16 | 2026-10-01 | Flooring & Dado | 100 | 0 |  | 2026-09-25 |  | 2026-10-09 |  | Tower A | Super Structure | L64 | Finishes | Flooring & Dado
42177 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-10-14 | 2026-10-16 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-09-25 |  | 2026-09-28 |  | Tower A | Super Structure | L75 | MEP | FPS 2nd Fix - MEP & Finishes
42178 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-10-14 | 2026-10-16 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-09-25 |  | 2026-09-28 |  | Tower A | Super Structure | L75 | MEP | Electrical 2nd Fix - MEP & Finishes
42195 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-10-14 | 2026-10-16 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-09-25 |  | 2026-09-28 |  | Tower A | Super Structure | L76 | MEP | FPS 2nd Fix - MEP & Finishes
42196 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-10-14 | 2026-10-16 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-09-25 |  | 2026-09-28 |  | Tower A | Super Structure | L76 | MEP | Electrical 2nd Fix - MEP & Finishes
43401 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-10-14 | 2026-10-16 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-09-25 |  | 2026-09-28 |  | Tower A | Super Structure | L73 | MEP | FPS 2nd Fix - MEP & Finishes
43402 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-10-14 | 2026-10-16 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-09-25 |  | 2026-09-28 |  | Tower A | Super Structure | L73 | MEP | Electrical 2nd Fix - MEP & Finishes
43419 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-10-14 | 2026-10-16 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-09-25 |  | 2026-09-28 |  | Tower A | Super Structure | L74 | MEP | FPS 2nd Fix - MEP & Finishes
43420 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-10-14 | 2026-10-16 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-09-25 |  | 2026-09-28 |  | Tower A | Super Structure | L74 | MEP | Electrical 2nd Fix - MEP & Finishes
43437 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-10-14 | 2026-10-16 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-09-25 |  | 2026-09-28 |  | Tower A | Super Structure | L77 | MEP | FPS 2nd Fix - MEP & Finishes
43438 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-10-14 | 2026-10-16 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-09-25 |  | 2026-09-28 |  | Tower A | Super Structure | L77 | MEP | Electrical 2nd Fix - MEP & Finishes
8892 | T-14-Staircase 1 | Not Ready |  | 2026-08-14 | 2026-08-26 | 01F-GF | 100 | 0 |  | 2026-09-26 |  | 2026-10-06
8906 | T-14-Staircase 2 | Not Ready |  | 2026-08-14 | 2026-08-26 | 02F-01F | 100 | 0 |  | 2026-09-26 |  | 2026-10-06
42006 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-09-18 | 2026-09-21 | FAPA Cabling | 100 | 0 |  | 2026-09-26 |  | 2026-09-30 |  | Tower A | Super Structure | L66
43297 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-15 | 2026-10-17 | Painting Works | 100 | 0 |  | 2026-09-26 |  | 2026-09-30 |  | Tower A | Super Structure | L67 | Finishes | Painting Works
43315 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-15 | 2026-10-17 | Painting Works | 100 | 0 |  | 2026-09-26 |  | 2026-09-30 |  | Tower A | Super Structure | L68 | Finishes | Painting Works
43333 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-15 | 2026-10-17 | Painting Works | 100 | 0 |  | 2026-09-26 |  | 2026-09-30 |  | Tower A | Super Structure | L69 | Finishes | Painting Works
46719 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-06-26 | 2026-07-28 | Flooring & Dado works | 100 | 0 |  | 2026-09-26 |  | 2026-10-28 |  | Tower B | Super Structure | L10 | Finishes | Flooring & Dado
47549 |  | Not Ready |  | 2026-02-25 | 2026-02-27 | Liner Wall | 100 | 0 |  | 2026-09-26 |  | 2026-09-30
47549 |  | Not Ready |  | 2026-02-25 | 2026-02-27 | Liner Wall | 100 | 0 |  | 2026-09-26 |  | 2026-09-30 |  |  |  |  | RCC Super Structure | Foundation RCC Works
47549 |  | Not Ready |  | 2026-02-25 | 2026-02-27 | Liner Wall | 100 | 0 |  | 2026-09-26 |  | 2026-09-30 |  |  |  |  | RCC Sub Structure | Raft RCC Works
47550 |  | Not Ready |  | 2026-02-25 | 2026-03-02 | Waterproofing Horizontal-toe area | 100 | 0 |  | 2026-09-26 |  | 2026-10-03
47556 |  | Not Committed |  | 2026-02-25 | 2026-04-01 | Pour 8 (grid PB-D to PB-K) | 100 | 0 |  | 2026-09-26 |  | 2026-11-03
47557 |  | Not Ready |  | 2026-02-25 | 2026-02-27 | Dressing & PCC | 100 | 0 |  | 2026-09-26 |  | 2026-09-30
47557 |  | Not Ready |  | 2026-02-25 | 2026-02-27 | Dressing & PCC | 100 | 0 |  | 2026-09-26 |  | 2026-09-30 |  |  |  |  | RCC Super Structure | Foundation RCC Works
47557 |  | Not Ready |  | 2026-02-25 | 2026-02-27 | Dressing & PCC | 100 | 0 |  | 2026-09-26 |  | 2026-09-30 |  |  |  |  | RCC Sub Structure | Raft RCC Works
41948 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-09-19 | 2026-09-24 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-09-28 |  | 2026-10-03 |  | Tower A | Super Structure | L62 | MEP | FPS 2nd Fix - MEP & Finishes
41949 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-09-19 | 2026-09-26 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-09-28 |  | 2026-10-06 |  | Tower A | Super Structure | L62 | MEP | Electrical 2nd Fix - MEP & Finishes
41950 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-09-19 | 2026-09-30 | FAPA Device Fixing | 100 | 0 |  | 2026-09-28 |  | 2026-10-08 |  | Tower A | Super Structure | L62
41950 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-09-19 | 2026-09-30 | FAPA Device Fixing | 100 | 0 |  | 2026-09-28 |  | 2026-10-08 |  | Tower A | Super Structure | L62
41950 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-09-19 | 2026-09-30 | FAPA Device Fixing | 100 | 0 |  | 2026-09-28 |  | 2026-10-08 |  | Tower A | Super Structure | L62
41950 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-09-19 | 2026-09-30 | FAPA Device Fixing | 100 | 0 |  | 2026-09-28 |  | 2026-10-08 |  | Tower A | Super Structure | L62
41951 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-09-19 | 2026-09-24 | HVAC Grill Fixing | 100 | 0 |  | 2026-09-28 |  | 2026-10-03 |  | Tower A | Super Structure | L62 | MEP | HVAC Grill Fixing
44562 | NTA_Zone 2 - Super Structure - GF to P1 | Not Ready | Finishes (Lobby & Floor Area) | 2026-02-16 | 2026-03-11 | MEP Rooms - Plaster & IPS | 100 | 0 |  | 2026-09-28 |  | 2026-10-22 |  | NTA_Zone 2 | Super Structure | GF
44562 | NTA_Zone 2 - Super Structure - GF to P1 | Not Ready | Finishes (Lobby & Floor Area) | 2026-02-16 | 2026-03-11 | MEP Rooms - Plaster & IPS | 100 | 0 |  | 2026-09-28 |  | 2026-10-22 |  | NTA_Zone 2 | Super Structure | GF
44563 | NTA_Zone 2 - Super Structure - GF to P1 | Not Ready | Finishes (Lobby & Floor Area) | 2026-02-16 | 2026-03-23 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2026-09-28 |  | 2026-11-03 |  | NTA_Zone 2 | Super Structure | GF
44563 | NTA_Zone 2 - Super Structure - GF to P1 | Not Ready | Finishes (Lobby & Floor Area) | 2026-02-16 | 2026-03-23 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2026-09-28 |  | 2026-11-03 |  | NTA_Zone 2 | Super Structure | GF
44634 |  | Not Committed |  | 2026-02-16 | 2026-10-24 | External Balustrade System (Ext 401, 802, 901) | 100 | 0 |  | 2026-09-28 |  | 2027-03-26
44641 |  | Not Committed |  | 2026-02-16 | 2026-04-09 | P1 level | 100 | 0 |  | 2026-09-28 |  | 2026-11-09
44642 | NTA_Zone 2 - Super Structure - P1 to P2 | Not Ready | External Balustrade System | 2026-02-16 | 2026-03-17 | RCC upstand | 100 | 0 |  | 2026-09-28 |  | 2026-10-15 |  | NTA_Zone 2 | Super Structure
44642 | NTA_Zone 2 - Super Structure - P1 to P2 | Not Ready | External Balustrade System | 2026-02-16 | 2026-03-17 | RCC upstand | 100 | 0 |  | 2026-09-28 |  | 2026-10-15 |  | NTA_Zone 2 | Super Structure
45327 | Tower B - Super Structure - Core & Outer Slab L25-26 | Not Ready | RCC Works - Slab | 2026-06-18 | 2026-06-24 | Outer Slab_TA | 100 | 0 |  | 2026-09-28 |  | 2026-10-07 |  | Tower B | Super Structure | L25 | RCC Sub Structure | RCC Works - Slab
10438 | T-21-Lift Lobby | Not Ready |  | 2026-10-27 | 2026-11-13 | BF | 100 | 0 |  | 2026-09-29 |  | 2026-10-14
8915 |  | Not Ready | De-Snagging & Handing Over | 2026-09-10 | 2026-12-20 | De-Snagging & Handing Over | 100 | 0 |  | 2026-09-30 |  | 2027-01-07
41937 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-09-21 | 2026-09-28 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-09-30 |  | 2026-10-07 |  | Tower A | Super Structure | L61 | MEP | Electrical
41938 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-09-21 | 2026-09-28 | Final Painting | 100 | 0 |  | 2026-09-30 |  | 2026-10-07 |  | Tower A | Super Structure | L61 | Finishes | Final Painting
41938 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-09-21 | 2026-09-28 | Final Painting | 100 | 0 |  | 2026-09-30 |  | 2026-10-07 |  | Tower A | Super Structure | L61 | Finishes | Final Painting
41938 | Tower A - Super Structure - Finishes & MEP - L61 to L62 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-09-21 | 2026-09-28 | Final Painting | 100 | 0 |  | 2026-09-30 |  | 2026-10-07 |  | Tower A | Super Structure | L61 | Finishes | Final Painting
42007 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-09-21 | 2026-10-01 | HVAC Ducting | 100 | 0 |  | 2026-09-30 |  | 2026-10-09 |  | Tower A | Super Structure | L66 | MEP | HVAC Ducting
42020 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-09-21 | 2026-09-28 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-09-30 |  | 2026-10-07 |  | Tower A | Super Structure | L67 | MEP | FPS 1st Fix - MEP & Finishes
42021 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-09-21 | 2026-09-25 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-09-30 |  | 2026-10-05 |  | Tower A | Super Structure | L67 | MEP | Electrical 1st Fixes
42179 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-10-17 | 2026-10-23 | False Ceiling | 100 | 0 |  | 2026-09-30 |  | 2026-10-06 |  | Tower A | Super Structure | L75 | Finishes | False Ceiling
42197 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-10-17 | 2026-10-23 | False Ceiling | 100 | 0 |  | 2026-09-30 |  | 2026-10-06 |  | Tower A | Super Structure | L76 | Finishes | False Ceiling
43350 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-10-17 | 2026-10-21 | PHE Final Fixes | 100 | 0 |  | 2026-09-30 |  | 2026-10-03 |  | Tower A | Super Structure | L70
43368 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-10-17 | 2026-10-21 | PHE Final Fixes | 100 | 0 |  | 2026-09-30 |  | 2026-10-03 |  | Tower A | Super Structure | L71
43386 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-10-17 | 2026-10-21 | PHE Final Fixes | 100 | 0 |  | 2026-09-30 |  | 2026-10-03 |  | Tower A | Super Structure | L72
43403 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-10-17 | 2026-10-23 | False Ceiling | 100 | 0 |  | 2026-09-30 |  | 2026-10-06 |  | Tower A | Super Structure | L73 | Finishes | False Ceiling
43421 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-10-17 | 2026-10-23 | False Ceiling | 100 | 0 |  | 2026-09-30 |  | 2026-10-06 |  | Tower A | Super Structure | L74 | Finishes | False Ceiling
43439 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-10-17 | 2026-10-23 | False Ceiling | 100 | 0 |  | 2026-09-30 |  | 2026-10-06 |  | Tower A | Super Structure | L77 | Finishes | False Ceiling
46718 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-06-30 | 2026-07-07 | Door & Window Frame work | 100 | 0 |  | 2026-09-30 |  | 2026-10-09 |  | Tower B | Super Structure | L10 | Finishes | Door & Window Frame work
46734 |  | Not Committed |  | 2026-06-30 | 2026-09-10 | Finishes after 1st Fix | 100 | 0 |  | 2026-09-30 |  | 2026-11-23
46735 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-06-30 | 2026-07-10 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-09-30 |  | 2026-10-13 |  | Tower B | Super Structure | L11 | Finishes | Blockwork
46894 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-06-30 | 2026-07-17 | Wet Area Waterproofing | 100 | 0 |  | 2026-09-30 |  | 2026-10-19 |  | Tower B | Super Structure | L20
47551 |  | Not Ready |  | 2026-02-28 | 2026-03-02 | Waterproofing vertical - toe ht. | 100 | 0 |  | 2026-09-30 |  | 2026-10-03
47551 |  | Not Ready |  | 2026-02-28 | 2026-03-02 | Waterproofing vertical - toe ht. | 100 | 0 |  | 2026-09-30 |  | 2026-10-03 |  |  |  |  | RCC Super Structure | Foundation RCC Works
47551 |  | Not Ready |  | 2026-02-28 | 2026-03-02 | Waterproofing vertical - toe ht. | 100 | 0 |  | 2026-09-30 |  | 2026-10-03 |  |  |  |  | RCC Sub Structure | Raft RCC Works
47558 |  | Not Ready |  | 2026-02-28 | 2026-03-06 | Liner Wall | 100 | 0 |  | 2026-09-30 |  | 2026-10-07
47558 |  | Not Ready |  | 2026-02-28 | 2026-03-06 | Liner Wall | 100 | 0 |  | 2026-09-30 |  | 2026-10-07 |  |  |  |  | RCC Super Structure | Foundation RCC Works
47558 |  | Not Ready |  | 2026-02-28 | 2026-03-06 | Liner Wall | 100 | 0 |  | 2026-09-30 |  | 2026-10-07 |  |  |  |  | RCC Sub Structure | Raft RCC Works
47559 |  | Not Ready |  | 2026-02-28 | 2026-03-06 | Waterproofing Horizontal-toe area | 100 | 0 |  | 2026-09-30 |  | 2026-10-07
48068 |  | Not Committed |  | 2026-06-02 | 2026-07-25 | dwg RT-04,03 | 100 | 0 |  | 2026-09-30 |  | 2026-11-23
48069 |  | Not Ready |  | 2026-06-02 | 2026-06-18 | Floor-Horizontal Al. add-on profile+Horizontal steel tube+Insulation+Al. sheet boxing | 100 | 0 |  | 2026-09-30 |  | 2026-10-17
48085 |  | Not Committed |  | 2026-06-02 | 2026-10-31 | Club House Façade | 100 | 0 |  | 2026-09-30 |  | 2027-02-20
48086 | Club House - Super structure - CH00 to CH01 | Not Ready |  | 2026-06-02 | 2026-09-24 | CH00-CH01 | 100 | 0 |  | 2026-09-30 |  | 2027-01-15 |  | Club House | Super Structure | CH00
9635 | T-16-1st Floor Common Area | Not Ready | 2nd Coat Painting | 2026-10-19 | 2026-11-22 | 2nd Coat Painting | 100 | 0 |  | 2026-10-01 |  | 2026-10-31
9903 | T-16-Lift | Not Ready | Waterproofing | 2026-10-28 | 2027-02-06 | Waterproofing | 100 | 0 |  | 2026-10-01 |  | 2027-01-08
9932 | T-16-Staircase 1 | Not Ready |  | 2026-10-09 | 2026-10-20 | 01F-GF | 100 | 0 |  | 2026-10-01 |  | 2026-10-14
9946 | T-16-Staircase 2 | Not Ready |  | 2026-10-09 | 2026-10-20 | 02F-01F | 100 | 0 |  | 2026-10-01 |  | 2026-10-14
10957 | T-20-Lift Lobby | Not Ready |  | 2026-10-22 | 2026-11-09 | GF | 100 | 0 |  | 2026-10-01 |  | 2026-10-19
40106 | Tower A - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2026-09-12 | 2026-09-24 | Fire Mode Testing | 100 | 0 |  | 2026-10-01 |  | 2026-10-12 |  | Tower A | Super Structure
44278 |  | Not Ready |  | 2026-09-12 | 2026-10-10 | STP Commissioning | 100 | 0 |  | 2026-10-01 |  | 2026-10-27
45492 | Tower B - Super Structure - Finishes & MEP - L21 to L22 | Not Ready | Partition Wall-Blockwork | 2026-06-27 | 2026-07-02 | Staircase Area | 100 | 0 |  | 2026-10-01 |  | 2026-10-08 |  | Tower B | Super Structure | L21
11996 | T-18-Lift Lobby | Not Ready |  | 2026-12-15 | 2026-12-31 | 01F | 100 | 0 |  | 2026-10-02 |  | 2026-10-19
8873 | T-14-Lift Lobby | Not Ready |  | 2026-08-26 | 2026-09-11 | 04F | 100 | 0 |  | 2026-10-03 |  | 2026-10-18
9913 | T-16-Lift Lobby | Not Ready |  | 2026-10-20 | 2026-11-06 | 04F | 100 | 0 |  | 2026-10-03 |  | 2026-10-17
41952 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-09-24 | 2026-09-28 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-10-03 |  | 2026-10-07 |  | Tower A | Super Structure | L62
41979 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-09-24 | 2026-10-05 | False Ceiling | 100 | 0 |  | 2026-10-03 |  | 2026-10-12 |  | Tower A | Super Structure | L64 | Finishes | False Ceiling
41994 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-09-24 | 2026-10-08 | Flooring & Dado | 100 | 0 |  | 2026-10-03 |  | 2026-10-15 |  | Tower A | Super Structure | L65 | Finishes | Flooring & Dado
43242 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-10-21 | 2026-10-26 | PHE Final Fixes | 100 | 0 |  | 2026-10-03 |  | 2026-10-08 |  | Tower A | Super Structure | L64
43260 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-10-21 | 2026-10-26 | PHE Final Fixes | 100 | 0 |  | 2026-10-03 |  | 2026-10-08 |  | Tower A | Super Structure | L65
46666 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-07-02 | 2026-07-16 | False Ceiling | 100 | 0 |  | 2026-10-03 |  | 2026-10-17 |  | Tower B | Super Structure | L7 | Finishes | False Ceiling
46877 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-07-06 | 2026-07-17 | Cement Plastering in wet areas | 100 | 0 |  | 2026-10-03 |  | 2026-10-15 |  | Tower B | Super Structure | L19
47552 |  | Not Ready |  | 2026-03-04 | 2026-03-09 | RW toe foundation | 100 | 0 |  | 2026-10-03 |  | 2026-10-09
47552 |  | Not Ready |  | 2026-03-04 | 2026-03-09 | RW toe foundation | 100 | 0 |  | 2026-10-03 |  | 2026-10-09 |  |  |  |  | RCC Super Structure | Foundation RCC Works
47552 |  | Not Ready |  | 2026-03-04 | 2026-03-09 | RW toe foundation | 100 | 0 |  | 2026-10-03 |  | 2026-10-09 |  |  |  |  | RCC Sub Structure | Raft RCC Works
47553 |  | Not Ready |  | 2026-03-04 | 2026-03-09 | Waterproofing-Raft Area | 100 | 0 |  | 2026-10-03 |  | 2026-10-09
11474 | T-19-Lift Lobby | Not Ready |  | 2026-10-15 | 2026-11-02 | 03F | 100 | 0 |  | 2026-10-04 |  | 2026-10-22
42022 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-09-25 | 2026-09-28 | FAPA Cabling | 100 | 0 |  | 2026-10-05 |  | 2026-10-07 |  | Tower A | Super Structure | L67
43351 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-22 | 2026-10-24 | Painting Works | 100 | 0 |  | 2026-10-05 |  | 2026-10-07 |  | Tower A | Super Structure | L70 | Finishes | Painting Works
43369 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-22 | 2026-10-24 | Painting Works | 100 | 0 |  | 2026-10-05 |  | 2026-10-07 |  | Tower A | Super Structure | L71 | Finishes | Painting Works
43387 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-22 | 2026-10-24 | Painting Works | 100 | 0 |  | 2026-10-05 |  | 2026-10-07 |  | Tower A | Super Structure | L72 | Finishes | Painting Works
44643 | NTA_Zone 2 - Super Structure - P1 to P2 | Not Ready | External Balustrade System | 2026-03-06 | 2026-03-23 | Drainage pipe | 100 | 0 |  | 2026-10-05 |  | 2026-10-22 |  | NTA_Zone 2 | Super Structure
44643 | NTA_Zone 2 - Super Structure - P1 to P2 | Not Ready | External Balustrade System | 2026-03-06 | 2026-03-23 | Drainage pipe | 100 | 0 |  | 2026-10-05 |  | 2026-10-22 |  | NTA_Zone 2 | Super Structure
45623 | Tower B - Super Structure - Finishes & MEP - L20 to L21 | Not Ready | Gypsum Plastering Works | 2026-07-03 | 2026-08-12 | L20-21 | 100 | 0 |  | 2026-10-05 |  | 2026-11-10 |  | Tower B | Super Structure | L20 | Finishes | Gypsum Plastering Works
45623 | Tower B - Super Structure - Finishes & MEP - L20 to L21 | Not Ready | Gypsum Plastering Works | 2026-07-03 | 2026-08-12 | L20-21 | 100 | 0 |  | 2026-10-05 |  | 2026-11-10 |  | Tower B | Super Structure | L20
48066 |  | Not Ready |  | 2026-06-05 | 2026-06-12 | Rockwool insulation work | 100 | 0 |  | 2026-10-05 |  | 2026-10-12
9396 | T-15-Lift Lobby | Not Ready |  | 2026-10-12 | 2026-10-28 | 01F | 100 | 0 |  | 2026-10-06 |  | 2026-10-22
41964 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-09-26 | 2026-10-01 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-10-06 |  | 2026-10-09 |  | Tower A | Super Structure | L63 | MEP | FPS 2nd Fix - MEP & Finishes
41965 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-09-26 | 2026-10-05 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-10-06 |  | 2026-10-12 |  | Tower A | Super Structure | L63 | MEP | Electrical 2nd Fix - MEP & Finishes
41966 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-09-26 | 2026-10-07 | FAPA Device Fixing | 100 | 0 |  | 2026-10-06 |  | 2026-10-14 |  | Tower A | Super Structure | L63
41966 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-09-26 | 2026-10-07 | FAPA Device Fixing | 100 | 0 |  | 2026-10-06 |  | 2026-10-14 |  | Tower A | Super Structure | L63
41966 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-09-26 | 2026-10-07 | FAPA Device Fixing | 100 | 0 |  | 2026-10-06 |  | 2026-10-14 |  | Tower A | Super Structure | L63
41966 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-09-26 | 2026-10-07 | FAPA Device Fixing | 100 | 0 |  | 2026-10-06 |  | 2026-10-14 |  | Tower A | Super Structure | L63
41967 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-09-26 | 2026-10-01 | HVAC Grill Fixing | 100 | 0 |  | 2026-10-06 |  | 2026-10-09 |  | Tower A | Super Structure | L63 | MEP | HVAC Grill Fixing
8893 | T-14-Staircase 1 | Not Ready |  | 2026-08-26 | 2026-09-06 | GF-BF | 100 | 0 |  | 2026-10-07 |  | 2026-10-16
8907 | T-14-Staircase 2 | Not Ready |  | 2026-08-26 | 2026-09-06 | 01F-GF | 100 | 0 |  | 2026-10-07 |  | 2026-10-16
11508 | T-19-Staircase 2 | Not Ready |  | 2026-10-09 | 2026-10-20 | GF-BF | 100 | 0 |  | 2026-10-07 |  | 2026-10-16
41953 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-09-28 | 2026-10-06 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-10-07 |  | 2026-10-13 |  | Tower A | Super Structure | L62 | MEP | Electrical
41954 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-09-28 | 2026-10-06 | Final Painting | 100 | 0 |  | 2026-10-07 |  | 2026-10-13 |  | Tower A | Super Structure | L62 | Finishes | Final Painting
41954 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-09-28 | 2026-10-06 | Final Painting | 100 | 0 |  | 2026-10-07 |  | 2026-10-13 |  | Tower A | Super Structure | L62 | Finishes | Final Painting
41954 | Tower A - Super Structure - Finishes & MEP - L62 to L63 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-09-28 | 2026-10-06 | Final Painting | 100 | 0 |  | 2026-10-07 |  | 2026-10-13 |  | Tower A | Super Structure | L62 | Finishes | Final Painting
42023 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-09-28 | 2026-10-08 | HVAC Ducting | 100 | 0 |  | 2026-10-07 |  | 2026-10-15 |  | Tower A | Super Structure | L67 | MEP | HVAC Ducting
42036 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-09-28 | 2026-10-06 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-10-07 |  | 2026-10-13 |  | Tower A | Super Structure | L68 | MEP | FPS 1st Fix - MEP & Finishes
42037 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-09-28 | 2026-10-03 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-10-07 |  | 2026-10-10 |  | Tower A | Super Structure | L68 | MEP | Electrical 1st Fixes
42180 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-10-24 | 2026-10-27 | PHE Final Fixes | 100 | 0 |  | 2026-10-07 |  | 2026-10-09 |  | Tower A | Super Structure | L75
42198 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-10-24 | 2026-10-27 | PHE Final Fixes | 100 | 0 |  | 2026-10-07 |  | 2026-10-09 |  | Tower A | Super Structure | L76
43404 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-10-24 | 2026-10-27 | PHE Final Fixes | 100 | 0 |  | 2026-10-07 |  | 2026-10-09 |  | Tower A | Super Structure | L73
43422 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-10-24 | 2026-10-27 | PHE Final Fixes | 100 | 0 |  | 2026-10-07 |  | 2026-10-09 |  | Tower A | Super Structure | L74
43440 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2026-10-24 | 2026-10-27 | PHE Final Fixes | 100 | 0 |  | 2026-10-07 |  | 2026-10-09 |  | Tower A | Super Structure | L77
45328 |  | Not Ready |  | 2026-06-25 | 2026-07-06 | L26-27 | 100 | 0 |  | 2026-10-07 |  | 2026-10-23
45328 |  | Not Ready |  | 2026-06-25 | 2026-07-06 | L26-27 | 100 | 0 |  | 2026-10-07 |  | 2026-10-23 |  |  |  |  | Finishes | Gypsum Plastering Works
45329 | Tower B - Super Structure - Core & Outer Slab L26-27 | Not Ready | RCC Works - Vertical | 2026-06-25 | 2026-07-03 | Outer Columns_TA | 100 | 0 |  | 2026-10-07 |  | 2026-10-19 |  | Tower B | Super Structure | L26 | RCC Sub Structure | RCC Works - Vertical
45497 |  | Not Committed |  | 2026-06-25 | 2026-08-06 | L23-24 | 100 | 0 |  | 2026-10-07 |  | 2026-11-09
45497 |  | Not Committed |  | 2026-06-25 | 2026-08-06 | L23-24 | 100 | 0 |  | 2026-10-07 |  | 2026-11-09 |  |  |  |  | Finishes | Gypsum Plastering Works
45498 | Tower B - Super Structure - Finishes & MEP - L23 to L24 | Not Ready | Partition Wall-Blockwork | 2026-06-25 | 2026-07-11 | De-shuttering & Area clearance | 100 | 0 |  | 2026-10-07 |  | 2026-10-26 |  | Tower B | Super Structure | L23
47416 | Tower B - Super Structure - Finishes & MEP - L13 to L18 | Not Ready | Façade Works - MEP & Finishes | 2026-07-06 | 2026-07-17 | DGU Assembly Installation | 100 | 0 |  | 2026-10-07 |  | 2026-10-19 |  | Tower B | Super Structure | L13 | Façade | Façade Works
47417 | Tower B - Super Structure - Finishes & MEP - L13 to L18 | Not Ready | Façade Works - MEP & Finishes | 2026-07-06 | 2026-08-07 | Installation of highly reflective metal sheet | 100 | 0 |  | 2026-10-07 |  | 2026-11-06 |  | Tower B | Super Structure | L13 | Façade | Façade Works
47418 | Tower B - Super Structure - Finishes & MEP - L13 to L18 | Not Ready | Façade Works - MEP & Finishes | 2026-07-06 | 2026-07-24 | Fixing of Backlit Laminated Glass assembly & ACP Panels | 100 | 0 |  | 2026-10-07 |  | 2026-10-26 |  | Tower B | Super Structure | L13 | Façade | Façade Works
47419 | Tower B - Super Structure - Finishes & MEP - L13 to L18 | Not Ready | Façade Works - MEP & Finishes | 2026-07-06 | 2026-07-24 | Fixing of Louvers | 100 | 0 |  | 2026-10-07 |  | 2026-10-26 |  | Tower B | Super Structure | L13 | Façade | Façade Works
47419 | Tower B - Super Structure - Finishes & MEP - L13 to L18 | Not Ready | Façade Works - MEP & Finishes | 2026-07-06 | 2026-07-24 | Fixing of Louvers | 100 | 0 |  | 2026-10-07 |  | 2026-10-26 |  | Tower B | Super Structure | L13
47560 |  | Not Ready |  | 2026-03-07 | 2026-03-09 | Waterproofing vertical - toe ht. | 100 | 0 |  | 2026-10-07 |  | 2026-10-09
47560 |  | Not Ready |  | 2026-03-07 | 2026-03-09 | Waterproofing vertical - toe ht. | 100 | 0 |  | 2026-10-07 |  | 2026-10-09 |  |  |  |  | RCC Super Structure | Foundation RCC Works
47560 |  | Not Ready |  | 2026-03-07 | 2026-03-09 | Waterproofing vertical - toe ht. | 100 | 0 |  | 2026-10-07 |  | 2026-10-09 |  |  |  |  | RCC Sub Structure | Raft RCC Works
46907 |  | Not Committed |  | 2026-07-03 | 2027-08-02 | L21-22 | 100 | 0 |  | 2026-10-08 |  | 2027-09-06
46907 |  | Not Committed |  | 2026-07-03 | 2027-08-02 | L21-22 | 100 | 0 |  | 2026-10-08 |  | 2027-09-06 |  |  |  |  | Finishes | Gypsum Plastering Works
46908 |  | Not Committed |  | 2026-07-03 | 2026-08-31 | MEP 1st Fixes | 100 | 0 |  | 2026-10-08 |  | 2026-11-16
46909 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-07-03 | 2026-07-10 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-10-08 |  | 2026-10-16 |  | Tower B | Super Structure | L21 | MEP | FPS 1st Fix - MEP & Finishes
46910 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-07-03 | 2026-07-08 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-10-08 |  | 2026-10-14 |  | Tower B | Super Structure | L21 | MEP | Electrical 1st Fixes
46911 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-07-03 | 2026-07-10 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-10-08 |  | 2026-10-16 |  | Tower B | Super Structure | L21
48235 | Retail & Clubhouse - Sub structure - B3 to B2 | Not Ready |  | 2026-04-21 | 2026-05-15 | Staircase Finishes | 100 | 0 |  | 2026-10-08 |  | 2026-11-02 |  | Club House | Sub Structure | B3
48235 | Retail & Clubhouse - Sub structure - B3 to B2 | Not Ready |  | 2026-04-21 | 2026-05-15 | Staircase Finishes | 100 | 0 |  | 2026-10-08 |  | 2026-11-02 |  | Club House | Sub Structure | B3
41968 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-10-01 | 2026-10-06 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-10-09 |  | 2026-10-13 |  | Tower A | Super Structure | L63
41995 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-10-01 | 2026-10-10 | False Ceiling | 100 | 0 |  | 2026-10-09 |  | 2026-10-17 |  | Tower A | Super Structure | L65 | Finishes | False Ceiling
42010 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-10-01 | 2026-10-14 | Flooring & Dado | 100 | 0 |  | 2026-10-09 |  | 2026-10-22 |  | Tower A | Super Structure | L66 | Finishes | Flooring & Dado
43243 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-27 | 2026-10-31 | Painting Works | 100 | 0 |  | 2026-10-09 |  | 2026-10-14 |  | Tower A | Super Structure | L64 | Finishes | Painting Works
43261 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-27 | 2026-10-31 | Painting Works | 100 | 0 |  | 2026-10-09 |  | 2026-10-14 |  | Tower A | Super Structure | L65 | Finishes | Painting Works
45495 | Tower B - Super Structure - Finishes & MEP - L22 to L23 | Not Ready | Partition Wall-Blockwork | 2026-07-01 | 2026-07-08 | Partition Walls | 100 | 0 |  | 2026-10-09 |  | 2026-10-17 |  | Tower B | Super Structure | L22
46737 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-07-08 | 2026-08-11 | Flooring & Dado works | 100 | 0 |  | 2026-10-09 |  | 2026-11-09 |  | Tower B | Super Structure | L11 | Finishes | Flooring & Dado
47554 |  | Not Ready |  | 2026-03-10 | 2026-03-20 | Raft & Footing Reinf_NTA | 100 | 0 |  | 2026-10-09 |  | 2026-10-22
47554 |  | Not Ready |  | 2026-03-10 | 2026-03-20 | Raft & Footing Reinf_NTA | 100 | 0 |  | 2026-10-09 |  | 2026-10-22 |  |  |  |  | RCC Super Structure | Foundation RCC Works
47554 |  | Not Ready |  | 2026-03-10 | 2026-03-20 | Raft & Footing Reinf_NTA | 100 | 0 |  | 2026-10-09 |  | 2026-10-22 |  |  |  |  | RCC Sub Structure | Raft RCC Works
47561 |  | Not Ready |  | 2026-03-10 | 2026-03-14 | RW toe foundation | 100 | 0 |  | 2026-10-09 |  | 2026-10-15
47561 |  | Not Ready |  | 2026-03-10 | 2026-03-14 | RW toe foundation | 100 | 0 |  | 2026-10-09 |  | 2026-10-15 |  |  |  |  | RCC Super Structure | Foundation RCC Works
47561 |  | Not Ready |  | 2026-03-10 | 2026-03-14 | RW toe foundation | 100 | 0 |  | 2026-10-09 |  | 2026-10-15 |  |  |  |  | RCC Sub Structure | Raft RCC Works
47562 |  | Not Ready |  | 2026-03-10 | 2026-03-14 | Waterproofing-Raft Area | 100 | 0 |  | 2026-10-09 |  | 2026-10-15
42038 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-10-03 | 2026-10-06 | FAPA Cabling | 100 | 0 |  | 2026-10-10 |  | 2026-10-13 |  | Tower A | Super Structure | L68
42181 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-28 | 2026-10-30 | Painting Works | 100 | 0 |  | 2026-10-10 |  | 2026-10-13 |  | Tower A | Super Structure | L75 | Finishes | Painting Works
42199 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-28 | 2026-10-30 | Painting Works | 100 | 0 |  | 2026-10-10 |  | 2026-10-13 |  | Tower A | Super Structure | L76 | Finishes | Painting Works
43405 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-28 | 2026-10-30 | Painting Works | 100 | 0 |  | 2026-10-10 |  | 2026-10-13 |  | Tower A | Super Structure | L73 | Finishes | Painting Works
43423 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-28 | 2026-10-30 | Painting Works | 100 | 0 |  | 2026-10-10 |  | 2026-10-13 |  | Tower A | Super Structure | L74 | Finishes | Painting Works
43441 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-28 | 2026-10-30 | Painting Works | 100 | 0 |  | 2026-10-10 |  | 2026-10-13 |  | Tower A | Super Structure | L77 | Finishes | Painting Works
11515 |  | Not Ready | De-Snagging & Handing Over | 2026-11-12 | 2027-02-20 | De-Snagging & Handing Over | 100 | 0 |  | 2026-10-12 |  | 2027-01-20
41980 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-10-05 | 2026-10-08 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-10-12 |  | 2026-10-15 |  | Tower A | Super Structure | L64 | MEP | FPS 2nd Fix - MEP & Finishes
41981 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-10-05 | 2026-10-10 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-10-12 |  | 2026-10-17 |  | Tower A | Super Structure | L64 | MEP | Electrical 2nd Fix - MEP & Finishes
41982 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-10-05 | 2026-10-13 | FAPA Device Fixing | 100 | 0 |  | 2026-10-12 |  | 2026-10-21 |  | Tower A | Super Structure | L64
41982 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-10-05 | 2026-10-13 | FAPA Device Fixing | 100 | 0 |  | 2026-10-12 |  | 2026-10-21 |  | Tower A | Super Structure | L64
41982 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-10-05 | 2026-10-13 | FAPA Device Fixing | 100 | 0 |  | 2026-10-12 |  | 2026-10-21 |  | Tower A | Super Structure | L64
41982 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-10-05 | 2026-10-13 | FAPA Device Fixing | 100 | 0 |  | 2026-10-12 |  | 2026-10-21 |  | Tower A | Super Structure | L64
41983 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-10-05 | 2026-10-08 | HVAC Grill Fixing | 100 | 0 |  | 2026-10-12 |  | 2026-10-15 |  | Tower A | Super Structure | L64 | MEP | HVAC Grill Fixing
44269 |  | Not Ready |  | 2026-09-25 | 2026-10-08 | Pump Room Fire Mode Commissioning | 100 | 0 |  | 2026-10-12 |  | 2026-11-11
48093 | Pump Room | Not Ready |  | 2026-06-12 | 2026-08-28 | Pump Room | 100 | 0 |  | 2026-10-12 |  | 2026-12-21 |  | Pump Room | --
48094 |  | Not Ready |  | 2026-06-12 | 2026-08-28 | Fire Command Centre | 100 | 0 |  | 2026-10-12 |  | 2026-12-21
48097 |  | Not Ready |  | 2026-06-12 | 2026-08-28 | Equipment Installation | 100 | 0 |  | 2026-10-12 |  | 2026-12-21
39274 |  | Not Committed |  | 2026-04-13 | 2026-06-10 | R1 to CH00 (7.32m) | 100 | 0 |  | 2026-10-13 |  | 2026-12-14
39275 | Retail - Super structure - R1 to CH00 | Not Ready | RCC Works - Vertical | 2026-04-13 | 2026-05-25 | Columns_RT | 100 | 0 |  | 2026-10-13 |  | 2026-11-23 |  | Retail | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
39275 | Retail - Super structure - R1 to CH00 | Not Ready | RCC Works - Vertical | 2026-04-13 | 2026-05-25 | Columns_RT | 100 | 0 |  | 2026-10-13 |  | 2026-11-23 |  | Retail | Super Structure
39276 | Retail - Super structure - R1 to CH00 | Not Ready | RCC Works - Slab | 2026-04-13 | 2026-05-18 | Staircase_RT | 100 | 0 |  | 2026-10-13 |  | 2026-11-16 |  | Retail | Super Structure |  | RCC Sub Structure | RCC Works - Slab
39276 | Retail - Super structure - R1 to CH00 | Not Ready | RCC Works - Slab | 2026-04-13 | 2026-05-18 | Staircase_RT | 100 | 0 |  | 2026-10-13 |  | 2026-11-16 |  | Retail | Super Structure
41969 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-10-06 | 2026-10-12 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-10-13 |  | 2026-10-19 |  | Tower A | Super Structure | L63 | MEP | Electrical
41970 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-06 | 2026-10-12 | Final Painting | 100 | 0 |  | 2026-10-13 |  | 2026-10-19 |  | Tower A | Super Structure | L63 | Finishes | Final Painting
41970 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-06 | 2026-10-12 | Final Painting | 100 | 0 |  | 2026-10-13 |  | 2026-10-19 |  | Tower A | Super Structure | L63 | Finishes | Final Painting
41970 | Tower A - Super Structure - Finishes & MEP - L63 to L64 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-06 | 2026-10-12 | Final Painting | 100 | 0 |  | 2026-10-13 |  | 2026-10-19 |  | Tower A | Super Structure | L63 | Finishes | Final Painting
42039 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-10-06 | 2026-10-14 | HVAC Ducting | 100 | 0 |  | 2026-10-13 |  | 2026-10-22 |  | Tower A | Super Structure | L68 | MEP | HVAC Ducting
42052 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-10-06 | 2026-10-12 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-10-13 |  | 2026-10-19 |  | Tower A | Super Structure | L69 | MEP | FPS 1st Fix - MEP & Finishes
42053 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-10-06 | 2026-10-09 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-10-13 |  | 2026-10-16 |  | Tower A | Super Structure | L69 | MEP | Electrical 1st Fixes
46736 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-07-11 | 2026-07-21 | Door & Window Frame work | 100 | 0 |  | 2026-10-13 |  | 2026-10-22 |  | Tower B | Super Structure | L11 | Finishes | Door & Window Frame work
46752 |  | Not Committed |  | 2026-07-11 | 2026-09-24 | Finishes after 1st Fix | 100 | 0 |  | 2026-10-13 |  | 2026-12-04
46753 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-07-11 | 2026-07-24 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-10-13 |  | 2026-10-26 |  | Tower B | Super Structure | L12 | Finishes | Blockwork
48067 |  | Not Ready |  | 2026-06-13 | 2026-06-30 | Al. cladding around spear col. | 100 | 0 |  | 2026-10-13 |  | 2026-10-30
48087 | Club House - Super structure - CH01 to CH02 | Not Ready |  | 2026-06-13 | 2026-10-07 | CH01-CH02 | 100 | 0 |  | 2026-10-13 |  | 2027-01-28 |  | Club House | Super Structure | CH01
48206 | Retail - Super structure - GF to R1 | Not Ready |  | 2026-04-13 | 2026-06-06 | GF to R1 | 100 | 0 |  | 2026-10-13 |  | 2026-12-04 |  | Retail | Super Structure | GF
45330 | Tower B - Super Structure - Core & Outer Slab L26-27 | Not Ready | RCC Works - Slab | 2026-06-30 | 2026-07-06 | Outer Slab_TA | 100 | 0 |  | 2026-10-14 |  | 2026-10-23 |  | Tower B | Super Structure | L26 | RCC Sub Structure | RCC Works - Slab
9933 | T-16-Staircase 1 | Not Ready |  | 2026-10-20 | 2026-10-30 | GF-BF | 100 | 0 |  | 2026-10-15 |  | 2026-10-24
9947 | T-16-Staircase 2 | Not Ready |  | 2026-10-20 | 2026-10-30 | 01F-GF | 100 | 0 |  | 2026-10-15 |  | 2026-10-24
41984 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-10-08 | 2026-10-12 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-10-15 |  | 2026-10-19 |  | Tower A | Super Structure | L64
42011 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-10-08 | 2026-10-16 | False Ceiling | 100 | 0 |  | 2026-10-15 |  | 2026-10-24 |  | Tower A | Super Structure | L66 | Finishes | False Ceiling
42026 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-10-08 | 2026-10-21 | Flooring & Dado | 100 | 0 |  | 2026-10-15 |  | 2026-10-28 |  | Tower A | Super Structure | L67 | Finishes | Flooring & Dado
45742 | Tower B - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2026-07-07 | 2026-09-04 | FHC & Accessories fixing | 100 | 0 |  | 2026-10-15 |  | 2026-12-08 |  | Tower B | Super Structure | L15
45744 | Tower B - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2026-07-07 | 2026-09-04 | Soil & Waste Downtake piping in Plumbing Shaft | 100 | 0 |  | 2026-10-15 |  | 2026-12-08 |  | Tower B | Super Structure | L15
45748 | Tower B - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2026-07-07 | 2026-09-04 | HVAC Shaft Ducting | 100 | 0 |  | 2026-10-15 |  | 2026-12-08 |  | Tower B | Super Structure | L15 | MEP | HVAC Grill Fixing
46702 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-07-17 | 2026-08-01 | False Ceiling | 100 | 0 |  | 2026-10-15 |  | 2026-10-30 |  | Tower B | Super Structure | L9 | Finishes | False Ceiling
47563 |  | Not Ready |  | 2026-03-16 | 2026-03-26 | Raft & Footing Reinf_NTA | 100 | 0 |  | 2026-10-15 |  | 2026-10-28
47563 |  | Not Ready |  | 2026-03-16 | 2026-03-26 | Raft & Footing Reinf_NTA | 100 | 0 |  | 2026-10-15 |  | 2026-10-28 |  |  |  |  | RCC Super Structure | Foundation RCC Works
47563 |  | Not Ready |  | 2026-03-16 | 2026-03-26 | Raft & Footing Reinf_NTA | 100 | 0 |  | 2026-10-15 |  | 2026-10-28 |  |  |  |  | RCC Sub Structure | Raft RCC Works
42054 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-10-09 | 2026-10-12 | FAPA Cabling | 100 | 0 |  | 2026-10-16 |  | 2026-10-19 |  | Tower A | Super Structure | L69
44644 | NTA_Zone 2 - Super Structure - P1 to P2 | Not Ready | External Balustrade System | 2026-03-18 | 2026-04-03 | SS tray work | 100 | 0 |  | 2026-10-16 |  | 2026-11-03 |  | NTA_Zone 2 | Super Structure
44665 |  | Not Committed |  | 2026-03-18 | 2026-05-09 | P2 level | 100 | 0 |  | 2026-10-16 |  | 2026-11-26
44666 | NTA_Zone 2 - Super Structure - P2 to P3 | Not Ready | External Balustrade System | 2026-03-18 | 2026-04-15 | RCC upstand | 100 | 0 |  | 2026-10-16 |  | 2026-11-03 |  | NTA_Zone 2 | Super Structure
44666 | NTA_Zone 2 - Super Structure - P2 to P3 | Not Ready | External Balustrade System | 2026-03-18 | 2026-04-15 | RCC upstand | 100 | 0 |  | 2026-10-16 |  | 2026-11-03 |  | NTA_Zone 2 | Super Structure
46912 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-07-11 | 2026-07-31 | Wet Area Waterproofing | 100 | 0 |  | 2026-10-16 |  | 2026-11-04 |  | Tower B | Super Structure | L21
8908 | T-14-Staircase 2 | Not Ready |  | 2026-09-06 | 2026-09-17 | GF-BF | 100 | 0 |  | 2026-10-17 |  | 2026-10-30
41996 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-10-10 | 2026-10-14 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-10-17 |  | 2026-10-22 |  | Tower A | Super Structure | L65 | MEP | FPS 2nd Fix - MEP & Finishes
41997 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-10-10 | 2026-10-16 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-10-17 |  | 2026-10-24 |  | Tower A | Super Structure | L65 | MEP | Electrical 2nd Fix - MEP & Finishes
41998 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-10-10 | 2026-10-19 | FAPA Device Fixing | 100 | 0 |  | 2026-10-17 |  | 2026-10-27 |  | Tower A | Super Structure | L65
41998 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-10-10 | 2026-10-19 | FAPA Device Fixing | 100 | 0 |  | 2026-10-17 |  | 2026-10-27 |  | Tower A | Super Structure | L65
41998 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-10-10 | 2026-10-19 | FAPA Device Fixing | 100 | 0 |  | 2026-10-17 |  | 2026-10-27 |  | Tower A | Super Structure | L65
41998 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-10-10 | 2026-10-19 | FAPA Device Fixing | 100 | 0 |  | 2026-10-17 |  | 2026-10-27 |  | Tower A | Super Structure | L65
41999 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-10-10 | 2026-10-14 | HVAC Grill Fixing | 100 | 0 |  | 2026-10-17 |  | 2026-10-22 |  | Tower A | Super Structure | L65 | MEP | HVAC Grill Fixing
44261 |  | Not Ready | External Development | 2026-08-25 | 2026-10-23 | Fire Tender Path | 100 | 0 |  | 2026-10-17 |  | 2026-12-10
45496 | Tower B - Super Structure - Finishes & MEP - L22 to L23 | Not Ready | Partition Wall-Blockwork | 2026-07-09 | 2026-07-15 | Staircase Area | 100 | 0 |  | 2026-10-17 |  | 2026-10-24 |  | Tower B | Super Structure | L22
46684 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-07-23 | 2026-08-07 | False Ceiling | 100 | 0 |  | 2026-10-17 |  | 2026-11-02 |  | Tower B | Super Structure | L8 | Finishes | False Ceiling
48102 |  | Not Committed |  | 2026-08-21 | 2026-09-26 | Hardscape Works | 100 | 0 |  | 2026-10-17 |  | 2026-11-21
48102 |  | Not Committed |  | 2026-08-21 | 2026-09-26 | Hardscape Works | 100 | 0 |  | 2026-10-17 |  | 2026-11-21
9914 | T-16-Lift Lobby | Not Ready |  | 2026-11-07 | 2026-11-23 | 03F | 100 | 0 |  | 2026-10-18 |  | 2026-11-05
8874 | T-14-Lift Lobby | Not Ready |  | 2026-09-11 | 2026-09-28 | 03F | 100 | 0 |  | 2026-10-19 |  | 2026-11-03
41985 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-10-12 | 2026-10-17 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-10-19 |  | 2026-10-26 |  | Tower A | Super Structure | L64 | MEP | Electrical
41986 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-12 | 2026-10-17 | Final Painting | 100 | 0 |  | 2026-10-19 |  | 2026-10-26 |  | Tower A | Super Structure | L64 | Finishes | Final Painting
41986 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-12 | 2026-10-17 | Final Painting | 100 | 0 |  | 2026-10-19 |  | 2026-10-26 |  | Tower A | Super Structure | L64 | Finishes | Final Painting
41986 | Tower A - Super Structure - Finishes & MEP - L64 to L65 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-12 | 2026-10-17 | Final Painting | 100 | 0 |  | 2026-10-19 |  | 2026-10-26 |  | Tower A | Super Structure | L64 | Finishes | Final Painting
42055 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-10-12 | 2026-10-21 | HVAC Ducting | 100 | 0 |  | 2026-10-19 |  | 2026-10-28 |  | Tower A | Super Structure | L69 | MEP | HVAC Ducting
42068 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-10-12 | 2026-10-17 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-10-19 |  | 2026-10-26 |  | Tower A | Super Structure | L70 | MEP | FPS 1st Fix - MEP & Finishes
42069 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-10-12 | 2026-10-15 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-10-19 |  | 2026-10-23 |  | Tower A | Super Structure | L70 | MEP | Electrical 1st Fixes
46895 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-07-24 | 2026-08-06 | Cement Plastering in wet areas | 100 | 0 |  | 2026-10-19 |  | 2026-10-31 |  | Tower B | Super Structure | L20
47420 | Tower B - Super Structure - Finishes & MEP - L13 to L18 | Not Ready | Façade Works - MEP & Finishes | 2026-07-24 | 2026-08-13 | Accessories & Alignment | 100 | 0 |  | 2026-10-19 |  | 2026-11-06 |  | Tower B | Super Structure | L13 | Façade | Façade Works
47420 | Tower B - Super Structure - Finishes & MEP - L13 to L18 | Not Ready | Façade Works - MEP & Finishes | 2026-07-24 | 2026-08-13 | Accessories & Alignment | 100 | 0 |  | 2026-10-19 |  | 2026-11-06 |  | Tower B | Super Structure | L13
48070 |  | Not Ready |  | 2026-06-19 | 2026-07-06 | Lvl1-Horizontal Al. add-on profile+Horizontal steel tube+Insulation+Al. sheet boxing | 100 | 0 |  | 2026-10-19 |  | 2026-11-05
48072 |  | Not Committed |  | 2026-06-19 | 2026-09-03 | dwg RT-05,06 | 100 | 0 |  | 2026-10-19 |  | 2026-12-12
48073 |  | Not Ready |  | 2026-06-19 | 2026-07-06 | Lvl2-Horizontal Al. add-on profile+Horizontal steel tube+Insulation+Al. sheet boxing | 100 | 0 |  | 2026-10-19 |  | 2026-11-05
10958 | T-20-Lift Lobby | Not Ready |  | 2026-11-09 | 2026-11-25 | BF | 100 | 0 |  | 2026-10-20 |  | 2026-11-04
11997 | T-18-Lift Lobby | Not Ready |  | 2026-12-31 | 2027-01-18 | GF | 100 | 0 |  | 2026-10-20 |  | 2026-11-06
45624 | Tower B - Super Structure - Finishes & MEP - L21 to L22 | Not Ready | Gypsum Plastering Works | 2026-07-18 | 2026-08-28 | L21-22 | 100 | 0 |  | 2026-10-21 |  | 2026-11-25 |  | Tower B | Super Structure | L21 | Finishes | Gypsum Plastering Works
45624 | Tower B - Super Structure - Finishes & MEP - L21 to L22 | Not Ready | Gypsum Plastering Works | 2026-07-18 | 2026-08-28 | L21-22 | 100 | 0 |  | 2026-10-21 |  | 2026-11-25 |  | Tower B | Super Structure | L21
42000 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-10-14 | 2026-10-17 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-10-22 |  | 2026-10-26 |  | Tower A | Super Structure | L65
42027 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-10-14 | 2026-10-23 | False Ceiling | 100 | 0 |  | 2026-10-22 |  | 2026-10-30 |  | Tower A | Super Structure | L67 | Finishes | False Ceiling
42042 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-10-14 | 2026-10-27 | Flooring & Dado | 100 | 0 |  | 2026-10-22 |  | 2026-11-03 |  | Tower A | Super Structure | L68 | Finishes | Flooring & Dado
46755 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-07-30 | 2026-09-01 | Flooring & Dado works | 100 | 0 |  | 2026-10-22 |  | 2026-11-20 |  | Tower B | Super Structure | L12 | Finishes | Flooring & Dado
47555 |  | Not Ready |  | 2026-03-21 | 2026-03-26 | Fwk & Casting_NTA | 100 | 0 |  | 2026-10-22 |  | 2026-10-28
47555 |  | Not Ready |  | 2026-03-21 | 2026-03-26 | Fwk & Casting_NTA | 100 | 0 |  | 2026-10-22 |  | 2026-10-28 |  |  |  |  | RCC Super Structure | Foundation RCC Works
47555 |  | Not Ready |  | 2026-03-21 | 2026-03-26 | Fwk & Casting_NTA | 100 | 0 |  | 2026-10-22 |  | 2026-10-28 |  |  |  |  | RCC Sub Structure | Raft RCC Works
9397 | T-15-Lift Lobby | Not Ready |  | 2026-10-28 | 2026-11-15 | GF | 100 | 0 |  | 2026-10-23 |  | 2026-11-10
11475 | T-19-Lift Lobby | Not Ready |  | 2026-11-02 | 2026-11-18 | 02F | 100 | 0 |  | 2026-10-23 |  | 2026-11-06
42070 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-10-15 | 2026-10-17 | FAPA Cabling | 100 | 0 |  | 2026-10-23 |  | 2026-10-26 |  | Tower A | Super Structure | L70
44645 | NTA_Zone 2 - Super Structure - P1 to P2 | Not Ready | External Balustrade System | 2026-03-24 | 2026-04-09 | GRC framing & GRC cladding | 100 | 0 |  | 2026-10-23 |  | 2026-11-09 |  | NTA_Zone 2 | Super Structure
44646 | NTA_Zone 2 - Super Structure - P1 to P2 | Not Ready | External Balustrade System | 2026-03-24 | 2026-04-09 | Planter works | 100 | 0 |  | 2026-10-23 |  | 2026-11-09 |  | NTA_Zone 2 | Super Structure
44646 | NTA_Zone 2 - Super Structure - P1 to P2 | Not Ready | External Balustrade System | 2026-03-24 | 2026-04-09 | Planter works | 100 | 0 |  | 2026-10-23 |  | 2026-11-09 |  | NTA_Zone 2 | Super Structure
44667 | NTA_Zone 2 - Super Structure - P2 to P3 | Not Ready | External Balustrade System | 2026-04-04 | 2026-04-21 | Drainage pipe | 100 | 0 |  | 2026-10-23 |  | 2026-11-09 |  | NTA_Zone 2 | Super Structure
44667 | NTA_Zone 2 - Super Structure - P2 to P3 | Not Ready | External Balustrade System | 2026-04-04 | 2026-04-21 | Drainage pipe | 100 | 0 |  | 2026-10-23 |  | 2026-11-09 |  | NTA_Zone 2 | Super Structure
45331 |  | Not Ready |  | 2026-07-07 | 2026-07-18 | L27-28 | 100 | 0 |  | 2026-10-23 |  | 2026-11-07
45331 |  | Not Ready |  | 2026-07-07 | 2026-07-18 | L27-28 | 100 | 0 |  | 2026-10-23 |  | 2026-11-07 |  |  |  |  | Finishes | Gypsum Plastering Works
45332 | Tower B - Super Structure - Core & Outer Slab L27-28 | Not Ready | RCC Works - Vertical | 2026-07-07 | 2026-07-16 | Outer Columns_TA | 100 | 0 |  | 2026-10-23 |  | 2026-11-04 |  | Tower B | Super Structure | L27 | RCC Sub Structure | RCC Works - Vertical
45501 |  | Not Committed |  | 2026-07-07 | 2026-08-28 | L24-25 | 100 | 0 |  | 2026-10-23 |  | 2026-11-24
45501 |  | Not Committed |  | 2026-07-07 | 2026-08-28 | L24-25 | 100 | 0 |  | 2026-10-23 |  | 2026-11-24 |  |  |  |  | Finishes | Gypsum Plastering Works
45502 | Tower B - Super Structure - Finishes & MEP - L24 to L25 | Not Ready | Partition Wall-Blockwork | 2026-07-07 | 2026-07-25 | De-shuttering & Area clearance | 100 | 0 |  | 2026-10-23 |  | 2026-11-10 |  | Tower B | Super Structure | L24
42012 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-10-16 | 2026-10-21 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-10-24 |  | 2026-10-28 |  | Tower A | Super Structure | L66 | MEP | FPS 2nd Fix - MEP & Finishes
42013 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-10-16 | 2026-10-23 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-10-24 |  | 2026-10-30 |  | Tower A | Super Structure | L66 | MEP | Electrical 2nd Fix - MEP & Finishes
42014 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-10-16 | 2026-10-26 | FAPA Device Fixing | 100 | 0 |  | 2026-10-24 |  | 2026-11-02 |  | Tower A | Super Structure | L66
42014 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-10-16 | 2026-10-26 | FAPA Device Fixing | 100 | 0 |  | 2026-10-24 |  | 2026-11-02 |  | Tower A | Super Structure | L66
42014 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-10-16 | 2026-10-26 | FAPA Device Fixing | 100 | 0 |  | 2026-10-24 |  | 2026-11-02 |  | Tower A | Super Structure | L66
42014 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-10-16 | 2026-10-26 | FAPA Device Fixing | 100 | 0 |  | 2026-10-24 |  | 2026-11-02 |  | Tower A | Super Structure | L66
42015 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-10-16 | 2026-10-21 | HVAC Grill Fixing | 100 | 0 |  | 2026-10-24 |  | 2026-10-28 |  | Tower A | Super Structure | L66 | MEP | HVAC Grill Fixing
46925 |  | Not Committed |  | 2026-07-18 | 2027-08-16 | L22-23 | 100 | 0 |  | 2026-10-24 |  | 2027-09-18
46925 |  | Not Committed |  | 2026-07-18 | 2027-08-16 | L22-23 | 100 | 0 |  | 2026-10-24 |  | 2027-09-18 |  |  |  |  | Finishes | Gypsum Plastering Works
46926 |  | Not Committed |  | 2026-07-18 | 2026-09-11 | MEP 1st Fixes | 100 | 0 |  | 2026-10-24 |  | 2026-12-01
46927 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-07-18 | 2026-07-28 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-10-24 |  | 2026-11-02 |  | Tower B | Super Structure | L22 | MEP | FPS 1st Fix - MEP & Finishes
46928 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-07-18 | 2026-07-24 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-10-24 |  | 2026-10-30 |  | Tower B | Super Structure | L22 | MEP | Electrical 1st Fixes
46929 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-07-18 | 2026-07-28 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-10-24 |  | 2026-11-02 |  | Tower B | Super Structure | L22
9948 | T-16-Staircase 2 | Not Ready |  | 2026-11-02 | 2026-11-12 | GF-BF | 100 | 0 |  | 2026-10-25 |  | 2026-11-05
42001 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-10-17 | 2026-10-24 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-10-26 |  | 2026-10-31 |  | Tower A | Super Structure | L65 | MEP | Electrical
42002 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-17 | 2026-10-24 | Final Painting | 100 | 0 |  | 2026-10-26 |  | 2026-10-31 |  | Tower A | Super Structure | L65 | Finishes | Final Painting
42002 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-17 | 2026-10-24 | Final Painting | 100 | 0 |  | 2026-10-26 |  | 2026-10-31 |  | Tower A | Super Structure | L65 | Finishes | Final Painting
42002 | Tower A - Super Structure - Finishes & MEP - L65 to L66 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-17 | 2026-10-24 | Final Painting | 100 | 0 |  | 2026-10-26 |  | 2026-10-31 |  | Tower A | Super Structure | L65 | Finishes | Final Painting
42071 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-10-17 | 2026-10-27 | HVAC Ducting | 100 | 0 |  | 2026-10-26 |  | 2026-11-03 |  | Tower A | Super Structure | L70 | MEP | HVAC Ducting
42084 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-10-17 | 2026-10-24 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-10-26 |  | 2026-10-31 |  | Tower A | Super Structure | L71 | MEP | FPS 1st Fix - MEP & Finishes
42085 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-10-17 | 2026-10-22 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-10-26 |  | 2026-10-29 |  | Tower A | Super Structure | L71 | MEP | Electrical 1st Fixes
45499 | Tower B - Super Structure - Finishes & MEP - L23 to L24 | Not Ready | Partition Wall-Blockwork | 2026-07-16 | 2026-07-24 | Partition Walls | 100 | 0 |  | 2026-10-26 |  | 2026-11-03 |  | Tower B | Super Structure | L23
46754 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-08-06 | 2026-08-14 | Door & Window Frame work | 100 | 0 |  | 2026-10-26 |  | 2026-11-03 |  | Tower B | Super Structure | L12 | Finishes | Door & Window Frame work
46770 |  | Not Committed |  | 2026-08-06 | 2026-10-07 | Finishes after 1st Fix | 100 | 0 |  | 2026-10-26 |  | 2026-12-16
46771 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-08-06 | 2026-08-20 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-10-26 |  | 2026-11-06 |  | Tower B | Super Structure | L13 | Finishes | Blockwork
48088 | Club House - Super structure - CH02 to CH03 | Not Ready |  | 2026-06-25 | 2026-10-19 | CH02-CH03 | 100 | 0 |  | 2026-10-26 |  | 2027-02-09 |  | Club House | Super Structure | CH02
42016 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-10-21 | 2026-10-24 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-10-28 |  | 2026-10-31 |  | Tower A | Super Structure | L66
42043 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-10-21 | 2026-10-29 | False Ceiling | 100 | 0 |  | 2026-10-28 |  | 2026-11-05 |  | Tower A | Super Structure | L68 | Finishes | False Ceiling
42058 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-10-21 | 2026-11-02 | Flooring & Dado | 100 | 0 |  | 2026-10-28 |  | 2026-11-09 |  | Tower A | Super Structure | L69 | Finishes | Flooring & Dado
45746 | Tower B - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2026-07-25 | 2026-09-03 | Shaft Cabling in Electrical & ELV Shaft | 100 | 0 |  | 2026-10-28 |  | 2026-12-02 |  | Tower B | Super Structure | L15
46720 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-08-08 | 2026-08-25 | False Ceiling | 100 | 0 |  | 2026-10-28 |  | 2026-11-11 |  | Tower B | Super Structure | L10 | Finishes | False Ceiling
47564 |  | Not Ready |  | 2026-03-27 | 2026-04-01 | Fwk & Casting_NTA | 100 | 0 |  | 2026-10-28 |  | 2026-11-03
47564 |  | Not Ready |  | 2026-03-27 | 2026-04-01 | Fwk & Casting_NTA | 100 | 0 |  | 2026-10-28 |  | 2026-11-03 |  |  |  |  | RCC Super Structure | Foundation RCC Works
47564 |  | Not Ready |  | 2026-03-27 | 2026-04-01 | Fwk & Casting_NTA | 100 | 0 |  | 2026-10-28 |  | 2026-11-03 |  |  |  |  | RCC Sub Structure | Raft RCC Works
47615 |  | Not Committed |  | 2026-03-27 | 2026-04-24 | Pour 7 (grid PB-K to PB-N) | 100 | 0 |  | 2026-10-28 |  | 2026-11-26
47616 |  | Not Ready |  | 2026-03-27 | 2026-04-13 | Columns/ Walls_NTA | 100 | 0 |  | 2026-10-28 |  | 2026-11-14
47616 |  | Not Ready |  | 2026-03-27 | 2026-04-13 | Columns/ Walls_NTA | 100 | 0 |  | 2026-10-28 |  | 2026-11-14 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
42086 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-10-22 | 2026-10-24 | FAPA Cabling | 100 | 0 |  | 2026-10-29 |  | 2026-10-31 |  | Tower A | Super Structure | L71
42028 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-10-23 | 2026-10-27 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-10-30 |  | 2026-11-03 |  | Tower A | Super Structure | L67 | MEP | FPS 2nd Fix - MEP & Finishes
42029 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-10-23 | 2026-10-29 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-10-30 |  | 2026-11-05 |  | Tower A | Super Structure | L67 | MEP | Electrical 2nd Fix - MEP & Finishes
42030 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-10-23 | 2026-10-31 | FAPA Device Fixing | 100 | 0 |  | 2026-10-30 |  | 2026-11-07 |  | Tower A | Super Structure | L67
42030 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-10-23 | 2026-10-31 | FAPA Device Fixing | 100 | 0 |  | 2026-10-30 |  | 2026-11-07 |  | Tower A | Super Structure | L67
42030 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-10-23 | 2026-10-31 | FAPA Device Fixing | 100 | 0 |  | 2026-10-30 |  | 2026-11-07 |  | Tower A | Super Structure | L67
42030 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-10-23 | 2026-10-31 | FAPA Device Fixing | 100 | 0 |  | 2026-10-30 |  | 2026-11-07 |  | Tower A | Super Structure | L67
42031 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-10-23 | 2026-10-27 | HVAC Grill Fixing | 100 | 0 |  | 2026-10-30 |  | 2026-11-03 |  | Tower A | Super Structure | L67 | MEP | HVAC Grill Fixing
45333 | Tower B - Super Structure - Core & Outer Slab L27-28 | Not Ready | RCC Works - Slab | 2026-07-11 | 2026-07-18 | Outer Slab_TA | 100 | 0 |  | 2026-10-30 |  | 2026-11-07 |  | Tower B | Super Structure | L27 | RCC Sub Structure | RCC Works - Slab
48228 | Club House - Super structure - CH03 to Roof | Not Ready |  | 2026-06-30 | 2026-08-07 | CH03-CH04 (MEP Level) | 100 | 0 |  | 2026-10-30 |  | 2026-12-03 |  | Club House | Super Structure | CH03
48251 | Retail - Super structure - CH02 to CH03 | Not Ready |  | 2026-06-30 | 2026-10-24 | CH02-CH03 (P6-7) | 100 | 0 |  | 2026-10-30 |  | 2027-02-13 |  | Retail | Super Structure | CH02
42017 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-10-24 | 2026-10-30 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-10-31 |  | 2026-11-06 |  | Tower A | Super Structure | L66 | MEP | Electrical
42018 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-24 | 2026-10-30 | Final Painting | 100 | 0 |  | 2026-10-31 |  | 2026-11-06 |  | Tower A | Super Structure | L66 | Finishes | Final Painting
42018 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-24 | 2026-10-30 | Final Painting | 100 | 0 |  | 2026-10-31 |  | 2026-11-06 |  | Tower A | Super Structure | L66 | Finishes | Final Painting
42018 | Tower A - Super Structure - Finishes & MEP - L66 to L67 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-24 | 2026-10-30 | Final Painting | 100 | 0 |  | 2026-10-31 |  | 2026-11-06 |  | Tower A | Super Structure | L66 | Finishes | Final Painting
42087 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-10-24 | 2026-11-02 | HVAC Ducting | 100 | 0 |  | 2026-10-31 |  | 2026-11-09 |  | Tower A | Super Structure | L71 | MEP | HVAC Ducting
42100 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-10-24 | 2026-10-30 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-10-31 |  | 2026-11-06 |  | Tower A | Super Structure | L72 | MEP | FPS 1st Fix - MEP & Finishes
42101 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-10-24 | 2026-10-28 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-10-31 |  | 2026-11-04 |  | Tower A | Super Structure | L72 | MEP | Electrical 1st Fixes
9955 |  | Not Ready | De-Snagging & Handing Over | 2026-12-03 | 2027-03-13 | De-Snagging & Handing Over | 100 | 0 |  | 2026-11-02 |  | 2027-02-11
46930 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-08-06 | 2026-08-26 | Wet Area Waterproofing | 100 | 0 |  | 2026-11-02 |  | 2026-11-19 |  | Tower B | Super Structure | L22
42032 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-10-27 | 2026-10-30 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-11-03 |  | 2026-11-06 |  | Tower A | Super Structure | L67
42059 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-10-27 | 2026-11-04 | False Ceiling | 100 | 0 |  | 2026-11-03 |  | 2026-11-11 |  | Tower A | Super Structure | L69 | Finishes | False Ceiling
42074 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-10-27 | 2026-11-07 | Flooring & Dado | 100 | 0 |  | 2026-11-03 |  | 2026-11-14 |  | Tower A | Super Structure | L70 | Finishes | Flooring & Dado
45500 | Tower B - Super Structure - Finishes & MEP - L23 to L24 | Not Ready | Partition Wall-Blockwork | 2026-07-31 | 2026-08-06 | Staircase Area | 100 | 0 |  | 2026-11-03 |  | 2026-11-09 |  | Tower B | Super Structure | L23
46773 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-08-22 | 2026-09-22 | Flooring & Dado works | 100 | 0 |  | 2026-11-03 |  | 2026-12-02 |  | Tower B | Super Structure | L13 | Finishes | Flooring & Dado
47618 |  | Not Committed |  | 2026-04-02 | 2026-04-30 | Pour 8 (grid PB-D to PB-K) | 100 | 0 |  | 2026-11-03 |  | 2026-12-02
47619 |  | Not Ready |  | 2026-04-02 | 2026-04-18 | Columns/ Walls_NTA | 100 | 0 |  | 2026-11-03 |  | 2026-11-20
47619 |  | Not Ready |  | 2026-04-02 | 2026-04-18 | Columns/ Walls_NTA | 100 | 0 |  | 2026-11-03 |  | 2026-11-20 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
8875 | T-14-Lift Lobby | Not Ready |  | 2026-09-28 | 2026-10-15 | 02F | 100 | 0 |  | 2026-11-04 |  | 2026-11-23
42102 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-10-28 | 2026-10-30 | FAPA Cabling | 100 | 0 |  | 2026-11-04 |  | 2026-11-06 |  | Tower A | Super Structure | L72
44564 | NTA_Zone 2 - Super Structure - GF to P1 | Not Ready | Finishes (Lobby & Floor Area) | 2026-03-24 | 2026-04-27 | Staircase Finishes | 100 | 0 |  | 2026-11-04 |  | 2026-12-08 |  | NTA_Zone 2 | Super Structure | GF
44564 | NTA_Zone 2 - Super Structure - GF to P1 | Not Ready | Finishes (Lobby & Floor Area) | 2026-03-24 | 2026-04-27 | Staircase Finishes | 100 | 0 |  | 2026-11-04 |  | 2026-12-08 |  | NTA_Zone 2 | Super Structure | GF
44659 |  | Not Committed |  | 2026-04-16 | 2026-06-09 | P3 level | 100 | 0 |  | 2026-11-04 |  | 2026-12-26
44660 | NTA_Zone 2 - Super Structure - P3 to P4 | Not Ready | External Balustrade System | 2026-04-16 | 2026-05-15 | RCC upstand | 100 | 0 |  | 2026-11-04 |  | 2026-12-02 |  | NTA_Zone 2 | Super Structure
44660 | NTA_Zone 2 - Super Structure - P3 to P4 | Not Ready | External Balustrade System | 2026-04-16 | 2026-05-15 | RCC upstand | 100 | 0 |  | 2026-11-04 |  | 2026-12-02 |  | NTA_Zone 2 | Super Structure
44668 | NTA_Zone 2 - Super Structure - P2 to P3 | Not Ready | External Balustrade System | 2026-04-16 | 2026-05-04 | SS tray work | 100 | 0 |  | 2026-11-04 |  | 2026-11-20 |  | NTA_Zone 2 | Super Structure
46913 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-08-20 | 2026-08-31 | Cement Plastering in wet areas | 100 | 0 |  | 2026-11-04 |  | 2026-11-16 |  | Tower B | Super Structure | L21
42044 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-10-29 | 2026-11-02 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-11-05 |  | 2026-11-09 |  | Tower A | Super Structure | L68 | MEP | FPS 2nd Fix - MEP & Finishes
42045 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-10-29 | 2026-11-04 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-11-05 |  | 2026-11-11 |  | Tower A | Super Structure | L68 | MEP | Electrical 2nd Fix - MEP & Finishes
42046 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-10-29 | 2026-11-06 | FAPA Device Fixing | 100 | 0 |  | 2026-11-05 |  | 2026-11-13 |  | Tower A | Super Structure | L68
42046 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-10-29 | 2026-11-06 | FAPA Device Fixing | 100 | 0 |  | 2026-11-05 |  | 2026-11-13 |  | Tower A | Super Structure | L68
42046 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-10-29 | 2026-11-06 | FAPA Device Fixing | 100 | 0 |  | 2026-11-05 |  | 2026-11-13 |  | Tower A | Super Structure | L68
42046 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-10-29 | 2026-11-06 | FAPA Device Fixing | 100 | 0 |  | 2026-11-05 |  | 2026-11-13 |  | Tower A | Super Structure | L68
42047 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-10-29 | 2026-11-02 | HVAC Grill Fixing | 100 | 0 |  | 2026-11-05 |  | 2026-11-09 |  | Tower A | Super Structure | L68 | MEP | HVAC Grill Fixing
45625 | Tower B - Super Structure - Finishes & MEP - L22 to L23 | Not Ready | Gypsum Plastering Works | 2026-08-13 | 2026-09-21 | L22-23 | 100 | 0 |  | 2026-11-05 |  | 2026-12-10 |  | Tower B | Super Structure | L22 | Finishes | Gypsum Plastering Works
45625 | Tower B - Super Structure - Finishes & MEP - L22 to L23 | Not Ready | Gypsum Plastering Works | 2026-08-13 | 2026-09-21 | L22-23 | 100 | 0 |  | 2026-11-05 |  | 2026-12-10 |  | Tower B | Super Structure | L22
48105 |  | Not Committed |  | 2026-09-08 | 2026-11-03 | Retail In/Out & Loading Bay In/Out | 100 | 0 |  | 2026-11-05 |  | 2026-12-28
48106 |  | Not Committed |  | 2026-09-08 | 2026-11-03 | Water feature | 100 | 0 |  | 2026-11-05 |  | 2026-12-28
48108 |  | Not Committed |  | 2026-09-08 | 2026-12-26 | Compound Wall | 100 | 0 |  | 2026-11-05 |  | 2027-02-19
48108 |  | Not Committed |  | 2026-09-08 | 2026-12-26 | Compound Wall | 100 | 0 |  | 2026-11-05 |  | 2027-02-19
9915 | T-16-Lift Lobby | Not Ready |  | 2026-11-23 | 2026-12-09 | 02F | 100 | 0 |  | 2026-11-06 |  | 2026-11-21
42033 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-10-30 | 2026-11-05 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-11-06 |  | 2026-11-12 |  | Tower A | Super Structure | L67 | MEP | Electrical
42034 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-30 | 2026-11-05 | Final Painting | 100 | 0 |  | 2026-11-06 |  | 2026-11-12 |  | Tower A | Super Structure | L67 | Finishes | Final Painting
42034 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-30 | 2026-11-05 | Final Painting | 100 | 0 |  | 2026-11-06 |  | 2026-11-12 |  | Tower A | Super Structure | L67 | Finishes | Final Painting
42034 | Tower A - Super Structure - Finishes & MEP - L67 to L68 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-10-30 | 2026-11-05 | Final Painting | 100 | 0 |  | 2026-11-06 |  | 2026-11-12 |  | Tower A | Super Structure | L67 | Finishes | Final Painting
42103 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-10-30 | 2026-11-07 | HVAC Ducting | 100 | 0 |  | 2026-11-06 |  | 2026-11-14 |  | Tower A | Super Structure | L72 | MEP | HVAC Ducting
42116 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-10-30 | 2026-11-05 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-11-06 |  | 2026-11-12 |  | Tower A | Super Structure | L73 | MEP | FPS 1st Fix - MEP & Finishes
42117 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-10-30 | 2026-11-03 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-11-06 |  | 2026-11-10 |  | Tower A | Super Structure | L73 | MEP | Electrical 1st Fixes
46772 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-08-26 | 2026-09-02 | Door & Window Frame work | 100 | 0 |  | 2026-11-06 |  | 2026-11-14 |  | Tower B | Super Structure | L13 | Finishes | Door & Window Frame work
46788 |  | Not Committed |  | 2026-08-26 | 2026-10-19 | Finishes after 1st Fix | 100 | 0 |  | 2026-11-06 |  | 2026-12-29
46789 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-08-26 | 2026-09-05 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-11-06 |  | 2026-11-18 |  | Tower B | Super Structure | L14 | Finishes | Blockwork
47421 |  | Not Committed |  | 2026-08-26 | 2026-10-21 | L18-23 | 100 | 0 |  | 2026-11-06 |  | 2026-12-30
47422 | Tower B - Super Structure - Finishes & MEP - L18 to L23 | Not Ready | Façade Works - MEP & Finishes | 2026-08-26 | 2026-09-19 | Al. Frame section (Mullion & Transom) Installation | 100 | 0 |  | 2026-11-06 |  | 2026-11-30 |  | Tower B | Super Structure | L18 | Façade | Façade Works
48071 |  | Not Ready |  | 2026-07-07 | 2026-07-25 | Cantilever Al. Light Boxing | 100 | 0 |  | 2026-11-06 |  | 2026-11-23
48074 |  | Not Ready |  | 2026-07-07 | 2026-07-15 | Steel bracket at cantilever end | 100 | 0 |  | 2026-11-06 |  | 2026-11-13
48089 | Club House - Super structure - CH03 to Roof | Not Ready |  | 2026-07-07 | 2026-10-31 | CH03-CH04 (MEP Level) | 100 | 0 |  | 2026-11-06 |  | 2027-02-20 |  | Club House | Super Structure | CH03
11476 | T-19-Lift Lobby | Not Ready |  | 2026-11-18 | 2026-12-04 | 01F | 100 | 0 |  | 2026-11-07 |  | 2026-11-23
11998 | T-18-Lift Lobby | Not Ready |  | 2027-01-18 | 2027-02-04 | BF | 100 | 0 |  | 2026-11-07 |  | 2026-11-22
45334 |  | Not Ready |  | 2026-07-25 | 2026-08-13 | L28-29 | 100 | 0 |  | 2026-11-07 |  | 2026-11-19
45334 |  | Not Ready |  | 2026-07-25 | 2026-08-13 | L28-29 | 100 | 0 |  | 2026-11-07 |  | 2026-11-19 |  |  |  |  | Finishes | Gypsum Plastering Works
45335 | Tower B - Super Structure - Core & Outer Slab L28-29 | Not Ready | RCC Works - Vertical | 2026-07-25 | 2026-08-05 | Outer Columns_TA | 100 | 0 |  | 2026-11-07 |  | 2026-11-17 |  | Tower B | Super Structure | L28 | RCC Sub Structure | RCC Works - Vertical
45505 |  | Not Committed |  | 2026-07-25 | 2026-09-09 | L25-26 | 100 | 0 |  | 2026-11-07 |  | 2026-12-09
45505 |  | Not Committed |  | 2026-07-25 | 2026-09-09 | L25-26 | 100 | 0 |  | 2026-11-07 |  | 2026-12-09 |  |  |  |  | Finishes | Gypsum Plastering Works
45506 | Tower B - Super Structure - Finishes & MEP - L25 to L26 | Not Ready | Partition Wall-Blockwork | 2026-07-25 | 2026-08-14 | De-shuttering & Area clearance | 100 | 0 |  | 2026-11-07 |  | 2026-11-25 |  | Tower B | Super Structure | L25
42048 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-11-02 | 2026-11-05 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-11-09 |  | 2026-11-12 |  | Tower A | Super Structure | L68
42075 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-11-02 | 2026-11-10 | False Ceiling | 100 | 0 |  | 2026-11-09 |  | 2026-11-17 |  | Tower A | Super Structure | L70 | Finishes | False Ceiling
42090 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-11-02 | 2026-11-13 | Flooring & Dado | 100 | 0 |  | 2026-11-09 |  | 2026-11-20 |  | Tower A | Super Structure | L71 | Finishes | Flooring & Dado
46738 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-08-28 | 2026-09-10 | False Ceiling | 100 | 0 |  | 2026-11-09 |  | 2026-11-23 |  | Tower B | Super Structure | L11 | Finishes | False Ceiling
46943 |  | Not Committed |  | 2026-08-13 | 2027-08-30 | L23-24 | 100 | 0 |  | 2026-11-09 |  | 2027-09-30
46943 |  | Not Committed |  | 2026-08-13 | 2027-08-30 | L23-24 | 100 | 0 |  | 2026-11-09 |  | 2027-09-30 |  |  |  |  | Finishes | Gypsum Plastering Works
46944 |  | Not Committed |  | 2026-08-13 | 2026-09-25 | MEP 1st Fixes | 100 | 0 |  | 2026-11-09 |  | 2026-12-16
46945 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-08-13 | 2026-08-22 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-11-09 |  | 2026-11-17 |  | Tower B | Super Structure | L23 | MEP | FPS 1st Fix - MEP & Finishes
46946 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-08-13 | 2026-08-20 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-11-09 |  | 2026-11-14 |  | Tower B | Super Structure | L23 | MEP | Electrical 1st Fixes
46947 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-08-13 | 2026-08-22 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-11-09 |  | 2026-11-17 |  | Tower B | Super Structure | L23
47617 |  | Not Ready |  | 2026-04-08 | 2026-04-24 | Slab_NTA | 100 | 0 |  | 2026-11-09 |  | 2026-11-26
47617 |  | Not Ready |  | 2026-04-08 | 2026-04-24 | Slab_NTA | 100 | 0 |  | 2026-11-09 |  | 2026-11-26 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
42118 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-11-03 | 2026-11-05 | FAPA Cabling | 100 | 0 |  | 2026-11-10 |  | 2026-11-12 |  | Tower A | Super Structure | L73
44669 | NTA_Zone 2 - Super Structure - P2 to P3 | Not Ready | External Balustrade System | 2026-04-22 | 2026-05-09 | GRC framing & GRC cladding | 100 | 0 |  | 2026-11-10 |  | 2026-11-26 |  | NTA_Zone 2 | Super Structure
44670 | NTA_Zone 2 - Super Structure - P2 to P3 | Not Ready | External Balustrade System | 2026-04-22 | 2026-05-09 | Planter works | 100 | 0 |  | 2026-11-10 |  | 2026-11-26 |  | NTA_Zone 2 | Super Structure
44670 | NTA_Zone 2 - Super Structure - P2 to P3 | Not Ready | External Balustrade System | 2026-04-22 | 2026-05-09 | Planter works | 100 | 0 |  | 2026-11-10 |  | 2026-11-26 |  | NTA_Zone 2 | Super Structure
45503 | Tower B - Super Structure - Finishes & MEP - L24 to L25 | Not Ready | Partition Wall-Blockwork | 2026-08-07 | 2026-08-18 | Partition Walls | 100 | 0 |  | 2026-11-10 |  | 2026-11-18 |  | Tower B | Super Structure | L24
9398 | T-15-Lift Lobby | Not Ready |  | 2026-11-15 | 2026-12-01 | BF | 100 | 0 |  | 2026-11-11 |  | 2026-11-27
42060 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-11-04 | 2026-11-07 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-11-11 |  | 2026-11-14 |  | Tower A | Super Structure | L69 | MEP | FPS 2nd Fix - MEP & Finishes
42061 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-11-04 | 2026-11-10 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-11-11 |  | 2026-11-17 |  | Tower A | Super Structure | L69 | MEP | Electrical 2nd Fix - MEP & Finishes
42062 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-11-04 | 2026-11-12 | FAPA Device Fixing | 100 | 0 |  | 2026-11-11 |  | 2026-11-19 |  | Tower A | Super Structure | L69
42062 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-11-04 | 2026-11-12 | FAPA Device Fixing | 100 | 0 |  | 2026-11-11 |  | 2026-11-19 |  | Tower A | Super Structure | L69
42062 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-11-04 | 2026-11-12 | FAPA Device Fixing | 100 | 0 |  | 2026-11-11 |  | 2026-11-19 |  | Tower A | Super Structure | L69
42062 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-11-04 | 2026-11-12 | FAPA Device Fixing | 100 | 0 |  | 2026-11-11 |  | 2026-11-19 |  | Tower A | Super Structure | L69
42063 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-11-04 | 2026-11-07 | HVAC Grill Fixing | 100 | 0 |  | 2026-11-11 |  | 2026-11-14 |  | Tower A | Super Structure | L69 | MEP | HVAC Grill Fixing
44271 |  | Not Ready |  | 2026-10-09 | 2026-10-23 | FAPA Integration | 100 | 0 |  | 2026-11-11 |  | 2026-12-10
42049 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-11-05 | 2026-11-11 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-11-12 |  | 2026-11-18 |  | Tower A | Super Structure | L68 | MEP | Electrical
42050 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-11-05 | 2026-11-11 | Final Painting | 100 | 0 |  | 2026-11-12 |  | 2026-11-18 |  | Tower A | Super Structure | L68 | Finishes | Final Painting
42050 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-11-05 | 2026-11-11 | Final Painting | 100 | 0 |  | 2026-11-12 |  | 2026-11-18 |  | Tower A | Super Structure | L68 | Finishes | Final Painting
42050 | Tower A - Super Structure - Finishes & MEP - L68 to L69 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-11-05 | 2026-11-11 | Final Painting | 100 | 0 |  | 2026-11-12 |  | 2026-11-18 |  | Tower A | Super Structure | L68 | Finishes | Final Painting
42119 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-11-05 | 2026-11-13 | HVAC Ducting | 100 | 0 |  | 2026-11-12 |  | 2026-11-20 |  | Tower A | Super Structure | L73 | MEP | HVAC Ducting
42132 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-11-05 | 2026-11-11 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-11-12 |  | 2026-11-18 |  | Tower A | Super Structure | L74 | MEP | FPS 1st Fix - MEP & Finishes
42133 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-11-05 | 2026-11-09 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-11-12 |  | 2026-11-16 |  | Tower A | Super Structure | L74 | MEP | Electrical 1st Fixes
45336 | Tower B - Super Structure - Core & Outer Slab L28-29 | Not Ready | RCC Works - Slab | 2026-08-06 | 2026-08-13 | Outer Slab_TA | 100 | 0 |  | 2026-11-12 |  | 2026-11-19 |  | Tower B | Super Structure | L28 | RCC Sub Structure | RCC Works - Slab
42064 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-11-07 | 2026-11-11 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-11-14 |  | 2026-11-18 |  | Tower A | Super Structure | L69
42091 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-11-07 | 2026-11-16 | False Ceiling | 100 | 0 |  | 2026-11-14 |  | 2026-11-23 |  | Tower A | Super Structure | L71 | Finishes | False Ceiling
42106 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-11-07 | 2026-11-19 | Flooring & Dado | 100 | 0 |  | 2026-11-14 |  | 2026-11-26 |  | Tower A | Super Structure | L72 | Finishes | Flooring & Dado
46791 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-09-03 | 2026-10-05 | Flooring & Dado works | 100 | 0 |  | 2026-11-14 |  | 2026-12-14 |  | Tower B | Super Structure | L14 | Finishes | Flooring & Dado
47620 |  | Not Ready |  | 2026-04-14 | 2026-04-30 | Slab_NTA | 100 | 0 |  | 2026-11-14 |  | 2026-12-02
47620 |  | Not Ready |  | 2026-04-14 | 2026-04-30 | Slab_NTA | 100 | 0 |  | 2026-11-14 |  | 2026-12-02 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
48075 |  | Not Ready |  | 2026-07-18 | 2026-07-31 | Al. framing below slab | 100 | 0 |  | 2026-11-14 |  | 2026-11-25
42134 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-11-09 | 2026-11-11 | FAPA Cabling | 100 | 0 |  | 2026-11-16 |  | 2026-11-18 |  | Tower A | Super Structure | L74
39277 | Retail - Super structure - R1 to CH00 | Not Ready | RCC Works - Slab | 2026-05-13 | 2026-06-10 | Slab_RT | 100 | 0 |  | 2026-11-17 |  | 2026-12-14 |  | Retail | Super Structure |  | RCC Sub Structure | RCC Works - Slab
39277 | Retail - Super structure - R1 to CH00 | Not Ready | RCC Works - Slab | 2026-05-13 | 2026-06-10 | Slab_RT | 100 | 0 |  | 2026-11-17 |  | 2026-12-14 |  | Retail | Super Structure
42076 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-11-10 | 2026-11-13 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-11-17 |  | 2026-11-20 |  | Tower A | Super Structure | L70 | MEP | FPS 2nd Fix - MEP & Finishes
42077 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-11-10 | 2026-11-16 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-11-17 |  | 2026-11-23 |  | Tower A | Super Structure | L70 | MEP | Electrical 2nd Fix - MEP & Finishes
42078 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-11-10 | 2026-11-18 | FAPA Device Fixing | 100 | 0 |  | 2026-11-17 |  | 2026-11-25 |  | Tower A | Super Structure | L70
42078 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-11-10 | 2026-11-18 | FAPA Device Fixing | 100 | 0 |  | 2026-11-17 |  | 2026-11-25 |  | Tower A | Super Structure | L70
42078 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-11-10 | 2026-11-18 | FAPA Device Fixing | 100 | 0 |  | 2026-11-17 |  | 2026-11-25 |  | Tower A | Super Structure | L70
42078 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-11-10 | 2026-11-18 | FAPA Device Fixing | 100 | 0 |  | 2026-11-17 |  | 2026-11-25 |  | Tower A | Super Structure | L70
42079 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-11-10 | 2026-11-13 | HVAC Grill Fixing | 100 | 0 |  | 2026-11-17 |  | 2026-11-20 |  | Tower A | Super Structure | L70 | MEP | HVAC Grill Fixing
46948 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-08-26 | 2026-09-11 | Wet Area Waterproofing | 100 | 0 |  | 2026-11-17 |  | 2026-12-04 |  | Tower B | Super Structure | L23
41028 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-11-11 | 2026-11-17 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-11-18 |  | 2026-11-24 |  | Tower A | Super Structure | L75 | MEP | FPS 1st Fix - MEP & Finishes
41029 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-11-11 | 2026-11-14 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-11-18 |  | 2026-11-21 |  | Tower A | Super Structure | L75 | MEP | Electrical 1st Fixes
42065 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-11-11 | 2026-11-17 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-11-18 |  | 2026-11-24 |  | Tower A | Super Structure | L69 | MEP | Electrical
42066 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-11-11 | 2026-11-17 | Final Painting | 100 | 0 |  | 2026-11-18 |  | 2026-11-24 |  | Tower A | Super Structure | L69 | Finishes | Final Painting
42066 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-11-11 | 2026-11-17 | Final Painting | 100 | 0 |  | 2026-11-18 |  | 2026-11-24 |  | Tower A | Super Structure | L69 | Finishes | Final Painting
42066 | Tower A - Super Structure - Finishes & MEP - L69 to L70 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-11-11 | 2026-11-17 | Final Painting | 100 | 0 |  | 2026-11-18 |  | 2026-11-24 |  | Tower A | Super Structure | L69 | Finishes | Final Painting
42135 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-11-11 | 2026-11-19 | HVAC Ducting | 100 | 0 |  | 2026-11-18 |  | 2026-11-26 |  | Tower A | Super Structure | L74 | MEP | HVAC Ducting
45504 | Tower B - Super Structure - Finishes & MEP - L24 to L25 | Not Ready | Partition Wall-Blockwork | 2026-08-24 | 2026-08-28 | Staircase Area | 100 | 0 |  | 2026-11-18 |  | 2026-11-24 |  | Tower B | Super Structure | L24
46790 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-09-07 | 2026-09-14 | Door & Window Frame work | 100 | 0 |  | 2026-11-18 |  | 2026-11-26 |  | Tower B | Super Structure | L14 | Finishes | Door & Window Frame work
46806 |  | Not Committed |  | 2026-09-07 | 2026-10-31 | Finishes after 1st Fix | 100 | 0 |  | 2026-11-18 |  | 2027-01-09
46807 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-09-07 | 2026-09-19 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-11-18 |  | 2026-11-30 |  | Tower B | Super Structure | L15 | Finishes | Blockwork
45337 |  | Not Ready |  | 2026-08-21 | 2026-09-01 | L29-30 | 100 | 0 |  | 2026-11-19 |  | 2026-12-01
45337 |  | Not Ready |  | 2026-08-21 | 2026-09-01 | L29-30 | 100 | 0 |  | 2026-11-19 |  | 2026-12-01 |  |  |  |  | Finishes | Gypsum Plastering Works
45338 | Tower B - Super Structure - Core & Outer Slab L29-30 | Not Ready | RCC Works - Vertical | 2026-08-21 | 2026-08-29 | Outer Columns_TA | 100 | 0 |  | 2026-11-19 |  | 2026-11-28 |  | Tower B | Super Structure | L29 | RCC Sub Structure | RCC Works - Vertical
45509 |  | Not Committed |  | 2026-08-21 | 2026-09-23 | L26-27 | 100 | 0 |  | 2026-11-19 |  | 2026-12-21
45509 |  | Not Committed |  | 2026-08-21 | 2026-09-23 | L26-27 | 100 | 0 |  | 2026-11-19 |  | 2026-12-21 |  |  |  |  | Finishes | Gypsum Plastering Works
45510 | Tower B - Super Structure - Finishes & MEP - L26 to L27 | Not Ready | Partition Wall-Blockwork | 2026-08-21 | 2026-09-07 | De-shuttering & Area clearance | 100 | 0 |  | 2026-11-19 |  | 2026-12-07 |  | Tower B | Super Structure | L26
46931 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-09-01 | 2026-09-11 | Cement Plastering in wet areas | 100 | 0 |  | 2026-11-19 |  | 2026-12-01 |  | Tower B | Super Structure | L22
42080 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-11-13 | 2026-11-17 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-11-20 |  | 2026-11-24 |  | Tower A | Super Structure | L70
42107 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-11-13 | 2026-11-21 | False Ceiling | 100 | 0 |  | 2026-11-20 |  | 2026-11-28 |  | Tower A | Super Structure | L72 | Finishes | False Ceiling
42122 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-11-13 | 2026-11-25 | Flooring & Dado | 100 | 0 |  | 2026-11-20 |  | 2026-12-02 |  | Tower A | Super Structure | L73 | Finishes | Flooring & Dado
45626 | Tower B - Super Structure - Finishes & MEP - L23 to L24 | Not Ready | Gypsum Plastering Works | 2026-08-29 | 2026-10-06 | L23-24 | 100 | 0 |  | 2026-11-20 |  | 2026-12-26 |  | Tower B | Super Structure | L23 | Finishes | Gypsum Plastering Works
45626 | Tower B - Super Structure - Finishes & MEP - L23 to L24 | Not Ready | Gypsum Plastering Works | 2026-08-29 | 2026-10-06 | L23-24 | 100 | 0 |  | 2026-11-20 |  | 2026-12-26 |  | Tower B | Super Structure | L23
46756 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-09-09 | 2026-09-24 | False Ceiling | 100 | 0 |  | 2026-11-20 |  | 2026-12-04 |  | Tower B | Super Structure | L12 | Finishes | False Ceiling
41030 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-11-14 | 2026-11-17 | FAPA Cabling | 100 | 0 |  | 2026-11-21 |  | 2026-11-24 |  | Tower A | Super Structure | L75
44661 | NTA_Zone 2 - Super Structure - P3 to P4 | Not Ready | External Balustrade System | 2026-05-05 | 2026-05-21 | Drainage pipe | 100 | 0 |  | 2026-11-21 |  | 2026-12-08 |  | NTA_Zone 2 | Super Structure
44661 | NTA_Zone 2 - Super Structure - P3 to P4 | Not Ready | External Balustrade System | 2026-05-05 | 2026-05-21 | Drainage pipe | 100 | 0 |  | 2026-11-21 |  | 2026-12-08 |  | NTA_Zone 2 | Super Structure
9916 | T-16-Lift Lobby | Not Ready |  | 2026-12-09 | 2026-12-26 | 01F | 100 | 0 |  | 2026-11-22 |  | 2026-12-07
42092 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-11-16 | 2026-11-19 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-11-23 |  | 2026-11-26 |  | Tower A | Super Structure | L71 | MEP | FPS 2nd Fix - MEP & Finishes
42093 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-11-16 | 2026-11-21 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-11-23 |  | 2026-11-28 |  | Tower A | Super Structure | L71 | MEP | Electrical 2nd Fix - MEP & Finishes
42094 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-11-16 | 2026-11-24 | FAPA Device Fixing | 100 | 0 |  | 2026-11-23 |  | 2026-12-01 |  | Tower A | Super Structure | L71
42094 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-11-16 | 2026-11-24 | FAPA Device Fixing | 100 | 0 |  | 2026-11-23 |  | 2026-12-01 |  | Tower A | Super Structure | L71
42094 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-11-16 | 2026-11-24 | FAPA Device Fixing | 100 | 0 |  | 2026-11-23 |  | 2026-12-01 |  | Tower A | Super Structure | L71
42094 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-11-16 | 2026-11-24 | FAPA Device Fixing | 100 | 0 |  | 2026-11-23 |  | 2026-12-01 |  | Tower A | Super Structure | L71
42095 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-11-16 | 2026-11-19 | HVAC Grill Fixing | 100 | 0 |  | 2026-11-23 |  | 2026-11-26 |  | Tower A | Super Structure | L71 | MEP | HVAC Grill Fixing
48103 |  | Not Committed |  | 2026-09-28 | 2026-11-03 | Softscape Works | 100 | 0 |  | 2026-11-23 |  | 2026-12-28
48103 |  | Not Committed |  | 2026-09-28 | 2026-11-03 | Softscape Works | 100 | 0 |  | 2026-11-23 |  | 2026-12-28
48103 |  | Not Committed |  | 2026-09-28 | 2026-11-03 | Softscape Works | 100 | 0 |  | 2026-11-23 |  | 2026-12-28
48109 |  | Not Committed |  | 2026-09-28 | 2026-11-03 | Integrated Testing & Commissioning | 100 | 0 |  | 2026-11-23 |  | 2026-12-28
8876 | T-14-Lift Lobby | Not Ready |  | 2026-10-15 | 2026-11-02 | 01F | 100 | 0 |  | 2026-11-24 |  | 2026-12-12
11477 | T-19-Lift Lobby | Not Ready |  | 2026-12-04 | 2026-12-21 | GF | 100 | 0 |  | 2026-11-24 |  | 2026-12-11
41031 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-11-17 | 2026-11-25 | HVAC Ducting | 100 | 0 |  | 2026-11-24 |  | 2026-12-02 |  | Tower A | Super Structure | L75 | MEP | HVAC Ducting
41044 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-11-17 | 2026-11-23 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-11-24 |  | 2026-11-30 |  | Tower A | Super Structure | L76 | MEP | FPS 1st Fix - MEP & Finishes
41045 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-11-17 | 2026-11-20 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-11-24 |  | 2026-11-27 |  | Tower A | Super Structure | L76 | MEP | Electrical 1st Fixes
42081 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-11-17 | 2026-11-23 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-11-24 |  | 2026-11-30 |  | Tower A | Super Structure | L70 | MEP | Electrical
42082 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-11-17 | 2026-11-23 | Final Painting | 100 | 0 |  | 2026-11-24 |  | 2026-11-30 |  | Tower A | Super Structure | L70 | Finishes | Final Painting
42082 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-11-17 | 2026-11-23 | Final Painting | 100 | 0 |  | 2026-11-24 |  | 2026-11-30 |  | Tower A | Super Structure | L70 | Finishes | Final Painting
42082 | Tower A - Super Structure - Finishes & MEP - L70 to L71 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-11-17 | 2026-11-23 | Final Painting | 100 | 0 |  | 2026-11-24 |  | 2026-11-30 |  | Tower A | Super Structure | L70 | Finishes | Final Painting
45339 | Tower B - Super Structure - Core & Outer Slab L29-30 | Not Ready | RCC Works - Slab | 2026-08-26 | 2026-09-01 | Outer Slab_TA | 100 | 0 |  | 2026-11-24 |  | 2026-12-01 |  | Tower B | Super Structure | L29 | RCC Sub Structure | RCC Works - Slab
46961 |  | Not Committed |  | 2026-08-29 | 2027-09-14 | L24-25 | 100 | 0 |  | 2026-11-24 |  | 2027-10-14
46962 |  | Not Committed |  | 2026-08-29 | 2026-10-01 | MEP 1st Fixes | 100 | 0 |  | 2026-11-24 |  | 2026-12-26
46963 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-08-29 | 2026-09-05 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-11-24 |  | 2026-12-02 |  | Tower B | Super Structure | L24 | MEP | FPS 1st Fix - MEP & Finishes
46964 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-08-29 | 2026-09-03 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-11-24 |  | 2026-11-30 |  | Tower B | Super Structure | L24 | MEP | Electrical 1st Fixes
46965 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-08-29 | 2026-09-05 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-11-24 |  | 2026-12-02 |  | Tower B | Super Structure | L24
45507 | Tower B - Super Structure - Finishes & MEP - L25 to L26 | Not Ready | Partition Wall-Blockwork | 2026-08-27 | 2026-09-03 | Partition Walls | 100 | 0 |  | 2026-11-25 |  | 2026-12-03 |  | Tower B | Super Structure | L25
42096 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-11-19 | 2026-11-23 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-11-26 |  | 2026-11-30 |  | Tower A | Super Structure | L71
42123 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-11-19 | 2026-11-25 | False Ceiling | 100 | 0 |  | 2026-11-26 |  | 2026-12-02 |  | Tower A | Super Structure | L73 | Finishes | False Ceiling
42138 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-11-19 | 2026-12-01 | Flooring & Dado | 100 | 0 |  | 2026-11-26 |  | 2026-12-08 |  | Tower A | Super Structure | L74 | Finishes | Flooring & Dado
46809 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-09-16 | 2026-10-16 | Flooring & Dado works | 100 | 0 |  | 2026-11-26 |  | 2026-12-26 |  | Tower B | Super Structure | L15 | Finishes | Flooring & Dado
48076 |  | Not Ready |  | 2026-08-13 | 2026-08-20 | Insulation | 100 | 0 |  | 2026-11-26 |  | 2026-12-01
41046 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-11-20 | 2026-11-23 | FAPA Cabling | 100 | 0 |  | 2026-11-27 |  | 2026-11-30 |  | Tower A | Super Structure | L76
42108 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-11-21 | 2026-11-25 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-11-28 |  | 2026-12-02 |  | Tower A | Super Structure | L72 | MEP | FPS 2nd Fix - MEP & Finishes
42109 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-11-21 | 2026-11-27 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-11-28 |  | 2026-12-04 |  | Tower A | Super Structure | L72 | MEP | Electrical 2nd Fix - MEP & Finishes
42110 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-11-21 | 2026-11-30 | FAPA Device Fixing | 100 | 0 |  | 2026-11-28 |  | 2026-12-07 |  | Tower A | Super Structure | L72
42110 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-11-21 | 2026-11-30 | FAPA Device Fixing | 100 | 0 |  | 2026-11-28 |  | 2026-12-07 |  | Tower A | Super Structure | L72
42110 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-11-21 | 2026-11-30 | FAPA Device Fixing | 100 | 0 |  | 2026-11-28 |  | 2026-12-07 |  | Tower A | Super Structure | L72
42110 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-11-21 | 2026-11-30 | FAPA Device Fixing | 100 | 0 |  | 2026-11-28 |  | 2026-12-07 |  | Tower A | Super Structure | L72
42111 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-11-21 | 2026-11-25 | HVAC Grill Fixing | 100 | 0 |  | 2026-11-28 |  | 2026-12-02 |  | Tower A | Super Structure | L72 | MEP | HVAC Grill Fixing
41047 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-11-23 | 2026-12-01 | HVAC Ducting | 100 | 0 |  | 2026-11-30 |  | 2026-12-08 |  | Tower A | Super Structure | L76 | MEP | HVAC Ducting
42097 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-11-23 | 2026-11-28 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-11-30 |  | 2026-12-05 |  | Tower A | Super Structure | L71 | MEP | Electrical
42098 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-11-23 | 2026-11-28 | Final Painting | 100 | 0 |  | 2026-11-30 |  | 2026-12-05 |  | Tower A | Super Structure | L71 | Finishes | Final Painting
42098 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-11-23 | 2026-11-28 | Final Painting | 100 | 0 |  | 2026-11-30 |  | 2026-12-05 |  | Tower A | Super Structure | L71 | Finishes | Final Painting
42098 | Tower A - Super Structure - Finishes & MEP - L71 to L72 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-11-23 | 2026-11-28 | Final Painting | 100 | 0 |  | 2026-11-30 |  | 2026-12-05 |  | Tower A | Super Structure | L71 | Finishes | Final Painting
42148 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-11-23 | 2026-11-28 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-11-30 |  | 2026-12-05 |  | Tower A | Super Structure | L77 | MEP | FPS 1st Fix - MEP & Finishes
42149 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-11-23 | 2026-11-26 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-11-30 |  | 2026-12-03 |  | Tower A | Super Structure | L77 | MEP | Electrical 1st Fixes
46808 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-09-21 | 2026-09-28 | Door & Window Frame work | 100 | 0 |  | 2026-11-30 |  | 2026-12-08 |  | Tower B | Super Structure | L15 | Finishes | Door & Window Frame work
46824 |  | Not Committed |  | 2026-09-21 | 2026-11-12 | Finishes after 1st Fix | 100 | 0 |  | 2026-11-30 |  | 2027-01-21
46825 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-09-21 | 2026-10-01 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-11-30 |  | 2026-12-11 |  | Tower B | Super Structure | L16 | Finishes | Blockwork
47423 | Tower B - Super Structure - Finishes & MEP - L18 to L23 | Not Ready | Façade Works - MEP & Finishes | 2026-09-21 | 2026-10-01 | DGU Assembly Installation | 100 | 0 |  | 2026-11-30 |  | 2026-12-11 |  | Tower B | Super Structure | L18 | Façade | Façade Works
47424 | Tower B - Super Structure - Finishes & MEP - L18 to L23 | Not Ready | Façade Works - MEP & Finishes | 2026-09-21 | 2026-10-21 | Installation of highly reflective metal sheet | 100 | 0 |  | 2026-11-30 |  | 2026-12-30 |  | Tower B | Super Structure | L18 | Façade | Façade Works
47425 | Tower B - Super Structure - Finishes & MEP - L18 to L23 | Not Ready | Façade Works - MEP & Finishes | 2026-09-21 | 2026-10-08 | Fixing of Backlit Laminated Glass assembly & ACP Panels | 100 | 0 |  | 2026-11-30 |  | 2026-12-17 |  | Tower B | Super Structure | L18 | Façade | Façade Works
47426 | Tower B - Super Structure - Finishes & MEP - L18 to L23 | Not Ready | Façade Works - MEP & Finishes | 2026-09-21 | 2026-10-08 | Fixing of Louvers | 100 | 0 |  | 2026-11-30 |  | 2026-12-17 |  | Tower B | Super Structure | L18 | Façade | Façade Works
47426 | Tower B - Super Structure - Finishes & MEP - L18 to L23 | Not Ready | Façade Works - MEP & Finishes | 2026-09-21 | 2026-10-08 | Fixing of Louvers | 100 | 0 |  | 2026-11-30 |  | 2026-12-17 |  | Tower B | Super Structure | L18
45340 |  | Not Ready |  | 2026-09-02 | 2026-09-12 | L30-31 | 100 | 0 |  | 2026-12-01 |  | 2026-12-12
45340 |  | Not Ready |  | 2026-09-02 | 2026-09-12 | L30-31 | 100 | 0 |  | 2026-12-01 |  | 2026-12-12 |  |  |  |  | Finishes | Gypsum Plastering Works
45341 | Tower B - Super Structure - Core & Outer Slab L30-31 | Not Ready | RCC Works - Vertical | 2026-09-02 | 2026-09-10 | Outer Columns_TA | 100 | 0 |  | 2026-12-01 |  | 2026-12-10 |  | Tower B | Super Structure | L30 | RCC Sub Structure | RCC Works - Vertical
45513 |  | Not Committed |  | 2026-09-02 | 2026-10-06 | L27-28 | 100 | 0 |  | 2026-12-01 |  | 2027-01-02
45513 |  | Not Committed |  | 2026-09-02 | 2026-10-06 | L27-28 | 100 | 0 |  | 2026-12-01 |  | 2027-01-02 |  |  |  |  | Finishes | Gypsum Plastering Works
45514 | Tower B - Super Structure - Finishes & MEP - L27 to L28 | Not Ready | Partition Wall-Blockwork | 2026-09-02 | 2026-09-21 | De-shuttering & Area clearance | 100 | 0 |  | 2026-12-01 |  | 2026-12-18 |  | Tower B | Super Structure | L27
41034 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-11-25 | 2026-12-07 | Flooring & Dado | 100 | 0 |  | 2026-12-02 |  | 2026-12-14 |  | Tower A | Super Structure | L75 | Finishes | Flooring & Dado
42112 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-11-25 | 2026-11-28 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-12-02 |  | 2026-12-05 |  | Tower A | Super Structure | L72
42124 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-11-25 | 2026-11-28 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-12-02 |  | 2026-12-05 |  | Tower A | Super Structure | L73 | MEP | FPS 2nd Fix - MEP & Finishes
42125 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-11-25 | 2026-12-01 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-12-02 |  | 2026-12-08 |  | Tower A | Super Structure | L73 | MEP | Electrical 2nd Fix - MEP & Finishes
42126 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-11-25 | 2026-12-03 | FAPA Device Fixing | 100 | 0 |  | 2026-12-02 |  | 2026-12-10 |  | Tower A | Super Structure | L73
42126 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-11-25 | 2026-12-03 | FAPA Device Fixing | 100 | 0 |  | 2026-12-02 |  | 2026-12-10 |  | Tower A | Super Structure | L73
42126 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-11-25 | 2026-12-03 | FAPA Device Fixing | 100 | 0 |  | 2026-12-02 |  | 2026-12-10 |  | Tower A | Super Structure | L73
42126 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-11-25 | 2026-12-03 | FAPA Device Fixing | 100 | 0 |  | 2026-12-02 |  | 2026-12-10 |  | Tower A | Super Structure | L73
42127 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-11-25 | 2026-11-28 | HVAC Grill Fixing | 100 | 0 |  | 2026-12-02 |  | 2026-12-05 |  | Tower A | Super Structure | L73 | MEP | HVAC Grill Fixing
42139 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-11-25 | 2026-12-01 | False Ceiling | 100 | 0 |  | 2026-12-02 |  | 2026-12-08 |  | Tower A | Super Structure | L74 | Finishes | False Ceiling
45747 | Tower B - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2026-09-14 | 2026-10-22 | Electrical Rising Mains | 100 | 0 |  | 2026-12-02 |  | 2027-01-07 |  | Tower B | Super Structure | L15
46774 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-09-23 | 2026-10-07 | False Ceiling | 100 | 0 |  | 2026-12-02 |  | 2026-12-16 |  | Tower B | Super Structure | L13 | Finishes | False Ceiling
46966 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-09-07 | 2026-09-25 | Wet Area Waterproofing | 100 | 0 |  | 2026-12-02 |  | 2026-12-19 |  | Tower B | Super Structure | L24
47640 |  | Not Ready |  | 2026-05-02 | 2026-05-09 | Section 6_lift 1 | 100 | 0 |  | 2026-12-02 |  | 2026-12-10
47640 |  | Not Ready |  | 2026-05-02 | 2026-05-09 | Section 6_lift 1 | 100 | 0 |  | 2026-12-02 |  | 2026-12-10 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47805 |  | Not Ready |  | 2026-05-02 | 2026-06-18 | B3 to B2 | 100 | 0 |  | 2026-12-02 |  | 2027-01-19
47805 |  | Not Ready |  | 2026-05-02 | 2026-06-18 | B3 to B2 | 100 | 0 |  | 2026-12-02 |  | 2027-01-19
47805 |  | Not Ready |  | 2026-05-02 | 2026-06-18 | B3 to B2 | 100 | 0 |  | 2026-12-02 |  | 2027-01-19
48077 |  | Not Ready |  | 2026-08-24 | 2026-09-03 | Al. sheet cladding | 100 | 0 |  | 2026-12-02 |  | 2026-12-12
42150 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-11-26 | 2026-11-28 | FAPA Cabling | 100 | 0 |  | 2026-12-03 |  | 2026-12-05 |  | Tower A | Super Structure | L77
44653 |  | Not Committed |  | 2026-05-16 | 2026-07-08 | P4 level | 100 | 0 |  | 2026-12-03 |  | 2027-01-25
44654 | NTA_Zone 2 - Super Structure - P4 to P5 | Not Ready | External Balustrade System | 2026-05-16 | 2026-06-15 | RCC upstand | 100 | 0 |  | 2026-12-03 |  | 2027-01-01 |  | NTA_Zone 2 | Super Structure
44654 | NTA_Zone 2 - Super Structure - P4 to P5 | Not Ready | External Balustrade System | 2026-05-16 | 2026-06-15 | RCC upstand | 100 | 0 |  | 2026-12-03 |  | 2027-01-01 |  | NTA_Zone 2 | Super Structure
44662 | NTA_Zone 2 - Super Structure - P3 to P4 | Not Ready | External Balustrade System | 2026-05-16 | 2026-06-03 | SS tray work | 100 | 0 |  | 2026-12-03 |  | 2026-12-19 |  | NTA_Zone 2 | Super Structure
45508 | Tower B - Super Structure - Finishes & MEP - L25 to L26 | Not Ready | Partition Wall-Blockwork | 2026-09-04 | 2026-09-09 | Staircase Area | 100 | 0 |  | 2026-12-03 |  | 2026-12-09 |  | Tower B | Super Structure | L25
46949 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-09-12 | 2026-09-25 | Cement Plastering in wet areas | 100 | 0 |  | 2026-12-04 |  | 2026-12-16 |  | Tower B | Super Structure | L23
42113 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-11-28 | 2026-12-04 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-12-05 |  | 2026-12-11 |  | Tower A | Super Structure | L72 | MEP | Electrical
42114 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-11-28 | 2026-12-04 | Final Painting | 100 | 0 |  | 2026-12-05 |  | 2026-12-11 |  | Tower A | Super Structure | L72 | Finishes | Final Painting
42114 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-11-28 | 2026-12-04 | Final Painting | 100 | 0 |  | 2026-12-05 |  | 2026-12-11 |  | Tower A | Super Structure | L72 | Finishes | Final Painting
42114 | Tower A - Super Structure - Finishes & MEP - L72 to L73 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-11-28 | 2026-12-04 | Final Painting | 100 | 0 |  | 2026-12-05 |  | 2026-12-11 |  | Tower A | Super Structure | L72 | Finishes | Final Painting
42128 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-11-28 | 2026-12-02 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-12-05 |  | 2026-12-09 |  | Tower A | Super Structure | L73
42151 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-11-28 | 2026-12-04 | HVAC Ducting | 100 | 0 |  | 2026-12-05 |  | 2026-12-11 |  | Tower A | Super Structure | L77 | MEP | HVAC Ducting
45342 | Tower B - Super Structure - Core & Outer Slab L30-31 | Not Ready | RCC Works - Slab | 2026-09-07 | 2026-09-12 | Outer Slab_TA | 100 | 0 |  | 2026-12-05 |  | 2026-12-12 |  | Tower B | Super Structure | L30 | RCC Sub Structure | RCC Works - Slab
45627 | Tower B - Super Structure - Finishes & MEP - L24 to L25 | Not Ready | Gypsum Plastering Works | 2026-09-10 | 2026-10-17 | L24-25 | 100 | 0 |  | 2026-12-05 |  | 2027-01-11 |  | Tower B | Super Structure | L24 | Finishes | Gypsum Plastering Works
45627 | Tower B - Super Structure - Finishes & MEP - L24 to L25 | Not Ready | Gypsum Plastering Works | 2026-09-10 | 2026-10-17 | L24-25 | 100 | 0 |  | 2026-12-05 |  | 2027-01-11 |  | Tower B | Super Structure | L24
48222 | Retail - Super structure - GF to R1 | Not Ready |  | 2026-06-06 | 2026-09-10 | GF to R1 (Meter Room, Toilets, Fire command, DG, shafts) | 100 | 0 |  | 2026-12-05 |  | 2027-03-04 |  | Retail | Super Structure | GF
45511 | Tower B - Super Structure - Finishes & MEP - L26 to L27 | Not Ready | Partition Wall-Blockwork | 2026-09-08 | 2026-09-16 | Partition Walls | 100 | 0 |  | 2026-12-07 |  | 2026-12-15 |  | Tower B | Super Structure | L26
9917 | T-16-Lift Lobby | Not Ready |  | 2026-12-26 | 2027-01-11 | GF | 100 | 0 |  | 2026-12-08 |  | 2026-12-25
41035 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-12-01 | 2026-12-07 | False Ceiling | 100 | 0 |  | 2026-12-08 |  | 2026-12-14 |  | Tower A | Super Structure | L75 | Finishes | False Ceiling
41050 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-12-01 | 2026-12-12 | Flooring & Dado | 100 | 0 |  | 2026-12-08 |  | 2026-12-19 |  | Tower A | Super Structure | L76 | Finishes | Flooring & Dado
42140 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-12-01 | 2026-12-04 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-12-08 |  | 2026-12-11 |  | Tower A | Super Structure | L74 | MEP | FPS 2nd Fix - MEP & Finishes
42141 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-12-01 | 2026-12-07 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-12-08 |  | 2026-12-14 |  | Tower A | Super Structure | L74 | MEP | Electrical 2nd Fix - MEP & Finishes
42142 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-01 | 2026-12-09 | FAPA Device Fixing | 100 | 0 |  | 2026-12-08 |  | 2026-12-16 |  | Tower A | Super Structure | L74
42142 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-01 | 2026-12-09 | FAPA Device Fixing | 100 | 0 |  | 2026-12-08 |  | 2026-12-16 |  | Tower A | Super Structure | L74
42142 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-01 | 2026-12-09 | FAPA Device Fixing | 100 | 0 |  | 2026-12-08 |  | 2026-12-16 |  | Tower A | Super Structure | L74
42142 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-01 | 2026-12-09 | FAPA Device Fixing | 100 | 0 |  | 2026-12-08 |  | 2026-12-16 |  | Tower A | Super Structure | L74
42143 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-12-01 | 2026-12-04 | HVAC Grill Fixing | 100 | 0 |  | 2026-12-08 |  | 2026-12-11 |  | Tower A | Super Structure | L74 | MEP | HVAC Grill Fixing
46827 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-09-29 | 2026-10-29 | Flooring & Dado works | 100 | 0 |  | 2026-12-08 |  | 2027-01-07 |  | Tower B | Super Structure | L16 | Finishes | Flooring & Dado
42129 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-12-02 | 2026-12-08 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-12-09 |  | 2026-12-15 |  | Tower A | Super Structure | L73 | MEP | Electrical
42130 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-12-02 | 2026-12-08 | Final Painting | 100 | 0 |  | 2026-12-09 |  | 2026-12-15 |  | Tower A | Super Structure | L73 | Finishes | Final Painting
42130 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-12-02 | 2026-12-08 | Final Painting | 100 | 0 |  | 2026-12-09 |  | 2026-12-15 |  | Tower A | Super Structure | L73 | Finishes | Final Painting
42130 | Tower A - Super Structure - Finishes & MEP - L73 to L74 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-12-02 | 2026-12-08 | Final Painting | 100 | 0 |  | 2026-12-09 |  | 2026-12-15 |  | Tower A | Super Structure | L73 | Finishes | Final Painting
44663 | NTA_Zone 2 - Super Structure - P3 to P4 | Not Ready | External Balustrade System | 2026-05-22 | 2026-06-09 | GRC framing & GRC cladding | 100 | 0 |  | 2026-12-09 |  | 2026-12-26 |  | NTA_Zone 2 | Super Structure
44664 | NTA_Zone 2 - Super Structure - P3 to P4 | Not Ready | External Balustrade System | 2026-05-22 | 2026-06-09 | Planter works | 100 | 0 |  | 2026-12-09 |  | 2026-12-26 |  | NTA_Zone 2 | Super Structure
44664 | NTA_Zone 2 - Super Structure - P3 to P4 | Not Ready | External Balustrade System | 2026-05-22 | 2026-06-09 | Planter works | 100 | 0 |  | 2026-12-09 |  | 2026-12-26 |  | NTA_Zone 2 | Super Structure
46979 |  | Not Committed |  | 2026-09-10 | 2027-09-29 | L25-26 | 100 | 0 |  | 2026-12-09 |  | 2027-10-26
46979 |  | Not Committed |  | 2026-09-10 | 2027-09-29 | L25-26 | 100 | 0 |  | 2026-12-09 |  | 2027-10-26 |  |  |  |  | Finishes | Gypsum Plastering Works
46980 |  | Not Committed |  | 2026-09-10 | 2026-10-21 | MEP 1st Fixes | 100 | 0 |  | 2026-12-09 |  | 2027-01-16
46981 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-09-10 | 2026-09-19 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-12-09 |  | 2026-12-17 |  | Tower B | Super Structure | L25 | MEP | FPS 1st Fix - MEP & Finishes
46982 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-09-10 | 2026-09-16 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-12-09 |  | 2026-12-15 |  | Tower B | Super Structure | L25 | MEP | Electrical 1st Fixes
46983 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-09-10 | 2026-09-19 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-12-09 |  | 2026-12-17 |  | Tower B | Super Structure | L25
44272 |  | Not Ready |  | 2026-10-24 | 2026-10-29 | CFO Visit 1 | 100 | 0 |  | 2026-12-10 |  | 2027-02-03
47643 |  | Not Ready |  | 2026-05-11 | 2026-05-18 | Section 9_lift 1 | 100 | 0 |  | 2026-12-10 |  | 2026-12-18
47643 |  | Not Ready |  | 2026-05-11 | 2026-05-18 | Section 9_lift 1 | 100 | 0 |  | 2026-12-10 |  | 2026-12-18 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47672 |  | Not Ready |  | 2026-07-04 | 2026-07-17 | Section 6_lift 1 | 100 | 0 |  | 2026-12-10 |  | 2026-12-23
47672 |  | Not Ready |  | 2026-07-04 | 2026-07-17 | Section 6_lift 1 | 100 | 0 |  | 2026-12-10 |  | 2026-12-23 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
42144 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-12-04 | 2026-12-08 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-12-11 |  | 2026-12-15 |  | Tower A | Super Structure | L74
42154 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-12-04 | 2026-12-16 | Flooring & Dado | 100 | 0 |  | 2026-12-11 |  | 2026-12-23 |  | Tower A | Super Structure | L77 | Finishes | Flooring & Dado
46826 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-10-03 | 2026-10-10 | Door & Window Frame work | 100 | 0 |  | 2026-12-11 |  | 2026-12-19 |  | Tower B | Super Structure | L16 | Finishes | Door & Window Frame work
46842 |  | Not Committed |  | 2026-10-03 | 2026-11-24 | Finishes after 1st Fix | 100 | 0 |  | 2026-12-11 |  | 2027-02-03
46843 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-10-03 | 2026-10-14 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-12-11 |  | 2026-12-23 |  | Tower B | Super Structure | L17 | Finishes | Blockwork
47427 | Tower B - Super Structure - Finishes & MEP - L18 to L23 | Not Ready | Façade Works - MEP & Finishes | 2026-10-03 | 2026-10-21 | Accessories & Alignment | 100 | 0 |  | 2026-12-11 |  | 2026-12-30 |  | Tower B | Super Structure | L18 | Façade | Façade Works
47427 | Tower B - Super Structure - Finishes & MEP - L18 to L23 | Not Ready | Façade Works - MEP & Finishes | 2026-10-03 | 2026-10-21 | Accessories & Alignment | 100 | 0 |  | 2026-12-11 |  | 2026-12-30 |  | Tower B | Super Structure | L18
11478 | T-19-Lift Lobby | Not Ready |  | 2026-12-21 | 2027-01-06 | BF | 100 | 0 |  | 2026-12-12 |  | 2026-12-30
45343 |  | Not Ready |  | 2026-09-14 | 2026-09-26 | L31-32 | 100 | 0 |  | 2026-12-12 |  | 2026-12-24
45343 |  | Not Ready |  | 2026-09-14 | 2026-09-26 | L31-32 | 100 | 0 |  | 2026-12-12 |  | 2026-12-24 |  |  |  |  | Finishes | Gypsum Plastering Works
45344 | Tower B - Super Structure - Core & Outer Slab L31-32 | Not Ready | RCC Works - Vertical | 2026-09-14 | 2026-09-24 | Outer Columns_TA | 100 | 0 |  | 2026-12-12 |  | 2026-12-22 |  | Tower B | Super Structure | L31 | RCC Sub Structure | RCC Works - Vertical
45517 |  | Not Committed |  | 2026-09-14 | 2026-10-17 | L28-29 | 100 | 0 |  | 2026-12-12 |  | 2027-01-14
45517 |  | Not Committed |  | 2026-09-14 | 2026-10-17 | L28-29 | 100 | 0 |  | 2026-12-12 |  | 2027-01-14 |  |  |  |  | Finishes | Gypsum Plastering Works
45518 | Tower B - Super Structure - Finishes & MEP - L28 to L29 | Not Ready | Partition Wall-Blockwork | 2026-09-14 | 2026-10-03 | De-shuttering & Area clearance | 100 | 0 |  | 2026-12-12 |  | 2026-12-31 |  | Tower B | Super Structure | L28
8877 | T-14-Lift Lobby | Not Ready |  | 2026-11-02 | 2026-11-18 | GF | 100 | 0 |  | 2026-12-13 |  | 2026-12-30
41036 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-12-07 | 2026-12-10 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-12-14 |  | 2026-12-17 |  | Tower A | Super Structure | L75 | MEP | FPS 2nd Fix - MEP & Finishes
41037 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-12-07 | 2026-12-12 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-12-14 |  | 2026-12-19 |  | Tower A | Super Structure | L75 | MEP | Electrical 2nd Fix - MEP & Finishes
41038 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-07 | 2026-12-15 | FAPA Device Fixing | 100 | 0 |  | 2026-12-14 |  | 2026-12-22 |  | Tower A | Super Structure | L75
41038 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-07 | 2026-12-15 | FAPA Device Fixing | 100 | 0 |  | 2026-12-14 |  | 2026-12-22 |  | Tower A | Super Structure | L75
41038 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-07 | 2026-12-15 | FAPA Device Fixing | 100 | 0 |  | 2026-12-14 |  | 2026-12-22 |  | Tower A | Super Structure | L75
41038 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-07 | 2026-12-15 | FAPA Device Fixing | 100 | 0 |  | 2026-12-14 |  | 2026-12-22 |  | Tower A | Super Structure | L75
41039 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-12-07 | 2026-12-10 | HVAC Grill Fixing | 100 | 0 |  | 2026-12-14 |  | 2026-12-17 |  | Tower A | Super Structure | L75 | MEP | HVAC Grill Fixing
41051 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-12-07 | 2026-12-12 | False Ceiling | 100 | 0 |  | 2026-12-14 |  | 2026-12-19 |  | Tower A | Super Structure | L76 | Finishes | False Ceiling
46045 |  | Not Committed |  | 2026-10-06 | 2028-03-29 | Typical Floor Lobby | 100 | 0 |  | 2026-12-14 |  | 2028-06-08
46046 |  | Not Committed |  | 2026-10-06 | 2027-09-30 | L7-8 | 100 | 0 |  | 2026-12-14 |  | 2027-11-04
46046 |  | Not Committed |  | 2026-10-06 | 2027-09-30 | L7-8 | 100 | 0 |  | 2026-12-14 |  | 2027-11-04 |  |  |  |  | Finishes | Gypsum Plastering Works
46047 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-10-06 | 2026-10-16 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-12-14 |  | 2026-12-26 |  | Tower B | Super Structure | L7 | MEP | FPS 1st Fix - MEP & Finishes
46048 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-10-06 | 2026-10-13 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-12-14 |  | 2026-12-22 |  | Tower B | Super Structure | L7 | MEP | Electrical 1st Fixes
46792 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-10-06 | 2026-10-19 | False Ceiling | 100 | 0 |  | 2026-12-14 |  | 2026-12-29 |  | Tower B | Super Structure | L14 | Finishes | False Ceiling
48078 |  | Not Committed |  | 2026-09-04 | 2026-10-05 | dwg Rt-08 | 100 | 0 |  | 2026-12-14 |  | 2027-01-11
48079 |  | Not Ready |  | 2026-09-04 | 2026-09-11 | Erection of Vertical steel tube with folded steel sheet | 100 | 0 |  | 2026-12-14 |  | 2026-12-21
42145 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-12-08 | 2026-12-14 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-12-15 |  | 2026-12-21 |  | Tower A | Super Structure | L74 | MEP | Electrical
42146 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-12-08 | 2026-12-14 | Final Painting | 100 | 0 |  | 2026-12-15 |  | 2026-12-21 |  | Tower A | Super Structure | L74 | Finishes | Final Painting
42146 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-12-08 | 2026-12-14 | Final Painting | 100 | 0 |  | 2026-12-15 |  | 2026-12-21 |  | Tower A | Super Structure | L74 | Finishes | Final Painting
42146 | Tower A - Super Structure - Finishes & MEP - L74 to L75 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-12-08 | 2026-12-14 | Final Painting | 100 | 0 |  | 2026-12-15 |  | 2026-12-21 |  | Tower A | Super Structure | L74 | Finishes | Final Painting
45512 | Tower B - Super Structure - Finishes & MEP - L26 to L27 | Not Ready | Partition Wall-Blockwork | 2026-09-18 | 2026-09-23 | Staircase Area | 100 | 0 |  | 2026-12-15 |  | 2026-12-21 |  | Tower B | Super Structure | L26
41040 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-12-10 | 2026-12-14 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-12-17 |  | 2026-12-21 |  | Tower A | Super Structure | L75
42155 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-12-10 | 2026-12-16 | False Ceiling | 100 | 0 |  | 2026-12-17 |  | 2026-12-23 |  | Tower A | Super Structure | L77 | Finishes | False Ceiling
45345 | Tower B - Super Structure - Core & Outer Slab L31-32 | Not Ready | RCC Works - Slab | 2026-09-21 | 2026-09-26 | Outer Slab_TA | 100 | 0 |  | 2026-12-17 |  | 2026-12-24 |  | Tower B | Super Structure | L31 | RCC Sub Structure | RCC Works - Slab
46984 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-09-21 | 2026-10-08 | Wet Area Waterproofing | 100 | 0 |  | 2026-12-17 |  | 2027-01-05 |  | Tower B | Super Structure | L25
45515 | Tower B - Super Structure - Finishes & MEP - L27 to L28 | Not Ready | Partition Wall-Blockwork | 2026-09-22 | 2026-09-29 | Partition Walls | 100 | 0 |  | 2026-12-18 |  | 2026-12-28 |  | Tower B | Super Structure | L27
47644 |  | Not Ready |  | 2026-05-19 | 2026-05-26 | Section 10_lift 1 | 100 | 0 |  | 2026-12-18 |  | 2026-12-28
47644 |  | Not Ready |  | 2026-05-19 | 2026-05-26 | Section 10_lift 1 | 100 | 0 |  | 2026-12-18 |  | 2026-12-28 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
41052 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-12-12 | 2026-12-16 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-12-19 |  | 2026-12-23 |  | Tower A | Super Structure | L76 | MEP | FPS 2nd Fix - MEP & Finishes
41053 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-12-12 | 2026-12-18 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-12-19 |  | 2026-12-26 |  | Tower A | Super Structure | L76 | MEP | Electrical 2nd Fix - MEP & Finishes
41054 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-12 | 2026-12-21 | FAPA Device Fixing | 100 | 0 |  | 2026-12-19 |  | 2026-12-29 |  | Tower A | Super Structure | L76
41054 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-12 | 2026-12-21 | FAPA Device Fixing | 100 | 0 |  | 2026-12-19 |  | 2026-12-29 |  | Tower A | Super Structure | L76
41054 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-12 | 2026-12-21 | FAPA Device Fixing | 100 | 0 |  | 2026-12-19 |  | 2026-12-29 |  | Tower A | Super Structure | L76
41054 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-12 | 2026-12-21 | FAPA Device Fixing | 100 | 0 |  | 2026-12-19 |  | 2026-12-29 |  | Tower A | Super Structure | L76
41055 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-12-12 | 2026-12-16 | HVAC Grill Fixing | 100 | 0 |  | 2026-12-19 |  | 2026-12-23 |  | Tower A | Super Structure | L76 | MEP | HVAC Grill Fixing
46845 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-10-12 | 2026-11-10 | Flooring & Dado works | 100 | 0 |  | 2026-12-19 |  | 2027-01-19 |  | Tower B | Super Structure | L17 | Finishes | Flooring & Dado
46967 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-09-26 | 2026-10-01 | Cement Plastering in wet areas | 100 | 0 |  | 2026-12-19 |  | 2026-12-26 |  | Tower B | Super Structure | L24
41041 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-12-14 | 2026-12-19 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-12-21 |  | 2026-12-28 |  | Tower A | Super Structure | L75 | MEP | Electrical
41042 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-12-14 | 2026-12-19 | Final Painting | 100 | 0 |  | 2026-12-21 |  | 2026-12-28 |  | Tower A | Super Structure | L75 | Finishes | Final Painting
41042 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-12-14 | 2026-12-19 | Final Painting | 100 | 0 |  | 2026-12-21 |  | 2026-12-28 |  | Tower A | Super Structure | L75 | Finishes | Final Painting
41042 | Tower A - Super Structure - Finishes & MEP - L75 to L76 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-12-14 | 2026-12-19 | Final Painting | 100 | 0 |  | 2026-12-21 |  | 2026-12-28 |  | Tower A | Super Structure | L75 | Finishes | Final Painting
44655 | NTA_Zone 2 - Super Structure - P4 to P5 | Not Ready | External Balustrade System | 2026-06-04 | 2026-06-20 | Drainage pipe | 100 | 0 |  | 2026-12-21 |  | 2027-01-07 |  | NTA_Zone 2 | Super Structure
44655 | NTA_Zone 2 - Super Structure - P4 to P5 | Not Ready | External Balustrade System | 2026-06-04 | 2026-06-20 | Drainage pipe | 100 | 0 |  | 2026-12-21 |  | 2027-01-07 |  | NTA_Zone 2 | Super Structure
45628 | Tower B - Super Structure - Finishes & MEP - L25 to L26 | Not Ready | Gypsum Plastering Works | 2026-09-24 | 2026-10-30 | L25-26 | 100 | 0 |  | 2026-12-21 |  | 2027-01-27 |  | Tower B | Super Structure | L25 | Finishes | Gypsum Plastering Works
45628 | Tower B - Super Structure - Finishes & MEP - L25 to L26 | Not Ready | Gypsum Plastering Works | 2026-09-24 | 2026-10-30 | L25-26 | 100 | 0 |  | 2026-12-21 |  | 2027-01-27 |  | Tower B | Super Structure | L25
46997 |  | Not Committed |  | 2026-09-24 | 2027-10-15 | L26-27 | 100 | 0 |  | 2026-12-21 |  | 2027-11-08
46997 |  | Not Committed |  | 2026-09-24 | 2027-10-15 | L26-27 | 100 | 0 |  | 2026-12-21 |  | 2027-11-08 |  |  |  |  | Finishes | Gypsum Plastering Works
46998 |  | Not Committed |  | 2026-09-24 | 2026-11-02 | MEP 1st Fixes | 100 | 0 |  | 2026-12-21 |  | 2027-01-29
46999 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-09-24 | 2026-10-01 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-12-21 |  | 2026-12-30 |  | Tower B | Super Structure | L26 | MEP | FPS 1st Fix - MEP & Finishes
47000 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-09-24 | 2026-09-29 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2026-12-21 |  | 2026-12-28 |  | Tower B | Super Structure | L26 | MEP | Electrical 1st Fixes
47001 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-09-24 | 2026-10-01 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2026-12-21 |  | 2026-12-30 |  | Tower B | Super Structure | L26
46049 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-10-14 | 2026-10-22 | FAPA Cabling | 100 | 0 |  | 2026-12-22 |  | 2026-12-31 |  | Tower B | Super Structure | L7
48080 |  | Not Ready |  | 2026-09-12 | 2026-09-22 | Al. add-on + Al. sheet wrapping + Al. boxing | 100 | 0 |  | 2026-12-22 |  | 2026-12-30
41056 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-12-16 | 2026-12-19 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-12-23 |  | 2026-12-28 |  | Tower A | Super Structure | L76
42156 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-12-16 | 2026-12-19 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2026-12-23 |  | 2026-12-28 |  | Tower A | Super Structure | L77 | MEP | FPS 2nd Fix - MEP & Finishes
42157 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-12-16 | 2026-12-22 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2026-12-23 |  | 2026-12-30 |  | Tower A | Super Structure | L77 | MEP | Electrical 2nd Fix - MEP & Finishes
42158 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-16 | 2026-12-24 | FAPA Device Fixing | 100 | 0 |  | 2026-12-23 |  | 2027-01-01 |  | Tower A | Super Structure | L77
42158 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-16 | 2026-12-24 | FAPA Device Fixing | 100 | 0 |  | 2026-12-23 |  | 2027-01-01 |  | Tower A | Super Structure | L77
42158 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-16 | 2026-12-24 | FAPA Device Fixing | 100 | 0 |  | 2026-12-23 |  | 2027-01-01 |  | Tower A | Super Structure | L77
42158 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-16 | 2026-12-24 | FAPA Device Fixing | 100 | 0 |  | 2026-12-23 |  | 2027-01-01 |  | Tower A | Super Structure | L77
42159 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-12-16 | 2026-12-19 | HVAC Grill Fixing | 100 | 0 |  | 2026-12-23 |  | 2026-12-28 |  | Tower A | Super Structure | L77 | MEP | HVAC Grill Fixing
46844 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-10-15 | 2026-10-23 | Door & Window Frame work | 100 | 0 |  | 2026-12-23 |  | 2027-01-01 |  | Tower B | Super Structure | L17 | Finishes | Door & Window Frame work
46860 |  | Not Committed |  | 2026-10-15 | 2026-12-05 | Finishes after 1st Fix | 100 | 0 |  | 2026-12-23 |  | 2027-02-15
46861 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-10-15 | 2026-10-27 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2026-12-23 |  | 2027-01-05 |  | Tower B | Super Structure | L18 | Finishes | Blockwork
47675 |  | Not Ready |  | 2026-07-24 | 2026-08-07 | Section 9_lift 1 | 100 | 0 |  | 2026-12-23 |  | 2027-01-06
47675 |  | Not Ready |  | 2026-07-24 | 2026-08-07 | Section 9_lift 1 | 100 | 0 |  | 2026-12-23 |  | 2027-01-06 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47684 |  | Not Ready |  | 2026-07-24 | 2026-08-01 | Section 6_lift 2 | 100 | 0 |  | 2026-12-23 |  | 2027-01-01
47684 |  | Not Ready |  | 2026-07-24 | 2026-08-01 | Section 6_lift 2 | 100 | 0 |  | 2026-12-23 |  | 2027-01-01 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
45346 |  | Not Ready |  | 2026-09-28 | 2026-10-09 | L32-33 | 100 | 0 |  | 2026-12-24 |  | 2027-01-06
45346 |  | Not Ready |  | 2026-09-28 | 2026-10-09 | L32-33 | 100 | 0 |  | 2026-12-24 |  | 2027-01-06 |  |  |  |  | Finishes | Gypsum Plastering Works
45347 | Tower B - Super Structure - Core & Outer Slab L32-33 | Not Ready | RCC Works - Vertical | 2026-09-28 | 2026-10-07 | Outer Columns_TA | 100 | 0 |  | 2026-12-24 |  | 2027-01-04 |  | Tower B | Super Structure | L32 | RCC Sub Structure | RCC Works - Vertical
45521 |  | Not Committed |  | 2026-09-28 | 2026-10-30 | L29-30 | 100 | 0 |  | 2026-12-24 |  | 2027-01-27
45521 |  | Not Committed |  | 2026-09-28 | 2026-10-30 | L29-30 | 100 | 0 |  | 2026-12-24 |  | 2027-01-27 |  |  |  |  | Finishes | Gypsum Plastering Works
45522 | Tower B - Super Structure - Finishes & MEP - L29 to L30 | Not Ready | Partition Wall-Blockwork | 2026-09-28 | 2026-10-15 | De-shuttering & Area clearance | 100 | 0 |  | 2026-12-24 |  | 2027-01-12 |  | Tower B | Super Structure | L29
45648 |  | Not Ready |  | 2026-11-10 | 2028-07-20 | High Side Services | 100 | 0 |  | 2026-12-24 |  | 2028-07-31
45707 |  | Not Committed |  | 2026-11-10 | 2028-01-29 | HVAC at MEP Service Floors | 100 | 0 |  | 2026-12-24 |  | 2028-03-16
45708 | Tower B - Super Structure - Finishes & MEP - MEP Service Floors | Not Ready |  | 2026-11-10 | 2027-06-12 | Staircase Pressurization Fans Installation | 100 | 0 |  | 2026-12-24 |  | 2027-07-28 |  | Tower B | Super Structure
9918 | T-16-Lift Lobby | Not Ready |  | 2027-01-11 | 2027-01-29 | BF | 100 | 0 |  | 2026-12-26 |  | 2027-01-12
46018 |  | Not Committed |  | 2026-10-17 | 2026-12-07 | Lobby/ Common Area | 100 | 0 |  | 2026-12-26 |  | 2027-02-16
46019 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-10-17 | 2026-10-26 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-12-26 |  | 2027-01-04 |  | Tower B | Super Structure |  | MEP | FPS 1st Fix - MEP & Finishes
46020 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-10-17 | 2026-10-21 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-12-26 |  | 2026-12-30 |  | Tower B | Super Structure |  | MEP | Electrical 1st Fixes
46050 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-10-17 | 2026-10-29 | HVAC Ducting | 100 | 0 |  | 2026-12-26 |  | 2027-01-07 |  | Tower B | Super Structure | L7 | MEP | HVAC Ducting
46062 |  | Not Committed |  | 2026-10-17 | 2027-10-07 | L8-9 | 100 | 0 |  | 2026-12-26 |  | 2027-11-10
46062 |  | Not Committed |  | 2026-10-17 | 2027-10-07 | L8-9 | 100 | 0 |  | 2026-12-26 |  | 2027-11-10 |  |  |  |  | Finishes | Gypsum Plastering Works
46063 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-10-17 | 2026-10-29 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2026-12-26 |  | 2027-01-07 |  | Tower B | Super Structure | L8 | MEP | FPS 1st Fix - MEP & Finishes
46064 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-10-17 | 2026-10-26 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2026-12-26 |  | 2027-01-04 |  | Tower B | Super Structure | L8 | MEP | Electrical 1st Fixes
46810 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-10-17 | 2026-10-31 | False Ceiling | 100 | 0 |  | 2026-12-26 |  | 2027-01-09 |  | Tower B | Super Structure | L15 | Finishes | False Ceiling
41057 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-12-19 | 2026-12-26 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-12-28 |  | 2027-01-02 |  | Tower A | Super Structure | L76 | MEP | Electrical
41058 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-12-19 | 2026-12-26 | Final Painting | 100 | 0 |  | 2026-12-28 |  | 2027-01-02 |  | Tower A | Super Structure | L76 | Finishes | Final Painting
41058 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-12-19 | 2026-12-26 | Final Painting | 100 | 0 |  | 2026-12-28 |  | 2027-01-02 |  | Tower A | Super Structure | L76 | Finishes | Final Painting
41058 | Tower A - Super Structure - Finishes & MEP - L76 to L77 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-12-19 | 2026-12-26 | Final Painting | 100 | 0 |  | 2026-12-28 |  | 2027-01-02 |  | Tower A | Super Structure | L76 | Finishes | Final Painting
42160 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-12-19 | 2026-12-23 | Staircase Fire Door Fixing | 100 | 0 |  | 2026-12-28 |  | 2026-12-31 |  | Tower A | Super Structure | L77
45516 | Tower B - Super Structure - Finishes & MEP - L27 to L28 | Not Ready | Partition Wall-Blockwork | 2026-09-30 | 2026-10-06 | Staircase Area | 100 | 0 |  | 2026-12-28 |  | 2027-01-02 |  | Tower B | Super Structure | L27
48107 |  | Not Committed |  | 2026-11-04 | 2026-12-26 | Security Cabin | 100 | 0 |  | 2026-12-29 |  | 2027-02-19
48110 |  | Not Committed |  | 2026-11-04 | 2026-12-08 | Fire NOC | 100 | 0 |  | 2026-12-29 |  | 2027-02-02
48112 |  | Not Committed |  | 2026-11-04 | 2026-12-26 | De-snagging & Handover | 100 | 0 |  | 2026-12-29 |  | 2027-02-19
45348 | Tower B - Super Structure - Core & Outer Slab L32-33 | Not Ready | RCC Works - Slab | 2026-10-03 | 2026-10-09 | Outer Slab_TA | 100 | 0 |  | 2026-12-30 |  | 2027-01-06 |  | Tower B | Super Structure | L32 | RCC Sub Structure | RCC Works - Slab
46021 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-10-22 | 2026-10-23 | FAPA Cabling | 100 | 0 |  | 2026-12-30 |  | 2027-01-01 |  | Tower B | Super Structure
47002 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-10-03 | 2026-10-21 | Wet Area Waterproofing | 100 | 0 |  | 2026-12-30 |  | 2027-01-16 |  | Tower B | Super Structure | L26
47428 |  | Not Committed |  | 2026-10-22 | 2026-12-12 | L23-28 | 100 | 0 |  | 2026-12-30 |  | 2027-02-22
47429 | Tower B - Super Structure - Finishes & MEP - L23 to L28 | Not Ready | Façade Works - MEP & Finishes | 2026-10-22 | 2026-11-13 | Al. Frame section (Mullion & Transom) Installation | 100 | 0 |  | 2026-12-30 |  | 2027-01-22 |  | Tower B | Super Structure | L23 | Façade | Façade Works
8878 | T-14-Lift Lobby | Not Ready |  | 2026-11-19 | 2026-12-05 | BF | 100 | 0 |  | 2026-12-31 |  | 2027-01-14
42161 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-12-23 | 2026-12-30 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2026-12-31 |  | 2027-01-06 |  | Tower A | Super Structure | L77 | MEP | Electrical
42162 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-12-23 | 2026-12-30 | Final Painting | 100 | 0 |  | 2026-12-31 |  | 2027-01-06 |  | Tower A | Super Structure | L77 | Finishes | Final Painting
42162 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-12-23 | 2026-12-30 | Final Painting | 100 | 0 |  | 2026-12-31 |  | 2027-01-06 |  | Tower A | Super Structure | L77 | Finishes | Final Painting
42162 | Tower A - Super Structure - Finishes & MEP - L77 to L78 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-12-23 | 2026-12-30 | Final Painting | 100 | 0 |  | 2026-12-31 |  | 2027-01-06 |  | Tower A | Super Structure | L77 | Finishes | Final Painting
45519 | Tower B - Super Structure - Finishes & MEP - L28 to L29 | Not Ready | Partition Wall-Blockwork | 2026-10-05 | 2026-10-12 | Partition Walls | 100 | 0 |  | 2026-12-31 |  | 2027-01-08 |  | Tower B | Super Structure | L28
48081 |  | Not Ready |  | 2026-09-23 | 2026-09-28 | Floor spring works | 100 | 0 |  | 2026-12-31 |  | 2027-01-05
46863 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-10-24 | 2026-11-21 | Flooring & Dado works | 100 | 0 |  | 2027-01-01 |  | 2027-02-01 |  | Tower B | Super Structure | L18 | Finishes | Flooring & Dado
47695 |  | Not Ready |  | 2026-08-08 | 2026-08-28 | Slab_NTA | 100 | 0 |  | 2027-01-01 |  | 2027-01-19
47695 |  | Not Ready |  | 2026-08-08 | 2026-08-28 | Slab_NTA | 100 | 0 |  | 2027-01-01 |  | 2027-01-19 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
44647 |  | Not Committed |  | 2026-06-16 | 2026-08-21 | P5 level | 100 | 0 |  | 2027-01-02 |  | 2027-02-24
44648 | NTA_Zone 2 - Super Structure - P5 to P6 | Not Ready | External Balustrade System | 2026-06-16 | 2026-07-15 | RCC upstand | 100 | 0 |  | 2027-01-02 |  | 2027-02-01 |  | NTA_Zone 2 | Super Structure
44648 | NTA_Zone 2 - Super Structure - P5 to P6 | Not Ready | External Balustrade System | 2026-06-16 | 2026-07-15 | RCC upstand | 100 | 0 |  | 2027-01-02 |  | 2027-02-01 |  | NTA_Zone 2 | Super Structure
44656 | NTA_Zone 2 - Super Structure - P4 to P5 | Not Ready | External Balustrade System | 2026-06-16 | 2026-07-02 | SS tray work | 100 | 0 |  | 2027-01-02 |  | 2027-01-19 |  | NTA_Zone 2 | Super Structure
45629 | Tower B - Super Structure - Finishes & MEP - L26 to L27 | Not Ready | Gypsum Plastering Works | 2026-10-07 | 2026-11-11 | L26-27 | 100 | 0 |  | 2027-01-02 |  | 2027-02-08 |  | Tower B | Super Structure | L26 | Finishes | Gypsum Plastering Works
45629 | Tower B - Super Structure - Finishes & MEP - L26 to L27 | Not Ready | Gypsum Plastering Works | 2026-10-07 | 2026-11-11 | L26-27 | 100 | 0 |  | 2027-01-02 |  | 2027-02-08 |  | Tower B | Super Structure | L26
47015 |  | Not Committed |  | 2026-10-07 | 2027-10-30 | L27-28 | 100 | 0 |  | 2027-01-02 |  | 2027-11-22
47015 |  | Not Committed |  | 2026-10-07 | 2027-10-30 | L27-28 | 100 | 0 |  | 2027-01-02 |  | 2027-11-22 |  |  |  |  | Finishes | Gypsum Plastering Works
47016 |  | Not Committed |  | 2026-10-07 | 2026-11-13 | MEP 1st Fixes | 100 | 0 |  | 2027-01-02 |  | 2027-02-10
47017 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-10-07 | 2026-10-14 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-01-02 |  | 2027-01-11 |  | Tower B | Super Structure | L27 | MEP | FPS 1st Fix - MEP & Finishes
47018 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-10-07 | 2026-10-12 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2027-01-02 |  | 2027-01-08 |  | Tower B | Super Structure | L27 | MEP | Electrical 1st Fixes
47019 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-10-07 | 2026-10-14 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2027-01-02 |  | 2027-01-11 |  | Tower B | Super Structure | L27
45609 | Tower B - Super Structure - Finishes & MEP - P6 to L7 | Not Ready | Gypsum Plastering Works | 2026-10-27 | 2026-12-11 | P6 to L7 | 100 | 0 |  | 2027-01-04 |  | 2027-02-20 |  | Tower B | Super Structure |  | Finishes | Gypsum Plastering Works
45609 | Tower B - Super Structure - Finishes & MEP - P6 to L7 | Not Ready | Gypsum Plastering Works | 2026-10-27 | 2026-12-11 | P6 to L7 | 100 | 0 |  | 2027-01-04 |  | 2027-02-20 |  | Tower B | Super Structure
45991 |  | Not Committed |  | 2026-10-27 | 2026-12-15 | Lobby/ Common Area | 100 | 0 |  | 2027-01-04 |  | 2027-02-24
45992 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-10-27 | 2026-11-03 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-01-04 |  | 2027-01-12 |  | Tower B | Super Structure |  | MEP | FPS 1st Fix - MEP & Finishes
45993 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-10-27 | 2026-10-29 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-01-04 |  | 2027-01-07 |  | Tower B | Super Structure |  | MEP | Electrical 1st Fixes
46022 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-10-27 | 2026-11-03 | HVAC Ducting | 100 | 0 |  | 2027-01-04 |  | 2027-01-12 |  | Tower B | Super Structure |  | MEP | HVAC Ducting
46023 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-10-27 | 2026-11-12 | Flooring & Dado | 100 | 0 |  | 2027-01-04 |  | 2027-01-21 |  | Tower B | Super Structure |  | Finishes | Flooring & Dado
46065 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-10-27 | 2026-11-03 | FAPA Cabling | 100 | 0 |  | 2027-01-04 |  | 2027-01-12 |  | Tower B | Super Structure | L8
47960 | Tower B | Not Committed | Award of Packages | 2026-09-28 | 2027-01-11 | STP | 100 | 0 |  | 2027-01-04 |  | 2027-04-16 |  | Tower B | --
47960 | Tower B | Not Committed | Award of Packages | 2026-09-28 | 2027-01-11 | STP | 100 | 0 |  | 2027-01-04 |  | 2027-04-16 |  | Tower B | --
46862 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-10-28 | 2026-11-04 | Door & Window Frame work | 100 | 0 |  | 2027-01-05 |  | 2027-01-13 |  | Tower B | Super Structure | L18 | Finishes | Door & Window Frame work
46878 |  | Not Committed |  | 2026-10-28 | 2026-12-17 | Finishes after 1st Fix | 100 | 0 |  | 2027-01-05 |  | 2027-02-26
46879 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-10-28 | 2026-11-07 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2027-01-05 |  | 2027-01-16 |  | Tower B | Super Structure | L19 | Finishes | Blockwork
46985 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-10-09 | 2026-10-21 | Cement Plastering in wet areas | 100 | 0 |  | 2027-01-05 |  | 2027-01-16 |  | Tower B | Super Structure | L25
45349 |  | Not Ready |  | 2026-10-10 | 2026-10-22 | L33-34 | 100 | 0 |  | 2027-01-06 |  | 2027-01-18
45349 |  | Not Ready |  | 2026-10-10 | 2026-10-22 | L33-34 | 100 | 0 |  | 2027-01-06 |  | 2027-01-18 |  |  |  |  | Finishes | Gypsum Plastering Works
45350 | Tower B - Super Structure - Core & Outer Slab L33-34 | Not Ready | RCC Works - Vertical | 2026-10-10 | 2026-10-19 | Outer Columns_TA | 100 | 0 |  | 2027-01-06 |  | 2027-01-15 |  | Tower B | Super Structure | L33 | RCC Sub Structure | RCC Works - Vertical
45525 |  | Not Committed |  | 2026-10-10 | 2026-11-11 | L30-31 | 100 | 0 |  | 2027-01-06 |  | 2027-02-08
45525 |  | Not Committed |  | 2026-10-10 | 2026-11-11 | L30-31 | 100 | 0 |  | 2027-01-06 |  | 2027-02-08 |  |  |  |  | Finishes | Gypsum Plastering Works
45526 | Tower B - Super Structure - Finishes & MEP - L30 to L31 | Not Ready | Partition Wall-Blockwork | 2026-10-10 | 2026-10-28 | De-shuttering & Area clearance | 100 | 0 |  | 2027-01-06 |  | 2027-01-23 |  | Tower B | Super Structure | L30
47676 |  | Not Ready |  | 2026-08-21 | 2026-09-02 | Section 10_lift 1 | 100 | 0 |  | 2027-01-06 |  | 2027-01-19
47676 |  | Not Ready |  | 2026-08-21 | 2026-09-02 | Section 10_lift 1 | 100 | 0 |  | 2027-01-06 |  | 2027-01-19 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47687 |  | Not Ready |  | 2026-08-21 | 2026-08-28 | Section 9_lift 2 | 100 | 0 |  | 2027-01-06 |  | 2027-01-14
47687 |  | Not Ready |  | 2026-08-21 | 2026-08-28 | Section 9_lift 2 | 100 | 0 |  | 2027-01-06 |  | 2027-01-14 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
48082 |  | Not Ready |  | 2026-09-29 | 2026-10-05 | Glass door fixing | 100 | 0 |  | 2027-01-06 |  | 2027-01-11
45596 | Tower B - Super Structure - Finishes & MEP | Not Ready | MEP Shaft Masonry | 2026-10-23 | 2026-11-20 | L15-L25 | 100 | 0 |  | 2027-01-07 |  | 2027-02-06 |  | Tower B | Super Structure
45994 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-10-30 | 2026-10-31 | FAPA Cabling | 100 | 0 |  | 2027-01-07 |  | 2027-01-09 |  | Tower B | Super Structure
46066 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-10-30 | 2026-11-10 | HVAC Ducting | 100 | 0 |  | 2027-01-07 |  | 2027-01-19 |  | Tower B | Super Structure | L8 | MEP | HVAC Ducting
46078 |  | Not Committed |  | 2026-10-30 | 2027-10-14 | L9-10 | 100 | 0 |  | 2027-01-07 |  | 2027-11-16
46078 |  | Not Committed |  | 2026-10-30 | 2027-10-14 | L9-10 | 100 | 0 |  | 2027-01-07 |  | 2027-11-16 |  |  |  |  | Finishes | Gypsum Plastering Works
46079 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-10-30 | 2026-11-10 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-01-07 |  | 2027-01-19 |  | Tower B | Super Structure | L9 | MEP | FPS 1st Fix - MEP & Finishes
46080 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-10-30 | 2026-11-06 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-01-07 |  | 2027-01-15 |  | Tower B | Super Structure | L9 | MEP | Electrical 1st Fixes
46828 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-10-30 | 2026-11-12 | False Ceiling | 100 | 0 |  | 2027-01-07 |  | 2027-01-21 |  | Tower B | Super Structure | L16 | Finishes | False Ceiling
44657 | NTA_Zone 2 - Super Structure - P4 to P5 | Not Ready | External Balustrade System | 2026-06-22 | 2026-07-08 | GRC framing & GRC cladding | 100 | 0 |  | 2027-01-08 |  | 2027-01-25 |  | NTA_Zone 2 | Super Structure
44658 | NTA_Zone 2 - Super Structure - P4 to P5 | Not Ready | External Balustrade System | 2026-06-22 | 2026-07-08 | Planter works | 100 | 0 |  | 2027-01-08 |  | 2027-01-25 |  | NTA_Zone 2 | Super Structure
44658 | NTA_Zone 2 - Super Structure - P4 to P5 | Not Ready | External Balustrade System | 2026-06-22 | 2026-07-08 | Planter works | 100 | 0 |  | 2027-01-08 |  | 2027-01-25 |  | NTA_Zone 2 | Super Structure
45520 | Tower B - Super Structure - Finishes & MEP - L28 to L29 | Not Ready | Partition Wall-Blockwork | 2026-10-13 | 2026-10-17 | Staircase Area | 100 | 0 |  | 2027-01-08 |  | 2027-01-14 |  | Tower B | Super Structure | L28
45351 | Tower B - Super Structure - Core & Outer Slab L33-34 | Not Ready | RCC Works - Slab | 2026-10-15 | 2026-10-22 | Outer Slab_TA | 100 | 0 |  | 2027-01-11 |  | 2027-01-18 |  | Tower B | Super Structure | L33 | RCC Sub Structure | RCC Works - Slab
47020 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-10-15 | 2026-11-02 | Wet Area Waterproofing | 100 | 0 |  | 2027-01-11 |  | 2027-01-29 |  | Tower B | Super Structure | L27
45523 | Tower B - Super Structure - Finishes & MEP - L29 to L30 | Not Ready | Partition Wall-Blockwork | 2026-10-16 | 2026-10-24 | Partition Walls | 100 | 0 |  | 2027-01-12 |  | 2027-01-20 |  | Tower B | Super Structure | L29
45608 | Tower B - Super Structure - Finishes & MEP - P5 to P6 | Not Ready | Gypsum Plastering Works | 2026-11-04 | 2026-12-26 | P5 to P6_TA & NTA | 100 | 0 |  | 2027-01-12 |  | 2027-03-06 |  | Tower B | Super Structure |  | Finishes | Gypsum Plastering Works
45964 |  | Not Committed |  | 2026-11-04 | 2026-12-23 | Lobby/ Common Area | 100 | 0 |  | 2027-01-12 |  | 2027-03-04
45965 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-11-04 | 2026-11-11 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-01-12 |  | 2027-01-20 |  | Tower B | Super Structure |  | MEP | FPS 1st Fix - MEP & Finishes
45966 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-11-04 | 2026-11-06 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-01-12 |  | 2027-01-15 |  | Tower B | Super Structure |  | MEP | Electrical 1st Fixes
45995 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-11-04 | 2026-11-11 | HVAC Ducting | 100 | 0 |  | 2027-01-12 |  | 2027-01-20 |  | Tower B | Super Structure |  | MEP | HVAC Ducting
45996 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-11-04 | 2026-11-20 | Flooring & Dado | 100 | 0 |  | 2027-01-12 |  | 2027-01-30 |  | Tower B | Super Structure |  | Finishes | Flooring & Dado
48083 |  | Not Committed |  | 2026-10-06 | 2026-10-23 | DGU Fixing | 100 | 0 |  | 2027-01-12 |  | 2027-01-29
48084 |  | Not Ready |  | 2026-10-06 | 2026-10-23 | Retail front | 100 | 0 |  | 2027-01-12 |  | 2027-01-29
46881 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-11-05 | 2026-12-03 | Flooring & Dado works | 100 | 0 |  | 2027-01-13 |  | 2027-02-12 |  | Tower B | Super Structure | L19 | Finishes | Flooring & Dado
45630 | Tower B - Super Structure - Finishes & MEP - L27 to L28 | Not Ready | Gypsum Plastering Works | 2026-10-19 | 2026-11-23 | L27-28 | 100 | 0 |  | 2027-01-14 |  | 2027-02-19 |  | Tower B | Super Structure | L27 | Finishes | Gypsum Plastering Works
45630 | Tower B - Super Structure - Finishes & MEP - L27 to L28 | Not Ready | Gypsum Plastering Works | 2026-10-19 | 2026-11-23 | L27-28 | 100 | 0 |  | 2027-01-14 |  | 2027-02-19 |  | Tower B | Super Structure | L27
47033 |  | Not Committed |  | 2026-10-19 | 2027-11-13 | L28-29 (Refuge) | 100 | 0 |  | 2027-01-14 |  | 2027-12-06
47034 |  | Not Committed |  | 2026-10-19 | 2026-11-25 | MEP 1st Fixes | 100 | 0 |  | 2027-01-14 |  | 2027-02-22
47035 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-10-19 | 2026-10-27 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-01-14 |  | 2027-01-22 |  | Tower B | Super Structure | L28 | MEP | FPS 1st Fix - MEP & Finishes
47036 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-10-19 | 2026-10-24 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2027-01-14 |  | 2027-01-20 |  | Tower B | Super Structure | L28 | MEP | Electrical 1st Fixes
47037 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-10-19 | 2026-10-27 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2027-01-14 |  | 2027-01-22 |  | Tower B | Super Structure | L28
45967 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-11-07 | 2026-11-09 | FAPA Cabling | 100 | 0 |  | 2027-01-15 |  | 2027-01-18 |  | Tower B | Super Structure
46024 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-11-07 | 2026-11-18 | False Ceiling | 100 | 0 |  | 2027-01-15 |  | 2027-01-28 |  | Tower B | Super Structure |  | Finishes | False Ceiling
46081 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-11-07 | 2026-11-14 | FAPA Cabling | 100 | 0 |  | 2027-01-15 |  | 2027-01-23 |  | Tower B | Super Structure | L9
46880 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-11-09 | 2026-11-16 | Door & Window Frame work | 100 | 0 |  | 2027-01-16 |  | 2027-01-25 |  | Tower B | Super Structure | L19 | Finishes | Door & Window Frame work
46896 |  | Not Committed |  | 2026-11-09 | 2026-12-30 | Finishes after 1st Fix | 100 | 0 |  | 2027-01-16 |  | 2027-03-10
46897 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-11-09 | 2026-11-19 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2027-01-16 |  | 2027-01-29 |  | Tower B | Super Structure | L20 | Finishes | Blockwork
47003 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-10-22 | 2026-11-02 | Cement Plastering in wet areas | 100 | 0 |  | 2027-01-16 |  | 2027-01-29 |  | Tower B | Super Structure | L26
45352 |  | Not Ready |  | 2026-10-23 | 2026-11-03 | L34-35 | 100 | 0 |  | 2027-01-18 |  | 2027-01-30
45352 |  | Not Ready |  | 2026-10-23 | 2026-11-03 | L34-35 | 100 | 0 |  | 2027-01-18 |  | 2027-01-30 |  |  |  |  | Finishes | Gypsum Plastering Works
45353 | Tower B - Super Structure - Core & Outer Slab L34-35 | Not Ready | RCC Works - Vertical | 2026-10-23 | 2026-10-31 | Outer Columns_TA | 100 | 0 |  | 2027-01-18 |  | 2027-01-28 |  | Tower B | Super Structure | L34 | RCC Sub Structure | RCC Works - Vertical
45529 |  | Not Committed |  | 2026-10-23 | 2026-11-23 | L31-32 | 100 | 0 |  | 2027-01-18 |  | 2027-02-19
45529 |  | Not Committed |  | 2026-10-23 | 2026-11-23 | L31-32 | 100 | 0 |  | 2027-01-18 |  | 2027-02-19 |  |  |  |  | Finishes | Gypsum Plastering Works
45530 | Tower B - Super Structure - Finishes & MEP - L31 to L32 | Not Ready | Partition Wall-Blockwork | 2026-10-23 | 2026-11-09 | De-shuttering & Area clearance | 100 | 0 |  | 2027-01-18 |  | 2027-02-05 |  | Tower B | Super Structure | L31
46082 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-11-11 | 2026-11-21 | HVAC Ducting | 100 | 0 |  | 2027-01-19 |  | 2027-02-01 |  | Tower B | Super Structure | L9 | MEP | HVAC Ducting
46094 |  | Not Committed |  | 2026-11-11 | 2027-10-20 | L10-11 | 100 | 0 |  | 2027-01-19 |  | 2027-11-22
46094 |  | Not Committed |  | 2026-11-11 | 2027-10-20 | L10-11 | 100 | 0 |  | 2027-01-19 |  | 2027-11-22 |  |  |  |  | Finishes | Gypsum Plastering Works
46095 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-11-11 | 2026-11-21 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-01-19 |  | 2027-02-01 |  | Tower B | Super Structure | L10 | MEP | FPS 1st Fix - MEP & Finishes
46096 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-11-11 | 2026-11-18 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-01-19 |  | 2027-01-28 |  | Tower B | Super Structure | L10 | MEP | Electrical 1st Fixes
46846 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-11-11 | 2026-11-24 | False Ceiling | 100 | 0 |  | 2027-01-19 |  | 2027-02-03 |  | Tower B | Super Structure | L17 | Finishes | False Ceiling
47665 |  | Not Ready |  | 2026-10-08 | 2026-11-07 | Plinth Checking (30 calendar days) | 100 | 0 |  | 2027-01-19 |  | 2027-02-19
47665 |  | Not Ready |  | 2026-10-08 | 2026-11-07 | Plinth Checking (30 calendar days) | 100 | 0 |  | 2027-01-19 |  | 2027-02-19
47688 |  | Not Ready |  | 2026-09-03 | 2026-09-10 | Section 10_lift 2 | 100 | 0 |  | 2027-01-19 |  | 2027-01-28
47688 |  | Not Ready |  | 2026-09-03 | 2026-09-10 | Section 10_lift 2 | 100 | 0 |  | 2027-01-19 |  | 2027-01-28 |  |  |  |  | RCC Super Structure | Retaining Wall RCC Works
47807 |  | Not Ready |  | 2026-10-08 | 2026-11-24 | B1 to GF | 100 | 0 |  | 2027-01-19 |  | 2027-03-08
47807 |  | Not Ready |  | 2026-10-08 | 2026-11-24 | B1 to GF | 100 | 0 |  | 2027-01-19 |  | 2027-03-08
47807 |  | Not Ready |  | 2026-10-08 | 2026-11-24 | B1 to GF | 100 | 0 |  | 2027-01-19 |  | 2027-03-08
47813 |  | Not Committed |  | 2026-06-19 | 2027-12-03 | MEP 1st Fixes | 100 | 0 |  | 2027-01-19 |  | 2028-06-08
47814 |  | Not Ready |  | 2026-06-19 | 2026-09-04 | B3 to B2 | 100 | 0 |  | 2027-01-19 |  | 2027-04-01
47814 |  | Not Ready |  | 2026-06-19 | 2026-09-04 | B3 to B2 | 100 | 0 |  | 2027-01-19 |  | 2027-04-01
47814 |  | Not Ready |  | 2026-06-19 | 2026-09-04 | B3 to B2 | 100 | 0 |  | 2027-01-19 |  | 2027-04-01
44649 | NTA_Zone 2 - Super Structure - P5 to P6 | Not Ready | External Balustrade System | 2026-07-03 | 2026-07-22 | Drainage pipe | 100 | 0 |  | 2027-01-20 |  | 2027-02-06 |  | NTA_Zone 2 | Super Structure
44649 | NTA_Zone 2 - Super Structure - P5 to P6 | Not Ready | External Balustrade System | 2026-07-03 | 2026-07-22 | Drainage pipe | 100 | 0 |  | 2027-01-20 |  | 2027-02-06 |  | NTA_Zone 2 | Super Structure
45524 | Tower B - Super Structure - Finishes & MEP - L29 to L30 | Not Ready | Partition Wall-Blockwork | 2026-10-26 | 2026-10-30 | Staircase Area | 100 | 0 |  | 2027-01-20 |  | 2027-01-27 |  | Tower B | Super Structure | L29
45607 | Tower B - Super Structure - Finishes & MEP - P4 to P5 | Not Ready | Gypsum Plastering Works | 2026-11-12 | 2027-01-04 | P4 to P5_TA & NTA | 100 | 0 |  | 2027-01-20 |  | 2027-03-15 |  | Tower B | Super Structure |  | Finishes | Gypsum Plastering Works
45937 |  | Not Committed |  | 2026-11-12 | 2027-01-01 | Lobby/ Common Area | 100 | 0 |  | 2027-01-20 |  | 2027-03-12
45938 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-11-12 | 2026-11-19 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-01-20 |  | 2027-01-29 |  | Tower B | Super Structure |  | MEP | FPS 1st Fix - MEP & Finishes
45939 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-11-12 | 2026-11-14 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-01-20 |  | 2027-01-23 |  | Tower B | Super Structure |  | MEP | Electrical 1st Fixes
45968 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-11-12 | 2026-11-19 | HVAC Ducting | 100 | 0 |  | 2027-01-20 |  | 2027-01-29 |  | Tower B | Super Structure |  | MEP | HVAC Ducting
45969 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-11-12 | 2026-11-28 | Flooring & Dado | 100 | 0 |  | 2027-01-20 |  | 2027-02-08 |  | Tower B | Super Structure |  | Finishes | Flooring & Dado
45354 | Tower B - Super Structure - Core & Outer Slab L34-35 | Not Ready | RCC Works - Slab | 2026-10-28 | 2026-11-03 | Outer Slab_TA | 100 | 0 |  | 2027-01-22 |  | 2027-01-30 |  | Tower B | Super Structure | L34 | RCC Sub Structure | RCC Works - Slab
47038 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-10-28 | 2026-11-13 | Wet Area Waterproofing | 100 | 0 |  | 2027-01-22 |  | 2027-02-10 |  | Tower B | Super Structure | L28
47430 | Tower B - Super Structure - Finishes & MEP - L23 to L28 | Not Ready | Façade Works - MEP & Finishes | 2026-11-14 | 2026-11-25 | DGU Assembly Installation | 100 | 0 |  | 2027-01-22 |  | 2027-02-04 |  | Tower B | Super Structure | L23 | Façade | Façade Works
47431 | Tower B - Super Structure - Finishes & MEP - L23 to L28 | Not Ready | Façade Works - MEP & Finishes | 2026-11-14 | 2026-12-12 | Installation of highly reflective metal sheet | 100 | 0 |  | 2027-01-22 |  | 2027-02-22 |  | Tower B | Super Structure | L23 | Façade | Façade Works
47432 | Tower B - Super Structure - Finishes & MEP - L23 to L28 | Not Ready | Façade Works - MEP & Finishes | 2026-11-14 | 2026-12-01 | Fixing of Backlit Laminated Glass assembly & ACP Panels | 100 | 0 |  | 2027-01-22 |  | 2027-02-10 |  | Tower B | Super Structure | L23 | Façade | Façade Works
47433 | Tower B - Super Structure - Finishes & MEP - L23 to L28 | Not Ready | Façade Works - MEP & Finishes | 2026-11-14 | 2026-12-01 | Fixing of Louvers | 100 | 0 |  | 2027-01-22 |  | 2027-02-10 |  | Tower B | Super Structure | L23 | Façade | Façade Works
47433 | Tower B - Super Structure - Finishes & MEP - L23 to L28 | Not Ready | Façade Works - MEP & Finishes | 2026-11-14 | 2026-12-01 | Fixing of Louvers | 100 | 0 |  | 2027-01-22 |  | 2027-02-10 |  | Tower B | Super Structure | L23
45527 | Tower B - Super Structure - Finishes & MEP - L30 to L31 | Not Ready | Partition Wall-Blockwork | 2026-10-29 | 2026-11-05 | Partition Walls | 100 | 0 |  | 2027-01-23 |  | 2027-02-02 |  | Tower B | Super Structure | L30
45940 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-11-16 | 2026-11-17 | FAPA Cabling | 100 | 0 |  | 2027-01-23 |  | 2027-01-27 |  | Tower B | Super Structure
45997 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-11-16 | 2026-11-26 | False Ceiling | 100 | 0 |  | 2027-01-23 |  | 2027-02-05 |  | Tower B | Super Structure |  | Finishes | False Ceiling
46899 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-11-17 | 2026-12-15 | Flooring & Dado works | 100 | 0 |  | 2027-01-25 |  | 2027-02-24 |  | Tower B | Super Structure | L20 | Finishes | Flooring & Dado
45631 | Tower B - Super Structure - Finishes & MEP - L28 to L29 | Not Ready | Gypsum Plastering Works | 2026-10-31 | 2026-12-04 | L28-29 | 100 | 0 |  | 2027-01-27 |  | 2027-03-03 |  | Tower B | Super Structure | L28 | Finishes | Gypsum Plastering Works
45631 | Tower B - Super Structure - Finishes & MEP - L28 to L29 | Not Ready | Gypsum Plastering Works | 2026-10-31 | 2026-12-04 | L28-29 | 100 | 0 |  | 2027-01-27 |  | 2027-03-03 |  | Tower B | Super Structure | L28
47051 |  | Not Committed |  | 2026-10-31 | 2027-11-27 | L29-30 | 100 | 0 |  | 2027-01-27 |  | 2027-12-20
47051 |  | Not Committed |  | 2026-10-31 | 2027-11-27 | L29-30 | 100 | 0 |  | 2027-01-27 |  | 2027-12-20 |  |  |  |  | Finishes | Gypsum Plastering Works
47052 |  | Not Committed |  | 2026-10-31 | 2026-12-07 | MEP 1st Fixes | 100 | 0 |  | 2027-01-27 |  | 2027-03-05
47053 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-10-31 | 2026-11-07 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-01-27 |  | 2027-02-04 |  | Tower B | Super Structure | L29 | MEP | FPS 1st Fix - MEP & Finishes
47054 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-10-31 | 2026-11-05 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2027-01-27 |  | 2027-02-02 |  | Tower B | Super Structure | L29 | MEP | Electrical 1st Fixes
47055 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-10-31 | 2026-11-07 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2027-01-27 |  | 2027-02-04 |  | Tower B | Super Structure | L29
46025 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-11-19 | 2026-11-21 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-01-28 |  | 2027-02-01 |  | Tower B | Super Structure |  | MEP | FPS 2nd Fix - MEP & Finishes
46026 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-11-19 | 2026-11-24 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-01-28 |  | 2027-02-03 |  | Tower B | Super Structure |  | MEP | Electrical 2nd Fix - MEP & Finishes
46027 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-11-19 | 2026-11-26 | FAPA Device Fixing | 100 | 0 |  | 2027-01-28 |  | 2027-02-05 |  | Tower B | Super Structure
46027 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-11-19 | 2026-11-26 | FAPA Device Fixing | 100 | 0 |  | 2027-01-28 |  | 2027-02-05 |  | Tower B | Super Structure
46027 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-11-19 | 2026-11-26 | FAPA Device Fixing | 100 | 0 |  | 2027-01-28 |  | 2027-02-05 |  | Tower B | Super Structure
46027 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-11-19 | 2026-11-26 | FAPA Device Fixing | 100 | 0 |  | 2027-01-28 |  | 2027-02-05 |  | Tower B | Super Structure
46028 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-11-19 | 2026-11-21 | HVAC Grill Fixing | 100 | 0 |  | 2027-01-28 |  | 2027-02-01 |  | Tower B | Super Structure |  | MEP | HVAC Grill Fixing
46097 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-11-19 | 2026-11-26 | FAPA Cabling | 100 | 0 |  | 2027-01-28 |  | 2027-02-05 |  | Tower B | Super Structure | L10
45606 | Tower B - Super Structure - Finishes & MEP - P3 to P4 | Not Ready | Gypsum Plastering Works | 2026-11-20 | 2027-01-12 | P3 to P4_TA & NTA | 100 | 0 |  | 2027-01-29 |  | 2027-03-24 |  | Tower B | Super Structure |  | Finishes | Gypsum Plastering Works
45910 |  | Not Committed |  | 2026-11-20 | 2027-01-09 | Lobby/ Common Area | 100 | 0 |  | 2027-01-29 |  | 2027-03-20
45911 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-11-20 | 2026-11-27 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-01-29 |  | 2027-02-06 |  | Tower B | Super Structure |  | MEP | FPS 1st Fix - MEP & Finishes
45912 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-11-20 | 2026-11-23 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-01-29 |  | 2027-02-02 |  | Tower B | Super Structure |  | MEP | Electrical 1st Fixes
45941 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-11-20 | 2026-11-27 | HVAC Ducting | 100 | 0 |  | 2027-01-29 |  | 2027-02-06 |  | Tower B | Super Structure |  | MEP | HVAC Ducting
45942 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-11-20 | 2026-12-07 | Flooring & Dado | 100 | 0 |  | 2027-01-29 |  | 2027-02-16 |  | Tower B | Super Structure |  | Finishes | Flooring & Dado
46898 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-11-20 | 2026-11-27 | Door & Window Frame work | 100 | 0 |  | 2027-01-29 |  | 2027-02-06 |  | Tower B | Super Structure | L20 | Finishes | Door & Window Frame work
46914 |  | Not Committed |  | 2026-11-20 | 2027-01-11 | Finishes after 1st Fix | 100 | 0 |  | 2027-01-29 |  | 2027-03-23
46915 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-11-20 | 2026-12-01 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2027-01-29 |  | 2027-02-10 |  | Tower B | Super Structure | L21 | Finishes | Blockwork
47021 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-11-03 | 2026-11-13 | Cement Plastering in wet areas | 100 | 0 |  | 2027-01-29 |  | 2027-02-10 |  | Tower B | Super Structure | L27
45355 |  | Not Ready |  | 2026-11-04 | 2026-11-14 | L35-36 | 100 | 0 |  | 2027-01-30 |  | 2027-02-11
45355 |  | Not Ready |  | 2026-11-04 | 2026-11-14 | L35-36 | 100 | 0 |  | 2027-01-30 |  | 2027-02-11 |  |  |  |  | Finishes | Gypsum Plastering Works
45356 | Tower B - Super Structure - Core & Outer Slab L35-36 | Not Ready | RCC Works - Vertical | 2026-11-04 | 2026-11-12 | Outer Columns_TA | 100 | 0 |  | 2027-01-30 |  | 2027-02-09 |  | Tower B | Super Structure | L35 | RCC Sub Structure | RCC Works - Vertical
45533 |  | Not Committed |  | 2026-11-04 | 2026-12-04 | L32-33 | 100 | 0 |  | 2027-01-30 |  | 2027-03-03
45533 |  | Not Committed |  | 2026-11-04 | 2026-12-04 | L32-33 | 100 | 0 |  | 2027-01-30 |  | 2027-03-03 |  |  |  |  | Finishes | Gypsum Plastering Works
45534 | Tower B - Super Structure - Finishes & MEP - L32 to L33 | Not Ready | Partition Wall-Blockwork | 2026-11-04 | 2026-11-20 | De-shuttering & Area clearance | 100 | 0 |  | 2027-01-30 |  | 2027-02-17 |  | Tower B | Super Structure | L32
45749 |  | Not Committed |  | 2026-11-04 | 2027-02-06 | L25-35 | 100 | 0 |  | 2027-01-30 |  | 2027-05-06
45749 |  | Not Committed |  | 2026-11-04 | 2027-02-06 | L25-35 | 100 | 0 |  | 2027-01-30 |  | 2027-05-06
45750 | Tower B - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2026-11-04 | 2026-11-26 | FHR Shaft Risers | 100 | 0 |  | 2027-01-30 |  | 2027-02-23 |  | Tower B | Super Structure | L25
45752 | Tower B - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2026-11-04 | 2026-12-26 | Domestic Water & Flushing Riser in Plumbing Shaft | 100 | 0 |  | 2027-01-30 |  | 2027-03-25 |  | Tower B | Super Structure | L25
45754 | Tower B - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2026-11-04 | 2026-12-08 | Shaft Cable Tray in Electrical Shaft | 100 | 0 |  | 2027-01-30 |  | 2027-03-06 |  | Tower B | Super Structure | L25
46029 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-11-23 | 2026-11-25 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-02-01 |  | 2027-02-04 |  | Tower B | Super Structure
46098 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-11-23 | 2026-12-03 | HVAC Ducting | 100 | 0 |  | 2027-02-01 |  | 2027-02-12 |  | Tower B | Super Structure | L10 | MEP | HVAC Ducting
46110 |  | Not Committed |  | 2026-11-23 | 2027-10-26 | L11-12 | 100 | 0 |  | 2027-02-01 |  | 2027-11-27
46110 |  | Not Committed |  | 2026-11-23 | 2027-10-26 | L11-12 | 100 | 0 |  | 2027-02-01 |  | 2027-11-27 |  |  |  |  | Finishes | Gypsum Plastering Works
46111 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-11-23 | 2026-12-03 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-02-01 |  | 2027-02-12 |  | Tower B | Super Structure | L11 | MEP | FPS 1st Fix - MEP & Finishes
46112 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-11-23 | 2026-11-30 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-02-01 |  | 2027-02-09 |  | Tower B | Super Structure | L11 | MEP | Electrical 1st Fixes
46864 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-11-23 | 2026-12-05 | False Ceiling | 100 | 0 |  | 2027-02-01 |  | 2027-02-15 |  | Tower B | Super Structure | L18 | Finishes | False Ceiling
44650 | NTA_Zone 2 - Super Structure - P5 to P6 | Not Ready | External Balustrade System | 2026-07-18 | 2026-08-07 | SS tray work | 100 | 0 |  | 2027-02-02 |  | 2027-02-18 |  | NTA_Zone 2 | Super Structure
45528 | Tower B - Super Structure - Finishes & MEP - L30 to L31 | Not Ready | Partition Wall-Blockwork | 2026-11-06 | 2026-11-11 | Staircase Area | 100 | 0 |  | 2027-02-02 |  | 2027-02-08 |  | Tower B | Super Structure | L30
45913 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-11-24 | 2026-11-25 | FAPA Cabling | 100 | 0 |  | 2027-02-02 |  | 2027-02-04 |  | Tower B | Super Structure
45970 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-11-24 | 2026-12-04 | False Ceiling | 100 | 0 |  | 2027-02-02 |  | 2027-02-13 |  | Tower B | Super Structure |  | Finishes | False Ceiling
44273 |  | Not Ready |  | 2026-10-30 | 2026-11-04 | CFO Visit 2 | 100 | 0 |  | 2027-02-03 |  | 2027-03-29
44263 |  | Not Ready | External Development | 2026-06-30 | 2026-10-28 | Softscape Works | 100 | 0 |  | 2027-02-04 |  | 2027-05-24
44263 |  | Not Ready | External Development | 2026-06-30 | 2026-10-28 | Softscape Works | 100 | 0 |  | 2027-02-04 |  | 2027-05-24
44263 |  | Not Ready | External Development | 2026-06-30 | 2026-10-28 | Softscape Works | 100 | 0 |  | 2027-02-04 |  | 2027-05-24
44281 |  | Not Ready |  | 2026-06-27 | 2026-12-30 | Hand Over_Zone 1 | 100 | 0 |  | 2027-02-04 |  | 2027-06-28
44282 |  | Not Ready |  | 2026-06-27 | 2026-10-26 | De-Snagging | 100 | 0 |  | 2027-02-04 |  | 2027-05-24
45357 | Tower B - Super Structure - Core & Outer Slab L35-36 | Not Ready | RCC Works - Slab | 2026-11-09 | 2026-11-14 | Outer Slab_TA | 100 | 0 |  | 2027-02-04 |  | 2027-02-11 |  | Tower B | Super Structure | L35 | RCC Sub Structure | RCC Works - Slab
46030 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-11-26 | 2026-12-01 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-02-04 |  | 2027-02-10 |  | Tower B | Super Structure |  | MEP | Electrical
47056 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-11-09 | 2026-11-25 | Wet Area Waterproofing | 100 | 0 |  | 2027-02-04 |  | 2027-02-22 |  | Tower B | Super Structure | L29
47434 | Tower B - Super Structure - Finishes & MEP - L23 to L28 | Not Ready | Façade Works - MEP & Finishes | 2026-11-26 | 2026-12-12 | Accessories & Alignment | 100 | 0 |  | 2027-02-04 |  | 2027-02-22 |  | Tower B | Super Structure | L23 | Façade | Façade Works
47434 | Tower B - Super Structure - Finishes & MEP - L23 to L28 | Not Ready | Façade Works - MEP & Finishes | 2026-11-26 | 2026-12-12 | Accessories & Alignment | 100 | 0 |  | 2027-02-04 |  | 2027-02-22 |  | Tower B | Super Structure | L23
45531 | Tower B - Super Structure - Finishes & MEP - L31 to L32 | Not Ready | Partition Wall-Blockwork | 2026-11-10 | 2026-11-17 | Partition Walls | 100 | 0 |  | 2027-02-05 |  | 2027-02-13 |  | Tower B | Super Structure | L31
45998 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-11-27 | 2026-11-30 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-02-05 |  | 2027-02-09 |  | Tower B | Super Structure |  | MEP | FPS 2nd Fix - MEP & Finishes
45999 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-11-27 | 2026-12-02 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-02-05 |  | 2027-02-11 |  | Tower B | Super Structure |  | MEP | Electrical 2nd Fix - MEP & Finishes
46000 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-11-27 | 2026-12-04 | FAPA Device Fixing | 100 | 0 |  | 2027-02-05 |  | 2027-02-13 |  | Tower B | Super Structure
46000 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-11-27 | 2026-12-04 | FAPA Device Fixing | 100 | 0 |  | 2027-02-05 |  | 2027-02-13 |  | Tower B | Super Structure
46000 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-11-27 | 2026-12-04 | FAPA Device Fixing | 100 | 0 |  | 2027-02-05 |  | 2027-02-13 |  | Tower B | Super Structure
46000 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-11-27 | 2026-12-04 | FAPA Device Fixing | 100 | 0 |  | 2027-02-05 |  | 2027-02-13 |  | Tower B | Super Structure
46001 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-11-27 | 2026-11-30 | HVAC Grill Fixing | 100 | 0 |  | 2027-02-05 |  | 2027-02-09 |  | Tower B | Super Structure |  | MEP | HVAC Grill Fixing
45605 | Tower B - Super Structure - Finishes & MEP - P2 to P3 | Not Ready | Gypsum Plastering Works | 2026-11-28 | 2027-01-20 | P2 to P3_TA & NTA | 100 | 0 |  | 2027-02-06 |  | 2027-04-01 |  | Tower B | Super Structure |  | Finishes | Gypsum Plastering Works
45883 |  | Not Committed |  | 2026-11-28 | 2027-01-18 | Lobby/ Common Area | 100 | 0 |  | 2027-02-06 |  | 2027-03-30
45884 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-11-28 | 2026-12-05 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-02-06 |  | 2027-02-15 |  | Tower B | Super Structure |  | MEP | FPS 1st Fix - MEP & Finishes
45885 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-11-28 | 2026-12-01 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-02-06 |  | 2027-02-10 |  | Tower B | Super Structure |  | MEP | Electrical 1st Fixes
45914 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-11-28 | 2026-12-05 | HVAC Ducting | 100 | 0 |  | 2027-02-06 |  | 2027-02-15 |  | Tower B | Super Structure |  | MEP | HVAC Ducting
45915 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-11-28 | 2026-12-15 | Flooring & Dado | 100 | 0 |  | 2027-02-06 |  | 2027-02-24 |  | Tower B | Super Structure |  | Finishes | Flooring & Dado
46917 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-11-28 | 2026-12-28 | Flooring & Dado works | 100 | 0 |  | 2027-02-06 |  | 2027-03-08 |  | Tower B | Super Structure | L21 | Finishes | Flooring & Dado
44651 | NTA_Zone 2 - Super Structure - P5 to P6 | Not Ready | External Balustrade System | 2026-07-31 | 2026-08-21 | GRC framing & GRC cladding | 100 | 0 |  | 2027-02-08 |  | 2027-02-24 |  | NTA_Zone 2 | Super Structure
44652 | NTA_Zone 2 - Super Structure - P5 to P6 | Not Ready | External Balustrade System | 2026-07-31 | 2026-08-21 | Planter works | 100 | 0 |  | 2027-02-08 |  | 2027-02-24 |  | NTA_Zone 2 | Super Structure
44652 | NTA_Zone 2 - Super Structure - P5 to P6 | Not Ready | External Balustrade System | 2026-07-31 | 2026-08-21 | Planter works | 100 | 0 |  | 2027-02-08 |  | 2027-02-24 |  | NTA_Zone 2 | Super Structure
45632 | Tower B - Super Structure - Finishes & MEP - L29 to L30 | Not Ready | Gypsum Plastering Works | 2026-11-12 | 2026-12-16 | L29-30 | 100 | 0 |  | 2027-02-08 |  | 2027-03-15 |  | Tower B | Super Structure | L29 | Finishes | Gypsum Plastering Works
45632 | Tower B - Super Structure - Finishes & MEP - L29 to L30 | Not Ready | Gypsum Plastering Works | 2026-11-12 | 2026-12-16 | L29-30 | 100 | 0 |  | 2027-02-08 |  | 2027-03-15 |  | Tower B | Super Structure | L29
47069 |  | Not Committed |  | 2026-11-12 | 2027-12-11 | L30-31 | 100 | 0 |  | 2027-02-08 |  | 2028-01-04
47069 |  | Not Committed |  | 2026-11-12 | 2027-12-11 | L30-31 | 100 | 0 |  | 2027-02-08 |  | 2028-01-04 |  |  |  |  | Finishes | Gypsum Plastering Works
47070 |  | Not Committed |  | 2026-11-12 | 2026-12-18 | MEP 1st Fixes | 100 | 0 |  | 2027-02-08 |  | 2027-03-17
47071 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-11-12 | 2026-11-19 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-02-08 |  | 2027-02-16 |  | Tower B | Super Structure | L30 | MEP | FPS 1st Fix - MEP & Finishes
47072 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-11-12 | 2026-11-17 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2027-02-08 |  | 2027-02-13 |  | Tower B | Super Structure | L30 | MEP | Electrical 1st Fixes
47073 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-11-12 | 2026-11-19 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2027-02-08 |  | 2027-02-16 |  | Tower B | Super Structure | L30
46002 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-12-01 | 2026-12-03 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-02-09 |  | 2027-02-12 |  | Tower B | Super Structure
46113 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-12-01 | 2026-12-08 | FAPA Cabling | 100 | 0 |  | 2027-02-09 |  | 2027-02-17 |  | Tower B | Super Structure | L11
45886 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-12-02 | 2026-12-03 | FAPA Cabling | 100 | 0 |  | 2027-02-10 |  | 2027-02-12 |  | Tower B | Super Structure
45943 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-12-02 | 2026-12-12 | False Ceiling | 100 | 0 |  | 2027-02-10 |  | 2027-02-22 |  | Tower B | Super Structure |  | Finishes | False Ceiling
46031 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-12-02 | 2026-12-07 | Final Painting | 100 | 0 |  | 2027-02-10 |  | 2027-02-16 |  | Tower B | Super Structure |  | Finishes | Final Painting
46031 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-12-02 | 2026-12-07 | Final Painting | 100 | 0 |  | 2027-02-10 |  | 2027-02-16 |  | Tower B | Super Structure |  | Finishes | Final Painting
46031 | Tower B - Super Structure - Finishes & MEP - P6 to L7 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-12-02 | 2026-12-07 | Final Painting | 100 | 0 |  | 2027-02-10 |  | 2027-02-16 |  | Tower B | Super Structure |  | Finishes | Final Painting
46916 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-12-02 | 2026-12-09 | Door & Window Frame work | 100 | 0 |  | 2027-02-10 |  | 2027-02-18 |  | Tower B | Super Structure | L21 | Finishes | Door & Window Frame work
46932 |  | Not Committed |  | 2026-12-02 | 2027-01-22 | Finishes after 1st Fix | 100 | 0 |  | 2027-02-10 |  | 2027-04-03
46933 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-12-02 | 2026-12-12 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2027-02-10 |  | 2027-02-22 |  | Tower B | Super Structure | L22 | Finishes | Blockwork
47039 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-11-14 | 2026-11-25 | Cement Plastering in wet areas | 100 | 0 |  | 2027-02-10 |  | 2027-02-22 |  | Tower B | Super Structure | L28
45358 |  | Not Ready |  | 2026-11-16 | 2026-11-26 | L36-37 | 100 | 0 |  | 2027-02-11 |  | 2027-02-23
45358 |  | Not Ready |  | 2026-11-16 | 2026-11-26 | L36-37 | 100 | 0 |  | 2027-02-11 |  | 2027-02-23 |  |  |  |  | Finishes | Gypsum Plastering Works
45359 | Tower B - Super Structure - Core & Outer Slab L36-37 | Not Ready | RCC Works - Vertical | 2026-11-16 | 2026-11-24 | Outer Columns_TA | 100 | 0 |  | 2027-02-11 |  | 2027-02-20 |  | Tower B | Super Structure | L36 | RCC Sub Structure | RCC Works - Vertical
45537 |  | Not Committed |  | 2026-11-16 | 2026-12-16 | L33-34 | 100 | 0 |  | 2027-02-11 |  | 2027-03-15
45537 |  | Not Committed |  | 2026-11-16 | 2026-12-16 | L33-34 | 100 | 0 |  | 2027-02-11 |  | 2027-03-15 |  |  |  |  | Finishes | Gypsum Plastering Works
45538 | Tower B - Super Structure - Finishes & MEP - L33 to L34 | Not Ready | Partition Wall-Blockwork | 2026-11-16 | 2026-12-02 | De-shuttering & Area clearance | 100 | 0 |  | 2027-02-11 |  | 2027-03-01 |  | Tower B | Super Structure | L33
46003 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-12-04 | 2026-12-09 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-02-12 |  | 2027-02-18 |  | Tower B | Super Structure |  | MEP | Electrical
46114 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-12-04 | 2026-12-15 | HVAC Ducting | 100 | 0 |  | 2027-02-12 |  | 2027-02-24 |  | Tower B | Super Structure | L11 | MEP | HVAC Ducting
46126 |  | Not Committed |  | 2026-12-04 | 2027-11-02 | L12-13 | 100 | 0 |  | 2027-02-12 |  | 2027-12-03
46126 |  | Not Committed |  | 2026-12-04 | 2027-11-02 | L12-13 | 100 | 0 |  | 2027-02-12 |  | 2027-12-03 |  |  |  |  | Finishes | Gypsum Plastering Works
46127 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-12-04 | 2026-12-15 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-02-12 |  | 2027-02-24 |  | Tower B | Super Structure | L12 | MEP | FPS 1st Fix - MEP & Finishes
46128 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-12-04 | 2026-12-11 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-02-12 |  | 2027-02-20 |  | Tower B | Super Structure | L12 | MEP | Electrical 1st Fixes
46882 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-12-04 | 2026-12-17 | False Ceiling | 100 | 0 |  | 2027-02-12 |  | 2027-02-26 |  | Tower B | Super Structure | L19 | Finishes | False Ceiling
45532 | Tower B - Super Structure - Finishes & MEP - L31 to L32 | Not Ready | Partition Wall-Blockwork | 2026-11-18 | 2026-11-23 | Staircase Area | 100 | 0 |  | 2027-02-13 |  | 2027-02-19 |  | Tower B | Super Structure | L31
45971 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-12-05 | 2026-12-08 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-02-13 |  | 2027-02-17 |  | Tower B | Super Structure |  | MEP | FPS 2nd Fix - MEP & Finishes
45972 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-12-05 | 2026-12-10 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-02-13 |  | 2027-02-19 |  | Tower B | Super Structure |  | MEP | Electrical 2nd Fix - MEP & Finishes
45973 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-05 | 2026-12-12 | FAPA Device Fixing | 100 | 0 |  | 2027-02-13 |  | 2027-02-22 |  | Tower B | Super Structure
45973 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-05 | 2026-12-12 | FAPA Device Fixing | 100 | 0 |  | 2027-02-13 |  | 2027-02-22 |  | Tower B | Super Structure
45973 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-05 | 2026-12-12 | FAPA Device Fixing | 100 | 0 |  | 2027-02-13 |  | 2027-02-22 |  | Tower B | Super Structure
45973 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-05 | 2026-12-12 | FAPA Device Fixing | 100 | 0 |  | 2027-02-13 |  | 2027-02-22 |  | Tower B | Super Structure
45974 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-12-05 | 2026-12-08 | HVAC Grill Fixing | 100 | 0 |  | 2027-02-13 |  | 2027-02-17 |  | Tower B | Super Structure |  | MEP | HVAC Grill Fixing
45604 | Tower B - Super Structure - Finishes & MEP - P1 to P2 | Not Ready | Gypsum Plastering Works | 2026-12-07 | 2027-01-29 | P1 to P2_TA & NTA | 100 | 0 |  | 2027-02-15 |  | 2027-04-09 |  | Tower B | Super Structure |  | Finishes | Gypsum Plastering Works
45853 |  | Not Committed |  | 2026-12-07 | 2027-01-27 | Lobby/ Common Area | 100 | 0 |  | 2027-02-15 |  | 2027-04-07
45854 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-12-07 | 2026-12-14 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-02-15 |  | 2027-02-23 |  | Tower B | Super Structure | GF | MEP | FPS 1st Fix - MEP & Finishes
45855 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-12-07 | 2026-12-09 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-02-15 |  | 2027-02-18 |  | Tower B | Super Structure | GF | MEP | Electrical 1st Fixes
45887 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-12-07 | 2026-12-14 | HVAC Ducting | 100 | 0 |  | 2027-02-15 |  | 2027-02-23 |  | Tower B | Super Structure |  | MEP | HVAC Ducting
45888 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-12-07 | 2026-12-23 | Flooring & Dado | 100 | 0 |  | 2027-02-15 |  | 2027-03-04 |  | Tower B | Super Structure |  | Finishes | Flooring & Dado
45360 | Tower B - Super Structure - Core & Outer Slab L36-37 | Not Ready | RCC Works - Slab | 2026-11-20 | 2026-11-26 | Outer Slab_TA | 100 | 0 |  | 2027-02-16 |  | 2027-02-23 |  | Tower B | Super Structure | L36 | RCC Sub Structure | RCC Works - Slab
47074 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-11-20 | 2026-12-07 | Wet Area Waterproofing | 100 | 0 |  | 2027-02-16 |  | 2027-03-05 |  | Tower B | Super Structure | L30
48256 |  | Not Committed |  | 2026-09-07 | 2026-12-26 | GF to R1 | 100 | 0 |  | 2027-02-16 |  | 2027-06-03
48257 | Retail - Super structure - GF to R1 | Not Ready |  | 2026-09-07 | 2026-12-26 | Retail Lift Lobby | 100 | 0 |  | 2027-02-16 |  | 2027-06-03 |  | Retail | Super Structure | GF
48258 | Retail - Super structure - GF to R1 | Not Ready |  | 2026-09-07 | 2026-12-26 | Toilets | 100 | 0 |  | 2027-02-16 |  | 2027-06-03 |  | Retail | Super Structure | GF
48259 | Retail - Super structure - GF to R1 | Not Ready |  | 2026-09-07 | 2026-12-26 | Club House Ground Lobby | 100 | 0 |  | 2027-02-16 |  | 2027-06-03 |  | Retail | Super Structure | GF
48260 | Retail - Super structure - GF to R1 | Not Ready |  | 2026-09-07 | 2026-12-26 | Circulation Area | 100 | 0 |  | 2027-02-16 |  | 2027-06-03 |  | Retail | Super Structure | GF
48261 | Retail - Super structure - GF to R1 | Not Ready |  | 2026-09-07 | 2026-11-20 | Staircase Finishes | 100 | 0 |  | 2027-02-16 |  | 2027-04-27 |  | Retail | Super Structure | GF
48261 | Retail - Super structure - GF to R1 | Not Ready |  | 2026-09-07 | 2026-11-20 | Staircase Finishes | 100 | 0 |  | 2027-02-16 |  | 2027-04-27 |  | Retail | Super Structure | GF
45535 | Tower B - Super Structure - Finishes & MEP - L32 to L33 | Not Ready | Partition Wall-Blockwork | 2026-11-21 | 2026-11-28 | Partition Walls | 100 | 0 |  | 2027-02-17 |  | 2027-02-25 |  | Tower B | Super Structure | L32
45975 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-12-09 | 2026-12-11 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-02-17 |  | 2027-02-20 |  | Tower B | Super Structure
45856 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-12-10 | 2026-12-11 | FAPA Cabling | 100 | 0 |  | 2027-02-18 |  | 2027-02-20 |  | Tower B | Super Structure | GF
45916 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-12-10 | 2026-12-21 | False Ceiling | 100 | 0 |  | 2027-02-18 |  | 2027-03-02 |  | Tower B | Super Structure |  | Finishes | False Ceiling
46004 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-12-10 | 2026-12-15 | Final Painting | 100 | 0 |  | 2027-02-18 |  | 2027-02-24 |  | Tower B | Super Structure |  | Finishes | Final Painting
46004 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-12-10 | 2026-12-15 | Final Painting | 100 | 0 |  | 2027-02-18 |  | 2027-02-24 |  | Tower B | Super Structure |  | Finishes | Final Painting
46004 | Tower B - Super Structure - Finishes & MEP - P5 to P6 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-12-10 | 2026-12-15 | Final Painting | 100 | 0 |  | 2027-02-18 |  | 2027-02-24 |  | Tower B | Super Structure |  | Finishes | Final Painting
46935 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-12-10 | 2027-01-08 | Flooring & Dado works | 100 | 0 |  | 2027-02-18 |  | 2027-03-19 |  | Tower B | Super Structure | L22 | Finishes | Flooring & Dado
45633 | Tower B - Super Structure - Finishes & MEP - L30 to L31 | Not Ready | Gypsum Plastering Works | 2026-11-24 | 2026-12-22 | L30-31 | 100 | 0 |  | 2027-02-19 |  | 2027-03-20 |  | Tower B | Super Structure | L30 | Finishes | Gypsum Plastering Works
45633 | Tower B - Super Structure - Finishes & MEP - L30 to L31 | Not Ready | Gypsum Plastering Works | 2026-11-24 | 2026-12-22 | L30-31 | 100 | 0 |  | 2027-02-19 |  | 2027-03-20 |  | Tower B | Super Structure | L30
47087 |  | Not Committed |  | 2026-11-24 | 2027-12-27 | L31-32 | 100 | 0 |  | 2027-02-19 |  | 2028-01-18
47087 |  | Not Committed |  | 2026-11-24 | 2027-12-27 | L31-32 | 100 | 0 |  | 2027-02-19 |  | 2028-01-18 |  |  |  |  | Finishes | Gypsum Plastering Works
47088 |  | Not Committed |  | 2026-11-24 | 2026-12-31 | MEP 1st Fixes | 100 | 0 |  | 2027-02-19 |  | 2027-03-30
47089 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-11-24 | 2026-12-01 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-02-19 |  | 2027-02-27 |  | Tower B | Super Structure | L31 | MEP | FPS 1st Fix - MEP & Finishes
47090 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-11-24 | 2026-11-28 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2027-02-19 |  | 2027-02-25 |  | Tower B | Super Structure | L31 | MEP | Electrical 1st Fixes
47091 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-11-24 | 2026-12-01 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2027-02-19 |  | 2027-02-27 |  | Tower B | Super Structure | L31
47708 |  | Not Committed |  | 2026-11-09 | 2027-06-11 | Super-Structure_NTA Zone 3 | 100 | 0 |  | 2027-02-19 |  | 2027-09-23
47709 |  | Not Committed |  | 2026-11-09 | 2027-01-18 | GF to P1 | 100 | 0 |  | 2027-02-19 |  | 2027-05-03
47709 |  | Not Committed |  | 2026-11-09 | 2027-01-18 | GF to P1 | 100 | 0 |  | 2027-02-19 |  | 2027-05-03
47709 |  | Not Committed |  | 2026-11-09 | 2027-01-18 | GF to P1 | 100 | 0 |  | 2027-02-19 |  | 2027-05-03
47710 |  | Not Committed |  | 2026-11-09 | 2026-12-18 | Pour 8 (grid PB-B to PB-J) | 100 | 0 |  | 2027-02-19 |  | 2027-04-02
47711 |  | Not Ready |  | 2026-11-09 | 2026-11-25 | Columns/ Walls_NTA | 100 | 0 |  | 2027-02-19 |  | 2027-03-09
47711 |  | Not Ready |  | 2026-11-09 | 2026-11-25 | Columns/ Walls_NTA | 100 | 0 |  | 2027-02-19 |  | 2027-03-09 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
47712 |  | Not Ready |  | 2026-11-09 | 2026-12-01 | Staircase_NTA | 100 | 0 |  | 2027-02-19 |  | 2027-03-15
47712 |  | Not Ready |  | 2026-11-09 | 2026-12-01 | Staircase_NTA | 100 | 0 |  | 2027-02-19 |  | 2027-03-15 |  |  |  |  | RCC Sub Structure | Staircase & Ramp RCC Works
47717 |  | Not Committed |  | 2026-11-09 | 2026-12-12 | Pour 10 (PA-A to PB-J) | 100 | 0 |  | 2027-02-19 |  | 2027-03-27
47718 |  | Not Ready |  | 2026-11-09 | 2026-11-25 | Columns/ Walls_NTA | 100 | 0 |  | 2027-02-19 |  | 2027-03-09
47718 |  | Not Ready |  | 2026-11-09 | 2026-11-25 | Columns/ Walls_NTA | 100 | 0 |  | 2027-02-19 |  | 2027-03-09 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
47719 |  | Not Ready |  | 2026-11-09 | 2026-12-07 | Ramp_NTA | 100 | 0 |  | 2027-02-19 |  | 2027-03-20
45976 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-12-12 | 2026-12-17 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-02-20 |  | 2027-02-26 |  | Tower B | Super Structure |  | MEP | Electrical
46129 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-12-12 | 2026-12-19 | FAPA Cabling | 100 | 0 |  | 2027-02-20 |  | 2027-03-01 |  | Tower B | Super Structure | L12
44264 |  | Not Ready | External Development | 2026-07-24 | 2026-11-02 | Compound Wall | 100 | 0 |  | 2027-02-22 |  | 2027-05-24
44264 |  | Not Ready | External Development | 2026-07-24 | 2026-11-02 | Compound Wall | 100 | 0 |  | 2027-02-22 |  | 2027-05-24
44283 |  | Not Ready |  | 2026-07-18 | 2026-11-14 | Integrated Testing & Commissioning | 100 | 0 |  | 2027-02-22 |  | 2027-06-10
45944 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-12-14 | 2026-12-16 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-02-22 |  | 2027-02-25 |  | Tower B | Super Structure |  | MEP | FPS 2nd Fix - MEP & Finishes
45945 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-12-14 | 2026-12-18 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-02-22 |  | 2027-02-27 |  | Tower B | Super Structure |  | MEP | Electrical 2nd Fix - MEP & Finishes
45946 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-14 | 2026-12-21 | FAPA Device Fixing | 100 | 0 |  | 2027-02-22 |  | 2027-03-02 |  | Tower B | Super Structure
45946 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-14 | 2026-12-21 | FAPA Device Fixing | 100 | 0 |  | 2027-02-22 |  | 2027-03-02 |  | Tower B | Super Structure
45946 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-14 | 2026-12-21 | FAPA Device Fixing | 100 | 0 |  | 2027-02-22 |  | 2027-03-02 |  | Tower B | Super Structure
45946 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-14 | 2026-12-21 | FAPA Device Fixing | 100 | 0 |  | 2027-02-22 |  | 2027-03-02 |  | Tower B | Super Structure
45947 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-12-14 | 2026-12-16 | HVAC Grill Fixing | 100 | 0 |  | 2027-02-22 |  | 2027-02-25 |  | Tower B | Super Structure |  | MEP | HVAC Grill Fixing
46934 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-12-14 | 2026-12-21 | Door & Window Frame work | 100 | 0 |  | 2027-02-22 |  | 2027-03-02 |  | Tower B | Super Structure | L22 | Finishes | Door & Window Frame work
46950 |  | Not Committed |  | 2026-12-14 | 2027-02-04 | Finishes after 1st Fix | 100 | 0 |  | 2027-02-22 |  | 2027-04-15
46951 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-12-14 | 2026-12-24 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2027-02-22 |  | 2027-03-05 |  | Tower B | Super Structure | L23 | Finishes | Blockwork
47057 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-11-26 | 2026-12-07 | Cement Plastering in wet areas | 100 | 0 |  | 2027-02-22 |  | 2027-03-05 |  | Tower B | Super Structure | L29
47435 |  | Not Committed |  | 2026-12-14 | 2027-02-05 | L28-33 | 100 | 0 |  | 2027-02-22 |  | 2027-04-16
47436 | Tower B - Super Structure - Finishes & MEP - L28 to L33 | Not Ready | Façade Works - MEP & Finishes | 2026-12-14 | 2027-01-06 | Al. Frame section (Mullion & Transom) Installation | 100 | 0 |  | 2027-02-22 |  | 2027-03-17 |  | Tower B | Super Structure | L28 | Façade | Façade Works
48111 |  | Not Committed |  | 2026-11-24 | 2026-12-29 | OC grant | 100 | 0 |  | 2027-02-22 |  | 2027-03-29
45361 |  | Not Ready |  | 2026-11-27 | 2026-12-08 | L37-38 | 100 | 0 |  | 2027-02-23 |  | 2027-03-06
45361 |  | Not Ready |  | 2026-11-27 | 2026-12-08 | L37-38 | 100 | 0 |  | 2027-02-23 |  | 2027-03-06 |  |  |  |  | Finishes | Gypsum Plastering Works
45362 | Tower B - Super Structure - Core & Outer Slab L37-38 | Not Ready | RCC Works - Vertical | 2026-11-27 | 2026-12-05 | Outer Columns_TA | 100 | 0 |  | 2027-02-23 |  | 2027-03-04 |  | Tower B | Super Structure | L37 | RCC Sub Structure | RCC Works - Vertical
45541 |  | Not Committed |  | 2026-11-27 | 2026-12-29 | L34-35 | 100 | 0 |  | 2027-02-23 |  | 2027-03-27
45541 |  | Not Committed |  | 2026-11-27 | 2026-12-29 | L34-35 | 100 | 0 |  | 2027-02-23 |  | 2027-03-27 |  |  |  |  | Finishes | Gypsum Plastering Works
45542 | Tower B - Super Structure - Finishes & MEP - L34 to L35 | Not Ready | Partition Wall-Blockwork | 2026-11-27 | 2026-12-14 | De-shuttering & Area clearance | 100 | 0 |  | 2027-02-23 |  | 2027-03-12 |  | Tower B | Super Structure | L34
45603 | Tower B - Super Structure - Finishes & MEP - GF to P1 | Not Ready | Gypsum Plastering Works | 2026-12-15 | 2027-02-24 | GF to P1_TA & NTA | 100 | 0 |  | 2027-02-23 |  | 2027-05-06 |  | Tower B | Super Structure | GF | Finishes | Gypsum Plastering Works
45751 | Tower B - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2026-11-27 | 2027-01-19 | FHC & Accessories fixing | 100 | 0 |  | 2027-02-23 |  | 2027-04-17 |  | Tower B | Super Structure | L25
45753 | Tower B - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2026-11-27 | 2027-01-19 | Soil & Waste Downtake piping in Plumbing Shaft | 100 | 0 |  | 2027-02-23 |  | 2027-04-17 |  | Tower B | Super Structure | L25
45757 | Tower B - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2026-11-27 | 2027-01-19 | HVAC Shaft Ducting | 100 | 0 |  | 2027-02-23 |  | 2027-04-17 |  | Tower B | Super Structure | L25 | MEP | HVAC Grill Fixing
45825 |  | Not Committed |  | 2026-12-15 | 2027-02-04 | Lobby/ Common Area | 100 | 0 |  | 2027-02-23 |  | 2027-04-15
45826 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-12-15 | 2026-12-22 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-02-23 |  | 2027-03-03 |  | Tower B | Sub Structure | B1 | MEP | FPS 1st Fix - MEP & Finishes
45827 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-12-15 | 2026-12-17 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-02-23 |  | 2027-02-26 |  | Tower B | Sub Structure | B1 | MEP | Electrical 1st Fixes
45857 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-12-15 | 2026-12-22 | HVAC Ducting | 100 | 0 |  | 2027-02-23 |  | 2027-03-03 |  | Tower B | Super Structure | GF | MEP | HVAC Ducting
45858 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-12-15 | 2027-01-01 | Flooring & Dado | 100 | 0 |  | 2027-02-23 |  | 2027-03-12 |  | Tower B | Super Structure | GF | Finishes | Flooring & Dado
46130 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-12-16 | 2026-12-28 | HVAC Ducting | 100 | 0 |  | 2027-02-24 |  | 2027-03-08 |  | Tower B | Super Structure | L12 | MEP | HVAC Ducting
46142 |  | Not Committed |  | 2026-12-16 | 2027-11-08 | L13-14 | 100 | 0 |  | 2027-02-24 |  | 2027-12-09
46142 |  | Not Committed |  | 2026-12-16 | 2027-11-08 | L13-14 | 100 | 0 |  | 2027-02-24 |  | 2027-12-09 |  |  |  |  | Finishes | Gypsum Plastering Works
46143 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-12-16 | 2026-12-28 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-02-24 |  | 2027-03-08 |  | Tower B | Super Structure | L13 | MEP | FPS 1st Fix - MEP & Finishes
46144 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-12-16 | 2026-12-23 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-02-24 |  | 2027-03-04 |  | Tower B | Super Structure | L13 | MEP | Electrical 1st Fixes
46900 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-12-16 | 2026-12-30 | False Ceiling | 100 | 0 |  | 2027-02-24 |  | 2027-03-10 |  | Tower B | Super Structure | L20 | Finishes | False Ceiling
44635 |  | Not Committed |  | 2026-08-29 | 2026-10-24 | GF level | 100 | 0 |  | 2027-02-25 |  | 2027-03-26
44636 | NTA_Zone 2 - Super Structure - GF to P1 | Not Ready | External Balustrade System | 2026-08-29 | 2026-09-29 | RCC upstand | 100 | 0 |  | 2027-02-25 |  | 2027-03-02 |  | NTA_Zone 2 | Super Structure | GF
44636 | NTA_Zone 2 - Super Structure - GF to P1 | Not Ready | External Balustrade System | 2026-08-29 | 2026-09-29 | RCC upstand | 100 | 0 |  | 2027-02-25 |  | 2027-03-02 |  | NTA_Zone 2 | Super Structure | GF
45536 | Tower B - Super Structure - Finishes & MEP - L32 to L33 | Not Ready | Partition Wall-Blockwork | 2026-11-30 | 2026-12-04 | Staircase Area | 100 | 0 |  | 2027-02-25 |  | 2027-03-03 |  | Tower B | Super Structure | L32
45948 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-12-17 | 2026-12-19 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-02-25 |  | 2027-03-01 |  | Tower B | Super Structure
45828 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-12-18 | 2026-12-19 | FAPA Cabling | 100 | 0 |  | 2027-02-26 |  | 2027-03-01 |  | Tower B | Sub Structure | B1
45889 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-12-18 | 2026-12-30 | False Ceiling | 100 | 0 |  | 2027-02-26 |  | 2027-03-10 |  | Tower B | Super Structure |  | Finishes | False Ceiling
45977 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-12-18 | 2026-12-23 | Final Painting | 100 | 0 |  | 2027-02-26 |  | 2027-03-04 |  | Tower B | Super Structure |  | Finishes | Final Painting
45977 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-12-18 | 2026-12-23 | Final Painting | 100 | 0 |  | 2027-02-26 |  | 2027-03-04 |  | Tower B | Super Structure |  | Finishes | Final Painting
45977 | Tower B - Super Structure - Finishes & MEP - P4 to P5 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-12-18 | 2026-12-23 | Final Painting | 100 | 0 |  | 2027-02-26 |  | 2027-03-04 |  | Tower B | Super Structure |  | Finishes | Final Painting
46667 |  | Not Committed |  | 2026-12-18 | 2027-01-23 | MEP final fix & Finishes | 100 | 0 |  | 2027-02-26 |  | 2027-04-02
46668 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2026-12-18 | 2027-01-01 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2027-02-26 |  | 2027-03-10 |  | Tower B | Super Structure | L7 | Finishes | Door & Window Fixing
45363 | Tower B - Super Structure - Core & Outer Slab L37-38 | Not Ready | RCC Works - Slab | 2026-12-02 | 2026-12-08 | Outer Slab_TA | 100 | 0 |  | 2027-02-27 |  | 2027-03-06 |  | Tower B | Super Structure | L37 | RCC Sub Structure | RCC Works - Slab
47092 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-12-02 | 2026-12-18 | Wet Area Waterproofing | 100 | 0 |  | 2027-02-27 |  | 2027-03-17 |  | Tower B | Super Structure | L31
45539 | Tower B - Super Structure - Finishes & MEP - L33 to L34 | Not Ready | Partition Wall-Blockwork | 2026-12-03 | 2026-12-10 | Partition Walls | 100 | 0 |  | 2027-03-01 |  | 2027-03-09 |  | Tower B | Super Structure | L33
45949 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-12-21 | 2026-12-26 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-03-01 |  | 2027-03-06 |  | Tower B | Super Structure |  | MEP | Electrical
45917 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-12-22 | 2026-12-24 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-03-02 |  | 2027-03-05 |  | Tower B | Super Structure |  | MEP | FPS 2nd Fix - MEP & Finishes
45918 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-12-22 | 2026-12-28 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-03-02 |  | 2027-03-08 |  | Tower B | Super Structure |  | MEP | Electrical 2nd Fix - MEP & Finishes
45919 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-22 | 2026-12-30 | FAPA Device Fixing | 100 | 0 |  | 2027-03-02 |  | 2027-03-10 |  | Tower B | Super Structure
45919 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-22 | 2026-12-30 | FAPA Device Fixing | 100 | 0 |  | 2027-03-02 |  | 2027-03-10 |  | Tower B | Super Structure
45919 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-22 | 2026-12-30 | FAPA Device Fixing | 100 | 0 |  | 2027-03-02 |  | 2027-03-10 |  | Tower B | Super Structure
45919 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-22 | 2026-12-30 | FAPA Device Fixing | 100 | 0 |  | 2027-03-02 |  | 2027-03-10 |  | Tower B | Super Structure
45920 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-12-22 | 2026-12-24 | HVAC Grill Fixing | 100 | 0 |  | 2027-03-02 |  | 2027-03-05 |  | Tower B | Super Structure |  | MEP | HVAC Grill Fixing
46953 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-12-22 | 2027-01-20 | Flooring & Dado works | 100 | 0 |  | 2027-03-02 |  | 2027-04-01 |  | Tower B | Super Structure | L23 | Finishes | Flooring & Dado
44637 | NTA_Zone 2 - Super Structure - GF to P1 | Not Ready | External Balustrade System | 2026-09-18 | 2026-10-06 | Drainage pipe | 100 | 0 |  | 2027-03-03 |  | 2027-03-08 |  | NTA_Zone 2 | Super Structure | GF
44637 | NTA_Zone 2 - Super Structure - GF to P1 | Not Ready | External Balustrade System | 2026-09-18 | 2026-10-06 | Drainage pipe | 100 | 0 |  | 2027-03-03 |  | 2027-03-08 |  | NTA_Zone 2 | Super Structure | GF
45602 | Tower B - Sub Structure - Finishes & MEP - B1 to GF | Not Ready | Gypsum Plastering Works | 2026-12-23 | 2027-01-28 | B1 to GF_TA & NTA | 100 | 0 |  | 2027-03-03 |  | 2027-04-08 |  | Tower B | Sub Structure | B1 | Finishes | Gypsum Plastering Works
45602 | Tower B - Sub Structure - Finishes & MEP - B1 to GF | Not Ready | Gypsum Plastering Works | 2026-12-23 | 2027-01-28 | B1 to GF_TA & NTA | 100 | 0 |  | 2027-03-03 |  | 2027-04-08 |  | Tower B | Sub Structure | B1
45634 | Tower B - Super Structure - Finishes & MEP - L31 to L32 | Not Ready | Gypsum Plastering Works | 2026-12-05 | 2027-01-04 | L31-32 | 100 | 0 |  | 2027-03-03 |  | 2027-04-02 |  | Tower B | Super Structure | L31 | Finishes | Gypsum Plastering Works
45634 | Tower B - Super Structure - Finishes & MEP - L31 to L32 | Not Ready | Gypsum Plastering Works | 2026-12-05 | 2027-01-04 | L31-32 | 100 | 0 |  | 2027-03-03 |  | 2027-04-02 |  | Tower B | Super Structure | L31
45798 |  | Not Committed |  | 2026-12-23 | 2027-02-12 | Lobby/ Common Area | 100 | 0 |  | 2027-03-03 |  | 2027-04-23
45799 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-12-23 | 2026-12-31 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-03-03 |  | 2027-03-11 |  | Tower B | Sub Structure | B2 | MEP | FPS 1st Fix - MEP & Finishes
45800 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-12-23 | 2026-12-26 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-03-03 |  | 2027-03-06 |  | Tower B | Sub Structure | B2 | MEP | Electrical 1st Fixes
45829 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-12-23 | 2026-12-31 | HVAC Ducting | 100 | 0 |  | 2027-03-03 |  | 2027-03-11 |  | Tower B | Sub Structure | B1 | MEP | HVAC Ducting
45830 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2026-12-23 | 2027-01-09 | Flooring & Dado | 100 | 0 |  | 2027-03-03 |  | 2027-03-20 |  | Tower B | Sub Structure | B1 | Finishes | Flooring & Dado
47105 |  | Not Committed |  | 2026-12-05 | 2028-01-10 | L32-33 | 100 | 0 |  | 2027-03-03 |  | 2028-02-02
47105 |  | Not Committed |  | 2026-12-05 | 2028-01-10 | L32-33 | 100 | 0 |  | 2027-03-03 |  | 2028-02-02 |  |  |  |  | Finishes | Gypsum Plastering Works
47106 |  | Not Committed |  | 2026-12-05 | 2027-01-12 | MEP 1st Fixes | 100 | 0 |  | 2027-03-03 |  | 2027-04-10
47107 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-12-05 | 2026-12-12 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-03-03 |  | 2027-03-11 |  | Tower B | Super Structure | L32 | MEP | FPS 1st Fix - MEP & Finishes
47108 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-12-05 | 2026-12-10 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2027-03-03 |  | 2027-03-09 |  | Tower B | Super Structure | L32 | MEP | Electrical 1st Fixes
47109 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-12-05 | 2026-12-12 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2027-03-03 |  | 2027-03-11 |  | Tower B | Super Structure | L32
46145 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-12-24 | 2027-01-01 | FAPA Cabling | 100 | 0 |  | 2027-03-04 |  | 2027-03-12 |  | Tower B | Super Structure | L13
45921 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2026-12-26 | 2026-12-29 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-03-05 |  | 2027-03-09 |  | Tower B | Super Structure
46952 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2026-12-26 | 2027-01-02 | Door & Window Frame work | 100 | 0 |  | 2027-03-05 |  | 2027-03-13 |  | Tower B | Super Structure | L23 | Finishes | Door & Window Frame work
46968 |  | Not Committed |  | 2026-12-26 | 2027-02-16 | Finishes after 1st Fix | 100 | 0 |  | 2027-03-05 |  | 2027-04-27
46969 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2026-12-26 | 2027-01-06 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2027-03-05 |  | 2027-03-17 |  | Tower B | Super Structure | L24 | Finishes | Blockwork
47075 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-12-08 | 2026-12-18 | Cement Plastering in wet areas | 100 | 0 |  | 2027-03-05 |  | 2027-03-17 |  | Tower B | Super Structure | L30
47958 | Tower B | Not Committed | Award of Packages | 2027-03-04 | 2027-07-22 | DG | 100 | 0 |  | 2027-03-05 |  | 2027-07-23 |  | Tower B | --
45364 |  | Not Ready |  | 2026-12-09 | 2026-12-19 | L38-39 | 100 | 0 |  | 2027-03-06 |  | 2027-03-18
45364 |  | Not Ready |  | 2026-12-09 | 2026-12-19 | L38-39 | 100 | 0 |  | 2027-03-06 |  | 2027-03-18 |  |  |  |  | Finishes | Gypsum Plastering Works
45365 | Tower B - Super Structure - Core & Outer Slab L38-39 | Not Ready | RCC Works - Vertical | 2026-12-09 | 2026-12-17 | Outer Columns_TA | 100 | 0 |  | 2027-03-06 |  | 2027-03-16 |  | Tower B | Super Structure | L38 | RCC Sub Structure | RCC Works - Vertical
45545 |  | Not Committed |  | 2026-12-09 | 2027-01-09 | L35-36 | 100 | 0 |  | 2027-03-06 |  | 2027-04-08
45545 |  | Not Committed |  | 2026-12-09 | 2027-01-09 | L35-36 | 100 | 0 |  | 2027-03-06 |  | 2027-04-08 |  |  |  |  | Finishes | Gypsum Plastering Works
45546 | Tower B - Super Structure - Finishes & MEP - L35 to L36 | Not Ready | Partition Wall-Blockwork | 2026-12-09 | 2026-12-26 | De-shuttering & Area clearance | 100 | 0 |  | 2027-03-06 |  | 2027-03-25 |  | Tower B | Super Structure | L35
45755 | Tower B - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2026-12-09 | 2027-01-13 | Shaft Cabling in Electrical & ELV Shaft | 100 | 0 |  | 2027-03-06 |  | 2027-04-12 |  | Tower B | Super Structure | L25
45801 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2026-12-28 | 2026-12-29 | FAPA Cabling | 100 | 0 |  | 2027-03-06 |  | 2027-03-09 |  | Tower B | Sub Structure | B2
45859 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | False Ceiling - MEP & Finishes | 2026-12-28 | 2027-01-07 | False Ceiling | 100 | 0 |  | 2027-03-06 |  | 2027-03-18 |  | Tower B | Super Structure | GF | Finishes | False Ceiling
45950 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-12-28 | 2027-01-01 | Final Painting | 100 | 0 |  | 2027-03-06 |  | 2027-03-12 |  | Tower B | Super Structure |  | Finishes | Final Painting
45950 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-12-28 | 2027-01-01 | Final Painting | 100 | 0 |  | 2027-03-06 |  | 2027-03-12 |  | Tower B | Super Structure |  | Finishes | Final Painting
45950 | Tower B - Super Structure - Finishes & MEP - P3 to P4 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2026-12-28 | 2027-01-01 | Final Painting | 100 | 0 |  | 2027-03-06 |  | 2027-03-12 |  | Tower B | Super Structure |  | Finishes | Final Painting
40702 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | Entrance Area Kiosks - MEP & Finishes | 2025-11-15 | 2025-12-19 | Entrance Area Kiosks | 100 | 0 |  | 2027-03-08 |  | 2027-04-12 |  | Tower A | Super Structure | GF
46146 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2026-12-29 | 2027-01-08 | HVAC Ducting | 100 | 0 |  | 2027-03-08 |  | 2027-03-19 |  | Tower B | Super Structure | L13 | MEP | HVAC Ducting
46158 |  | Not Committed |  | 2026-12-29 | 2027-11-13 | L14-15 | 100 | 0 |  | 2027-03-08 |  | 2027-12-15
46158 |  | Not Committed |  | 2026-12-29 | 2027-11-13 | L14-15 | 100 | 0 |  | 2027-03-08 |  | 2027-12-15 |  |  |  |  | Finishes | Gypsum Plastering Works
46159 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-12-29 | 2027-01-08 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-03-08 |  | 2027-03-19 |  | Tower B | Super Structure | L14 | MEP | FPS 1st Fix - MEP & Finishes
46160 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-12-29 | 2027-01-05 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-03-08 |  | 2027-03-16 |  | Tower B | Super Structure | L14 | MEP | Electrical 1st Fixes
46918 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2026-12-29 | 2027-01-11 | False Ceiling | 100 | 0 |  | 2027-03-08 |  | 2027-03-23 |  | Tower B | Super Structure | L21 | Finishes | False Ceiling
44262 |  | Not Ready | External Development | 2026-08-24 | 2026-12-14 | Hardscape Works | 100 | 0 |  | 2027-03-09 |  | 2027-06-25
44262 |  | Not Ready | External Development | 2026-08-24 | 2026-12-14 | Hardscape Works | 100 | 0 |  | 2027-03-09 |  | 2027-06-25
45540 | Tower B - Super Structure - Finishes & MEP - L33 to L34 | Not Ready | Partition Wall-Blockwork | 2026-12-11 | 2026-12-16 | Staircase Area | 100 | 0 |  | 2027-03-09 |  | 2027-03-15 |  | Tower B | Super Structure | L33
45922 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2026-12-30 | 2027-01-04 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-03-09 |  | 2027-03-15 |  | Tower B | Super Structure |  | MEP | Electrical
47713 |  | Not Ready |  | 2026-11-26 | 2026-12-18 | Slab_NTA | 100 | 0 |  | 2027-03-09 |  | 2027-04-02
47713 |  | Not Ready |  | 2026-11-26 | 2026-12-18 | Slab_NTA | 100 | 0 |  | 2027-03-09 |  | 2027-04-02 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
47714 |  | Not Committed |  | 2026-11-26 | 2026-12-24 | Pour 9 (grid PB-06 to PB-C) | 100 | 0 |  | 2027-03-09 |  | 2027-04-08
47715 |  | Not Ready |  | 2026-11-26 | 2026-12-12 | Columns/ Walls_NTA | 100 | 0 |  | 2027-03-09 |  | 2027-03-27
47715 |  | Not Ready |  | 2026-11-26 | 2026-12-12 | Columns/ Walls_NTA | 100 | 0 |  | 2027-03-09 |  | 2027-03-27 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
47720 |  | Not Ready |  | 2026-11-26 | 2026-12-12 | Slab_NTA | 100 | 0 |  | 2027-03-09 |  | 2027-03-27
47720 |  | Not Ready |  | 2026-11-26 | 2026-12-12 | Slab_NTA | 100 | 0 |  | 2027-03-09 |  | 2027-03-27 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
47721 |  | Not Committed |  | 2026-11-26 | 2026-12-18 | Pour 11 (PB-C to PB-K) | 100 | 0 |  | 2027-03-09 |  | 2027-04-02
47722 |  | Not Ready |  | 2026-11-26 | 2026-12-12 | Columns/ Walls_NTA | 100 | 0 |  | 2027-03-09 |  | 2027-03-27
47722 |  | Not Ready |  | 2026-11-26 | 2026-12-12 | Columns/ Walls_NTA | 100 | 0 |  | 2027-03-09 |  | 2027-03-27 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
45890 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2026-12-31 | 2027-01-02 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-03-10 |  | 2027-03-13 |  | Tower B | Super Structure |  | MEP | FPS 2nd Fix - MEP & Finishes
45891 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2026-12-31 | 2027-01-05 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-03-10 |  | 2027-03-16 |  | Tower B | Super Structure |  | MEP | Electrical 2nd Fix - MEP & Finishes
45892 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-31 | 2027-01-07 | FAPA Device Fixing | 100 | 0 |  | 2027-03-10 |  | 2027-03-18 |  | Tower B | Super Structure
45892 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-31 | 2027-01-07 | FAPA Device Fixing | 100 | 0 |  | 2027-03-10 |  | 2027-03-18 |  | Tower B | Super Structure
45892 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-31 | 2027-01-07 | FAPA Device Fixing | 100 | 0 |  | 2027-03-10 |  | 2027-03-18 |  | Tower B | Super Structure
45892 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2026-12-31 | 2027-01-07 | FAPA Device Fixing | 100 | 0 |  | 2027-03-10 |  | 2027-03-18 |  | Tower B | Super Structure
45893 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2026-12-31 | 2027-01-02 | HVAC Grill Fixing | 100 | 0 |  | 2027-03-10 |  | 2027-03-13 |  | Tower B | Super Structure |  | MEP | HVAC Grill Fixing
46669 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-01-02 | 2027-01-09 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-03-10 |  | 2027-03-18 |  | Tower B | Super Structure | L7 | MEP | FPS 2nd Fix - MEP & Finishes
46670 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-01-02 | 2027-01-09 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-03-10 |  | 2027-03-18 |  | Tower B | Super Structure | L7 | MEP | Electrical 2nd Fix - MEP & Finishes
46685 |  | Not Committed |  | 2027-01-02 | 2027-02-08 | MEP final fix & Finishes | 100 | 0 |  | 2027-03-10 |  | 2027-04-14
46686 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2027-01-02 | 2027-01-15 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2027-03-10 |  | 2027-03-23 |  | Tower B | Super Structure | L8 | Finishes | Door & Window Fixing
40701 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2025-11-19 | 2025-12-02 | Final Painting | 100 | 0 |  | 2027-03-11 |  | 2027-03-25 |  | Tower A | Super Structure | GF | Finishes | Final Painting
40701 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2025-11-19 | 2025-12-02 | Final Painting | 100 | 0 |  | 2027-03-11 |  | 2027-03-25 |  | Tower A | Super Structure | GF | Finishes | Final Painting
40701 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2025-11-19 | 2025-12-02 | Final Painting | 100 | 0 |  | 2027-03-11 |  | 2027-03-25 |  | Tower A | Super Structure | GF | Finishes | Final Painting
44265 |  | Not Ready | External Development | 2026-08-26 | 2026-11-11 | Entry/ Exit Gates | 100 | 0 |  | 2027-03-11 |  | 2027-05-24
45366 | Tower B - Super Structure - Core & Outer Slab L38-39 | Not Ready | RCC Works - Slab | 2026-12-14 | 2026-12-19 | Outer Slab_TA | 100 | 0 |  | 2027-03-11 |  | 2027-03-18 |  | Tower B | Super Structure | L38 | RCC Sub Structure | RCC Works - Slab
45601 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 | Not Ready | Gypsum Plastering Works | 2027-01-01 | 2027-02-05 | B2 to B1_TA & NTA | 100 | 0 |  | 2027-03-11 |  | 2027-04-16 |  | Tower B | Sub Structure | B2 | Finishes | Gypsum Plastering Works
45601 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 | Not Ready | Gypsum Plastering Works | 2027-01-01 | 2027-02-05 | B2 to B1_TA & NTA | 100 | 0 |  | 2027-03-11 |  | 2027-04-16 |  | Tower B | Sub Structure | B2
45769 |  | Not Committed |  | 2027-01-01 | 2027-02-20 | Lobby/ Common Area | 100 | 0 |  | 2027-03-11 |  | 2027-05-03
45770 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-01-01 | 2027-01-08 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-03-11 |  | 2027-03-19 |  | Tower B | Sub Structure | B3 | MEP | FPS 1st Fix - MEP & Finishes
45771 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-01-01 | 2027-01-04 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-03-11 |  | 2027-03-15 |  | Tower B | Sub Structure | B3 | MEP | Electrical 1st Fixes
45802 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-01-01 | 2027-01-08 | HVAC Ducting | 100 | 0 |  | 2027-03-11 |  | 2027-03-19 |  | Tower B | Sub Structure | B2 | MEP | HVAC Ducting
45803 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-01-01 | 2027-01-18 | Flooring & Dado | 100 | 0 |  | 2027-03-11 |  | 2027-03-30 |  | Tower B | Sub Structure | B2 | Finishes | Flooring & Dado
47110 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-12-14 | 2026-12-31 | Wet Area Waterproofing | 100 | 0 |  | 2027-03-11 |  | 2027-03-30 |  | Tower B | Super Structure | L32
45543 | Tower B - Super Structure - Finishes & MEP - L34 to L35 | Not Ready | Partition Wall-Blockwork | 2026-12-15 | 2026-12-22 | Partition Walls | 100 | 0 |  | 2027-03-12 |  | 2027-03-20 |  | Tower B | Super Structure | L34
45894 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-01-04 | 2027-01-06 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-03-13 |  | 2027-03-17 |  | Tower B | Super Structure
46971 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-01-04 | 2027-02-02 | Flooring & Dado works | 100 | 0 |  | 2027-03-13 |  | 2027-04-13 |  | Tower B | Super Structure | L24 | Finishes | Flooring & Dado
44638 | NTA_Zone 2 - Super Structure - GF to P1 | Not Ready | External Balustrade System | 2026-09-30 | 2026-10-17 | SS tray work | 100 | 0 |  | 2027-03-15 |  | 2027-03-19 |  | NTA_Zone 2 | Super Structure | GF
44639 | NTA_Zone 2 - Super Structure - GF to P1 | Not Ready | External Balustrade System | 2026-10-07 | 2026-10-24 | GRC framing & GRC cladding | 100 | 0 |  | 2027-03-15 |  | 2027-03-26 |  | NTA_Zone 2 | Super Structure | GF
44640 | NTA_Zone 2 - Super Structure - GF to P1 | Not Ready | External Balustrade System | 2026-10-07 | 2026-10-24 | Planter works | 100 | 0 |  | 2027-03-15 |  | 2027-03-26 |  | NTA_Zone 2 | Super Structure | GF
44640 | NTA_Zone 2 - Super Structure - GF to P1 | Not Ready | External Balustrade System | 2026-10-07 | 2026-10-24 | Planter works | 100 | 0 |  | 2027-03-15 |  | 2027-03-26 |  | NTA_Zone 2 | Super Structure | GF
45635 | Tower B - Super Structure - Finishes & MEP - L32 to L33 | Not Ready | Gypsum Plastering Works | 2026-12-17 | 2027-01-15 | L32-33 | 100 | 0 |  | 2027-03-15 |  | 2027-04-14 |  | Tower B | Super Structure | L32 | Finishes | Gypsum Plastering Works
45635 | Tower B - Super Structure - Finishes & MEP - L32 to L33 | Not Ready | Gypsum Plastering Works | 2026-12-17 | 2027-01-15 | L32-33 | 100 | 0 |  | 2027-03-15 |  | 2027-04-14 |  | Tower B | Super Structure | L32
45772 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-01-05 | 2027-01-06 | FAPA Cabling | 100 | 0 |  | 2027-03-15 |  | 2027-03-17 |  | Tower B | Sub Structure | B3
45831 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-01-05 | 2027-01-15 | False Ceiling | 100 | 0 |  | 2027-03-15 |  | 2027-03-27 |  | Tower B | Sub Structure | B1 | Finishes | False Ceiling
45923 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-01-05 | 2027-01-09 | Final Painting | 100 | 0 |  | 2027-03-15 |  | 2027-03-20 |  | Tower B | Super Structure |  | Finishes | Final Painting
45923 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-01-05 | 2027-01-09 | Final Painting | 100 | 0 |  | 2027-03-15 |  | 2027-03-20 |  | Tower B | Super Structure |  | Finishes | Final Painting
45923 | Tower B - Super Structure - Finishes & MEP - P2 to P3 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-01-05 | 2027-01-09 | Final Painting | 100 | 0 |  | 2027-03-15 |  | 2027-03-20 |  | Tower B | Super Structure |  | Finishes | Final Painting
47123 |  | Not Committed |  | 2026-12-17 | 2028-01-24 | L33-34 | 100 | 0 |  | 2027-03-15 |  | 2028-02-16
47123 |  | Not Committed |  | 2026-12-17 | 2028-01-24 | L33-34 | 100 | 0 |  | 2027-03-15 |  | 2028-02-16 |  |  |  |  | Finishes | Gypsum Plastering Works
47124 |  | Not Committed |  | 2026-12-17 | 2027-01-23 | MEP 1st Fixes | 100 | 0 |  | 2027-03-15 |  | 2027-04-22
47125 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-12-17 | 2026-12-24 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-03-15 |  | 2027-03-24 |  | Tower B | Super Structure | L33 | MEP | FPS 1st Fix - MEP & Finishes
47126 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-12-17 | 2026-12-22 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2027-03-15 |  | 2027-03-20 |  | Tower B | Super Structure | L33 | MEP | Electrical 1st Fixes
47127 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-12-17 | 2026-12-24 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2027-03-15 |  | 2027-03-24 |  | Tower B | Super Structure | L33
47716 |  | Not Ready |  | 2026-12-02 | 2026-12-24 | Slab_NTA | 100 | 0 |  | 2027-03-15 |  | 2027-04-08
47716 |  | Not Ready |  | 2026-12-02 | 2026-12-24 | Slab_NTA | 100 | 0 |  | 2027-03-15 |  | 2027-04-08 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
47723 |  | Not Ready |  | 2026-12-02 | 2026-12-18 | Slab_NTA (tie-beams) | 100 | 0 |  | 2027-03-15 |  | 2027-04-02
47723 |  | Not Ready |  | 2026-12-02 | 2026-12-18 | Slab_NTA (tie-beams) | 100 | 0 |  | 2027-03-15 |  | 2027-04-02 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
47963 | Tower B | Not Committed | Award of Packages | 2027-02-08 | 2027-05-03 | External Development | 100 | 0 |  | 2027-03-15 |  | 2027-06-04 |  | Tower B | --
47963 | Tower B | Not Committed | Award of Packages | 2027-02-08 | 2027-05-03 | External Development | 100 | 0 |  | 2027-03-15 |  | 2027-06-04 |  | Tower B | --
46161 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-01-06 | 2027-01-13 | FAPA Cabling | 100 | 0 |  | 2027-03-16 |  | 2027-03-25 |  | Tower B | Super Structure | L14
45895 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-01-07 | 2027-01-12 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-03-17 |  | 2027-03-24 |  | Tower B | Super Structure |  | MEP | Electrical
46970 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2027-01-07 | 2027-01-14 | Door & Window Frame work | 100 | 0 |  | 2027-03-17 |  | 2027-03-26 |  | Tower B | Super Structure | L24 | Finishes | Door & Window Frame work
46986 |  | Not Committed |  | 2027-01-07 | 2027-02-27 | Finishes after 1st Fix | 100 | 0 |  | 2027-03-17 |  | 2027-05-10
46987 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2027-01-07 | 2027-01-18 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2027-03-17 |  | 2027-03-30 |  | Tower B | Super Structure | L25 | Finishes | Blockwork
47093 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2026-12-19 | 2026-12-31 | Cement Plastering in wet areas | 100 | 0 |  | 2027-03-17 |  | 2027-03-30 |  | Tower B | Super Structure | L31
47437 | Tower B - Super Structure - Finishes & MEP - L28 to L33 | Not Ready | Façade Works - MEP & Finishes | 2027-01-07 | 2027-01-18 | DGU Assembly Installation | 100 | 0 |  | 2027-03-17 |  | 2027-03-30 |  | Tower B | Super Structure | L28 | Façade | Façade Works
47438 | Tower B - Super Structure - Finishes & MEP - L28 to L33 | Not Ready | Façade Works - MEP & Finishes | 2027-01-07 | 2027-02-05 | Installation of highly reflective metal sheet | 100 | 0 |  | 2027-03-17 |  | 2027-04-16 |  | Tower B | Super Structure | L28 | Façade | Façade Works
47439 | Tower B - Super Structure - Finishes & MEP - L28 to L33 | Not Ready | Façade Works - MEP & Finishes | 2027-01-07 | 2027-01-23 | Fixing of Backlit Laminated Glass assembly & ACP Panels | 100 | 0 |  | 2027-03-17 |  | 2027-04-05 |  | Tower B | Super Structure | L28 | Façade | Façade Works
47440 | Tower B - Super Structure - Finishes & MEP - L28 to L33 | Not Ready | Façade Works - MEP & Finishes | 2027-01-07 | 2027-01-23 | Fixing of Louvers | 100 | 0 |  | 2027-03-17 |  | 2027-04-05 |  | Tower B | Super Structure | L28 | Façade | Façade Works
47440 | Tower B - Super Structure - Finishes & MEP - L28 to L33 | Not Ready | Façade Works - MEP & Finishes | 2027-01-07 | 2027-01-23 | Fixing of Louvers | 100 | 0 |  | 2027-03-17 |  | 2027-04-05 |  | Tower B | Super Structure | L28
12036 |  | Not Committed |  | 2027-03-18 | 2027-03-18 | PROJECT COMPLETE | 100 | 0 |  | 2027-03-18 |  | 2027-04-21
45367 |  | Not Ready |  | 2026-12-21 | 2027-01-01 | L39-40 | 100 | 0 |  | 2027-03-18 |  | 2027-03-31
45367 |  | Not Ready |  | 2026-12-21 | 2027-01-01 | L39-40 | 100 | 0 |  | 2027-03-18 |  | 2027-03-31 |  |  |  |  | Finishes | Gypsum Plastering Works
45368 | Tower B - Super Structure - Core & Outer Slab L39-40 | Not Ready | RCC Works - Vertical | 2026-12-21 | 2026-12-30 | Outer Columns_TA | 100 | 0 |  | 2027-03-18 |  | 2027-03-29 |  | Tower B | Super Structure | L39 | RCC Sub Structure | RCC Works - Vertical
45549 |  | Not Committed |  | 2026-12-21 | 2027-01-21 | L36-37 | 100 | 0 |  | 2027-03-18 |  | 2027-04-20
45549 |  | Not Committed |  | 2026-12-21 | 2027-01-21 | L36-37 | 100 | 0 |  | 2027-03-18 |  | 2027-04-20 |  |  |  |  | Finishes | Gypsum Plastering Works
45550 | Tower B - Super Structure - Finishes & MEP - L36 to L37 | Not Ready | Partition Wall-Blockwork | 2026-12-21 | 2027-01-07 | De-shuttering & Area clearance | 100 | 0 |  | 2027-03-18 |  | 2027-04-06 |  | Tower B | Super Structure | L36
45860 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-01-08 | 2027-01-11 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-03-18 |  | 2027-03-23 |  | Tower B | Super Structure | GF | MEP | FPS 2nd Fix - MEP & Finishes
45861 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-01-08 | 2027-01-13 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-03-18 |  | 2027-03-25 |  | Tower B | Super Structure | GF | MEP | Electrical 2nd Fix - MEP & Finishes
45862 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-01-08 | 2027-01-15 | FAPA Device Fixing | 100 | 0 |  | 2027-03-18 |  | 2027-03-27 |  | Tower B | Super Structure | GF
45862 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-01-08 | 2027-01-15 | FAPA Device Fixing | 100 | 0 |  | 2027-03-18 |  | 2027-03-27 |  | Tower B | Super Structure | GF
45862 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-01-08 | 2027-01-15 | FAPA Device Fixing | 100 | 0 |  | 2027-03-18 |  | 2027-03-27 |  | Tower B | Super Structure | GF
45862 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-01-08 | 2027-01-15 | FAPA Device Fixing | 100 | 0 |  | 2027-03-18 |  | 2027-03-27 |  | Tower B | Super Structure | GF
45863 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-01-08 | 2027-01-11 | HVAC Grill Fixing | 100 | 0 |  | 2027-03-18 |  | 2027-03-23 |  | Tower B | Super Structure | GF | MEP | HVAC Grill Fixing
46671 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2027-01-11 | 2027-01-15 | PHE Final Fixes | 100 | 0 |  | 2027-03-18 |  | 2027-03-25 |  | Tower B | Super Structure | L7
45600 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 | Not Ready | Gypsum Plastering Works | 2027-01-09 | 2027-02-13 | B3 to B2_TA & NTA | 100 | 0 |  | 2027-03-19 |  | 2027-04-24 |  | Tower B | Sub Structure | B3 | Finishes | Gypsum Plastering Works
45600 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 | Not Ready | Gypsum Plastering Works | 2027-01-09 | 2027-02-13 | B3 to B2_TA & NTA | 100 | 0 |  | 2027-03-19 |  | 2027-04-24 |  | Tower B | Sub Structure | B3
45773 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-01-09 | 2027-01-16 | HVAC Ducting | 100 | 0 |  | 2027-03-19 |  | 2027-03-29 |  | Tower B | Sub Structure | B3 | MEP | HVAC Ducting
45774 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-01-09 | 2027-01-27 | Flooring & Dado | 100 | 0 |  | 2027-03-19 |  | 2027-04-07 |  | Tower B | Sub Structure | B3 | Finishes | Flooring & Dado
46162 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-01-09 | 2027-01-20 | HVAC Ducting | 100 | 0 |  | 2027-03-19 |  | 2027-04-01 |  | Tower B | Super Structure | L14 | MEP | HVAC Ducting
46174 |  | Not Committed |  | 2027-01-09 | 2027-09-24 | L15-16 | 100 | 0 |  | 2027-03-19 |  | 2027-10-28
46174 |  | Not Committed |  | 2027-01-09 | 2027-09-24 | L15-16 | 100 | 0 |  | 2027-03-19 |  | 2027-10-28 |  |  |  |  | Finishes | Gypsum Plastering Works
46175 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-01-09 | 2027-01-20 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-03-19 |  | 2027-04-01 |  | Tower B | Super Structure | L15 | MEP | FPS 1st Fix - MEP & Finishes
46176 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-01-09 | 2027-01-16 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-03-19 |  | 2027-03-29 |  | Tower B | Super Structure | L15 | MEP | Electrical 1st Fixes
46936 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2027-01-09 | 2027-01-22 | False Ceiling | 100 | 0 |  | 2027-03-19 |  | 2027-04-03 |  | Tower B | Super Structure | L22 | Finishes | False Ceiling
45544 | Tower B - Super Structure - Finishes & MEP - L34 to L35 | Not Ready | Partition Wall-Blockwork | 2026-12-23 | 2026-12-29 | Staircase Area | 100 | 0 |  | 2027-03-20 |  | 2027-03-27 |  | Tower B | Super Structure | L34
45864 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-01-12 | 2027-01-14 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-03-23 |  | 2027-03-26 |  | Tower B | Super Structure | GF
46687 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-01-16 | 2027-01-23 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-03-23 |  | 2027-03-31 |  | Tower B | Super Structure | L8 | MEP | FPS 2nd Fix - MEP & Finishes
46688 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-01-16 | 2027-01-23 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-03-23 |  | 2027-03-31 |  | Tower B | Super Structure | L8 | MEP | Electrical 2nd Fix - MEP & Finishes
46703 |  | Not Committed |  | 2027-01-16 | 2027-02-22 | MEP final fix & Finishes | 100 | 0 |  | 2027-03-23 |  | 2027-04-26
46704 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2027-01-16 | 2027-01-30 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2027-03-23 |  | 2027-04-03 |  | Tower B | Super Structure | L9 | Finishes | Door & Window Fixing
45369 | Tower B - Super Structure - Core & Outer Slab L39-40 | Not Ready | RCC Works - Slab | 2026-12-26 | 2027-01-01 | Outer Slab_TA | 100 | 0 |  | 2027-03-24 |  | 2027-03-31 |  | Tower B | Super Structure | L39 | RCC Sub Structure | RCC Works - Slab
45804 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-01-13 | 2027-01-23 | False Ceiling | 100 | 0 |  | 2027-03-24 |  | 2027-04-05 |  | Tower B | Sub Structure | B2 | Finishes | False Ceiling
45896 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-01-13 | 2027-01-18 | Final Painting | 100 | 0 |  | 2027-03-24 |  | 2027-03-30 |  | Tower B | Super Structure |  | Finishes | Final Painting
45896 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-01-13 | 2027-01-18 | Final Painting | 100 | 0 |  | 2027-03-24 |  | 2027-03-30 |  | Tower B | Super Structure |  | Finishes | Final Painting
45896 | Tower B - Super Structure - Finishes & MEP - P1 to P2 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-01-13 | 2027-01-18 | Final Painting | 100 | 0 |  | 2027-03-24 |  | 2027-03-30 |  | Tower B | Super Structure |  | Finishes | Final Painting
47128 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2026-12-26 | 2027-01-12 | Wet Area Waterproofing | 100 | 0 |  | 2027-03-24 |  | 2027-04-10 |  | Tower B | Super Structure | L33
45547 | Tower B - Super Structure - Finishes & MEP - L35 to L36 | Not Ready | Partition Wall-Blockwork | 2026-12-28 | 2027-01-04 | Partition Walls | 100 | 0 |  | 2027-03-25 |  | 2027-04-02 |  | Tower B | Super Structure | L35
45679 |  | Not Committed |  | 2027-02-13 | 2028-02-26 | Pump Room | 100 | 0 |  | 2027-03-25 |  | 2028-04-07
45680 | Tower B - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2027-02-13 | 2027-04-07 | Tank Waterproofing | 100 | 0 |  | 2027-03-25 |  | 2027-05-19 |  | Tower B | Super Structure
46672 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2027-01-16 | 2027-01-23 | Painting Works | 100 | 0 |  | 2027-03-25 |  | 2027-04-02 |  | Tower B | Super Structure | L7 | Finishes | Painting Works
40703 | Tower A - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | Fixing of Artifacts - MEP & Finishes | 2025-12-03 | 2026-01-07 | Fixing of Artifacts | 100 | 0 |  | 2027-03-26 |  | 2027-04-29 |  | Tower A | Super Structure | GF
45865 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-01-15 | 2027-01-20 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-03-26 |  | 2027-04-01 |  | Tower B | Super Structure | GF | MEP | Electrical
46989 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-01-15 | 2027-02-13 | Flooring & Dado works | 100 | 0 |  | 2027-03-26 |  | 2027-04-24 |  | Tower B | Super Structure | L25 | Finishes | Flooring & Dado
45636 | Tower B - Super Structure - Finishes & MEP - L33 to L34 | Not Ready | Gypsum Plastering Works | 2026-12-30 | 2027-01-28 | L33-34 | 100 | 0 |  | 2027-03-27 |  | 2027-04-26 |  | Tower B | Super Structure | L33 | Finishes | Gypsum Plastering Works
45636 | Tower B - Super Structure - Finishes & MEP - L33 to L34 | Not Ready | Gypsum Plastering Works | 2026-12-30 | 2027-01-28 | L33-34 | 100 | 0 |  | 2027-03-27 |  | 2027-04-26 |  | Tower B | Super Structure | L33
45832 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-01-16 | 2027-01-19 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-03-27 |  | 2027-03-31 |  | Tower B | Sub Structure | B1 | MEP | FPS 2nd Fix - MEP & Finishes
45833 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-01-16 | 2027-01-21 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-03-27 |  | 2027-04-02 |  | Tower B | Sub Structure | B1 | MEP | Electrical 2nd Fix - MEP & Finishes
45834 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-01-16 | 2027-01-23 | FAPA Device Fixing | 100 | 0 |  | 2027-03-27 |  | 2027-04-05 |  | Tower B | Sub Structure | B1
45834 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-01-16 | 2027-01-23 | FAPA Device Fixing | 100 | 0 |  | 2027-03-27 |  | 2027-04-05 |  | Tower B | Sub Structure | B1
45834 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-01-16 | 2027-01-23 | FAPA Device Fixing | 100 | 0 |  | 2027-03-27 |  | 2027-04-05 |  | Tower B | Sub Structure | B1
45834 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-01-16 | 2027-01-23 | FAPA Device Fixing | 100 | 0 |  | 2027-03-27 |  | 2027-04-05 |  | Tower B | Sub Structure | B1
45835 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-01-16 | 2027-01-19 | HVAC Grill Fixing | 100 | 0 |  | 2027-03-27 |  | 2027-03-31 |  | Tower B | Sub Structure | B1 | MEP | HVAC Grill Fixing
47141 |  | Not Committed |  | 2026-12-30 | 2028-02-08 | L34-35 | 100 | 0 |  | 2027-03-27 |  | 2028-03-01
47141 |  | Not Committed |  | 2026-12-30 | 2028-02-08 | L34-35 | 100 | 0 |  | 2027-03-27 |  | 2028-03-01 |  |  |  |  | Finishes | Gypsum Plastering Works
47142 |  | Not Committed |  | 2026-12-30 | 2027-02-05 | MEP 1st Fixes | 100 | 0 |  | 2027-03-27 |  | 2027-05-05
47143 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2026-12-30 | 2027-01-06 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-03-27 |  | 2027-04-05 |  | Tower B | Super Structure | L34 | MEP | FPS 1st Fix - MEP & Finishes
47144 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2026-12-30 | 2027-01-04 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2027-03-27 |  | 2027-04-02 |  | Tower B | Super Structure | L34 | MEP | Electrical 1st Fixes
47145 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2026-12-30 | 2027-01-06 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2027-03-27 |  | 2027-04-05 |  | Tower B | Super Structure | L34
47724 |  | Not Committed |  | 2026-12-14 | 2027-01-18 | Pour 12 (PB-03 to PB-06) | 100 | 0 |  | 2027-03-27 |  | 2027-05-03
47725 |  | Not Ready |  | 2026-12-14 | 2026-12-31 | Columns/ Walls_NTA | 100 | 0 |  | 2027-03-27 |  | 2027-04-14
47725 |  | Not Ready |  | 2026-12-14 | 2026-12-31 | Columns/ Walls_NTA | 100 | 0 |  | 2027-03-27 |  | 2027-04-14 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
47726 |  | Not Ready |  | 2026-12-14 | 2027-01-06 | Staircase_NTA | 100 | 0 |  | 2027-03-27 |  | 2027-04-20
47726 |  | Not Ready |  | 2026-12-14 | 2027-01-06 | Staircase_NTA | 100 | 0 |  | 2027-03-27 |  | 2027-04-20 |  |  |  |  | RCC Sub Structure | Staircase & Ramp RCC Works
47728 |  | Not Committed |  | 2026-12-14 | 2027-02-23 | P1 to P2 | 100 | 0 |  | 2027-03-27 |  | 2027-06-08
47728 |  | Not Committed |  | 2026-12-14 | 2027-02-23 | P1 to P2 | 100 | 0 |  | 2027-03-27 |  | 2027-06-08
47728 |  | Not Committed |  | 2026-12-14 | 2027-02-23 | P1 to P2 | 100 | 0 |  | 2027-03-27 |  | 2027-06-08
47736 |  | Not Committed |  | 2026-12-14 | 2027-01-18 | Pour 10 (PA-A to PB-J) | 100 | 0 |  | 2027-03-27 |  | 2027-05-03
47737 |  | Not Ready |  | 2026-12-14 | 2026-12-31 | Columns/ Walls_NTA | 100 | 0 |  | 2027-03-27 |  | 2027-04-14
47737 |  | Not Ready |  | 2026-12-14 | 2026-12-31 | Columns/ Walls_NTA | 100 | 0 |  | 2027-03-27 |  | 2027-04-14 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
47738 |  | Not Ready |  | 2026-12-14 | 2027-01-12 | Ramp_NTA | 100 | 0 |  | 2027-03-27 |  | 2027-04-26
44274 |  | Not Ready |  | 2026-11-05 | 2026-11-10 | CFO Visit 3 | 100 | 0 |  | 2027-03-29 |  | 2027-05-22
46177 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-01-18 | 2027-01-25 | FAPA Cabling | 100 | 0 |  | 2027-03-29 |  | 2027-04-06 |  | Tower B | Super Structure | L15
46988 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2027-01-19 | 2027-01-27 | Door & Window Frame work | 100 | 0 |  | 2027-03-30 |  | 2027-04-07 |  | Tower B | Super Structure | L25 | Finishes | Door & Window Frame work
47004 |  | Not Committed |  | 2027-01-19 | 2027-03-11 | Finishes after 1st Fix | 100 | 0 |  | 2027-03-30 |  | 2027-05-22
47005 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2027-01-19 | 2027-01-30 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2027-03-30 |  | 2027-04-10 |  | Tower B | Super Structure | L26 | Finishes | Blockwork
47111 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2027-01-01 | 2027-01-12 | Cement Plastering in wet areas | 100 | 0 |  | 2027-03-30 |  | 2027-04-10 |  | Tower B | Super Structure | L32
47441 | Tower B - Super Structure - Finishes & MEP - L28 to L33 | Not Ready | Façade Works - MEP & Finishes | 2027-01-19 | 2027-02-05 | Accessories & Alignment | 100 | 0 |  | 2027-03-30 |  | 2027-04-16 |  | Tower B | Super Structure | L28 | Façade | Façade Works
47441 | Tower B - Super Structure - Finishes & MEP - L28 to L33 | Not Ready | Façade Works - MEP & Finishes | 2027-01-19 | 2027-02-05 | Accessories & Alignment | 100 | 0 |  | 2027-03-30 |  | 2027-04-16 |  | Tower B | Super Structure | L28
45370 |  | Not Ready |  | 2027-01-02 | 2027-01-13 | L40-41 | 100 | 0 |  | 2027-03-31 |  | 2027-04-12
45370 |  | Not Ready |  | 2027-01-02 | 2027-01-13 | L40-41 | 100 | 0 |  | 2027-03-31 |  | 2027-04-12 |  |  |  |  | Finishes | Gypsum Plastering Works
45371 | Tower B - Super Structure - Core & Outer Slab L40-41 | Not Ready | RCC Works - Vertical | 2027-01-02 | 2027-01-11 | Outer Columns_TA | 100 | 0 |  | 2027-03-31 |  | 2027-04-09 |  | Tower B | Super Structure | L40 | RCC Sub Structure | RCC Works - Vertical
45553 |  | Not Committed |  | 2027-01-02 | 2027-02-03 | L37-38 | 100 | 0 |  | 2027-03-31 |  | 2027-05-03
45553 |  | Not Committed |  | 2027-01-02 | 2027-02-03 | L37-38 | 100 | 0 |  | 2027-03-31 |  | 2027-05-03 |  |  |  |  | Finishes | Gypsum Plastering Works
45554 | Tower B - Super Structure - Finishes & MEP - L37 to L38 | Not Ready | Partition Wall-Blockwork | 2027-01-02 | 2027-01-19 | De-shuttering & Area clearance | 100 | 0 |  | 2027-03-31 |  | 2027-04-17 |  | Tower B | Super Structure | L37
45836 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-01-20 | 2027-01-22 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-03-31 |  | 2027-04-03 |  | Tower B | Sub Structure | B1
46689 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2027-01-25 | 2027-01-30 | PHE Final Fixes | 100 | 0 |  | 2027-03-31 |  | 2027-04-06 |  | Tower B | Super Structure | L8
45775 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-01-21 | 2027-02-02 | False Ceiling | 100 | 0 |  | 2027-04-01 |  | 2027-04-13 |  | Tower B | Sub Structure | B3 | Finishes | False Ceiling
45866 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-01-21 | 2027-01-27 | Final Painting | 100 | 0 |  | 2027-04-01 |  | 2027-04-07 |  | Tower B | Super Structure | GF | Finishes | Final Painting
45866 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-01-21 | 2027-01-27 | Final Painting | 100 | 0 |  | 2027-04-01 |  | 2027-04-07 |  | Tower B | Super Structure | GF | Finishes | Final Painting
45866 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-01-21 | 2027-01-27 | Final Painting | 100 | 0 |  | 2027-04-01 |  | 2027-04-07 |  | Tower B | Super Structure | GF | Finishes | Final Painting
46178 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-01-21 | 2027-02-02 | HVAC Ducting | 100 | 0 |  | 2027-04-01 |  | 2027-04-13 |  | Tower B | Super Structure | L15 | MEP | HVAC Ducting
46190 |  | Not Committed |  | 2027-01-21 | 2027-09-30 | L16-17 | 100 | 0 |  | 2027-04-01 |  | 2027-11-04
46190 |  | Not Committed |  | 2027-01-21 | 2027-09-30 | L16-17 | 100 | 0 |  | 2027-04-01 |  | 2027-11-04 |  |  |  |  | Finishes | Gypsum Plastering Works
46191 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-01-21 | 2027-02-02 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-04-01 |  | 2027-04-13 |  | Tower B | Super Structure | L16 | MEP | FPS 1st Fix - MEP & Finishes
46192 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-01-21 | 2027-01-29 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-04-01 |  | 2027-04-09 |  | Tower B | Super Structure | L16 | MEP | Electrical 1st Fixes
46954 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2027-01-21 | 2027-02-04 | False Ceiling | 100 | 0 |  | 2027-04-01 |  | 2027-04-15 |  | Tower B | Super Structure | L23 | Finishes | False Ceiling
47815 |  | Not Ready |  | 2026-09-22 | 2026-12-02 | B2 to B1 | 100 | 0 |  | 2027-04-01 |  | 2027-06-12
47815 |  | Not Ready |  | 2026-09-22 | 2026-12-02 | B2 to B1 | 100 | 0 |  | 2027-04-01 |  | 2027-06-12
47815 |  | Not Ready |  | 2026-09-22 | 2026-12-02 | B2 to B1 | 100 | 0 |  | 2027-04-01 |  | 2027-06-12
47822 |  | Not Committed |  | 2026-09-22 | 2028-07-06 | Finishes (Lobby & Floor area) | 100 | 0 |  | 2027-04-01 |  | 2028-09-21
47823 |  | Not Committed |  | 2026-09-22 | 2027-01-07 | B3 to B2 | 100 | 0 |  | 2027-04-01 |  | 2027-07-17
47823 |  | Not Committed |  | 2026-09-22 | 2027-01-07 | B3 to B2 | 100 | 0 |  | 2027-04-01 |  | 2027-07-17
47823 |  | Not Committed |  | 2026-09-22 | 2027-01-07 | B3 to B2 | 100 | 0 |  | 2027-04-01 |  | 2027-07-17
47824 |  | Not Ready |  | 2026-09-22 | 2026-10-28 | VDF Flooring | 100 | 0 |  | 2027-04-01 |  | 2027-05-07
47824 |  | Not Ready |  | 2026-09-22 | 2026-10-28 | VDF Flooring | 100 | 0 |  | 2027-04-01 |  | 2027-05-07
45548 | Tower B - Super Structure - Finishes & MEP - L35 to L36 | Not Ready | Partition Wall-Blockwork | 2027-01-05 | 2027-01-09 | Staircase Area | 100 | 0 |  | 2027-04-02 |  | 2027-04-08 |  | Tower B | Super Structure | L35
47729 |  | Not Committed |  | 2026-12-19 | 2027-01-30 | Pour 8 (grid PB-B to PB-J) | 100 | 0 |  | 2027-04-02 |  | 2027-05-14
47730 |  | Not Ready |  | 2026-12-19 | 2027-01-06 | Columns/ Walls_NTA | 100 | 0 |  | 2027-04-02 |  | 2027-04-20
47730 |  | Not Ready |  | 2026-12-19 | 2027-01-06 | Columns/ Walls_NTA | 100 | 0 |  | 2027-04-02 |  | 2027-04-20 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
47731 |  | Not Ready |  | 2026-12-19 | 2027-01-12 | Staircase_NTA | 100 | 0 |  | 2027-04-02 |  | 2027-04-26
47731 |  | Not Ready |  | 2026-12-19 | 2027-01-12 | Staircase_NTA | 100 | 0 |  | 2027-04-02 |  | 2027-04-26 |  |  |  |  | RCC Sub Structure | Staircase & Ramp RCC Works
45837 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-01-23 | 2027-01-29 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-04-03 |  | 2027-04-09 |  | Tower B | Sub Structure | B1 | MEP | Electrical
46705 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-02-01 | 2027-02-08 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-04-03 |  | 2027-04-12 |  | Tower B | Super Structure | L9 | MEP | FPS 2nd Fix - MEP & Finishes
46706 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-02-01 | 2027-02-08 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-04-03 |  | 2027-04-12 |  | Tower B | Super Structure | L9 | MEP | Electrical 2nd Fix - MEP & Finishes
46721 |  | Not Committed |  | 2027-02-01 | 2027-03-08 | MEP final fix & Finishes | 100 | 0 |  | 2027-04-03 |  | 2027-05-08
46722 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2027-02-01 | 2027-02-13 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2027-04-03 |  | 2027-04-15 |  | Tower B | Super Structure | L10 | Finishes | Door & Window Fixing
45372 | Tower B - Super Structure - Core & Outer Slab L40-41 | Not Ready | RCC Works - Slab | 2027-01-07 | 2027-01-13 | Outer Slab_TA | 100 | 0 |  | 2027-04-05 |  | 2027-04-12 |  | Tower B | Super Structure | L40 | RCC Sub Structure | RCC Works - Slab
45805 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-01-25 | 2027-01-28 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-04-05 |  | 2027-04-08 |  | Tower B | Sub Structure | B2 | MEP | FPS 2nd Fix - MEP & Finishes
45806 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-01-25 | 2027-01-30 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-04-05 |  | 2027-04-10 |  | Tower B | Sub Structure | B2 | MEP | Electrical 2nd Fix - MEP & Finishes
45807 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-01-25 | 2027-02-02 | FAPA Device Fixing | 100 | 0 |  | 2027-04-05 |  | 2027-04-13 |  | Tower B | Sub Structure | B2
45807 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-01-25 | 2027-02-02 | FAPA Device Fixing | 100 | 0 |  | 2027-04-05 |  | 2027-04-13 |  | Tower B | Sub Structure | B2
45807 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-01-25 | 2027-02-02 | FAPA Device Fixing | 100 | 0 |  | 2027-04-05 |  | 2027-04-13 |  | Tower B | Sub Structure | B2
45807 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-01-25 | 2027-02-02 | FAPA Device Fixing | 100 | 0 |  | 2027-04-05 |  | 2027-04-13 |  | Tower B | Sub Structure | B2
45808 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-01-25 | 2027-01-28 | HVAC Grill Fixing | 100 | 0 |  | 2027-04-05 |  | 2027-04-08 |  | Tower B | Sub Structure | B2 | MEP | HVAC Grill Fixing
47146 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2027-01-07 | 2027-01-23 | Wet Area Waterproofing | 100 | 0 |  | 2027-04-05 |  | 2027-04-22 |  | Tower B | Super Structure | L34
45551 | Tower B - Super Structure - Finishes & MEP - L36 to L37 | Not Ready | Partition Wall-Blockwork | 2027-01-08 | 2027-01-15 | Partition Walls | 100 | 0 |  | 2027-04-06 |  | 2027-04-14 |  | Tower B | Super Structure | L36
46690 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2027-02-01 | 2027-02-08 | Painting Works | 100 | 0 |  | 2027-04-06 |  | 2027-04-14 |  | Tower B | Super Structure | L8 | Finishes | Painting Works
47007 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-01-28 | 2027-02-25 | Flooring & Dado works | 100 | 0 |  | 2027-04-07 |  | 2027-05-07 |  | Tower B | Super Structure | L26 | Finishes | Flooring & Dado
45637 | Tower B - Super Structure - Finishes & MEP - L34 to L35 | Not Ready | Gypsum Plastering Works | 2027-01-11 | 2027-02-09 | L34-35 | 100 | 0 |  | 2027-04-08 |  | 2027-05-08 |  | Tower B | Super Structure | L34 | Finishes | Gypsum Plastering Works
45637 | Tower B - Super Structure - Finishes & MEP - L34 to L35 | Not Ready | Gypsum Plastering Works | 2027-01-11 | 2027-02-09 | L34-35 | 100 | 0 |  | 2027-04-08 |  | 2027-05-08 |  | Tower B | Super Structure | L34
45809 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-01-29 | 2027-02-01 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-04-08 |  | 2027-04-12 |  | Tower B | Sub Structure | B2
47159 |  | Not Committed |  | 2027-01-11 | 2028-02-22 | L35-36 (Refuge) | 100 | 0 |  | 2027-04-08 |  | 2028-03-16
47160 |  | Not Committed |  | 2027-01-11 | 2027-02-17 | MEP 1st Fixes | 100 | 0 |  | 2027-04-08 |  | 2027-05-18
47161 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-01-11 | 2027-01-18 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-04-08 |  | 2027-04-16 |  | Tower B | Super Structure | L35 | MEP | FPS 1st Fix - MEP & Finishes
47162 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-01-11 | 2027-01-15 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2027-04-08 |  | 2027-04-14 |  | Tower B | Super Structure | L35 | MEP | Electrical 1st Fixes
47163 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2027-01-11 | 2027-01-18 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2027-04-08 |  | 2027-04-16 |  | Tower B | Super Structure | L35
45838 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-01-30 | 2027-02-04 | Final Painting | 100 | 0 |  | 2027-04-09 |  | 2027-04-15 |  | Tower B | Sub Structure | B1 | Finishes | Final Painting
45838 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-01-30 | 2027-02-04 | Final Painting | 100 | 0 |  | 2027-04-09 |  | 2027-04-15 |  | Tower B | Sub Structure | B1 | Finishes | Final Painting
45838 | Tower B - Sub Structure - Finishes & MEP - B1 to GF - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-01-30 | 2027-02-04 | Final Painting | 100 | 0 |  | 2027-04-09 |  | 2027-04-15 |  | Tower B | Sub Structure | B1 | Finishes | Final Painting
46193 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-01-30 | 2027-02-06 | FAPA Cabling | 100 | 0 |  | 2027-04-09 |  | 2027-04-17 |  | Tower B | Super Structure | L16
47006 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2027-02-01 | 2027-02-08 | Door & Window Frame work | 100 | 0 |  | 2027-04-10 |  | 2027-04-19 |  | Tower B | Super Structure | L26 | Finishes | Door & Window Frame work
47022 |  | Not Committed |  | 2027-02-01 | 2027-03-24 | Finishes after 1st Fix | 100 | 0 |  | 2027-04-10 |  | 2027-06-03
47023 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2027-02-01 | 2027-02-11 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2027-04-10 |  | 2027-04-22 |  | Tower B | Super Structure | L27 | Finishes | Blockwork
47129 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2027-01-13 | 2027-01-23 | Cement Plastering in wet areas | 100 | 0 |  | 2027-04-10 |  | 2027-04-22 |  | Tower B | Super Structure | L33
44284 |  | Not Ready |  | 2026-10-19 | 2026-12-30 | Project Completion & Handover | 100 | 0 |  | 2027-04-12 |  | 2027-06-28
45373 |  | Not Ready |  | 2027-01-14 | 2027-01-25 | L41-42 | 100 | 0 |  | 2027-04-12 |  | 2027-04-23
45373 |  | Not Ready |  | 2027-01-14 | 2027-01-25 | L41-42 | 100 | 0 |  | 2027-04-12 |  | 2027-04-23 |  |  |  |  | Finishes | Gypsum Plastering Works
45374 | Tower B - Super Structure - Core & Outer Slab L41-42 | Not Ready | RCC Works - Vertical | 2027-01-14 | 2027-01-22 | Outer Columns_TA | 100 | 0 |  | 2027-04-12 |  | 2027-04-21 |  | Tower B | Super Structure | L41 | RCC Sub Structure | RCC Works - Vertical
45557 |  | Not Committed |  | 2027-01-14 | 2027-02-15 | L38-39 | 100 | 0 |  | 2027-04-12 |  | 2027-05-14
45557 |  | Not Committed |  | 2027-01-14 | 2027-02-15 | L38-39 | 100 | 0 |  | 2027-04-12 |  | 2027-05-14 |  |  |  |  | Finishes | Gypsum Plastering Works
45558 | Tower B - Super Structure - Finishes & MEP - L38 to L39 | Not Ready | Partition Wall-Blockwork | 2027-01-14 | 2027-02-01 | De-shuttering & Area clearance | 100 | 0 |  | 2027-04-12 |  | 2027-04-29 |  | Tower B | Super Structure | L38
45756 | Tower B - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2027-01-14 | 2027-02-06 | Electrical Rising Mains | 100 | 0 |  | 2027-04-12 |  | 2027-05-06 |  | Tower B | Super Structure | L25
45810 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-02-02 | 2027-02-06 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-04-12 |  | 2027-04-17 |  | Tower B | Sub Structure | B2 | MEP | Electrical
46707 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2027-02-09 | 2027-02-13 | PHE Final Fixes | 100 | 0 |  | 2027-04-12 |  | 2027-04-17 |  | Tower B | Super Structure | L9
45776 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-02-03 | 2027-02-05 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-04-13 |  | 2027-04-16 |  | Tower B | Sub Structure | B3 | MEP | FPS 2nd Fix - MEP & Finishes
45777 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-02-03 | 2027-02-08 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-04-13 |  | 2027-04-19 |  | Tower B | Sub Structure | B3 | MEP | Electrical 2nd Fix - MEP & Finishes
45778 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-02-03 | 2027-02-10 | FAPA Device Fixing | 100 | 0 |  | 2027-04-13 |  | 2027-04-21 |  | Tower B | Sub Structure | B3
45778 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-02-03 | 2027-02-10 | FAPA Device Fixing | 100 | 0 |  | 2027-04-13 |  | 2027-04-21 |  | Tower B | Sub Structure | B3
45778 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-02-03 | 2027-02-10 | FAPA Device Fixing | 100 | 0 |  | 2027-04-13 |  | 2027-04-21 |  | Tower B | Sub Structure | B3
45778 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-02-03 | 2027-02-10 | FAPA Device Fixing | 100 | 0 |  | 2027-04-13 |  | 2027-04-21 |  | Tower B | Sub Structure | B3
45779 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-02-03 | 2027-02-05 | HVAC Grill Fixing | 100 | 0 |  | 2027-04-13 |  | 2027-04-16 |  | Tower B | Sub Structure | B3 | MEP | HVAC Grill Fixing
46181 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-02-03 | 2027-03-03 | Flooring & Dado | 100 | 0 |  | 2027-04-13 |  | 2027-05-13 |  | Tower B | Super Structure | L15 | Finishes | Flooring & Dado
46194 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-02-03 | 2027-02-13 | HVAC Ducting | 100 | 0 |  | 2027-04-13 |  | 2027-04-24 |  | Tower B | Super Structure | L16 | MEP | HVAC Ducting
46206 |  | Not Committed |  | 2027-02-03 | 2027-10-07 | L17-18 | 100 | 0 |  | 2027-04-13 |  | 2027-11-10
46206 |  | Not Committed |  | 2027-02-03 | 2027-10-07 | L17-18 | 100 | 0 |  | 2027-04-13 |  | 2027-11-10 |  |  |  |  | Finishes | Gypsum Plastering Works
46207 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-02-03 | 2027-02-13 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-04-13 |  | 2027-04-24 |  | Tower B | Super Structure | L17 | MEP | FPS 1st Fix - MEP & Finishes
46208 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-02-03 | 2027-02-10 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-04-13 |  | 2027-04-21 |  | Tower B | Super Structure | L17 | MEP | Electrical 1st Fixes
46972 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2027-02-03 | 2027-02-16 | False Ceiling | 100 | 0 |  | 2027-04-13 |  | 2027-04-27 |  | Tower B | Super Structure | L24 | Finishes | False Ceiling
45552 | Tower B - Super Structure - Finishes & MEP - L36 to L37 | Not Ready | Partition Wall-Blockwork | 2027-01-16 | 2027-01-21 | Staircase Area | 100 | 0 |  | 2027-04-14 |  | 2027-04-20 |  | Tower B | Super Structure | L36
47727 |  | Not Ready |  | 2027-01-01 | 2027-01-18 | Slab_NTA | 100 | 0 |  | 2027-04-14 |  | 2027-05-03
47727 |  | Not Ready |  | 2027-01-01 | 2027-01-18 | Slab_NTA | 100 | 0 |  | 2027-04-14 |  | 2027-05-03 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
47739 |  | Not Ready |  | 2027-01-01 | 2027-01-18 | Slab_NTA | 100 | 0 |  | 2027-04-14 |  | 2027-05-03
47739 |  | Not Ready |  | 2027-01-01 | 2027-01-18 | Slab_NTA | 100 | 0 |  | 2027-04-14 |  | 2027-05-03 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
47740 |  | Not Committed |  | 2027-01-01 | 2027-01-23 | Pour 11 (PB-C to PB-K) | 100 | 0 |  | 2027-04-14 |  | 2027-05-08
47741 |  | Not Ready |  | 2027-01-01 | 2027-01-18 | Columns/ Walls_NTA | 100 | 0 |  | 2027-04-14 |  | 2027-05-03
47741 |  | Not Ready |  | 2027-01-01 | 2027-01-18 | Columns/ Walls_NTA | 100 | 0 |  | 2027-04-14 |  | 2027-05-03 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
46723 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-02-15 | 2027-02-22 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-04-15 |  | 2027-04-23 |  | Tower B | Super Structure | L10 | MEP | FPS 2nd Fix - MEP & Finishes
46724 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-02-15 | 2027-02-22 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-04-15 |  | 2027-04-23 |  | Tower B | Super Structure | L10 | MEP | Electrical 2nd Fix - MEP & Finishes
46739 |  | Not Committed |  | 2027-02-15 | 2027-03-23 | MEP final fix & Finishes | 100 | 0 |  | 2027-04-15 |  | 2027-05-21
46740 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2027-02-15 | 2027-02-27 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2027-04-15 |  | 2027-04-27 |  | Tower B | Super Structure | L11 | Finishes | Door & Window Fixing
45375 | Tower B - Super Structure - Core & Outer Slab L41-42 | Not Ready | RCC Works - Slab | 2027-01-19 | 2027-01-25 | Outer Slab_TA | 100 | 0 |  | 2027-04-16 |  | 2027-04-23 |  | Tower B | Super Structure | L41 | RCC Sub Structure | RCC Works - Slab
45780 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-02-06 | 2027-02-09 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-04-16 |  | 2027-04-20 |  | Tower B | Sub Structure | B3
47164 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2027-01-19 | 2027-02-05 | Wet Area Waterproofing | 100 | 0 |  | 2027-04-16 |  | 2027-05-05 |  | Tower B | Super Structure | L35
47442 |  | Not Committed |  | 2027-02-06 | 2027-04-12 | L33-38 | 100 | 0 |  | 2027-04-16 |  | 2027-06-22
47443 | Tower B - Super Structure - Finishes & MEP - L33 to L38 | Not Ready | Façade Works - MEP & Finishes | 2027-02-06 | 2027-03-06 | Al. Frame section (Mullion & Transom) Installation | 100 | 0 |  | 2027-04-16 |  | 2027-05-18 |  | Tower B | Super Structure | L33 | Façade | Façade Works
45555 | Tower B - Super Structure - Finishes & MEP - L37 to L38 | Not Ready | Partition Wall-Blockwork | 2027-01-20 | 2027-01-28 | Partition Walls | 100 | 0 |  | 2027-04-17 |  | 2027-04-26 |  | Tower B | Super Structure | L37
45811 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-02-08 | 2027-02-12 | Final Painting | 100 | 0 |  | 2027-04-17 |  | 2027-04-23 |  | Tower B | Sub Structure | B2 | Finishes | Final Painting
45811 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-02-08 | 2027-02-12 | Final Painting | 100 | 0 |  | 2027-04-17 |  | 2027-04-23 |  | Tower B | Sub Structure | B2 | Finishes | Final Painting
45811 | Tower B - Sub Structure - Finishes & MEP - B2 to B1 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-02-08 | 2027-02-12 | Final Painting | 100 | 0 |  | 2027-04-17 |  | 2027-04-23 |  | Tower B | Sub Structure | B2 | Finishes | Final Painting
46708 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2027-02-15 | 2027-02-22 | Painting Works | 100 | 0 |  | 2027-04-17 |  | 2027-04-26 |  | Tower B | Super Structure | L9 | Finishes | Painting Works
47025 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-02-09 | 2027-03-09 | Flooring & Dado works | 100 | 0 |  | 2027-04-19 |  | 2027-05-20 |  | Tower B | Super Structure | L27 | Finishes | Flooring & Dado
45638 | Tower B - Super Structure - Finishes & MEP - L35 to L36 | Not Ready | Gypsum Plastering Works | 2027-01-22 | 2027-02-20 | L35-36 | 100 | 0 |  | 2027-04-20 |  | 2027-05-21 |  | Tower B | Super Structure | L35 | Finishes | Gypsum Plastering Works
45638 | Tower B - Super Structure - Finishes & MEP - L35 to L36 | Not Ready | Gypsum Plastering Works | 2027-01-22 | 2027-02-20 | L35-36 | 100 | 0 |  | 2027-04-20 |  | 2027-05-21 |  | Tower B | Super Structure | L35
45781 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-02-10 | 2027-02-15 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-04-20 |  | 2027-04-26 |  | Tower B | Sub Structure | B3 | MEP | Electrical
47177 |  | Not Committed |  | 2027-01-22 | 2028-03-07 | L36-37 | 100 | 0 |  | 2027-04-20 |  | 2028-03-30
47177 |  | Not Committed |  | 2027-01-22 | 2028-03-07 | L36-37 | 100 | 0 |  | 2027-04-20 |  | 2028-03-30 |  |  |  |  | Finishes | Gypsum Plastering Works
47178 |  | Not Committed |  | 2027-01-22 | 2027-03-01 | MEP 1st Fixes | 100 | 0 |  | 2027-04-20 |  | 2027-05-29
47179 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-01-22 | 2027-01-30 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-04-20 |  | 2027-04-28 |  | Tower B | Super Structure | L36 | MEP | FPS 1st Fix - MEP & Finishes
47180 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-01-22 | 2027-01-28 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2027-04-20 |  | 2027-04-26 |  | Tower B | Super Structure | L36 | MEP | Electrical 1st Fixes
47181 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2027-01-22 | 2027-01-30 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2027-04-20 |  | 2027-04-28 |  | Tower B | Super Structure | L36
47732 |  | Not Ready |  | 2027-01-07 | 2027-01-30 | Slab_NTA | 100 | 0 |  | 2027-04-20 |  | 2027-05-14
47732 |  | Not Ready |  | 2027-01-07 | 2027-01-30 | Slab_NTA | 100 | 0 |  | 2027-04-20 |  | 2027-05-14 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
47733 |  | Not Committed |  | 2027-01-07 | 2027-02-05 | Pour 9 (grid PB-06 to PB-C) | 100 | 0 |  | 2027-04-20 |  | 2027-05-21
47734 |  | Not Ready |  | 2027-01-07 | 2027-01-23 | Columns/ Walls_NTA | 100 | 0 |  | 2027-04-20 |  | 2027-05-08
47734 |  | Not Ready |  | 2027-01-07 | 2027-01-23 | Columns/ Walls_NTA | 100 | 0 |  | 2027-04-20 |  | 2027-05-08 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
47742 |  | Not Ready |  | 2027-01-07 | 2027-01-23 | Slab_NTA (tie-beams) | 100 | 0 |  | 2027-04-20 |  | 2027-05-08
47742 |  | Not Ready |  | 2027-01-07 | 2027-01-23 | Slab_NTA (tie-beams) | 100 | 0 |  | 2027-04-20 |  | 2027-05-08 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
46209 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-02-11 | 2027-02-18 | FAPA Cabling | 100 | 0 |  | 2027-04-21 |  | 2027-04-29 |  | Tower B | Super Structure | L17
47024 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2027-02-12 | 2027-02-19 | Door & Window Frame work | 100 | 0 |  | 2027-04-22 |  | 2027-04-30 |  | Tower B | Super Structure | L27 | Finishes | Door & Window Frame work
47040 |  | Not Committed |  | 2027-02-12 | 2027-04-05 | Finishes after 1st Fix | 100 | 0 |  | 2027-04-22 |  | 2027-06-15
47041 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2027-02-12 | 2027-02-23 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2027-04-22 |  | 2027-05-05 |  | Tower B | Super Structure | L28 | Finishes | Blockwork
47147 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2027-01-25 | 2027-02-05 | Cement Plastering in wet areas | 100 | 0 |  | 2027-04-22 |  | 2027-05-05 |  | Tower B | Super Structure | L34
45376 |  | Not Ready |  | 2027-01-27 | 2027-02-06 | L42-43 | 100 | 0 |  | 2027-04-23 |  | 2027-05-06
45376 |  | Not Ready |  | 2027-01-27 | 2027-02-06 | L42-43 | 100 | 0 |  | 2027-04-23 |  | 2027-05-06 |  |  |  |  | Finishes | Gypsum Plastering Works
45377 | Tower B - Super Structure - Core & Outer Slab L42-43 | Not Ready | RCC Works - Vertical | 2027-01-27 | 2027-02-04 | Outer Columns_TA | 100 | 0 |  | 2027-04-23 |  | 2027-05-04 |  | Tower B | Super Structure | L42 | RCC Sub Structure | RCC Works - Vertical
45561 |  | Not Committed |  | 2027-01-27 | 2027-02-26 | L39-40 | 100 | 0 |  | 2027-04-23 |  | 2027-05-27
45561 |  | Not Committed |  | 2027-01-27 | 2027-02-26 | L39-40 | 100 | 0 |  | 2027-04-23 |  | 2027-05-27 |  |  |  |  | Finishes | Gypsum Plastering Works
45562 | Tower B - Super Structure - Finishes & MEP - L39 to L40 | Not Ready | Partition Wall-Blockwork | 2027-01-27 | 2027-02-12 | De-shuttering & Area clearance | 100 | 0 |  | 2027-04-23 |  | 2027-05-12 |  | Tower B | Super Structure | L39
46725 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2027-02-23 | 2027-02-27 | PHE Final Fixes | 100 | 0 |  | 2027-04-23 |  | 2027-04-29 |  | Tower B | Super Structure | L10
46197 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-02-15 | 2027-03-15 | Flooring & Dado | 100 | 0 |  | 2027-04-24 |  | 2027-05-26 |  | Tower B | Super Structure | L16 | Finishes | Flooring & Dado
46210 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-02-15 | 2027-02-25 | HVAC Ducting | 100 | 0 |  | 2027-04-24 |  | 2027-05-07 |  | Tower B | Super Structure | L17 | MEP | HVAC Ducting
46222 |  | Not Committed |  | 2027-02-15 | 2027-10-14 | L18-19 | 100 | 0 |  | 2027-04-24 |  | 2027-11-16
46222 |  | Not Committed |  | 2027-02-15 | 2027-10-14 | L18-19 | 100 | 0 |  | 2027-04-24 |  | 2027-11-16 |  |  |  |  | Finishes | Gypsum Plastering Works
46223 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-02-15 | 2027-02-25 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-04-24 |  | 2027-05-07 |  | Tower B | Super Structure | L18 | MEP | FPS 1st Fix - MEP & Finishes
46224 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-02-15 | 2027-02-22 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-04-24 |  | 2027-05-04 |  | Tower B | Super Structure | L18 | MEP | Electrical 1st Fixes
46990 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2027-02-15 | 2027-02-27 | False Ceiling | 100 | 0 |  | 2027-04-24 |  | 2027-05-10 |  | Tower B | Super Structure | L25 | Finishes | False Ceiling
45556 | Tower B - Super Structure - Finishes & MEP - L37 to L38 | Not Ready | Partition Wall-Blockwork | 2027-01-29 | 2027-02-03 | Staircase Area | 100 | 0 |  | 2027-04-26 |  | 2027-05-03 |  | Tower B | Super Structure | L37
45782 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-02-16 | 2027-02-20 | Final Painting | 100 | 0 |  | 2027-04-26 |  | 2027-05-03 |  | Tower B | Sub Structure | B3 | Finishes | Final Painting
45782 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-02-16 | 2027-02-20 | Final Painting | 100 | 0 |  | 2027-04-26 |  | 2027-05-03 |  | Tower B | Sub Structure | B3 | Finishes | Final Painting
45782 | Tower B - Sub Structure - Finishes & MEP - B3 to B2 - Lobby/Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-02-16 | 2027-02-20 | Final Painting | 100 | 0 |  | 2027-04-26 |  | 2027-05-03 |  | Tower B | Sub Structure | B3 | Finishes | Final Painting
47735 |  | Not Ready |  | 2027-01-13 | 2027-02-05 | Slab_NTA | 100 | 0 |  | 2027-04-26 |  | 2027-05-21
47735 |  | Not Ready |  | 2027-01-13 | 2027-02-05 | Slab_NTA | 100 | 0 |  | 2027-04-26 |  | 2027-05-21 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
46741 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-03-01 | 2027-03-08 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-04-27 |  | 2027-05-06 |  | Tower B | Super Structure | L11 | MEP | FPS 2nd Fix - MEP & Finishes
46742 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-03-01 | 2027-03-08 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-04-27 |  | 2027-05-06 |  | Tower B | Super Structure | L11 | MEP | Electrical 2nd Fix - MEP & Finishes
46757 |  | Not Committed |  | 2027-03-01 | 2027-04-06 | MEP final fix & Finishes | 100 | 0 |  | 2027-04-27 |  | 2027-06-02
46758 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2027-03-01 | 2027-03-13 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2027-04-27 |  | 2027-05-10 |  | Tower B | Super Structure | L12 | Finishes | Door & Window Fixing
45378 | Tower B - Super Structure - Core & Outer Slab L42-43 | Not Ready | RCC Works - Slab | 2027-02-01 | 2027-02-06 | Outer Slab_TA | 100 | 0 |  | 2027-04-28 |  | 2027-05-06 |  | Tower B | Super Structure | L42 | RCC Sub Structure | RCC Works - Slab
47182 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2027-02-01 | 2027-02-17 | Wet Area Waterproofing | 100 | 0 |  | 2027-04-28 |  | 2027-05-18 |  | Tower B | Super Structure | L36
45559 | Tower B - Super Structure - Finishes & MEP - L38 to L39 | Not Ready | Partition Wall-Blockwork | 2027-02-02 | 2027-02-09 | Partition Walls | 100 | 0 |  | 2027-04-29 |  | 2027-05-08 |  | Tower B | Super Structure | L38
45709 | Tower B - Super Structure - Finishes & MEP - MEP Service Floors | Not Ready |  | 2027-03-15 | 2027-10-18 | Lift Well Pressurization Fans Installations | 100 | 0 |  | 2027-04-29 |  | 2027-12-03 |  | Tower B | Super Structure
46726 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2027-03-01 | 2027-03-08 | Painting Works | 100 | 0 |  | 2027-04-29 |  | 2027-05-08 |  | Tower B | Super Structure | L10 | Finishes | Painting Works
47043 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-02-20 | 2027-03-20 | Flooring & Dado works | 100 | 0 |  | 2027-04-30 |  | 2027-06-01 |  | Tower B | Super Structure | L28 | Finishes | Flooring & Dado
45639 | Tower B - Super Structure - Finishes & MEP - L36 to L37 | Not Ready | Gypsum Plastering Works | 2027-02-04 | 2027-03-04 | L36-37 | 100 | 0 |  | 2027-05-03 |  | 2027-06-02 |  | Tower B | Super Structure | L36 | Finishes | Gypsum Plastering Works
45639 | Tower B - Super Structure - Finishes & MEP - L36 to L37 | Not Ready | Gypsum Plastering Works | 2027-02-04 | 2027-03-04 | L36-37 | 100 | 0 |  | 2027-05-03 |  | 2027-06-02 |  | Tower B | Super Structure | L36
47195 |  | Not Committed |  | 2027-02-04 | 2028-03-22 | L37-38 | 100 | 0 |  | 2027-05-03 |  | 2028-04-13
47195 |  | Not Committed |  | 2027-02-04 | 2028-03-22 | L37-38 | 100 | 0 |  | 2027-05-03 |  | 2028-04-13 |  |  |  |  | Finishes | Gypsum Plastering Works
47196 |  | Not Committed |  | 2027-02-04 | 2027-03-12 | MEP 1st Fixes | 100 | 0 |  | 2027-05-03 |  | 2027-06-10
47197 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-02-04 | 2027-02-11 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-05-03 |  | 2027-05-11 |  | Tower B | Super Structure | L37 | MEP | FPS 1st Fix - MEP & Finishes
47198 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-02-04 | 2027-02-09 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2027-05-03 |  | 2027-05-08 |  | Tower B | Super Structure | L37 | MEP | Electrical 1st Fixes
47199 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2027-02-04 | 2027-02-11 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2027-05-03 |  | 2027-05-11 |  | Tower B | Super Structure | L37
47743 |  | Not Committed |  | 2027-01-19 | 2027-02-23 | Pour 12 (PB-03 to PB-06) | 100 | 0 |  | 2027-05-03 |  | 2027-06-08
47744 |  | Not Ready |  | 2027-01-19 | 2027-02-05 | Columns/ Walls_NTA | 100 | 0 |  | 2027-05-03 |  | 2027-05-21
47744 |  | Not Ready |  | 2027-01-19 | 2027-02-05 | Columns/ Walls_NTA | 100 | 0 |  | 2027-05-03 |  | 2027-05-21 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
47745 |  | Not Ready |  | 2027-01-19 | 2027-02-11 | Staircase_NTA | 100 | 0 |  | 2027-05-03 |  | 2027-05-27
47745 |  | Not Ready |  | 2027-01-19 | 2027-02-11 | Staircase_NTA | 100 | 0 |  | 2027-05-03 |  | 2027-05-27 |  |  |  |  | RCC Sub Structure | Staircase & Ramp RCC Works
47747 |  | Not Committed |  | 2027-01-19 | 2027-03-31 | P2 to P3 | 100 | 0 |  | 2027-05-03 |  | 2027-07-13
47747 |  | Not Committed |  | 2027-01-19 | 2027-03-31 | P2 to P3 | 100 | 0 |  | 2027-05-03 |  | 2027-07-13
47747 |  | Not Committed |  | 2027-01-19 | 2027-03-31 | P2 to P3 | 100 | 0 |  | 2027-05-03 |  | 2027-07-13
47755 |  | Not Committed |  | 2027-01-19 | 2027-02-23 | Pour 10 (PA-A to PB-J) | 100 | 0 |  | 2027-05-03 |  | 2027-06-08
47756 |  | Not Ready |  | 2027-01-19 | 2027-02-05 | Columns/ Walls_NTA | 100 | 0 |  | 2027-05-03 |  | 2027-05-21
47756 |  | Not Ready |  | 2027-01-19 | 2027-02-05 | Columns/ Walls_NTA | 100 | 0 |  | 2027-05-03 |  | 2027-05-21 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
47757 |  | Not Ready |  | 2027-01-19 | 2027-02-17 | Ramp_NTA | 100 | 0 |  | 2027-05-03 |  | 2027-06-02
47808 |  | Not Ready |  | 2027-01-19 | 2027-03-06 | GF to P1 | 100 | 0 |  | 2027-05-03 |  | 2027-06-19
47808 |  | Not Ready |  | 2027-01-19 | 2027-03-06 | GF to P1 | 100 | 0 |  | 2027-05-03 |  | 2027-06-19
47808 |  | Not Ready |  | 2027-01-19 | 2027-03-06 | GF to P1 | 100 | 0 |  | 2027-05-03 |  | 2027-06-19
46225 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-02-23 | 2027-03-02 | FAPA Cabling | 100 | 0 |  | 2027-05-04 |  | 2027-05-12 |  | Tower B | Super Structure | L18
47042 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2027-02-24 | 2027-03-03 | Door & Window Frame work | 100 | 0 |  | 2027-05-05 |  | 2027-05-13 |  | Tower B | Super Structure | L28 | Finishes | Door & Window Frame work
47058 |  | Not Committed |  | 2027-02-24 | 2027-04-28 | Finishes after 1st Fix | 100 | 0 |  | 2027-05-05 |  | 2027-07-08
47059 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2027-02-24 | 2027-03-06 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2027-05-05 |  | 2027-05-18 |  | Tower B | Super Structure | L29 | Finishes | Blockwork
47165 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2027-02-06 | 2027-02-17 | Cement Plastering in wet areas | 100 | 0 |  | 2027-05-05 |  | 2027-05-18 |  | Tower B | Super Structure | L35
45379 |  | Not Ready |  | 2027-02-08 | 2027-02-18 | L43-44 | 100 | 0 |  | 2027-05-06 |  | 2027-05-19
45379 |  | Not Ready |  | 2027-02-08 | 2027-02-18 | L43-44 | 100 | 0 |  | 2027-05-06 |  | 2027-05-19 |  |  |  |  | Finishes | Gypsum Plastering Works
45380 | Tower B - Super Structure - Core & Outer Slab L43-44 | Not Ready | RCC Works - Vertical | 2027-02-08 | 2027-02-16 | Outer Columns_TA | 100 | 0 |  | 2027-05-06 |  | 2027-05-15 |  | Tower B | Super Structure | L43 | RCC Sub Structure | RCC Works - Vertical
45565 |  | Not Committed |  | 2027-02-08 | 2027-03-10 | L40-41 | 100 | 0 |  | 2027-05-06 |  | 2027-06-08
45565 |  | Not Committed |  | 2027-02-08 | 2027-03-10 | L40-41 | 100 | 0 |  | 2027-05-06 |  | 2027-06-08 |  |  |  |  | Finishes | Gypsum Plastering Works
45566 | Tower B - Super Structure - Finishes & MEP - L40 to L41 | Not Ready | Partition Wall-Blockwork | 2027-02-08 | 2027-02-24 | De-shuttering & Area clearance | 100 | 0 |  | 2027-05-06 |  | 2027-05-25 |  | Tower B | Super Structure | L40
45597 | Tower B - Super Structure - Finishes & MEP | Not Ready | MEP Shaft Masonry | 2027-02-08 | 2027-03-08 | L25-L35 | 100 | 0 |  | 2027-05-06 |  | 2027-06-05 |  | Tower B | Super Structure
46743 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2027-03-09 | 2027-03-13 | PHE Final Fixes | 100 | 0 |  | 2027-05-06 |  | 2027-05-12 |  | Tower B | Super Structure | L11
46182 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-02-26 | 2027-03-11 | False Ceiling | 100 | 0 |  | 2027-05-07 |  | 2027-05-22 |  | Tower B | Super Structure | L15 | Finishes | False Ceiling
46213 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-02-26 | 2027-03-27 | Flooring & Dado | 100 | 0 |  | 2027-05-07 |  | 2027-06-07 |  | Tower B | Super Structure | L17 | Finishes | Flooring & Dado
46226 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-02-26 | 2027-03-09 | HVAC Ducting | 100 | 0 |  | 2027-05-07 |  | 2027-05-20 |  | Tower B | Super Structure | L18 | MEP | HVAC Ducting
46238 |  | Not Committed |  | 2027-02-26 | 2027-10-20 | L19-20 | 100 | 0 |  | 2027-05-07 |  | 2027-11-22
46238 |  | Not Committed |  | 2027-02-26 | 2027-10-20 | L19-20 | 100 | 0 |  | 2027-05-07 |  | 2027-11-22 |  |  |  |  | Finishes | Gypsum Plastering Works
46239 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-02-26 | 2027-03-09 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-05-07 |  | 2027-05-20 |  | Tower B | Super Structure | L19 | MEP | FPS 1st Fix - MEP & Finishes
46240 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-02-26 | 2027-03-05 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-05-07 |  | 2027-05-15 |  | Tower B | Super Structure | L19 | MEP | Electrical 1st Fixes
47008 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2027-02-26 | 2027-03-11 | False Ceiling | 100 | 0 |  | 2027-05-07 |  | 2027-05-22 |  | Tower B | Super Structure | L26 | Finishes | False Ceiling
47825 |  | Not Ready |  | 2026-10-29 | 2026-11-20 | MEP Rooms - Plaster & IPS | 100 | 0 |  | 2027-05-07 |  | 2027-06-01
47825 |  | Not Ready |  | 2026-10-29 | 2026-11-20 | MEP Rooms - Plaster & IPS | 100 | 0 |  | 2027-05-07 |  | 2027-06-01
47826 |  | Not Ready |  | 2026-10-29 | 2026-12-02 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2027-05-07 |  | 2027-06-12
47826 |  | Not Ready |  | 2026-10-29 | 2026-12-02 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2027-05-07 |  | 2027-06-12
45560 | Tower B - Super Structure - Finishes & MEP - L38 to L39 | Not Ready | Partition Wall-Blockwork | 2027-02-10 | 2027-02-15 | Staircase Area | 100 | 0 |  | 2027-05-08 |  | 2027-05-14 |  | Tower B | Super Structure | L38
46759 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-03-15 | 2027-03-23 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-05-10 |  | 2027-05-19 |  | Tower B | Super Structure | L12 | MEP | FPS 2nd Fix - MEP & Finishes
46760 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-03-15 | 2027-03-23 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-05-10 |  | 2027-05-19 |  | Tower B | Super Structure | L12 | MEP | Electrical 2nd Fix - MEP & Finishes
46775 |  | Not Committed |  | 2027-03-15 | 2027-04-20 | MEP final fix & Finishes | 100 | 0 |  | 2027-05-10 |  | 2027-06-14
46776 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2027-03-15 | 2027-03-29 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2027-05-10 |  | 2027-05-22 |  | Tower B | Super Structure | L13 | Finishes | Door & Window Fixing
45381 | Tower B - Super Structure - Core & Outer Slab L43-44 | Not Ready | RCC Works - Slab | 2027-02-12 | 2027-02-18 | Outer Slab_TA | 100 | 0 |  | 2027-05-11 |  | 2027-05-19 |  | Tower B | Super Structure | L43 | RCC Sub Structure | RCC Works - Slab
47200 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2027-02-12 | 2027-03-01 | Wet Area Waterproofing | 100 | 0 |  | 2027-05-11 |  | 2027-05-29 |  | Tower B | Super Structure | L37
45563 | Tower B - Super Structure - Finishes & MEP - L39 to L40 | Not Ready | Partition Wall-Blockwork | 2027-02-13 | 2027-02-20 | Partition Walls | 100 | 0 |  | 2027-05-12 |  | 2027-05-21 |  | Tower B | Super Structure | L39
46744 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2027-03-15 | 2027-03-23 | Painting Works | 100 | 0 |  | 2027-05-12 |  | 2027-05-21 |  | Tower B | Super Structure | L11 | Finishes | Painting Works
45640 | Tower B - Super Structure - Finishes & MEP - L37 to L38 | Not Ready | Gypsum Plastering Works | 2027-02-16 | 2027-03-16 | L37-38 | 100 | 0 |  | 2027-05-14 |  | 2027-06-14 |  | Tower B | Super Structure | L37 | Finishes | Gypsum Plastering Works
45640 | Tower B - Super Structure - Finishes & MEP - L37 to L38 | Not Ready | Gypsum Plastering Works | 2027-02-16 | 2027-03-16 | L37-38 | 100 | 0 |  | 2027-05-14 |  | 2027-06-14 |  | Tower B | Super Structure | L37
47213 |  | Not Committed |  | 2027-02-16 | 2028-04-05 | L38-39 | 100 | 0 |  | 2027-05-14 |  | 2028-04-27
47213 |  | Not Committed |  | 2027-02-16 | 2028-04-05 | L38-39 | 100 | 0 |  | 2027-05-14 |  | 2028-04-27 |  |  |  |  | Finishes | Gypsum Plastering Works
47214 |  | Not Committed |  | 2027-02-16 | 2027-03-25 | MEP 1st Fixes | 100 | 0 |  | 2027-05-14 |  | 2027-06-22
47215 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-02-16 | 2027-02-23 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-05-14 |  | 2027-05-24 |  | Tower B | Super Structure | L38 | MEP | FPS 1st Fix - MEP & Finishes
47216 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-02-16 | 2027-02-20 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2027-05-14 |  | 2027-05-21 |  | Tower B | Super Structure | L38 | MEP | Electrical 1st Fixes
47217 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2027-02-16 | 2027-02-23 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2027-05-14 |  | 2027-05-24 |  | Tower B | Super Structure | L38
47748 |  | Not Committed |  | 2027-02-01 | 2027-03-12 | Pour 8 (grid PB-B to PB-J) | 100 | 0 |  | 2027-05-14 |  | 2027-06-25
47749 |  | Not Ready |  | 2027-02-01 | 2027-02-17 | Columns/ Walls_NTA | 100 | 0 |  | 2027-05-14 |  | 2027-06-02
47749 |  | Not Ready |  | 2027-02-01 | 2027-02-17 | Columns/ Walls_NTA | 100 | 0 |  | 2027-05-14 |  | 2027-06-02 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
47750 |  | Not Ready |  | 2027-02-01 | 2027-02-23 | Staircase_NTA | 100 | 0 |  | 2027-05-14 |  | 2027-06-08
47750 |  | Not Ready |  | 2027-02-01 | 2027-02-23 | Staircase_NTA | 100 | 0 |  | 2027-05-14 |  | 2027-06-08 |  |  |  |  | RCC Sub Structure | Staircase & Ramp RCC Works
46241 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-03-06 | 2027-03-13 | FAPA Cabling | 100 | 0 |  | 2027-05-15 |  | 2027-05-25 |  | Tower B | Super Structure | L19
47060 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2027-03-08 | 2027-03-15 | Door & Window Frame work | 100 | 0 |  | 2027-05-18 |  | 2027-05-26 |  | Tower B | Super Structure | L29 | Finishes | Door & Window Frame work
47076 |  | Not Committed |  | 2027-03-08 | 2027-04-28 | Finishes after 1st Fix | 100 | 0 |  | 2027-05-18 |  | 2027-07-08
47077 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2027-03-08 | 2027-03-18 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2027-05-18 |  | 2027-05-29 |  | Tower B | Super Structure | L30 | Finishes | Blockwork
47183 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2027-02-18 | 2027-03-01 | Cement Plastering in wet areas | 100 | 0 |  | 2027-05-18 |  | 2027-05-29 |  | Tower B | Super Structure | L36
47444 | Tower B - Super Structure - Finishes & MEP - L33 to L38 | Not Ready | Façade Works - MEP & Finishes | 2027-03-08 | 2027-03-25 | DGU Assembly Installation | 100 | 0 |  | 2027-05-18 |  | 2027-06-04 |  | Tower B | Super Structure | L33 | Façade | Façade Works
47445 | Tower B - Super Structure - Finishes & MEP - L33 to L38 | Not Ready | Façade Works - MEP & Finishes | 2027-03-08 | 2027-04-12 | Installation of highly reflective metal sheet | 100 | 0 |  | 2027-05-18 |  | 2027-06-22 |  | Tower B | Super Structure | L33 | Façade | Façade Works
47446 | Tower B - Super Structure - Finishes & MEP - L33 to L38 | Not Ready | Façade Works - MEP & Finishes | 2027-03-08 | 2027-03-25 | Fixing of Backlit Laminated Glass assembly & ACP Panels | 100 | 0 |  | 2027-05-18 |  | 2027-06-04 |  | Tower B | Super Structure | L33 | Façade | Façade Works
47447 | Tower B - Super Structure - Finishes & MEP - L33 to L38 | Not Ready | Façade Works - MEP & Finishes | 2027-03-08 | 2027-03-25 | Fixing of Louvers | 100 | 0 |  | 2027-05-18 |  | 2027-06-04 |  | Tower B | Super Structure | L33 | Façade | Façade Works
47447 | Tower B - Super Structure - Finishes & MEP - L33 to L38 | Not Ready | Façade Works - MEP & Finishes | 2027-03-08 | 2027-03-25 | Fixing of Louvers | 100 | 0 |  | 2027-05-18 |  | 2027-06-04 |  | Tower B | Super Structure | L33
45382 |  | Not Ready |  | 2027-02-19 | 2027-03-02 | L44-45 | 100 | 0 |  | 2027-05-19 |  | 2027-05-31
45382 |  | Not Ready |  | 2027-02-19 | 2027-03-02 | L44-45 | 100 | 0 |  | 2027-05-19 |  | 2027-05-31 |  |  |  |  | Finishes | Gypsum Plastering Works
45383 | Tower B - Super Structure - Core & Outer Slab L44-45 | Not Ready | RCC Works - Vertical | 2027-02-19 | 2027-02-27 | Outer Columns_TA | 100 | 0 |  | 2027-05-19 |  | 2027-05-28 |  | Tower B | Super Structure | L44 | RCC Sub Structure | RCC Works - Vertical
45569 |  | Not Committed |  | 2027-02-19 | 2027-03-23 | L41-42 | 100 | 0 |  | 2027-05-19 |  | 2027-06-19
45569 |  | Not Committed |  | 2027-02-19 | 2027-03-23 | L41-42 | 100 | 0 |  | 2027-05-19 |  | 2027-06-19 |  |  |  |  | Finishes | Gypsum Plastering Works
45570 | Tower B - Super Structure - Finishes & MEP - L41 to L42 | Not Ready | Partition Wall-Blockwork | 2027-02-19 | 2027-03-08 | De-shuttering & Area clearance | 100 | 0 |  | 2027-05-19 |  | 2027-06-05 |  | Tower B | Super Structure | L41
45681 | Tower B - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2027-04-08 | 2027-06-01 | FPS & PHE Pumps foundation & handover to MEP | 100 | 0 |  | 2027-05-19 |  | 2027-07-10 |  | Tower B | Super Structure
46761 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2027-03-24 | 2027-03-29 | PHE Final Fixes | 100 | 0 |  | 2027-05-19 |  | 2027-05-25 |  | Tower B | Super Structure | L12
46198 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-03-10 | 2027-03-24 | False Ceiling | 100 | 0 |  | 2027-05-20 |  | 2027-06-03 |  | Tower B | Super Structure | L16 | Finishes | False Ceiling
46229 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-03-10 | 2027-04-08 | Flooring & Dado | 100 | 0 |  | 2027-05-20 |  | 2027-06-18 |  | Tower B | Super Structure | L18 | Finishes | Flooring & Dado
46242 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-03-10 | 2027-03-20 | HVAC Ducting | 100 | 0 |  | 2027-05-20 |  | 2027-06-01 |  | Tower B | Super Structure | L19 | MEP | HVAC Ducting
46254 |  | Not Committed |  | 2027-03-10 | 2027-10-26 | L20-21 | 100 | 0 |  | 2027-05-20 |  | 2027-11-27
46254 |  | Not Committed |  | 2027-03-10 | 2027-10-26 | L20-21 | 100 | 0 |  | 2027-05-20 |  | 2027-11-27 |  |  |  |  | Finishes | Gypsum Plastering Works
46255 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-03-10 | 2027-03-20 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-05-20 |  | 2027-06-01 |  | Tower B | Super Structure | L20 | MEP | FPS 1st Fix - MEP & Finishes
46256 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-03-10 | 2027-03-17 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-05-20 |  | 2027-05-28 |  | Tower B | Super Structure | L20 | MEP | Electrical 1st Fixes
47026 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2027-03-10 | 2027-03-24 | False Ceiling | 100 | 0 |  | 2027-05-20 |  | 2027-06-03 |  | Tower B | Super Structure | L27 | Finishes | False Ceiling
45564 | Tower B - Super Structure - Finishes & MEP - L39 to L40 | Not Ready | Partition Wall-Blockwork | 2027-02-22 | 2027-02-26 | Staircase Area | 100 | 0 |  | 2027-05-21 |  | 2027-05-27 |  | Tower B | Super Structure | L39
47746 |  | Not Ready |  | 2027-02-06 | 2027-02-23 | Slab_NTA | 100 | 0 |  | 2027-05-21 |  | 2027-06-08
47746 |  | Not Ready |  | 2027-02-06 | 2027-02-23 | Slab_NTA | 100 | 0 |  | 2027-05-21 |  | 2027-06-08 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
47758 |  | Not Ready |  | 2027-02-06 | 2027-02-23 | Slab_NTA | 100 | 0 |  | 2027-05-21 |  | 2027-06-08
47758 |  | Not Ready |  | 2027-02-06 | 2027-02-23 | Slab_NTA | 100 | 0 |  | 2027-05-21 |  | 2027-06-08 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
47759 |  | Not Committed |  | 2027-02-06 | 2027-03-01 | Pour 11 (PB-C to PB-K) | 100 | 0 |  | 2027-05-21 |  | 2027-06-14
47760 |  | Not Ready |  | 2027-02-06 | 2027-02-23 | Columns/ Walls_NTA | 100 | 0 |  | 2027-05-21 |  | 2027-06-08
47760 |  | Not Ready |  | 2027-02-06 | 2027-02-23 | Columns/ Walls_NTA | 100 | 0 |  | 2027-05-21 |  | 2027-06-08 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
44275 |  | Not Ready |  | 2026-11-11 | 2026-11-11 | Fire NOC Readiness | 100 | 0 |  | 2027-05-22 |  | 2027-05-24
46183 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-03-12 | 2027-03-19 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-05-22 |  | 2027-05-31 |  | Tower B | Super Structure | L15 | MEP | FPS 2nd Fix - MEP & Finishes
46184 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-03-12 | 2027-03-19 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-05-22 |  | 2027-05-31 |  | Tower B | Super Structure | L15 | MEP | Electrical 2nd Fix - MEP & Finishes
46185 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-03-12 | 2027-03-24 | FAPA Device Fixing | 100 | 0 |  | 2027-05-22 |  | 2027-06-03 |  | Tower B | Super Structure | L15
46185 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-03-12 | 2027-03-24 | FAPA Device Fixing | 100 | 0 |  | 2027-05-22 |  | 2027-06-03 |  | Tower B | Super Structure | L15
46185 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-03-12 | 2027-03-24 | FAPA Device Fixing | 100 | 0 |  | 2027-05-22 |  | 2027-06-03 |  | Tower B | Super Structure | L15
46185 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-03-12 | 2027-03-24 | FAPA Device Fixing | 100 | 0 |  | 2027-05-22 |  | 2027-06-03 |  | Tower B | Super Structure | L15
46186 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-03-12 | 2027-03-19 | HVAC Grill Fixing | 100 | 0 |  | 2027-05-22 |  | 2027-05-31 |  | Tower B | Super Structure | L15 | MEP | HVAC Grill Fixing
46777 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-03-30 | 2027-04-06 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-05-22 |  | 2027-05-31 |  | Tower B | Super Structure | L13 | MEP | FPS 2nd Fix - MEP & Finishes
46778 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-03-30 | 2027-04-06 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-05-22 |  | 2027-05-31 |  | Tower B | Super Structure | L13 | MEP | Electrical 2nd Fix - MEP & Finishes
46793 |  | Not Committed |  | 2027-03-30 | 2027-05-05 | MEP final fix & Finishes | 100 | 0 |  | 2027-05-22 |  | 2027-06-25
46794 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2027-03-30 | 2027-04-12 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2027-05-22 |  | 2027-06-03 |  | Tower B | Super Structure | L14 | Finishes | Door & Window Fixing
39124 |  | Not Committed |  | 2026-11-12 |  | TA_Fire NOC Readiness | 100 | 0 |  | 2027-05-24
44279 |  | Not Ready |  | 2026-11-12 | 2026-11-27 | OC Readiness | 100 | 0 |  | 2027-05-24 |  | 2027-06-10
45384 | Tower B - Super Structure - Core & Outer Slab L44-45 | Not Ready | RCC Works - Slab | 2027-02-24 | 2027-03-02 | Outer Slab_TB | 100 | 0 |  | 2027-05-24 |  | 2027-05-31 |  | Tower B | Super Structure | L44 | RCC Sub Structure | RCC Works - Slab
47218 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2027-02-24 | 2027-03-12 | Wet Area Waterproofing | 100 | 0 |  | 2027-05-24 |  | 2027-06-10 |  | Tower B | Super Structure | L38
45567 | Tower B - Super Structure - Finishes & MEP - L40 to L41 | Not Ready | Partition Wall-Blockwork | 2027-02-25 | 2027-03-04 | Partition Walls | 100 | 0 |  | 2027-05-25 |  | 2027-06-02 |  | Tower B | Super Structure | L40
46762 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2027-03-30 | 2027-04-06 | Painting Works | 100 | 0 |  | 2027-05-25 |  | 2027-06-02 |  | Tower B | Super Structure | L12 | Finishes | Painting Works
47061 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-03-16 | 2027-04-14 | Flooring & Dado works | 100 | 0 |  | 2027-05-26 |  | 2027-06-24 |  | Tower B | Super Structure | L29 | Finishes | Flooring & Dado
47079 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-03-16 | 2027-04-14 | Flooring & Dado works | 100 | 0 |  | 2027-05-26 |  | 2027-06-24 |  | Tower B | Super Structure | L30 | Finishes | Flooring & Dado
45641 | Tower B - Super Structure - Finishes & MEP - L38 to L39 | Not Ready | Gypsum Plastering Works | 2027-02-27 | 2027-03-29 | L38-39 | 100 | 0 |  | 2027-05-27 |  | 2027-06-25 |  | Tower B | Super Structure | L38 | Finishes | Gypsum Plastering Works
45641 | Tower B - Super Structure - Finishes & MEP - L38 to L39 | Not Ready | Gypsum Plastering Works | 2027-02-27 | 2027-03-29 | L38-39 | 100 | 0 |  | 2027-05-27 |  | 2027-06-25 |  | Tower B | Super Structure | L38
47231 |  | Not Committed |  | 2027-02-27 | 2028-04-15 | L39-40 | 100 | 0 |  | 2027-05-27 |  | 2028-05-09
47231 |  | Not Committed |  | 2027-02-27 | 2028-04-15 | L39-40 | 100 | 0 |  | 2027-05-27 |  | 2028-05-09 |  |  |  |  | Finishes | Gypsum Plastering Works
47232 |  | Not Committed |  | 2027-02-27 | 2027-04-06 | MEP 1st Fixes | 100 | 0 |  | 2027-05-27 |  | 2027-07-03
47233 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-02-27 | 2027-03-06 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-05-27 |  | 2027-06-04 |  | Tower B | Super Structure | L39 | MEP | FPS 1st Fix - MEP & Finishes
47234 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-02-27 | 2027-03-04 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2027-05-27 |  | 2027-06-02 |  | Tower B | Super Structure | L39 | MEP | Electrical 1st Fixes
47235 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2027-02-27 | 2027-03-06 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2027-05-27 |  | 2027-06-04 |  | Tower B | Super Structure | L39
47761 |  | Not Ready |  | 2027-02-12 | 2027-03-01 | Slab_NTA (tie-beams) | 100 | 0 |  | 2027-05-27 |  | 2027-06-14
47761 |  | Not Ready |  | 2027-02-12 | 2027-03-01 | Slab_NTA (tie-beams) | 100 | 0 |  | 2027-05-27 |  | 2027-06-14 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
46257 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-03-18 | 2027-03-26 | FAPA Cabling | 100 | 0 |  | 2027-05-28 |  | 2027-06-05 |  | Tower B | Super Structure | L20
47078 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2027-03-19 | 2027-03-27 | Door & Window Frame work | 100 | 0 |  | 2027-05-29 |  | 2027-06-07 |  | Tower B | Super Structure | L30 | Finishes | Door & Window Frame work
47094 |  | Not Committed |  | 2027-03-19 | 2027-05-11 | Finishes after 1st Fix | 100 | 0 |  | 2027-05-29 |  | 2027-07-20
47095 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2027-03-19 | 2027-03-31 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2027-05-29 |  | 2027-06-10 |  | Tower B | Super Structure | L31 | Finishes | Blockwork
47201 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2027-03-02 | 2027-03-12 | Cement Plastering in wet areas | 100 | 0 |  | 2027-05-29 |  | 2027-06-10 |  | Tower B | Super Structure | L37
39128 |  | Not Committed |  | 2027-03-03 |  | TB_Completion of Top Slab | 100 | 0 |  | 2027-05-31
45385 |  | Not Ready |  | 2027-02-27 | 2027-05-28 | Above Terrace Structure | 100 | 0 |  | 2027-05-31 |  | 2027-06-29
45386 | Tower B - Super Structure - Core & Outer Slab Above Terrace | Not Ready | RCC Works - Vertical | 2027-02-27 | 2027-05-28 | Lift Machine Room | 100 | 0 |  | 2027-05-31 |  | 2027-06-29 |  | Tower B | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
45387 | Tower B - Super Structure - Core & Outer Slab Above Terrace | Not Ready | RCC Works - Vertical | 2027-03-03 | 2027-05-20 | Over Head Tanks | 100 | 0 |  | 2027-05-31 |  | 2027-06-29 |  | Tower B | Super Structure |  | RCC Sub Structure | RCC Works - Slab
45387 | Tower B - Super Structure - Core & Outer Slab Above Terrace | Not Ready | RCC Works - Vertical | 2027-03-03 | 2027-05-20 | Over Head Tanks | 100 | 0 |  | 2027-05-31 |  | 2027-06-29 |  | Tower B | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
45388 | Tower B - Super Structure - Core & Outer Slab Above Terrace | Not Ready | RCC Works - Slab | 2027-02-27 | 2027-05-15 | Mumty Slab | 100 | 0 |  | 2027-05-31 |  | 2027-06-29 |  | Tower B | Super Structure |  | RCC Sub Structure | RCC Works - Slab
45389 | Tower B - Super Structure - Core & Outer Slab Above Terrace | Not Ready | RCC Works - Vertical | 2027-03-03 | 2027-05-13 | Miscellaneous - Parapet, Architectural, MEP Utility | 100 | 0 |  | 2027-05-31 |  | 2027-06-29 |  | Tower B | Super Structure |  | RCC Sub Structure | RCC Works - Vertical
45573 |  | Not Committed |  | 2027-03-03 | 2027-04-03 | L42-43 | 100 | 0 |  | 2027-05-31 |  | 2027-07-01
45573 |  | Not Committed |  | 2027-03-03 | 2027-04-03 | L42-43 | 100 | 0 |  | 2027-05-31 |  | 2027-07-01 |  |  |  |  | Finishes | Gypsum Plastering Works
45574 | Tower B - Super Structure - Finishes & MEP - L42 to L43 | Not Ready | Partition Wall-Blockwork | 2027-03-03 | 2027-03-19 | De-shuttering & Area clearance | 100 | 0 |  | 2027-05-31 |  | 2027-06-17 |  | Tower B | Super Structure | L42
45758 |  | Not Committed |  | 2027-03-03 | 2027-06-07 | L35-Terrace | 100 | 0 |  | 2027-05-31 |  | 2027-09-01
45758 |  | Not Committed |  | 2027-03-03 | 2027-06-07 | L35-Terrace | 100 | 0 |  | 2027-05-31 |  | 2027-09-01
45759 | Tower B - Super Structure - Finishes & MEP - L35 to Terrace | Not Ready |  | 2027-03-03 | 2027-03-26 | FHR Shaft Risers | 100 | 0 |  | 2027-05-31 |  | 2027-06-23 |  | Tower B | Super Structure | L35
45761 | Tower B - Super Structure - Finishes & MEP - L35 to Terrace | Not Ready |  | 2027-03-03 | 2027-04-24 | Domestic Water & Flushing Riser in Plumbing Shaft | 100 | 0 |  | 2027-05-31 |  | 2027-07-22 |  | Tower B | Super Structure | L35
45763 | Tower B - Super Structure - Finishes & MEP - L35 to Terrace | Not Ready |  | 2027-03-03 | 2027-04-07 | Shaft Cable Tray in Electrical Shaft | 100 | 0 |  | 2027-05-31 |  | 2027-07-05 |  | Tower B | Super Structure | L35
46187 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-03-20 | 2027-03-29 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-05-31 |  | 2027-06-08 |  | Tower B | Super Structure | L15
46779 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2027-04-07 | 2027-04-12 | PHE Final Fixes | 100 | 0 |  | 2027-05-31 |  | 2027-06-05 |  | Tower B | Super Structure | L13
46214 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-03-23 | 2027-04-05 | False Ceiling | 100 | 0 |  | 2027-06-01 |  | 2027-06-15 |  | Tower B | Super Structure | L17 | Finishes | False Ceiling
46245 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-03-23 | 2027-04-20 | Flooring & Dado | 100 | 0 |  | 2027-06-01 |  | 2027-06-30 |  | Tower B | Super Structure | L19 | Finishes | Flooring & Dado
46258 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-03-23 | 2027-04-02 | HVAC Ducting | 100 | 0 |  | 2027-06-01 |  | 2027-06-12 |  | Tower B | Super Structure | L20 | MEP | HVAC Ducting
46270 |  | Not Committed |  | 2027-03-23 | 2027-11-02 | L21-22 | 100 | 0 |  | 2027-06-01 |  | 2027-12-03
46270 |  | Not Committed |  | 2027-03-23 | 2027-11-02 | L21-22 | 100 | 0 |  | 2027-06-01 |  | 2027-12-03 |  |  |  |  | Finishes | Gypsum Plastering Works
46271 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-03-23 | 2027-04-02 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-06-01 |  | 2027-06-12 |  | Tower B | Super Structure | L21 | MEP | FPS 1st Fix - MEP & Finishes
46272 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-03-23 | 2027-03-30 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-06-01 |  | 2027-06-09 |  | Tower B | Super Structure | L21 | MEP | Electrical 1st Fixes
47044 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2027-03-23 | 2027-04-05 | False Ceiling | 100 | 0 |  | 2027-06-01 |  | 2027-06-15 |  | Tower B | Super Structure | L28 | Finishes | False Ceiling
45568 | Tower B - Super Structure - Finishes & MEP - L40 to L41 | Not Ready | Partition Wall-Blockwork | 2027-03-05 | 2027-03-10 | Staircase Area | 100 | 0 |  | 2027-06-02 |  | 2027-06-08 |  | Tower B | Super Structure | L40
47751 |  | Not Ready |  | 2027-02-18 | 2027-03-12 | Slab_NTA | 100 | 0 |  | 2027-06-02 |  | 2027-06-25
47751 |  | Not Ready |  | 2027-02-18 | 2027-03-12 | Slab_NTA | 100 | 0 |  | 2027-06-02 |  | 2027-06-25 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
47752 |  | Not Committed |  | 2027-02-18 | 2027-03-18 | Pour 9 (grid PB-06 to PB-C) | 100 | 0 |  | 2027-06-02 |  | 2027-07-01
47753 |  | Not Ready |  | 2027-02-18 | 2027-03-06 | Columns/ Walls_NTA | 100 | 0 |  | 2027-06-02 |  | 2027-06-19
47753 |  | Not Ready |  | 2027-02-18 | 2027-03-06 | Columns/ Walls_NTA | 100 | 0 |  | 2027-06-02 |  | 2027-06-19 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
46199 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-03-25 | 2027-04-01 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-06-03 |  | 2027-06-11 |  | Tower B | Super Structure | L16 | MEP | FPS 2nd Fix - MEP & Finishes
46200 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-03-25 | 2027-04-01 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-06-03 |  | 2027-06-11 |  | Tower B | Super Structure | L16 | MEP | Electrical 2nd Fix - MEP & Finishes
46201 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-03-25 | 2027-04-05 | FAPA Device Fixing | 100 | 0 |  | 2027-06-03 |  | 2027-06-15 |  | Tower B | Super Structure | L16
46201 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-03-25 | 2027-04-05 | FAPA Device Fixing | 100 | 0 |  | 2027-06-03 |  | 2027-06-15 |  | Tower B | Super Structure | L16
46201 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-03-25 | 2027-04-05 | FAPA Device Fixing | 100 | 0 |  | 2027-06-03 |  | 2027-06-15 |  | Tower B | Super Structure | L16
46201 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-03-25 | 2027-04-05 | FAPA Device Fixing | 100 | 0 |  | 2027-06-03 |  | 2027-06-15 |  | Tower B | Super Structure | L16
46202 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-03-25 | 2027-04-01 | HVAC Grill Fixing | 100 | 0 |  | 2027-06-03 |  | 2027-06-11 |  | Tower B | Super Structure | L16 | MEP | HVAC Grill Fixing
46795 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-04-13 | 2027-04-20 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-06-03 |  | 2027-06-11 |  | Tower B | Super Structure | L14 | MEP | FPS 2nd Fix - MEP & Finishes
46796 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-04-13 | 2027-04-20 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-06-03 |  | 2027-06-11 |  | Tower B | Super Structure | L14 | MEP | Electrical 2nd Fix - MEP & Finishes
46811 |  | Not Committed |  | 2027-04-13 | 2027-05-20 | MEP final fix & Finishes | 100 | 0 |  | 2027-06-03 |  | 2027-07-07
46812 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2027-04-13 | 2027-04-26 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2027-06-03 |  | 2027-06-15 |  | Tower B | Super Structure | L15 | Finishes | Door & Window Fixing
47236 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2027-03-08 | 2027-03-25 | Wet Area Waterproofing | 100 | 0 |  | 2027-06-04 |  | 2027-06-22 |  | Tower B | Super Structure | L39
47448 | Tower B - Super Structure - Finishes & MEP - L33 to L38 | Not Ready | Façade Works - MEP & Finishes | 2027-03-26 | 2027-04-12 | Accessories & Alignment | 100 | 0 |  | 2027-06-04 |  | 2027-06-22 |  | Tower B | Super Structure | L33 | Façade | Façade Works
47448 | Tower B - Super Structure - Finishes & MEP - L33 to L38 | Not Ready | Façade Works - MEP & Finishes | 2027-03-26 | 2027-04-12 | Accessories & Alignment | 100 | 0 |  | 2027-06-04 |  | 2027-06-22 |  | Tower B | Super Structure | L33
45571 | Tower B - Super Structure - Finishes & MEP - L41 to L42 | Not Ready | Partition Wall-Blockwork | 2027-03-09 | 2027-03-16 | Partition Walls | 100 | 0 |  | 2027-06-05 |  | 2027-06-14 |  | Tower B | Super Structure | L41
46780 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2027-04-13 | 2027-04-20 | Painting Works | 100 | 0 |  | 2027-06-05 |  | 2027-06-14 |  | Tower B | Super Structure | L13 | Finishes | Painting Works
47097 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-03-29 | 2027-04-26 | Flooring & Dado works | 100 | 0 |  | 2027-06-07 |  | 2027-07-06 |  | Tower B | Super Structure | L31 | Finishes | Flooring & Dado
45642 | Tower B - Super Structure - Finishes & MEP - L39 to L40 | Not Ready | Gypsum Plastering Works | 2027-03-11 | 2027-04-09 | L39-40 | 100 | 0 |  | 2027-06-08 |  | 2027-07-07 |  | Tower B | Super Structure | L39 | Finishes | Gypsum Plastering Works
45642 | Tower B - Super Structure - Finishes & MEP - L39 to L40 | Not Ready | Gypsum Plastering Works | 2027-03-11 | 2027-04-09 | L39-40 | 100 | 0 |  | 2027-06-08 |  | 2027-07-07 |  | Tower B | Super Structure | L39
46188 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-03-30 | 2027-04-06 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-06-08 |  | 2027-06-16 |  | Tower B | Super Structure | L15 | MEP | Electrical
47249 |  | Not Committed |  | 2027-03-11 | 2028-05-12 | L40-41 | 100 | 0 |  | 2027-06-08 |  | 2028-06-05
47249 |  | Not Committed |  | 2027-03-11 | 2028-05-12 | L40-41 | 100 | 0 |  | 2027-06-08 |  | 2028-06-05 |  |  |  |  | Finishes | Gypsum Plastering Works
47250 |  | Not Committed |  | 2027-03-11 | 2027-04-17 | MEP 1st Fixes | 100 | 0 |  | 2027-06-08 |  | 2027-07-15
47251 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-03-11 | 2027-03-18 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-06-08 |  | 2027-06-16 |  | Tower B | Super Structure | L40 | MEP | FPS 1st Fix - MEP & Finishes
47252 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-03-11 | 2027-03-16 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2027-06-08 |  | 2027-06-14 |  | Tower B | Super Structure | L40 | MEP | Electrical 1st Fixes
47253 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2027-03-11 | 2027-03-18 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2027-06-08 |  | 2027-06-16 |  | Tower B | Super Structure | L40
47754 |  | Not Ready |  | 2027-02-24 | 2027-03-18 | Slab_NTA | 100 | 0 |  | 2027-06-08 |  | 2027-07-01
47754 |  | Not Ready |  | 2027-02-24 | 2027-03-18 | Slab_NTA | 100 | 0 |  | 2027-06-08 |  | 2027-07-01 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
47762 |  | Not Committed |  | 2027-02-24 | 2027-03-31 | Pour 12 (PB-03 to PB-06) | 100 | 0 |  | 2027-06-08 |  | 2027-07-13
47763 |  | Not Ready |  | 2027-02-24 | 2027-03-12 | Columns/ Walls_NTA | 100 | 0 |  | 2027-06-08 |  | 2027-06-25
47763 |  | Not Ready |  | 2027-02-24 | 2027-03-12 | Columns/ Walls_NTA | 100 | 0 |  | 2027-06-08 |  | 2027-06-25 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
47764 |  | Not Ready |  | 2027-02-24 | 2027-03-18 | Staircase_NTA | 100 | 0 |  | 2027-06-08 |  | 2027-07-01
47764 |  | Not Ready |  | 2027-02-24 | 2027-03-18 | Staircase_NTA | 100 | 0 |  | 2027-06-08 |  | 2027-07-01 |  |  |  |  | RCC Sub Structure | Staircase & Ramp RCC Works
47766 |  | Not Committed |  | 2027-02-24 | 2027-05-06 | P3 to P4 | 100 | 0 |  | 2027-06-08 |  | 2027-08-17
47766 |  | Not Committed |  | 2027-02-24 | 2027-05-06 | P3 to P4 | 100 | 0 |  | 2027-06-08 |  | 2027-08-17
47766 |  | Not Committed |  | 2027-02-24 | 2027-05-06 | P3 to P4 | 100 | 0 |  | 2027-06-08 |  | 2027-08-17
47774 |  | Not Committed |  | 2027-02-24 | 2027-03-31 | Pour 10 (PA-A to PB-J) | 100 | 0 |  | 2027-06-08 |  | 2027-07-13
47775 |  | Not Ready |  | 2027-02-24 | 2027-03-12 | Columns/ Walls_NTA | 100 | 0 |  | 2027-06-08 |  | 2027-06-25
47775 |  | Not Ready |  | 2027-02-24 | 2027-03-12 | Columns/ Walls_NTA | 100 | 0 |  | 2027-06-08 |  | 2027-06-25 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
47776 |  | Not Ready |  | 2027-02-24 | 2027-03-25 | Ramp_NTA | 100 | 0 |  | 2027-06-08 |  | 2027-07-07
47809 |  | Not Ready |  | 2027-02-24 | 2027-03-25 | P1 to P2 | 100 | 0 |  | 2027-06-08 |  | 2027-07-07
47809 |  | Not Ready |  | 2027-02-24 | 2027-03-25 | P1 to P2 | 100 | 0 |  | 2027-06-08 |  | 2027-07-07
47809 |  | Not Ready |  | 2027-02-24 | 2027-03-25 | P1 to P2 | 100 | 0 |  | 2027-06-08 |  | 2027-07-07
46273 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-03-31 | 2027-04-07 | FAPA Cabling | 100 | 0 |  | 2027-06-09 |  | 2027-06-17 |  | Tower B | Super Structure | L21
39125 |  | Not Committed |  | 2026-11-30 |  | TA_Occupancy Certificate | 100 | 0 |  | 2027-06-10
44280 |  | Not Ready |  | 2026-11-28 | 2026-12-14 | Inspector Visit & Grant of OC | 100 | 0 |  | 2027-06-10 |  | 2027-06-28
47096 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2027-04-01 | 2027-04-08 | Door & Window Frame work | 100 | 0 |  | 2027-06-10 |  | 2027-06-18 |  | Tower B | Super Structure | L31 | Finishes | Door & Window Frame work
47112 |  | Not Committed |  | 2027-04-01 | 2027-05-24 | Finishes after 1st Fix | 100 | 0 |  | 2027-06-10 |  | 2027-07-31
47113 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2027-04-01 | 2027-04-12 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2027-06-10 |  | 2027-06-22 |  | Tower B | Super Structure | L32 | Finishes | Blockwork
47219 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2027-03-13 | 2027-03-25 | Cement Plastering in wet areas | 100 | 0 |  | 2027-06-10 |  | 2027-06-22 |  | Tower B | Super Structure | L38
46203 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-04-02 | 2027-04-09 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-06-11 |  | 2027-06-19 |  | Tower B | Super Structure | L16
46797 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2027-04-21 | 2027-04-26 | PHE Final Fixes | 100 | 0 |  | 2027-06-11 |  | 2027-06-17 |  | Tower B | Super Structure | L14
46230 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-04-03 | 2027-04-16 | False Ceiling | 100 | 0 |  | 2027-06-12 |  | 2027-06-26 |  | Tower B | Super Structure | L18 | Finishes | False Ceiling
46261 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-04-03 | 2027-05-03 | Flooring & Dado | 100 | 0 |  | 2027-06-12 |  | 2027-07-12 |  | Tower B | Super Structure | L20 | Finishes | Flooring & Dado
46274 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-04-03 | 2027-04-14 | HVAC Ducting | 100 | 0 |  | 2027-06-12 |  | 2027-06-24 |  | Tower B | Super Structure | L21 | MEP | HVAC Ducting
46286 |  | Not Committed |  | 2027-04-03 | 2027-11-08 | L22-23 | 100 | 0 |  | 2027-06-12 |  | 2027-12-09
46286 |  | Not Committed |  | 2027-04-03 | 2027-11-08 | L22-23 | 100 | 0 |  | 2027-06-12 |  | 2027-12-09 |  |  |  |  | Finishes | Gypsum Plastering Works
46287 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-04-03 | 2027-04-14 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-06-12 |  | 2027-06-24 |  | Tower B | Super Structure | L22 | MEP | FPS 1st Fix - MEP & Finishes
46288 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-04-03 | 2027-04-10 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-06-12 |  | 2027-06-21 |  | Tower B | Super Structure | L22 | MEP | Electrical 1st Fixes
47816 |  | Not Ready |  | 2026-12-03 | 2027-03-02 | B1 to GF | 100 | 0 |  | 2027-06-12 |  | 2027-09-09
47816 |  | Not Ready |  | 2026-12-03 | 2027-03-02 | B1 to GF | 100 | 0 |  | 2027-06-12 |  | 2027-09-09
47816 |  | Not Ready |  | 2026-12-03 | 2027-03-02 | B1 to GF | 100 | 0 |  | 2027-06-12 |  | 2027-09-09
47827 |  | Not Ready |  | 2026-12-03 | 2027-01-07 | Staircase Finishes | 100 | 0 |  | 2027-06-12 |  | 2027-07-17
47827 |  | Not Ready |  | 2026-12-03 | 2027-01-07 | Staircase Finishes | 100 | 0 |  | 2027-06-12 |  | 2027-07-17
47828 |  | Not Committed |  | 2026-12-03 | 2027-03-19 | B2 to B1 | 100 | 0 |  | 2027-06-12 |  | 2027-09-28
47828 |  | Not Committed |  | 2026-12-03 | 2027-03-19 | B2 to B1 | 100 | 0 |  | 2027-06-12 |  | 2027-09-28
47828 |  | Not Committed |  | 2026-12-03 | 2027-03-19 | B2 to B1 | 100 | 0 |  | 2027-06-12 |  | 2027-09-28
47829 |  | Not Ready |  | 2026-12-03 | 2027-01-07 | VDF Flooring | 100 | 0 |  | 2027-06-12 |  | 2027-07-17
47829 |  | Not Ready |  | 2026-12-03 | 2027-01-07 | VDF Flooring | 100 | 0 |  | 2027-06-12 |  | 2027-07-17
45572 | Tower B - Super Structure - Finishes & MEP - L41 to L42 | Not Ready | Partition Wall-Blockwork | 2027-03-17 | 2027-03-23 | Staircase Area | 100 | 0 |  | 2027-06-14 |  | 2027-06-19 |  | Tower B | Super Structure | L41
46215 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-04-06 | 2027-04-13 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-06-15 |  | 2027-06-23 |  | Tower B | Super Structure | L17 | MEP | FPS 2nd Fix - MEP & Finishes
46216 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-04-06 | 2027-04-13 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-06-15 |  | 2027-06-23 |  | Tower B | Super Structure | L17 | MEP | Electrical 2nd Fix - MEP & Finishes
46217 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-04-06 | 2027-04-16 | FAPA Device Fixing | 100 | 0 |  | 2027-06-15 |  | 2027-06-26 |  | Tower B | Super Structure | L17
46217 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-04-06 | 2027-04-16 | FAPA Device Fixing | 100 | 0 |  | 2027-06-15 |  | 2027-06-26 |  | Tower B | Super Structure | L17
46217 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-04-06 | 2027-04-16 | FAPA Device Fixing | 100 | 0 |  | 2027-06-15 |  | 2027-06-26 |  | Tower B | Super Structure | L17
46217 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-04-06 | 2027-04-16 | FAPA Device Fixing | 100 | 0 |  | 2027-06-15 |  | 2027-06-26 |  | Tower B | Super Structure | L17
46218 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-04-06 | 2027-04-13 | HVAC Grill Fixing | 100 | 0 |  | 2027-06-15 |  | 2027-06-23 |  | Tower B | Super Structure | L17 | MEP | HVAC Grill Fixing
46813 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-04-27 | 2027-05-05 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-06-15 |  | 2027-06-23 |  | Tower B | Super Structure | L15 | MEP | FPS 2nd Fix - MEP & Finishes
46814 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-04-27 | 2027-05-05 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-06-15 |  | 2027-06-23 |  | Tower B | Super Structure | L15 | MEP | Electrical 2nd Fix - MEP & Finishes
46829 |  | Not Committed |  | 2027-04-27 | 2027-05-28 | MEP final fix & Finishes | 100 | 0 |  | 2027-06-15 |  | 2027-07-15
46830 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2027-04-27 | 2027-05-11 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2027-06-15 |  | 2027-06-26 |  | Tower B | Super Structure | L16 | Finishes | Door & Window Fixing
46189 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-04-07 | 2027-04-14 | Final Painting | 100 | 0 |  | 2027-06-16 |  | 2027-06-24 |  | Tower B | Super Structure | L15 | Finishes | Final Painting
46189 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-04-07 | 2027-04-14 | Final Painting | 100 | 0 |  | 2027-06-16 |  | 2027-06-24 |  | Tower B | Super Structure | L15 | Finishes | Final Painting
46189 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-04-07 | 2027-04-14 | Final Painting | 100 | 0 |  | 2027-06-16 |  | 2027-06-24 |  | Tower B | Super Structure | L15 | Finishes | Final Painting
47254 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2027-03-19 | 2027-04-06 | Wet Area Waterproofing | 100 | 0 |  | 2027-06-16 |  | 2027-07-03 |  | Tower B | Super Structure | L40
45575 | Tower B - Super Structure - Finishes & MEP - L42 to L43 | Not Ready | Partition Wall-Blockwork | 2027-03-20 | 2027-03-29 | Partition Walls | 100 | 0 |  | 2027-06-17 |  | 2027-06-25 |  | Tower B | Super Structure | L42
45577 |  | Not Committed |  | 2027-03-20 | 2027-04-21 | L43-44 | 100 | 0 |  | 2027-06-17 |  | 2027-07-19
45577 |  | Not Committed |  | 2027-03-20 | 2027-04-21 | L43-44 | 100 | 0 |  | 2027-06-17 |  | 2027-07-19 |  |  |  |  | Finishes | Gypsum Plastering Works
45578 | Tower B - Super Structure - Finishes & MEP - L43 to L44 | Not Ready | Partition Wall-Blockwork | 2027-03-20 | 2027-04-07 | De-shuttering & Area clearance | 100 | 0 |  | 2027-06-17 |  | 2027-07-05 |  | Tower B | Super Structure | L43
46798 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2027-04-27 | 2027-05-05 | Painting Works | 100 | 0 |  | 2027-06-17 |  | 2027-06-25 |  | Tower B | Super Structure | L14 | Finishes | Painting Works
47115 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-04-09 | 2027-05-08 | Flooring & Dado works | 100 | 0 |  | 2027-06-18 |  | 2027-07-17 |  | Tower B | Super Structure | L32 | Finishes | Flooring & Dado
45643 | Tower B - Super Structure - Finishes & MEP - L40 to L41 | Not Ready | Gypsum Plastering Works | 2027-03-24 | 2027-04-21 | L40-41 | 100 | 0 |  | 2027-06-19 |  | 2027-07-19 |  | Tower B | Super Structure | L40 | Finishes | Gypsum Plastering Works
45643 | Tower B - Super Structure - Finishes & MEP - L40 to L41 | Not Ready | Gypsum Plastering Works | 2027-03-24 | 2027-04-21 | L40-41 | 100 | 0 |  | 2027-06-19 |  | 2027-07-19 |  | Tower B | Super Structure | L40
46204 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-04-10 | 2027-04-17 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-06-19 |  | 2027-06-28 |  | Tower B | Super Structure | L16 | MEP | Electrical
47268 |  | Not Committed |  | 2027-03-24 | 2027-04-29 | MEP 1st Fixes | 100 | 0 |  | 2027-06-19 |  | 2027-07-27
47269 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-03-24 | 2027-03-31 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-06-19 |  | 2027-06-28 |  | Tower B | Super Structure | L41 | MEP | FPS 1st Fix - MEP & Finishes
47270 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-03-24 | 2027-03-29 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2027-06-19 |  | 2027-06-25 |  | Tower B | Super Structure | L41 | MEP | Electrical 1st Fixes
47271 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2027-03-24 | 2027-03-31 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2027-06-19 |  | 2027-06-28 |  | Tower B | Super Structure | L41
46289 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-04-12 | 2027-04-19 | FAPA Cabling | 100 | 0 |  | 2027-06-21 |  | 2027-06-29 |  | Tower B | Super Structure | L22
47114 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2027-04-13 | 2027-04-20 | Door & Window Frame work | 100 | 0 |  | 2027-06-22 |  | 2027-06-30 |  | Tower B | Super Structure | L32 | Finishes | Door & Window Frame work
47130 |  | Not Committed |  | 2027-04-13 | 2027-06-04 | Finishes after 1st Fix | 100 | 0 |  | 2027-06-22 |  | 2027-08-12
47131 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2027-04-13 | 2027-04-23 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2027-06-22 |  | 2027-07-03 |  | Tower B | Super Structure | L33 | Finishes | Blockwork
47237 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2027-03-26 | 2027-04-06 | Cement Plastering in wet areas | 100 | 0 |  | 2027-06-22 |  | 2027-07-03 |  | Tower B | Super Structure | L39
47449 |  | Not Committed |  | 2027-04-13 | 2027-07-10 | L38-Terrace | 100 | 0 |  | 2027-06-22 |  | 2027-09-20
47450 | Tower B - Super Structure - Finishes & MEP - L38 to Terrace | Not Ready | Façade Works - MEP & Finishes | 2027-04-13 | 2027-05-25 | Al. Frame section (Mullion & Transom) Installation | 100 | 0 |  | 2027-06-22 |  | 2027-08-02 |  | Tower B | Super Structure | L38 | Façade | Façade Works
45760 | Tower B - Super Structure - Finishes & MEP - L35 to Terrace | Not Ready |  | 2027-03-27 | 2027-05-20 | FHC & Accessories fixing | 100 | 0 |  | 2027-06-23 |  | 2027-08-14 |  | Tower B | Super Structure | L35
45762 | Tower B - Super Structure - Finishes & MEP - L35 to Terrace | Not Ready |  | 2027-03-27 | 2027-05-20 | Soil & Waste Downtake piping in Plumbing Shaft | 100 | 0 |  | 2027-06-23 |  | 2027-08-14 |  | Tower B | Super Structure | L35
45766 | Tower B - Super Structure - Finishes & MEP - L35 to Terrace | Not Ready |  | 2027-03-27 | 2027-05-20 | HVAC Shaft Ducting | 100 | 0 |  | 2027-06-23 |  | 2027-08-14 |  | Tower B | Super Structure | L35 | MEP | HVAC Grill Fixing
46219 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-04-14 | 2027-04-21 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-06-23 |  | 2027-07-01 |  | Tower B | Super Structure | L17
46815 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2027-05-06 | 2027-05-11 | PHE Final Fixes | 100 | 0 |  | 2027-06-23 |  | 2027-06-29 |  | Tower B | Super Structure | L15
46246 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-04-15 | 2027-04-28 | False Ceiling | 100 | 0 |  | 2027-06-24 |  | 2027-07-08 |  | Tower B | Super Structure | L19 | Finishes | False Ceiling
46277 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-04-15 | 2027-05-14 | Flooring & Dado | 100 | 0 |  | 2027-06-24 |  | 2027-07-23 |  | Tower B | Super Structure | L21 | Finishes | Flooring & Dado
46290 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-04-15 | 2027-04-26 | HVAC Ducting | 100 | 0 |  | 2027-06-24 |  | 2027-07-06 |  | Tower B | Super Structure | L22 | MEP | HVAC Ducting
46302 |  | Not Committed |  | 2027-04-15 | 2027-11-13 | L23-24 | 100 | 0 |  | 2027-06-24 |  | 2027-12-15
46302 |  | Not Committed |  | 2027-04-15 | 2027-11-13 | L23-24 | 100 | 0 |  | 2027-06-24 |  | 2027-12-15 |  |  |  |  | Finishes | Gypsum Plastering Works
46303 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-04-15 | 2027-04-26 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-06-24 |  | 2027-07-06 |  | Tower B | Super Structure | L23 | MEP | FPS 1st Fix - MEP & Finishes
46304 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-04-15 | 2027-04-22 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-06-24 |  | 2027-07-02 |  | Tower B | Super Structure | L23 | MEP | Electrical 1st Fixes
47062 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2027-04-15 | 2027-04-28 | False Ceiling | 100 | 0 |  | 2027-06-24 |  | 2027-07-08 |  | Tower B | Super Structure | L29 | Finishes | False Ceiling
47080 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2027-04-15 | 2027-04-28 | False Ceiling | 100 | 0 |  | 2027-06-24 |  | 2027-07-08 |  | Tower B | Super Structure | L30 | Finishes | False Ceiling
45576 | Tower B - Super Structure - Finishes & MEP - L42 to L43 | Not Ready | Partition Wall-Blockwork | 2027-03-30 | 2027-04-03 | Staircase Area | 100 | 0 |  | 2027-06-25 |  | 2027-07-01 |  | Tower B | Super Structure | L42
47765 |  | Not Ready |  | 2027-03-13 | 2027-03-31 | Slab_NTA | 100 | 0 |  | 2027-06-25 |  | 2027-07-13
47765 |  | Not Ready |  | 2027-03-13 | 2027-03-31 | Slab_NTA | 100 | 0 |  | 2027-06-25 |  | 2027-07-13 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
47767 |  | Not Committed |  | 2027-03-13 | 2027-04-23 | Pour 8 (grid PB-B to PB-J) | 100 | 0 |  | 2027-06-25 |  | 2027-08-05
47768 |  | Not Ready |  | 2027-03-13 | 2027-03-31 | Columns/ Walls_NTA | 100 | 0 |  | 2027-06-25 |  | 2027-07-13
47768 |  | Not Ready |  | 2027-03-13 | 2027-03-31 | Columns/ Walls_NTA | 100 | 0 |  | 2027-06-25 |  | 2027-07-13 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
47769 |  | Not Ready |  | 2027-03-13 | 2027-04-06 | Staircase_NTA | 100 | 0 |  | 2027-06-25 |  | 2027-07-19
47769 |  | Not Ready |  | 2027-03-13 | 2027-04-06 | Staircase_NTA | 100 | 0 |  | 2027-06-25 |  | 2027-07-19 |  |  |  |  | RCC Sub Structure | Staircase & Ramp RCC Works
47777 |  | Not Ready |  | 2027-03-13 | 2027-03-31 | Slab_NTA | 100 | 0 |  | 2027-06-25 |  | 2027-07-13
47777 |  | Not Ready |  | 2027-03-13 | 2027-03-31 | Slab_NTA | 100 | 0 |  | 2027-06-25 |  | 2027-07-13 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
47778 |  | Not Committed |  | 2027-03-13 | 2027-04-06 | Pour 11 (PB-C to PB-K) | 100 | 0 |  | 2027-06-25 |  | 2027-07-19
47779 |  | Not Ready |  | 2027-03-13 | 2027-03-31 | Columns/ Walls_NTA | 100 | 0 |  | 2027-06-25 |  | 2027-07-13
47779 |  | Not Ready |  | 2027-03-13 | 2027-03-31 | Columns/ Walls_NTA | 100 | 0 |  | 2027-06-25 |  | 2027-07-13 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
46231 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-04-17 | 2027-04-24 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-06-26 |  | 2027-07-05 |  | Tower B | Super Structure | L18 | MEP | FPS 2nd Fix - MEP & Finishes
46232 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-04-17 | 2027-04-24 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-06-26 |  | 2027-07-05 |  | Tower B | Super Structure | L18 | MEP | Electrical 2nd Fix - MEP & Finishes
46233 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-04-17 | 2027-04-28 | FAPA Device Fixing | 100 | 0 |  | 2027-06-26 |  | 2027-07-08 |  | Tower B | Super Structure | L18
46233 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-04-17 | 2027-04-28 | FAPA Device Fixing | 100 | 0 |  | 2027-06-26 |  | 2027-07-08 |  | Tower B | Super Structure | L18
46233 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-04-17 | 2027-04-28 | FAPA Device Fixing | 100 | 0 |  | 2027-06-26 |  | 2027-07-08 |  | Tower B | Super Structure | L18
46233 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-04-17 | 2027-04-28 | FAPA Device Fixing | 100 | 0 |  | 2027-06-26 |  | 2027-07-08 |  | Tower B | Super Structure | L18
46234 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-04-17 | 2027-04-24 | HVAC Grill Fixing | 100 | 0 |  | 2027-06-26 |  | 2027-07-05 |  | Tower B | Super Structure | L18 | MEP | HVAC Grill Fixing
46831 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-05-12 | 2027-05-20 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-06-26 |  | 2027-07-05 |  | Tower B | Super Structure | L16 | MEP | FPS 2nd Fix - MEP & Finishes
46832 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-05-12 | 2027-05-20 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-06-26 |  | 2027-07-05 |  | Tower B | Super Structure | L16 | MEP | Electrical 2nd Fix - MEP & Finishes
46847 |  | Not Committed |  | 2027-05-12 | 2027-06-09 | MEP final fix & Finishes | 100 | 0 |  | 2027-06-26 |  | 2027-07-23
46848 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2027-05-12 | 2027-05-26 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2027-06-26 |  | 2027-07-08 |  | Tower B | Super Structure | L17 | Finishes | Door & Window Fixing
39126 |  | Not Committed |  | 2026-12-30 |  | TA_Handing Over | 100 | 0 |  | 2027-06-28
46205 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-04-19 | 2027-04-26 | Final Painting | 100 | 0 |  | 2027-06-28 |  | 2027-07-06 |  | Tower B | Super Structure | L16 | Finishes | Final Painting
46205 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-04-19 | 2027-04-26 | Final Painting | 100 | 0 |  | 2027-06-28 |  | 2027-07-06 |  | Tower B | Super Structure | L16 | Finishes | Final Painting
46205 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-04-19 | 2027-04-26 | Final Painting | 100 | 0 |  | 2027-06-28 |  | 2027-07-06 |  | Tower B | Super Structure | L16 | Finishes | Final Painting
47272 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2027-04-01 | 2027-04-17 | Wet Area Waterproofing | 100 | 0 |  | 2027-06-28 |  | 2027-07-15 |  | Tower B | Super Structure | L41
45585 |  | Not Committed |  | 2027-05-14 | 2027-06-21 | Above Terrace Masonry | 100 | 0 |  | 2027-06-29 |  | 2027-08-03
45586 | Tower B - Super Structure - Finishes & MEP - Above Terrace | Not Ready | Partition Wall-Blockwork | 2027-05-14 | 2027-06-12 | MEP related works | 100 | 0 |  | 2027-06-29 |  | 2027-07-28 |  | Tower B | Super Structure
45587 | Tower B - Super Structure - Finishes & MEP - Above Terrace | Not Ready | Partition Wall-Blockwork | 2027-05-29 | 2027-06-15 | LMR Masonry | 100 | 0 |  | 2027-06-29 |  | 2027-07-16 |  | Tower B | Super Structure
45588 | Tower B - Super Structure - Finishes & MEP - Above Terrace | Not Ready | Partition Wall-Blockwork | 2027-05-14 | 2027-06-01 | Terrace Area works | 100 | 0 |  | 2027-06-29 |  | 2027-07-16 |  | Tower B | Super Structure
45589 | Tower B - Super Structure - Finishes & MEP - Above Terrace | Not Ready | Partition Wall-Blockwork | 2027-05-18 | 2027-06-21 | Staircase Area | 100 | 0 |  | 2027-06-29 |  | 2027-08-03 |  | Tower B | Super Structure
45649 |  | Not Committed |  | 2027-05-29 | 2028-02-17 | Elevator | 100 | 0 |  | 2027-06-29 |  | 2028-03-08
45649 |  | Not Committed |  | 2027-05-29 | 2028-02-17 | Elevator | 100 | 0 |  | 2027-06-29 |  | 2028-03-08
45650 |  | Not Committed |  | 2027-05-29 | 2027-10-12 | CTU Elevators | 100 | 0 |  | 2027-06-29 |  | 2027-11-13
45651 | Tower B - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2027-05-29 | 2027-07-20 | Plumb check & door centre line by Lift agency for lobby blockwork | 100 | 0 |  | 2027-06-29 |  | 2027-08-20 |  | Tower B | Super Structure
45651 | Tower B - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2027-05-29 | 2027-07-20 | Plumb check & door centre line by Lift agency for lobby blockwork | 100 | 0 |  | 2027-06-29 |  | 2027-08-20 |  | Tower B | Super Structure
45651 | Tower B - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2027-05-29 | 2027-07-20 | Plumb check & door centre line by Lift agency for lobby blockwork | 100 | 0 |  | 2027-06-29 |  | 2027-08-20 |  | Tower B | Super Structure
45652 | Tower B - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2027-05-29 | 2027-06-14 | Shaft clearance & White Wash up to LMR | 100 | 0 |  | 2027-06-29 |  | 2027-07-15 |  | Tower B | Super Structure
45652 | Tower B - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2027-05-29 | 2027-06-14 | Shaft clearance & White Wash up to LMR | 100 | 0 |  | 2027-06-29 |  | 2027-07-15 |  | Tower B | Super Structure
45657 | Tower B - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2027-05-29 | 2027-08-06 | LMR Works | 100 | 0 |  | 2027-06-29 |  | 2027-09-08 |  | Tower B | Super Structure
45657 | Tower B - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2027-05-29 | 2027-08-06 | LMR Works | 100 | 0 |  | 2027-06-29 |  | 2027-09-08 |  | Tower B | Super Structure
45664 |  | Not Committed |  | 2027-05-29 | 2028-02-17 | Other Elevators | 100 | 0 |  | 2027-06-29 |  | 2028-03-08
45665 | Tower B - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2027-05-29 | 2027-08-24 | Crash deck removal & De-commission of temporary LMR | 100 | 0 |  | 2027-06-29 |  | 2027-09-27 |  | Tower B | Super Structure
46816 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2027-05-12 | 2027-05-20 | Painting Works | 100 | 0 |  | 2027-06-29 |  | 2027-07-07 |  | Tower B | Super Structure | L15 | Finishes | Painting Works
46833 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2027-05-12 | 2027-05-18 | PHE Final Fixes | 100 | 0 |  | 2027-06-29 |  | 2027-07-05 |  | Tower B | Super Structure | L16
47133 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-04-21 | 2027-05-21 | Flooring & Dado works | 100 | 0 |  | 2027-06-30 |  | 2027-07-29 |  | Tower B | Super Structure | L33 | Finishes | Flooring & Dado
45644 | Tower B - Super Structure - Finishes & MEP - L41 to L42 | Not Ready | Gypsum Plastering Works | 2027-04-05 | 2027-05-04 | L41-42 | 100 | 0 |  | 2027-07-01 |  | 2027-07-30 |  | Tower B | Super Structure | L41 | Finishes | Gypsum Plastering Works
45644 | Tower B - Super Structure - Finishes & MEP - L41 to L42 | Not Ready | Gypsum Plastering Works | 2027-04-05 | 2027-05-04 | L41-42 | 100 | 0 |  | 2027-07-01 |  | 2027-07-30 |  | Tower B | Super Structure | L41
46220 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-04-22 | 2027-04-29 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-07-01 |  | 2027-07-09 |  | Tower B | Super Structure | L17 | MEP | Electrical
47286 |  | Not Committed |  | 2027-04-05 | 2027-05-12 | MEP 1st Fixes | 100 | 0 |  | 2027-07-01 |  | 2027-08-07
47287 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-04-05 | 2027-04-12 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-07-01 |  | 2027-07-09 |  | Tower B | Super Structure | L42 | MEP | FPS 1st Fix - MEP & Finishes
47288 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-04-05 | 2027-04-09 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2027-07-01 |  | 2027-07-07 |  | Tower B | Super Structure | L42 | MEP | Electrical 1st Fixes
47289 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2027-04-05 | 2027-04-12 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2027-07-01 |  | 2027-07-09 |  | Tower B | Super Structure | L42
47780 |  | Not Ready |  | 2027-03-19 | 2027-04-06 | Slab_NTA (tie-beams) | 100 | 0 |  | 2027-07-01 |  | 2027-07-19
47780 |  | Not Ready |  | 2027-03-19 | 2027-04-06 | Slab_NTA (tie-beams) | 100 | 0 |  | 2027-07-01 |  | 2027-07-19 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
46305 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-04-23 | 2027-04-30 | FAPA Cabling | 100 | 0 |  | 2027-07-02 |  | 2027-07-10 |  | Tower B | Super Structure | L23
47132 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2027-04-24 | 2027-05-03 | Door & Window Frame work | 100 | 0 |  | 2027-07-03 |  | 2027-07-12 |  | Tower B | Super Structure | L33 | Finishes | Door & Window Frame work
47148 |  | Not Committed |  | 2027-04-24 | 2027-06-16 | Finishes after 1st Fix | 100 | 0 |  | 2027-07-03 |  | 2027-08-24
47149 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2027-04-24 | 2027-05-06 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2027-07-03 |  | 2027-07-15 |  | Tower B | Super Structure | L34 | Finishes | Blockwork
47255 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2027-04-07 | 2027-04-17 | Cement Plastering in wet areas | 100 | 0 |  | 2027-07-03 |  | 2027-07-15 |  | Tower B | Super Structure | L40
45579 | Tower B - Super Structure - Finishes & MEP - L43 to L44 | Not Ready | Partition Wall-Blockwork | 2027-04-08 | 2027-04-15 | Partition Walls | 100 | 0 |  | 2027-07-05 |  | 2027-07-13 |  | Tower B | Super Structure | L43
45581 |  | Not Committed |  | 2027-04-08 | 2027-05-10 | L44-45 | 100 | 0 |  | 2027-07-05 |  | 2027-08-05
45581 |  | Not Committed |  | 2027-04-08 | 2027-05-10 | L44-45 | 100 | 0 |  | 2027-07-05 |  | 2027-08-05 |  |  |  |  | Finishes | Gypsum Plastering Works
45582 | Tower B - Super Structure - Finishes & MEP - L44 to L45 | Not Ready | Partition Wall-Blockwork | 2027-04-08 | 2027-04-24 | De-shuttering & Area clearance | 100 | 0 |  | 2027-07-05 |  | 2027-07-22 |  | Tower B | Super Structure | L44
45682 | Tower B - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2027-05-27 | 2027-06-24 | Pipe & Support Fabrication | 100 | 0 |  | 2027-07-05 |  | 2027-08-03 |  | Tower B | Super Structure
45764 | Tower B - Super Structure - Finishes & MEP - L35 to Terrace | Not Ready |  | 2027-04-08 | 2027-05-13 | Shaft Cabling in Electrical & ELV Shaft | 100 | 0 |  | 2027-07-05 |  | 2027-08-09 |  | Tower B | Super Structure | L35
46235 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-04-26 | 2027-05-04 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-07-05 |  | 2027-07-13 |  | Tower B | Super Structure | L18
46262 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-04-27 | 2027-05-11 | False Ceiling | 100 | 0 |  | 2027-07-06 |  | 2027-07-20 |  | Tower B | Super Structure | L20 | Finishes | False Ceiling
46293 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-04-27 | 2027-05-27 | Flooring & Dado | 100 | 0 |  | 2027-07-06 |  | 2027-08-04 |  | Tower B | Super Structure | L22 | Finishes | Flooring & Dado
46306 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-04-27 | 2027-05-08 | HVAC Ducting | 100 | 0 |  | 2027-07-06 |  | 2027-07-17 |  | Tower B | Super Structure | L23 | MEP | HVAC Ducting
46318 |  | Not Committed |  | 2027-04-27 | 2027-11-19 | L24-25 | 100 | 0 |  | 2027-07-06 |  | 2027-12-21
46318 |  | Not Committed |  | 2027-04-27 | 2027-11-19 | L24-25 | 100 | 0 |  | 2027-07-06 |  | 2027-12-21 |  |  |  |  | Finishes | Gypsum Plastering Works
46319 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-04-27 | 2027-05-08 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-07-06 |  | 2027-07-17 |  | Tower B | Super Structure | L24 | MEP | FPS 1st Fix - MEP & Finishes
46320 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-04-27 | 2027-05-05 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-07-06 |  | 2027-07-14 |  | Tower B | Super Structure | L24 | MEP | Electrical 1st Fixes
47098 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2027-04-27 | 2027-05-11 | False Ceiling | 100 | 0 |  | 2027-07-06 |  | 2027-07-20 |  | Tower B | Super Structure | L31 | Finishes | False Ceiling
46834 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2027-05-21 | 2027-05-28 | Painting Works | 100 | 0 |  | 2027-07-07 |  | 2027-07-15 |  | Tower B | Super Structure | L16 | Finishes | Painting Works
46247 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-04-29 | 2027-05-07 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-07-08 |  | 2027-07-16 |  | Tower B | Super Structure | L19 | MEP | FPS 2nd Fix - MEP & Finishes
46248 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-04-29 | 2027-05-07 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-07-08 |  | 2027-07-16 |  | Tower B | Super Structure | L19 | MEP | Electrical 2nd Fix - MEP & Finishes
46249 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-04-29 | 2027-05-11 | FAPA Device Fixing | 100 | 0 |  | 2027-07-08 |  | 2027-07-20 |  | Tower B | Super Structure | L19
46249 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-04-29 | 2027-05-11 | FAPA Device Fixing | 100 | 0 |  | 2027-07-08 |  | 2027-07-20 |  | Tower B | Super Structure | L19
46249 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-04-29 | 2027-05-11 | FAPA Device Fixing | 100 | 0 |  | 2027-07-08 |  | 2027-07-20 |  | Tower B | Super Structure | L19
46249 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-04-29 | 2027-05-11 | FAPA Device Fixing | 100 | 0 |  | 2027-07-08 |  | 2027-07-20 |  | Tower B | Super Structure | L19
46250 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-04-29 | 2027-05-07 | HVAC Grill Fixing | 100 | 0 |  | 2027-07-08 |  | 2027-07-16 |  | Tower B | Super Structure | L19 | MEP | HVAC Grill Fixing
46849 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-05-27 | 2027-06-03 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-07-08 |  | 2027-07-16 |  | Tower B | Super Structure | L17 | MEP | FPS 2nd Fix - MEP & Finishes
46850 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-05-27 | 2027-06-03 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-07-08 |  | 2027-07-16 |  | Tower B | Super Structure | L17 | MEP | Electrical 2nd Fix - MEP & Finishes
46851 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2027-05-27 | 2027-06-01 | PHE Final Fixes | 100 | 0 |  | 2027-07-08 |  | 2027-07-14 |  | Tower B | Super Structure | L17
46865 |  | Not Committed |  | 2027-05-27 | 2027-06-21 | MEP final fix & Finishes | 100 | 0 |  | 2027-07-08 |  | 2027-07-31
46866 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2027-05-27 | 2027-06-09 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2027-07-08 |  | 2027-07-20 |  | Tower B | Super Structure | L18 | Finishes | Door & Window Fixing
46221 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-04-30 | 2027-05-08 | Final Painting | 100 | 0 |  | 2027-07-09 |  | 2027-07-17 |  | Tower B | Super Structure | L17 | Finishes | Final Painting
46221 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-04-30 | 2027-05-08 | Final Painting | 100 | 0 |  | 2027-07-09 |  | 2027-07-17 |  | Tower B | Super Structure | L17 | Finishes | Final Painting
46221 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-04-30 | 2027-05-08 | Final Painting | 100 | 0 |  | 2027-07-09 |  | 2027-07-17 |  | Tower B | Super Structure | L17 | Finishes | Final Painting
47290 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2027-04-13 | 2027-04-29 | Wet Area Waterproofing | 100 | 0 |  | 2027-07-09 |  | 2027-07-27 |  | Tower B | Super Structure | L42
45683 | Tower B - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2027-06-02 | 2027-07-23 | Support & Pipe Installation | 100 | 0 |  | 2027-07-10 |  | 2027-09-01 |  | Tower B | Super Structure
47151 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-05-04 | 2027-06-02 | Flooring & Dado works | 100 | 0 |  | 2027-07-12 |  | 2027-08-10 |  | Tower B | Super Structure | L34 | Finishes | Flooring & Dado
45580 | Tower B - Super Structure - Finishes & MEP - L43 to L44 | Not Ready | Partition Wall-Blockwork | 2027-04-16 | 2027-04-21 | Staircase Area | 100 | 0 |  | 2027-07-13 |  | 2027-07-19 |  | Tower B | Super Structure | L43
45645 | Tower B - Super Structure - Finishes & MEP - L42 to L43 | Not Ready | Gypsum Plastering Works | 2027-04-16 | 2027-05-15 | L42-43 | 100 | 0 |  | 2027-07-13 |  | 2027-08-11 |  | Tower B | Super Structure | L42 | Finishes | Gypsum Plastering Works
45645 | Tower B - Super Structure - Finishes & MEP - L42 to L43 | Not Ready | Gypsum Plastering Works | 2027-04-16 | 2027-05-15 | L42-43 | 100 | 0 |  | 2027-07-13 |  | 2027-08-11 |  | Tower B | Super Structure | L42
46236 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-05-05 | 2027-05-12 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-07-13 |  | 2027-07-21 |  | Tower B | Super Structure | L18 | MEP | Electrical
47770 |  | Not Ready |  | 2027-04-01 | 2027-04-23 | Slab_NTA | 100 | 0 |  | 2027-07-13 |  | 2027-08-05
47770 |  | Not Ready |  | 2027-04-01 | 2027-04-23 | Slab_NTA | 100 | 0 |  | 2027-07-13 |  | 2027-08-05 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
47771 |  | Not Committed |  | 2027-04-01 | 2027-04-29 | Pour 9 (grid PB-06 to PB-C) | 100 | 0 |  | 2027-07-13 |  | 2027-08-11
47772 |  | Not Ready |  | 2027-04-01 | 2027-04-17 | Columns/ Walls_NTA | 100 | 0 |  | 2027-07-13 |  | 2027-07-30
47772 |  | Not Ready |  | 2027-04-01 | 2027-04-17 | Columns/ Walls_NTA | 100 | 0 |  | 2027-07-13 |  | 2027-07-30 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
47781 |  | Not Committed |  | 2027-04-01 | 2027-05-06 | Pour 12 (PB-03 to PB-06) | 100 | 0 |  | 2027-07-13 |  | 2027-08-17
47782 |  | Not Ready |  | 2027-04-01 | 2027-04-17 | Columns/ Walls_NTA | 100 | 0 |  | 2027-07-13 |  | 2027-07-30
47782 |  | Not Ready |  | 2027-04-01 | 2027-04-17 | Columns/ Walls_NTA | 100 | 0 |  | 2027-07-13 |  | 2027-07-30 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
47783 |  | Not Ready |  | 2027-04-01 | 2027-04-23 | Staircase_NTA | 100 | 0 |  | 2027-07-13 |  | 2027-08-05
47783 |  | Not Ready |  | 2027-04-01 | 2027-04-23 | Staircase_NTA | 100 | 0 |  | 2027-07-13 |  | 2027-08-05 |  |  |  |  | RCC Sub Structure | Staircase & Ramp RCC Works
47785 |  | Not Committed |  | 2027-04-01 | 2027-06-11 | P4 to P5 | 100 | 0 |  | 2027-07-13 |  | 2027-09-23
47785 |  | Not Committed |  | 2027-04-01 | 2027-06-11 | P4 to P5 | 100 | 0 |  | 2027-07-13 |  | 2027-09-23
47785 |  | Not Committed |  | 2027-04-01 | 2027-06-11 | P4 to P5 | 100 | 0 |  | 2027-07-13 |  | 2027-09-23
47793 |  | Not Committed |  | 2027-04-01 | 2027-05-06 | Pour 10 (PA-A to PB-J) | 100 | 0 |  | 2027-07-13 |  | 2027-08-17
47794 |  | Not Ready |  | 2027-04-01 | 2027-04-17 | Columns/ Walls_NTA | 100 | 0 |  | 2027-07-13 |  | 2027-07-30
47794 |  | Not Ready |  | 2027-04-01 | 2027-04-17 | Columns/ Walls_NTA | 100 | 0 |  | 2027-07-13 |  | 2027-07-30 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
47795 |  | Not Ready |  | 2027-04-01 | 2027-04-29 | Ramp_NTA | 100 | 0 |  | 2027-07-13 |  | 2027-08-11
47810 |  | Not Ready |  | 2027-04-01 | 2027-05-19 | P2 to P3 | 100 | 0 |  | 2027-07-13 |  | 2027-08-28
47810 |  | Not Ready |  | 2027-04-01 | 2027-05-19 | P2 to P3 | 100 | 0 |  | 2027-07-13 |  | 2027-08-28
47810 |  | Not Ready |  | 2027-04-01 | 2027-05-19 | P2 to P3 | 100 | 0 |  | 2027-07-13 |  | 2027-08-28
46321 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-05-06 | 2027-05-13 | FAPA Cabling | 100 | 0 |  | 2027-07-14 |  | 2027-07-22 |  | Tower B | Super Structure | L24
45653 | Tower B - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2027-06-15 | 2027-06-30 | Bulk head light fix + Electrical works + Earthing | 100 | 0 |  | 2027-07-15 |  | 2027-07-31 |  | Tower B | Super Structure
45653 | Tower B - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2027-06-15 | 2027-06-30 | Bulk head light fix + Electrical works + Earthing | 100 | 0 |  | 2027-07-15 |  | 2027-07-31 |  | Tower B | Super Structure
45653 | Tower B - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2027-06-15 | 2027-06-30 | Bulk head light fix + Electrical works + Earthing | 100 | 0 |  | 2027-07-15 |  | 2027-07-31 |  | Tower B | Super Structure
46852 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2027-06-02 | 2027-06-09 | Painting Works | 100 | 0 |  | 2027-07-15 |  | 2027-07-23 |  | Tower B | Super Structure | L17 | Finishes | Painting Works
47150 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2027-05-07 | 2027-05-14 | Door & Window Frame work | 100 | 0 |  | 2027-07-15 |  | 2027-07-23 |  | Tower B | Super Structure | L34 | Finishes | Door & Window Frame work
47166 |  | Not Committed |  | 2027-05-07 | 2027-06-16 | Finishes after 1st Fix | 100 | 0 |  | 2027-07-15 |  | 2027-08-24
47167 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2027-05-07 | 2027-05-19 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2027-07-15 |  | 2027-07-27 |  | Tower B | Super Structure | L35 | Finishes | Blockwork
47273 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2027-04-19 | 2027-04-29 | Cement Plastering in wet areas | 100 | 0 |  | 2027-07-15 |  | 2027-07-27 |  | Tower B | Super Structure | L41
46251 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-05-08 | 2027-05-15 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-07-16 |  | 2027-07-24 |  | Tower B | Super Structure | L19
46278 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-05-10 | 2027-05-24 | False Ceiling | 100 | 0 |  | 2027-07-17 |  | 2027-07-31 |  | Tower B | Super Structure | L21 | Finishes | False Ceiling
46309 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-05-10 | 2027-06-08 | Flooring & Dado | 100 | 0 |  | 2027-07-17 |  | 2027-08-16 |  | Tower B | Super Structure | L23 | Finishes | Flooring & Dado
46322 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-05-10 | 2027-05-21 | HVAC Ducting | 100 | 0 |  | 2027-07-17 |  | 2027-07-29 |  | Tower B | Super Structure | L24 | MEP | HVAC Ducting
46334 |  | Not Committed |  | 2027-05-10 | 2027-11-25 | L25-26 | 100 | 0 |  | 2027-07-17 |  | 2027-12-28
46334 |  | Not Committed |  | 2027-05-10 | 2027-11-25 | L25-26 | 100 | 0 |  | 2027-07-17 |  | 2027-12-28 |  |  |  |  | Finishes | Gypsum Plastering Works
46335 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-05-10 | 2027-05-21 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-07-17 |  | 2027-07-29 |  | Tower B | Super Structure | L25 | MEP | FPS 1st Fix - MEP & Finishes
46336 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-05-10 | 2027-05-18 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-07-17 |  | 2027-07-26 |  | Tower B | Super Structure | L25 | MEP | Electrical 1st Fixes
47116 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2027-05-10 | 2027-05-24 | False Ceiling | 100 | 0 |  | 2027-07-17 |  | 2027-07-31 |  | Tower B | Super Structure | L32 | Finishes | False Ceiling
47830 |  | Not Ready |  | 2027-01-08 | 2027-02-01 | MEP Rooms - Plaster & IPS | 100 | 0 |  | 2027-07-17 |  | 2027-08-10
47830 |  | Not Ready |  | 2027-01-08 | 2027-02-01 | MEP Rooms - Plaster & IPS | 100 | 0 |  | 2027-07-17 |  | 2027-08-10
47831 |  | Not Ready |  | 2027-01-08 | 2027-02-12 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2027-07-17 |  | 2027-08-21
47831 |  | Not Ready |  | 2027-01-08 | 2027-02-12 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2027-07-17 |  | 2027-08-21
47304 |  | Not Committed |  | 2027-04-22 | 2027-05-31 | MEP 1st Fixes | 100 | 0 |  | 2027-07-19 |  | 2027-08-25
47305 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-04-22 | 2027-04-29 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-07-19 |  | 2027-07-27 |  | Tower B | Super Structure | L43 | MEP | FPS 1st Fix - MEP & Finishes
47306 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-04-22 | 2027-04-27 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2027-07-19 |  | 2027-07-24 |  | Tower B | Super Structure | L43 | MEP | Electrical 1st Fixes
47307 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2027-04-22 | 2027-04-29 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2027-07-19 |  | 2027-07-27 |  | Tower B | Super Structure | L43
47773 |  | Not Ready |  | 2027-04-07 | 2027-04-29 | Slab_NTA | 100 | 0 |  | 2027-07-19 |  | 2027-08-11
47773 |  | Not Ready |  | 2027-04-07 | 2027-04-29 | Slab_NTA | 100 | 0 |  | 2027-07-19 |  | 2027-08-11 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
46263 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-05-12 | 2027-05-20 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-07-20 |  | 2027-07-28 |  | Tower B | Super Structure | L20 | MEP | FPS 2nd Fix - MEP & Finishes
46264 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-05-12 | 2027-05-20 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-07-20 |  | 2027-07-28 |  | Tower B | Super Structure | L20 | MEP | Electrical 2nd Fix - MEP & Finishes
46265 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-05-12 | 2027-05-24 | FAPA Device Fixing | 100 | 0 |  | 2027-07-20 |  | 2027-07-31 |  | Tower B | Super Structure | L20
46265 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-05-12 | 2027-05-24 | FAPA Device Fixing | 100 | 0 |  | 2027-07-20 |  | 2027-07-31 |  | Tower B | Super Structure | L20
46265 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-05-12 | 2027-05-24 | FAPA Device Fixing | 100 | 0 |  | 2027-07-20 |  | 2027-07-31 |  | Tower B | Super Structure | L20
46265 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-05-12 | 2027-05-24 | FAPA Device Fixing | 100 | 0 |  | 2027-07-20 |  | 2027-07-31 |  | Tower B | Super Structure | L20
46266 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-05-12 | 2027-05-20 | HVAC Grill Fixing | 100 | 0 |  | 2027-07-20 |  | 2027-07-28 |  | Tower B | Super Structure | L20 | MEP | HVAC Grill Fixing
46867 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-06-10 | 2027-06-17 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-07-20 |  | 2027-07-28 |  | Tower B | Super Structure | L18 | MEP | FPS 2nd Fix - MEP & Finishes
46868 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-06-10 | 2027-06-17 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-07-20 |  | 2027-07-28 |  | Tower B | Super Structure | L18 | MEP | Electrical 2nd Fix - MEP & Finishes
46869 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2027-06-10 | 2027-06-15 | PHE Final Fixes | 100 | 0 |  | 2027-07-20 |  | 2027-07-26 |  | Tower B | Super Structure | L18
46883 |  | Not Committed |  | 2027-06-10 | 2027-07-05 | MEP final fix & Finishes | 100 | 0 |  | 2027-07-20 |  | 2027-08-12
46884 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2027-06-10 | 2027-06-23 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2027-07-20 |  | 2027-07-31 |  | Tower B | Super Structure | L19 | Finishes | Door & Window Fixing
46237 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-05-13 | 2027-05-21 | Final Painting | 100 | 0 |  | 2027-07-21 |  | 2027-07-29 |  | Tower B | Super Structure | L18 | Finishes | Final Painting
46237 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-05-13 | 2027-05-21 | Final Painting | 100 | 0 |  | 2027-07-21 |  | 2027-07-29 |  | Tower B | Super Structure | L18 | Finishes | Final Painting
46237 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-05-13 | 2027-05-21 | Final Painting | 100 | 0 |  | 2027-07-21 |  | 2027-07-29 |  | Tower B | Super Structure | L18 | Finishes | Final Painting
45583 | Tower B - Super Structure - Finishes & MEP - L44 to L45 | Not Ready | Partition Wall-Blockwork | 2027-04-26 | 2027-05-04 | Partition Walls | 100 | 0 |  | 2027-07-22 |  | 2027-07-30 |  | Tower B | Super Structure | L44
47169 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-05-15 | 2027-06-02 | Flooring & Dado works | 100 | 0 |  | 2027-07-23 |  | 2027-08-10 |  | Tower B | Super Structure | L35 | Finishes | Flooring & Dado
47277 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-09-03 | 2027-10-05 | Flooring & Dado works | 100 | 0 |  | 2027-07-23 |  | 2027-08-21 |  | Tower B | Super Structure | L41 | Finishes | Flooring & Dado
46252 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-05-18 | 2027-05-25 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-07-24 |  | 2027-08-02 |  | Tower B | Super Structure | L19 | MEP | Electrical
46337 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-05-19 | 2027-05-26 | FAPA Cabling | 100 | 0 |  | 2027-07-26 |  | 2027-08-03 |  | Tower B | Super Structure | L25
46870 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2027-06-16 | 2027-06-21 | Painting Works | 100 | 0 |  | 2027-07-26 |  | 2027-07-31 |  | Tower B | Super Structure | L18 | Finishes | Painting Works
47168 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2027-05-20 | 2027-05-27 | Door & Window Frame work | 100 | 0 |  | 2027-07-27 |  | 2027-08-04 |  | Tower B | Super Structure | L35 | Finishes | Door & Window Frame work
47184 |  | Not Committed |  | 2027-05-20 | 2027-07-09 | Finishes after 1st Fix | 100 | 0 |  | 2027-07-27 |  | 2027-09-18
47185 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2027-05-20 | 2027-05-31 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2027-07-27 |  | 2027-08-07 |  | Tower B | Super Structure | L36 | Finishes | Blockwork
47276 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2027-09-08 | 2027-09-15 | Door & Window Frame work | 100 | 0 |  | 2027-07-27 |  | 2027-08-04 |  | Tower B | Super Structure | L41 | Finishes | Door & Window Frame work
47291 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2027-04-30 | 2027-05-12 | Cement Plastering in wet areas | 100 | 0 |  | 2027-07-27 |  | 2027-08-07 |  | Tower B | Super Structure | L42
47308 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2027-04-30 | 2027-05-19 | Wet Area Waterproofing | 100 | 0 |  | 2027-07-27 |  | 2027-08-13 |  | Tower B | Super Structure | L43
46267 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-05-21 | 2027-05-28 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-07-28 |  | 2027-08-05 |  | Tower B | Super Structure | L20
47517 |  | Not Ready |  | 2027-06-14 | 2028-09-20 | External Development | 100 | 0 |  | 2027-07-28 |  | 2028-09-22
47517 |  | Not Ready |  | 2027-06-14 | 2028-09-20 | External Development | 100 | 0 |  | 2027-07-28 |  | 2028-09-22
47518 |  | Not Ready | External Development | 2027-06-14 | 2027-12-10 | Above Terrace MEP | 100 | 0 |  | 2027-07-28 |  | 2028-01-27
46294 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-05-22 | 2027-06-04 | False Ceiling | 100 | 0 |  | 2027-07-29 |  | 2027-08-12 |  | Tower B | Super Structure | L22 | Finishes | False Ceiling
46325 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-05-22 | 2027-06-19 | Flooring & Dado | 100 | 0 |  | 2027-07-29 |  | 2027-08-27 |  | Tower B | Super Structure | L24 | Finishes | Flooring & Dado
46338 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-05-22 | 2027-06-02 | HVAC Ducting | 100 | 0 |  | 2027-07-29 |  | 2027-08-10 |  | Tower B | Super Structure | L25 | MEP | HVAC Ducting
46350 |  | Not Committed |  | 2027-05-22 | 2027-12-01 | L26-27 | 100 | 0 |  | 2027-07-29 |  | 2028-01-03
46350 |  | Not Committed |  | 2027-05-22 | 2027-12-01 | L26-27 | 100 | 0 |  | 2027-07-29 |  | 2028-01-03 |  |  |  |  | Finishes | Gypsum Plastering Works
46351 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-05-22 | 2027-06-02 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-07-29 |  | 2027-08-10 |  | Tower B | Super Structure | L26 | MEP | FPS 1st Fix - MEP & Finishes
46352 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-05-22 | 2027-05-29 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-07-29 |  | 2027-08-06 |  | Tower B | Super Structure | L26 | MEP | Electrical 1st Fixes
47134 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2027-05-22 | 2027-06-04 | False Ceiling | 100 | 0 |  | 2027-07-29 |  | 2027-08-12 |  | Tower B | Super Structure | L33 | Finishes | False Ceiling
45584 | Tower B - Super Structure - Finishes & MEP - L44 to L45 | Not Ready | Partition Wall-Blockwork | 2027-05-05 | 2027-05-10 | Staircase Area | 100 | 0 |  | 2027-07-30 |  | 2027-08-05 |  | Tower B | Super Structure | L44
45646 | Tower B - Super Structure - Finishes & MEP - L43 to L44 | Not Ready | Gypsum Plastering Works | 2027-05-05 | 2027-06-03 | L43-44 | 100 | 0 |  | 2027-07-30 |  | 2027-08-28 |  | Tower B | Super Structure | L43 | Finishes | Gypsum Plastering Works
45646 | Tower B - Super Structure - Finishes & MEP - L43 to L44 | Not Ready | Gypsum Plastering Works | 2027-05-05 | 2027-06-03 | L43-44 | 100 | 0 |  | 2027-07-30 |  | 2027-08-28 |  | Tower B | Super Structure | L43
47784 |  | Not Ready |  | 2027-04-19 | 2027-05-06 | Slab_NTA | 100 | 0 |  | 2027-07-30 |  | 2027-08-17
47784 |  | Not Ready |  | 2027-04-19 | 2027-05-06 | Slab_NTA | 100 | 0 |  | 2027-07-30 |  | 2027-08-17 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
47796 |  | Not Ready |  | 2027-04-19 | 2027-05-06 | Slab_NTA | 100 | 0 |  | 2027-07-30 |  | 2027-08-17
47796 |  | Not Ready |  | 2027-04-19 | 2027-05-06 | Slab_NTA | 100 | 0 |  | 2027-07-30 |  | 2027-08-17 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
47797 |  | Not Committed |  | 2027-04-19 | 2027-05-12 | Pour 11 (PB-C to PB-K) | 100 | 0 |  | 2027-07-30 |  | 2027-08-23
47798 |  | Not Ready |  | 2027-04-19 | 2027-05-06 | Columns/ Walls_NTA | 100 | 0 |  | 2027-07-30 |  | 2027-08-17
47798 |  | Not Ready |  | 2027-04-19 | 2027-05-06 | Columns/ Walls_NTA | 100 | 0 |  | 2027-07-30 |  | 2027-08-17 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
45654 | Tower B - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2027-07-01 | 2027-07-08 | Jump platform installation | 100 | 0 |  | 2027-07-31 |  | 2027-08-09 |  | Tower B | Super Structure
45654 | Tower B - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2027-07-01 | 2027-07-08 | Jump platform installation | 100 | 0 |  | 2027-07-31 |  | 2027-08-09 |  | Tower B | Super Structure
45654 | Tower B - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2027-07-01 | 2027-07-08 | Jump platform installation | 100 | 0 |  | 2027-07-31 |  | 2027-08-09 |  | Tower B | Super Structure
46279 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-05-25 | 2027-06-01 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-07-31 |  | 2027-08-09 |  | Tower B | Super Structure | L21 | MEP | FPS 2nd Fix - MEP & Finishes
46280 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-05-25 | 2027-06-01 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-07-31 |  | 2027-08-09 |  | Tower B | Super Structure | L21 | MEP | Electrical 2nd Fix - MEP & Finishes
46281 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-05-25 | 2027-06-04 | FAPA Device Fixing | 100 | 0 |  | 2027-07-31 |  | 2027-08-12 |  | Tower B | Super Structure | L21
46281 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-05-25 | 2027-06-04 | FAPA Device Fixing | 100 | 0 |  | 2027-07-31 |  | 2027-08-12 |  | Tower B | Super Structure | L21
46281 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-05-25 | 2027-06-04 | FAPA Device Fixing | 100 | 0 |  | 2027-07-31 |  | 2027-08-12 |  | Tower B | Super Structure | L21
46281 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-05-25 | 2027-06-04 | FAPA Device Fixing | 100 | 0 |  | 2027-07-31 |  | 2027-08-12 |  | Tower B | Super Structure | L21
46282 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-05-25 | 2027-06-01 | HVAC Grill Fixing | 100 | 0 |  | 2027-07-31 |  | 2027-08-09 |  | Tower B | Super Structure | L21 | MEP | HVAC Grill Fixing
46885 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-06-24 | 2027-07-01 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-07-31 |  | 2027-08-09 |  | Tower B | Super Structure | L19 | MEP | FPS 2nd Fix - MEP & Finishes
46886 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-06-24 | 2027-07-01 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-07-31 |  | 2027-08-09 |  | Tower B | Super Structure | L19 | MEP | Electrical 2nd Fix - MEP & Finishes
46887 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2027-06-24 | 2027-06-29 | PHE Final Fixes | 100 | 0 |  | 2027-07-31 |  | 2027-08-06 |  | Tower B | Super Structure | L19
46901 |  | Not Committed |  | 2027-06-24 | 2027-07-19 | MEP final fix & Finishes | 100 | 0 |  | 2027-07-31 |  | 2027-08-24
46902 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2027-06-24 | 2027-07-07 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2027-07-31 |  | 2027-08-12 |  | Tower B | Super Structure | L20 | Finishes | Door & Window Fixing
46253 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-05-26 | 2027-06-02 | Final Painting | 100 | 0 |  | 2027-08-02 |  | 2027-08-10 |  | Tower B | Super Structure | L19 | Finishes | Final Painting
46253 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-05-26 | 2027-06-02 | Final Painting | 100 | 0 |  | 2027-08-02 |  | 2027-08-10 |  | Tower B | Super Structure | L19 | Finishes | Final Painting
46253 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-05-26 | 2027-06-02 | Final Painting | 100 | 0 |  | 2027-08-02 |  | 2027-08-10 |  | Tower B | Super Structure | L19 | Finishes | Final Painting
47451 | Tower B - Super Structure - Finishes & MEP - L38 to Terrace | Not Ready | Façade Works - MEP & Finishes | 2027-05-26 | 2027-06-17 | DGU Assembly Installation | 100 | 0 |  | 2027-08-02 |  | 2027-08-25 |  | Tower B | Super Structure | L38 | Façade | Façade Works
47452 | Tower B - Super Structure - Finishes & MEP - L38 to Terrace | Not Ready | Façade Works - MEP & Finishes | 2027-05-26 | 2027-07-05 | Installation of highly reflective metal sheet | 100 | 0 |  | 2027-08-02 |  | 2027-09-13 |  | Tower B | Super Structure | L38 | Façade | Façade Works
47453 | Tower B - Super Structure - Finishes & MEP - L38 to Terrace | Not Ready | Façade Works - MEP & Finishes | 2027-05-26 | 2027-06-17 | Fixing of Backlit Laminated Glass assembly & ACP Panels | 100 | 0 |  | 2027-08-02 |  | 2027-08-25 |  | Tower B | Super Structure | L38 | Façade | Façade Works
47454 | Tower B - Super Structure - Finishes & MEP - L38 to Terrace | Not Ready | Façade Works - MEP & Finishes | 2027-05-26 | 2027-06-17 | Fixing of Louvers | 100 | 0 |  | 2027-08-02 |  | 2027-08-25 |  | Tower B | Super Structure | L38 | Façade | Façade Works
47454 | Tower B - Super Structure - Finishes & MEP - L38 to Terrace | Not Ready | Façade Works - MEP & Finishes | 2027-05-26 | 2027-06-17 | Fixing of Louvers | 100 | 0 |  | 2027-08-02 |  | 2027-08-25 |  | Tower B | Super Structure | L38
45590 |  | Not Committed |  | 2027-06-22 | 2027-08-03 | Terrace Waterproofing | 100 | 0 |  | 2027-08-03 |  | 2027-09-16
45591 | Tower B - Super Structure - Finishes & MEP - Above Terrace | Not Ready | Waterproofing | 2027-06-22 | 2027-06-29 | Area clearance & preparation | 100 | 0 |  | 2027-08-03 |  | 2027-08-11 |  | Tower B | Super Structure
47187 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-05-28 | 2027-06-25 | Flooring & Dado works | 100 | 0 |  | 2027-08-04 |  | 2027-09-02 |  | Tower B | Super Structure | L36 | Finishes | Flooring & Dado
47295 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-09-16 | 2027-10-18 | Flooring & Dado works | 100 | 0 |  | 2027-08-04 |  | 2027-09-02 |  | Tower B | Super Structure | L42 | Finishes | Flooring & Dado
46268 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-05-29 | 2027-06-05 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-08-05 |  | 2027-08-13 |  | Tower B | Super Structure | L20 | MEP | Electrical
47322 |  | Not Committed |  | 2027-05-11 | 2027-06-17 | MEP 1st Fixes | 100 | 0 |  | 2027-08-05 |  | 2027-09-13
47323 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Apartment Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-05-11 | 2027-05-19 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-08-05 |  | 2027-08-13 |  | Tower B | Super Structure | L44 | MEP | FPS 1st Fix - MEP & Finishes
47324 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Apartment Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-05-11 | 2027-05-15 | Electrical 1st Fixes (Chase cutting, conduiting, back box fixing) | 100 | 0 |  | 2027-08-05 |  | 2027-08-11 |  | Tower B | Super Structure | L44 | MEP | Electrical 1st Fixes
47325 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Apartment Area | Not Ready | PHE 1st Fix - MEP & Finishes | 2027-05-11 | 2027-05-19 | PHE 1st Fixes (Pipe installations & Testing, Supply & Drainage) | 100 | 0 |  | 2027-08-05 |  | 2027-08-13 |  | Tower B | Super Structure | L44
47786 |  | Not Committed |  | 2027-04-24 | 2027-06-05 | Pour 8 (grid PB-B to PB-J) | 100 | 0 |  | 2027-08-05 |  | 2027-09-16
47787 |  | Not Ready |  | 2027-04-24 | 2027-05-12 | Columns/ Walls_NTA | 100 | 0 |  | 2027-08-05 |  | 2027-08-23
47787 |  | Not Ready |  | 2027-04-24 | 2027-05-12 | Columns/ Walls_NTA | 100 | 0 |  | 2027-08-05 |  | 2027-08-23 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
47788 |  | Not Ready |  | 2027-04-24 | 2027-05-19 | Staircase_NTA | 100 | 0 |  | 2027-08-05 |  | 2027-08-28
47788 |  | Not Ready |  | 2027-04-24 | 2027-05-19 | Staircase_NTA | 100 | 0 |  | 2027-08-05 |  | 2027-08-28 |  |  |  |  | RCC Sub Structure | Staircase & Ramp RCC Works
47799 |  | Not Ready |  | 2027-04-24 | 2027-05-12 | Slab_NTA (tie-beams) | 100 | 0 |  | 2027-08-05 |  | 2027-08-23
47799 |  | Not Ready |  | 2027-04-24 | 2027-05-12 | Slab_NTA (tie-beams) | 100 | 0 |  | 2027-08-05 |  | 2027-08-23 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
46353 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-05-31 | 2027-06-07 | FAPA Cabling | 100 | 0 |  | 2027-08-06 |  | 2027-08-14 |  | Tower B | Super Structure | L26
46888 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2027-06-30 | 2027-07-05 | Painting Works | 100 | 0 |  | 2027-08-06 |  | 2027-08-12 |  | Tower B | Super Structure | L19 | Finishes | Painting Works
47859 |  | Not Committed |  | 2027-12-07 | 2028-09-28 | External Balustrade System (EXT 401, 114, 110) | 100 | 0 |  | 2027-08-06 |  | 2028-06-05
47866 |  | Not Committed |  | 2027-12-07 | 2028-03-17 | P1 level | 100 | 0 |  | 2027-08-06 |  | 2027-11-19
47867 |  | Not Ready |  | 2027-12-07 | 2027-12-30 | RCC upstand | 100 | 0 |  | 2027-08-06 |  | 2027-08-30
47867 |  | Not Ready |  | 2027-12-07 | 2027-12-30 | RCC upstand | 100 | 0 |  | 2027-08-06 |  | 2027-08-30
47186 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2027-06-01 | 2027-06-08 | Door & Window Frame work | 100 | 0 |  | 2027-08-07 |  | 2027-08-16 |  | Tower B | Super Structure | L36 | Finishes | Door & Window Frame work
47202 |  | Not Committed |  | 2027-06-01 | 2027-07-21 | Finishes after 1st Fix | 100 | 0 |  | 2027-08-07 |  | 2027-09-30
47203 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2027-06-01 | 2027-06-11 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2027-08-07 |  | 2027-08-19 |  | Tower B | Super Structure | L37 | Finishes | Blockwork
47294 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2027-09-21 | 2027-09-28 | Door & Window Frame work | 100 | 0 |  | 2027-08-07 |  | 2027-08-16 |  | Tower B | Super Structure | L42 | Finishes | Door & Window Frame work
45655 | Tower B - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2027-07-09 | 2027-07-24 | Guide Rail Installation by rising platform (only car guide rails) | 100 | 0 |  | 2027-08-09 |  | 2027-08-25 |  | Tower B | Super Structure
45765 | Tower B - Super Structure - Finishes & MEP - L35 to Terrace | Not Ready |  | 2027-05-14 | 2027-06-07 | Electrical Rising Mains | 100 | 0 |  | 2027-08-09 |  | 2027-09-01 |  | Tower B | Super Structure | L35
46283 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-06-02 | 2027-06-09 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-08-09 |  | 2027-08-17 |  | Tower B | Super Structure | L21
46310 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-06-03 | 2027-06-16 | False Ceiling | 100 | 0 |  | 2027-08-10 |  | 2027-08-24 |  | Tower B | Super Structure | L23 | Finishes | False Ceiling
46341 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-06-03 | 2027-07-01 | Flooring & Dado | 100 | 0 |  | 2027-08-10 |  | 2027-09-09 |  | Tower B | Super Structure | L25 | Finishes | Flooring & Dado
46354 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-06-03 | 2027-06-14 | HVAC Ducting | 100 | 0 |  | 2027-08-10 |  | 2027-08-21 |  | Tower B | Super Structure | L26 | MEP | HVAC Ducting
46366 |  | Not Committed |  | 2027-06-03 | 2027-12-07 | L27-28 | 100 | 0 |  | 2027-08-10 |  | 2028-01-08
46366 |  | Not Committed |  | 2027-06-03 | 2027-12-07 | L27-28 | 100 | 0 |  | 2027-08-10 |  | 2028-01-08 |  |  |  |  | Finishes | Gypsum Plastering Works
46367 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-06-03 | 2027-06-14 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-08-10 |  | 2027-08-21 |  | Tower B | Super Structure | L27 | MEP | FPS 1st Fix - MEP & Finishes
46368 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-06-03 | 2027-06-10 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-08-10 |  | 2027-08-18 |  | Tower B | Super Structure | L27 | MEP | Electrical 1st Fixes
47152 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2027-06-03 | 2027-06-16 | False Ceiling | 100 | 0 |  | 2027-08-10 |  | 2027-08-24 |  | Tower B | Super Structure | L34 | Finishes | False Ceiling
47170 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2027-06-03 | 2027-06-16 | False Ceiling | 100 | 0 |  | 2027-08-10 |  | 2027-08-24 |  | Tower B | Super Structure | L35 | Finishes | False Ceiling
47313 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-09-29 | 2027-10-30 | Flooring & Dado works | 100 | 0 |  | 2027-08-10 |  | 2027-09-09 |  | Tower B | Super Structure | L43 | Finishes | Flooring & Dado
45592 | Tower B - Super Structure - Finishes & MEP - Above Terrace | Not Ready | Waterproofing | 2027-06-30 | 2027-08-03 | Waterproofing with approved MS | 100 | 0 |  | 2027-08-11 |  | 2027-09-16 |  | Tower B | Super Structure
46295 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-06-05 | 2027-06-12 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-08-12 |  | 2027-08-20 |  | Tower B | Super Structure | L22 | MEP | FPS 2nd Fix - MEP & Finishes
46296 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-06-05 | 2027-06-12 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-08-12 |  | 2027-08-20 |  | Tower B | Super Structure | L22 | MEP | Electrical 2nd Fix - MEP & Finishes
46297 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-06-05 | 2027-06-16 | FAPA Device Fixing | 100 | 0 |  | 2027-08-12 |  | 2027-08-24 |  | Tower B | Super Structure | L22
46297 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-06-05 | 2027-06-16 | FAPA Device Fixing | 100 | 0 |  | 2027-08-12 |  | 2027-08-24 |  | Tower B | Super Structure | L22
46297 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-06-05 | 2027-06-16 | FAPA Device Fixing | 100 | 0 |  | 2027-08-12 |  | 2027-08-24 |  | Tower B | Super Structure | L22
46297 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-06-05 | 2027-06-16 | FAPA Device Fixing | 100 | 0 |  | 2027-08-12 |  | 2027-08-24 |  | Tower B | Super Structure | L22
46298 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-06-05 | 2027-06-12 | HVAC Grill Fixing | 100 | 0 |  | 2027-08-12 |  | 2027-08-20 |  | Tower B | Super Structure | L22 | MEP | HVAC Grill Fixing
46903 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-07-08 | 2027-07-15 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-08-12 |  | 2027-08-20 |  | Tower B | Super Structure | L20 | MEP | FPS 2nd Fix - MEP & Finishes
46904 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-07-08 | 2027-07-15 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-08-12 |  | 2027-08-20 |  | Tower B | Super Structure | L20 | MEP | Electrical 2nd Fix - MEP & Finishes
46905 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2027-07-08 | 2027-07-13 | PHE Final Fixes | 100 | 0 |  | 2027-08-12 |  | 2027-08-18 |  | Tower B | Super Structure | L20
46919 |  | Not Committed |  | 2027-07-08 | 2027-08-02 | MEP final fix & Finishes | 100 | 0 |  | 2027-08-12 |  | 2027-09-06
46920 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2027-07-08 | 2027-07-21 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2027-08-12 |  | 2027-08-24 |  | Tower B | Super Structure | L21 | Finishes | Door & Window Fixing
46269 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-06-07 | 2027-06-14 | Final Painting | 100 | 0 |  | 2027-08-13 |  | 2027-08-21 |  | Tower B | Super Structure | L20 | Finishes | Final Painting
46269 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-06-07 | 2027-06-14 | Final Painting | 100 | 0 |  | 2027-08-13 |  | 2027-08-21 |  | Tower B | Super Structure | L20 | Finishes | Final Painting
46269 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-06-07 | 2027-06-14 | Final Painting | 100 | 0 |  | 2027-08-13 |  | 2027-08-21 |  | Tower B | Super Structure | L20 | Finishes | Final Painting
47309 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2027-05-20 | 2027-05-31 | Cement Plastering in wet areas | 100 | 0 |  | 2027-08-13 |  | 2027-08-25 |  | Tower B | Super Structure | L43
47312 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2027-10-04 | 2027-10-12 | Door & Window Frame work | 100 | 0 |  | 2027-08-13 |  | 2027-08-21 |  | Tower B | Super Structure | L43 | Finishes | Door & Window Frame work
47326 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Apartment Area | Not Ready | Wet Area Waterproofing - MEP & Finishes | 2027-05-20 | 2027-06-05 | Wet Area Waterproofing | 100 | 0 |  | 2027-08-13 |  | 2027-08-31 |  | Tower B | Super Structure | L44
45710 | Tower B - Super Structure - Finishes & MEP - MEP Service Floors | Not Ready |  | 2027-07-01 | 2027-11-23 | Outdoor Units Installations | 100 | 0 |  | 2027-08-14 |  | 2028-01-08 |  | Tower B | Super Structure
45711 | Tower B - Super Structure - Finishes & MEP - MEP Service Floors | Not Ready |  | 2027-07-01 | 2027-12-29 | Refrigeration & Condensation Piping Works | 100 | 0 |  | 2027-08-14 |  | 2028-02-14 |  | Tower B | Super Structure
47205 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-06-09 | 2027-07-07 | Flooring & Dado works | 100 | 0 |  | 2027-08-16 |  | 2027-09-15 |  | Tower B | Super Structure | L37 | Finishes | Flooring & Dado
45647 | Tower B - Super Structure - Finishes & MEP - L44 to L45 | Not Ready | Gypsum Plastering Works | 2027-05-24 | 2027-06-21 | L44-45 | 100 | 0 |  | 2027-08-17 |  | 2027-09-16 |  | Tower B | Super Structure | L44 | Finishes | Gypsum Plastering Works
45647 | Tower B - Super Structure - Finishes & MEP - L44 to L45 | Not Ready | Gypsum Plastering Works | 2027-05-24 | 2027-06-21 | L44-45 | 100 | 0 |  | 2027-08-17 |  | 2027-09-16 |  | Tower B | Super Structure | L44
46284 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-06-10 | 2027-06-17 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-08-17 |  | 2027-08-25 |  | Tower B | Super Structure | L21 | MEP | Electrical
47800 |  | Not Committed |  | 2027-05-07 | 2027-06-11 | Pour 12 (PB-03 to PB-06) | 100 | 0 |  | 2027-08-17 |  | 2027-09-23
47801 |  | Not Ready |  | 2027-05-07 | 2027-05-25 | Columns/ Walls_NTA | 100 | 0 |  | 2027-08-17 |  | 2027-09-03
47801 |  | Not Ready |  | 2027-05-07 | 2027-05-25 | Columns/ Walls_NTA | 100 | 0 |  | 2027-08-17 |  | 2027-09-03 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
47802 |  | Not Ready |  | 2027-05-07 | 2027-05-31 | Staircase_NTA | 100 | 0 |  | 2027-08-17 |  | 2027-09-10
47802 |  | Not Ready |  | 2027-05-07 | 2027-05-31 | Staircase_NTA | 100 | 0 |  | 2027-08-17 |  | 2027-09-10 |  |  |  |  | RCC Sub Structure | Staircase & Ramp RCC Works
47811 |  | Not Ready |  | 2027-05-07 | 2027-06-23 | P3 to P4 | 100 | 0 |  | 2027-08-17 |  | 2027-10-06
47811 |  | Not Ready |  | 2027-05-07 | 2027-06-23 | P3 to P4 | 100 | 0 |  | 2027-08-17 |  | 2027-10-06
47811 |  | Not Ready |  | 2027-05-07 | 2027-06-23 | P3 to P4 | 100 | 0 |  | 2027-08-17 |  | 2027-10-06
46369 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-06-11 | 2027-06-18 | FAPA Cabling | 100 | 0 |  | 2027-08-18 |  | 2027-08-26 |  | Tower B | Super Structure | L27
46906 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2027-07-14 | 2027-07-19 | Painting Works | 100 | 0 |  | 2027-08-18 |  | 2027-08-24 |  | Tower B | Super Structure | L20 | Finishes | Painting Works
47204 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2027-06-12 | 2027-06-19 | Door & Window Frame work | 100 | 0 |  | 2027-08-19 |  | 2027-08-27 |  | Tower B | Super Structure | L37 | Finishes | Door & Window Frame work
47220 |  | Not Committed |  | 2027-06-12 | 2027-08-02 | Finishes after 1st Fix | 100 | 0 |  | 2027-08-19 |  | 2027-10-14
47221 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2027-06-12 | 2027-06-23 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2027-08-19 |  | 2027-08-31 |  | Tower B | Super Structure | L38 | Finishes | Blockwork
45684 | Tower B - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2027-07-13 | 2027-07-29 | Pumps & Accessories Installation | 100 | 0 |  | 2027-08-20 |  | 2027-09-08 |  | Tower B | Super Structure
46051 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2027-07-21 | 2027-07-26 | Lobby Blockwork | 100 | 0 |  | 2027-08-20 |  | 2027-08-26 |  | Tower B | Super Structure | L7 | Finishes | Blockwork
46053 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-07-21 | 2027-08-18 | Flooring & Dado | 100 | 0 |  | 2027-08-20 |  | 2027-09-21 |  | Tower B | Super Structure | L7 | Finishes | Flooring & Dado
46299 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-06-14 | 2027-06-21 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-08-20 |  | 2027-08-28 |  | Tower B | Super Structure | L22
46326 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-06-15 | 2027-06-28 | False Ceiling | 100 | 0 |  | 2027-08-21 |  | 2027-09-06 |  | Tower B | Super Structure | L24 | Finishes | False Ceiling
46357 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-06-15 | 2027-07-13 | Flooring & Dado | 100 | 0 |  | 2027-08-21 |  | 2027-09-22 |  | Tower B | Super Structure | L26 | Finishes | Flooring & Dado
46370 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-06-15 | 2027-06-25 | HVAC Ducting | 100 | 0 |  | 2027-08-21 |  | 2027-09-02 |  | Tower B | Super Structure | L27 | MEP | HVAC Ducting
46382 |  | Not Committed |  | 2027-06-15 | 2027-12-13 | L28-29 | 100 | 0 |  | 2027-08-21 |  | 2028-01-14
46382 |  | Not Committed |  | 2027-06-15 | 2027-12-13 | L28-29 | 100 | 0 |  | 2027-08-21 |  | 2028-01-14 |  |  |  |  | Finishes | Gypsum Plastering Works
46383 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-06-15 | 2027-06-25 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-08-21 |  | 2027-09-02 |  | Tower B | Super Structure | L28 | MEP | FPS 1st Fix - MEP & Finishes
46384 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-06-15 | 2027-06-22 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-08-21 |  | 2027-08-30 |  | Tower B | Super Structure | L28 | MEP | Electrical 1st Fixes
47278 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2027-10-06 | 2027-10-20 | False Ceiling | 100 | 0 |  | 2027-08-21 |  | 2027-09-06 |  | Tower B | Super Structure | L41 | Finishes | False Ceiling
47832 |  | Not Ready |  | 2027-02-13 | 2027-03-19 | Staircase Finishes | 100 | 0 |  | 2027-08-21 |  | 2027-09-28
47832 |  | Not Ready |  | 2027-02-13 | 2027-03-19 | Staircase Finishes | 100 | 0 |  | 2027-08-21 |  | 2027-09-28
47789 |  | Not Ready |  | 2027-05-13 | 2027-06-05 | Slab_NTA | 100 | 0 |  | 2027-08-23 |  | 2027-09-16
47789 |  | Not Ready |  | 2027-05-13 | 2027-06-05 | Slab_NTA | 100 | 0 |  | 2027-08-23 |  | 2027-09-16 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
47790 |  | Not Committed |  | 2027-05-13 | 2027-06-11 | Pour 9 (grid PB-06 to PB-C) | 100 | 0 |  | 2027-08-23 |  | 2027-09-23
47791 |  | Not Ready |  | 2027-05-13 | 2027-05-31 | Columns/ Walls_NTA | 100 | 0 |  | 2027-08-23 |  | 2027-09-10
47791 |  | Not Ready |  | 2027-05-13 | 2027-05-31 | Columns/ Walls_NTA | 100 | 0 |  | 2027-08-23 |  | 2027-09-10 |  |  |  |  | RCC Sub Structure | RCC Works - Vertical
45659 | Tower B - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2027-07-24 | 2027-08-27 | Completion of Electrical Works | 100 | 0 |  | 2027-08-24 |  | 2027-09-30 |  | Tower B | Super Structure
45659 | Tower B - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2027-07-24 | 2027-08-27 | Completion of Electrical Works | 100 | 0 |  | 2027-08-24 |  | 2027-09-30 |  | Tower B | Super Structure
46311 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-06-17 | 2027-06-24 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-08-24 |  | 2027-09-01 |  | Tower B | Super Structure | L23 | MEP | FPS 2nd Fix - MEP & Finishes
46312 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-06-17 | 2027-06-24 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-08-24 |  | 2027-09-01 |  | Tower B | Super Structure | L23 | MEP | Electrical 2nd Fix - MEP & Finishes
46313 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-06-17 | 2027-06-28 | FAPA Device Fixing | 100 | 0 |  | 2027-08-24 |  | 2027-09-06 |  | Tower B | Super Structure | L23
46313 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-06-17 | 2027-06-28 | FAPA Device Fixing | 100 | 0 |  | 2027-08-24 |  | 2027-09-06 |  | Tower B | Super Structure | L23
46313 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-06-17 | 2027-06-28 | FAPA Device Fixing | 100 | 0 |  | 2027-08-24 |  | 2027-09-06 |  | Tower B | Super Structure | L23
46313 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-06-17 | 2027-06-28 | FAPA Device Fixing | 100 | 0 |  | 2027-08-24 |  | 2027-09-06 |  | Tower B | Super Structure | L23
46314 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-06-17 | 2027-06-24 | HVAC Grill Fixing | 100 | 0 |  | 2027-08-24 |  | 2027-09-01 |  | Tower B | Super Structure | L23 | MEP | HVAC Grill Fixing
46921 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-07-22 | 2027-07-29 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-08-24 |  | 2027-09-01 |  | Tower B | Super Structure | L21 | MEP | FPS 2nd Fix - MEP & Finishes
46922 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-07-22 | 2027-07-29 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-08-24 |  | 2027-09-01 |  | Tower B | Super Structure | L21 | MEP | Electrical 2nd Fix - MEP & Finishes
46923 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2027-07-22 | 2027-07-27 | PHE Final Fixes | 100 | 0 |  | 2027-08-24 |  | 2027-08-30 |  | Tower B | Super Structure | L21
46937 |  | Not Committed |  | 2027-07-22 | 2027-08-16 | MEP final fix & Finishes | 100 | 0 |  | 2027-08-24 |  | 2027-09-18
46938 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2027-07-22 | 2027-08-04 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2027-08-24 |  | 2027-09-06 |  | Tower B | Super Structure | L22 | Finishes | Door & Window Fixing
45656 | Tower B - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2027-07-26 | 2027-08-10 | Guide Rail installation for CWT (up to LMR) | 100 | 0 |  | 2027-08-25 |  | 2027-09-11 |  | Tower B | Super Structure
45656 | Tower B - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2027-07-26 | 2027-08-10 | Guide Rail installation for CWT (up to LMR) | 100 | 0 |  | 2027-08-25 |  | 2027-09-11 |  | Tower B | Super Structure
46285 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-06-18 | 2027-06-25 | Final Painting | 100 | 0 |  | 2027-08-25 |  | 2027-09-02 |  | Tower B | Super Structure | L21 | Finishes | Final Painting
46285 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-06-18 | 2027-06-25 | Final Painting | 100 | 0 |  | 2027-08-25 |  | 2027-09-02 |  | Tower B | Super Structure | L21 | Finishes | Final Painting
46285 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-06-18 | 2027-06-25 | Final Painting | 100 | 0 |  | 2027-08-25 |  | 2027-09-02 |  | Tower B | Super Structure | L21 | Finishes | Final Painting
47455 | Tower B - Super Structure - Finishes & MEP - L38 to Terrace | Not Ready | Façade Works - MEP & Finishes | 2027-06-18 | 2027-07-10 | Accessories & Alignment | 100 | 0 |  | 2027-08-25 |  | 2027-09-20 |  | Tower B | Super Structure | L38 | Façade | Façade Works
47455 | Tower B - Super Structure - Finishes & MEP - L38 to Terrace | Not Ready | Façade Works - MEP & Finishes | 2027-06-18 | 2027-07-10 | Accessories & Alignment | 100 | 0 |  | 2027-08-25 |  | 2027-09-20 |  | Tower B | Super Structure | L38
46052 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2027-07-27 | 2027-08-06 | Lobby Plastering | 100 | 0 |  | 2027-08-26 |  | 2027-09-08 |  | Tower B | Super Structure | L7 | Finishes | Lobby Plastering
46067 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2027-07-27 | 2027-07-31 | Lobby Blockwork | 100 | 0 |  | 2027-08-26 |  | 2027-09-01 |  | Tower B | Super Structure | L8 | Finishes | Blockwork
46069 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-07-27 | 2027-08-24 | Flooring & Dado | 100 | 0 |  | 2027-08-26 |  | 2027-09-27 |  | Tower B | Super Structure | L8 | Finishes | Flooring & Dado
47223 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-06-21 | 2027-07-19 | Flooring & Dado works | 100 | 0 |  | 2027-08-27 |  | 2027-09-28 |  | Tower B | Super Structure | L38 | Finishes | Flooring & Dado
46300 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-06-22 | 2027-06-29 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-08-28 |  | 2027-09-07 |  | Tower B | Super Structure | L22 | MEP | Electrical
47792 |  | Not Ready |  | 2027-05-20 | 2027-06-11 | Slab_NTA | 100 | 0 |  | 2027-08-28 |  | 2027-09-23
47792 |  | Not Ready |  | 2027-05-20 | 2027-06-11 | Slab_NTA | 100 | 0 |  | 2027-08-28 |  | 2027-09-23 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
46385 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-06-23 | 2027-06-30 | FAPA Cabling | 100 | 0 |  | 2027-08-30 |  | 2027-09-08 |  | Tower B | Super Structure | L28
46924 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2027-07-28 | 2027-08-02 | Painting Works | 100 | 0 |  | 2027-08-30 |  | 2027-09-06 |  | Tower B | Super Structure | L21 | Finishes | Painting Works
47868 |  | Not Ready |  | 2027-12-31 | 2028-01-17 | Drainage pipe | 100 | 0 |  | 2027-08-30 |  | 2027-09-18
47868 |  | Not Ready |  | 2027-12-31 | 2028-01-17 | Drainage pipe | 100 | 0 |  | 2027-08-30 |  | 2027-09-18
47872 |  | Not Committed |  | 2027-12-31 | 2028-04-10 | P2 level | 100 | 0 |  | 2027-08-30 |  | 2027-12-13
47873 |  | Not Ready |  | 2027-12-31 | 2028-01-22 | RCC upstand | 100 | 0 |  | 2027-08-30 |  | 2027-09-24
47873 |  | Not Ready |  | 2027-12-31 | 2028-01-22 | RCC upstand | 100 | 0 |  | 2027-08-30 |  | 2027-09-24
47222 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2027-06-24 | 2027-07-01 | Door & Window Frame work | 100 | 0 |  | 2027-08-31 |  | 2027-09-09 |  | Tower B | Super Structure | L38 | Finishes | Door & Window Frame work
47238 |  | Not Committed |  | 2027-06-24 | 2027-08-13 | Finishes after 1st Fix | 100 | 0 |  | 2027-08-31 |  | 2027-10-26
47239 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2027-06-24 | 2027-07-05 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2027-08-31 |  | 2027-09-13 |  | Tower B | Super Structure | L39 | Finishes | Blockwork
47327 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Apartment Area | Not Ready | Cement Plastering in Wet Areas - MEP & Finishes | 2027-06-07 | 2027-06-17 | Cement Plastering in wet areas | 100 | 0 |  | 2027-08-31 |  | 2027-09-13 |  | Tower B | Super Structure | L44
45598 | Tower B - Super Structure - Finishes & MEP | Not Ready | MEP Shaft Masonry | 2027-06-08 | 2027-07-06 | L35-L45 | 100 | 0 |  | 2027-09-01 |  | 2027-10-04 |  | Tower B | Super Structure
45685 | Tower B - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2027-07-24 | 2027-08-27 | Exhaust Piping & Insulation | 100 | 0 |  | 2027-09-01 |  | 2027-10-11 |  | Tower B | Super Structure
46068 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2027-08-02 | 2027-08-12 | Lobby Plastering | 100 | 0 |  | 2027-09-01 |  | 2027-09-14 |  | Tower B | Super Structure | L8 | Finishes | Lobby Plastering
46083 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2027-08-02 | 2027-08-06 | Lobby Blockwork | 100 | 0 |  | 2027-09-01 |  | 2027-09-08 |  | Tower B | Super Structure | L9 | Finishes | Blockwork
46085 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-08-02 | 2027-08-30 | Flooring & Dado | 100 | 0 |  | 2027-09-01 |  | 2027-10-04 |  | Tower B | Super Structure | L9 | Finishes | Flooring & Dado
46315 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-06-25 | 2027-07-02 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-09-01 |  | 2027-09-10 |  | Tower B | Super Structure | L23
46342 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-06-26 | 2027-07-09 | False Ceiling | 100 | 0 |  | 2027-09-02 |  | 2027-09-18 |  | Tower B | Super Structure | L25 | Finishes | False Ceiling
46373 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-06-26 | 2027-07-24 | Flooring & Dado | 100 | 0 |  | 2027-09-02 |  | 2027-10-05 |  | Tower B | Super Structure | L27 | Finishes | Flooring & Dado
46386 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-06-26 | 2027-07-07 | HVAC Ducting | 100 | 0 |  | 2027-09-02 |  | 2027-09-15 |  | Tower B | Super Structure | L28 | MEP | HVAC Ducting
46398 |  | Not Committed |  | 2027-06-26 | 2027-12-18 | L29-30 | 100 | 0 |  | 2027-09-02 |  | 2028-01-20
46398 |  | Not Committed |  | 2027-06-26 | 2027-12-18 | L29-30 | 100 | 0 |  | 2027-09-02 |  | 2028-01-20 |  |  |  |  | Finishes | Gypsum Plastering Works
46399 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-06-26 | 2027-07-07 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-09-02 |  | 2027-09-15 |  | Tower B | Super Structure | L29 | MEP | FPS 1st Fix - MEP & Finishes
46400 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-06-26 | 2027-07-03 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-09-02 |  | 2027-09-11 |  | Tower B | Super Structure | L29 | MEP | Electrical 1st Fixes
47188 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2027-06-26 | 2027-07-09 | False Ceiling | 100 | 0 |  | 2027-09-02 |  | 2027-09-18 |  | Tower B | Super Structure | L36 | Finishes | False Ceiling
47296 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2027-10-19 | 2027-11-02 | False Ceiling | 100 | 0 |  | 2027-09-02 |  | 2027-09-18 |  | Tower B | Super Structure | L42 | Finishes | False Ceiling
47803 |  | Not Ready |  | 2027-05-26 | 2027-06-11 | Slab_NTA | 100 | 0 |  | 2027-09-03 |  | 2027-09-23
47803 |  | Not Ready |  | 2027-05-26 | 2027-06-11 | Slab_NTA | 100 | 0 |  | 2027-09-03 |  | 2027-09-23 |  |  |  |  | RCC Sub Structure | RCC Works - Slab
46327 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-06-29 | 2027-07-06 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-09-06 |  | 2027-09-14 |  | Tower B | Super Structure | L24 | MEP | FPS 2nd Fix - MEP & Finishes
46328 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-06-29 | 2027-07-06 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-09-06 |  | 2027-09-14 |  | Tower B | Super Structure | L24 | MEP | Electrical 2nd Fix - MEP & Finishes
46329 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-06-29 | 2027-07-09 | FAPA Device Fixing | 100 | 0 |  | 2027-09-06 |  | 2027-09-18 |  | Tower B | Super Structure | L24
46329 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-06-29 | 2027-07-09 | FAPA Device Fixing | 100 | 0 |  | 2027-09-06 |  | 2027-09-18 |  | Tower B | Super Structure | L24
46329 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-06-29 | 2027-07-09 | FAPA Device Fixing | 100 | 0 |  | 2027-09-06 |  | 2027-09-18 |  | Tower B | Super Structure | L24
46329 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-06-29 | 2027-07-09 | FAPA Device Fixing | 100 | 0 |  | 2027-09-06 |  | 2027-09-18 |  | Tower B | Super Structure | L24
46330 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-06-29 | 2027-07-06 | HVAC Grill Fixing | 100 | 0 |  | 2027-09-06 |  | 2027-09-14 |  | Tower B | Super Structure | L24 | MEP | HVAC Grill Fixing
46939 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-08-05 | 2027-08-12 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-09-06 |  | 2027-09-14 |  | Tower B | Super Structure | L22 | MEP | FPS 2nd Fix - MEP & Finishes
46940 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-08-05 | 2027-08-12 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-09-06 |  | 2027-09-14 |  | Tower B | Super Structure | L22 | MEP | Electrical 2nd Fix - MEP & Finishes
46941 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2027-08-05 | 2027-08-10 | PHE Final Fixes | 100 | 0 |  | 2027-09-06 |  | 2027-09-11 |  | Tower B | Super Structure | L22
46955 |  | Not Committed |  | 2027-08-05 | 2027-08-30 | MEP final fix & Finishes | 100 | 0 |  | 2027-09-06 |  | 2027-09-30
46956 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2027-08-05 | 2027-08-18 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2027-09-06 |  | 2027-09-18 |  | Tower B | Super Structure | L23 | Finishes | Door & Window Fixing
47339 |  | Not Ready |  | 2027-10-21 | 2028-08-19 | Staircase Finishes | 100 | 0 |  | 2027-09-06 |  | 2028-07-10
47339 |  | Not Ready |  | 2027-10-21 | 2028-08-19 | Staircase Finishes | 100 | 0 |  | 2027-09-06 |  | 2028-07-10
47354 |  | Not Committed |  | 2027-10-21 | 2028-03-13 | L7-15 | 100 | 0 |  | 2027-09-06 |  | 2028-01-31
47354 |  | Not Committed |  | 2027-10-21 | 2028-03-13 | L7-15 | 100 | 0 |  | 2027-09-06 |  | 2028-01-31
47355 | Tower B - Super Structure - Finishes & MEP - L7 to L15 | Not Ready | Staircase Finishes - MEP & Finishes | 2027-10-21 | 2027-12-13 | Staircase Wall & Ceiling finishes | 100 | 0 |  | 2027-09-06 |  | 2027-11-02 |  | Tower B | Super Structure | L7
46301 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-06-30 | 2027-07-07 | Final Painting | 100 | 0 |  | 2027-09-07 |  | 2027-09-15 |  | Tower B | Super Structure | L22 | Finishes | Final Painting
46301 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-06-30 | 2027-07-07 | Final Painting | 100 | 0 |  | 2027-09-07 |  | 2027-09-15 |  | Tower B | Super Structure | L22 | Finishes | Final Painting
46301 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-06-30 | 2027-07-07 | Final Painting | 100 | 0 |  | 2027-09-07 |  | 2027-09-15 |  | Tower B | Super Structure | L22 | Finishes | Final Painting
46084 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2027-08-07 | 2027-08-18 | Lobby Plastering | 100 | 0 |  | 2027-09-08 |  | 2027-09-21 |  | Tower B | Super Structure | L9 | Finishes | Lobby Plastering
46099 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2027-08-07 | 2027-08-12 | Lobby Blockwork | 100 | 0 |  | 2027-09-08 |  | 2027-09-14 |  | Tower B | Super Structure | L10 | Finishes | Blockwork
46101 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-08-07 | 2027-09-06 | Flooring & Dado | 100 | 0 |  | 2027-09-08 |  | 2027-10-11 |  | Tower B | Super Structure | L10 | Finishes | Flooring & Dado
47241 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-07-02 | 2027-07-30 | Flooring & Dado works | 100 | 0 |  | 2027-09-09 |  | 2027-10-12 |  | Tower B | Super Structure | L39 | Finishes | Flooring & Dado
47314 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2027-11-01 | 2027-11-13 | False Ceiling | 100 | 0 |  | 2027-09-09 |  | 2027-09-24 |  | Tower B | Super Structure | L43 | Finishes | False Ceiling
47331 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-10-13 | 2027-11-11 | Flooring & Dado works | 100 | 0 |  | 2027-09-09 |  | 2027-10-12 |  | Tower B | Super Structure | L44 | Finishes | Flooring & Dado
47817 |  | Not Ready |  | 2027-03-08 | 2027-05-19 | GF to P1 | 100 | 0 |  | 2027-09-09 |  | 2027-11-23
47817 |  | Not Ready |  | 2027-03-08 | 2027-05-19 | GF to P1 | 100 | 0 |  | 2027-09-09 |  | 2027-11-23
47817 |  | Not Ready |  | 2027-03-08 | 2027-05-19 | GF to P1 | 100 | 0 |  | 2027-09-09 |  | 2027-11-23
47833 |  | Not Committed |  | 2027-03-03 | 2027-06-18 | B1 to GF | 100 | 0 |  | 2027-09-09 |  | 2027-12-29
47833 |  | Not Committed |  | 2027-03-03 | 2027-06-18 | B1 to GF | 100 | 0 |  | 2027-09-09 |  | 2027-12-29
47833 |  | Not Committed |  | 2027-03-03 | 2027-06-18 | B1 to GF | 100 | 0 |  | 2027-09-09 |  | 2027-12-29
47834 |  | Not Ready |  | 2027-03-03 | 2027-04-07 | VDF Flooring/ IPS in MEP Rooms | 100 | 0 |  | 2027-09-09 |  | 2027-10-18
46316 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-07-03 | 2027-07-10 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-09-10 |  | 2027-09-20 |  | Tower B | Super Structure | L23 | MEP | Electrical
45658 | Tower B - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2027-08-11 | 2027-08-27 | Roping & Car Fixing | 100 | 0 |  | 2027-09-11 |  | 2027-09-30 |  | Tower B | Super Structure
45658 | Tower B - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2027-08-11 | 2027-08-27 | Roping & Car Fixing | 100 | 0 |  | 2027-09-11 |  | 2027-09-30 |  | Tower B | Super Structure
46401 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-07-05 | 2027-07-12 | FAPA Cabling | 100 | 0 |  | 2027-09-11 |  | 2027-09-21 |  | Tower B | Super Structure | L29
46942 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2027-08-11 | 2027-08-16 | Painting Works | 100 | 0 |  | 2027-09-11 |  | 2027-09-18 |  | Tower B | Super Structure | L22 | Finishes | Painting Works
47240 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2027-07-06 | 2027-07-13 | Door & Window Frame work | 100 | 0 |  | 2027-09-13 |  | 2027-09-22 |  | Tower B | Super Structure | L39 | Finishes | Door & Window Frame work
47256 |  | Not Committed |  | 2027-07-06 | 2027-08-25 | Finishes after 1st Fix | 100 | 0 |  | 2027-09-13 |  | 2027-11-08
47257 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Apartment Area | Not Ready | Blockwork & Gypsym Works - MEP & Finishes | 2027-07-06 | 2027-07-16 | Balance Blockwork & Gypsum Works | 100 | 0 |  | 2027-09-13 |  | 2027-09-25 |  | Tower B | Super Structure | L40 | Finishes | Blockwork
47330 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2027-10-16 | 2027-10-23 | Door & Window Frame work | 100 | 0 |  | 2027-09-13 |  | 2027-09-22 |  | Tower B | Super Structure | L44 | Finishes | Door & Window Frame work
46054 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-08-13 | 2027-08-26 | False Ceiling | 100 | 0 |  | 2027-09-14 |  | 2027-09-29 |  | Tower B | Super Structure | L7 | Finishes | False Ceiling
46100 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2027-08-13 | 2027-08-24 | Lobby Plastering | 100 | 0 |  | 2027-09-14 |  | 2027-09-27 |  | Tower B | Super Structure | L10 | Finishes | Lobby Plastering
46115 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2027-08-13 | 2027-08-18 | Lobby Blockwork | 100 | 0 |  | 2027-09-14 |  | 2027-09-21 |  | Tower B | Super Structure | L11 | Finishes | Blockwork
46117 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-08-13 | 2027-09-11 | Flooring & Dado | 100 | 0 |  | 2027-09-14 |  | 2027-10-16 |  | Tower B | Super Structure | L11 | Finishes | Flooring & Dado
46331 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-07-07 | 2027-07-14 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-09-14 |  | 2027-09-23 |  | Tower B | Super Structure | L24
46358 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-07-08 | 2027-07-21 | False Ceiling | 100 | 0 |  | 2027-09-15 |  | 2027-09-30 |  | Tower B | Super Structure | L26 | Finishes | False Ceiling
46389 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-07-08 | 2027-08-05 | Flooring & Dado | 100 | 0 |  | 2027-09-15 |  | 2027-10-18 |  | Tower B | Super Structure | L28 | Finishes | Flooring & Dado
46402 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-07-08 | 2027-07-19 | HVAC Ducting | 100 | 0 |  | 2027-09-15 |  | 2027-09-28 |  | Tower B | Super Structure | L29 | MEP | HVAC Ducting
46414 |  | Not Committed |  | 2027-07-08 | 2027-12-24 | L30-31 | 100 | 0 |  | 2027-09-15 |  | 2028-01-27
46414 |  | Not Committed |  | 2027-07-08 | 2027-12-24 | L30-31 | 100 | 0 |  | 2027-09-15 |  | 2028-01-27 |  |  |  |  | Finishes | Gypsum Plastering Works
46415 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-07-08 | 2027-07-19 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-09-15 |  | 2027-09-28 |  | Tower B | Super Structure | L30 | MEP | FPS 1st Fix - MEP & Finishes
46416 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-07-08 | 2027-07-15 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-09-15 |  | 2027-09-24 |  | Tower B | Super Structure | L30 | MEP | Electrical 1st Fixes
47206 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2027-07-08 | 2027-07-21 | False Ceiling | 100 | 0 |  | 2027-09-15 |  | 2027-09-30 |  | Tower B | Super Structure | L37 | Finishes | False Ceiling
46343 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-07-10 | 2027-07-17 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-09-18 |  | 2027-09-27 |  | Tower B | Super Structure | L25 | MEP | FPS 2nd Fix - MEP & Finishes
46344 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-07-10 | 2027-07-17 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-09-18 |  | 2027-09-27 |  | Tower B | Super Structure | L25 | MEP | Electrical 2nd Fix - MEP & Finishes
46345 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-07-10 | 2027-07-21 | FAPA Device Fixing | 100 | 0 |  | 2027-09-18 |  | 2027-09-30 |  | Tower B | Super Structure | L25
46345 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-07-10 | 2027-07-21 | FAPA Device Fixing | 100 | 0 |  | 2027-09-18 |  | 2027-09-30 |  | Tower B | Super Structure | L25
46345 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-07-10 | 2027-07-21 | FAPA Device Fixing | 100 | 0 |  | 2027-09-18 |  | 2027-09-30 |  | Tower B | Super Structure | L25
46345 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-07-10 | 2027-07-21 | FAPA Device Fixing | 100 | 0 |  | 2027-09-18 |  | 2027-09-30 |  | Tower B | Super Structure | L25
46346 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-07-10 | 2027-07-17 | HVAC Grill Fixing | 100 | 0 |  | 2027-09-18 |  | 2027-09-27 |  | Tower B | Super Structure | L25 | MEP | HVAC Grill Fixing
46957 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-08-19 | 2027-08-26 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-09-18 |  | 2027-09-27 |  | Tower B | Super Structure | L23 | MEP | FPS 2nd Fix - MEP & Finishes
46958 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-08-19 | 2027-08-26 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-09-18 |  | 2027-09-27 |  | Tower B | Super Structure | L23 | MEP | Electrical 2nd Fix - MEP & Finishes
46959 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2027-08-19 | 2027-08-24 | PHE Final Fixes | 100 | 0 |  | 2027-09-18 |  | 2027-09-24 |  | Tower B | Super Structure | L23
46973 |  | Not Committed |  | 2027-08-19 | 2027-09-14 | MEP final fix & Finishes | 100 | 0 |  | 2027-09-18 |  | 2027-10-14
46974 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2027-08-19 | 2027-09-01 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2027-09-18 |  | 2027-09-30 |  | Tower B | Super Structure | L24 | Finishes | Door & Window Fixing
47869 |  | Not Ready |  | 2028-01-18 | 2028-02-04 | SS work | 100 | 0 |  | 2027-09-18 |  | 2027-10-07
46317 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-07-12 | 2027-07-19 | Final Painting | 100 | 0 |  | 2027-09-20 |  | 2027-09-28 |  | Tower B | Super Structure | L23 | Finishes | Final Painting
46317 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-07-12 | 2027-07-19 | Final Painting | 100 | 0 |  | 2027-09-20 |  | 2027-09-28 |  | Tower B | Super Structure | L23 | Finishes | Final Painting
46317 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-07-12 | 2027-07-19 | Final Painting | 100 | 0 |  | 2027-09-20 |  | 2027-09-28 |  | Tower B | Super Structure | L23 | Finishes | Final Painting
47383 |  | Not Committed |  | 2027-07-12 | 2028-02-19 | Podium Floors at Tower periphery | 100 | 0 |  | 2027-09-20 |  | 2028-04-29
47399 |  | Not Committed |  | 2027-07-12 | 2027-09-14 | P3-L7 | 100 | 0 |  | 2027-09-20 |  | 2027-11-26
47400 | Tower B - Super Structure - Finishes & MEP - P3 to L7 | Not Ready | Façade Works - MEP & Finishes | 2027-07-12 | 2027-08-14 | Al. Frame section (Mullion & Transom) Installation | 100 | 0 |  | 2027-09-20 |  | 2027-10-27 |  | Tower B | Super Structure |  | Façade | Façade Works
46070 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-08-19 | 2027-09-01 | False Ceiling | 100 | 0 |  | 2027-09-21 |  | 2027-10-06 |  | Tower B | Super Structure | L8 | Finishes | False Ceiling
46116 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2027-08-19 | 2027-08-30 | Lobby Plastering | 100 | 0 |  | 2027-09-21 |  | 2027-10-04 |  | Tower B | Super Structure | L11 | Finishes | Lobby Plastering
46131 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2027-08-19 | 2027-08-24 | Lobby Blockwork | 100 | 0 |  | 2027-09-21 |  | 2027-09-27 |  | Tower B | Super Structure | L12 | Finishes | Blockwork
46133 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-08-19 | 2027-09-18 | Flooring & Dado | 100 | 0 |  | 2027-09-21 |  | 2027-10-22 |  | Tower B | Super Structure | L12 | Finishes | Flooring & Dado
47259 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Apartment Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-07-14 | 2027-08-11 | Flooring & Dado works | 100 | 0 |  | 2027-09-22 |  | 2027-10-23 |  | Tower B | Super Structure | L40 | Finishes | Flooring & Dado
46332 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-07-15 | 2027-07-22 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-09-23 |  | 2027-10-01 |  | Tower B | Super Structure | L24 | MEP | Electrical
47812 |  | Not Ready |  | 2027-06-12 | 2027-07-28 | P4 to P5 | 100 | 0 |  | 2027-09-23 |  | 2027-11-12
47812 |  | Not Ready |  | 2027-06-12 | 2027-07-28 | P4 to P5 | 100 | 0 |  | 2027-09-23 |  | 2027-11-12
47812 |  | Not Ready |  | 2027-06-12 | 2027-07-28 | P4 to P5 | 100 | 0 |  | 2027-09-23 |  | 2027-11-12
46417 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-07-16 | 2027-07-23 | FAPA Cabling | 100 | 0 |  | 2027-09-24 |  | 2027-10-04 |  | Tower B | Super Structure | L30
46960 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2027-08-25 | 2027-08-30 | Painting Works | 100 | 0 |  | 2027-09-24 |  | 2027-09-30 |  | Tower B | Super Structure | L23 | Finishes | Painting Works
47356 | Tower B - Super Structure - Finishes & MEP - L7 to L15 | Not Ready | Staircase Finishes - MEP & Finishes | 2027-11-09 | 2028-01-18 | Staircase Flooring | 100 | 0 |  | 2027-09-24 |  | 2027-12-07 |  | Tower B | Super Structure | L7 | Finishes | Staircase Flooring
47874 |  | Not Ready |  | 2028-01-24 | 2028-02-10 | Drainage pipe | 100 | 0 |  | 2027-09-24 |  | 2027-10-14
47874 |  | Not Ready |  | 2028-01-24 | 2028-02-10 | Drainage pipe | 100 | 0 |  | 2027-09-24 |  | 2027-10-14
47878 |  | Not Committed |  | 2028-01-24 | 2028-05-04 | P3 level | 100 | 0 |  | 2027-09-24 |  | 2028-01-06
47879 |  | Not Ready |  | 2028-01-24 | 2028-02-16 | RCC upstand | 100 | 0 |  | 2027-09-24 |  | 2027-10-20
47879 |  | Not Ready |  | 2028-01-24 | 2028-02-16 | RCC upstand | 100 | 0 |  | 2027-09-24 |  | 2027-10-20
47258 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Apartment Area | Not Ready | Door & Window 1st Fix- MEP & Finishes | 2027-07-17 | 2027-07-24 | Door & Window Frame work | 100 | 0 |  | 2027-09-25 |  | 2027-10-05 |  | Tower B | Super Structure | L40 | Finishes | Door & Window Frame work
45666 | Tower B - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2027-08-25 | 2027-09-10 | Plumb check & door centre line by Lift agency for lobby blockwork | 100 | 0 |  | 2027-09-27 |  | 2027-10-15 |  | Tower B | Super Structure
45666 | Tower B - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2027-08-25 | 2027-09-10 | Plumb check & door centre line by Lift agency for lobby blockwork | 100 | 0 |  | 2027-09-27 |  | 2027-10-15 |  | Tower B | Super Structure
45666 | Tower B - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2027-08-25 | 2027-09-10 | Plumb check & door centre line by Lift agency for lobby blockwork | 100 | 0 |  | 2027-09-27 |  | 2027-10-15 |  | Tower B | Super Structure
45667 | Tower B - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2027-08-25 | 2027-09-10 | Shaft clearance & White Wash up to LMR | 100 | 0 |  | 2027-09-27 |  | 2027-10-15 |  | Tower B | Super Structure
45667 | Tower B - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2027-08-25 | 2027-09-10 | Shaft clearance & White Wash up to LMR | 100 | 0 |  | 2027-09-27 |  | 2027-10-15 |  | Tower B | Super Structure
45672 | Tower B - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2027-08-25 | 2027-11-08 | LMR Works | 100 | 0 |  | 2027-09-27 |  | 2027-11-04 |  | Tower B | Super Structure
45672 | Tower B - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2027-08-25 | 2027-11-08 | LMR Works | 100 | 0 |  | 2027-09-27 |  | 2027-11-04 |  | Tower B | Super Structure
46086 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-08-25 | 2027-09-08 | False Ceiling | 100 | 0 |  | 2027-09-27 |  | 2027-10-13 |  | Tower B | Super Structure | L9 | Finishes | False Ceiling
46132 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2027-08-25 | 2027-09-06 | Lobby Plastering | 100 | 0 |  | 2027-09-27 |  | 2027-10-11 |  | Tower B | Super Structure | L12 | Finishes | Lobby Plastering
46147 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2027-08-25 | 2027-08-30 | Lobby Blockwork | 100 | 0 |  | 2027-09-27 |  | 2027-10-04 |  | Tower B | Super Structure | L13 | Finishes | Blockwork
46149 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-08-25 | 2027-09-24 | Flooring & Dado | 100 | 0 |  | 2027-09-27 |  | 2027-10-28 |  | Tower B | Super Structure | L13 | Finishes | Flooring & Dado
46347 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-07-19 | 2027-07-26 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-09-27 |  | 2027-10-06 |  | Tower B | Super Structure | L25
46374 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-07-20 | 2027-08-02 | False Ceiling | 100 | 0 |  | 2027-09-28 |  | 2027-10-14 |  | Tower B | Super Structure | L27 | Finishes | False Ceiling
46405 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-07-20 | 2027-08-17 | Flooring & Dado | 100 | 0 |  | 2027-09-28 |  | 2027-10-30 |  | Tower B | Super Structure | L29 | Finishes | Flooring & Dado
46418 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-07-20 | 2027-07-30 | HVAC Ducting | 100 | 0 |  | 2027-09-28 |  | 2027-10-12 |  | Tower B | Super Structure | L30 | MEP | HVAC Ducting
46430 |  | Not Committed |  | 2027-07-20 | 2027-12-31 | L31-32 | 100 | 0 |  | 2027-09-28 |  | 2028-02-02
46430 |  | Not Committed |  | 2027-07-20 | 2027-12-31 | L31-32 | 100 | 0 |  | 2027-09-28 |  | 2028-02-02 |  |  |  |  | Finishes | Gypsum Plastering Works
46431 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-07-20 | 2027-07-30 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-09-28 |  | 2027-10-12 |  | Tower B | Super Structure | L31 | MEP | FPS 1st Fix - MEP & Finishes
46432 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-07-20 | 2027-07-27 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-09-28 |  | 2027-10-07 |  | Tower B | Super Structure | L31 | MEP | Electrical 1st Fixes
47224 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2027-07-20 | 2027-08-02 | False Ceiling | 100 | 0 |  | 2027-09-28 |  | 2027-10-14 |  | Tower B | Super Structure | L38 | Finishes | False Ceiling
46055 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-08-27 | 2027-09-03 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-09-29 |  | 2027-10-08 |  | Tower B | Super Structure | L7 | MEP | FPS 2nd Fix - MEP & Finishes
46056 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-08-27 | 2027-09-03 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-09-29 |  | 2027-10-08 |  | Tower B | Super Structure | L7 | MEP | Electrical 2nd Fix - MEP & Finishes
46057 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-08-27 | 2027-09-08 | FAPA Device Fixing | 100 | 0 |  | 2027-09-29 |  | 2027-10-13 |  | Tower B | Super Structure | L7
46057 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-08-27 | 2027-09-08 | FAPA Device Fixing | 100 | 0 |  | 2027-09-29 |  | 2027-10-13 |  | Tower B | Super Structure | L7
46057 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-08-27 | 2027-09-08 | FAPA Device Fixing | 100 | 0 |  | 2027-09-29 |  | 2027-10-13 |  | Tower B | Super Structure | L7
46057 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-08-27 | 2027-09-08 | FAPA Device Fixing | 100 | 0 |  | 2027-09-29 |  | 2027-10-13 |  | Tower B | Super Structure | L7
46058 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-08-27 | 2027-09-03 | HVAC Grill Fixing | 100 | 0 |  | 2027-09-29 |  | 2027-10-08 |  | Tower B | Super Structure | L7 | MEP | HVAC Grill Fixing
45660 | Tower B - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2027-08-28 | 2027-09-09 | Slow Speed Testing | 100 | 0 |  | 2027-09-30 |  | 2027-10-14 |  | Tower B | Super Structure
45660 | Tower B - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2027-08-28 | 2027-09-09 | Slow Speed Testing | 100 | 0 |  | 2027-09-30 |  | 2027-10-14 |  | Tower B | Super Structure
46359 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-07-22 | 2027-07-29 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-09-30 |  | 2027-10-11 |  | Tower B | Super Structure | L26 | MEP | FPS 2nd Fix - MEP & Finishes
46360 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-07-22 | 2027-07-29 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-09-30 |  | 2027-10-11 |  | Tower B | Super Structure | L26 | MEP | Electrical 2nd Fix - MEP & Finishes
46361 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-07-22 | 2027-08-02 | FAPA Device Fixing | 100 | 0 |  | 2027-09-30 |  | 2027-10-14 |  | Tower B | Super Structure | L26
46361 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-07-22 | 2027-08-02 | FAPA Device Fixing | 100 | 0 |  | 2027-09-30 |  | 2027-10-14 |  | Tower B | Super Structure | L26
46361 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-07-22 | 2027-08-02 | FAPA Device Fixing | 100 | 0 |  | 2027-09-30 |  | 2027-10-14 |  | Tower B | Super Structure | L26
46361 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-07-22 | 2027-08-02 | FAPA Device Fixing | 100 | 0 |  | 2027-09-30 |  | 2027-10-14 |  | Tower B | Super Structure | L26
46362 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-07-22 | 2027-07-29 | HVAC Grill Fixing | 100 | 0 |  | 2027-09-30 |  | 2027-10-11 |  | Tower B | Super Structure | L26 | MEP | HVAC Grill Fixing
46975 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-09-02 | 2027-09-10 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-09-30 |  | 2027-10-11 |  | Tower B | Super Structure | L24 | MEP | FPS 2nd Fix - MEP & Finishes
46976 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-09-02 | 2027-09-10 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-09-30 |  | 2027-10-11 |  | Tower B | Super Structure | L24 | MEP | Electrical 2nd Fix - MEP & Finishes
46977 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2027-09-02 | 2027-09-08 | PHE Final Fixes | 100 | 0 |  | 2027-09-30 |  | 2027-10-07 |  | Tower B | Super Structure | L24
46991 |  | Not Committed |  | 2027-09-02 | 2027-09-29 | MEP final fix & Finishes | 100 | 0 |  | 2027-09-30 |  | 2027-10-26
46992 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2027-09-02 | 2027-09-16 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2027-09-30 |  | 2027-10-14 |  | Tower B | Super Structure | L25 | Finishes | Door & Window Fixing
46333 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-07-23 | 2027-07-30 | Final Painting | 100 | 0 |  | 2027-10-01 |  | 2027-10-12 |  | Tower B | Super Structure | L24 | Finishes | Final Painting
46333 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-07-23 | 2027-07-30 | Final Painting | 100 | 0 |  | 2027-10-01 |  | 2027-10-12 |  | Tower B | Super Structure | L24 | Finishes | Final Painting
46333 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-07-23 | 2027-07-30 | Final Painting | 100 | 0 |  | 2027-10-01 |  | 2027-10-12 |  | Tower B | Super Structure | L24 | Finishes | Final Painting
45686 | Tower B - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2027-08-23 | 2027-10-18 | Panel Installation | 100 | 0 |  | 2027-10-04 |  | 2027-11-27 |  | Tower B | Super Structure
45686 | Tower B - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2027-08-23 | 2027-10-18 | Panel Installation | 100 | 0 |  | 2027-10-04 |  | 2027-11-27 |  | Tower B | Super Structure
46102 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-08-31 | 2027-09-14 | False Ceiling | 100 | 0 |  | 2027-10-04 |  | 2027-10-19 |  | Tower B | Super Structure | L10 | Finishes | False Ceiling
46148 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2027-08-31 | 2027-09-11 | Lobby Plastering | 100 | 0 |  | 2027-10-04 |  | 2027-10-16 |  | Tower B | Super Structure | L13 | Finishes | Lobby Plastering
46163 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2027-08-31 | 2027-09-06 | Lobby Blockwork | 100 | 0 |  | 2027-10-04 |  | 2027-10-11 |  | Tower B | Super Structure | L14 | Finishes | Blockwork
46165 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-08-31 | 2027-09-30 | Flooring & Dado | 100 | 0 |  | 2027-10-04 |  | 2027-11-04 |  | Tower B | Super Structure | L14 | Finishes | Flooring & Dado
46071 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-09-02 | 2027-09-10 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-10-06 |  | 2027-10-15 |  | Tower B | Super Structure | L8 | MEP | FPS 2nd Fix - MEP & Finishes
46072 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-09-02 | 2027-09-10 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-10-06 |  | 2027-10-15 |  | Tower B | Super Structure | L8 | MEP | Electrical 2nd Fix - MEP & Finishes
46073 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-09-02 | 2027-09-14 | FAPA Device Fixing | 100 | 0 |  | 2027-10-06 |  | 2027-10-19 |  | Tower B | Super Structure | L8
46073 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-09-02 | 2027-09-14 | FAPA Device Fixing | 100 | 0 |  | 2027-10-06 |  | 2027-10-19 |  | Tower B | Super Structure | L8
46073 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-09-02 | 2027-09-14 | FAPA Device Fixing | 100 | 0 |  | 2027-10-06 |  | 2027-10-19 |  | Tower B | Super Structure | L8
46073 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-09-02 | 2027-09-14 | FAPA Device Fixing | 100 | 0 |  | 2027-10-06 |  | 2027-10-19 |  | Tower B | Super Structure | L8
46074 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-09-02 | 2027-09-10 | HVAC Grill Fixing | 100 | 0 |  | 2027-10-06 |  | 2027-10-15 |  | Tower B | Super Structure | L8 | MEP | HVAC Grill Fixing
46348 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-07-27 | 2027-08-03 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-10-06 |  | 2027-10-15 |  | Tower B | Super Structure | L25 | MEP | Electrical
46433 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-07-28 | 2027-08-04 | FAPA Cabling | 100 | 0 |  | 2027-10-07 |  | 2027-10-16 |  | Tower B | Super Structure | L31
46978 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2027-09-09 | 2027-09-14 | Painting Works | 100 | 0 |  | 2027-10-07 |  | 2027-10-14 |  | Tower B | Super Structure | L24 | Finishes | Painting Works
47870 |  | Not Ready |  | 2028-02-05 | 2028-02-22 | Handrail lighting work | 100 | 0 |  | 2027-10-07 |  | 2027-10-26
46059 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-09-06 | 2027-09-13 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-10-08 |  | 2027-10-18 |  | Tower B | Super Structure | L7
46118 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-09-07 | 2027-09-21 | False Ceiling | 100 | 0 |  | 2027-10-11 |  | 2027-10-25 |  | Tower B | Super Structure | L11 | Finishes | False Ceiling
46164 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2027-09-07 | 2027-09-18 | Lobby Plastering | 100 | 0 |  | 2027-10-11 |  | 2027-10-22 |  | Tower B | Super Structure | L14 | Finishes | Lobby Plastering
46179 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2027-09-07 | 2027-09-11 | Lobby Blockwork | 100 | 0 |  | 2027-10-11 |  | 2027-10-16 |  | Tower B | Super Structure | L15 | Finishes | Blockwork
46363 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-07-30 | 2027-08-06 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-10-11 |  | 2027-10-19 |  | Tower B | Super Structure | L26
47519 |  | Not Ready | External Development | 2027-08-23 | 2027-12-10 | External Fire Hydrant Line (Outlet) | 100 | 0 |  | 2027-10-11 |  | 2028-01-27
46390 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-07-31 | 2027-08-13 | False Ceiling | 100 | 0 |  | 2027-10-12 |  | 2027-10-26 |  | Tower B | Super Structure | L28 | Finishes | False Ceiling
46421 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-07-31 | 2027-08-28 | Flooring & Dado | 100 | 0 |  | 2027-10-12 |  | 2027-11-11 |  | Tower B | Super Structure | L30 | Finishes | Flooring & Dado
46434 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-07-31 | 2027-08-11 | HVAC Ducting | 100 | 0 |  | 2027-10-12 |  | 2027-10-23 |  | Tower B | Super Structure | L31 | MEP | HVAC Ducting
46446 |  | Not Committed |  | 2027-07-31 | 2028-01-06 | L32-33 | 100 | 0 |  | 2027-10-12 |  | 2028-02-08
46446 |  | Not Committed |  | 2027-07-31 | 2028-01-06 | L32-33 | 100 | 0 |  | 2027-10-12 |  | 2028-02-08 |  |  |  |  | Finishes | Gypsum Plastering Works
46447 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-07-31 | 2027-08-11 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-10-12 |  | 2027-10-23 |  | Tower B | Super Structure | L32 | MEP | FPS 1st Fix - MEP & Finishes
46448 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-07-31 | 2027-08-07 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-10-12 |  | 2027-10-20 |  | Tower B | Super Structure | L32 | MEP | Electrical 1st Fixes
47242 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2027-07-31 | 2027-08-13 | False Ceiling | 100 | 0 |  | 2027-10-12 |  | 2027-10-26 |  | Tower B | Super Structure | L39 | Finishes | False Ceiling
47332 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2027-11-12 | 2027-11-25 | False Ceiling | 100 | 0 |  | 2027-10-12 |  | 2027-10-26 |  | Tower B | Super Structure | L44 | Finishes | False Ceiling
46087 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-09-09 | 2027-09-16 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-10-13 |  | 2027-10-21 |  | Tower B | Super Structure | L9 | MEP | FPS 2nd Fix - MEP & Finishes
46088 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-09-09 | 2027-09-16 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-10-13 |  | 2027-10-21 |  | Tower B | Super Structure | L9 | MEP | Electrical 2nd Fix - MEP & Finishes
46089 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-09-09 | 2027-09-21 | FAPA Device Fixing | 100 | 0 |  | 2027-10-13 |  | 2027-10-25 |  | Tower B | Super Structure | L9
46089 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-09-09 | 2027-09-21 | FAPA Device Fixing | 100 | 0 |  | 2027-10-13 |  | 2027-10-25 |  | Tower B | Super Structure | L9
46089 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-09-09 | 2027-09-21 | FAPA Device Fixing | 100 | 0 |  | 2027-10-13 |  | 2027-10-25 |  | Tower B | Super Structure | L9
46089 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-09-09 | 2027-09-21 | FAPA Device Fixing | 100 | 0 |  | 2027-10-13 |  | 2027-10-25 |  | Tower B | Super Structure | L9
46090 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-09-09 | 2027-09-16 | HVAC Grill Fixing | 100 | 0 |  | 2027-10-13 |  | 2027-10-21 |  | Tower B | Super Structure | L9 | MEP | HVAC Grill Fixing
45661 | Tower B - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2027-09-10 | 2027-09-28 | Balancing, Load Testing, High Speed Testing | 100 | 0 |  | 2027-10-14 |  | 2027-11-02 |  | Tower B | Super Structure
45661 | Tower B - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2027-09-10 | 2027-09-28 | Balancing, Load Testing, High Speed Testing | 100 | 0 |  | 2027-10-14 |  | 2027-11-02 |  | Tower B | Super Structure
46375 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-08-03 | 2027-08-10 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-10-14 |  | 2027-10-22 |  | Tower B | Super Structure | L27 | MEP | FPS 2nd Fix - MEP & Finishes
46376 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-08-03 | 2027-08-10 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-10-14 |  | 2027-10-22 |  | Tower B | Super Structure | L27 | MEP | Electrical 2nd Fix - MEP & Finishes
46377 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-08-03 | 2027-08-13 | FAPA Device Fixing | 100 | 0 |  | 2027-10-14 |  | 2027-10-26 |  | Tower B | Super Structure | L27
46377 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-08-03 | 2027-08-13 | FAPA Device Fixing | 100 | 0 |  | 2027-10-14 |  | 2027-10-26 |  | Tower B | Super Structure | L27
46377 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-08-03 | 2027-08-13 | FAPA Device Fixing | 100 | 0 |  | 2027-10-14 |  | 2027-10-26 |  | Tower B | Super Structure | L27
46377 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-08-03 | 2027-08-13 | FAPA Device Fixing | 100 | 0 |  | 2027-10-14 |  | 2027-10-26 |  | Tower B | Super Structure | L27
46378 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-08-03 | 2027-08-10 | HVAC Grill Fixing | 100 | 0 |  | 2027-10-14 |  | 2027-10-22 |  | Tower B | Super Structure | L27 | MEP | HVAC Grill Fixing
46993 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-09-18 | 2027-09-25 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-10-14 |  | 2027-10-22 |  | Tower B | Super Structure | L25 | MEP | FPS 2nd Fix - MEP & Finishes
46994 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-09-18 | 2027-09-25 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-10-14 |  | 2027-10-22 |  | Tower B | Super Structure | L25 | MEP | Electrical 2nd Fix - MEP & Finishes
46995 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2027-09-18 | 2027-09-23 | PHE Final Fixes | 100 | 0 |  | 2027-10-14 |  | 2027-10-20 |  | Tower B | Super Structure | L25
47009 |  | Not Committed |  | 2027-09-18 | 2027-10-15 | MEP final fix & Finishes | 100 | 0 |  | 2027-10-14 |  | 2027-11-08
47010 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2027-09-18 | 2027-10-01 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2027-10-14 |  | 2027-10-26 |  | Tower B | Super Structure | L26 | Finishes | Door & Window Fixing
47875 |  | Not Ready |  | 2028-02-11 | 2028-02-28 | SS work | 100 | 0 |  | 2027-10-14 |  | 2027-11-02
45668 | Tower B - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2027-09-11 | 2027-09-28 | Bulk head light fix + Electrical works + Earthing | 100 | 0 |  | 2027-10-15 |  | 2027-11-02 |  | Tower B | Super Structure
45668 | Tower B - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2027-09-11 | 2027-09-28 | Bulk head light fix + Electrical works + Earthing | 100 | 0 |  | 2027-10-15 |  | 2027-11-02 |  | Tower B | Super Structure
45668 | Tower B - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2027-09-11 | 2027-09-28 | Bulk head light fix + Electrical works + Earthing | 100 | 0 |  | 2027-10-15 |  | 2027-11-02 |  | Tower B | Super Structure
46075 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-09-11 | 2027-09-20 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-10-15 |  | 2027-10-23 |  | Tower B | Super Structure | L8
46349 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-08-04 | 2027-08-11 | Final Painting | 100 | 0 |  | 2027-10-15 |  | 2027-10-23 |  | Tower B | Super Structure | L25 | Finishes | Final Painting
46349 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-08-04 | 2027-08-11 | Final Painting | 100 | 0 |  | 2027-10-15 |  | 2027-10-23 |  | Tower B | Super Structure | L25 | Finishes | Final Painting
46349 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-08-04 | 2027-08-11 | Final Painting | 100 | 0 |  | 2027-10-15 |  | 2027-10-23 |  | Tower B | Super Structure | L25 | Finishes | Final Painting
46134 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-09-13 | 2027-09-27 | False Ceiling | 100 | 0 |  | 2027-10-16 |  | 2027-11-01 |  | Tower B | Super Structure | L12 | Finishes | False Ceiling
46180 | Tower B - Super Structure - Finishes & MEP - L15 to L16 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2027-09-13 | 2027-09-24 | Lobby Plastering | 100 | 0 |  | 2027-10-16 |  | 2027-10-28 |  | Tower B | Super Structure | L15 | Finishes | Lobby Plastering
46195 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2027-09-13 | 2027-09-18 | Lobby Blockwork | 100 | 0 |  | 2027-10-16 |  | 2027-10-22 |  | Tower B | Super Structure | L16 | Finishes | Blockwork
46060 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-09-14 | 2027-09-22 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-10-18 |  | 2027-10-26 |  | Tower B | Super Structure | L7 | MEP | Electrical
47835 |  | Not Ready |  | 2027-04-08 | 2027-04-30 | MEP Rooms - Plaster & IPS | 100 | 0 |  | 2027-10-18 |  | 2027-11-11
47835 |  | Not Ready |  | 2027-04-08 | 2027-04-30 | MEP Rooms - Plaster & IPS | 100 | 0 |  | 2027-10-18 |  | 2027-11-11
47836 |  | Not Ready |  | 2027-04-08 | 2027-05-13 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2027-10-18 |  | 2027-11-23
47836 |  | Not Ready |  | 2027-04-08 | 2027-05-13 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2027-10-18 |  | 2027-11-23
46103 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-09-15 | 2027-09-23 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-10-19 |  | 2027-10-27 |  | Tower B | Super Structure | L10 | MEP | FPS 2nd Fix - MEP & Finishes
46104 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-09-15 | 2027-09-23 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-10-19 |  | 2027-10-27 |  | Tower B | Super Structure | L10 | MEP | Electrical 2nd Fix - MEP & Finishes
46105 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-09-15 | 2027-09-27 | FAPA Device Fixing | 100 | 0 |  | 2027-10-19 |  | 2027-11-01 |  | Tower B | Super Structure | L10
46105 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-09-15 | 2027-09-27 | FAPA Device Fixing | 100 | 0 |  | 2027-10-19 |  | 2027-11-01 |  | Tower B | Super Structure | L10
46105 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-09-15 | 2027-09-27 | FAPA Device Fixing | 100 | 0 |  | 2027-10-19 |  | 2027-11-01 |  | Tower B | Super Structure | L10
46105 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-09-15 | 2027-09-27 | FAPA Device Fixing | 100 | 0 |  | 2027-10-19 |  | 2027-11-01 |  | Tower B | Super Structure | L10
46106 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-09-15 | 2027-09-23 | HVAC Grill Fixing | 100 | 0 |  | 2027-10-19 |  | 2027-10-27 |  | Tower B | Super Structure | L10 | MEP | HVAC Grill Fixing
46364 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-08-07 | 2027-08-14 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-10-19 |  | 2027-10-27 |  | Tower B | Super Structure | L26 | MEP | Electrical
46449 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-08-09 | 2027-08-16 | FAPA Cabling | 100 | 0 |  | 2027-10-20 |  | 2027-10-28 |  | Tower B | Super Structure | L32
46996 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2027-09-24 | 2027-09-29 | Painting Works | 100 | 0 |  | 2027-10-20 |  | 2027-10-26 |  | Tower B | Super Structure | L25 | Finishes | Painting Works
47880 |  | Not Ready |  | 2028-02-17 | 2028-03-04 | Drainage pipe | 100 | 0 |  | 2027-10-20 |  | 2027-11-08
47880 |  | Not Ready |  | 2028-02-17 | 2028-03-04 | Drainage pipe | 100 | 0 |  | 2027-10-20 |  | 2027-11-08
47884 |  | Not Committed |  | 2028-02-17 | 2028-05-29 | P4 level | 100 | 0 |  | 2027-10-20 |  | 2028-01-31
47885 |  | Not Ready |  | 2028-02-17 | 2028-03-10 | RCC upstand | 100 | 0 |  | 2027-10-20 |  | 2027-11-13
47885 |  | Not Ready |  | 2028-02-17 | 2028-03-10 | RCC upstand | 100 | 0 |  | 2027-10-20 |  | 2027-11-13
46091 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-09-18 | 2027-09-25 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-10-21 |  | 2027-10-30 |  | Tower B | Super Structure | L9
46150 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-09-20 | 2027-10-04 | False Ceiling | 100 | 0 |  | 2027-10-22 |  | 2027-11-06 |  | Tower B | Super Structure | L13 | Finishes | False Ceiling
46196 | Tower B - Super Structure - Finishes & MEP - L16 to L17 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2027-09-20 | 2027-09-30 | Lobby Plastering | 100 | 0 |  | 2027-10-22 |  | 2027-11-04 |  | Tower B | Super Structure | L16 | Finishes | Lobby Plastering
46211 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2027-09-20 | 2027-09-24 | Lobby Blockwork | 100 | 0 |  | 2027-10-22 |  | 2027-10-28 |  | Tower B | Super Structure | L17 | Finishes | Blockwork
46379 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-08-11 | 2027-08-18 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-10-22 |  | 2027-11-01 |  | Tower B | Super Structure | L27
46076 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-09-21 | 2027-09-28 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-10-23 |  | 2027-11-02 |  | Tower B | Super Structure | L8 | MEP | Electrical
46406 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-08-12 | 2027-08-25 | False Ceiling | 100 | 0 |  | 2027-10-23 |  | 2027-11-08 |  | Tower B | Super Structure | L29 | Finishes | False Ceiling
46437 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-08-12 | 2027-09-10 | Flooring & Dado | 100 | 0 |  | 2027-10-23 |  | 2027-11-23 |  | Tower B | Super Structure | L31 | Finishes | Flooring & Dado
46450 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-08-12 | 2027-08-23 | HVAC Ducting | 100 | 0 |  | 2027-10-23 |  | 2027-11-05 |  | Tower B | Super Structure | L32 | MEP | HVAC Ducting
46462 |  | Not Committed |  | 2027-08-12 | 2028-01-12 | L33-34 | 100 | 0 |  | 2027-10-23 |  | 2028-02-14
46462 |  | Not Committed |  | 2027-08-12 | 2028-01-12 | L33-34 | 100 | 0 |  | 2027-10-23 |  | 2028-02-14 |  |  |  |  | Finishes | Gypsum Plastering Works
46463 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-08-12 | 2027-08-23 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-10-23 |  | 2027-11-05 |  | Tower B | Super Structure | L33 | MEP | FPS 1st Fix - MEP & Finishes
46464 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-08-12 | 2027-08-19 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-10-23 |  | 2027-11-02 |  | Tower B | Super Structure | L33 | MEP | Electrical 1st Fixes
47260 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Apartment Area | Not Ready | False Ceiling - MEP & Finishes | 2027-08-12 | 2027-08-25 | False Ceiling | 100 | 0 |  | 2027-10-23 |  | 2027-11-08 |  | Tower B | Super Structure | L40 | Finishes | False Ceiling
46119 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-09-22 | 2027-09-29 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-10-25 |  | 2027-11-03 |  | Tower B | Super Structure | L11 | MEP | FPS 2nd Fix - MEP & Finishes
46120 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-09-22 | 2027-09-29 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-10-25 |  | 2027-11-03 |  | Tower B | Super Structure | L11 | MEP | Electrical 2nd Fix - MEP & Finishes
46121 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-09-22 | 2027-10-04 | FAPA Device Fixing | 100 | 0 |  | 2027-10-25 |  | 2027-11-06 |  | Tower B | Super Structure | L11
46121 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-09-22 | 2027-10-04 | FAPA Device Fixing | 100 | 0 |  | 2027-10-25 |  | 2027-11-06 |  | Tower B | Super Structure | L11
46121 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-09-22 | 2027-10-04 | FAPA Device Fixing | 100 | 0 |  | 2027-10-25 |  | 2027-11-06 |  | Tower B | Super Structure | L11
46121 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-09-22 | 2027-10-04 | FAPA Device Fixing | 100 | 0 |  | 2027-10-25 |  | 2027-11-06 |  | Tower B | Super Structure | L11
46122 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-09-22 | 2027-09-29 | HVAC Grill Fixing | 100 | 0 |  | 2027-10-25 |  | 2027-11-03 |  | Tower B | Super Structure | L11 | MEP | HVAC Grill Fixing
46061 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-09-23 | 2027-09-30 | Final Painting | 100 | 0 |  | 2027-10-26 |  | 2027-11-04 |  | Tower B | Super Structure | L7 | Finishes | Final Painting
46061 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-09-23 | 2027-09-30 | Final Painting | 100 | 0 |  | 2027-10-26 |  | 2027-11-04 |  | Tower B | Super Structure | L7 | Finishes | Final Painting
46061 | Tower B - Super Structure - Finishes & MEP - L7 to L8 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-09-23 | 2027-09-30 | Final Painting | 100 | 0 |  | 2027-10-26 |  | 2027-11-04 |  | Tower B | Super Structure | L7 | Finishes | Final Painting
46391 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-08-14 | 2027-08-21 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-10-26 |  | 2027-11-04 |  | Tower B | Super Structure | L28 | MEP | FPS 2nd Fix - MEP & Finishes
46392 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-08-14 | 2027-08-21 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-10-26 |  | 2027-11-04 |  | Tower B | Super Structure | L28 | MEP | Electrical 2nd Fix - MEP & Finishes
46393 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-08-14 | 2027-08-25 | FAPA Device Fixing | 100 | 0 |  | 2027-10-26 |  | 2027-11-08 |  | Tower B | Super Structure | L28
46393 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-08-14 | 2027-08-25 | FAPA Device Fixing | 100 | 0 |  | 2027-10-26 |  | 2027-11-08 |  | Tower B | Super Structure | L28
46393 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-08-14 | 2027-08-25 | FAPA Device Fixing | 100 | 0 |  | 2027-10-26 |  | 2027-11-08 |  | Tower B | Super Structure | L28
46393 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-08-14 | 2027-08-25 | FAPA Device Fixing | 100 | 0 |  | 2027-10-26 |  | 2027-11-08 |  | Tower B | Super Structure | L28
46394 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-08-14 | 2027-08-21 | HVAC Grill Fixing | 100 | 0 |  | 2027-10-26 |  | 2027-11-04 |  | Tower B | Super Structure | L28 | MEP | HVAC Grill Fixing
47011 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-10-04 | 2027-10-12 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-10-26 |  | 2027-11-04 |  | Tower B | Super Structure | L26 | MEP | FPS 2nd Fix - MEP & Finishes
47012 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-10-04 | 2027-10-12 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-10-26 |  | 2027-11-04 |  | Tower B | Super Structure | L26 | MEP | Electrical 2nd Fix - MEP & Finishes
47013 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2027-10-04 | 2027-10-08 | PHE Final Fixes | 100 | 0 |  | 2027-10-26 |  | 2027-11-02 |  | Tower B | Super Structure | L26
47027 |  | Not Committed |  | 2027-10-04 | 2027-10-30 | MEP final fix & Finishes | 100 | 0 |  | 2027-10-26 |  | 2027-11-22
47028 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2027-10-04 | 2027-10-18 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2027-10-26 |  | 2027-11-10 |  | Tower B | Super Structure | L27 | Finishes | Door & Window Fixing
47871 |  | Not Ready |  | 2028-02-23 | 2028-03-17 | Planter works | 100 | 0 |  | 2027-10-26 |  | 2027-11-19
47871 |  | Not Ready |  | 2028-02-23 | 2028-03-17 | Planter works | 100 | 0 |  | 2027-10-26 |  | 2027-11-19
46107 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-09-24 | 2027-10-01 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-10-27 |  | 2027-11-05 |  | Tower B | Super Structure | L10
46365 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-08-16 | 2027-08-23 | Final Painting | 100 | 0 |  | 2027-10-27 |  | 2027-11-05 |  | Tower B | Super Structure | L26 | Finishes | Final Painting
46365 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-08-16 | 2027-08-23 | Final Painting | 100 | 0 |  | 2027-10-27 |  | 2027-11-05 |  | Tower B | Super Structure | L26 | Finishes | Final Painting
46365 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-08-16 | 2027-08-23 | Final Painting | 100 | 0 |  | 2027-10-27 |  | 2027-11-05 |  | Tower B | Super Structure | L26 | Finishes | Final Painting
47401 | Tower B - Super Structure - Finishes & MEP - P3 to L7 | Not Ready | Façade Works - MEP & Finishes | 2027-08-16 | 2027-09-01 | DGU Assembly Installation | 100 | 0 |  | 2027-10-27 |  | 2027-11-15 |  | Tower B | Super Structure |  | Façade | Façade Works
47402 | Tower B - Super Structure - Finishes & MEP - P3 to L7 | Not Ready | Façade Works - MEP & Finishes | 2027-08-16 | 2027-09-14 | Installation of highly reflective metal sheet | 100 | 0 |  | 2027-10-27 |  | 2027-11-26 |  | Tower B | Super Structure |  | Façade | Façade Works
47403 | Tower B - Super Structure - Finishes & MEP - P3 to L7 | Not Ready | Façade Works - MEP & Finishes | 2027-08-16 | 2027-09-01 | Fixing of Backlit Laminated Glass assembly & ACP Panels | 100 | 0 |  | 2027-10-27 |  | 2027-11-15 |  | Tower B | Super Structure |  | Façade | Façade Works
47404 | Tower B - Super Structure - Finishes & MEP - P3 to L7 | Not Ready | Façade Works - MEP & Finishes | 2027-08-16 | 2027-08-26 | Fixing of Louvers | 100 | 0 |  | 2027-10-27 |  | 2027-11-09 |  | Tower B | Super Structure |  | Façade | Façade Works
47404 | Tower B - Super Structure - Finishes & MEP - P3 to L7 | Not Ready | Façade Works - MEP & Finishes | 2027-08-16 | 2027-08-26 | Fixing of Louvers | 100 | 0 |  | 2027-10-27 |  | 2027-11-09 |  | Tower B | Super Structure
46166 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-09-25 | 2027-10-11 | False Ceiling | 100 | 0 |  | 2027-10-28 |  | 2027-11-12 |  | Tower B | Super Structure | L14 | Finishes | False Ceiling
46212 | Tower B - Super Structure - Finishes & MEP - L17 to L18 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2027-09-25 | 2027-10-07 | Lobby Plastering | 100 | 0 |  | 2027-10-28 |  | 2027-11-10 |  | Tower B | Super Structure | L17 | Finishes | Lobby Plastering
46227 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2027-09-25 | 2027-09-30 | Lobby Blockwork | 100 | 0 |  | 2027-10-28 |  | 2027-11-04 |  | Tower B | Super Structure | L18 | Finishes | Blockwork
47520 |  | Not Ready | External Development | 2027-09-10 | 2027-12-10 | Inlet Line for Fire Tanks | 100 | 0 |  | 2027-10-28 |  | 2028-01-27
45880 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | Entrance Area Kiosks - MEP & Finishes | 2027-09-06 | 2027-10-13 | Entrance Area Kiosks | 100 | 0 |  | 2027-10-30 |  | 2027-12-04 |  | Tower B | Super Structure | GF
46092 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-09-27 | 2027-10-05 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-10-30 |  | 2027-11-08 |  | Tower B | Super Structure | L9 | MEP | Electrical
46135 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-09-28 | 2027-10-06 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-11-01 |  | 2027-11-09 |  | Tower B | Super Structure | L12 | MEP | FPS 2nd Fix - MEP & Finishes
46136 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-09-28 | 2027-10-06 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-11-01 |  | 2027-11-09 |  | Tower B | Super Structure | L12 | MEP | Electrical 2nd Fix - MEP & Finishes
46137 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-09-28 | 2027-10-11 | FAPA Device Fixing | 100 | 0 |  | 2027-11-01 |  | 2027-11-12 |  | Tower B | Super Structure | L12
46137 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-09-28 | 2027-10-11 | FAPA Device Fixing | 100 | 0 |  | 2027-11-01 |  | 2027-11-12 |  | Tower B | Super Structure | L12
46137 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-09-28 | 2027-10-11 | FAPA Device Fixing | 100 | 0 |  | 2027-11-01 |  | 2027-11-12 |  | Tower B | Super Structure | L12
46137 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-09-28 | 2027-10-11 | FAPA Device Fixing | 100 | 0 |  | 2027-11-01 |  | 2027-11-12 |  | Tower B | Super Structure | L12
46138 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-09-28 | 2027-10-06 | HVAC Grill Fixing | 100 | 0 |  | 2027-11-01 |  | 2027-11-09 |  | Tower B | Super Structure | L12 | MEP | HVAC Grill Fixing
46380 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-08-19 | 2027-08-26 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-11-01 |  | 2027-11-09 |  | Tower B | Super Structure | L27 | MEP | Electrical
45662 | Tower B - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2027-09-29 | 2027-10-05 | 3rd Party Testing & Commissioning | 100 | 0 |  | 2027-11-02 |  | 2027-11-08 |  | Tower B | Super Structure
45662 | Tower B - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2027-09-29 | 2027-10-05 | 3rd Party Testing & Commissioning | 100 | 0 |  | 2027-11-02 |  | 2027-11-08 |  | Tower B | Super Structure
45669 | Tower B - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2027-09-29 | 2027-10-16 | Jump platform installation | 100 | 0 |  | 2027-11-02 |  | 2027-11-18 |  | Tower B | Super Structure
45669 | Tower B - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2027-09-29 | 2027-10-16 | Jump platform installation | 100 | 0 |  | 2027-11-02 |  | 2027-11-18 |  | Tower B | Super Structure
45669 | Tower B - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2027-09-29 | 2027-10-16 | Jump platform installation | 100 | 0 |  | 2027-11-02 |  | 2027-11-18 |  | Tower B | Super Structure
46077 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-09-29 | 2027-10-07 | Final Painting | 100 | 0 |  | 2027-11-02 |  | 2027-11-10 |  | Tower B | Super Structure | L8 | Finishes | Final Painting
46077 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-09-29 | 2027-10-07 | Final Painting | 100 | 0 |  | 2027-11-02 |  | 2027-11-10 |  | Tower B | Super Structure | L8 | Finishes | Final Painting
46077 | Tower B - Super Structure - Finishes & MEP - L8 to L9 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-09-29 | 2027-10-07 | Final Painting | 100 | 0 |  | 2027-11-02 |  | 2027-11-10 |  | Tower B | Super Structure | L8 | Finishes | Final Painting
46465 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-08-20 | 2027-08-27 | FAPA Cabling | 100 | 0 |  | 2027-11-02 |  | 2027-11-10 |  | Tower B | Super Structure | L33
47014 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2027-10-11 | 2027-10-15 | Painting Works | 100 | 0 |  | 2027-11-02 |  | 2027-11-08 |  | Tower B | Super Structure | L26 | Finishes | Painting Works
47347 |  | Not Committed |  | 2027-12-14 | 2028-05-05 | GF-L7 | 100 | 0 |  | 2027-11-02 |  | 2028-03-24
47348 | Tower B - Super Structure - Finishes & MEP - GF to L7 | Not Ready | Staircase Finishes - MEP & Finishes | 2027-12-14 | 2028-02-05 | Staircase Wall & Ceiling finishes | 100 | 0 |  | 2027-11-02 |  | 2027-12-24 |  | Tower B | Super Structure | GF
47357 | Tower B - Super Structure - Finishes & MEP - L7 to L15 | Not Ready | Staircase Finishes - MEP & Finishes | 2027-12-14 | 2028-01-18 | Staircase Window | 100 | 0 |  | 2027-11-02 |  | 2027-12-07 |  | Tower B | Super Structure | L7
47359 | Tower B - Super Structure - Finishes & MEP - L7 to L15 | Not Ready | Staircase Finishes - MEP & Finishes | 2027-12-14 | 2027-12-31 | Staircase cabling | 100 | 0 |  | 2027-11-02 |  | 2027-11-19 |  | Tower B | Super Structure | L7
47361 |  | Not Committed |  | 2027-12-14 | 2028-05-05 | L15-25 | 100 | 0 |  | 2027-11-02 |  | 2028-03-24
47361 |  | Not Committed |  | 2027-12-14 | 2028-05-05 | L15-25 | 100 | 0 |  | 2027-11-02 |  | 2028-03-24
47362 | Tower B - Super Structure - Finishes & MEP - L15 to L25 | Not Ready | Staircase Finishes - MEP & Finishes | 2027-12-14 | 2028-02-05 | Staircase Wall & Ceiling finishes | 100 | 0 |  | 2027-11-02 |  | 2027-12-24 |  | Tower B | Super Structure | L15
47876 |  | Not Ready |  | 2028-02-29 | 2028-03-17 | Handrail lighting work | 100 | 0 |  | 2027-11-02 |  | 2027-11-19
45879 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2027-09-09 | 2027-09-23 | Final Painting | 100 | 0 |  | 2027-11-03 |  | 2027-11-17 |  | Tower B | Super Structure | GF | Finishes | Final Painting
45879 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2027-09-09 | 2027-09-23 | Final Painting | 100 | 0 |  | 2027-11-03 |  | 2027-11-17 |  | Tower B | Super Structure | GF | Finishes | Final Painting
45879 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | Final Painting - MEP & Finishes | 2027-09-09 | 2027-09-23 | Final Painting | 100 | 0 |  | 2027-11-03 |  | 2027-11-17 |  | Tower B | Super Structure | GF | Finishes | Final Painting
46123 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-09-30 | 2027-10-08 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-11-03 |  | 2027-11-11 |  | Tower B | Super Structure | L11
46228 | Tower B - Super Structure - Finishes & MEP - L18 to L19 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2027-10-01 | 2027-10-14 | Lobby Plastering | 100 | 0 |  | 2027-11-04 |  | 2027-11-16 |  | Tower B | Super Structure | L18 | Finishes | Lobby Plastering
46243 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2027-10-01 | 2027-10-07 | Lobby Blockwork | 100 | 0 |  | 2027-11-04 |  | 2027-11-10 |  | Tower B | Super Structure | L19 | Finishes | Blockwork
46395 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-08-23 | 2027-08-30 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-11-04 |  | 2027-11-12 |  | Tower B | Super Structure | L28
46108 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-10-04 | 2027-10-12 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-11-05 |  | 2027-11-13 |  | Tower B | Super Structure | L10 | MEP | Electrical
46422 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-08-24 | 2027-09-07 | False Ceiling | 100 | 0 |  | 2027-11-05 |  | 2027-11-19 |  | Tower B | Super Structure | L30 | Finishes | False Ceiling
46453 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-08-24 | 2027-09-23 | Flooring & Dado | 100 | 0 |  | 2027-11-05 |  | 2027-12-04 |  | Tower B | Super Structure | L32 | Finishes | Flooring & Dado
46466 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-08-24 | 2027-09-03 | HVAC Ducting | 100 | 0 |  | 2027-11-05 |  | 2027-11-17 |  | Tower B | Super Structure | L33 | MEP | HVAC Ducting
46478 |  | Not Committed |  | 2027-08-24 | 2028-01-18 | L34-35 | 100 | 0 |  | 2027-11-05 |  | 2028-02-19
46478 |  | Not Committed |  | 2027-08-24 | 2028-01-18 | L34-35 | 100 | 0 |  | 2027-11-05 |  | 2028-02-19 |  |  |  |  | Finishes | Gypsum Plastering Works
46479 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-08-24 | 2027-09-03 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-11-05 |  | 2027-11-17 |  | Tower B | Super Structure | L34 | MEP | FPS 1st Fix - MEP & Finishes
46480 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-08-24 | 2027-08-31 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-11-05 |  | 2027-11-13 |  | Tower B | Super Structure | L34 | MEP | Electrical 1st Fixes
46151 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-10-05 | 2027-10-13 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-11-06 |  | 2027-11-15 |  | Tower B | Super Structure | L13 | MEP | FPS 2nd Fix - MEP & Finishes
46152 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-10-05 | 2027-10-13 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-11-06 |  | 2027-11-15 |  | Tower B | Super Structure | L13 | MEP | Electrical 2nd Fix - MEP & Finishes
46153 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-10-05 | 2027-10-16 | FAPA Device Fixing | 100 | 0 |  | 2027-11-06 |  | 2027-11-18 |  | Tower B | Super Structure | L13
46153 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-10-05 | 2027-10-16 | FAPA Device Fixing | 100 | 0 |  | 2027-11-06 |  | 2027-11-18 |  | Tower B | Super Structure | L13
46153 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-10-05 | 2027-10-16 | FAPA Device Fixing | 100 | 0 |  | 2027-11-06 |  | 2027-11-18 |  | Tower B | Super Structure | L13
46153 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-10-05 | 2027-10-16 | FAPA Device Fixing | 100 | 0 |  | 2027-11-06 |  | 2027-11-18 |  | Tower B | Super Structure | L13
46154 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-10-05 | 2027-10-13 | HVAC Grill Fixing | 100 | 0 |  | 2027-11-06 |  | 2027-11-15 |  | Tower B | Super Structure | L13 | MEP | HVAC Grill Fixing
45663 | Tower B - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2027-10-06 | 2027-10-12 | Obtaining PWD Lisence | 100 | 0 |  | 2027-11-08 |  | 2027-11-13 |  | Tower B | Super Structure
45663 | Tower B - Super Structure - Finishes & MEP | Not Ready | CTU Elevators - High Side Services | 2027-10-06 | 2027-10-12 | Obtaining PWD Lisence | 100 | 0 |  | 2027-11-08 |  | 2027-11-13 |  | Tower B | Super Structure
46093 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-10-06 | 2027-10-14 | Final Painting | 100 | 0 |  | 2027-11-08 |  | 2027-11-16 |  | Tower B | Super Structure | L9 | Finishes | Final Painting
46093 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-10-06 | 2027-10-14 | Final Painting | 100 | 0 |  | 2027-11-08 |  | 2027-11-16 |  | Tower B | Super Structure | L9 | Finishes | Final Painting
46093 | Tower B - Super Structure - Finishes & MEP - L9 to L10 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-10-06 | 2027-10-14 | Final Painting | 100 | 0 |  | 2027-11-08 |  | 2027-11-16 |  | Tower B | Super Structure | L9 | Finishes | Final Painting
46407 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-08-26 | 2027-09-02 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-11-08 |  | 2027-11-16 |  | Tower B | Super Structure | L29 | MEP | FPS 2nd Fix - MEP & Finishes
46408 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-08-26 | 2027-09-02 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-11-08 |  | 2027-11-16 |  | Tower B | Super Structure | L29 | MEP | Electrical 2nd Fix - MEP & Finishes
46409 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-08-26 | 2027-09-07 | FAPA Device Fixing | 100 | 0 |  | 2027-11-08 |  | 2027-11-19 |  | Tower B | Super Structure | L29
46409 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-08-26 | 2027-09-07 | FAPA Device Fixing | 100 | 0 |  | 2027-11-08 |  | 2027-11-19 |  | Tower B | Super Structure | L29
46409 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-08-26 | 2027-09-07 | FAPA Device Fixing | 100 | 0 |  | 2027-11-08 |  | 2027-11-19 |  | Tower B | Super Structure | L29
46409 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-08-26 | 2027-09-07 | FAPA Device Fixing | 100 | 0 |  | 2027-11-08 |  | 2027-11-19 |  | Tower B | Super Structure | L29
46410 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-08-26 | 2027-09-02 | HVAC Grill Fixing | 100 | 0 |  | 2027-11-08 |  | 2027-11-16 |  | Tower B | Super Structure | L29 | MEP | HVAC Grill Fixing
47881 |  | Not Ready |  | 2028-03-06 | 2028-03-23 | SS work | 100 | 0 |  | 2027-11-08 |  | 2027-11-25
46139 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-10-07 | 2027-10-15 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-11-09 |  | 2027-11-17 |  | Tower B | Super Structure | L12
46381 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-08-27 | 2027-09-03 | Final Painting | 100 | 0 |  | 2027-11-09 |  | 2027-11-17 |  | Tower B | Super Structure | L27 | Finishes | Final Painting
46381 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-08-27 | 2027-09-03 | Final Painting | 100 | 0 |  | 2027-11-09 |  | 2027-11-17 |  | Tower B | Super Structure | L27 | Finishes | Final Painting
46381 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-08-27 | 2027-09-03 | Final Painting | 100 | 0 |  | 2027-11-09 |  | 2027-11-17 |  | Tower B | Super Structure | L27 | Finishes | Final Painting
46244 | Tower B - Super Structure - Finishes & MEP - L19 to L20 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2027-10-08 | 2027-10-20 | Lobby Plastering | 100 | 0 |  | 2027-11-10 |  | 2027-11-22 |  | Tower B | Super Structure | L19 | Finishes | Lobby Plastering
46259 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2027-10-08 | 2027-10-14 | Lobby Blockwork | 100 | 0 |  | 2027-11-10 |  | 2027-11-16 |  | Tower B | Super Structure | L20 | Finishes | Blockwork
47029 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-10-19 | 2027-10-26 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-11-10 |  | 2027-11-18 |  | Tower B | Super Structure | L27 | MEP | FPS 2nd Fix - MEP & Finishes
47030 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-10-19 | 2027-10-26 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-11-10 |  | 2027-11-18 |  | Tower B | Super Structure | L27 | MEP | Electrical 2nd Fix - MEP & Finishes
47031 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2027-10-19 | 2027-10-23 | PHE Final Fixes | 100 | 0 |  | 2027-11-10 |  | 2027-11-16 |  | Tower B | Super Structure | L27
47045 |  | Not Committed |  | 2027-10-19 | 2027-11-13 | MEP final fix & Finishes | 100 | 0 |  | 2027-11-10 |  | 2027-12-06
47046 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2027-10-19 | 2027-11-02 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2027-11-10 |  | 2027-11-24 |  | Tower B | Super Structure | L28 | Finishes | Door & Window Fixing
46124 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-10-11 | 2027-10-18 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-11-11 |  | 2027-11-19 |  | Tower B | Super Structure | L11 | MEP | Electrical
46167 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-10-12 | 2027-10-19 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-11-12 |  | 2027-11-20 |  | Tower B | Super Structure | L14 | MEP | FPS 2nd Fix - MEP & Finishes
46168 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-10-12 | 2027-10-19 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-11-12 |  | 2027-11-20 |  | Tower B | Super Structure | L14 | MEP | Electrical 2nd Fix - MEP & Finishes
46169 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-10-12 | 2027-10-22 | FAPA Device Fixing | 100 | 0 |  | 2027-11-12 |  | 2027-11-24 |  | Tower B | Super Structure | L14
46169 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-10-12 | 2027-10-22 | FAPA Device Fixing | 100 | 0 |  | 2027-11-12 |  | 2027-11-24 |  | Tower B | Super Structure | L14
46169 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-10-12 | 2027-10-22 | FAPA Device Fixing | 100 | 0 |  | 2027-11-12 |  | 2027-11-24 |  | Tower B | Super Structure | L14
46169 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-10-12 | 2027-10-22 | FAPA Device Fixing | 100 | 0 |  | 2027-11-12 |  | 2027-11-24 |  | Tower B | Super Structure | L14
46170 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-10-12 | 2027-10-19 | HVAC Grill Fixing | 100 | 0 |  | 2027-11-12 |  | 2027-11-20 |  | Tower B | Super Structure | L14 | MEP | HVAC Grill Fixing
46396 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-08-31 | 2027-09-08 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-11-12 |  | 2027-11-20 |  | Tower B | Super Structure | L28 | MEP | Electrical
46109 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-10-13 | 2027-10-20 | Final Painting | 100 | 0 |  | 2027-11-13 |  | 2027-11-22 |  | Tower B | Super Structure | L10 | Finishes | Final Painting
46109 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-10-13 | 2027-10-20 | Final Painting | 100 | 0 |  | 2027-11-13 |  | 2027-11-22 |  | Tower B | Super Structure | L10 | Finishes | Final Painting
46109 | Tower B - Super Structure - Finishes & MEP - L10 to L11 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-10-13 | 2027-10-20 | Final Painting | 100 | 0 |  | 2027-11-13 |  | 2027-11-22 |  | Tower B | Super Structure | L10 | Finishes | Final Painting
46481 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-09-01 | 2027-09-09 | FAPA Cabling | 100 | 0 |  | 2027-11-13 |  | 2027-11-22 |  | Tower B | Super Structure | L34
47459 |  | Not Ready |  | 2027-10-13 | 2028-07-21 | Leave Out Bay | 100 | 0 |  | 2027-11-13 |  | 2028-08-22
47460 |  | Not Committed |  | 2027-10-13 | 2027-11-11 | Hoist Removal | 100 | 0 |  | 2027-11-13 |  | 2027-12-13
47461 | Tower B | Not Ready | Leave Out Bay - Hoist Removal | 2027-10-13 | 2027-11-11 | Removal of 1 set of twin cage hoist (from back side) | 100 | 0 |  | 2027-11-13 |  | 2027-12-13 |  | Tower B | --
47886 |  | Not Ready |  | 2028-03-13 | 2028-03-29 | Drainage pipe | 100 | 0 |  | 2027-11-13 |  | 2027-12-01
47886 |  | Not Ready |  | 2028-03-13 | 2028-03-29 | Drainage pipe | 100 | 0 |  | 2027-11-13 |  | 2027-12-01
47890 |  | Not Committed |  | 2028-03-13 | 2028-06-21 | P5 level | 100 | 0 |  | 2027-11-13 |  | 2028-02-23
47891 |  | Not Ready |  | 2028-03-13 | 2028-04-04 | RCC upstand | 100 | 0 |  | 2027-11-13 |  | 2027-12-07
47891 |  | Not Ready |  | 2028-03-13 | 2028-04-04 | RCC upstand | 100 | 0 |  | 2027-11-13 |  | 2027-12-07
46155 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-10-14 | 2027-10-21 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-11-15 |  | 2027-11-23 |  | Tower B | Super Structure | L13
47405 | Tower B - Super Structure - Finishes & MEP - P3 to L7 | Not Ready | Façade Works - MEP & Finishes | 2027-09-02 | 2027-09-14 | Accessories & Alignment | 100 | 0 |  | 2027-11-15 |  | 2027-11-26 |  | Tower B | Super Structure |  | Façade | Façade Works
47405 | Tower B - Super Structure - Finishes & MEP - P3 to L7 | Not Ready | Façade Works - MEP & Finishes | 2027-09-02 | 2027-09-14 | Accessories & Alignment | 100 | 0 |  | 2027-11-15 |  | 2027-11-26 |  | Tower B | Super Structure
45687 | Tower B - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2027-10-06 | 2027-11-11 | Cable Tray & Cabling Work | 100 | 0 |  | 2027-11-16 |  | 2027-12-21 |  | Tower B | Super Structure
46260 | Tower B - Super Structure - Finishes & MEP - L20 to L21 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2027-10-15 | 2027-10-26 | Lobby Plastering | 100 | 0 |  | 2027-11-16 |  | 2027-11-27 |  | Tower B | Super Structure | L20 | Finishes | Lobby Plastering
46275 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2027-10-15 | 2027-10-20 | Lobby Blockwork | 100 | 0 |  | 2027-11-16 |  | 2027-11-22 |  | Tower B | Super Structure | L21 | Finishes | Blockwork
46411 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-09-03 | 2027-09-11 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-11-16 |  | 2027-11-24 |  | Tower B | Super Structure | L29
47032 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2027-10-25 | 2027-10-30 | Painting Works | 100 | 0 |  | 2027-11-16 |  | 2027-11-22 |  | Tower B | Super Structure | L27 | Finishes | Painting Works
45881 | Tower B - Super Structure - Finishes & MEP - GF to P1 - Floor Area | Not Ready | Fixing of Artifacts - MEP & Finishes | 2027-09-24 | 2027-11-01 | Fixing of Artifacts | 100 | 0 |  | 2027-11-17 |  | 2027-12-22 |  | Tower B | Super Structure | GF
46140 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-10-16 | 2027-10-23 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-11-17 |  | 2027-11-25 |  | Tower B | Super Structure | L12 | MEP | Electrical
46438 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-09-06 | 2027-09-20 | False Ceiling | 100 | 0 |  | 2027-11-17 |  | 2027-12-01 |  | Tower B | Super Structure | L31 | Finishes | False Ceiling
46469 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-09-06 | 2027-10-06 | Flooring & Dado | 100 | 0 |  | 2027-11-17 |  | 2027-12-16 |  | Tower B | Super Structure | L33 | Finishes | Flooring & Dado
46482 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-09-06 | 2027-09-16 | HVAC Ducting | 100 | 0 |  | 2027-11-17 |  | 2027-11-29 |  | Tower B | Super Structure | L34 | MEP | HVAC Ducting
46494 |  | Not Committed |  | 2027-09-06 | 2028-01-24 | L35-36 | 100 | 0 |  | 2027-11-17 |  | 2028-02-25
46494 |  | Not Committed |  | 2027-09-06 | 2028-01-24 | L35-36 | 100 | 0 |  | 2027-11-17 |  | 2028-02-25 |  |  |  |  | Finishes | Gypsum Plastering Works
46495 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-09-06 | 2027-09-16 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-11-17 |  | 2027-11-29 |  | Tower B | Super Structure | L35 | MEP | FPS 1st Fix - MEP & Finishes
46496 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-09-06 | 2027-09-13 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-11-17 |  | 2027-11-25 |  | Tower B | Super Structure | L35 | MEP | Electrical 1st Fixes
45670 | Tower B - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2027-10-18 | 2027-11-03 | Guide Rail Installation by rising platform (only car guide rails) | 100 | 0 |  | 2027-11-18 |  | 2027-12-04 |  | Tower B | Super Structure
46125 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-10-19 | 2027-10-26 | Final Painting | 100 | 0 |  | 2027-11-19 |  | 2027-11-27 |  | Tower B | Super Structure | L11 | Finishes | Final Painting
46125 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-10-19 | 2027-10-26 | Final Painting | 100 | 0 |  | 2027-11-19 |  | 2027-11-27 |  | Tower B | Super Structure | L11 | Finishes | Final Painting
46125 | Tower B - Super Structure - Finishes & MEP - L11 to L12 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-10-19 | 2027-10-26 | Final Painting | 100 | 0 |  | 2027-11-19 |  | 2027-11-27 |  | Tower B | Super Structure | L11 | Finishes | Final Painting
46423 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-09-08 | 2027-09-15 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-11-19 |  | 2027-11-27 |  | Tower B | Super Structure | L30 | MEP | FPS 2nd Fix - MEP & Finishes
46424 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-09-08 | 2027-09-15 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-11-19 |  | 2027-11-27 |  | Tower B | Super Structure | L30 | MEP | Electrical 2nd Fix - MEP & Finishes
46425 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-09-08 | 2027-09-20 | FAPA Device Fixing | 100 | 0 |  | 2027-11-19 |  | 2027-12-01 |  | Tower B | Super Structure | L30
46425 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-09-08 | 2027-09-20 | FAPA Device Fixing | 100 | 0 |  | 2027-11-19 |  | 2027-12-01 |  | Tower B | Super Structure | L30
46425 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-09-08 | 2027-09-20 | FAPA Device Fixing | 100 | 0 |  | 2027-11-19 |  | 2027-12-01 |  | Tower B | Super Structure | L30
46425 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-09-08 | 2027-09-20 | FAPA Device Fixing | 100 | 0 |  | 2027-11-19 |  | 2027-12-01 |  | Tower B | Super Structure | L30
46426 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-09-08 | 2027-09-15 | HVAC Grill Fixing | 100 | 0 |  | 2027-11-19 |  | 2027-11-27 |  | Tower B | Super Structure | L30 | MEP | HVAC Grill Fixing
47349 | Tower B - Super Structure - Finishes & MEP - GF to L7 | Not Ready | Staircase Finishes - MEP & Finishes | 2028-01-01 | 2028-03-13 | Staircase Flooring | 100 | 0 |  | 2027-11-19 |  | 2028-01-31 |  | Tower B | Super Structure | GF | Finishes | Staircase Flooring
47363 | Tower B - Super Structure - Finishes & MEP - L15 to L25 | Not Ready | Staircase Finishes - MEP & Finishes | 2028-01-01 | 2028-03-13 | Staircase Flooring | 100 | 0 |  | 2027-11-19 |  | 2028-01-31 |  | Tower B | Super Structure | L15 | Finishes | Staircase Flooring
47877 |  | Not Ready |  | 2028-03-18 | 2028-04-10 | Planter works | 100 | 0 |  | 2027-11-19 |  | 2027-12-13
47877 |  | Not Ready |  | 2028-03-18 | 2028-04-10 | Planter works | 100 | 0 |  | 2027-11-19 |  | 2027-12-13
46171 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-10-20 | 2027-10-27 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-11-20 |  | 2027-11-29 |  | Tower B | Super Structure | L14
46397 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-09-09 | 2027-09-16 | Final Painting | 100 | 0 |  | 2027-11-20 |  | 2027-11-29 |  | Tower B | Super Structure | L28 | Finishes | Final Painting
46397 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-09-09 | 2027-09-16 | Final Painting | 100 | 0 |  | 2027-11-20 |  | 2027-11-29 |  | Tower B | Super Structure | L28 | Finishes | Final Painting
46397 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-09-09 | 2027-09-16 | Final Painting | 100 | 0 |  | 2027-11-20 |  | 2027-11-29 |  | Tower B | Super Structure | L28 | Finishes | Final Painting
45718 |  | Not Committed |  | 2027-07-30 | 2028-01-28 | STP | 100 | 0 |  | 2027-11-22 |  | 2028-03-08
45718 |  | Not Committed |  | 2027-07-30 | 2028-01-28 | STP | 100 | 0 |  | 2027-11-22 |  | 2028-03-08
45719 | Tower B - Super Structure - Finishes & MEP - STP | Not Ready |  | 2027-07-30 | 2027-12-22 | Equipment Installation | 100 | 0 |  | 2027-11-22 |  | 2028-02-02 |  | Tower B | Super Structure
46276 | Tower B - Super Structure - Finishes & MEP - L21 to L22 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2027-10-21 | 2027-11-02 | Lobby Plastering | 100 | 0 |  | 2027-11-22 |  | 2027-12-03 |  | Tower B | Super Structure | L21 | Finishes | Lobby Plastering
46291 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2027-10-21 | 2027-10-26 | Lobby Blockwork | 100 | 0 |  | 2027-11-22 |  | 2027-11-27 |  | Tower B | Super Structure | L22 | Finishes | Blockwork
46156 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-10-22 | 2027-10-30 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-11-23 |  | 2027-12-01 |  | Tower B | Super Structure | L13 | MEP | Electrical
47818 |  | Not Ready |  | 2027-05-20 | 2027-06-05 | P1 to P2 | 100 | 0 |  | 2027-11-23 |  | 2027-12-10
47818 |  | Not Ready |  | 2027-05-20 | 2027-06-05 | P1 to P2 | 100 | 0 |  | 2027-11-23 |  | 2027-12-10
47818 |  | Not Ready |  | 2027-05-20 | 2027-06-05 | P1 to P2 | 100 | 0 |  | 2027-11-23 |  | 2027-12-10
47837 |  | Not Ready |  | 2027-05-14 | 2027-06-18 | Staircase Finishes | 100 | 0 |  | 2027-11-23 |  | 2027-12-29
47837 |  | Not Ready |  | 2027-05-14 | 2027-06-18 | Staircase Finishes | 100 | 0 |  | 2027-11-23 |  | 2027-12-29
47838 |  | Not Committed |  | 2028-03-22 | 2028-07-06 | GF to P1 | 100 | 0 |  | 2027-11-23 |  | 2028-03-09
47838 |  | Not Committed |  | 2028-03-22 | 2028-07-06 | GF to P1 | 100 | 0 |  | 2027-11-23 |  | 2028-03-09
47838 |  | Not Committed |  | 2028-03-22 | 2028-07-06 | GF to P1 | 100 | 0 |  | 2027-11-23 |  | 2028-03-09
47839 |  | Not Ready |  | 2028-03-22 | 2028-04-25 | VDF Flooring/ IPS in MEP Rooms | 100 | 0 |  | 2027-11-23 |  | 2027-12-29
46412 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-09-13 | 2027-09-21 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-11-24 |  | 2027-12-02 |  | Tower B | Super Structure | L29 | MEP | Electrical
47047 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-11-03 | 2027-11-10 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-11-24 |  | 2027-12-02 |  | Tower B | Super Structure | L28 | MEP | FPS 2nd Fix - MEP & Finishes
47048 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-11-03 | 2027-11-10 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-11-24 |  | 2027-12-02 |  | Tower B | Super Structure | L28 | MEP | Electrical 2nd Fix - MEP & Finishes
47049 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2027-11-03 | 2027-11-08 | PHE Final Fixes | 100 | 0 |  | 2027-11-24 |  | 2027-11-30 |  | Tower B | Super Structure | L28
47063 |  | Not Committed |  | 2027-11-03 | 2027-11-27 | MEP final fix & Finishes | 100 | 0 |  | 2027-11-24 |  | 2027-12-20
47064 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2027-11-03 | 2027-11-16 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2027-11-24 |  | 2027-12-08 |  | Tower B | Super Structure | L29 | Finishes | Door & Window Fixing
46141 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-10-25 | 2027-11-02 | Final Painting | 100 | 0 |  | 2027-11-25 |  | 2027-12-03 |  | Tower B | Super Structure | L12 | Finishes | Final Painting
46141 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-10-25 | 2027-11-02 | Final Painting | 100 | 0 |  | 2027-11-25 |  | 2027-12-03 |  | Tower B | Super Structure | L12 | Finishes | Final Painting
46141 | Tower B - Super Structure - Finishes & MEP - L12 to L13 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-10-25 | 2027-11-02 | Final Painting | 100 | 0 |  | 2027-11-25 |  | 2027-12-03 |  | Tower B | Super Structure | L12 | Finishes | Final Painting
46497 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-09-14 | 2027-09-22 | FAPA Cabling | 100 | 0 |  | 2027-11-25 |  | 2027-12-03 |  | Tower B | Super Structure | L35
47882 |  | Not Ready |  | 2028-03-24 | 2028-04-10 | Handrail lighting work | 100 | 0 |  | 2027-11-25 |  | 2027-12-13
47392 |  | Not Committed |  | 2027-09-15 | 2027-11-22 | P1-P3 | 100 | 0 |  | 2027-11-26 |  | 2028-02-01
47393 | Tower B - Super Structure - Finishes & MEP - P1 to P3 | Not Ready | Façade Works - MEP & Finishes | 2027-09-15 | 2027-10-22 | Al. Frame section (Mullion & Transom) Installation | 100 | 0 |  | 2027-11-26 |  | 2028-01-01 |  | Tower B | Super Structure |  | Façade | Façade Works
46292 | Tower B - Super Structure - Finishes & MEP - L22 to L23 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2027-10-27 | 2027-11-08 | Lobby Plastering | 100 | 0 |  | 2027-11-27 |  | 2027-12-09 |  | Tower B | Super Structure | L22 | Finishes | Lobby Plastering
46307 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2027-10-27 | 2027-11-02 | Lobby Blockwork | 100 | 0 |  | 2027-11-27 |  | 2027-12-03 |  | Tower B | Super Structure | L23 | Finishes | Blockwork
46427 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-09-16 | 2027-09-24 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-11-27 |  | 2027-12-06 |  | Tower B | Super Structure | L30
45712 | Tower B - Super Structure - Finishes & MEP - MEP Service Floors | Not Ready |  | 2027-10-14 | 2028-01-29 | Testing & Commissioning | 100 | 0 |  | 2027-11-29 |  | 2028-03-16 |  | Tower B | Super Structure
45712 | Tower B - Super Structure - Finishes & MEP - MEP Service Floors | Not Ready |  | 2027-10-14 | 2028-01-29 | Testing & Commissioning | 100 | 0 |  | 2027-11-29 |  | 2028-03-16 |  | Tower B | Super Structure
46172 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-10-28 | 2027-11-05 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-11-29 |  | 2027-12-07 |  | Tower B | Super Structure | L14 | MEP | Electrical
46454 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-09-18 | 2027-10-01 | False Ceiling | 100 | 0 |  | 2027-11-29 |  | 2027-12-13 |  | Tower B | Super Structure | L32 | Finishes | False Ceiling
46485 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-09-18 | 2027-10-19 | Flooring & Dado | 100 | 0 |  | 2027-11-29 |  | 2027-12-29 |  | Tower B | Super Structure | L34 | Finishes | Flooring & Dado
46498 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-09-18 | 2027-09-29 | HVAC Ducting | 100 | 0 |  | 2027-11-29 |  | 2027-12-10 |  | Tower B | Super Structure | L35 | MEP | HVAC Ducting
46510 |  | Not Committed |  | 2027-09-18 | 2028-01-31 | L36-37 | 100 | 0 |  | 2027-11-29 |  | 2028-03-03
46510 |  | Not Committed |  | 2027-09-18 | 2028-01-31 | L36-37 | 100 | 0 |  | 2027-11-29 |  | 2028-03-03 |  |  |  |  | Finishes | Gypsum Plastering Works
46511 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-09-18 | 2027-09-29 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-11-29 |  | 2027-12-10 |  | Tower B | Super Structure | L36 | MEP | FPS 1st Fix - MEP & Finishes
46512 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-09-18 | 2027-09-25 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-11-29 |  | 2027-12-07 |  | Tower B | Super Structure | L36 | MEP | Electrical 1st Fixes
47050 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2027-11-09 | 2027-11-13 | Painting Works | 100 | 0 |  | 2027-11-30 |  | 2027-12-06 |  | Tower B | Super Structure | L28 | Finishes | Painting Works
46157 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-11-01 | 2027-11-08 | Final Painting | 100 | 0 |  | 2027-12-01 |  | 2027-12-09 |  | Tower B | Super Structure | L13 | Finishes | Final Painting
46157 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-11-01 | 2027-11-08 | Final Painting | 100 | 0 |  | 2027-12-01 |  | 2027-12-09 |  | Tower B | Super Structure | L13 | Finishes | Final Painting
46157 | Tower B - Super Structure - Finishes & MEP - L13 to L14 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-11-01 | 2027-11-08 | Final Painting | 100 | 0 |  | 2027-12-01 |  | 2027-12-09 |  | Tower B | Super Structure | L13 | Finishes | Final Painting
46439 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-09-21 | 2027-09-28 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-12-01 |  | 2027-12-09 |  | Tower B | Super Structure | L31 | MEP | FPS 2nd Fix - MEP & Finishes
46440 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-09-21 | 2027-09-28 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-12-01 |  | 2027-12-09 |  | Tower B | Super Structure | L31 | MEP | Electrical 2nd Fix - MEP & Finishes
46441 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-09-21 | 2027-10-01 | FAPA Device Fixing | 100 | 0 |  | 2027-12-01 |  | 2027-12-13 |  | Tower B | Super Structure | L31
46441 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-09-21 | 2027-10-01 | FAPA Device Fixing | 100 | 0 |  | 2027-12-01 |  | 2027-12-13 |  | Tower B | Super Structure | L31
46441 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-09-21 | 2027-10-01 | FAPA Device Fixing | 100 | 0 |  | 2027-12-01 |  | 2027-12-13 |  | Tower B | Super Structure | L31
46441 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-09-21 | 2027-10-01 | FAPA Device Fixing | 100 | 0 |  | 2027-12-01 |  | 2027-12-13 |  | Tower B | Super Structure | L31
46442 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-09-21 | 2027-09-28 | HVAC Grill Fixing | 100 | 0 |  | 2027-12-01 |  | 2027-12-09 |  | Tower B | Super Structure | L31 | MEP | HVAC Grill Fixing
47887 |  | Not Ready |  | 2028-03-30 | 2028-04-15 | SS work | 100 | 0 |  | 2027-12-01 |  | 2027-12-18
46413 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-09-22 | 2027-09-29 | Final Painting | 100 | 0 |  | 2027-12-02 |  | 2027-12-10 |  | Tower B | Super Structure | L29 | Finishes | Final Painting
46413 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-09-22 | 2027-09-29 | Final Painting | 100 | 0 |  | 2027-12-02 |  | 2027-12-10 |  | Tower B | Super Structure | L29 | Finishes | Final Painting
46413 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-09-22 | 2027-09-29 | Final Painting | 100 | 0 |  | 2027-12-02 |  | 2027-12-10 |  | Tower B | Super Structure | L29 | Finishes | Final Painting
45674 | Tower B - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2027-11-15 | 2027-12-18 | Completion of Electrical Works | 100 | 0 |  | 2027-12-03 |  | 2028-01-08 |  | Tower B | Super Structure
45674 | Tower B - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2027-11-15 | 2027-12-18 | Completion of Electrical Works | 100 | 0 |  | 2027-12-03 |  | 2028-01-08 |  | Tower B | Super Structure
46308 | Tower B - Super Structure - Finishes & MEP - L23 to L24 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2027-11-03 | 2027-11-13 | Lobby Plastering | 100 | 0 |  | 2027-12-03 |  | 2027-12-15 |  | Tower B | Super Structure | L23 | Finishes | Lobby Plastering
46323 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2027-11-03 | 2027-11-08 | Lobby Blockwork | 100 | 0 |  | 2027-12-03 |  | 2027-12-09 |  | Tower B | Super Structure | L24 | Finishes | Blockwork
45671 | Tower B - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2027-11-04 | 2027-11-19 | Guide Rail installation for CWT (up to LMR) | 100 | 0 |  | 2027-12-04 |  | 2027-12-21 |  | Tower B | Super Structure
45671 | Tower B - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2027-11-04 | 2027-11-19 | Guide Rail installation for CWT (up to LMR) | 100 | 0 |  | 2027-12-04 |  | 2027-12-21 |  | Tower B | Super Structure
46428 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-09-25 | 2027-10-04 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-12-06 |  | 2027-12-14 |  | Tower B | Super Structure | L30 | MEP | Electrical
46173 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-11-06 | 2027-11-13 | Final Painting | 100 | 0 |  | 2027-12-07 |  | 2027-12-15 |  | Tower B | Super Structure | L14 | Finishes | Final Painting
46173 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-11-06 | 2027-11-13 | Final Painting | 100 | 0 |  | 2027-12-07 |  | 2027-12-15 |  | Tower B | Super Structure | L14 | Finishes | Final Painting
46173 | Tower B - Super Structure - Finishes & MEP - L14 to L15 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-11-06 | 2027-11-13 | Final Painting | 100 | 0 |  | 2027-12-07 |  | 2027-12-15 |  | Tower B | Super Structure | L14 | Finishes | Final Painting
46513 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-09-27 | 2027-10-05 | FAPA Cabling | 100 | 0 |  | 2027-12-07 |  | 2027-12-15 |  | Tower B | Super Structure | L36
47358 | Tower B - Super Structure - Finishes & MEP - L7 to L15 | Not Ready | Staircase Finishes - MEP & Finishes | 2028-01-19 | 2028-02-23 | Staircase Railing | 100 | 0 |  | 2027-12-07 |  | 2028-01-12 |  | Tower B | Super Structure | L7
47892 |  | Not Ready |  | 2028-04-05 | 2028-04-21 | Drainage pipe | 100 | 0 |  | 2027-12-07 |  | 2027-12-24
47892 |  | Not Ready |  | 2028-04-05 | 2028-04-21 | Drainage pipe | 100 | 0 |  | 2027-12-07 |  | 2027-12-24
47065 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-11-17 | 2027-11-24 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-12-08 |  | 2027-12-16 |  | Tower B | Super Structure | L29 | MEP | FPS 2nd Fix - MEP & Finishes
47066 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-11-17 | 2027-11-24 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-12-08 |  | 2027-12-16 |  | Tower B | Super Structure | L29 | MEP | Electrical 2nd Fix - MEP & Finishes
47067 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2027-11-17 | 2027-11-22 | PHE Final Fixes | 100 | 0 |  | 2027-12-08 |  | 2027-12-14 |  | Tower B | Super Structure | L29
47081 |  | Not Committed |  | 2027-11-17 | 2027-12-11 | MEP final fix & Finishes | 100 | 0 |  | 2027-12-08 |  | 2028-01-04
47082 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2027-11-17 | 2027-11-30 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2027-12-08 |  | 2027-12-22 |  | Tower B | Super Structure | L30 | Finishes | Door & Window Fixing
46324 | Tower B - Super Structure - Finishes & MEP - L24 to L25 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2027-11-09 | 2027-11-19 | Lobby Plastering | 100 | 0 |  | 2027-12-09 |  | 2027-12-21 |  | Tower B | Super Structure | L24 | Finishes | Lobby Plastering
46339 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2027-11-09 | 2027-11-13 | Lobby Blockwork | 100 | 0 |  | 2027-12-09 |  | 2027-12-15 |  | Tower B | Super Structure | L25 | Finishes | Blockwork
46443 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-09-29 | 2027-10-07 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-12-09 |  | 2027-12-17 |  | Tower B | Super Structure | L31
46470 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-09-30 | 2027-10-15 | False Ceiling | 100 | 0 |  | 2027-12-10 |  | 2027-12-24 |  | Tower B | Super Structure | L33 | Finishes | False Ceiling
46501 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-09-30 | 2027-11-01 | Flooring & Dado | 100 | 0 |  | 2027-12-10 |  | 2028-01-10 |  | Tower B | Super Structure | L35 | Finishes | Flooring & Dado
46514 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-09-30 | 2027-10-13 | HVAC Ducting | 100 | 0 |  | 2027-12-10 |  | 2027-12-22 |  | Tower B | Super Structure | L36 | MEP | HVAC Ducting
46526 |  | Not Committed |  | 2027-09-30 | 2028-02-05 | L37-38 | 100 | 0 |  | 2027-12-10 |  | 2028-03-16
46526 |  | Not Committed |  | 2027-09-30 | 2028-02-05 | L37-38 | 100 | 0 |  | 2027-12-10 |  | 2028-03-16 |  |  |  |  | Finishes | Gypsum Plastering Works
46527 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-09-30 | 2027-10-13 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-12-10 |  | 2027-12-22 |  | Tower B | Super Structure | L37 | MEP | FPS 1st Fix - MEP & Finishes
46528 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-09-30 | 2027-10-08 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-12-10 |  | 2027-12-18 |  | Tower B | Super Structure | L37 | MEP | Electrical 1st Fixes
47819 |  | Not Ready |  | 2027-06-07 | 2027-08-14 | P2 to P3 | 100 | 0 |  | 2027-12-10 |  | 2028-02-21
47819 |  | Not Ready |  | 2027-06-07 | 2027-08-14 | P2 to P3 | 100 | 0 |  | 2027-12-10 |  | 2028-02-21
47819 |  | Not Ready |  | 2027-06-07 | 2027-08-14 | P2 to P3 | 100 | 0 |  | 2027-12-10 |  | 2028-02-21
47843 |  | Not Committed |  | 2027-06-07 | 2027-09-21 | P1 to P2 | 100 | 0 |  | 2027-12-10 |  | 2028-03-28
47843 |  | Not Committed |  | 2027-06-07 | 2027-09-21 | P1 to P2 | 100 | 0 |  | 2027-12-10 |  | 2028-03-28
47843 |  | Not Committed |  | 2027-06-07 | 2027-09-21 | P1 to P2 | 100 | 0 |  | 2027-12-10 |  | 2028-03-28
47844 |  | Not Ready |  | 2027-06-07 | 2027-07-10 | VDF Flooring | 100 | 0 |  | 2027-12-10 |  | 2028-01-15
47844 |  | Not Ready |  | 2027-06-07 | 2027-07-10 | VDF Flooring | 100 | 0 |  | 2027-12-10 |  | 2028-01-15
46455 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-10-04 | 2027-10-12 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-12-13 |  | 2027-12-21 |  | Tower B | Super Structure | L32 | MEP | FPS 2nd Fix - MEP & Finishes
46456 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-10-04 | 2027-10-12 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-12-13 |  | 2027-12-21 |  | Tower B | Super Structure | L32 | MEP | Electrical 2nd Fix - MEP & Finishes
46457 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-10-04 | 2027-10-15 | FAPA Device Fixing | 100 | 0 |  | 2027-12-13 |  | 2027-12-24 |  | Tower B | Super Structure | L32
46457 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-10-04 | 2027-10-15 | FAPA Device Fixing | 100 | 0 |  | 2027-12-13 |  | 2027-12-24 |  | Tower B | Super Structure | L32
46457 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-10-04 | 2027-10-15 | FAPA Device Fixing | 100 | 0 |  | 2027-12-13 |  | 2027-12-24 |  | Tower B | Super Structure | L32
46457 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-10-04 | 2027-10-15 | FAPA Device Fixing | 100 | 0 |  | 2027-12-13 |  | 2027-12-24 |  | Tower B | Super Structure | L32
46458 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-10-04 | 2027-10-12 | HVAC Grill Fixing | 100 | 0 |  | 2027-12-13 |  | 2027-12-21 |  | Tower B | Super Structure | L32 | MEP | HVAC Grill Fixing
47462 |  | Not Committed |  | 2027-11-12 | 2028-04-05 | Façade Closure at Left Out Bay (front side) | 100 | 0 |  | 2027-12-13 |  | 2028-05-08
47463 |  | Not Committed |  | 2027-11-12 | 2028-01-06 | L7-15 | 100 | 0 |  | 2027-12-13 |  | 2028-02-08
47463 |  | Not Committed |  | 2027-11-12 | 2028-01-06 | L7-15 | 100 | 0 |  | 2027-12-13 |  | 2028-02-08
47464 | Tower B - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2027-11-12 | 2027-12-10 | Al. Frame Section Installation | 100 | 0 |  | 2027-12-13 |  | 2028-01-12 |  | Tower B | Super Structure | L7
47487 |  | Not Committed |  | 2027-11-12 | 2028-04-05 | Façade Closure at Left Out Bay (back side) | 100 | 0 |  | 2027-12-13 |  | 2028-05-08
47488 |  | Not Committed |  | 2027-11-12 | 2028-01-06 | L7-15 | 100 | 0 |  | 2027-12-13 |  | 2028-02-08
47488 |  | Not Committed |  | 2027-11-12 | 2028-01-06 | L7-15 | 100 | 0 |  | 2027-12-13 |  | 2028-02-08
47489 | Tower B - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2027-11-12 | 2027-12-10 | Al. Frame Section Installation | 100 | 0 |  | 2027-12-13 |  | 2028-01-12 |  | Tower B | Super Structure | L7
47883 |  | Not Ready |  | 2028-04-11 | 2028-05-04 | Planter works | 100 | 0 |  | 2027-12-13 |  | 2028-01-06
47883 |  | Not Ready |  | 2028-04-11 | 2028-05-04 | Planter works | 100 | 0 |  | 2027-12-13 |  | 2028-01-06
46429 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-10-05 | 2027-10-13 | Final Painting | 100 | 0 |  | 2027-12-14 |  | 2027-12-22 |  | Tower B | Super Structure | L30 | Finishes | Final Painting
46429 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-10-05 | 2027-10-13 | Final Painting | 100 | 0 |  | 2027-12-14 |  | 2027-12-22 |  | Tower B | Super Structure | L30 | Finishes | Final Painting
46429 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-10-05 | 2027-10-13 | Final Painting | 100 | 0 |  | 2027-12-14 |  | 2027-12-22 |  | Tower B | Super Structure | L30 | Finishes | Final Painting
47068 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2027-11-23 | 2027-11-27 | Painting Works | 100 | 0 |  | 2027-12-14 |  | 2027-12-20 |  | Tower B | Super Structure | L29 | Finishes | Painting Works
46340 | Tower B - Super Structure - Finishes & MEP - L25 to L26 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2027-11-15 | 2027-11-25 | Lobby Plastering | 100 | 0 |  | 2027-12-15 |  | 2027-12-28 |  | Tower B | Super Structure | L25 | Finishes | Lobby Plastering
46355 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2027-11-15 | 2027-11-19 | Lobby Blockwork | 100 | 0 |  | 2027-12-15 |  | 2027-12-21 |  | Tower B | Super Structure | L26 | Finishes | Blockwork
45713 |  | Not Committed |  | 2027-11-25 | 2028-06-27 | DG Sets | 100 | 0 |  | 2027-12-16 |  | 2028-07-19
45714 | Tower B - Super Structure - Finishes & MEP - DG Sets | Not Ready |  | 2027-11-25 | 2028-02-04 | DG Foundation | 100 | 0 |  | 2027-12-16 |  | 2028-02-26 |  | Tower B | Super Structure
46444 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-10-08 | 2027-10-16 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-12-17 |  | 2027-12-27 |  | Tower B | Super Structure | L31 | MEP | Electrical
46529 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-10-11 | 2027-10-18 | FAPA Cabling | 100 | 0 |  | 2027-12-18 |  | 2027-12-28 |  | Tower B | Super Structure | L37
47888 |  | Not Ready |  | 2028-04-17 | 2028-05-04 | Handrail lighting work | 100 | 0 |  | 2027-12-18 |  | 2028-01-06
45673 | Tower B - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2027-11-20 | 2027-12-18 | Roping & Car Fixing | 100 | 0 |  | 2027-12-21 |  | 2028-01-08 |  | Tower B | Super Structure
45673 | Tower B - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2027-11-20 | 2027-12-18 | Roping & Car Fixing | 100 | 0 |  | 2027-12-21 |  | 2028-01-08 |  | Tower B | Super Structure
45688 | Tower B - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2027-11-12 | 2027-11-29 | Connections & Termination Works | 100 | 0 |  | 2027-12-21 |  | 2028-01-08 |  | Tower B | Super Structure
46356 | Tower B - Super Structure - Finishes & MEP - L26 to L27 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2027-11-20 | 2027-12-01 | Lobby Plastering | 100 | 0 |  | 2027-12-21 |  | 2028-01-03 |  | Tower B | Super Structure | L26 | Finishes | Lobby Plastering
46371 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2027-11-20 | 2027-11-25 | Lobby Blockwork | 100 | 0 |  | 2027-12-21 |  | 2027-12-28 |  | Tower B | Super Structure | L27 | Finishes | Blockwork
46459 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-10-13 | 2027-10-20 | Staircase Fire Door Fixing | 100 | 0 |  | 2027-12-21 |  | 2027-12-30 |  | Tower B | Super Structure | L32
46486 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-10-14 | 2027-10-27 | False Ceiling | 100 | 0 |  | 2027-12-22 |  | 2028-01-06 |  | Tower B | Super Structure | L34 | Finishes | False Ceiling
46517 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-10-14 | 2027-11-12 | Flooring & Dado | 100 | 0 |  | 2027-12-22 |  | 2028-01-21 |  | Tower B | Super Structure | L36 | Finishes | Flooring & Dado
46530 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-10-14 | 2027-10-25 | HVAC Ducting | 100 | 0 |  | 2027-12-22 |  | 2028-01-04 |  | Tower B | Super Structure | L37 | MEP | HVAC Ducting
46542 |  | Not Committed |  | 2027-10-14 | 2028-02-11 | L38-39 | 100 | 0 |  | 2027-12-22 |  | 2028-03-28
46542 |  | Not Committed |  | 2027-10-14 | 2028-02-11 | L38-39 | 100 | 0 |  | 2027-12-22 |  | 2028-03-28 |  |  |  |  | Finishes | Gypsum Plastering Works
46543 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-10-14 | 2027-10-25 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2027-12-22 |  | 2028-01-04 |  | Tower B | Super Structure | L38 | MEP | FPS 1st Fix - MEP & Finishes
46544 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-10-14 | 2027-10-21 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2027-12-22 |  | 2027-12-31 |  | Tower B | Super Structure | L38 | MEP | Electrical 1st Fixes
47083 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-12-01 | 2027-12-08 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-12-22 |  | 2027-12-31 |  | Tower B | Super Structure | L30 | MEP | FPS 2nd Fix - MEP & Finishes
47084 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-12-01 | 2027-12-08 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-12-22 |  | 2027-12-31 |  | Tower B | Super Structure | L30 | MEP | Electrical 2nd Fix - MEP & Finishes
47085 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2027-12-01 | 2027-12-06 | PHE Final Fixes | 100 | 0 |  | 2027-12-22 |  | 2027-12-29 |  | Tower B | Super Structure | L30
47099 |  | Not Committed |  | 2027-12-01 | 2027-12-27 | MEP final fix & Finishes | 100 | 0 |  | 2027-12-22 |  | 2028-01-18
47100 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2027-12-01 | 2027-12-14 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2027-12-22 |  | 2028-01-06 |  | Tower B | Super Structure | L31 | Finishes | Door & Window Fixing
46471 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-10-16 | 2027-10-23 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2027-12-24 |  | 2028-01-03 |  | Tower B | Super Structure | L33 | MEP | FPS 2nd Fix - MEP & Finishes
46472 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-10-16 | 2027-10-23 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2027-12-24 |  | 2028-01-03 |  | Tower B | Super Structure | L33 | MEP | Electrical 2nd Fix - MEP & Finishes
46473 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-10-16 | 2027-10-27 | FAPA Device Fixing | 100 | 0 |  | 2027-12-24 |  | 2028-01-06 |  | Tower B | Super Structure | L33
46473 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-10-16 | 2027-10-27 | FAPA Device Fixing | 100 | 0 |  | 2027-12-24 |  | 2028-01-06 |  | Tower B | Super Structure | L33
46473 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-10-16 | 2027-10-27 | FAPA Device Fixing | 100 | 0 |  | 2027-12-24 |  | 2028-01-06 |  | Tower B | Super Structure | L33
46473 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-10-16 | 2027-10-27 | FAPA Device Fixing | 100 | 0 |  | 2027-12-24 |  | 2028-01-06 |  | Tower B | Super Structure | L33
46474 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-10-16 | 2027-10-23 | HVAC Grill Fixing | 100 | 0 |  | 2027-12-24 |  | 2028-01-03 |  | Tower B | Super Structure | L33 | MEP | HVAC Grill Fixing
47340 |  | Not Committed |  | 2028-02-07 | 2028-06-28 | GF-B3 | 100 | 0 |  | 2027-12-24 |  | 2028-05-18
47341 | Tower B - Super Structure - Finishes & MEP - B3 to GF | Not Ready | Staircase Finishes - MEP & Finishes | 2028-02-07 | 2028-03-30 | Staircase Wall & Ceiling finishes | 100 | 0 |  | 2027-12-24 |  | 2028-02-17 |  | Tower B | Super Structure | B3
47350 | Tower B - Super Structure - Finishes & MEP - GF to L7 | Not Ready | Staircase Finishes - MEP & Finishes | 2028-02-07 | 2028-03-13 | Staircase Window | 100 | 0 |  | 2027-12-24 |  | 2028-01-31 |  | Tower B | Super Structure | GF
47352 | Tower B - Super Structure - Finishes & MEP - GF to L7 | Not Ready | Staircase Finishes - MEP & Finishes | 2028-02-07 | 2028-02-23 | Staircase cabling | 100 | 0 |  | 2027-12-24 |  | 2028-01-12 |  | Tower B | Super Structure | GF
47364 | Tower B - Super Structure - Finishes & MEP - L15 to L25 | Not Ready | Staircase Finishes - MEP & Finishes | 2028-02-07 | 2028-03-13 | Staircase Window | 100 | 0 |  | 2027-12-24 |  | 2028-01-31 |  | Tower B | Super Structure | L15
47366 | Tower B - Super Structure - Finishes & MEP - L15 to L25 | Not Ready | Staircase Finishes - MEP & Finishes | 2028-02-07 | 2028-02-23 | Staircase cabling | 100 | 0 |  | 2027-12-24 |  | 2028-01-12 |  | Tower B | Super Structure | L15
47368 |  | Not Committed |  | 2028-02-07 | 2028-06-28 | L25-35 | 100 | 0 |  | 2027-12-24 |  | 2028-05-18
47368 |  | Not Committed |  | 2028-02-07 | 2028-06-28 | L25-35 | 100 | 0 |  | 2027-12-24 |  | 2028-05-18
47369 | Tower B - Super Structure - Finishes & MEP - L25 to L35 | Not Ready | Staircase Finishes - MEP & Finishes | 2028-02-07 | 2028-03-30 | Staircase Wall & Ceiling finishes | 100 | 0 |  | 2027-12-24 |  | 2028-02-17 |  | Tower B | Super Structure | L25
47893 |  | Not Ready |  | 2028-04-22 | 2028-05-10 | SS work | 100 | 0 |  | 2027-12-24 |  | 2028-01-12
46445 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-10-18 | 2027-10-25 | Final Painting | 100 | 0 |  | 2027-12-27 |  | 2028-01-04 |  | Tower B | Super Structure | L31 | Finishes | Final Painting
46445 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-10-18 | 2027-10-25 | Final Painting | 100 | 0 |  | 2027-12-27 |  | 2028-01-04 |  | Tower B | Super Structure | L31 | Finishes | Final Painting
46445 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-10-18 | 2027-10-25 | Final Painting | 100 | 0 |  | 2027-12-27 |  | 2028-01-04 |  | Tower B | Super Structure | L31 | Finishes | Final Painting
45689 | Tower B - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2027-11-18 | 2027-12-22 | Pump Testing & Commissioning | 100 | 0 |  | 2027-12-28 |  | 2028-02-02 |  | Tower B | Super Structure
46372 | Tower B - Super Structure - Finishes & MEP - L27 to L28 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2027-11-26 | 2027-12-07 | Lobby Plastering | 100 | 0 |  | 2027-12-28 |  | 2028-01-08 |  | Tower B | Super Structure | L27 | Finishes | Lobby Plastering
46387 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2027-11-26 | 2027-12-01 | Lobby Blockwork | 100 | 0 |  | 2027-12-28 |  | 2028-01-03 |  | Tower B | Super Structure | L28 | Finishes | Blockwork
47086 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2027-12-07 | 2027-12-11 | Painting Works | 100 | 0 |  | 2027-12-29 |  | 2028-01-04 |  | Tower B | Super Structure | L30 | Finishes | Painting Works
47840 |  | Not Ready |  | 2028-04-26 | 2028-05-20 | MEP Rooms - Plaster & IPS | 100 | 0 |  | 2027-12-29 |  | 2028-01-21
47840 |  | Not Ready |  | 2028-04-26 | 2028-05-20 | MEP Rooms - Plaster & IPS | 100 | 0 |  | 2027-12-29 |  | 2028-01-21
47841 |  | Not Ready |  | 2028-04-26 | 2028-06-01 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2027-12-29 |  | 2028-02-03
47841 |  | Not Ready |  | 2028-04-26 | 2028-06-01 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2027-12-29 |  | 2028-02-03
46460 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-10-21 | 2027-10-28 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2027-12-30 |  | 2028-01-07 |  | Tower B | Super Structure | L32 | MEP | Electrical
46545 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-10-22 | 2027-10-30 | FAPA Cabling | 100 | 0 |  | 2027-12-31 |  | 2028-01-08 |  | Tower B | Super Structure | L38
47394 | Tower B - Super Structure - Finishes & MEP - P1 to P3 | Not Ready | Façade Works - MEP & Finishes | 2027-10-23 | 2027-11-10 | DGU Assembly Installation | 100 | 0 |  | 2028-01-01 |  | 2028-01-19 |  | Tower B | Super Structure |  | Façade | Façade Works
47395 | Tower B - Super Structure - Finishes & MEP - P1 to P3 | Not Ready | Façade Works - MEP & Finishes | 2027-10-23 | 2027-11-22 | Installation of highly reflective metal sheet | 100 | 0 |  | 2028-01-01 |  | 2028-02-01 |  | Tower B | Super Structure |  | Façade | Façade Works
47396 | Tower B - Super Structure - Finishes & MEP - P1 to P3 | Not Ready | Façade Works - MEP & Finishes | 2027-10-23 | 2027-11-10 | Fixing of Backlit Laminated Glass assembly & ACP Panels | 100 | 0 |  | 2028-01-01 |  | 2028-01-19 |  | Tower B | Super Structure |  | Façade | Façade Works
47397 | Tower B - Super Structure - Finishes & MEP - P1 to P3 | Not Ready | Façade Works - MEP & Finishes | 2027-10-23 | 2027-11-04 | Fixing of Louvers | 100 | 0 |  | 2028-01-01 |  | 2028-01-13 |  | Tower B | Super Structure |  | Façade | Façade Works
47397 | Tower B - Super Structure - Finishes & MEP - P1 to P3 | Not Ready | Façade Works - MEP & Finishes | 2027-10-23 | 2027-11-04 | Fixing of Louvers | 100 | 0 |  | 2028-01-01 |  | 2028-01-13 |  | Tower B | Super Structure
46388 | Tower B - Super Structure - Finishes & MEP - L28 to L29 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2027-12-02 | 2027-12-13 | Lobby Plastering | 100 | 0 |  | 2028-01-03 |  | 2028-01-14 |  | Tower B | Super Structure | L28 | Finishes | Lobby Plastering
46403 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2027-12-02 | 2027-12-07 | Lobby Blockwork | 100 | 0 |  | 2028-01-03 |  | 2028-01-08 |  | Tower B | Super Structure | L29 | Finishes | Blockwork
46475 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-10-25 | 2027-11-02 | Staircase Fire Door Fixing | 100 | 0 |  | 2028-01-03 |  | 2028-01-11 |  | Tower B | Super Structure | L33
46502 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-10-26 | 2027-11-09 | False Ceiling | 100 | 0 |  | 2028-01-04 |  | 2028-01-18 |  | Tower B | Super Structure | L35 | Finishes | False Ceiling
46533 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-10-26 | 2027-11-24 | Flooring & Dado | 100 | 0 |  | 2028-01-04 |  | 2028-02-03 |  | Tower B | Super Structure | L37 | Finishes | Flooring & Dado
46546 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-10-26 | 2027-11-06 | HVAC Ducting | 100 | 0 |  | 2028-01-04 |  | 2028-01-15 |  | Tower B | Super Structure | L38 | MEP | HVAC Ducting
46558 |  | Not Committed |  | 2027-10-26 | 2028-02-17 | L39-40 | 100 | 0 |  | 2028-01-04 |  | 2028-04-08
46558 |  | Not Committed |  | 2027-10-26 | 2028-02-17 | L39-40 | 100 | 0 |  | 2028-01-04 |  | 2028-04-08 |  |  |  |  | Finishes | Gypsum Plastering Works
46559 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-10-26 | 2027-11-06 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2028-01-04 |  | 2028-01-15 |  | Tower B | Super Structure | L39 | MEP | FPS 1st Fix - MEP & Finishes
46560 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-10-26 | 2027-11-03 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2028-01-04 |  | 2028-01-12 |  | Tower B | Super Structure | L39 | MEP | Electrical 1st Fixes
46487 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-10-28 | 2027-11-05 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2028-01-06 |  | 2028-01-14 |  | Tower B | Super Structure | L34 | MEP | FPS 2nd Fix - MEP & Finishes
46488 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-10-28 | 2027-11-05 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2028-01-06 |  | 2028-01-14 |  | Tower B | Super Structure | L34 | MEP | Electrical 2nd Fix - MEP & Finishes
46489 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-10-28 | 2027-11-09 | FAPA Device Fixing | 100 | 0 |  | 2028-01-06 |  | 2028-01-18 |  | Tower B | Super Structure | L34
46489 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-10-28 | 2027-11-09 | FAPA Device Fixing | 100 | 0 |  | 2028-01-06 |  | 2028-01-18 |  | Tower B | Super Structure | L34
46489 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-10-28 | 2027-11-09 | FAPA Device Fixing | 100 | 0 |  | 2028-01-06 |  | 2028-01-18 |  | Tower B | Super Structure | L34
46489 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-10-28 | 2027-11-09 | FAPA Device Fixing | 100 | 0 |  | 2028-01-06 |  | 2028-01-18 |  | Tower B | Super Structure | L34
46490 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-10-28 | 2027-11-05 | HVAC Grill Fixing | 100 | 0 |  | 2028-01-06 |  | 2028-01-14 |  | Tower B | Super Structure | L34 | MEP | HVAC Grill Fixing
47101 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-12-15 | 2027-12-22 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2028-01-06 |  | 2028-01-14 |  | Tower B | Super Structure | L31 | MEP | FPS 2nd Fix - MEP & Finishes
47102 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-12-15 | 2027-12-22 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2028-01-06 |  | 2028-01-14 |  | Tower B | Super Structure | L31 | MEP | Electrical 2nd Fix - MEP & Finishes
47103 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2027-12-15 | 2027-12-20 | PHE Final Fixes | 100 | 0 |  | 2028-01-06 |  | 2028-01-12 |  | Tower B | Super Structure | L31
47117 |  | Not Committed |  | 2027-12-15 | 2028-01-10 | MEP final fix & Finishes | 100 | 0 |  | 2028-01-06 |  | 2028-02-02
47118 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2027-12-15 | 2027-12-29 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2028-01-06 |  | 2028-01-20 |  | Tower B | Super Structure | L32 | Finishes | Door & Window Fixing
47889 |  | Not Ready |  | 2028-05-05 | 2028-05-29 | Planter works | 100 | 0 |  | 2028-01-06 |  | 2028-01-31
47889 |  | Not Ready |  | 2028-05-05 | 2028-05-29 | Planter works | 100 | 0 |  | 2028-01-06 |  | 2028-01-31
46461 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-10-30 | 2027-11-06 | Final Painting | 100 | 0 |  | 2028-01-07 |  | 2028-01-15 |  | Tower B | Super Structure | L32 | Finishes | Final Painting
46461 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-10-30 | 2027-11-06 | Final Painting | 100 | 0 |  | 2028-01-07 |  | 2028-01-15 |  | Tower B | Super Structure | L32 | Finishes | Final Painting
46461 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-10-30 | 2027-11-06 | Final Painting | 100 | 0 |  | 2028-01-07 |  | 2028-01-15 |  | Tower B | Super Structure | L32 | Finishes | Final Painting
45675 | Tower B - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2027-12-20 | 2028-01-06 | Slow Speed Testing | 100 | 0 |  | 2028-01-08 |  | 2028-01-27 |  | Tower B | Super Structure
45675 | Tower B - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2027-12-20 | 2028-01-06 | Slow Speed Testing | 100 | 0 |  | 2028-01-08 |  | 2028-01-27 |  | Tower B | Super Structure
46404 | Tower B - Super Structure - Finishes & MEP - L29 to L30 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2027-12-08 | 2027-12-18 | Lobby Plastering | 100 | 0 |  | 2028-01-08 |  | 2028-01-20 |  | Tower B | Super Structure | L29 | Finishes | Lobby Plastering
46419 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2027-12-08 | 2027-12-13 | Lobby Blockwork | 100 | 0 |  | 2028-01-08 |  | 2028-01-14 |  | Tower B | Super Structure | L30 | Finishes | Blockwork
46476 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-11-03 | 2027-11-10 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2028-01-11 |  | 2028-01-19 |  | Tower B | Super Structure | L33 | MEP | Electrical
46561 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-11-04 | 2027-11-11 | FAPA Cabling | 100 | 0 |  | 2028-01-12 |  | 2028-01-20 |  | Tower B | Super Structure | L39
47104 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2027-12-21 | 2027-12-27 | Painting Works | 100 | 0 |  | 2028-01-12 |  | 2028-01-18 |  | Tower B | Super Structure | L31 | Finishes | Painting Works
47342 | Tower B - Super Structure - Finishes & MEP - B3 to GF | Not Ready | Staircase Finishes - MEP & Finishes | 2028-02-24 | 2028-05-05 | Staircase Flooring | 100 | 0 |  | 2028-01-12 |  | 2028-03-24 |  | Tower B | Super Structure | B3 | Finishes | Staircase Flooring
47360 | Tower B - Super Structure - Finishes & MEP - L7 to L15 | Not Ready | Staircase Finishes - MEP & Finishes | 2028-02-24 | 2028-03-13 | Staircase Light Fixtures & Devices fixing | 100 | 0 |  | 2028-01-12 |  | 2028-01-31 |  | Tower B | Super Structure | L7
47370 | Tower B - Super Structure - Finishes & MEP - L25 to L35 | Not Ready | Staircase Finishes - MEP & Finishes | 2028-02-24 | 2028-05-05 | Staircase Flooring | 100 | 0 |  | 2028-01-12 |  | 2028-03-24 |  | Tower B | Super Structure | L25 | Finishes | Staircase Flooring
47465 | Tower B - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2027-12-11 | 2027-12-29 | Glass Assembly Installation | 100 | 0 |  | 2028-01-12 |  | 2028-01-31 |  | Tower B | Super Structure | L7
47466 | Tower B - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2027-12-11 | 2027-12-22 | ACP Sheet & Insulation fixing | 100 | 0 |  | 2028-01-12 |  | 2028-01-24 |  | Tower B | Super Structure | L7
47467 | Tower B - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2027-12-11 | 2027-12-18 | Fixing of Louvers | 100 | 0 |  | 2028-01-12 |  | 2028-01-20 |  | Tower B | Super Structure | L7 | Façade | Façade Works
47467 | Tower B - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2027-12-11 | 2027-12-18 | Fixing of Louvers | 100 | 0 |  | 2028-01-12 |  | 2028-01-20 |  | Tower B | Super Structure | L7
47469 |  | Not Committed |  | 2027-12-11 | 2028-02-05 | L15-25 | 100 | 0 |  | 2028-01-12 |  | 2028-03-08
47469 |  | Not Committed |  | 2027-12-11 | 2028-02-05 | L15-25 | 100 | 0 |  | 2028-01-12 |  | 2028-03-08
47470 | Tower B - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2027-12-11 | 2028-01-10 | Al. Frame Section Installation | 100 | 0 |  | 2028-01-12 |  | 2028-02-11 |  | Tower B | Super Structure | L15
47490 | Tower B - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2027-12-11 | 2027-12-29 | Glass Assembly Installation | 100 | 0 |  | 2028-01-12 |  | 2028-01-31 |  | Tower B | Super Structure | L7
47491 | Tower B - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2027-12-11 | 2027-12-22 | ACP Sheet & Insulation fixing | 100 | 0 |  | 2028-01-12 |  | 2028-01-24 |  | Tower B | Super Structure | L7
47492 | Tower B - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2027-12-11 | 2027-12-18 | Fixing of Louvers | 100 | 0 |  | 2028-01-12 |  | 2028-01-20 |  | Tower B | Super Structure | L7 | Façade | Façade Works
47492 | Tower B - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2027-12-11 | 2027-12-18 | Fixing of Louvers | 100 | 0 |  | 2028-01-12 |  | 2028-01-20 |  | Tower B | Super Structure | L7
47494 |  | Not Committed |  | 2027-12-11 | 2028-02-05 | L15-25 | 100 | 0 |  | 2028-01-12 |  | 2028-03-08
47494 |  | Not Committed |  | 2027-12-11 | 2028-02-05 | L15-25 | 100 | 0 |  | 2028-01-12 |  | 2028-03-08
47495 | Tower B - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2027-12-11 | 2028-01-10 | Al. Frame Section Installation | 100 | 0 |  | 2028-01-12 |  | 2028-02-11 |  | Tower B | Super Structure | L15
47894 |  | Not Ready |  | 2028-05-11 | 2028-05-29 | Handrail lighting work | 100 | 0 |  | 2028-01-12 |  | 2028-01-31
46420 | Tower B - Super Structure - Finishes & MEP - L30 to L31 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2027-12-14 | 2027-12-24 | Lobby Plastering | 100 | 0 |  | 2028-01-14 |  | 2028-01-27 |  | Tower B | Super Structure | L30 | Finishes | Lobby Plastering
46435 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2027-12-14 | 2027-12-18 | Lobby Blockwork | 100 | 0 |  | 2028-01-14 |  | 2028-01-20 |  | Tower B | Super Structure | L31 | Finishes | Blockwork
46491 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-11-06 | 2027-11-13 | Staircase Fire Door Fixing | 100 | 0 |  | 2028-01-14 |  | 2028-01-22 |  | Tower B | Super Structure | L34
46518 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-11-08 | 2027-11-20 | False Ceiling | 100 | 0 |  | 2028-01-15 |  | 2028-01-31 |  | Tower B | Super Structure | L36 | Finishes | False Ceiling
46549 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-11-08 | 2027-12-06 | Flooring & Dado | 100 | 0 |  | 2028-01-15 |  | 2028-02-15 |  | Tower B | Super Structure | L38 | Finishes | Flooring & Dado
46562 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-11-08 | 2027-11-18 | HVAC Ducting | 100 | 0 |  | 2028-01-15 |  | 2028-01-28 |  | Tower B | Super Structure | L39 | MEP | HVAC Ducting
46574 |  | Not Committed |  | 2027-11-08 | 2028-02-23 | L40-41 | 100 | 0 |  | 2028-01-15 |  | 2028-04-20
46574 |  | Not Committed |  | 2027-11-08 | 2028-02-23 | L40-41 | 100 | 0 |  | 2028-01-15 |  | 2028-04-20 |  |  |  |  | Finishes | Gypsum Plastering Works
46575 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-11-08 | 2027-11-18 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2028-01-15 |  | 2028-01-28 |  | Tower B | Super Structure | L40 | MEP | FPS 1st Fix - MEP & Finishes
46576 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-11-08 | 2027-11-15 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2028-01-15 |  | 2028-01-24 |  | Tower B | Super Structure | L40 | MEP | Electrical 1st Fixes
47845 |  | Not Ready |  | 2027-07-12 | 2027-08-14 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2028-01-15 |  | 2028-02-21
47845 |  | Not Ready |  | 2027-07-12 | 2027-08-14 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2028-01-15 |  | 2028-02-21
46503 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-11-10 | 2027-11-17 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2028-01-18 |  | 2028-01-27 |  | Tower B | Super Structure | L35 | MEP | FPS 2nd Fix - MEP & Finishes
46504 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-11-10 | 2027-11-17 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2028-01-18 |  | 2028-01-27 |  | Tower B | Super Structure | L35 | MEP | Electrical 2nd Fix - MEP & Finishes
46505 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-11-10 | 2027-11-20 | FAPA Device Fixing | 100 | 0 |  | 2028-01-18 |  | 2028-01-31 |  | Tower B | Super Structure | L35
46505 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-11-10 | 2027-11-20 | FAPA Device Fixing | 100 | 0 |  | 2028-01-18 |  | 2028-01-31 |  | Tower B | Super Structure | L35
46505 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-11-10 | 2027-11-20 | FAPA Device Fixing | 100 | 0 |  | 2028-01-18 |  | 2028-01-31 |  | Tower B | Super Structure | L35
46505 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-11-10 | 2027-11-20 | FAPA Device Fixing | 100 | 0 |  | 2028-01-18 |  | 2028-01-31 |  | Tower B | Super Structure | L35
46506 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-11-10 | 2027-11-17 | HVAC Grill Fixing | 100 | 0 |  | 2028-01-18 |  | 2028-01-27 |  | Tower B | Super Structure | L35 | MEP | HVAC Grill Fixing
46477 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-11-11 | 2027-11-18 | Final Painting | 100 | 0 |  | 2028-01-19 |  | 2028-01-28 |  | Tower B | Super Structure | L33 | Finishes | Final Painting
46477 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-11-11 | 2027-11-18 | Final Painting | 100 | 0 |  | 2028-01-19 |  | 2028-01-28 |  | Tower B | Super Structure | L33 | Finishes | Final Painting
46477 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-11-11 | 2027-11-18 | Final Painting | 100 | 0 |  | 2028-01-19 |  | 2028-01-28 |  | Tower B | Super Structure | L33 | Finishes | Final Painting
47398 | Tower B - Super Structure - Finishes & MEP - P1 to P3 | Not Ready | Façade Works - MEP & Finishes | 2027-11-11 | 2027-11-22 | Accessories & Alignment | 100 | 0 |  | 2028-01-19 |  | 2028-02-01 |  | Tower B | Super Structure |  | Façade | Façade Works
47398 | Tower B - Super Structure - Finishes & MEP - P1 to P3 | Not Ready | Façade Works - MEP & Finishes | 2027-11-11 | 2027-11-22 | Accessories & Alignment | 100 | 0 |  | 2028-01-19 |  | 2028-02-01 |  | Tower B | Super Structure
46436 | Tower B - Super Structure - Finishes & MEP - L31 to L32 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2027-12-20 | 2027-12-31 | Lobby Plastering | 100 | 0 |  | 2028-01-20 |  | 2028-02-02 |  | Tower B | Super Structure | L31 | Finishes | Lobby Plastering
46451 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2027-12-20 | 2027-12-24 | Lobby Blockwork | 100 | 0 |  | 2028-01-20 |  | 2028-01-27 |  | Tower B | Super Structure | L32 | Finishes | Blockwork
47119 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-12-30 | 2028-01-06 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2028-01-20 |  | 2028-01-29 |  | Tower B | Super Structure | L32 | MEP | FPS 2nd Fix - MEP & Finishes
47120 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-12-30 | 2028-01-06 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2028-01-20 |  | 2028-01-29 |  | Tower B | Super Structure | L32 | MEP | Electrical 2nd Fix - MEP & Finishes
47121 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2027-12-30 | 2028-01-04 | PHE Final Fixes | 100 | 0 |  | 2028-01-20 |  | 2028-01-27 |  | Tower B | Super Structure | L32
47135 |  | Not Committed |  | 2027-12-30 | 2028-01-24 | MEP final fix & Finishes | 100 | 0 |  | 2028-01-20 |  | 2028-02-16
47136 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2027-12-30 | 2028-01-12 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2028-01-20 |  | 2028-02-04 |  | Tower B | Super Structure | L33 | Finishes | Door & Window Fixing
46492 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-11-15 | 2027-11-22 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2028-01-22 |  | 2028-02-01 |  | Tower B | Super Structure | L34 | MEP | Electrical
46577 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-11-16 | 2027-11-23 | FAPA Cabling | 100 | 0 |  | 2028-01-24 |  | 2028-02-02 |  | Tower B | Super Structure | L40
45676 | Tower B - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2028-01-07 | 2028-01-24 | Balancing, Load Testing, High Speed Testing | 100 | 0 |  | 2028-01-27 |  | 2028-02-14 |  | Tower B | Super Structure
45676 | Tower B - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2028-01-07 | 2028-01-24 | Balancing, Load Testing, High Speed Testing | 100 | 0 |  | 2028-01-27 |  | 2028-02-14 |  | Tower B | Super Structure
45690 | Tower B - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2027-12-17 | 2028-01-04 | Wiring & Light Fixture | 100 | 0 |  | 2028-01-27 |  | 2028-02-14 |  | Tower B | Super Structure
46452 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2027-12-27 | 2028-01-06 | Lobby Plastering | 100 | 0 |  | 2028-01-27 |  | 2028-02-08 |  | Tower B | Super Structure | L32 | Finishes | Lobby Plastering
46467 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2027-12-27 | 2027-12-31 | Lobby Blockwork | 100 | 0 |  | 2028-01-27 |  | 2028-02-02 |  | Tower B | Super Structure | L33 | Finishes | Blockwork
46507 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-11-18 | 2027-11-25 | Staircase Fire Door Fixing | 100 | 0 |  | 2028-01-27 |  | 2028-02-04 |  | Tower B | Super Structure | L35
47122 | Tower B - Super Structure - Finishes & MEP - L32 to L33 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2028-01-05 | 2028-01-10 | Painting Works | 100 | 0 |  | 2028-01-27 |  | 2028-02-02 |  | Tower B | Super Structure | L32 | Finishes | Painting Works
45694 |  | Not Committed |  | 2027-07-20 | 2028-07-20 | Sub-Station | 100 | 0 |  | 2028-01-28 |  | 2028-07-31
45695 | Tower B - Super Structure - Finishes & MEP - Sub Station | Not Ready | Sub Station - High Side Services | 2027-07-20 | 2027-09-29 | Masonry Works (Trench, Partitions etc) | 100 | 0 |  | 2028-01-28 |  | 2028-02-21 |  | Tower B | Super Structure
46534 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-11-19 | 2027-12-02 | False Ceiling | 100 | 0 |  | 2028-01-28 |  | 2028-02-11 |  | Tower B | Super Structure | L37 | Finishes | False Ceiling
46565 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-11-19 | 2027-12-17 | Flooring & Dado | 100 | 0 |  | 2028-01-28 |  | 2028-02-26 |  | Tower B | Super Structure | L39 | Finishes | Flooring & Dado
46578 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-11-19 | 2027-11-30 | HVAC Ducting | 100 | 0 |  | 2028-01-28 |  | 2028-02-09 |  | Tower B | Super Structure | L40 | MEP | HVAC Ducting
46590 |  | Not Committed |  | 2027-11-19 | 2028-02-29 | L41-42 | 100 | 0 |  | 2028-01-28 |  | 2028-05-03
46590 |  | Not Committed |  | 2027-11-19 | 2028-02-29 | L41-42 | 100 | 0 |  | 2028-01-28 |  | 2028-05-03 |  |  |  |  | Finishes | Gypsum Plastering Works
46591 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-11-19 | 2027-11-30 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2028-01-28 |  | 2028-02-09 |  | Tower B | Super Structure | L41 | MEP | FPS 1st Fix - MEP & Finishes
46592 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-11-19 | 2027-11-26 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2028-01-28 |  | 2028-02-05 |  | Tower B | Super Structure | L41 | MEP | Electrical 1st Fixes
46519 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-11-22 | 2027-11-29 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2028-01-31 |  | 2028-02-08 |  | Tower B | Super Structure | L36 | MEP | FPS 2nd Fix - MEP & Finishes
46520 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-11-22 | 2027-11-29 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2028-01-31 |  | 2028-02-08 |  | Tower B | Super Structure | L36 | MEP | Electrical 2nd Fix - MEP & Finishes
46521 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-11-22 | 2027-12-02 | FAPA Device Fixing | 100 | 0 |  | 2028-01-31 |  | 2028-02-11 |  | Tower B | Super Structure | L36
46521 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-11-22 | 2027-12-02 | FAPA Device Fixing | 100 | 0 |  | 2028-01-31 |  | 2028-02-11 |  | Tower B | Super Structure | L36
46521 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-11-22 | 2027-12-02 | FAPA Device Fixing | 100 | 0 |  | 2028-01-31 |  | 2028-02-11 |  | Tower B | Super Structure | L36
46521 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-11-22 | 2027-12-02 | FAPA Device Fixing | 100 | 0 |  | 2028-01-31 |  | 2028-02-11 |  | Tower B | Super Structure | L36
46522 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-11-22 | 2027-11-29 | HVAC Grill Fixing | 100 | 0 |  | 2028-01-31 |  | 2028-02-08 |  | Tower B | Super Structure | L36 | MEP | HVAC Grill Fixing
47351 | Tower B - Super Structure - Finishes & MEP - GF to L7 | Not Ready | Staircase Finishes - MEP & Finishes | 2028-03-14 | 2028-04-17 | Staircase Railing | 100 | 0 |  | 2028-01-31 |  | 2028-03-06 |  | Tower B | Super Structure | GF
47365 | Tower B - Super Structure - Finishes & MEP - L15 to L25 | Not Ready | Staircase Finishes - MEP & Finishes | 2028-03-14 | 2028-04-17 | Staircase Railing | 100 | 0 |  | 2028-01-31 |  | 2028-03-06 |  | Tower B | Super Structure | L15
47468 | Tower B - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2027-12-30 | 2028-01-06 | Accessories & Alignment | 100 | 0 |  | 2028-01-31 |  | 2028-02-08 |  | Tower B | Super Structure | L7 | Façade | Façade Works
47468 | Tower B - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2027-12-30 | 2028-01-06 | Accessories & Alignment | 100 | 0 |  | 2028-01-31 |  | 2028-02-08 |  | Tower B | Super Structure | L7
47493 | Tower B - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2027-12-30 | 2028-01-06 | Accessories & Alignment | 100 | 0 |  | 2028-01-31 |  | 2028-02-08 |  | Tower B | Super Structure | L7 | Façade | Façade Works
47493 | Tower B - Super Structure - Finishes & MEP - L7 to L15 | Not Ready |  | 2027-12-30 | 2028-01-06 | Accessories & Alignment | 100 | 0 |  | 2028-01-31 |  | 2028-02-08 |  | Tower B | Super Structure | L7
47895 |  | Not Ready |  | 2028-05-30 | 2028-06-21 | Planter works | 100 | 0 |  | 2028-01-31 |  | 2028-02-23
47895 |  | Not Ready |  | 2028-05-30 | 2028-06-21 | Planter works | 100 | 0 |  | 2028-01-31 |  | 2028-02-23
46493 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-11-23 | 2027-11-30 | Final Painting | 100 | 0 |  | 2028-02-01 |  | 2028-02-09 |  | Tower B | Super Structure | L34 | Finishes | Final Painting
46493 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-11-23 | 2027-11-30 | Final Painting | 100 | 0 |  | 2028-02-01 |  | 2028-02-09 |  | Tower B | Super Structure | L34 | Finishes | Final Painting
46493 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-11-23 | 2027-11-30 | Final Painting | 100 | 0 |  | 2028-02-01 |  | 2028-02-09 |  | Tower B | Super Structure | L34 | Finishes | Final Painting
47384 |  | Not Committed |  | 2027-11-23 | 2028-02-19 | GF-P1 | 100 | 0 |  | 2028-02-01 |  | 2028-04-29
47385 | Tower B - Super Structure - Finishes & MEP - GF to P1 | Not Ready | Façade Works - MEP & Finishes | 2027-11-23 | 2027-12-28 | Al. Frame section (Mullion & Transom) Installation | 100 | 0 |  | 2028-02-01 |  | 2028-03-07 |  | Tower B | Super Structure | GF | Façade | Façade Works
45720 | Tower B - Super Structure - Finishes & MEP - STP | Not Ready |  | 2027-12-23 | 2028-01-28 | Testing & Commissioning | 100 | 0 |  | 2028-02-02 |  | 2028-03-08 |  | Tower B | Super Structure
45720 | Tower B - Super Structure - Finishes & MEP - STP | Not Ready |  | 2027-12-23 | 2028-01-28 | Testing & Commissioning | 100 | 0 |  | 2028-02-02 |  | 2028-03-08 |  | Tower B | Super Structure
46468 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2028-01-01 | 2028-01-12 | Lobby Plastering | 100 | 0 |  | 2028-02-02 |  | 2028-02-14 |  | Tower B | Super Structure | L33 | Finishes | Lobby Plastering
46483 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2028-01-01 | 2028-01-06 | Lobby Blockwork | 100 | 0 |  | 2028-02-02 |  | 2028-02-08 |  | Tower B | Super Structure | L34 | Finishes | Blockwork
47456 |  | Not Ready |  | 2027-12-17 | 2028-06-14 | BMU Installation | 100 | 0 |  | 2028-02-02 |  | 2028-07-29
47456 |  | Not Ready |  | 2027-12-17 | 2028-06-14 | BMU Installation | 100 | 0 |  | 2028-02-02 |  | 2028-07-29
47457 | Tower B | Not Ready | BMU Installation | 2027-12-17 | 2028-02-26 | Pedestal & Support Structure | 100 | 0 |  | 2028-02-02 |  | 2028-04-13 |  | Tower B | --
47842 |  | Not Ready |  | 2028-06-02 | 2028-07-06 | Staircase Finishes | 100 | 0 |  | 2028-02-03 |  | 2028-03-09
47842 |  | Not Ready |  | 2028-06-02 | 2028-07-06 | Staircase Finishes | 100 | 0 |  | 2028-02-03 |  | 2028-03-09
46508 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-11-26 | 2027-12-03 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2028-02-04 |  | 2028-02-12 |  | Tower B | Super Structure | L35 | MEP | Electrical
47137 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2028-01-13 | 2028-01-20 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2028-02-04 |  | 2028-02-12 |  | Tower B | Super Structure | L33 | MEP | FPS 2nd Fix - MEP & Finishes
47138 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2028-01-13 | 2028-01-20 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2028-02-04 |  | 2028-02-12 |  | Tower B | Super Structure | L33 | MEP | Electrical 2nd Fix - MEP & Finishes
47139 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2028-01-13 | 2028-01-18 | PHE Final Fixes | 100 | 0 |  | 2028-02-04 |  | 2028-02-10 |  | Tower B | Super Structure | L33
47153 |  | Not Committed |  | 2028-01-13 | 2028-02-08 | MEP final fix & Finishes | 100 | 0 |  | 2028-02-04 |  | 2028-03-01
47154 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2028-01-13 | 2028-01-27 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2028-02-04 |  | 2028-02-18 |  | Tower B | Super Structure | L34 | Finishes | Door & Window Fixing
46593 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-11-27 | 2027-12-04 | FAPA Cabling | 100 | 0 |  | 2028-02-05 |  | 2028-02-14 |  | Tower B | Super Structure | L41
45691 | Tower B - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2027-12-30 | 2028-01-28 | FAPA Cable Works | 100 | 0 |  | 2028-02-08 |  | 2028-03-08 |  | Tower B | Super Structure
46484 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2028-01-07 | 2028-01-18 | Lobby Plastering | 100 | 0 |  | 2028-02-08 |  | 2028-02-19 |  | Tower B | Super Structure | L34 | Finishes | Lobby Plastering
46499 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2028-01-07 | 2028-01-12 | Lobby Blockwork | 100 | 0 |  | 2028-02-08 |  | 2028-02-14 |  | Tower B | Super Structure | L35 | Finishes | Blockwork
46523 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-11-30 | 2027-12-07 | Staircase Fire Door Fixing | 100 | 0 |  | 2028-02-08 |  | 2028-02-16 |  | Tower B | Super Structure | L36
47512 |  | Not Committed |  | 2028-01-07 | 2028-07-21 | Hoist Corridor Finishes | 100 | 0 |  | 2028-02-08 |  | 2028-08-22
47513 | Tower B - Super Structure - Finishes & MEP - L7 to L15 | Not Ready | Hoist Corridor Finishes | 2028-01-07 | 2028-04-22 | L7-15 | 100 | 0 |  | 2028-02-08 |  | 2028-05-26 |  | Tower B | Super Structure | L7
47513 | Tower B - Super Structure - Finishes & MEP - L7 to L15 | Not Ready | Hoist Corridor Finishes | 2028-01-07 | 2028-04-22 | L7-15 | 100 | 0 |  | 2028-02-08 |  | 2028-05-26 |  | Tower B | Super Structure | L7
46550 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-12-01 | 2027-12-14 | False Ceiling | 100 | 0 |  | 2028-02-09 |  | 2028-02-23 |  | Tower B | Super Structure | L38 | Finishes | False Ceiling
46581 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-12-01 | 2027-12-30 | Flooring & Dado | 100 | 0 |  | 2028-02-09 |  | 2028-03-09 |  | Tower B | Super Structure | L40 | Finishes | Flooring & Dado
46594 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-12-01 | 2027-12-11 | HVAC Ducting | 100 | 0 |  | 2028-02-09 |  | 2028-02-21 |  | Tower B | Super Structure | L41 | MEP | HVAC Ducting
46606 |  | Not Committed |  | 2027-12-01 | 2028-03-06 | L42-43 | 100 | 0 |  | 2028-02-09 |  | 2028-05-15
46606 |  | Not Committed |  | 2027-12-01 | 2028-03-06 | L42-43 | 100 | 0 |  | 2028-02-09 |  | 2028-05-15 |  |  |  |  | Finishes | Gypsum Plastering Works
46607 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-12-01 | 2027-12-11 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2028-02-09 |  | 2028-02-21 |  | Tower B | Super Structure | L42 | MEP | FPS 1st Fix - MEP & Finishes
46608 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-12-01 | 2027-12-08 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2028-02-09 |  | 2028-02-17 |  | Tower B | Super Structure | L42 | MEP | Electrical 1st Fixes
47140 | Tower B - Super Structure - Finishes & MEP - L33 to L34 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2028-01-19 | 2028-01-24 | Painting Works | 100 | 0 |  | 2028-02-10 |  | 2028-02-16 |  | Tower B | Super Structure | L33 | Finishes | Painting Works
46535 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-12-03 | 2027-12-10 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2028-02-11 |  | 2028-02-19 |  | Tower B | Super Structure | L37 | MEP | FPS 2nd Fix - MEP & Finishes
46536 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-12-03 | 2027-12-10 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2028-02-11 |  | 2028-02-19 |  | Tower B | Super Structure | L37 | MEP | Electrical 2nd Fix - MEP & Finishes
46537 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-12-03 | 2027-12-14 | FAPA Device Fixing | 100 | 0 |  | 2028-02-11 |  | 2028-02-23 |  | Tower B | Super Structure | L37
46537 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-12-03 | 2027-12-14 | FAPA Device Fixing | 100 | 0 |  | 2028-02-11 |  | 2028-02-23 |  | Tower B | Super Structure | L37
46537 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-12-03 | 2027-12-14 | FAPA Device Fixing | 100 | 0 |  | 2028-02-11 |  | 2028-02-23 |  | Tower B | Super Structure | L37
46537 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-12-03 | 2027-12-14 | FAPA Device Fixing | 100 | 0 |  | 2028-02-11 |  | 2028-02-23 |  | Tower B | Super Structure | L37
46538 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-12-03 | 2027-12-10 | HVAC Grill Fixing | 100 | 0 |  | 2028-02-11 |  | 2028-02-19 |  | Tower B | Super Structure | L37 | MEP | HVAC Grill Fixing
47471 | Tower B - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2028-01-11 | 2028-01-28 | Glass Assembly Installation | 100 | 0 |  | 2028-02-11 |  | 2028-02-29 |  | Tower B | Super Structure | L15
47472 | Tower B - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2028-01-11 | 2028-01-21 | ACP Sheet & Insulation fixing | 100 | 0 |  | 2028-02-11 |  | 2028-02-23 |  | Tower B | Super Structure | L15
47473 | Tower B - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2028-01-11 | 2028-01-18 | Fixing of Louvers | 100 | 0 |  | 2028-02-11 |  | 2028-02-19 |  | Tower B | Super Structure | L15 | Façade | Façade Works
47473 | Tower B - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2028-01-11 | 2028-01-18 | Fixing of Louvers | 100 | 0 |  | 2028-02-11 |  | 2028-02-19 |  | Tower B | Super Structure | L15
47475 |  | Not Committed |  | 2028-01-11 | 2028-03-06 | L25-35 | 100 | 0 |  | 2028-02-11 |  | 2028-04-07
47475 |  | Not Committed |  | 2028-01-11 | 2028-03-06 | L25-35 | 100 | 0 |  | 2028-02-11 |  | 2028-04-07
47476 | Tower B - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2028-01-11 | 2028-02-09 | Al. Frame Section Installation | 100 | 0 |  | 2028-02-11 |  | 2028-03-13 |  | Tower B | Super Structure | L25
47496 | Tower B - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2028-01-11 | 2028-01-28 | Glass Assembly Installation | 100 | 0 |  | 2028-02-11 |  | 2028-02-29 |  | Tower B | Super Structure | L15
47497 | Tower B - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2028-01-11 | 2028-01-21 | ACP Sheet & Insulation fixing | 100 | 0 |  | 2028-02-11 |  | 2028-02-23 |  | Tower B | Super Structure | L15
47498 | Tower B - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2028-01-11 | 2028-01-18 | Fixing of Louvers | 100 | 0 |  | 2028-02-11 |  | 2028-02-19 |  | Tower B | Super Structure | L15 | Façade | Façade Works
47498 | Tower B - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2028-01-11 | 2028-01-18 | Fixing of Louvers | 100 | 0 |  | 2028-02-11 |  | 2028-02-19 |  | Tower B | Super Structure | L15
47500 |  | Not Committed |  | 2028-01-11 | 2028-03-06 | L25-35 | 100 | 0 |  | 2028-02-11 |  | 2028-04-07
47500 |  | Not Committed |  | 2028-01-11 | 2028-03-06 | L25-35 | 100 | 0 |  | 2028-02-11 |  | 2028-04-07
47501 | Tower B - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2028-01-11 | 2028-02-09 | Al. Frame Section Installation | 100 | 0 |  | 2028-02-11 |  | 2028-03-13 |  | Tower B | Super Structure | L25
46509 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-12-04 | 2027-12-11 | Final Painting | 100 | 0 |  | 2028-02-12 |  | 2028-02-21 |  | Tower B | Super Structure | L35 | Finishes | Final Painting
46509 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-12-04 | 2027-12-11 | Final Painting | 100 | 0 |  | 2028-02-12 |  | 2028-02-21 |  | Tower B | Super Structure | L35 | Finishes | Final Painting
46509 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-12-04 | 2027-12-11 | Final Painting | 100 | 0 |  | 2028-02-12 |  | 2028-02-21 |  | Tower B | Super Structure | L35 | Finishes | Final Painting
45677 | Tower B - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2028-01-25 | 2028-02-05 | 3rd Party Testing & Commissioning | 100 | 0 |  | 2028-02-14 |  | 2028-02-25 |  | Tower B | Super Structure
45677 | Tower B - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2028-01-25 | 2028-02-05 | 3rd Party Testing & Commissioning | 100 | 0 |  | 2028-02-14 |  | 2028-02-25 |  | Tower B | Super Structure
46500 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2028-01-13 | 2028-01-24 | Lobby Plastering | 100 | 0 |  | 2028-02-14 |  | 2028-02-25 |  | Tower B | Super Structure | L35 | Finishes | Lobby Plastering
46515 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2028-01-13 | 2028-01-18 | Lobby Blockwork | 100 | 0 |  | 2028-02-14 |  | 2028-02-19 |  | Tower B | Super Structure | L36 | Finishes | Blockwork
46524 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-12-08 | 2027-12-15 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2028-02-16 |  | 2028-02-24 |  | Tower B | Super Structure | L36 | MEP | Electrical
47896 |  | Not Committed |  | 2028-02-07 | 2028-06-21 | Final MEP fix & Finishes (after Tower B High Side) | 100 | 0 |  | 2028-02-16 |  | 2028-07-01
47897 |  | Not Committed |  | 2028-02-07 | 2028-03-20 | B3 to B2 | 100 | 0 |  | 2028-02-16 |  | 2028-03-30
47897 |  | Not Committed |  | 2028-02-07 | 2028-03-20 | B3 to B2 | 100 | 0 |  | 2028-02-16 |  | 2028-03-30
47897 |  | Not Committed |  | 2028-02-07 | 2028-03-20 | B3 to B2 | 100 | 0 |  | 2028-02-16 |  | 2028-03-30
47898 |  | Not Ready |  | 2028-02-07 | 2028-02-14 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2028-02-16 |  | 2028-02-24 |  |  |  |  | MEP | FPS final fixes
47898 |  | Not Ready |  | 2028-02-07 | 2028-02-14 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2028-02-16 |  | 2028-02-24 |  |  |  |  | MEP | FPS final fixes
47945 |  | Not Committed |  | 2028-02-07 | 2028-05-24 | Landscape on P5 level | 100 | 0 |  | 2028-02-16 |  | 2028-06-03
47946 |  | Not Ready |  | 2028-02-07 | 2028-03-30 | Above Terrace Structure/ Hardscape works | 100 | 0 |  | 2028-02-16 |  | 2028-04-10
47946 |  | Not Ready |  | 2028-02-07 | 2028-03-30 | Above Terrace Structure/ Hardscape works | 100 | 0 |  | 2028-02-16 |  | 2028-04-10
47947 |  | Not Ready |  | 2028-02-07 | 2028-03-30 | Tower A canopy at P5 | 100 | 0 |  | 2028-02-16 |  | 2028-04-10
47947 |  | Not Ready |  | 2028-02-07 | 2028-03-30 | Tower A canopy at P5 | 100 | 0 |  | 2028-02-16 |  | 2028-04-10
46609 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-12-09 | 2027-12-16 | FAPA Cabling | 100 | 0 |  | 2028-02-17 |  | 2028-02-25 |  | Tower B | Super Structure | L42
47343 | Tower B - Super Structure - Finishes & MEP - B3 to GF | Not Ready | Staircase Finishes - MEP & Finishes | 2028-03-31 | 2028-05-05 | Staircase Window | 100 | 0 |  | 2028-02-17 |  | 2028-03-24 |  | Tower B | Super Structure | B3
47345 | Tower B - Super Structure - Finishes & MEP - B3 to GF | Not Ready | Staircase Finishes - MEP & Finishes | 2028-03-31 | 2028-04-17 | Staircase cabling | 100 | 0 |  | 2028-02-17 |  | 2028-03-06 |  | Tower B | Super Structure | B3
47371 | Tower B - Super Structure - Finishes & MEP - L25 to L35 | Not Ready | Staircase Finishes - MEP & Finishes | 2028-03-31 | 2028-05-05 | Staircase Window | 100 | 0 |  | 2028-02-17 |  | 2028-03-24 |  | Tower B | Super Structure | L25
47373 | Tower B - Super Structure - Finishes & MEP - L25 to L35 | Not Ready | Staircase Finishes - MEP & Finishes | 2028-03-31 | 2028-04-17 | Staircase cabling | 100 | 0 |  | 2028-02-17 |  | 2028-03-06 |  | Tower B | Super Structure | L25
47375 |  | Not Committed |  | 2028-03-31 | 2028-08-19 | L35-Terrace | 100 | 0 |  | 2028-02-17 |  | 2028-07-10
47375 |  | Not Committed |  | 2028-03-31 | 2028-08-19 | L35-Terrace | 100 | 0 |  | 2028-02-17 |  | 2028-07-10
47376 | Tower B - Super Structure - Finishes & MEP - L35 to Terrace | Not Ready | Staircase Finishes - MEP & Finishes | 2028-03-31 | 2028-05-24 | Staircase Wall & Ceiling finishes | 100 | 0 |  | 2028-02-17 |  | 2028-04-11 |  | Tower B | Super Structure | L35
47155 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2028-01-28 | 2028-02-04 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2028-02-18 |  | 2028-02-26 |  | Tower B | Super Structure | L34 | MEP | FPS 2nd Fix - MEP & Finishes
47156 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2028-01-28 | 2028-02-04 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2028-02-18 |  | 2028-02-26 |  | Tower B | Super Structure | L34 | MEP | Electrical 2nd Fix - MEP & Finishes
47157 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2028-01-28 | 2028-02-02 | PHE Final Fixes | 100 | 0 |  | 2028-02-18 |  | 2028-02-24 |  | Tower B | Super Structure | L34
47171 |  | Not Committed |  | 2028-01-28 | 2028-02-22 | MEP final fix & Finishes | 100 | 0 |  | 2028-02-18 |  | 2028-03-16
47172 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2028-01-28 | 2028-02-10 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2028-02-18 |  | 2028-03-03 |  | Tower B | Super Structure | L35 | Finishes | Door & Window Fixing
46516 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2028-01-19 | 2028-01-31 | Lobby Plastering | 100 | 0 |  | 2028-02-19 |  | 2028-03-02 |  | Tower B | Super Structure | L36 | Finishes | Lobby Plastering
46531 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2028-01-19 | 2028-01-24 | Lobby Blockwork | 100 | 0 |  | 2028-02-19 |  | 2028-02-25 |  | Tower B | Super Structure | L37 | Finishes | Blockwork
46539 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-12-11 | 2027-12-18 | Staircase Fire Door Fixing | 100 | 0 |  | 2028-02-19 |  | 2028-02-28 |  | Tower B | Super Structure | L37
45696 | Tower B - Super Structure - Finishes & MEP - Sub Station | Not Ready | Sub Station - High Side Services | 2027-09-30 | 2027-11-01 | IPS Flooring & Trench Finishing | 100 | 0 |  | 2028-02-21 |  | 2028-03-03 |  | Tower B | Super Structure
46566 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-12-13 | 2027-12-27 | False Ceiling | 100 | 0 |  | 2028-02-21 |  | 2028-03-06 |  | Tower B | Super Structure | L39 | Finishes | False Ceiling
46597 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-12-13 | 2028-01-11 | Flooring & Dado | 100 | 0 |  | 2028-02-21 |  | 2028-03-22 |  | Tower B | Super Structure | L41 | Finishes | Flooring & Dado
46610 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-12-13 | 2027-12-23 | HVAC Ducting | 100 | 0 |  | 2028-02-21 |  | 2028-03-03 |  | Tower B | Super Structure | L42 | MEP | HVAC Ducting
46622 |  | Not Committed |  | 2027-12-13 | 2028-03-17 | L43-44 | 100 | 0 |  | 2028-02-21 |  | 2028-05-27
46622 |  | Not Committed |  | 2027-12-13 | 2028-03-17 | L43-44 | 100 | 0 |  | 2028-02-21 |  | 2028-05-27 |  |  |  |  | Finishes | Gypsum Plastering Works
46623 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-12-13 | 2027-12-23 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2028-02-21 |  | 2028-03-03 |  | Tower B | Super Structure | L43 | MEP | FPS 1st Fix - MEP & Finishes
46624 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-12-13 | 2027-12-20 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2028-02-21 |  | 2028-02-29 |  | Tower B | Super Structure | L43 | MEP | Electrical 1st Fixes
47820 |  | Not Ready |  | 2027-08-16 | 2027-10-11 | P3 to P4 | 100 | 0 |  | 2028-02-21 |  | 2028-04-14
47820 |  | Not Ready |  | 2027-08-16 | 2027-10-11 | P3 to P4 | 100 | 0 |  | 2028-02-21 |  | 2028-04-14
47820 |  | Not Ready |  | 2027-08-16 | 2027-10-11 | P3 to P4 | 100 | 0 |  | 2028-02-21 |  | 2028-04-14
47846 |  | Not Ready |  | 2027-08-16 | 2027-09-21 | Staircase Finishes | 100 | 0 |  | 2028-02-21 |  | 2028-03-28
47846 |  | Not Ready |  | 2027-08-16 | 2027-09-21 | Staircase Finishes | 100 | 0 |  | 2028-02-21 |  | 2028-03-28
47847 |  | Not Committed |  | 2027-08-16 | 2027-12-03 | P2 to P3 | 100 | 0 |  | 2028-02-21 |  | 2028-06-08
47847 |  | Not Committed |  | 2027-08-16 | 2027-12-03 | P2 to P3 | 100 | 0 |  | 2028-02-21 |  | 2028-06-08
47847 |  | Not Committed |  | 2027-08-16 | 2027-12-03 | P2 to P3 | 100 | 0 |  | 2028-02-21 |  | 2028-06-08
47848 |  | Not Ready |  | 2027-08-16 | 2027-09-21 | VDF Flooring | 100 | 0 |  | 2028-02-21 |  | 2028-03-28
47848 |  | Not Ready |  | 2027-08-16 | 2027-09-21 | VDF Flooring | 100 | 0 |  | 2028-02-21 |  | 2028-03-28
46551 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-12-15 | 2027-12-22 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2028-02-23 |  | 2028-03-02 |  | Tower B | Super Structure | L38 | MEP | FPS 2nd Fix - MEP & Finishes
46552 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-12-15 | 2027-12-22 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2028-02-23 |  | 2028-03-02 |  | Tower B | Super Structure | L38 | MEP | Electrical 2nd Fix - MEP & Finishes
46553 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-12-15 | 2027-12-27 | FAPA Device Fixing | 100 | 0 |  | 2028-02-23 |  | 2028-03-06 |  | Tower B | Super Structure | L38
46553 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-12-15 | 2027-12-27 | FAPA Device Fixing | 100 | 0 |  | 2028-02-23 |  | 2028-03-06 |  | Tower B | Super Structure | L38
46553 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-12-15 | 2027-12-27 | FAPA Device Fixing | 100 | 0 |  | 2028-02-23 |  | 2028-03-06 |  | Tower B | Super Structure | L38
46553 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-12-15 | 2027-12-27 | FAPA Device Fixing | 100 | 0 |  | 2028-02-23 |  | 2028-03-06 |  | Tower B | Super Structure | L38
46554 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-12-15 | 2027-12-22 | HVAC Grill Fixing | 100 | 0 |  | 2028-02-23 |  | 2028-03-02 |  | Tower B | Super Structure | L38 | MEP | HVAC Grill Fixing
47860 |  | Not Committed |  | 2028-06-22 | 2028-09-28 | GF level | 100 | 0 |  | 2028-02-23 |  | 2028-06-05
47861 |  | Not Ready |  | 2028-06-22 | 2028-07-14 | RCC upstand | 100 | 0 |  | 2028-02-23 |  | 2028-03-18
47861 |  | Not Ready |  | 2028-06-22 | 2028-07-14 | RCC upstand | 100 | 0 |  | 2028-02-23 |  | 2028-03-18
46525 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-12-16 | 2027-12-23 | Final Painting | 100 | 0 |  | 2028-02-24 |  | 2028-03-03 |  | Tower B | Super Structure | L36 | Finishes | Final Painting
46525 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-12-16 | 2027-12-23 | Final Painting | 100 | 0 |  | 2028-02-24 |  | 2028-03-03 |  | Tower B | Super Structure | L36 | Finishes | Final Painting
46525 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-12-16 | 2027-12-23 | Final Painting | 100 | 0 |  | 2028-02-24 |  | 2028-03-03 |  | Tower B | Super Structure | L36 | Finishes | Final Painting
47158 | Tower B - Super Structure - Finishes & MEP - L34 to L35 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2028-02-03 | 2028-02-08 | Painting Works | 100 | 0 |  | 2028-02-24 |  | 2028-03-01 |  | Tower B | Super Structure | L34 | Finishes | Painting Works
47899 |  | Not Ready |  | 2028-02-15 | 2028-02-22 | FAPA Device Fixing | 100 | 0 |  | 2028-02-24 |  | 2028-03-03
47899 |  | Not Ready |  | 2028-02-15 | 2028-02-22 | FAPA Device Fixing | 100 | 0 |  | 2028-02-24 |  | 2028-03-03
47899 |  | Not Ready |  | 2028-02-15 | 2028-02-22 | FAPA Device Fixing | 100 | 0 |  | 2028-02-24 |  | 2028-03-03
47899 |  | Not Ready |  | 2028-02-15 | 2028-02-22 | FAPA Device Fixing | 100 | 0 |  | 2028-02-24 |  | 2028-03-03
47903 |  | Not Committed |  | 2028-02-15 | 2028-03-28 | B2 to B1 | 100 | 0 |  | 2028-02-24 |  | 2028-04-07
47903 |  | Not Committed |  | 2028-02-15 | 2028-03-28 | B2 to B1 | 100 | 0 |  | 2028-02-24 |  | 2028-04-07
47903 |  | Not Committed |  | 2028-02-15 | 2028-03-28 | B2 to B1 | 100 | 0 |  | 2028-02-24 |  | 2028-04-07
47904 |  | Not Ready |  | 2028-02-15 | 2028-02-22 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2028-02-24 |  | 2028-03-03 |  |  |  |  | MEP | FPS final fixes
47904 |  | Not Ready |  | 2028-02-15 | 2028-02-22 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2028-02-24 |  | 2028-03-03 |  |  |  |  | MEP | FPS final fixes
45678 | Tower B - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2028-02-07 | 2028-02-17 | Obtaining PWD Lisence | 100 | 0 |  | 2028-02-25 |  | 2028-03-08 |  | Tower B | Super Structure
45678 | Tower B - Super Structure - Finishes & MEP | Not Ready | Other Elevators - High Side Services | 2028-02-07 | 2028-02-17 | Obtaining PWD Lisence | 100 | 0 |  | 2028-02-25 |  | 2028-03-08 |  | Tower B | Super Structure
46532 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2028-01-25 | 2028-02-05 | Lobby Plastering | 100 | 0 |  | 2028-02-25 |  | 2028-03-08 |  | Tower B | Super Structure | L37 | Finishes | Lobby Plastering
46547 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2028-01-25 | 2028-01-31 | Lobby Blockwork | 100 | 0 |  | 2028-02-25 |  | 2028-03-02 |  | Tower B | Super Structure | L38 | Finishes | Blockwork
45715 | Tower B - Super Structure - Finishes & MEP - DG Sets | Not Ready |  | 2028-02-05 | 2028-03-29 | DG Placing | 100 | 0 |  | 2028-02-26 |  | 2028-04-20 |  | Tower B | Super Structure
46540 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2027-12-20 | 2027-12-28 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2028-02-28 |  | 2028-03-07 |  | Tower B | Super Structure | L37 | MEP | Electrical
46625 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2027-12-21 | 2027-12-29 | FAPA Cabling | 100 | 0 |  | 2028-02-29 |  | 2028-03-08 |  | Tower B | Super Structure | L43
47474 | Tower B - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2028-01-29 | 2028-02-05 | Accessories & Alignment | 100 | 0 |  | 2028-02-29 |  | 2028-03-08 |  | Tower B | Super Structure | L15 | Façade | Façade Works
47474 | Tower B - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2028-01-29 | 2028-02-05 | Accessories & Alignment | 100 | 0 |  | 2028-02-29 |  | 2028-03-08 |  | Tower B | Super Structure | L15
47499 | Tower B - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2028-01-29 | 2028-02-05 | Accessories & Alignment | 100 | 0 |  | 2028-02-29 |  | 2028-03-08 |  | Tower B | Super Structure | L15 | Façade | Façade Works
47499 | Tower B - Super Structure - Finishes & MEP - L15 to L25 | Not Ready |  | 2028-01-29 | 2028-02-05 | Accessories & Alignment | 100 | 0 |  | 2028-02-29 |  | 2028-03-08 |  | Tower B | Super Structure | L15
46548 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2028-02-01 | 2028-02-11 | Lobby Plastering | 100 | 0 |  | 2028-03-02 |  | 2028-03-15 |  | Tower B | Super Structure | L38 | Finishes | Lobby Plastering
46555 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2027-12-23 | 2027-12-31 | Staircase Fire Door Fixing | 100 | 0 |  | 2028-03-02 |  | 2028-03-10 |  | Tower B | Super Structure | L38
46563 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2028-02-01 | 2028-02-05 | Lobby Blockwork | 100 | 0 |  | 2028-03-02 |  | 2028-03-08 |  | Tower B | Super Structure | L39 | Finishes | Blockwork
45697 | Tower B - Super Structure - Finishes & MEP - Sub Station | Not Ready | Sub Station - High Side Services | 2027-11-02 | 2027-11-30 | Platform fixing for Transformer Placing | 100 | 0 |  | 2028-03-03 |  | 2028-03-22 |  | Tower B | Super Structure
46582 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2027-12-24 | 2028-01-07 | False Ceiling | 100 | 0 |  | 2028-03-03 |  | 2028-03-18 |  | Tower B | Super Structure | L40 | Finishes | False Ceiling
46613 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2027-12-24 | 2028-01-22 | Flooring & Dado | 100 | 0 |  | 2028-03-03 |  | 2028-04-03 |  | Tower B | Super Structure | L42 | Finishes | Flooring & Dado
46626 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2027-12-24 | 2028-01-05 | HVAC Ducting | 100 | 0 |  | 2028-03-03 |  | 2028-03-16 |  | Tower B | Super Structure | L43 | MEP | HVAC Ducting
46638 |  | Not Committed |  | 2027-12-24 | 2028-03-29 | L44-45 | 100 | 0 |  | 2028-03-03 |  | 2028-06-08
46638 |  | Not Committed |  | 2027-12-24 | 2028-03-29 | L44-45 | 100 | 0 |  | 2028-03-03 |  | 2028-06-08 |  |  |  |  | Finishes | Gypsum Plastering Works
46639 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | FPS 1st Fix - MEP & Finishes | 2027-12-24 | 2028-01-05 | FPS 1st Fixes (Pipe Installations & Testing) | 100 | 0 |  | 2028-03-03 |  | 2028-03-16 |  | Tower B | Super Structure | L44 | MEP | FPS 1st Fix - MEP & Finishes
46640 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | Electrical 1st Fix - MEP & Finishes | 2027-12-24 | 2028-01-01 | Electrical 1st Fixes (Cable Tray/ Cabling) | 100 | 0 |  | 2028-03-03 |  | 2028-03-13 |  | Tower B | Super Structure | L44 | MEP | Electrical 1st Fixes
47173 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2028-02-11 | 2028-02-18 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2028-03-03 |  | 2028-03-13 |  | Tower B | Super Structure | L35 | MEP | FPS 2nd Fix - MEP & Finishes
47174 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2028-02-11 | 2028-02-18 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2028-03-03 |  | 2028-03-13 |  | Tower B | Super Structure | L35 | MEP | Electrical 2nd Fix - MEP & Finishes
47175 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2028-02-11 | 2028-02-16 | PHE Final Fixes | 100 | 0 |  | 2028-03-03 |  | 2028-03-09 |  | Tower B | Super Structure | L35
47189 |  | Not Committed |  | 2028-02-11 | 2028-03-07 | MEP final fix & Finishes | 100 | 0 |  | 2028-03-03 |  | 2028-03-30
47190 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2028-02-11 | 2028-02-24 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2028-03-03 |  | 2028-03-18 |  | Tower B | Super Structure | L36 | Finishes | Door & Window Fixing
47900 |  | Not Ready |  | 2028-02-23 | 2028-03-01 | HVAC Fans fixing | 100 | 0 |  | 2028-03-03 |  | 2028-03-13 |  |  |  |  | MEP | HVAC Grill Fixing
47900 |  | Not Ready |  | 2028-02-23 | 2028-03-01 | HVAC Fans fixing | 100 | 0 |  | 2028-03-03 |  | 2028-03-13 |  |  |  |  | MEP | HVAC Grill Fixing
47905 |  | Not Ready |  | 2028-02-23 | 2028-03-01 | FAPA Device Fixing | 100 | 0 |  | 2028-03-03 |  | 2028-03-13
47905 |  | Not Ready |  | 2028-02-23 | 2028-03-01 | FAPA Device Fixing | 100 | 0 |  | 2028-03-03 |  | 2028-03-13
47905 |  | Not Ready |  | 2028-02-23 | 2028-03-01 | FAPA Device Fixing | 100 | 0 |  | 2028-03-03 |  | 2028-03-13
47905 |  | Not Ready |  | 2028-02-23 | 2028-03-01 | FAPA Device Fixing | 100 | 0 |  | 2028-03-03 |  | 2028-03-13
47909 |  | Not Committed |  | 2028-02-23 | 2028-04-05 | B1 to GF | 100 | 0 |  | 2028-03-03 |  | 2028-04-15
47909 |  | Not Committed |  | 2028-02-23 | 2028-04-05 | B1 to GF | 100 | 0 |  | 2028-03-03 |  | 2028-04-15
47909 |  | Not Committed |  | 2028-02-23 | 2028-04-05 | B1 to GF | 100 | 0 |  | 2028-03-03 |  | 2028-04-15
47910 |  | Not Ready |  | 2028-02-23 | 2028-03-01 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2028-03-03 |  | 2028-03-13 |  |  |  |  | MEP | FPS final fixes
47910 |  | Not Ready |  | 2028-02-23 | 2028-03-01 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2028-03-03 |  | 2028-03-13 |  |  |  |  | MEP | FPS final fixes
46567 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2027-12-28 | 2028-01-04 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2028-03-06 |  | 2028-03-15 |  | Tower B | Super Structure | L39 | MEP | FPS 2nd Fix - MEP & Finishes
46568 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2027-12-28 | 2028-01-04 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2028-03-06 |  | 2028-03-15 |  | Tower B | Super Structure | L39 | MEP | Electrical 2nd Fix - MEP & Finishes
46569 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-12-28 | 2028-01-07 | FAPA Device Fixing | 100 | 0 |  | 2028-03-06 |  | 2028-03-18 |  | Tower B | Super Structure | L39
46569 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-12-28 | 2028-01-07 | FAPA Device Fixing | 100 | 0 |  | 2028-03-06 |  | 2028-03-18 |  | Tower B | Super Structure | L39
46569 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-12-28 | 2028-01-07 | FAPA Device Fixing | 100 | 0 |  | 2028-03-06 |  | 2028-03-18 |  | Tower B | Super Structure | L39
46569 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2027-12-28 | 2028-01-07 | FAPA Device Fixing | 100 | 0 |  | 2028-03-06 |  | 2028-03-18 |  | Tower B | Super Structure | L39
46570 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2027-12-28 | 2028-01-04 | HVAC Grill Fixing | 100 | 0 |  | 2028-03-06 |  | 2028-03-15 |  | Tower B | Super Structure | L39 | MEP | HVAC Grill Fixing
47353 | Tower B - Super Structure - Finishes & MEP - GF to L7 | Not Ready | Staircase Finishes - MEP & Finishes | 2028-04-18 | 2028-05-05 | Staircase Light Fixtures & Devices fixing | 100 | 0 |  | 2028-03-06 |  | 2028-03-24 |  | Tower B | Super Structure | GF
47367 | Tower B - Super Structure - Finishes & MEP - L15 to L25 | Not Ready | Staircase Finishes - MEP & Finishes | 2028-04-18 | 2028-05-05 | Staircase Light Fixtures & Devices fixing | 100 | 0 |  | 2028-03-06 |  | 2028-03-24 |  | Tower B | Super Structure | L15
47377 | Tower B - Super Structure - Finishes & MEP - L35 to Terrace | Not Ready | Staircase Finishes - MEP & Finishes | 2028-04-18 | 2028-06-28 | Staircase Flooring | 100 | 0 |  | 2028-03-06 |  | 2028-05-18 |  | Tower B | Super Structure | L35 | Finishes | Staircase Flooring
46541 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-12-29 | 2028-01-05 | Final Painting | 100 | 0 |  | 2028-03-07 |  | 2028-03-16 |  | Tower B | Super Structure | L37 | Finishes | Final Painting
46541 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-12-29 | 2028-01-05 | Final Painting | 100 | 0 |  | 2028-03-07 |  | 2028-03-16 |  | Tower B | Super Structure | L37 | Finishes | Final Painting
46541 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2027-12-29 | 2028-01-05 | Final Painting | 100 | 0 |  | 2028-03-07 |  | 2028-03-16 |  | Tower B | Super Structure | L37 | Finishes | Final Painting
47386 | Tower B - Super Structure - Finishes & MEP - GF to P1 | Not Ready | Façade Works - MEP & Finishes | 2027-12-29 | 2028-01-14 | DGU Assembly Installation | 100 | 0 |  | 2028-03-07 |  | 2028-03-25 |  | Tower B | Super Structure | GF | Façade | Façade Works
47387 | Tower B - Super Structure - Finishes & MEP - GF to P1 | Not Ready | Façade Works - MEP & Finishes | 2027-12-29 | 2028-01-27 | Installation of highly reflective metal sheet | 100 | 0 |  | 2028-03-07 |  | 2028-04-06 |  | Tower B | Super Structure | GF | Façade | Façade Works
47388 | Tower B - Super Structure - Finishes & MEP - GF to P1 | Not Ready | Façade Works - MEP & Finishes | 2027-12-29 | 2028-01-14 | Fixing of Backlit Laminated Glass assembly & ACP Panels | 100 | 0 |  | 2028-03-07 |  | 2028-03-25 |  | Tower B | Super Structure | GF | Façade | Façade Works
47389 | Tower B - Super Structure - Finishes & MEP - GF to P1 | Not Ready | Façade Works - MEP & Finishes | 2027-12-29 | 2028-01-14 | Fixing of Louvers | 100 | 0 |  | 2028-03-07 |  | 2028-03-25 |  | Tower B | Super Structure | GF | Façade | Façade Works
47389 | Tower B - Super Structure - Finishes & MEP - GF to P1 | Not Ready | Façade Works - MEP & Finishes | 2027-12-29 | 2028-01-14 | Fixing of Louvers | 100 | 0 |  | 2028-03-07 |  | 2028-03-25 |  | Tower B | Super Structure | GF
47391 | Tower B - Super Structure - Finishes & MEP - GF to P1 | Not Ready | Façade Works - MEP & Finishes | 2027-12-29 | 2028-02-19 | Entrance Canopy | 100 | 0 |  | 2028-03-07 |  | 2028-04-29 |  | Tower B | Super Structure | GF | Façade | Façade Works
45692 | Tower B - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2028-01-29 | 2028-02-15 | FAPA Device Fixing | 100 | 0 |  | 2028-03-08 |  | 2028-03-27 |  | Tower B | Super Structure
45692 | Tower B - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2028-01-29 | 2028-02-15 | FAPA Device Fixing | 100 | 0 |  | 2028-03-08 |  | 2028-03-27 |  | Tower B | Super Structure
45692 | Tower B - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2028-01-29 | 2028-02-15 | FAPA Device Fixing | 100 | 0 |  | 2028-03-08 |  | 2028-03-27 |  | Tower B | Super Structure
45692 | Tower B - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2028-01-29 | 2028-02-15 | FAPA Device Fixing | 100 | 0 |  | 2028-03-08 |  | 2028-03-27 |  | Tower B | Super Structure
46564 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2028-02-07 | 2028-02-17 | Lobby Plastering | 100 | 0 |  | 2028-03-08 |  | 2028-03-21 |  | Tower B | Super Structure | L39 | Finishes | Lobby Plastering
46579 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2028-02-07 | 2028-02-11 | Lobby Blockwork | 100 | 0 |  | 2028-03-08 |  | 2028-03-15 |  | Tower B | Super Structure | L40 | Finishes | Blockwork
47514 | Tower B - Super Structure - Finishes & MEP - L15 to L25 | Not Ready | Hoist Corridor Finishes | 2028-02-07 | 2028-05-24 | L15-25 | 100 | 0 |  | 2028-03-08 |  | 2028-06-24 |  | Tower B | Super Structure | L15
47514 | Tower B - Super Structure - Finishes & MEP - L15 to L25 | Not Ready | Hoist Corridor Finishes | 2028-02-07 | 2028-05-24 | L15-25 | 100 | 0 |  | 2028-03-08 |  | 2028-06-24 |  | Tower B | Super Structure | L15
47536 |  | Not Ready |  | 2028-01-29 | 2028-09-18 | Statutory Approvals - OC_Zone 3 | 100 | 0 |  | 2028-03-08 |  | 2028-09-22
47537 |  | Not Ready |  | 2028-02-18 | 2028-03-24 | Lift Commissioning with Permanent Power | 100 | 0 |  | 2028-03-08 |  | 2028-03-27
47538 |  | Not Ready |  | 2028-01-29 | 2028-03-03 | STP Commissioning | 100 | 0 |  | 2028-03-08 |  | 2028-03-27
47176 | Tower B - Super Structure - Finishes & MEP - L35 to L36 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2028-02-17 | 2028-02-22 | Painting Works | 100 | 0 |  | 2028-03-09 |  | 2028-03-16 |  | Tower B | Super Structure | L35 | Finishes | Painting Works
46556 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2028-01-01 | 2028-01-08 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2028-03-10 |  | 2028-03-20 |  | Tower B | Super Structure | L38 | MEP | Electrical
46641 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | FAPA Cabling - MEP & Finishes | 2028-01-03 | 2028-01-10 | FAPA Cabling | 100 | 0 |  | 2028-03-13 |  | 2028-03-21 |  | Tower B | Super Structure | L44
47477 | Tower B - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2028-02-10 | 2028-02-26 | Glass Assembly Installation | 100 | 0 |  | 2028-03-13 |  | 2028-03-30 |  | Tower B | Super Structure | L25
47478 | Tower B - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2028-02-10 | 2028-02-21 | ACP Sheet & Insulation fixing | 100 | 0 |  | 2028-03-13 |  | 2028-03-24 |  | Tower B | Super Structure | L25
47479 | Tower B - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2028-02-10 | 2028-02-17 | Fixing of Louvers | 100 | 0 |  | 2028-03-13 |  | 2028-03-21 |  | Tower B | Super Structure | L25 | Façade | Façade Works
47479 | Tower B - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2028-02-10 | 2028-02-17 | Fixing of Louvers | 100 | 0 |  | 2028-03-13 |  | 2028-03-21 |  | Tower B | Super Structure | L25
47481 |  | Not Committed |  | 2028-02-10 | 2028-04-05 | L35-Terrace | 100 | 0 |  | 2028-03-13 |  | 2028-05-08
47481 |  | Not Committed |  | 2028-02-10 | 2028-04-05 | L35-Terrace | 100 | 0 |  | 2028-03-13 |  | 2028-05-08
47482 | Tower B - Super Structure - Finishes & MEP - L35 to Terrace | Not Ready |  | 2028-02-10 | 2028-03-09 | Al. Frame Section Installation | 100 | 0 |  | 2028-03-13 |  | 2028-04-11 |  | Tower B | Super Structure | L35
47502 | Tower B - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2028-02-10 | 2028-02-26 | Glass Assembly Installation | 100 | 0 |  | 2028-03-13 |  | 2028-03-30 |  | Tower B | Super Structure | L25
47503 | Tower B - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2028-02-10 | 2028-02-21 | ACP Sheet & Insulation fixing | 100 | 0 |  | 2028-03-13 |  | 2028-03-24 |  | Tower B | Super Structure | L25
47504 | Tower B - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2028-02-10 | 2028-02-17 | Fixing of Louvers | 100 | 0 |  | 2028-03-13 |  | 2028-03-21 |  | Tower B | Super Structure | L25 | Façade | Façade Works
47504 | Tower B - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2028-02-10 | 2028-02-17 | Fixing of Louvers | 100 | 0 |  | 2028-03-13 |  | 2028-03-21 |  | Tower B | Super Structure | L25
47506 |  | Not Committed |  | 2028-02-10 | 2028-04-05 | L35-Terrace | 100 | 0 |  | 2028-03-13 |  | 2028-05-08
47506 |  | Not Committed |  | 2028-02-10 | 2028-04-05 | L35-Terrace | 100 | 0 |  | 2028-03-13 |  | 2028-05-08
47507 | Tower B - Super Structure - Finishes & MEP - L35 to Terrace | Not Ready |  | 2028-02-10 | 2028-03-09 | Al. Frame Section Installation | 100 | 0 |  | 2028-03-13 |  | 2028-04-11 |  | Tower B | Super Structure | L35
47901 |  | Not Ready |  | 2028-03-02 | 2028-03-14 | Final Painting | 100 | 0 |  | 2028-03-13 |  | 2028-03-24 |  |  |  |  | Finishes | Final Painting
47901 |  | Not Ready |  | 2028-03-02 | 2028-03-14 | Final Painting | 100 | 0 |  | 2028-03-13 |  | 2028-03-24 |  |  |  |  | Finishes | Final Painting
47901 |  | Not Ready |  | 2028-03-02 | 2028-03-14 | Final Painting | 100 | 0 |  | 2028-03-13 |  | 2028-03-24 |  |  |  |  | Finishes | Final Painting
47906 |  | Not Ready |  | 2028-03-02 | 2028-03-09 | HVAC Fans fixing | 100 | 0 |  | 2028-03-13 |  | 2028-03-21 |  |  |  |  | MEP | HVAC Grill Fixing
47906 |  | Not Ready |  | 2028-03-02 | 2028-03-09 | HVAC Fans fixing | 100 | 0 |  | 2028-03-13 |  | 2028-03-21 |  |  |  |  | MEP | HVAC Grill Fixing
47911 |  | Not Ready |  | 2028-03-02 | 2028-03-09 | FAPA Device Fixing | 100 | 0 |  | 2028-03-13 |  | 2028-03-21
47911 |  | Not Ready |  | 2028-03-02 | 2028-03-09 | FAPA Device Fixing | 100 | 0 |  | 2028-03-13 |  | 2028-03-21
47911 |  | Not Ready |  | 2028-03-02 | 2028-03-09 | FAPA Device Fixing | 100 | 0 |  | 2028-03-13 |  | 2028-03-21
47911 |  | Not Ready |  | 2028-03-02 | 2028-03-09 | FAPA Device Fixing | 100 | 0 |  | 2028-03-13 |  | 2028-03-21
47921 |  | Not Committed |  | 2028-03-02 | 2028-04-13 | P1 to P2 | 100 | 0 |  | 2028-03-13 |  | 2028-04-24
47921 |  | Not Committed |  | 2028-03-02 | 2028-04-13 | P1 to P2 | 100 | 0 |  | 2028-03-13 |  | 2028-04-24
47921 |  | Not Committed |  | 2028-03-02 | 2028-04-13 | P1 to P2 | 100 | 0 |  | 2028-03-13 |  | 2028-04-24
47922 |  | Not Ready |  | 2028-03-02 | 2028-03-09 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2028-03-13 |  | 2028-03-21 |  |  |  |  | MEP | FPS final fixes
47922 |  | Not Ready |  | 2028-03-02 | 2028-03-09 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2028-03-13 |  | 2028-03-21 |  |  |  |  | MEP | FPS final fixes
46571 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2028-01-05 | 2028-01-12 | Staircase Fire Door Fixing | 100 | 0 |  | 2028-03-15 |  | 2028-03-23 |  | Tower B | Super Structure | L39
46580 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2028-02-12 | 2028-02-23 | Lobby Plastering | 100 | 0 |  | 2028-03-15 |  | 2028-03-27 |  | Tower B | Super Structure | L40 | Finishes | Lobby Plastering
46595 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2028-02-12 | 2028-02-17 | Lobby Blockwork | 100 | 0 |  | 2028-03-15 |  | 2028-03-21 |  | Tower B | Super Structure | L41 | Finishes | Blockwork
46598 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2028-01-06 | 2028-01-19 | False Ceiling | 100 | 0 |  | 2028-03-16 |  | 2028-03-30 |  | Tower B | Super Structure | L41 | Finishes | False Ceiling
46629 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2028-01-06 | 2028-02-04 | Flooring & Dado | 100 | 0 |  | 2028-03-16 |  | 2028-04-14 |  | Tower B | Super Structure | L43 | Finishes | Flooring & Dado
46642 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | HVAC Ducting - MEP & Finishes | 2028-01-06 | 2028-01-17 | HVAC Ducting | 100 | 0 |  | 2028-03-16 |  | 2028-03-28 |  | Tower B | Super Structure | L44 | MEP | HVAC Ducting
47526 |  | Not Ready |  | 2028-01-31 | 2028-08-08 | Statutory Approvals - Fire NOC_Zone 3 | 100 | 0 |  | 2028-03-16 |  | 2028-08-30
47530 |  | Not Ready |  | 2028-01-31 | 2028-02-10 | Exhaust & Pressurization System Commissioning | 100 | 0 |  | 2028-03-16 |  | 2028-03-22
46583 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2028-01-08 | 2028-01-15 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2028-03-18 |  | 2028-03-27 |  | Tower B | Super Structure | L40 | MEP | FPS 2nd Fix - MEP & Finishes
46584 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2028-01-08 | 2028-01-15 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2028-03-18 |  | 2028-03-27 |  | Tower B | Super Structure | L40 | MEP | Electrical 2nd Fix - MEP & Finishes
46585 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2028-01-08 | 2028-01-19 | FAPA Device Fixing | 100 | 0 |  | 2028-03-18 |  | 2028-03-30 |  | Tower B | Super Structure | L40
46585 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2028-01-08 | 2028-01-19 | FAPA Device Fixing | 100 | 0 |  | 2028-03-18 |  | 2028-03-30 |  | Tower B | Super Structure | L40
46585 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2028-01-08 | 2028-01-19 | FAPA Device Fixing | 100 | 0 |  | 2028-03-18 |  | 2028-03-30 |  | Tower B | Super Structure | L40
46585 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2028-01-08 | 2028-01-19 | FAPA Device Fixing | 100 | 0 |  | 2028-03-18 |  | 2028-03-30 |  | Tower B | Super Structure | L40
46586 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2028-01-08 | 2028-01-15 | HVAC Grill Fixing | 100 | 0 |  | 2028-03-18 |  | 2028-03-27 |  | Tower B | Super Structure | L40 | MEP | HVAC Grill Fixing
47191 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2028-02-25 | 2028-03-03 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2028-03-18 |  | 2028-03-27 |  | Tower B | Super Structure | L36 | MEP | FPS 2nd Fix - MEP & Finishes
47192 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2028-02-25 | 2028-03-03 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2028-03-18 |  | 2028-03-27 |  | Tower B | Super Structure | L36 | MEP | Electrical 2nd Fix - MEP & Finishes
47193 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2028-02-25 | 2028-03-01 | PHE Final Fixes | 100 | 0 |  | 2028-03-18 |  | 2028-03-24 |  | Tower B | Super Structure | L36
47207 |  | Not Committed |  | 2028-02-25 | 2028-03-22 | MEP final fix & Finishes | 100 | 0 |  | 2028-03-18 |  | 2028-04-13
47208 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2028-02-25 | 2028-03-09 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2028-03-18 |  | 2028-04-01 |  | Tower B | Super Structure | L37 | Finishes | Door & Window Fixing
47862 |  | Not Ready |  | 2028-07-15 | 2028-08-01 | Drainage pipe | 100 | 0 |  | 2028-03-18 |  | 2028-04-05
47862 |  | Not Ready |  | 2028-07-15 | 2028-08-01 | Drainage pipe | 100 | 0 |  | 2028-03-18 |  | 2028-04-05
46557 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2028-01-10 | 2028-01-17 | Final Painting | 100 | 0 |  | 2028-03-20 |  | 2028-03-28 |  | Tower B | Super Structure | L38 | Finishes | Final Painting
46557 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2028-01-10 | 2028-01-17 | Final Painting | 100 | 0 |  | 2028-03-20 |  | 2028-03-28 |  | Tower B | Super Structure | L38 | Finishes | Final Painting
46557 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2028-01-10 | 2028-01-17 | Final Painting | 100 | 0 |  | 2028-03-20 |  | 2028-03-28 |  | Tower B | Super Structure | L38 | Finishes | Final Painting
46596 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2028-02-18 | 2028-02-29 | Lobby Plastering | 100 | 0 |  | 2028-03-21 |  | 2028-04-01 |  | Tower B | Super Structure | L41 | Finishes | Lobby Plastering
46611 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2028-02-18 | 2028-02-23 | Lobby Blockwork | 100 | 0 |  | 2028-03-21 |  | 2028-03-27 |  | Tower B | Super Structure | L42 | Finishes | Blockwork
47907 |  | Not Ready |  | 2028-03-10 | 2028-03-22 | Final Painting | 100 | 0 |  | 2028-03-21 |  | 2028-04-01 |  |  |  |  | Finishes | Final Painting
47907 |  | Not Ready |  | 2028-03-10 | 2028-03-22 | Final Painting | 100 | 0 |  | 2028-03-21 |  | 2028-04-01 |  |  |  |  | Finishes | Final Painting
47907 |  | Not Ready |  | 2028-03-10 | 2028-03-22 | Final Painting | 100 | 0 |  | 2028-03-21 |  | 2028-04-01 |  |  |  |  | Finishes | Final Painting
47912 |  | Not Ready |  | 2028-03-10 | 2028-03-18 | HVAC Fans fixing | 100 | 0 |  | 2028-03-21 |  | 2028-03-29 |  |  |  |  | MEP | HVAC Grill Fixing
47912 |  | Not Ready |  | 2028-03-10 | 2028-03-18 | HVAC Fans fixing | 100 | 0 |  | 2028-03-21 |  | 2028-03-29 |  |  |  |  | MEP | HVAC Grill Fixing
47923 |  | Not Ready |  | 2028-03-10 | 2028-03-18 | FAPA Device Fixing | 100 | 0 |  | 2028-03-21 |  | 2028-03-29
47923 |  | Not Ready |  | 2028-03-10 | 2028-03-18 | FAPA Device Fixing | 100 | 0 |  | 2028-03-21 |  | 2028-03-29
47923 |  | Not Ready |  | 2028-03-10 | 2028-03-18 | FAPA Device Fixing | 100 | 0 |  | 2028-03-21 |  | 2028-03-29
47923 |  | Not Ready |  | 2028-03-10 | 2028-03-18 | FAPA Device Fixing | 100 | 0 |  | 2028-03-21 |  | 2028-03-29
47927 |  | Not Committed |  | 2028-03-10 | 2028-04-21 | P2 to P3 | 100 | 0 |  | 2028-03-21 |  | 2028-05-03
47927 |  | Not Committed |  | 2028-03-10 | 2028-04-21 | P2 to P3 | 100 | 0 |  | 2028-03-21 |  | 2028-05-03
47927 |  | Not Committed |  | 2028-03-10 | 2028-04-21 | P2 to P3 | 100 | 0 |  | 2028-03-21 |  | 2028-05-03
47928 |  | Not Ready |  | 2028-03-10 | 2028-03-18 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2028-03-21 |  | 2028-03-29 |  |  |  |  | MEP | FPS final fixes
47928 |  | Not Ready |  | 2028-03-10 | 2028-03-18 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2028-03-21 |  | 2028-03-29 |  |  |  |  | MEP | FPS final fixes
45698 | Tower B - Super Structure - Finishes & MEP - Sub Station | Not Ready | Sub Station - High Side Services | 2027-12-01 | 2027-12-17 | Transformer Shifting & Placing | 100 | 0 |  | 2028-03-22 |  | 2028-04-03 |  | Tower B | Super Structure
46572 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2028-01-13 | 2028-01-20 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2028-03-23 |  | 2028-03-31 |  | Tower B | Super Structure | L39 | MEP | Electrical
47194 | Tower B - Super Structure - Finishes & MEP - L36 to L37 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2028-03-02 | 2028-03-07 | Painting Works | 100 | 0 |  | 2028-03-24 |  | 2028-03-30 |  | Tower B | Super Structure | L36 | Finishes | Painting Works
47344 | Tower B - Super Structure - Finishes & MEP - B3 to GF | Not Ready | Staircase Finishes - MEP & Finishes | 2028-05-06 | 2028-06-10 | Staircase Railing | 100 | 0 |  | 2028-03-24 |  | 2028-04-28 |  | Tower B | Super Structure | B3
47372 | Tower B - Super Structure - Finishes & MEP - L25 to L35 | Not Ready | Staircase Finishes - MEP & Finishes | 2028-05-06 | 2028-06-10 | Staircase Railing | 100 | 0 |  | 2028-03-24 |  | 2028-04-28 |  | Tower B | Super Structure | L25
47902 |  | Not Ready |  | 2028-03-15 | 2028-03-20 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2028-03-24 |  | 2028-03-30
47902 |  | Not Ready |  | 2028-03-15 | 2028-03-20 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2028-03-24 |  | 2028-03-30
47902 |  | Not Ready |  | 2028-03-15 | 2028-03-20 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2028-03-24 |  | 2028-03-30
47390 | Tower B - Super Structure - Finishes & MEP - GF to P1 | Not Ready | Façade Works - MEP & Finishes | 2028-01-15 | 2028-02-02 | Accessories & Alignment | 100 | 0 |  | 2028-03-25 |  | 2028-04-12 |  | Tower B | Super Structure | GF | Façade | Façade Works
47390 | Tower B - Super Structure - Finishes & MEP - GF to P1 | Not Ready | Façade Works - MEP & Finishes | 2028-01-15 | 2028-02-02 | Accessories & Alignment | 100 | 0 |  | 2028-03-25 |  | 2028-04-12 |  | Tower B | Super Structure | GF
45693 | Tower B - Super Structure - Finishes & MEP - Pump Room | Not Ready | Pump Room - High Side Services | 2028-02-16 | 2028-02-26 | Fire Mode Testing | 100 | 0 |  | 2028-03-27 |  | 2028-04-07 |  | Tower B | Super Structure
46587 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2028-01-17 | 2028-01-24 | Staircase Fire Door Fixing | 100 | 0 |  | 2028-03-27 |  | 2028-04-04 |  | Tower B | Super Structure | L40
46612 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2028-02-24 | 2028-03-06 | Lobby Plastering | 100 | 0 |  | 2028-03-27 |  | 2028-04-07 |  | Tower B | Super Structure | L42 | Finishes | Lobby Plastering
46627 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2028-02-24 | 2028-02-29 | Lobby Blockwork | 100 | 0 |  | 2028-03-27 |  | 2028-04-01 |  | Tower B | Super Structure | L43 | Finishes | Blockwork
46614 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2028-01-18 | 2028-02-01 | False Ceiling | 100 | 0 |  | 2028-03-28 |  | 2028-04-11 |  | Tower B | Super Structure | L42 | Finishes | False Ceiling
46645 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | Flooring & Dado - MEP & Finishes | 2028-01-18 | 2028-02-16 | Flooring & Dado | 100 | 0 |  | 2028-03-28 |  | 2028-04-26 |  | Tower B | Super Structure | L44 | Finishes | Flooring & Dado
47849 |  | Not Ready |  | 2027-09-22 | 2027-10-28 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2028-03-28 |  | 2028-05-03
47849 |  | Not Ready |  | 2027-09-22 | 2027-10-28 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2028-03-28 |  | 2028-05-03
47522 |  | Not Ready | External Development | 2028-03-28 | 2028-07-12 | Hardscape Works | 100 | 0 |  | 2028-03-29 |  | 2028-07-14
47522 |  | Not Ready | External Development | 2028-03-28 | 2028-07-12 | Hardscape Works | 100 | 0 |  | 2028-03-29 |  | 2028-07-14
47913 |  | Not Ready |  | 2028-03-20 | 2028-03-30 | Final Painting | 100 | 0 |  | 2028-03-29 |  | 2028-04-10 |  |  |  |  | Finishes | Final Painting
47913 |  | Not Ready |  | 2028-03-20 | 2028-03-30 | Final Painting | 100 | 0 |  | 2028-03-29 |  | 2028-04-10 |  |  |  |  | Finishes | Final Painting
47913 |  | Not Ready |  | 2028-03-20 | 2028-03-30 | Final Painting | 100 | 0 |  | 2028-03-29 |  | 2028-04-10 |  |  |  |  | Finishes | Final Painting
47924 |  | Not Ready |  | 2028-03-20 | 2028-03-27 | HVAC Fans fixing | 100 | 0 |  | 2028-03-29 |  | 2028-04-06 |  |  |  |  | MEP | HVAC Grill Fixing
47924 |  | Not Ready |  | 2028-03-20 | 2028-03-27 | HVAC Fans fixing | 100 | 0 |  | 2028-03-29 |  | 2028-04-06 |  |  |  |  | MEP | HVAC Grill Fixing
47929 |  | Not Ready |  | 2028-03-20 | 2028-03-27 | FAPA Device Fixing | 100 | 0 |  | 2028-03-29 |  | 2028-04-06
47929 |  | Not Ready |  | 2028-03-20 | 2028-03-27 | FAPA Device Fixing | 100 | 0 |  | 2028-03-29 |  | 2028-04-06
47929 |  | Not Ready |  | 2028-03-20 | 2028-03-27 | FAPA Device Fixing | 100 | 0 |  | 2028-03-29 |  | 2028-04-06
47929 |  | Not Ready |  | 2028-03-20 | 2028-03-27 | FAPA Device Fixing | 100 | 0 |  | 2028-03-29 |  | 2028-04-06
47933 |  | Not Committed |  | 2028-03-20 | 2028-04-29 | P3 to P4 | 100 | 0 |  | 2028-03-29 |  | 2028-05-11
47933 |  | Not Committed |  | 2028-03-20 | 2028-04-29 | P3 to P4 | 100 | 0 |  | 2028-03-29 |  | 2028-05-11
47933 |  | Not Committed |  | 2028-03-20 | 2028-04-29 | P3 to P4 | 100 | 0 |  | 2028-03-29 |  | 2028-05-11
47934 |  | Not Ready |  | 2028-03-20 | 2028-03-27 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2028-03-29 |  | 2028-04-06 |  |  |  |  | MEP | FPS final fixes
47934 |  | Not Ready |  | 2028-03-20 | 2028-03-27 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2028-03-29 |  | 2028-04-06 |  |  |  |  | MEP | FPS final fixes
46599 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2028-01-20 | 2028-01-28 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2028-03-30 |  | 2028-04-07 |  | Tower B | Super Structure | L41 | MEP | FPS 2nd Fix - MEP & Finishes
46600 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2028-01-20 | 2028-01-28 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2028-03-30 |  | 2028-04-07 |  | Tower B | Super Structure | L41 | MEP | Electrical 2nd Fix - MEP & Finishes
46601 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2028-01-20 | 2028-02-01 | FAPA Device Fixing | 100 | 0 |  | 2028-03-30 |  | 2028-04-11 |  | Tower B | Super Structure | L41
46601 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2028-01-20 | 2028-02-01 | FAPA Device Fixing | 100 | 0 |  | 2028-03-30 |  | 2028-04-11 |  | Tower B | Super Structure | L41
46601 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2028-01-20 | 2028-02-01 | FAPA Device Fixing | 100 | 0 |  | 2028-03-30 |  | 2028-04-11 |  | Tower B | Super Structure | L41
46601 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2028-01-20 | 2028-02-01 | FAPA Device Fixing | 100 | 0 |  | 2028-03-30 |  | 2028-04-11 |  | Tower B | Super Structure | L41
46602 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2028-01-20 | 2028-01-28 | HVAC Grill Fixing | 100 | 0 |  | 2028-03-30 |  | 2028-04-07 |  | Tower B | Super Structure | L41 | MEP | HVAC Grill Fixing
47480 | Tower B - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2028-02-28 | 2028-03-06 | Accessories & Alignment | 100 | 0 |  | 2028-03-30 |  | 2028-04-07 |  | Tower B | Super Structure | L25 | Façade | Façade Works
47480 | Tower B - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2028-02-28 | 2028-03-06 | Accessories & Alignment | 100 | 0 |  | 2028-03-30 |  | 2028-04-07 |  | Tower B | Super Structure | L25
47505 | Tower B - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2028-02-28 | 2028-03-06 | Accessories & Alignment | 100 | 0 |  | 2028-03-30 |  | 2028-04-07 |  | Tower B | Super Structure | L25 | Façade | Façade Works
47505 | Tower B - Super Structure - Finishes & MEP - L25 to L35 | Not Ready |  | 2028-02-28 | 2028-03-06 | Accessories & Alignment | 100 | 0 |  | 2028-03-30 |  | 2028-04-07 |  | Tower B | Super Structure | L25
46573 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2028-01-21 | 2028-01-29 | Final Painting | 100 | 0 |  | 2028-03-31 |  | 2028-04-08 |  | Tower B | Super Structure | L39 | Finishes | Final Painting
46573 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2028-01-21 | 2028-01-29 | Final Painting | 100 | 0 |  | 2028-03-31 |  | 2028-04-08 |  | Tower B | Super Structure | L39 | Finishes | Final Painting
46573 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2028-01-21 | 2028-01-29 | Final Painting | 100 | 0 |  | 2028-03-31 |  | 2028-04-08 |  | Tower B | Super Structure | L39 | Finishes | Final Painting
46628 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2028-03-01 | 2028-03-13 | Lobby Plastering | 100 | 0 |  | 2028-04-01 |  | 2028-04-13 |  | Tower B | Super Structure | L43 | Finishes | Lobby Plastering
46643 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | Lobby Blockwork - MEP & Finishes | 2028-03-01 | 2028-03-06 | Lobby Blockwork | 100 | 0 |  | 2028-04-01 |  | 2028-04-07 |  | Tower B | Super Structure | L44 | Finishes | Blockwork
47209 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2028-03-10 | 2028-03-18 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2028-04-01 |  | 2028-04-10 |  | Tower B | Super Structure | L37 | MEP | FPS 2nd Fix - MEP & Finishes
47210 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2028-03-10 | 2028-03-18 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2028-04-01 |  | 2028-04-10 |  | Tower B | Super Structure | L37 | MEP | Electrical 2nd Fix - MEP & Finishes
47211 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2028-03-10 | 2028-03-16 | PHE Final Fixes | 100 | 0 |  | 2028-04-01 |  | 2028-04-07 |  | Tower B | Super Structure | L37
47225 |  | Not Committed |  | 2028-03-10 | 2028-04-05 | MEP final fix & Finishes | 100 | 0 |  | 2028-04-01 |  | 2028-04-27
47226 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2028-03-10 | 2028-03-24 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2028-04-01 |  | 2028-04-15 |  | Tower B | Super Structure | L38 | Finishes | Door & Window Fixing
47908 |  | Not Ready |  | 2028-03-23 | 2028-03-28 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2028-04-01 |  | 2028-04-07
47908 |  | Not Ready |  | 2028-03-23 | 2028-03-28 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2028-04-01 |  | 2028-04-07
47908 |  | Not Ready |  | 2028-03-23 | 2028-03-28 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2028-04-01 |  | 2028-04-07
45699 | Tower B - Super Structure - Finishes & MEP - Sub Station | Not Ready | Sub Station - High Side Services | 2027-12-18 | 2028-01-29 | Panel Installation | 100 | 0 |  | 2028-04-03 |  | 2028-04-20 |  | Tower B | Super Structure
45699 | Tower B - Super Structure - Finishes & MEP - Sub Station | Not Ready | Sub Station - High Side Services | 2027-12-18 | 2028-01-29 | Panel Installation | 100 | 0 |  | 2028-04-03 |  | 2028-04-20 |  | Tower B | Super Structure
45716 | Tower B - Super Structure - Finishes & MEP - DG Sets | Not Ready |  | 2028-03-13 | 2028-05-23 | DG Sync Panel Installation | 100 | 0 |  | 2028-04-03 |  | 2028-06-14 |  | Tower B | Super Structure
46588 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2028-01-25 | 2028-02-02 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2028-04-04 |  | 2028-04-12 |  | Tower B | Super Structure | L40 | MEP | Electrical
47863 |  | Not Ready |  | 2028-08-02 | 2028-08-18 | SS work | 100 | 0 |  | 2028-04-05 |  | 2028-04-22
47925 |  | Not Ready |  | 2028-03-28 | 2028-04-07 | Final Painting | 100 | 0 |  | 2028-04-06 |  | 2028-04-18 |  |  |  |  | Finishes | Final Painting
47925 |  | Not Ready |  | 2028-03-28 | 2028-04-07 | Final Painting | 100 | 0 |  | 2028-04-06 |  | 2028-04-18 |  |  |  |  | Finishes | Final Painting
47925 |  | Not Ready |  | 2028-03-28 | 2028-04-07 | Final Painting | 100 | 0 |  | 2028-04-06 |  | 2028-04-18 |  |  |  |  | Finishes | Final Painting
47930 |  | Not Ready |  | 2028-03-28 | 2028-04-04 | HVAC Fans fixing | 100 | 0 |  | 2028-04-06 |  | 2028-04-14 |  |  |  |  | MEP | HVAC Grill Fixing
47930 |  | Not Ready |  | 2028-03-28 | 2028-04-04 | HVAC Fans fixing | 100 | 0 |  | 2028-04-06 |  | 2028-04-14 |  |  |  |  | MEP | HVAC Grill Fixing
47935 |  | Not Ready |  | 2028-03-28 | 2028-04-04 | FAPA Device Fixing | 100 | 0 |  | 2028-04-06 |  | 2028-04-14
47935 |  | Not Ready |  | 2028-03-28 | 2028-04-04 | FAPA Device Fixing | 100 | 0 |  | 2028-04-06 |  | 2028-04-14
47935 |  | Not Ready |  | 2028-03-28 | 2028-04-04 | FAPA Device Fixing | 100 | 0 |  | 2028-04-06 |  | 2028-04-14
47935 |  | Not Ready |  | 2028-03-28 | 2028-04-04 | FAPA Device Fixing | 100 | 0 |  | 2028-04-06 |  | 2028-04-14
47939 |  | Not Committed |  | 2028-03-28 | 2028-05-09 | P4 to P5 | 100 | 0 |  | 2028-04-06 |  | 2028-05-20
47939 |  | Not Committed |  | 2028-03-28 | 2028-05-09 | P4 to P5 | 100 | 0 |  | 2028-04-06 |  | 2028-05-20
47939 |  | Not Committed |  | 2028-03-28 | 2028-05-09 | P4 to P5 | 100 | 0 |  | 2028-04-06 |  | 2028-05-20
47940 |  | Not Ready |  | 2028-03-28 | 2028-04-04 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2028-04-06 |  | 2028-04-14 |  |  |  |  | MEP | FPS final fixes
47940 |  | Not Ready |  | 2028-03-28 | 2028-04-04 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2028-04-06 |  | 2028-04-14 |  |  |  |  | MEP | FPS final fixes
46603 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2028-01-29 | 2028-02-05 | Staircase Fire Door Fixing | 100 | 0 |  | 2028-04-07 |  | 2028-04-15 |  | Tower B | Super Structure | L41
46644 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | Lobby Plastering - MEP & Finishes | 2028-03-07 | 2028-03-18 | Lobby Plastering | 100 | 0 |  | 2028-04-07 |  | 2028-04-19 |  | Tower B | Super Structure | L44 | Finishes | Lobby Plastering
47212 | Tower B - Super Structure - Finishes & MEP - L37 to L38 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2028-03-17 | 2028-03-22 | Painting Works | 100 | 0 |  | 2028-04-07 |  | 2028-04-13 |  | Tower B | Super Structure | L37 | Finishes | Painting Works
47515 | Tower B - Super Structure - Finishes & MEP - L25 to L35 | Not Ready | Hoist Corridor Finishes | 2028-03-07 | 2028-06-22 | L25-35 | 100 | 0 |  | 2028-04-07 |  | 2028-07-24 |  | Tower B | Super Structure | L25
47515 | Tower B - Super Structure - Finishes & MEP - L25 to L35 | Not Ready | Hoist Corridor Finishes | 2028-03-07 | 2028-06-22 | L25-35 | 100 | 0 |  | 2028-04-07 |  | 2028-07-24 |  | Tower B | Super Structure | L25
47529 |  | Not Ready |  | 2028-02-28 | 2028-03-09 | Pump Room Fire Mode Commissioning | 100 | 0 |  | 2028-04-07 |  | 2028-04-13
46630 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2028-01-31 | 2028-02-12 | False Ceiling | 100 | 0 |  | 2028-04-08 |  | 2028-04-22 |  | Tower B | Super Structure | L43 | Finishes | False Ceiling
47914 |  | Not Ready |  | 2028-03-31 | 2028-04-05 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2028-04-10 |  | 2028-04-15
47914 |  | Not Ready |  | 2028-03-31 | 2028-04-05 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2028-04-10 |  | 2028-04-15
47914 |  | Not Ready |  | 2028-03-31 | 2028-04-05 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2028-04-10 |  | 2028-04-15
47948 |  | Not Ready |  | 2028-03-31 | 2028-05-24 | Softscape Works | 100 | 0 |  | 2028-04-10 |  | 2028-06-03
46615 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2028-02-02 | 2028-02-09 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2028-04-11 |  | 2028-04-19 |  | Tower B | Super Structure | L42 | MEP | FPS 2nd Fix - MEP & Finishes
46616 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2028-02-02 | 2028-02-09 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2028-04-11 |  | 2028-04-19 |  | Tower B | Super Structure | L42 | MEP | Electrical 2nd Fix - MEP & Finishes
46617 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2028-02-02 | 2028-02-12 | FAPA Device Fixing | 100 | 0 |  | 2028-04-11 |  | 2028-04-22 |  | Tower B | Super Structure | L42
46617 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2028-02-02 | 2028-02-12 | FAPA Device Fixing | 100 | 0 |  | 2028-04-11 |  | 2028-04-22 |  | Tower B | Super Structure | L42
46617 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2028-02-02 | 2028-02-12 | FAPA Device Fixing | 100 | 0 |  | 2028-04-11 |  | 2028-04-22 |  | Tower B | Super Structure | L42
46617 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2028-02-02 | 2028-02-12 | FAPA Device Fixing | 100 | 0 |  | 2028-04-11 |  | 2028-04-22 |  | Tower B | Super Structure | L42
46618 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2028-02-02 | 2028-02-09 | HVAC Grill Fixing | 100 | 0 |  | 2028-04-11 |  | 2028-04-19 |  | Tower B | Super Structure | L42 | MEP | HVAC Grill Fixing
47378 | Tower B - Super Structure - Finishes & MEP - L35 to Terrace | Not Ready | Staircase Finishes - MEP & Finishes | 2028-05-25 | 2028-06-28 | Staircase Window | 100 | 0 |  | 2028-04-11 |  | 2028-05-18 |  | Tower B | Super Structure | L35
47380 | Tower B - Super Structure - Finishes & MEP - L35 to Terrace | Not Ready | Staircase Finishes - MEP & Finishes | 2028-05-25 | 2028-06-10 | Staircase cabling | 100 | 0 |  | 2028-04-11 |  | 2028-04-28 |  | Tower B | Super Structure | L35
47483 | Tower B - Super Structure - Finishes & MEP - L35 to Terrace | Not Ready |  | 2028-03-10 | 2028-03-28 | Glass Assembly Installation | 100 | 0 |  | 2028-04-11 |  | 2028-04-28 |  | Tower B | Super Structure | L35
47484 | Tower B - Super Structure - Finishes & MEP - L35 to Terrace | Not Ready |  | 2028-03-10 | 2028-03-22 | ACP Sheet & Insulation fixing | 100 | 0 |  | 2028-04-11 |  | 2028-04-22 |  | Tower B | Super Structure | L35
47485 | Tower B - Super Structure - Finishes & MEP - L35 to Terrace | Not Ready |  | 2028-03-10 | 2028-03-18 | Fixing of Louvers | 100 | 0 |  | 2028-04-11 |  | 2028-04-19 |  | Tower B | Super Structure | L35 | Façade | Façade Works
47485 | Tower B - Super Structure - Finishes & MEP - L35 to Terrace | Not Ready |  | 2028-03-10 | 2028-03-18 | Fixing of Louvers | 100 | 0 |  | 2028-04-11 |  | 2028-04-19 |  | Tower B | Super Structure | L35
47508 | Tower B - Super Structure - Finishes & MEP - L35 to Terrace | Not Ready |  | 2028-03-10 | 2028-03-28 | Glass Assembly Installation | 100 | 0 |  | 2028-04-11 |  | 2028-04-28 |  | Tower B | Super Structure | L35
47509 | Tower B - Super Structure - Finishes & MEP - L35 to Terrace | Not Ready |  | 2028-03-10 | 2028-03-22 | ACP Sheet & Insulation fixing | 100 | 0 |  | 2028-04-11 |  | 2028-04-22 |  | Tower B | Super Structure | L35
47510 | Tower B - Super Structure - Finishes & MEP - L35 to Terrace | Not Ready |  | 2028-03-10 | 2028-03-18 | Fixing of Louvers | 100 | 0 |  | 2028-04-11 |  | 2028-04-19 |  | Tower B | Super Structure | L35 | Façade | Façade Works
47510 | Tower B - Super Structure - Finishes & MEP - L35 to Terrace | Not Ready |  | 2028-03-10 | 2028-03-18 | Fixing of Louvers | 100 | 0 |  | 2028-04-11 |  | 2028-04-19 |  | Tower B | Super Structure | L35
46589 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2028-02-03 | 2028-02-10 | Final Painting | 100 | 0 |  | 2028-04-12 |  | 2028-04-20 |  | Tower B | Super Structure | L40 | Finishes | Final Painting
46589 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2028-02-03 | 2028-02-10 | Final Painting | 100 | 0 |  | 2028-04-12 |  | 2028-04-20 |  | Tower B | Super Structure | L40 | Finishes | Final Painting
46589 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2028-02-03 | 2028-02-10 | Final Painting | 100 | 0 |  | 2028-04-12 |  | 2028-04-20 |  | Tower B | Super Structure | L40 | Finishes | Final Painting
47458 | Tower B | Not Ready | BMU Installation | 2028-02-28 | 2028-06-14 | BMU Installation | 100 | 0 |  | 2028-04-13 |  | 2028-07-29 |  | Tower B | --
47458 | Tower B | Not Ready | BMU Installation | 2028-02-28 | 2028-06-14 | BMU Installation | 100 | 0 |  | 2028-04-13 |  | 2028-07-29 |  | Tower B | --
47821 |  | Not Ready |  | 2027-10-12 | 2027-12-03 | P4 to P5 | 100 | 0 |  | 2028-04-14 |  | 2028-06-08
47821 |  | Not Ready |  | 2027-10-12 | 2027-12-03 | P4 to P5 | 100 | 0 |  | 2028-04-14 |  | 2028-06-08
47821 |  | Not Ready |  | 2027-10-12 | 2027-12-03 | P4 to P5 | 100 | 0 |  | 2028-04-14 |  | 2028-06-08
47851 |  | Not Committed |  | 2027-10-12 | 2028-01-27 | P3 to P4 | 100 | 0 |  | 2028-04-14 |  | 2028-07-31
47851 |  | Not Committed |  | 2027-10-12 | 2028-01-27 | P3 to P4 | 100 | 0 |  | 2028-04-14 |  | 2028-07-31
47851 |  | Not Committed |  | 2027-10-12 | 2028-01-27 | P3 to P4 | 100 | 0 |  | 2028-04-14 |  | 2028-07-31
47852 |  | Not Ready |  | 2027-10-12 | 2027-11-16 | VDF Flooring/ IPS in MEP & CH Kitchen | 100 | 0 |  | 2028-04-14 |  | 2028-05-22
47931 |  | Not Ready |  | 2028-04-05 | 2028-04-15 | Final Painting | 100 | 0 |  | 2028-04-14 |  | 2028-04-26 |  |  |  |  | Finishes | Final Painting
47931 |  | Not Ready |  | 2028-04-05 | 2028-04-15 | Final Painting | 100 | 0 |  | 2028-04-14 |  | 2028-04-26 |  |  |  |  | Finishes | Final Painting
47931 |  | Not Ready |  | 2028-04-05 | 2028-04-15 | Final Painting | 100 | 0 |  | 2028-04-14 |  | 2028-04-26 |  |  |  |  | Finishes | Final Painting
47936 |  | Not Ready |  | 2028-04-05 | 2028-04-12 | HVAC Fans fixing | 100 | 0 |  | 2028-04-14 |  | 2028-04-22 |  |  |  |  | MEP | HVAC Grill Fixing
47936 |  | Not Ready |  | 2028-04-05 | 2028-04-12 | HVAC Fans fixing | 100 | 0 |  | 2028-04-14 |  | 2028-04-22 |  |  |  |  | MEP | HVAC Grill Fixing
47941 |  | Not Ready |  | 2028-04-05 | 2028-04-12 | FAPA Device Fixing | 100 | 0 |  | 2028-04-14 |  | 2028-04-22
47941 |  | Not Ready |  | 2028-04-05 | 2028-04-12 | FAPA Device Fixing | 100 | 0 |  | 2028-04-14 |  | 2028-04-22
47941 |  | Not Ready |  | 2028-04-05 | 2028-04-12 | FAPA Device Fixing | 100 | 0 |  | 2028-04-14 |  | 2028-04-22
47941 |  | Not Ready |  | 2028-04-05 | 2028-04-12 | FAPA Device Fixing | 100 | 0 |  | 2028-04-14 |  | 2028-04-22
46604 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2028-02-07 | 2028-02-14 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2028-04-15 |  | 2028-04-24 |  | Tower B | Super Structure | L41 | MEP | Electrical
47227 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2028-03-25 | 2028-04-01 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2028-04-15 |  | 2028-04-24 |  | Tower B | Super Structure | L38 | MEP | FPS 2nd Fix - MEP & Finishes
47228 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2028-03-25 | 2028-04-01 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2028-04-15 |  | 2028-04-24 |  | Tower B | Super Structure | L38 | MEP | Electrical 2nd Fix - MEP & Finishes
47229 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2028-03-25 | 2028-03-30 | PHE Final Fixes | 100 | 0 |  | 2028-04-15 |  | 2028-04-21 |  | Tower B | Super Structure | L38
47243 |  | Not Committed |  | 2028-03-25 | 2028-04-15 | MEP final fix & Finishes | 100 | 0 |  | 2028-04-15 |  | 2028-05-09
47244 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2028-03-25 | 2028-04-07 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2028-04-15 |  | 2028-04-29 |  | Tower B | Super Structure | L39 | Finishes | Door & Window Fixing
47926 |  | Not Ready |  | 2028-04-08 | 2028-04-13 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2028-04-18 |  | 2028-04-24
47926 |  | Not Ready |  | 2028-04-08 | 2028-04-13 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2028-04-18 |  | 2028-04-24
47926 |  | Not Ready |  | 2028-04-08 | 2028-04-13 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2028-04-18 |  | 2028-04-24
46619 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2028-02-10 | 2028-02-17 | Staircase Fire Door Fixing | 100 | 0 |  | 2028-04-19 |  | 2028-04-27 |  | Tower B | Super Structure | L42
45700 | Tower B - Super Structure - Finishes & MEP - Sub Station | Not Ready | Sub Station - High Side Services | 2028-01-31 | 2028-02-16 | Cable support bracket work at Trench | 100 | 0 |  | 2028-04-20 |  | 2028-05-09 |  | Tower B | Super Structure
46646 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | False Ceiling - MEP & Finishes | 2028-02-11 | 2028-02-24 | False Ceiling | 100 | 0 |  | 2028-04-20 |  | 2028-05-05 |  | Tower B | Super Structure | L44 | Finishes | False Ceiling
47230 | Tower B - Super Structure - Finishes & MEP - L38 to L39 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2028-03-31 | 2028-04-05 | Painting Works | 100 | 0 |  | 2028-04-21 |  | 2028-04-27 |  | Tower B | Super Structure | L38 | Finishes | Painting Works
47247 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2028-03-31 | 2028-04-05 | PHE Final Fixes | 100 | 0 |  | 2028-04-21 |  | 2028-04-27 |  | Tower B | Super Structure | L39
46631 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2028-02-14 | 2028-02-21 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2028-04-22 |  | 2028-05-02 |  | Tower B | Super Structure | L43 | MEP | FPS 2nd Fix - MEP & Finishes
46632 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2028-02-14 | 2028-02-21 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2028-04-22 |  | 2028-05-02 |  | Tower B | Super Structure | L43 | MEP | Electrical 2nd Fix - MEP & Finishes
46633 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2028-02-14 | 2028-02-24 | FAPA Device Fixing | 100 | 0 |  | 2028-04-22 |  | 2028-05-05 |  | Tower B | Super Structure | L43
46633 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2028-02-14 | 2028-02-24 | FAPA Device Fixing | 100 | 0 |  | 2028-04-22 |  | 2028-05-05 |  | Tower B | Super Structure | L43
46633 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2028-02-14 | 2028-02-24 | FAPA Device Fixing | 100 | 0 |  | 2028-04-22 |  | 2028-05-05 |  | Tower B | Super Structure | L43
46633 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2028-02-14 | 2028-02-24 | FAPA Device Fixing | 100 | 0 |  | 2028-04-22 |  | 2028-05-05 |  | Tower B | Super Structure | L43
46634 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2028-02-14 | 2028-02-21 | HVAC Grill Fixing | 100 | 0 |  | 2028-04-22 |  | 2028-05-02 |  | Tower B | Super Structure | L43 | MEP | HVAC Grill Fixing
47864 |  | Not Ready |  | 2028-08-19 | 2028-09-05 | Handrail lighting work | 100 | 0 |  | 2028-04-22 |  | 2028-05-11
47937 |  | Not Ready |  | 2028-04-13 | 2028-04-24 | Final Painting | 100 | 0 |  | 2028-04-22 |  | 2028-05-05 |  |  |  |  | Finishes | Final Painting
47937 |  | Not Ready |  | 2028-04-13 | 2028-04-24 | Final Painting | 100 | 0 |  | 2028-04-22 |  | 2028-05-05 |  |  |  |  | Finishes | Final Painting
47937 |  | Not Ready |  | 2028-04-13 | 2028-04-24 | Final Painting | 100 | 0 |  | 2028-04-22 |  | 2028-05-05 |  |  |  |  | Finishes | Final Painting
47942 |  | Not Ready |  | 2028-04-13 | 2028-04-20 | HVAC Fans fixing | 100 | 0 |  | 2028-04-22 |  | 2028-05-02 |  |  |  |  | MEP | HVAC Grill Fixing
47942 |  | Not Ready |  | 2028-04-13 | 2028-04-20 | HVAC Fans fixing | 100 | 0 |  | 2028-04-22 |  | 2028-05-02 |  |  |  |  | MEP | HVAC Grill Fixing
46605 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2028-02-15 | 2028-02-22 | Final Painting | 100 | 0 |  | 2028-04-24 |  | 2028-05-03 |  | Tower B | Super Structure | L41 | Finishes | Final Painting
46605 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2028-02-15 | 2028-02-22 | Final Painting | 100 | 0 |  | 2028-04-24 |  | 2028-05-03 |  | Tower B | Super Structure | L41 | Finishes | Final Painting
46605 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2028-02-15 | 2028-02-22 | Final Painting | 100 | 0 |  | 2028-04-24 |  | 2028-05-03 |  | Tower B | Super Structure | L41 | Finishes | Final Painting
47932 |  | Not Ready |  | 2028-04-17 | 2028-04-21 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2028-04-26 |  | 2028-05-03
47932 |  | Not Ready |  | 2028-04-17 | 2028-04-21 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2028-04-26 |  | 2028-05-03
47932 |  | Not Ready |  | 2028-04-17 | 2028-04-21 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2028-04-26 |  | 2028-05-03
46620 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2028-02-18 | 2028-02-25 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2028-04-27 |  | 2028-05-06 |  | Tower B | Super Structure | L42 | MEP | Electrical
47248 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2028-04-06 | 2028-04-11 | Painting Works | 100 | 0 |  | 2028-04-27 |  | 2028-05-04 |  | Tower B | Super Structure | L39 | Finishes | Painting Works
47346 | Tower B - Super Structure - Finishes & MEP - B3 to GF | Not Ready | Staircase Finishes - MEP & Finishes | 2028-06-12 | 2028-06-28 | Staircase Light Fixtures & Devices fixing | 100 | 0 |  | 2028-04-28 |  | 2028-05-18 |  | Tower B | Super Structure | B3
47374 | Tower B - Super Structure - Finishes & MEP - L25 to L35 | Not Ready | Staircase Finishes - MEP & Finishes | 2028-06-12 | 2028-06-28 | Staircase Light Fixtures & Devices fixing | 100 | 0 |  | 2028-04-28 |  | 2028-05-18 |  | Tower B | Super Structure | L25
47486 | Tower B - Super Structure - Finishes & MEP - L35 to Terrace | Not Ready |  | 2028-03-29 | 2028-04-05 | Accessories & Alignment | 100 | 0 |  | 2028-04-28 |  | 2028-05-08 |  | Tower B | Super Structure | L35 | Façade | Façade Works
47486 | Tower B - Super Structure - Finishes & MEP - L35 to Terrace | Not Ready |  | 2028-03-29 | 2028-04-05 | Accessories & Alignment | 100 | 0 |  | 2028-04-28 |  | 2028-05-08 |  | Tower B | Super Structure | L35
47511 | Tower B - Super Structure - Finishes & MEP - L35 to Terrace | Not Ready |  | 2028-03-29 | 2028-04-05 | Accessories & Alignment | 100 | 0 |  | 2028-04-28 |  | 2028-05-08 |  | Tower B | Super Structure | L35 | Façade | Façade Works
47511 | Tower B - Super Structure - Finishes & MEP - L35 to Terrace | Not Ready |  | 2028-03-29 | 2028-04-05 | Accessories & Alignment | 100 | 0 |  | 2028-04-28 |  | 2028-05-08 |  | Tower B | Super Structure | L35
47245 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2028-04-08 | 2028-04-15 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2028-04-29 |  | 2028-05-09 |  | Tower B | Super Structure | L39 | MEP | FPS 2nd Fix - MEP & Finishes
47246 | Tower B - Super Structure - Finishes & MEP - L39 to L40 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2028-04-08 | 2028-04-15 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2028-04-29 |  | 2028-05-09 |  | Tower B | Super Structure | L39 | MEP | Electrical 2nd Fix - MEP & Finishes
47261 |  | Not Committed |  | 2028-04-08 | 2028-05-12 | MEP final fix & Finishes | 100 | 0 |  | 2028-04-29 |  | 2028-06-05
47262 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2028-04-08 | 2028-04-21 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2028-04-29 |  | 2028-05-15 |  | Tower B | Super Structure | L40 | Finishes | Door & Window Fixing
46635 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2028-02-22 | 2028-02-29 | Staircase Fire Door Fixing | 100 | 0 |  | 2028-05-02 |  | 2028-05-10 |  | Tower B | Super Structure | L43
47943 |  | Not Ready |  | 2028-04-21 | 2028-05-03 | Final Painting | 100 | 0 |  | 2028-05-02 |  | 2028-05-13 |  |  |  |  | Finishes | Final Painting
47943 |  | Not Ready |  | 2028-04-21 | 2028-05-03 | Final Painting | 100 | 0 |  | 2028-05-02 |  | 2028-05-13 |  |  |  |  | Finishes | Final Painting
47943 |  | Not Ready |  | 2028-04-21 | 2028-05-03 | Final Painting | 100 | 0 |  | 2028-05-02 |  | 2028-05-13 |  |  |  |  | Finishes | Final Painting
47850 |  | Not Ready |  | 2027-10-30 | 2027-12-03 | Staircase Finishes | 100 | 0 |  | 2028-05-03 |  | 2028-06-08
47850 |  | Not Ready |  | 2027-10-30 | 2027-12-03 | Staircase Finishes | 100 | 0 |  | 2028-05-03 |  | 2028-06-08
46647 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2028-02-25 | 2028-03-03 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2028-05-05 |  | 2028-05-13 |  | Tower B | Super Structure | L44 | MEP | FPS 2nd Fix - MEP & Finishes
46648 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2028-02-25 | 2028-03-03 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2028-05-05 |  | 2028-05-13 |  | Tower B | Super Structure | L44 | MEP | Electrical 2nd Fix - MEP & Finishes
46649 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2028-02-25 | 2028-03-07 | FAPA Device Fixing | 100 | 0 |  | 2028-05-05 |  | 2028-05-18 |  | Tower B | Super Structure | L44
46649 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2028-02-25 | 2028-03-07 | FAPA Device Fixing | 100 | 0 |  | 2028-05-05 |  | 2028-05-18 |  | Tower B | Super Structure | L44
46649 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2028-02-25 | 2028-03-07 | FAPA Device Fixing | 100 | 0 |  | 2028-05-05 |  | 2028-05-18 |  | Tower B | Super Structure | L44
46649 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | FAPA Device Fixing - MEP & Finishes | 2028-02-25 | 2028-03-07 | FAPA Device Fixing | 100 | 0 |  | 2028-05-05 |  | 2028-05-18 |  | Tower B | Super Structure | L44
46650 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | HVAC Grill Fixing - MEP & Finishes | 2028-02-25 | 2028-03-03 | HVAC Grill Fixing | 100 | 0 |  | 2028-05-05 |  | 2028-05-13 |  | Tower B | Super Structure | L44 | MEP | HVAC Grill Fixing
47938 |  | Not Ready |  | 2028-04-25 | 2028-04-29 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2028-05-05 |  | 2028-05-11
47938 |  | Not Ready |  | 2028-04-25 | 2028-04-29 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2028-05-05 |  | 2028-05-11
47938 |  | Not Ready |  | 2028-04-25 | 2028-04-29 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2028-05-05 |  | 2028-05-11
46621 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2028-02-26 | 2028-03-04 | Final Painting | 100 | 0 |  | 2028-05-06 |  | 2028-05-15 |  | Tower B | Super Structure | L42 | Finishes | Final Painting
46621 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2028-02-26 | 2028-03-04 | Final Painting | 100 | 0 |  | 2028-05-06 |  | 2028-05-15 |  | Tower B | Super Structure | L42 | Finishes | Final Painting
46621 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2028-02-26 | 2028-03-04 | Final Painting | 100 | 0 |  | 2028-05-06 |  | 2028-05-15 |  | Tower B | Super Structure | L42 | Finishes | Final Painting
47516 | Tower B - Super Structure - Finishes & MEP - L35 to Terrace | Not Ready | Hoist Corridor Finishes | 2028-04-06 | 2028-07-21 | L35-Terrace | 100 | 0 |  | 2028-05-08 |  | 2028-08-22 |  | Tower B | Super Structure | L35
47516 | Tower B - Super Structure - Finishes & MEP - L35 to Terrace | Not Ready | Hoist Corridor Finishes | 2028-04-06 | 2028-07-21 | L35-Terrace | 100 | 0 |  | 2028-05-08 |  | 2028-08-22 |  | Tower B | Super Structure | L35
45701 | Tower B - Super Structure - Finishes & MEP - Sub Station | Not Ready | Sub Station - High Side Services | 2028-02-17 | 2028-03-17 | Cable Tray Fixing | 100 | 0 |  | 2028-05-09 |  | 2028-05-27 |  | Tower B | Super Structure
46636 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2028-03-01 | 2028-03-08 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2028-05-10 |  | 2028-05-19 |  | Tower B | Super Structure | L43 | MEP | Electrical
47865 |  | Not Ready |  | 2028-09-06 | 2028-09-28 | Planter works | 100 | 0 |  | 2028-05-11 |  | 2028-06-05
47865 |  | Not Ready |  | 2028-09-06 | 2028-09-28 | Planter works | 100 | 0 |  | 2028-05-11 |  | 2028-06-05
46651 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | Straircase Fire Door Fixing - MEP & Finishes | 2028-03-04 | 2028-03-13 | Staircase Fire Door Fixing | 100 | 0 |  | 2028-05-13 |  | 2028-05-23 |  | Tower B | Super Structure | L44
47944 |  | Not Ready |  | 2028-05-04 | 2028-05-09 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2028-05-13 |  | 2028-05-20
47944 |  | Not Ready |  | 2028-05-04 | 2028-05-09 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2028-05-13 |  | 2028-05-20
47944 |  | Not Ready |  | 2028-05-04 | 2028-05-09 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2028-05-13 |  | 2028-05-20
47263 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2028-04-22 | 2028-04-29 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2028-05-15 |  | 2028-05-24 |  | Tower B | Super Structure | L40 | MEP | FPS 2nd Fix - MEP & Finishes
47264 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2028-04-22 | 2028-04-29 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2028-05-15 |  | 2028-05-24 |  | Tower B | Super Structure | L40 | MEP | Electrical 2nd Fix - MEP & Finishes
47279 |  | Not Committed |  | 2028-04-22 | 2028-05-27 | MEP final fix & Finishes | 100 | 0 |  | 2028-05-15 |  | 2028-06-19
47280 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2028-04-22 | 2028-05-06 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2028-05-15 |  | 2028-05-30 |  | Tower B | Super Structure | L41 | Finishes | Door & Window Fixing
47379 | Tower B - Super Structure - Finishes & MEP - L35 to Terrace | Not Ready | Staircase Finishes - MEP & Finishes | 2028-06-29 | 2028-08-02 | Staircase Railing | 100 | 0 |  | 2028-05-18 |  | 2028-06-22 |  | Tower B | Super Structure | L35
46637 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2028-03-09 | 2028-03-17 | Final Painting | 100 | 0 |  | 2028-05-19 |  | 2028-05-27 |  | Tower B | Super Structure | L43 | Finishes | Final Painting
46637 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2028-03-09 | 2028-03-17 | Final Painting | 100 | 0 |  | 2028-05-19 |  | 2028-05-27 |  | Tower B | Super Structure | L43 | Finishes | Final Painting
46637 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2028-03-09 | 2028-03-17 | Final Painting | 100 | 0 |  | 2028-05-19 |  | 2028-05-27 |  | Tower B | Super Structure | L43 | Finishes | Final Painting
47915 |  | Not Committed |  | 2028-05-10 | 2028-06-21 | GF to P1 | 100 | 0 |  | 2028-05-20 |  | 2028-07-01
47915 |  | Not Committed |  | 2028-05-10 | 2028-06-21 | GF to P1 | 100 | 0 |  | 2028-05-20 |  | 2028-07-01
47915 |  | Not Committed |  | 2028-05-10 | 2028-06-21 | GF to P1 | 100 | 0 |  | 2028-05-20 |  | 2028-07-01
47916 |  | Not Ready |  | 2028-05-10 | 2028-05-18 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2028-05-20 |  | 2028-05-29 |  |  |  |  | MEP | FPS final fixes
47916 |  | Not Ready |  | 2028-05-10 | 2028-05-18 | FPS final fixes (sprinklers & smoke detectors) | 100 | 0 |  | 2028-05-20 |  | 2028-05-29 |  |  |  |  | MEP | FPS final fixes
47853 |  | Not Ready |  | 2027-11-17 | 2027-12-21 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2028-05-22 |  | 2028-06-26
47853 |  | Not Ready |  | 2027-11-17 | 2027-12-21 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2028-05-22 |  | 2028-06-26
46652 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | Shaft Doors Fixing - MEP & Finishes | 2028-03-14 | 2028-03-21 | Shaft Doors Fixing (Electrical, ELV) | 100 | 0 |  | 2028-05-23 |  | 2028-05-31 |  | Tower B | Super Structure | L44 | MEP | Electrical
47265 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2028-05-02 | 2028-05-06 | PHE Final Fixes | 100 | 0 |  | 2028-05-24 |  | 2028-05-30 |  | Tower B | Super Structure | L40
45702 | Tower B - Super Structure - Finishes & MEP - Sub Station | Not Ready | Sub Station - High Side Services | 2028-03-18 | 2028-05-10 | Cable Laying & Termination | 100 | 0 |  | 2028-05-27 |  | 2028-06-20 |  | Tower B | Super Structure
45717 | Tower B - Super Structure - Finishes & MEP - DG Sets | Not Ready |  | 2028-05-05 | 2028-06-27 | Testing & Commissioning | 100 | 0 |  | 2028-05-27 |  | 2028-07-19 |  | Tower B | Super Structure
45717 | Tower B - Super Structure - Finishes & MEP - DG Sets | Not Ready |  | 2028-05-05 | 2028-06-27 | Testing & Commissioning | 100 | 0 |  | 2028-05-27 |  | 2028-07-19 |  | Tower B | Super Structure
47917 |  | Not Ready |  | 2028-05-19 | 2028-05-26 | FAPA Device Fixing | 100 | 0 |  | 2028-05-29 |  | 2028-06-06
47917 |  | Not Ready |  | 2028-05-19 | 2028-05-26 | FAPA Device Fixing | 100 | 0 |  | 2028-05-29 |  | 2028-06-06
47917 |  | Not Ready |  | 2028-05-19 | 2028-05-26 | FAPA Device Fixing | 100 | 0 |  | 2028-05-29 |  | 2028-06-06
47917 |  | Not Ready |  | 2028-05-19 | 2028-05-26 | FAPA Device Fixing | 100 | 0 |  | 2028-05-29 |  | 2028-06-06
47266 | Tower B - Super Structure - Finishes & MEP - L40 to L41 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2028-05-08 | 2028-05-12 | Painting Works | 100 | 0 |  | 2028-05-30 |  | 2028-06-05 |  | Tower B | Super Structure | L40 | Finishes | Painting Works
47281 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2028-05-08 | 2028-05-15 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2028-05-30 |  | 2028-06-07 |  | Tower B | Super Structure | L41 | MEP | FPS 2nd Fix - MEP & Finishes
47282 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2028-05-08 | 2028-05-15 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2028-05-30 |  | 2028-06-07 |  | Tower B | Super Structure | L41 | MEP | Electrical 2nd Fix - MEP & Finishes
47297 |  | Not Committed |  | 2028-05-08 | 2028-06-10 | MEP final fix & Finishes | 100 | 0 |  | 2028-05-30 |  | 2028-07-03
47298 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2028-05-08 | 2028-05-22 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2028-05-30 |  | 2028-06-13 |  | Tower B | Super Structure | L42 | Finishes | Door & Window Fixing
46653 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2028-03-22 | 2028-03-29 | Final Painting | 100 | 0 |  | 2028-05-31 |  | 2028-06-08 |  | Tower B | Super Structure | L44 | Finishes | Final Painting
46653 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2028-03-22 | 2028-03-29 | Final Painting | 100 | 0 |  | 2028-05-31 |  | 2028-06-08 |  | Tower B | Super Structure | L44 | Finishes | Final Painting
46653 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Lobby/ Common Area | Not Ready | Final Painting - MEP & Finishes | 2028-03-22 | 2028-03-29 | Final Painting | 100 | 0 |  | 2028-05-31 |  | 2028-06-08 |  | Tower B | Super Structure | L44 | Finishes | Final Painting
47918 |  | Not Ready |  | 2028-05-27 | 2028-06-03 | HVAC Fans fixing | 100 | 0 |  | 2028-06-06 |  | 2028-06-14 |  |  |  |  | MEP | HVAC Grill Fixing
47918 |  | Not Ready |  | 2028-05-27 | 2028-06-03 | HVAC Fans fixing | 100 | 0 |  | 2028-06-06 |  | 2028-06-14 |  |  |  |  | MEP | HVAC Grill Fixing
47283 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2028-05-16 | 2028-05-22 | PHE Final Fixes | 100 | 0 |  | 2028-06-07 |  | 2028-06-13 |  | Tower B | Super Structure | L41
47855 |  | Not Committed |  | 2027-12-04 | 2028-03-21 | P4 to P5 | 100 | 0 |  | 2028-06-08 |  | 2028-09-21
47855 |  | Not Committed |  | 2027-12-04 | 2028-03-21 | P4 to P5 | 100 | 0 |  | 2028-06-08 |  | 2028-09-21
47855 |  | Not Committed |  | 2027-12-04 | 2028-03-21 | P4 to P5 | 100 | 0 |  | 2028-06-08 |  | 2028-09-21
47856 |  | Not Ready |  | 2027-12-04 | 2028-01-08 | VDF Flooring | 100 | 0 |  | 2028-06-08 |  | 2028-07-13
47856 |  | Not Ready |  | 2027-12-04 | 2028-01-08 | VDF Flooring | 100 | 0 |  | 2028-06-08 |  | 2028-07-13
47284 | Tower B - Super Structure - Finishes & MEP - L41 to L42 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2028-05-23 | 2028-05-27 | Painting Works | 100 | 0 |  | 2028-06-13 |  | 2028-06-19 |  | Tower B | Super Structure | L41 | Finishes | Painting Works
47299 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2028-05-23 | 2028-05-30 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2028-06-13 |  | 2028-06-21 |  | Tower B | Super Structure | L42 | MEP | FPS 2nd Fix - MEP & Finishes
47300 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2028-05-23 | 2028-05-30 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2028-06-13 |  | 2028-06-21 |  | Tower B | Super Structure | L42 | MEP | Electrical 2nd Fix - MEP & Finishes
47315 |  | Not Committed |  | 2028-05-23 | 2028-06-24 | MEP final fix & Finishes | 100 | 0 |  | 2028-06-13 |  | 2028-07-17
47316 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2028-05-23 | 2028-06-05 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2028-06-13 |  | 2028-06-27 |  | Tower B | Super Structure | L43 | Finishes | Door & Window Fixing
47919 |  | Not Ready |  | 2028-06-05 | 2028-06-15 | Final Painting | 100 | 0 |  | 2028-06-14 |  | 2028-06-26 |  |  |  |  | Finishes | Final Painting
47919 |  | Not Ready |  | 2028-06-05 | 2028-06-15 | Final Painting | 100 | 0 |  | 2028-06-14 |  | 2028-06-26 |  |  |  |  | Finishes | Final Painting
47919 |  | Not Ready |  | 2028-06-05 | 2028-06-15 | Final Painting | 100 | 0 |  | 2028-06-14 |  | 2028-06-26 |  |  |  |  | Finishes | Final Painting
47949 |  | Not Committed |  | 2028-06-05 | 2028-07-08 | Testing & Commissioning and Handover | 100 | 0 |  | 2028-06-14 |  | 2028-07-19
47950 |  | Not Ready |  | 2028-06-05 | 2028-07-08 | Integrated T&C | 100 | 0 |  | 2028-06-14 |  | 2028-07-19
45703 | Tower B - Super Structure - Finishes & MEP - Sub Station | Not Ready | Sub Station - High Side Services | 2028-05-11 | 2028-06-15 | MS Shutter Fixing & FRD Door Fixing | 100 | 0 |  | 2028-06-20 |  | 2028-07-13 |  | Tower B | Super Structure
47521 |  | Not Ready | External Development | 2028-05-11 | 2028-07-20 | Fire Tender Path | 100 | 0 |  | 2028-06-20 |  | 2028-07-25
47301 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2028-05-31 | 2028-06-05 | PHE Final Fixes | 100 | 0 |  | 2028-06-21 |  | 2028-06-27 |  | Tower B | Super Structure | L42
47381 | Tower B - Super Structure - Finishes & MEP - L35 to Terrace | Not Ready | Staircase Finishes - MEP & Finishes | 2028-08-03 | 2028-08-19 | Staircase Light Fixtures & Devices fixing | 100 | 0 |  | 2028-06-22 |  | 2028-07-10 |  | Tower B | Super Structure | L35
47854 |  | Not Ready |  | 2027-12-22 | 2028-01-27 | Staircase Finishes | 100 | 0 |  | 2028-06-26 |  | 2028-07-31
47854 |  | Not Ready |  | 2027-12-22 | 2028-01-27 | Staircase Finishes | 100 | 0 |  | 2028-06-26 |  | 2028-07-31
47920 |  | Not Ready |  | 2028-06-16 | 2028-06-21 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2028-06-26 |  | 2028-07-01
47920 |  | Not Ready |  | 2028-06-16 | 2028-06-21 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2028-06-26 |  | 2028-07-01
47920 |  | Not Ready |  | 2028-06-16 | 2028-06-21 | Parking Mirror & Signages Fixing | 100 | 0 |  | 2028-06-26 |  | 2028-07-01
47302 | Tower B - Super Structure - Finishes & MEP - L42 to L43 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2028-06-06 | 2028-06-10 | Painting Works | 100 | 0 |  | 2028-06-27 |  | 2028-07-03 |  | Tower B | Super Structure | L42 | Finishes | Painting Works
47317 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2028-06-06 | 2028-06-13 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2028-06-27 |  | 2028-07-05 |  | Tower B | Super Structure | L43 | MEP | FPS 2nd Fix - MEP & Finishes
47318 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2028-06-06 | 2028-06-13 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2028-06-27 |  | 2028-07-05 |  | Tower B | Super Structure | L43 | MEP | Electrical 2nd Fix - MEP & Finishes
47333 |  | Not Committed |  | 2028-06-06 | 2028-07-08 | MEP final fix & Finishes | 100 | 0 |  | 2028-06-27 |  | 2028-07-31
47334 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Apartment Area | Not Ready | Door & Window 2nd Fix- MEP & Finishes | 2028-06-06 | 2028-06-19 | Door & Window Fixing (with accessories) | 100 | 0 |  | 2028-06-27 |  | 2028-07-11 |  | Tower B | Super Structure | L44 | Finishes | Door & Window Fixing
47319 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2028-06-14 | 2028-06-19 | PHE Final Fixes | 100 | 0 |  | 2028-07-05 |  | 2028-07-11 |  | Tower B | Super Structure | L43
47320 | Tower B - Super Structure - Finishes & MEP - L43 to L44 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2028-06-20 | 2028-06-24 | Painting Works | 100 | 0 |  | 2028-07-11 |  | 2028-07-17 |  | Tower B | Super Structure | L43 | Finishes | Painting Works
47335 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Apartment Area | Not Ready | FPS 2nd Fix - MEP & Finishes | 2028-06-20 | 2028-06-27 | FPS 2nd Fixes (Sprinklers/ Smoke Detectors) | 100 | 0 |  | 2028-07-11 |  | 2028-07-19 |  | Tower B | Super Structure | L44 | MEP | FPS 2nd Fix - MEP & Finishes
47336 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Apartment Area | Not Ready | Electrical 2nd Fix - MEP & Finishes | 2028-06-20 | 2028-06-27 | Electrical 2nd Fixes (Switch Box, Light Fixtures) | 100 | 0 |  | 2028-07-11 |  | 2028-07-19 |  | Tower B | Super Structure | L44 | MEP | Electrical 2nd Fix - MEP & Finishes
45704 | Tower B - Super Structure - Finishes & MEP - Sub Station | Not Ready | Sub Station - High Side Services | 2028-06-16 | 2028-06-27 | Transformer Charging | 100 | 0 |  | 2028-07-13 |  | 2028-07-19 |  | Tower B | Super Structure
47857 |  | Not Ready |  | 2028-01-10 | 2028-02-14 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2028-07-13 |  | 2028-08-17
47857 |  | Not Ready |  | 2028-01-10 | 2028-02-14 | Ceiling/ Column/ Wall punning | 100 | 0 |  | 2028-07-13 |  | 2028-08-17
45705 | Tower B - Super Structure - Finishes & MEP - Sub Station | Not Ready | Sub Station - High Side Services | 2028-06-28 | 2028-07-08 | Testing & Commissioning | 100 | 0 |  | 2028-07-19 |  | 2028-07-25 |  | Tower B | Super Structure
45705 | Tower B - Super Structure - Finishes & MEP - Sub Station | Not Ready | Sub Station - High Side Services | 2028-06-28 | 2028-07-08 | Testing & Commissioning | 100 | 0 |  | 2028-07-19 |  | 2028-07-25 |  | Tower B | Super Structure
47337 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Apartment Area | Not Ready | PHE 2nd Fix - MEP & Finishes | 2028-06-28 | 2028-07-03 | PHE Final Fixes | 100 | 0 |  | 2028-07-19 |  | 2028-07-25 |  | Tower B | Super Structure | L44
47528 |  | Not Ready |  | 2028-06-28 | 2028-07-08 | DG Set License by Chief Electrical Inspector | 100 | 0 |  | 2028-07-19 |  | 2028-07-25
47531 |  | Not Ready |  | 2028-07-10 | 2028-07-20 | FAPA Integration | 100 | 0 |  | 2028-07-19 |  | 2028-07-25
45706 | Tower B - Super Structure - Finishes & MEP - Sub Station | Not Ready | Sub Station - High Side Services | 2028-07-10 | 2028-07-20 | Obtain PWD Lisence | 100 | 0 |  | 2028-07-25 |  | 2028-07-31 |  | Tower B | Super Structure
47338 | Tower B - Super Structure - Finishes & MEP - L44 to L45 - Apartment Area | Not Ready | Final Painting - MEP & Finishes | 2028-07-04 | 2028-07-08 | Painting Works | 100 | 0 |  | 2028-07-25 |  | 2028-07-31 |  | Tower B | Super Structure | L44 | Finishes | Painting Works
47527 |  | Not Ready |  | 2028-07-10 | 2028-07-20 | Sub-Station License by Chief Electrical Inspector | 100 | 0 |  | 2028-07-25 |  | 2028-07-31
47532 |  | Not Ready |  | 2028-07-21 | 2028-07-26 | CFO Visit 1 | 100 | 0 |  | 2028-07-25 |  | 2028-08-05
47533 |  | Not Ready |  | 2028-07-27 | 2028-08-01 | CFO Visit 2 | 100 | 0 |  | 2028-08-05 |  | 2028-08-17
47534 |  | Not Ready |  | 2028-08-02 | 2028-08-07 | CFO Visit 3 | 100 | 0 |  | 2028-08-17 |  | 2028-08-29
47858 |  | Not Ready |  | 2028-02-15 | 2028-03-21 | Staircase Finishes | 100 | 0 |  | 2028-08-17 |  | 2028-09-21
47858 |  | Not Ready |  | 2028-02-15 | 2028-03-21 | Staircase Finishes | 100 | 0 |  | 2028-08-17 |  | 2028-09-21
47523 |  | Not Ready | External Development | 2028-05-03 | 2028-09-20 | Softscape Works | 100 | 0 |  | 2028-08-18 |  | 2028-09-22
47523 |  | Not Ready | External Development | 2028-05-03 | 2028-09-20 | Softscape Works | 100 | 0 |  | 2028-08-18 |  | 2028-09-22
47523 |  | Not Ready | External Development | 2028-05-03 | 2028-09-20 | Softscape Works | 100 | 0 |  | 2028-08-18 |  | 2028-09-22
47524 |  | Not Ready | External Development | 2028-06-08 | 2028-09-20 | Compound Wall | 100 | 0 |  | 2028-08-18 |  | 2028-09-22
47524 |  | Not Ready | External Development | 2028-06-08 | 2028-09-20 | Compound Wall | 100 | 0 |  | 2028-08-18 |  | 2028-09-22
47525 |  | Not Ready | External Development | 2028-07-13 | 2028-09-20 | Entry/ Exit Gates | 100 | 0 |  | 2028-08-18 |  | 2028-09-22
47541 |  | Not Ready |  | 2028-04-29 | 2028-09-26 | Hand Over_Tower B_Zone 3 | 100 | 0 |  | 2028-08-18 |  | 2028-09-28
47542 |  | Not Ready |  | 2028-04-29 | 2028-09-18 | De-Snagging | 100 | 0 |  | 2028-08-18 |  | 2028-09-22
47543 |  | Not Ready |  | 2028-06-06 | 2028-09-18 | Integrated Testing & Commissioning | 100 | 0 |  | 2028-08-24 |  | 2028-09-28
47544 |  | Not Ready |  | 2028-07-19 | 2028-09-26 | Project Completion & Handover | 100 | 0 |  | 2028-08-24 |  | 2028-09-28
47535 |  | Not Ready |  | 2028-08-08 | 2028-08-08 | Fire NOC Readiness | 100 | 0 |  | 2028-08-29 |  | 2028-08-30
39118 |  | Not Committed |  | 2028-08-09 |  | TB_Fire NOC Readiness | 100 | 0 |  | 2028-08-30
47539 |  | Not Ready |  | 2028-08-09 | 2028-08-25 | OC Readiness | 100 | 0 |  | 2028-08-30 |  | 2028-09-11
39119 |  | Not Committed |  | 2028-08-28 |  | TB_Occupancy Certificate | 100 | 0 |  | 2028-09-11
47540 |  | Not Ready |  | 2028-08-26 | 2028-09-18 | Inspector Visit & Grant of OC | 100 | 0 |  | 2028-09-11 |  | 2028-09-22
39120 |  | Not Committed |  | 2028-09-27 |  | TB_Handing Over | 100 | 0 |  | 2028-09-28
29804 | Tower A | Not Ready | RCC Works - Slab |  | 2024-08-01 | On Completion of 24th Slab | 100 | 0 |  |  |  | 2024-08-01 |  | Tower A | -- |  | RCC Sub Structure | RCC Works - Slab
29805 | Tower A | Not Ready | RCC Works - Slab |  | 2025-04-01 | On Completion of 48th Slab | 100 | 0 |  |  |  | 2025-04-01 |  | Tower A | -- |  | RCC Sub Structure | RCC Works - Slab
29806 | Tower A | Not Ready | RCC Works - Slab |  | 2026-01-01 | On Completion of 65th Slab | 100 | 0 |  |  |  | 2026-01-01 |  | Tower A | -- |  | RCC Sub Structure | RCC Works - Slab
29807 | Tower A | Not Ready | RCC Works - Slab |  | 2026-07-01 | On Completion of Super Structure | 100 | 0 |  |  |  | 2026-07-01 |  | Tower A | -- |  | RCC Sub Structure | RCC Works - Slab
29808 | Tower A | Not Ready | Façade Works - MEP & Finishes |  | 2026-12-01 | On Completion of Façade | 100 | 0 |  |  |  | 2026-12-01 |  | Tower A | -- |  | Façade | Façade Works
29809 | Tower A | Not Ready | MEP fix & Finishes |  | 2027-06-01 | On Completion of MEP & Finishes | 100 | 0 |  |  |  | 2027-06-01 |  | Tower A | --
29810 | Tower A | Not Ready | RERA |  | 2028-03-01 | On Receipt of Occupation Certificate | 100 | 0 |  |  |  | 2028-03-01 |  | Tower A | --
29811 | Tower A | Not Ready | RERA |  | 2028-03-31 | RERA | 100 | 0 |  |  |  | 2028-03-31 |  | Tower A | --
29813 | Tower B | Not Ready | RCC Works - Slab |  | 2025-12-01 | On Completion of 10th Slab | 100 | 0 |  |  |  | 2025-12-01 |  | Tower B | -- |  | RCC Sub Structure | RCC Works - Slab
29814 | Tower B | Not Ready | RCC Works - Slab |  | 2026-09-01 | On Completion of 30th Slab | 100 | 0 |  |  |  | 2026-09-01 |  | Tower B | -- |  | RCC Sub Structure | RCC Works - Slab
29815 | Tower B | Not Ready | MEP fix & Finishes |  | 2028-02-01 | On Completion of Internal Plumbing | 100 | 0 |  |  |  | 2028-02-01 |  | Tower B | -- |  | MEP | Plumbing
29816 | Tower B | Not Ready | RERA |  | 2029-03-01 | On Offer of Possession | 100 | 0 |  |  |  | 2029-03-01 |  | Tower B | --
29817 | Tower B | Not Ready | RERA |  | 2029-03-31 | RERA | 100 | 0 |  |  |  | 2029-03-31 |  | Tower B | --